NEC3 Term Service Contract (TSC3)

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | The provision for Submerged Scraper Conveyor Outage scope of work execution and spares supply at Medupi Power Station for period of 60 months |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [●] |
| Part C2 | Pricing Data | [●] |
| Part C3 | Scope of Work | [●] |
| CONTRACT No. |  |  |

PART C1:	AGREEMENTS & CONTRACT DATA

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance | [●] |
| C1.2a | Contract Data provided by the Employer | [●] |
| C1.2b | Contract Data provided by the Contractor | [●] |
| C1.3 | Proforma Guarantees | [●] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for:

# The provision of Submerged Scraper Conveying Service at Medupi Power Station for period of 60 months

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the row for the Options which do not apply

| Options A | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | Sub total | R [●] |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Service Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed and signed original copy of this document, including the Schedule of Deviations (if any).

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 TSC3 Contract Data

# Part one - Data provided by the Employer

| Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | ## General |  |  |  |  |
|  | The conditions of contract are the core clauses and the clauses for main Option: |  |  |  |  |
|  |  | A: Priced contract with price list |  |  |  |
|  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |
|  | and secondary Options |  |  |  |  |
|  |  | X1: Price adjustment for inflation |  |  |  |
|  |  | X2 Changes in the law X7: Delay Damages |  |  |  |
|  |  | X17: Low service damages |  |  |  |
|  |  | X18: Limitation of liability |  |  |  |
|  |  | X19: Task Order |  |  |  |
|  |  | Z: Additional conditions of contract |  |  |  |
|  | of the NEC3 Term Service Contract April 2013 (TSC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |
| 10.1 | The Employer is (name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |
|  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |
| 10.1 | The Service Manager is (name): | TBC |  |  |  |
|  | Address | Medupi Power Station, Steenbokpan Road |  |  |  |
|  | Tel | TBC |  |  |  |
|  | e-mail | TBC |  |  |  |
| 11.2(2) | The Affected Property is | Medupi Power Station |  |  |  |
| 11.2(13) | The service is | The provision for Submerged Scraper Conveyor Outage scope of work execution and spares supply at Medupi Power Station for period of 60 months |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register | All risks will be identified prior, addressed and registered during the risk reduction meeting that will take place as agreed between the parties |  |  |  |
| 11.2(15) | The Service Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |
| 12.2 | The law of the contract is the law of | the Republic of South Africa |  |  |  |
| 13.1 | The language of this contract is | English |  |  |  |
| 13.3 | The period for reply is | 14 days |  |  |  |
| ## 2 | ## The Contractor’s main responsibilities |  |  |  |  |
| 21.1 | The Contractor submits a first plan for acceptance within | period agreed by both Parties |  |  |  |
| ## 3 | ## Time |  |  |  |  |
| 30.1 | The starting date is. | TBO |  |  |  |
| 30.1 | The service period is | 60 Months |  |  |  |
| ## 4 | ## Testing and defects |  |  |  |  |
| ## 42.2 | ## The Contractor corrects notified Defects within | ## 14 days |  |  |  |
| ## 5 | ## Payment |  |  |  |  |
| 50.1 | The assessment interval is | between the 21 days of each successive month. |  |  |  |
| 51.1 | The currency of this contract is the | South African Rand |  |  |  |
| 51.2 | The period within which payments are made is | 30 calendar days after reception of a valid tax invoice/ 60 calendar days after reception of a valid tax invoice for contract value above 50 million rand |  |  |  |
| 51.4 | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365-day year) charged by from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands |  |  |  |
| ## 6 | ## Compensation events | As per NEC3 TSC Core clause 6 |  |  |  |
| ## 7 | ## Use of Equipment Plant and Materials | ## As per NEC3 TSC Core clause 7 |  |  |  |
| ## 8 | ## Risks and insurance |  |  |  |  |
| 80.1 | These are additional Employer's risks | All risks will be identified prior and addressed and registered during the Risk Register meeting that will take place as agreed between the Parties |  |  |  |
| ## 9 | ## Termination | As per NEC3 TSC Core clause 9 |  |  |  |
| ## 10 | ## Data for main Option clause |  |  |  |  |
| A | Priced contract with price list |  |  |  |  |
| 20.5 | The Contractor prepares forecasts of the final total of the Prices for the whole of the service at intervals no longer than | Four (4) weeks. |  |  |  |
| ## 11 | ## Data for Option W1 |  |  |  |  |
| W1.1 | The Adjudicator | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |
|  | Address | 1st Floor, Maisels Chamber, 4 Protea Place, Sandton |  |  |  |
|  | Tel No. | 011 320 0600 |  |  |  |
|  | Fax No. | 011 320 0533 |  |  |  |
|  | e-mail | info@arbitration.co.za |  |  |  |
| W1.2(3) | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the Institution of Civil Engineers (London) (see www.ice-sa.org.za ) or its successor body. |  |  |  |
| W1.4(2) | The tribunal is: | arbitration |  |  |  |
| W1.4(5) | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |
|  | The place where arbitration is to be held is | South Africa |  |  |  |
|  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |
| ## 12 | ## Data for secondary Option clauses |  |  |  |  |
| X1 | Price adjustment for inflation |  |  |  |  |
| X1.1 | The base date for indices is | is the month before the month in which the enquiry closed. Rates are fixed and firm for first 12 Months after Contract Date. There after CPA escalation will apply. |  |  |  |
|  | The proportions used to calculate the Price Adjustment Factor are: | proportion | linked to index for | Index prepared by |  |
|  |  | 0. | [●] | [●] |  |
|  |  | 0. | [●] | [●] |  |
|  |  | 0. | [●] | [●] |  |
|  |  | 0. | [●] | [●] |  |
|  |  | 0. | [●] | [●] |  |
|  |  | 0.15 | non-adjustable |  |  |
|  |  | 1.00 |  |  |  |
| X2 | Changes in the law | As per NEC3 TSC Secondary Option clause X2 |  |  |  |
| X17 | Low service damages | X17 table will be discussed during monthly contract meetings. Quarterly amendments can be made after agreement between the Parties. |  |  |  |
| X17.1 | Service level table see below: |  |  |  |  |

|  | Low Service Damage Description |  |  |  |  | Value of Low Service Damages |  | Limit of Low Service Damage |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Service delaying the Outage/opportunity Outages Critical Path agreed schedule or Delaying other Contractor(s) from starting/completing their work or delaying the RTS of the unit |  |  |  |  | 2% per total value of the Task orders for the Outage per day |  | Limited to 15% of the total value of the Task Order(s) for the outage |  |  |  |
|  | - Service delays not finishing as per agreed upon project plan submitted and approved by the Service Manager |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the outage |  |  |  |
|  | - Failure to submit documents as per agreed upon Contract Document Submittal Schedule in this service agreement |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the Outage |  |  |  |
|  | - Failure to comply to hold and witness points on QCP’s |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the Outage |  |  |  |
|  | - Failure to update Daily Progress Report/program |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of Task Order Value |  |  |  |
|  | - Failure to respond to an NCR within 3 days |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the Outage |  |  |  |
|  | - Failure to resolve an NCR within 30 days |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the Outage |  |  |  |
|  | - Failure to Handover completed data books per outage within 14 days from outage completion. |  |  |  |  | 0.5% per total value of the Task Order(s) for the outage per day |  | Limited to 10% of the total value of the Task Order(s) for the outage |  |  |  |
|  | - Using Personnel which are not Qualified as per this service agreement |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | Limited to 10% of the total value of the Task Order(s) for the Outage |  |  |  |
|  | - Defect(s) is/are because of poor quality from the Contractor’s work performed as per paragraph 2.9 during outages |  |  |  |  | 0.5% per total value of the Task Order(s) for the outage per day |  | Limited to 10% of the total value of the Task Order(s) for the outage |  |  |  |
|  | - Defect(s) is/are because of poor quality from the Contractor’s work performed as per paragraph 2.9 during the Outages |  |  |  |  | 2% per total value of the Task Order(s) for the per day |  | Limited to 15% of the total value of the Task Order(s) for the outage |  |  |  |
|  | - Unavailability of crew beyond 1 days of being notified to mobilize to site. |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per day |  | 15% per total value of the Task Order(s) for the Outage |  |  |  |
|  | - Contractor sustains a First Aid or Medical Incident |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per incident |  | 0.5% per total value of the Task Order(s) for the Outage per incident |  |  |  |
|  | - Contractor sustains a Lost Time Incident |  |  |  |  | 1% per total value of the Task Order(s) for the Outage per incident |  | 1% per total value of the Task Order(s) for the Outage per incident |  |  |  |
|  | - Contractor not reporting safety incidents within the same shift to the Eskom Coordinator and Contract Service Manager |  |  |  |  | 0.5% per total value of the Task Order(s) for the Outage per incident |  | 0.5% per total value of the Task Order(s) for the Outage per incident |  |  |  |
|  | - Failure to keep the Safety File up to date and audited on a monthly basis to cater for Outages |  |  |  |  | R10 000 once-off deductive from the task order and then a further R10 000 per day until the file is audited and approved |  | R50 000 |  |  |  |
|  | - Work Stoppages due to Contractors internal HR failure |  |  |  |  | R10 000 once-off deductive from the task order and then a further R10 000 per day until the file is audited and approved |  | Limited to 10% of the total value of the Task Order(s) for the outage |  |  |  |
| X18 |  |  |  | Limitation of liability |  |  |  |  |  |  |  |
| X18.1 |  |  |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to |  |  | R0.0 (zero Rand) |  |  |  |  |
| X18.2 |  |  |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to |  |  | the amount of the deductibles relevant to the event |  |  |  |  |
| X18.3 |  |  |  | The Contractor’s liability for Defects due to his design of an item of Equipment is limited to |  |  | The greater of - the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s insurance (other than the resulting physical damage to the Employer’s property which is not excluded) plus the applicable deductibles |  |  |  |  |
| X18.4 |  |  |  | The Contractor’s total liability to the Employer, for all matters arising under or in connection with this contract, other than the excluded matters, is limited to |  |  | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design, plan and specification, - Defects due to manufacture and fabrication outside the Affected Property, - loss of or damage to property (other than the Employer’s property, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |  |  |  |  |
| X18.5 |  |  |  | The end of liability date is |  |  | 12 months after the end of the service period. |  |  |  |  |
| X19 |  |  |  | Task Order |  |  |  |  |  |  |  |
| X19.5 |  |  |  | The Contractor submits a Task Order programme to the Service Manager within |  |  | 5 days of receiving the Task Order |  |  |  |  |
| Z |  |  |  | The additional conditions of contract are |  |  | Z1 to Z14 always apply. |  |  |  |  |
| Z1 |  |  | Cession delegation and assignment |  |  |  |  |  |  |  |  |
| Z1.1 |  |  | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |  |
| Z1.2 |  |  | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |  |
| Z2 |  |  | Joint ventures |  |  |  |  |  |  |  |  |
| Z2.1 |  |  | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |  |
| Z2.2 |  |  | Unless already notified to the Employer, the persons or organisations notify the Service Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |  |
| Z2.3 |  |  | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |  |
| Z3 |  |  |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |  |
| Z3.1 |  |  |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |  |
| Z3.2 |  |  |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Service Manager within thirty days of the notification or as otherwise instructed by the Service Manager. |  |  |  |  |  |  |  |
| Z3.3 |  |  |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Service. |  |  |  |  |  |  |  |
| Z3.4 |  |  |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P4 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |  |
| Z4 |  |  | Confidentiality |  |  |  |  |  |  |  |  |
| Z4.1 |  |  | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |  |
| Z4.2 |  |  | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Service Manager. |  |  |  |  |  |  |  |  |
| Z4.3 |  |  | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |  |
| Z4.4 |  |  | The taking of images (whether photographs, video footage or otherwise) of the Affected Property or any portion thereof, in the course of Providing the Service and after the end of the service period, requires the prior written consent of the Service Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |  |
| Z4.5 |  |  | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |  |
| Z5 |  |  | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |  |
| Z5.1 |  |  | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Service Manager or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |  |
| Z6 |  |  |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |  |
| Z6.1 |  |  |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the service. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Affected Property; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of the service; and - undertakes, in and about the execution of the service, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |
| Z6.2 |  |  |  | The Contractor, in and about the execution of the service, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |
| Z7 |  |  | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |  |
| Z7.1 |  |  | Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Service Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |  |
| Z7.2 |  |  | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |  |
| Z7.3 |  |  | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |  |
| Z8 |  |  | Notifying compensation events |  |  |  |  |  |  |  |  |
| Z8.1 |  |  | Delete the last paragraph of core clause 61.3 and replace with: If the Contractor does not notify a compensation event within eight weeks of becoming aware of the event, he is not entitled to a change in the Prices. |  |  |  |  |  |  |  |  |
| Z9 |  |  | Employer’s limitation of liability |  |  |  |  |  |  |  |  |
| Z9.1 |  |  | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |  |
| Z9.2 |  |  | The Contractor’s entitlement under the indemnity in 82.1 is provided for in 60.1(12) and the Employer’s liability under the indemnity is limited to compensation as provided for in core clause 63 and X19.11 if Option X19 Task Order applies to this contract. |  |  |  |  |  |  |  |  |
| Z10 |  |  | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |  |
| Z10.1 |  |  | or had a business rescue order granted against it. |  |  |  |  |  |  |  |  |
| Z11 |  | Ethics |  |  |  |  |  |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |  |  |  |  |  |  |
| Affected Party |  |  |  |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |  |  |  |  |  |  |
| Coercive Action |  |  |  |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |
| Collusive Action |  |  |  |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |
| Committing Party |  |  |  |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees, |  |  |  |  |  |  |
| Corrupt Action |  |  |  |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |  |  |  |  |  |
| Fraudulent Action |  |  |  |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |  |  |  |  |  |
| Obstructive Action |  |  |  |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |  |  |  |  |  |
| Prohibited Action |  |  |  |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |  |  |  |  |  |  |
| Z11.1 |  | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |  |  |  |  |  |  |
| Z11.2 |  | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |  |  |  |  |  |  |  |  |
| Z11.3 |  | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |  |  |  |  |  |  |
| Z11.4 |  | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |  |  |  |  |  |  |  |  |

Z12		Insurance

Z _12_.1	Replace core clause 83 with the following:

| Insurance cover | 83 |  |
| --- | --- | --- |
|  | 83.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 83.2 | The Contractor provides the insurances stated in the Insurance Table A from the starting date until the earlier of Completion and the date of the termination certificate. INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage caused by the Contractor to the Employer’s property; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.. Loss of or damage to Plant and Materials; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.. Loss of or damage to Equipment; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.. The Contractor’s liability for loss of or damage to property (except the Employer’s property, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Service; Loss of or damage to property The replacement cost Bodily injury to or death of a person The amount required by the applicable law.. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law.. |

Z __12.2	Replace core clause 86 with the following:

| Insurance by the Employer | 86 |  |
| --- | --- | --- |
|  | 86.1 | The Employer provides the insurances stated in the Insurance Table B |
|  |  | INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z13 | Nuclear Liability |  |
| --- | --- | --- |
| Z13.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z13.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.3 | Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z13.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z14 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z14.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z14.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z14.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z14.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z14.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z14.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z14.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

C1.2 Contract Data

# Part two - Data provided by the Contractor

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 11.2(8) | The direct fee percentage is | % |
|  | The subcontracted fee percentage is | % |
| 11.2(14) | The following matters will be included in the Risk Register |  |
| 11.2(15) | The Service Information for the Contractor’s plan is in: |  |
| 21.1 | The plan identified in the Contract Data is contained in: |  |
| 24.1 | The key people are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | 2 Name: |  |
|  | Job |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  |  | CV's (and further key person's data including CVs) are in . |
| A | Priced contract with price list |  |
| 11.2(12) | The price list is in |  |
| 11.2(19) | The tendered total of the Prices is | R |

Part 2: Pricing Data

TSC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A | 2 |
| C2.2 | The price list | [●] |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Term Service Contract (TSC3) core clauses and Option A states:

| Identified and defined terms | 11 11.2 | (12) The Price List is the price list unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (17) The Price for Services Provided to Date is the total of - the Price for each lump sum item in the Price List which the Contractor has completed and - where a quantity is stated for an item in the Price List, an amount calculated by multiplying the quantity which the Contractor has completed by the rate. |
|  |  | (19) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate. |

This confirms that Option A is a priced contract where the Prices are derived from a list of items of service which can be priced as lump sums or as expected quantities of service multiplied by a rate or a mix of both.

# Function of the Price List

Clause 54.1 in Option A states: “Information in the Price List is not Service Information”.  This confirms that instructions to do work or how it is to be done are not included in the Price List but in the Service Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Service in accordance with the Service Information”. Hence the Contractor does not Provide the Service in accordance with the Price List.   The Price List is only a pricing document.

# Link to the Contractor’s plan

Clause 21.4 states “The Contractor provides information which shows how each item description on the Price List relates to the operations on each plan which he submits for acceptance”.  Hence when compiling the price list, the tendering contractor needs to develop his first clause 21.2 plan in such a way that operations shown on it can be priced in the price list  and result in a satisfactory cash flow in terms of clause 11.2(17).

# Preparing the price list

Before preparing the price list, both the Employer and tendering contractors should read the TSC3 Guidance Notes pages 14 and 15.  In an Option A contract, either Party may have entered items into the price list either as a process of offer and acceptance (tendering) or by negotiation depending on the nature of the service to be provided.  Alternatively the Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in the price list to be prepared and priced by him.

It is assumed that in preparing or finalising the price list the Contractor:

- Has taken account of the guidance given in the TSC3 Guidance Notes relevant to Option A;

- Understands the function of the Price List and how work is priced and paid for;

- Is aware of the need to link operations shown in his plan to items shown in the Price List;

- Has listed and priced items in the price list which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Service Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate item within the Prices or rates of other listed items in order to fulfil the obligation to complete the service for the tendered total of the Prices.

- Understands there is no adjustment to items priced as lump sums if the amount, or quantity, of work within that item later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the (lump sum) Prices is as a result of a compensation event.

## Format of the price list

(From the example given in an Appendix within the TSC3 Guidance Notes)

Entries in the first four columns in the price list in section C2.2 are made either by the Employer or the tendering contractor.

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tendering contractor enters the amount in the Price column only, the Unit, Expected Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for an item of work which is the rate for the work multiplied by the quantity completed, the tendering contractor enters the rate which is then multiplied by the Expected Quantity to produce the Price, which is also entered.

If the Contractor is to be paid a Price for an item proportional to the length of time for which a service is provided, a unit of time is stated in the Unit column and the expected length of time (as a quantity of the stated units of time) is stated in the Expected Quantity column.

C2.2 the price list

| Item nr | Description | Unit | Expected Quantity | Rate | Price |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices |  |
| --- | --- |

Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Service Information |  |
| C3.2 | Contractor’s Service Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

C3.1: Employer’s service Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s service Information	2

1	Description of the service	4

1.1	Executive overview	4

1.2	Employer’s requirements for the service	4

1.3	Interpretation and terminology	4

2	Management strategy and start up.	5

2.1	The Contractor’s plan for the service	5

2.2	Management meetings	5

2.3	Contractor’s management, supervision and key people	6

2.4	Provision of bonds and guarantees	6

2.5	Documentation control	6

2.6	Invoicing and payment	6

2.7	Contract change management	6

2.8	Records of Defined Cost to be kept by the Contractor	7

2.9	Insurance provided by the Employer	7

2.10	Training workshops and technology transfer	7

2.11	Design and supply of Equipment	7

2.12	Things provided at the end of the service period for the Employer’s use	7

2.12.1	Equipment	7

2.12.2	Information and other things	7

2.13	Management of work done by Task Order	8

3	Health and safety, the environment and quality assurance	9

3.1	Health and safety risk management	9

3.2	Environmental constraints and management	9

3.3	Quality assurance requirements	9

4	Procurement	10

4.1	People	10

4.1.1	Minimum requirements of people employed	10

4.1.2	BBBEE and preferencing scheme	10

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	10

4.2	Subcontracting	10

4.2.1	Preferred subcontractors	10

4.2.2	Subcontract documentation, and assessment of subcontract tenders	10

4.2.3	Limitations on subcontracting	11

4.2.4	Attendance on subcontractors	11

4.3	Plant and Materials	11

4.3.1	Specifications	11

4.3.2	Correction of defects	11

4.3.3	Contractor’s procurement of Plant and Materials	11

4.3.4	Tests and inspections before delivery	11

4.3.5	Plant & Materials provided “free issue” by the Employer	12

4.3.6	Cataloguing requirements	12

5	Working on the Affected Property	13

5.1	Employer’s site entry and security control, permits, and site regulations	13

5.2	People restrictions, hours of work, conduct and records	13

5.3	Health and safety facilities on the Affected Property	13

5.4	Environmental controls, fauna & flora	13

5.5	Cooperating with and obtaining acceptance of Others	13

5.6	Records of Contractor’s Equipment	13

5.7	Equipment provided by the Employer	14

5.8	Site services and facilities	14

5.8.1	Provided by the Employer	14

5.8.2	Provided by the Contractor	14

5.9	Control of noise, dust, water and waste	14

5.10	Hook ups to existing works	14

5.11	Tests and inspections	14

5.11.1	Description of tests and inspections	14

5.11.2	Materials facilities and samples for tests and inspections	14

6	List of drawings	15

6.1	Drawings issued by the Employer	15

# Description of the service

## Executive overview

Medupi Power Station wants to contract out the execution of the Submerged Scraper Conveyor (SSC) Plant scope of work during outages. The plant to be contracted out includes the Submerged Scraper Conveyor (SSC), discharge chute with grizzlies, dipper boxes, and the agitation, make-up, cooling, and chain washing water systems. This contract will comprise of the execution of Mechanical and Control and Instrumentation maintenance, inspection and repairs on the Philosophy outages.

Employers service information must be read, interpreted and applied in conjunction with Employers scope of work document 241-20221245.

## Employer’s requirements for the service

The SSC plays an import role in outage execution, because it has a possibility of impacting other stake holders if manager poorly and can potentially delay the return to service of unit during outage execution. There contractor is expected to comply to timelines give by the Employer and help reduce outage durations

### Applicable plant areas

Below is the list of applicable plant areas to which the works shall be applied.

Table 1: Applicable plant areas

| Plant Area | Boundaries of Plant Area |
| --- | --- |
| Submerged Scraper Conveyor | Submerged Scraper Conveyor (SSC), discharge chute with grizzlies, dipper boxes, and the agitation, make-up, cooling, and chain washing water systems |

### Outage SOW.

The Contractor will be responsible for outage work on the DHP during all outages. This includes scheduled Philosophy outages.

### Philosophy Outages

- Each unit will go out on a planned outage every 18 months as per the Medupi outage philosophy 240-92360717.

- The Contractor will be responsible to perform all required activities / tasks on planned outages as per the Outage SOW applicable to the relevant unit going on outage. This also includes CM activities that requires an outage to be able to complete the work.

- The SSC generic outage SOW document 241-20221245, indicates a typical scope of work that should be executed during every outage. This generic SOW will change as and when improvements to the maintenance strategy is required. Activities can also be added or removed following an outage scope variation process.

- The Contractor will draw up a Quality Control Plan for all activities prior to commencement of the work, for approval by the Employer. The Employer and the Contractor agrees on hold and witness points.

- The Contractor shall ensure all required tools and equipment is readily available to execute the outage work within time.

### Manpower requirements

It is expected that the Contractor will provide skilled and suitably qualified staff with relevant experience and medical fitness to fulfil services required. Such skills requirement shall include but not be limited to English proficiency, knowledge of Occupational Health and Safety Act 85 of 1993, NEC contract management, quality management, control and assurance. Skills requirements will also be part of the Technical Evaluation and once a contract is in place these requirements need to be adhered to for the appointment of staff.

The Contractor shall employ in and about the execution of the works, only such persons that are careful, competent and efficient in their specific trades and callings and the Employer shall be at liberty to object to and require the Contractor to remove from the works forthwith any person employed by the Contractor in or about the execution of the works who, in the opinion of the Employer, misconducts himself or is incompetent or negligent in the proper performance of his/her duties and such person shall not again be employed for the works without the written permission of the Employer. Proof of qualification is to be supplied on request to the Employer.

It is further expected of the management strategy to support the governmental socio-economic requirements such as prioritisation of locals during recruitment and local black economic empowerment as well as transfer of skills and operational experience.

### Plant Safety Regulations

It is compulsory for the Contractor to have at least two persons trained and authorised as Responsible Persons (RP) in terms of Plant Safety Regulations, for every outage. This training will be provided by the Employer within 3 months of contract award date. Authorization of the persons as RPs will be through the Employer authorization committee within 3 months of theoretical training and thereafter RPs will be expected to undergo re-authorization every two years.

- Eskom Medupi Gx will allow each RP to attend the training free of charge

- If the RP fails, the training on the first try it does not exempt the contractor from the compulsory requirement of have persons authorized

- Eskom Medupi Gx will not pay the contractor for the hours spent on the RP training of an incumbent that has to repeat the training.

- The expectation is that the contractor will have RP trained and authorized 6 months after the contract start date.

### Engineering services

It is envisaged that various plant modifications are planned for the continuous improvement of the Medupi SSC and as such the Contractor could be requested to supply engineering and or other technical guidance on an as and when required basis to assist in the continuous improvement of the plant design. Engineering services should be included in the price list and should include the following services:

- Design reviews of possible identified modifications.

- Commissioning.

### Additional services required

In addition to the above-mentioned Maintenance and Engineering services, the following is also required to be done by the Contractor:

- Provide advice to operating/commissioning personnel in person or telephonically if there are any abnormal conditions on the plat equipment or are operational challenges.

- Development of Quality Control Documentation where required.

- Transfer of knowledge and skills to Eskom operating maintenance and Engineering personnel on a continuous basis is a critical output.

- Review the training material for the Submerged Scraper Conveyor and provide overview training to Medupi personnel where required.

- Catalogue new spare items that are not yet on the Employers SAP system.

- Review the catalogued Spares information for the SSC spares and ensure that updates/reviews are completed and where required new items are catalogued.

### Spares Supply & Refurbishment Scope of Work

The scope of this contract shall include the supply of various types of spares used on the SSC system as and when required by the Employer.

#### Recommissioning Requirements

All Plant equipment on the SSC shall be re-commissioned as per site specific procedures after any outage execution.

    - Spares and Consumables

#### Outage Spares

The employer will be responsible to provide all spares for the replacement of plant components during outages. These spares and the minimum and maximum levels at which they are required to be kept in the stores are captured in the spares strategy for the SSC is referenced in[2]. Due to the relatively short duration of the outages and the criticality of the Units returning to service on time, the employer can however from time to time request the contractor to supply spares to ensure that the return to service dates are met. This will typically include, but not limited to, items that are not stock items in the stores. This will be done on an actual cost-plus fee basis. The contractor will only supply spares after a task order has been issued by the employer. A provision for spares will therefore be made on the contract for these purposes.

#### Outage consumables

As indicated in the notes at the end of Table 3, outage consumables like bolts, nuts, washer, gaskets and sealants for piping, valves and trough plates, and doors, should be included for in the price of the relevant activities. Cutting and welding consumables should also be included in the relevant activities, as indicated. The employer may also request the contractor to supply any other outage consumables for the SSC not included above, where required. The contractor supplies these consumables on an actual cost-plus fee basis. A fixed value will also be provided for outage consumables for the purposes of this contract.

      - Stores Reservation and booking back of components

The employer will create reservation for all components to be withdrawn from stores and the contractor will be responsible to collect these items from stores and transport to the plant for installation.

All refurbish-able components will be returned to stores by the contractor with the required paperwork for booking the ‘damaged or used’ components back into the stores. The Employer will be responsible to prepare the required documentation.

### General requirements

- All activities above include transport of the equipment from the stores to the plant, rigging in and out of the components and removal of the old components to the area designated for refurbishable items or the appropriate scrap area.

- The contactor supplies all the tools to execute the activities above.

- The contractor supplies all of the welding and cutting consumables for all cutting and welding activities and includes it in the pricing of the activities where applicable.

- The SSC is a wet scaling environment, and bolts can be difficult to remove. In most case the bolt, nuts and washers, and where applicable, pipe gaskets, on the water pipes and trough plates and doors will most probably not be re-usable, and the contractor will have to replace most of the bolts, nuts, washer, and pipe gaskets an inspection manhole cover gaskets as part of the SOW. These consumables should be included in the pricing of the activities and the contractor should ensure that these items are sources and delivered to site on time. It will also include sealants, where required. This excludes the side door rubber seals which is a stock item and will be withdrawn form stores. Only hot dipped galvanised bolts, nuts and washer will be used for pipes flanges, valves and the trough plates and doors. Black or electroplated bolts and nuts will not be accepted

- The Employer and Contractor in this scope of work shall commit towards the following:

- Continuous improvement of Medupi Power Station.

- Continuous cost reduction.

- Working together to ensure the Medupi plant availability, reliability and UCLF targets are met.

- The Contractor immediately reports all injuries as well as any threat to health or safety of which it becomes aware of on the site of the Employer.

- The contract entered into with the Contractor is non-exclusive and work included in this contract can only be performed upon receipt of a task order.

- Equipment to be used on site must comply with Medupi User Requirements Specifications (240-97020108) latest revision.

- Before any work start on site the Contractor is responsible to submit their Safety File to the Employer for review and acceptance.

- The Contractor shall carry out tasks as described in the scope of work

- The Contractor should include the price list for day-to-day work and overtimes for every outage when upon request by the Employer.

- The Contractor will provide with the tender a quality management program in accordance with ISO 9001 or equivalent which will comply with Eskom quality management system.

- The Contractor will be required to contain spillages and clean up oil/grease spillages caused by the Contractor’s personal and will be held liable for all costs involved.

- The Contractor shall, as far is reasonably possible, make use of local (Lephalale) manpower to execute the works.

- All works will be subject to anytime inspection from the Employer.

- The Contractor shall ensure that damaged plant labelling, including KKS labelling, (because of the Contractor’s works execution) are replaced within a reasonable time period.

- The Contractor shall ensure the integrity of Plant labelling and that deficiency with regards to KKS labelling is reported immediately

## Interpretation and terminology

The following abbreviations are used in this Service Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| BOM | Bill of Material |
| BU | Business Unit |
| C&I | Control and Instrumentation |
| DCF | Data Capture Form |
| DHP | Dust Handling Plant |
| ISO | International Standards Organisation |
| KKS | Kraftwerk Kennzeichen System |
| KPI | Key Performance Indicator |
| NEC | New Engineering Contract |
| OEM | Original Equipment Manufacturer |
| PER | Pressure Equipment Regulations |
| PCLF | Planned Capability Loss Factor |
| PM | Plant Maintenance |
| QCP | Quality Control Plan |
| QMP | Quality Management Programme |
| RP | Responsible Person |
| SHEQ | Safety, Health, Environment, Quality |
| SANS | South African National Standards |
| SOW | Scope of Work |
| UCF | Unit Capability Factor |
| UCLF | Unplanned Capability Loss Factor |

# Management strategy and start up.

## The Contractor’s plan for the service

The Contractor submits a programme in Primavera format (soft copy Format) & Manpower curve with a detailed skills breakdown for each outage

The programme includes:

- Fully Sequenced Activities

- Durations in hours

- Must be shift sensitive (Every activity to must be less than 12 hours)

- Predecessors

- Successor

- Total float

- No constraints (linking to be done properly)

- No resources (Remove activities that are not lick to any activities)

- No unnecessary calendars (remove calendars not assigned to activities)

- No empty lines and open ends

- Critical Path(s)

## Management strategy requirements

The management strategy of the contractor is expected to comply with the Safety, Health, Environment and Quality policies of Eskom Generation. The Contractor is also expected to support the business competitiveness, retention of critical skills and high-performance culture.

Complementary services to improve plant and labour performance shall include project management (inclusive of cost and IR management), value engineering, QCP’s and documentation control, and spares supply, where required. It is further expected of the management strategy to support the governmental socio-economic requirements such as local black economic empowerment as well as transfer of skills and operational experience.

## Outage Management meetings

Regular meetings of a general nature may be convened and chaired by the Service Manager as indicated in the table below:

Table 2: Outage Meetings

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Scope clarification meetings | From 18 months before start-date of an outage | Medupi Power Station | Site Manager, Supervisors, System Engineer, Outage coordinator and Quality Inspectors |
| Commissioning schedule meeting | 3 Months before the start of the outage | Medupi Power Station | Site Manager, Supervisors, System Engineer, Outage coordinator and Quality Inspectors |
| Stakeholder’s schedules buy-in meeting | 1 Month before the start of the outage | Medupi Power Station | Site Manager, Outage Planner, Outage Co-ordinator |
| Outage Kick-off meeting | Just before start-date of an outage | Medupi Power Station | Site Manager, Outage Co-ordinator |
| Overall Outage contract progress and feedback | Daily | Medupi Power Station | Employer, Contractor and Supervisors |
| Daily outage technical meeting | Daily | Medupi Power Station | Site Manager, System Engineer, Outage coordinator and Quality Inspectors |
| Gemba / Safety Plant Walk | Saturdays/Sundays during Outage | Medupi Power Station | Safety Officer |
| Safety meeting | Weekly during Outage | Medupi Power Station | Safety Officer |
| Assessment meetings | After completion of each task order | Medupi Power Station | Site Manager, System Engineer, Outage coordinator |
| Post-mortem meeting | After outage completion | Medupi Power Station | Site Manager, System Engineer, Outage coordinator and Quality Inspectors |

Meetings of a specialist nature may be convened as specified elsewhere in this Service Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the service.  Records of these meetings shall be submitted to the Service Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Contractor’s management, supervision and key people

- The Contractor shall provide daily project reports to the Employer’s Manager.

- The type of reports, level of detail and frequency of reporting will be mutually agreed by the Employer and the Contractor during the contract negotiations phase of this agreement. These may change from time to time on request by the Employer.

- The Contractor is to be represented at any ad-hoc meetings that may arise in order to address any progress or safety related matters.

- The Contractor shall appoint a trained Site Supervisor who shall manage all contract and technical related issues. Proof of experience and qualifications of the Contractor site Supervisor must be submitted within one week of the contract start date. Change to this key person shall be communicated in writing within one Month of such change to the Service Supervisor.

- The Contractor site Supervisor to be available after hours telephonically. Where the Contractor site Supervisor is not available due to excessive hours worked, leave or Illness a suitably qualified alternate must be made available.

- The Contractor site Supervisor must be able to communicate satisfactorily in English and have formal education as per Eskom Job description requirements. If at any time, it is found that the Contractor site Supervisor ability to either supervise the workers, practice good communication skills (verbal or written) or exercise competency is lacking, the Service Supervisor may give instruction for the removal of such person from site.

- The Contractor Quality Control Technicians shall be trained and meet all requirements as per attached Job Profile Appendix A. Proof of qualifications and experience of the Quality Control Technicians must be submitted before the contract start date.

- The Contractor shall ensure that at least 2 people are authorized as Responsible Person (RP), in terms of the Eskom Plant Safety Regulations (PSR) within 6 months of the contract start date. As authorisations are valid for two years only, the Contractor must ensure that their personnel are re-authorised before the authorisation lapses. The necessary training and evaluations will be provided by Medupi free of charge and the Contractor employees must be available to attend, when the course is scheduled.

- All key people undertaking work shall be appropriately trained, Qualified, Skilled and competent to perform such work and proof thereof must be submitted. Incidence of poor quality work and non-adherence to site regulations and procedures will prompt the Employer to request the immediate and permanent removal of such person from all site activities.

- Qualification and Qualified, are to be interpreted according to the minimum requirement as per the Occupational Health and Safety Act firstly and then Eskom’s “job profile” for positions within the Contractor’s organizational structure and be supported by Eskom’s “Recruitment and selection procedure” Unique Identifier: 32-1023.

## Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Service Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

## Documentation control

All governance documents shall be registered and controlled using approved Eskom Document Management Systems (EDMS). Governance documents or technical documents as a minimum shall comply with the following:

- The document ownership must reside within the Business domain

- Document must be unique in its purpose, content and aim.

- The document must be uniquely identified.

- Safety files to be submitted and approved before outage work commence as per client requirements, at least one month in advance for outages.

- The Contractor’s Outage safety file will be handed over to the Service Manager after each outage

- The Contractor’s Safety File will be kept up to date and audited monthly to cater for Outages. It is the Contractor’s responsibility to arrange the appointments with the Medupi Safety officers.

- All NEC standard forms should be used e.g. Task orders, Early Warnings, Defect certificates and Assessments.

- The Contractor is responsible to plan the supply of the documentation during the various project stages and to provide the documentation in accordance with the Contractor Document Submission Schedule (CDSS). A document is thus any written or pictorial information describing, defining, specifying or certifying activities, requirements, procedures or results

- The Contractor submits all documentation on a formal transmittal form to the Service Manager.

- All manuals, documents, drawings and engineering documentation shall be presented in British English in both software and hardware.

- All Communications will be filed and kept on site as it is crucial to have the correct communication structures. These communication documents are to adhere to the NEC 3 Term Service Contract communication requirements.

- Budget quotation, Schedules with manpower plan and Quality Control Plans for outage work to be submitted one week after SOW submission/SOW clarification

- Compensation for Occupational Injuries and Diseases (COID) Certificate and letter of good standing must be valid at all times and submitted to the Service Manager at each anniversary of the contract. These documents are to be submitted to the Eskom vendor database by the Contractor, before they expire.

- Two hard copies of the completed data packs submitted to the Service Manager. An Electronic copy of all reports to be provided on CD/ DVD

- Data Packs should be submitted within 60 Days after an Outage

- WPS supported by a valid WPQR/PQR shall be submitted and approved before any welding work on Eskom plant. Eskom shall reserve the right to review a WPQ, WPQR/PQR and associated weld maps prior to commencement of fabrication

## Invoicing and payment

Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Service Manager’s payment certificate.

The Contractor shall address the tax invoice to

invoiceseskomlocal@eskom.co.za

and include on each invoice the following information:

- Name and address of the Contractor and the Service Manager;

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- Description of service provided for each item invoiced based on the Price List;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

## Contract change management

Refer to NEC3 TSC Core clause 6(Compensation events), in the event any change to the Contract needs to be managed.

## Records of Defined Cost to be kept by the Contractor

The Contractor is required to keep record and submit proof of all the actuals, to be verified at the completion of the Payment Certificate and assessment, should the Service Manager’s request to do so.

## Insurance provided by the Employer

Below is information with regards to the Eskom Insurance Management Services, for in case the Contractor has any inquiry:

| Names & Surname | Contact details | e-mails address |
| --- | --- | --- |
| Mr Krishan Chaithoo | +27 11 800 4455 | ChaithK@eskom.co.za |

## Training

The Contractor shall attend safety trainings and awareness provided by the Employer as and when required basis.

All training related to the scope, shall be provided by the Contractor - e.g., working at heights, laser alignment etc.

The Contractor shall train its employees on proper understanding of the plant and on the technical aspects of executing their work.

## Design and supply of Equipment

Equipment supplied must always be in safe working order, irrespective whether the equipment is supplies by the Employer or Contractor. Regular maintenance must be done on all equipment used to execute the service required.

## Things provided by the Contractor

### Tools, Equipment and Transportation

- The Contractor shall provide all hand tools, including electrical hand tools, required to execute the outage scope of work. These tools should be readily available on site at the unit.

- The contractor will supply all their the tools including all special tools and equipment required to execute the scope of work as stated. This typically includes but is not limited to:

- Torque wrenches

- Electrical impact wrenches and impact wrench sockets

- Portable hydraulic jacks and portable hydraulic power pack

- Flogging spanners

- Portable lighting and extension cables

- Power tools such as grinders, portable welding machines and drilling machines

- Vernier callipers for measuring chain wear (600 mm and digital 200 or 300mm)

- Forklift (if requested by the Employer)

- All tools that need calibration must always have valid certificates of calibration before being utilized in the plant. These certificates must be readily available on site.

- The contractor shall supply all his own lifting equipment, i.e., web slings, chain slings, shackles, chain blocks, tirfor hoists, lever hoists, etc. This will also include tools to move the SSC into maintenance position and back to its operational position. Usually, a minimum of four 5-ton tirfors are used.

- All lifting equipment shall comply to OHS act and Driven Machinery Regulation, Compliance shall be verified by the Employers GMR2.1.

- All lifting equipment compliance documentation shall be readily available on site and will be made available to the employer on request.

- The contractor will be responsible to transport all spares from the stores to the plant using the appropriate transport equipment. This includes but is not limited to spares component like chains, flights, planetary gearboxes, stub-shafts, drive shafts, tension shafts, steel plates sheet and liners, and all small replacement components.

- The contractor will also be required to transport all refurbish-able components back to the stores. and submit the paperwork required to book these components back into the stores. The contractor will also be required to transport all scraped component and material to the appropriate disposal area on site

- The contractor will be required to make provision for a forklift when so required. The employer will instruct the contractor to mobilise the forklift, when required, by issuing a task order for the period required. When the truck is on site, it can also be used on plants other than the SSC.

- Mobile lifting equipment like cranes, telehandlers, scissor lifts, cherry pickers and forklifts will be supplied by the Employer. The contractor’s lifting equipment operators should however be authorised to operate all the employers mobile Equipment. The Contractor’s Lifting equipment operators should be authorised to operate the employer’s 90 ton and 25 tons cranes at the start of the contract and should be authorised to operate the rest of the equipment within 3 months from the site establishment.

## Management of work done by Task Order

- A quotation will be requested from the contractor before every outage

- The Contractor must respond to the task order with quotation and a programme.

- A Task Order starting with 45* series number will be issued to the Contractor before every outage

- The Contractor will be required to provide daily updates of the works as per agreed programme

- In the case of emergency repairs outside the SOW, a scope variation process needs to be followed

# Health and safety, the environment and quality assurance

## Health and safety risk management

All Contractor employees shall comply with the Medupi Maintenance Contracts User Requirement Specification, including non-use of cell phones in restricted areas, adherence to Eskom’s life-saving rules, adherence to Generation Occurrence Management Procedure, No Smoking Policy, etc.

The Contractor shall ensure:

- All employees are medically, physical, and psychologically fit to perform the Works.

- Compliance with Eskom’s SHE policy, procedures, standards, guidelines, specifications, and site regulations. Employees shall have a valid medical certificate of fitness specific to the work to be performed.

- Employees are informed of hazards identified in the risk assessment before commencement of Works. The Method Statement shall also be communicated to the employees on this work activity before commencement of Works.

- The emergency rescue plan shall also be communicated to personnel undertaking the Works.

- All safety and health related incidents around site or working areas and threats that pose a danger to one’s life or health are immediately reported.

- Sufficient health and safety information as well as resources are made available.

- All employees undergo safety induction on-site.

- All power tools will be inspected as and when required.

- Prescribed PPE for the specified Works shall be always worn. The provision of PPE shall be the responsibility of the Contractor.

- Correct site drawings are obtained and communicated to the employees undertaking the Works.

- The Contractor shall comply with the health and safety requirements contained in Act No 85: Occupational Health and Safety Act & Regulations.

- The Contractor shall be required to do safety induction prior to start any work on site.

- Before any work start on site the Contractor is responsible to submit their Safety File to the Employer for review and acceptance. The Contractor’s safety file must be approved before any work commence on site.

## Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints stated in Medupi Power Station Environmental Requirements for Contracts and Suppliers Procedure.

The Contractor shall ensure:

- Appropriate measures shall be undertaken to minimise the generation of dust from work activities.

- All environmental incidents must be reported.

- The work area is kept clean, tidy, and free of waster/rubbish. Waste shall be disposed of in designated bins

- Adherence to Water Use License (WUL 27086983) and Regulation 704 of the National Water Act (Act 36 of 1998).

- Plant and machinery shall be equipped with drip trays. Oil refills for plant and machinery shall take. Place in designated areas

## Quality assurance requirements

The Contractor shall comply to the requirements of ISO 9001 Quality Management Systems

### Quality control

- The Contractor has to ensure that all contractor’s measuring and testing equipment are calibrated in accordance with Medupi Power Station Test Equipment Calibration User Scope of Work Specification (240-94144946) at all times and proof thereof must be readily available.

- The Contractor shall utilise the Employer’s quality documentation management system and processes. The Contractor complies with the applicable quality standards and requirements relative to the required scope of service.

- All Quality References and Standards as stipulated in this document will be adhered to.

### Quality assurance

The Contractor shall provide a complete Quality Assurance plan in accordance with the requirements of ISO 9001: 2015 to the Employer for approval. This plan must ensure an integrated quality service as part of the contract. Execution of all quality related activities, including inspection and test plans compilation and execution and all quality related record keeping is part of the Contractor’s scope of work.

The Contractor shall always ensure that workmanship is of a standard that is acceptable as the best practice of the particular trade involved and as stipulated in written standards of recognised organisations or institutions of the respective trades except as exceeded or qualified by the specifications. The Employer shall determine the acceptability of workmanship.

# Procurement

## People

### Minimum requirements of people employed

The Contractor shall utilise / provide skilled and suitably qualified staff as governed by Medupi Maintenance Contracts User Specification Requirements with current experience in the following:

- Quality Management Control and Assurance as per ISO Standards.

- Staff must meet minimum requirements of Eskom job descriptions, with additional requirements specified.

- Occupational Health and Safety Act 85/19 and (SHE) Standards.

- Procedure writing.

- Familiarisation and adherence of Employer’s SHE goals and initiatives.

Note: All artisans and supervisors should be trained and authorised as Responsible Persons (RP) in terms of Plant Safety Regulations. This training will be provided by the Employer within 6 months of contract award date. Authorization of the persons as RPs will be through the Employer authorization committee within 6 months of theoretical training and thereafter RPs will be expected to undergo re-authorization every two years.

### Skills required

The maximum manpower numbers envisaged for this contract is indicated in Table  below. For the purpose of determining the total contract value these numbers will be used. It should however be noted that these are the maximum envisaged manpower number and that contract manpower numbers will be negotiated during the final contract negotiation. Task orders will be issued based on the agreed manpower numbers. Any additional manpower will only be mobilised if instructed to do so by additional task orders issued by the employer. Task orders will also be issued for the Skill, the number off and the duration of ad-hoc additional personnel required.

| No: | Skill | Dayshift | Nightshift | Total |
| --- | --- | --- | --- | --- |
| 1. | Site manager | 1 | 0 | 1 |
| 2. | Supervisor | 1 | 1 | 2 |
| 3. | Quality Controller | 1 | 0 | 1 |
| 4. | Safety Officer | 1 | 0 | 1 |
| 5. | Project Planner | 1 | 0 | 1 |
| 6. | Material Controller | 1 | 1 | 2 |
| 7. | Mechanical Fitters | 4 | 2 | 6 |
| 8. | Mechanical Rigger | 1 | 1 | 2 |
| 9. | Rigger Assistants | 2 | 1 | 3 |
| 10. | Semi-Skilled Labour | 14 | 7 | 21 |
| 11. | Boilermaker | 4 | 2 | 6 |
| 12. | Welder | 4 | 2 | 6 |
| 13. | Welding Engineer | 1 | 0 | 1 |
| Sub-Total |  | 36 | 17 | 53 |

### BBBEE and preferencing scheme

The Employer requires the Contractor to achieve a Broad Based Black Economic Empowerment Recognition Level (B-BBEE Recognition Level) of 4 (the “Required B-BBEE Recognition Level”) within six months from date of Contract Award in terms of Eskom’s Directive “Implementation of Eskom’s Black Economic Empowerment Strategy ” and Standard “Application of the Broad Based Black Economic Empowerment Codes of Good Practice within Eskom (32-1034)”.

Eskom’s policy is to maximise purchases from Black or Black Empowering Enterprises (BEE’s) whether Black Woman-owned, small or Large Black or Black empowering suppliers. The purpose is to promote entrepreneurship in black communities and give black business access to the mainstream of business opportunity.

### Social Development Localization and Industrialization (SDL&I)

The Contractor complies with and fulfils the Contractor’s obligations in respect of the SD&L requirements in accordance with and as provided for in the Contractor’s SD&L Compliance Schedule. The Contractor to provide proposed skill development target on the table below:

| Skills Type | Entry Level | Output | Tenderers Proposal |
| --- | --- | --- | --- |
| Project Planning & Scheduling | NQF Level 3 (Technical) | Advanced Primavera P6 Training 1 Year Experience |  |
| Business Admin | NQF Level 3 (Non-technical) | At least 1 Year Experience |  |

The Contractor shall keep accurate records and provide the Service Manager with reports on the Contractor’s actual delivery against the above stated SD&L criteria. The Contractor shall submit monthly/quarterly SD&L report to the Service Manager.  The SD&L report template will be provided to the Contractor by Service Manager.

The Contractor’s failure to comply with his SD&L obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract. The Contractor shall submit a bond equivalent to 2.5% of the Contract Value and shall only be released to the Contractor upon fulfilment of all SDL&I Obligations

## Subcontracting

### Preferred subcontractors

Eskom will do business with the suppliers that are prepared to sub-contract 30% of the contract value to EME or QSE’s that are at least 51% Black Owned from rural/underdeveloped/township. SDL&I 30% must include transportation of Contractors employees from home to site and back in accordance with regulations to prioritize local transport businesses. Contractors must ensure that local taxis comply with Workers Transport Permit (WTP) and local by-laws

### Subcontract documentation, and assessment of subcontract tenders

- The Contractor submits the proposed contract data for each subcontracting for acceptance to the Project Manager.

- The Contractor prepares s subcontracting document as according to the NEC Contract.

- The Contractor must inform the Project Manager when intending to subcontract some of the works from the contract scope.

- The Contractor takes note that their Subcontractors Safety Files will  be accepted by the Contractor Safety Manager before it will be handed to the SHE practitioner/Officers for verification of compliance before any work commence.  Proof of acceptance by the Contractor Safety Manager needs to be in the Safety file when handed over to SHE Practitioners for verification.

- The Contractor only employs qualified sub-contractors

### Limitations on subcontracting

A supplier awarded a contract may not subcontract more than 25% of the value of the contract

to any other entity that does not have an equal or higher B-BBEE status level of a contributor than

the supplier concerned unless the contract is subcontracted to an EME that has the capability and

ability to execute the subcontract.

## Plant and Materials

### Specifications

- The Contractor shall be required to provide tools required for fault finding, inspections, repairs, maintaining, replacing, and fitting as well as commissioning.

- Any damage caused to existing spares is repaired by the Contractor at his own cost prior to take over.

- The Contractor shall be required to provide all relevant hand tools for the trade.

### Contractor’s procurement of Plant and Materials

Replacement materials/components will be kept as the Employer’s Inventory/stock and issued as stock items when required. The Contractor must inform the Employer immediately of any constraints experienced during the procurement process of plant and materials whenever required to procure any materials.

### Plant & Materials provided “free issue” by the Employer

Both parties shall agree if there is any Plant and Material that the Contractor require to execute work. All other Plant and Materials are to be provided by the Contractor.

### Cataloguing requirements by the Contractor

The Contractor shall be responsible to Fill in the appropriate Data Capturing form (DCF) to capture the information for the changes or new spares. Updates on the cataloguing and SAP systems will be done by the Employer, but the Contractor will be responsible to drive the updates and give monthly feedback to Engineering and Maintenance on the progress made. The Format of the reporting will be agreed with the Employer.

# Working on the Affected Property

## Employer’s site entry and security control, permits, and site regulations

The Entry to site is only approved once the following minimum requirements are adhered to:

- The Contractors Safety file is to be approved by the Employer’s Safety department.

- Site-specific induction is to be done by all personnel.

- Acceptance of this tender is subject to the condition that both the contracting company’s management and its employees will provide Eskom with a clear criminal record not older than thirty (30) days from a reputable screening company. If the principal contractor appoints a subcontractor, the same provisions and measures will apply to the subcontractor. Acceptance of the tender is also subject to the condition that the contractor will implement all such security measures for the safe performance of the work as required in the scope of the contract. Should the awarded contractor fail to comply with the criminal record check process requirements and/or critical staff identified as part of the contract, failing the screening requirements, the Employer may terminate the contract

## People restrictions, hours of work, conduct and records

All work will be coordinated by the Employer. Working times can be subject to change, the Employer will inform the Contractor well in advance.

The Contractor will align his operating shifts to that of the Employer’s shift cycle.

- Normal working hours is:

- Monday to Thursday 	07:00 - 16:15(30 minutes lunch)

- Friday:			07:00-12:00(No lunch)

- Saturday & Sunday	Overtime

- All Timesheets are to be kept for records purposes i.e., man-hours worked safely etc.

- Overtime to be approved by the Service Manager

- Daily time sheet must always be kept up to date of normal and overtime worked.

- All overtime worked must comply with Eskom rest period requirements

## Health and safety facilities on the Affected Property

There is a medical station on site and a fire and rescue service for assistance with serious incidents and treatment of all serious injuries during normal working hours. Emergency services are available during normal working hours by dialling this phone number 078 100 5614/ 014 762 6911 (fire and rescue) and also available after hours or else contacting the Electrical Operating Desk (EOD) at 014 762 6491   However, the Contractor is expected to handle all minor incidents in-house by providing a first aider and a first aid kit.

The Contractor must familiarise themselves with the emergency procedure which will be provided by the Employer.

## Environmental controls, fauna & flora

The Contractor shall comply with the environmental procedure and polices applicable to Medupi Power Station. The Contractor shall prepare an environmental management plan relating to their activities that will be carried out. The environmental management plan shall be based on, amongst others, Eskom Medupi Power Station’s OEMP and any other applicable environmental legislation. The environmental management plan must include all the aspects and impacts relating to the activity and address the principle of continual improvement.

Eskom Medupi Power Station shall issue non-conformances where there are deviations from Eskom Medupi Power Station Procedures and any other environmental requirements. Method statements shall be submitted for approval by the Eskom Medupi Power Station Senior Environmental Advisor, prior to commencement of and activity. Non-conformance and incident reporting and investigations shall be done by the partner, such reports must include but not limited to the following information:

- The cause of the non-conformance/incident

- The proposed actions to correct and prevent recurrence

## Cooperating with and obtaining acceptance of Others

Proper co-ordination and work planning must be done when working in any area where others are performing work or activities.  Interfacing may be required with the Contractors.

## Records of Contractor’s Equipment

- The Contractor to declare all equipment and tools via a pre-set-up list at the main entrance, where removal permit will be issued by Security personnel.

- The Contractor needs to have a list of inventories of their equipment on site.

- Proof of site entrance needs to be provided before equipment can be removed from site.

- The Contractor shall ensure that there is a process in place to manage his equipment and tools. The statutory inspections and testing shall be done according to the requirements of the law.

- The equipment shall be inspected as per the requirements by the law. The small equipment and tools that are used daily by the cleaners shall be marked with unique codes and signed in and out by the employee using them.

## Equipment provided by the Employer

Equipment provided by the Employer is to be signed out on the tools register and returned in a serviceable condition.

## Site services and facilities

### Provided by the Employer

Sanitary services, water, compressed air, and electricity shall be provided by Eskom at fixed points on the plant. There is also a tuck-shop on site, but both only operate on weekdays and are for the Contractor’s own cost

### Provided by the Contractor

The Contractor is to supply all the personal protective equipment, transport, accommodation, tools, equipment, and consumables to perform all the required tasks on site.

## Control of noise, dust, water and waste

Employees to wear safety ear protection when working at the plant where the noise level is more than 80 db.

## Hook ups to existing works

Hooking up on heights is a non-negotiable lifesaving rule of Eskom, Medupi Power Station applies Zero Tolerance to non-compliance of the rule or any other lifesaving rule. The same disciplinary process and procedure will be followed when any of the lifesaving rules have been breached.

## Tests and inspections

### Description of tests and inspections

The test and inspection to be carried out by the Contractor, the Employer must be informed in advanced.

### Materials facilities and samples for tests and inspections

The materials facilities and samples for test and inspection to be carried out by the Contractor, the Employer and others will be determined and communicated by the Employer when the Contract commences.

# List of drawings

## Drawing issued by the Employer

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008 Fax 086 539 1902 www.ecs.co.za