{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["ORCA_LIZIBUKO - EL"],"not_rendered":{"images":1,"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"ORCA_LIZIBUKO - EL","index":0,"n_rows":832,"n_cols":6,"rows_kept":832,"merged":[[5,0,5,5],[6,0,6,5],[76,0,76,4],[124,1,124,5],[154,0,154,4],[231,0,231,4],[302,0,302,4],[379,0,379,4],[384,2,384,5],[385,2,385,3],[386,2,386,3],[387,2,387,3],[388,2,388,3],[389,2,389,3],[390,2,390,3],[391,2,391,3],[392,2,392,3],[408,0,408,5],[409,0,409,5],[481,0,481,4],[529,1,529,3],[560,0,560,4],[637,0,637,4],[713,0,713,4],[781,0,781,4],[786,2,786,5],[787,2,787,3],[788,2,788,3],[789,2,789,3],[790,2,790,3],[791,2,791,3],[792,2,792,3],[793,2,793,3],[794,2,794,3],[795,1,795,2],[797,4,797,5],[814,2,814,5],[815,2,815,5],[816,2,816,5],[817,2,817,5],[818,2,818,5],[819,2,819,5],[820,2,820,5]]}
[null,"TNPA MARINE SERVICES"]
[null,"REQUEST FOR PROPOSAL [RFP] No\t\t\t:\t"]
[null,"FOR THE PROVISION OF:"]
[null,"DRYDOCK OF TUG ORCA AND TUG LIZIBUKO FOR A ONCE-OFF PERIOD"]
[]
[" DRYDOCKING IN PORT OF EAST LONDON  - 2026/2027"]
["TASK 1 - TUG ORCA"]
["Item no","Description","Unit","Qty","Rate","Amount \n(excl VAT)"]
[1,"SERVICES AND SURVEYS"]
[]
[1.1,"SERVICES REQUIRED"]
["1.1.1","Provision of Fire Watch Man (8hrs/day)","Days",2]
["1.1.2","Provision of Hot Work Permit (8hrs/day)","Days",2]
["1.1.3","Provision of Non Destructive, Crack and Thickness Testing Where Needed","per/metre",10]
["1.1.4","Mobile Crane (1 Ton) (4hrs/day)","Days",3]
[]
[2,"ENGINE ROOM WORK"]
[]
[2.1,"VALVES"]
["2.1.1","Remove, Overhaul and Assemble Discharge Valves as Per South African Maritime Safety Authority Requirements and;"]
["2.1.2","Remove, Overhaul and Assemble Suction Valves as Per Samsa Requirements and; Renew all gaskets (non-metallic) "]
["2.1.3","Pressure Test Certificates for Valves to Be Supplied for the following valves "]
[null,"All valves to be inspected by Surveyor, assembled and pressure tested/Certified to 4 bar. "]
["V1","Black Water Overboard Valve  100 NB","No.",1]
["V2","Sewage Plant Overboard Valve 25 NB","No.",1]
["V3","Grey Water Overboard Valve   50 NB","No.",1]
["V4","A/C Plant Overboard Valve   32 NB","No.",1]
["V5","General Service Pump Isolating Valve  100 NB","No.",1]
["V6","Aft General Service Overboard Discharge Valve  80 NB","No.",1]
["V7","Fwd General Service Overboard Discharge Valve  80 NB","No.",1]
["V8","Oily Water Separator Overboard Valve  25 NB","No.",1]
["V9","Galley Overboard Valve  50 NB","No.",1]
["V10","Starboard Fire Pump Isolating Valve (Butterfly - To Be Cleaned In Place)  303 NB","No.",1]
["V11","Port Fire Pump Isolating Valve (Butterfly - To Be Cleaned In Place)  303 NB","No.",1]
["V12","Main Sea Chest Vent Valves 50 NB","No.",2]
["V13","Voith Vent Valves 25 NB","No.",2]
["V14","Service Hydraulic Fuel Drop Valves ","No.",4]
[]
[2.2,"PIPING (Pricing on schedule 40 for all)"]
["2.2.1","Engine Room Sea Water Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
["2.2.2","Engine Room Lubricating Oil Piping (Φ50mm) to Be Renewed Subject to Condition","Metre",2]
["2.2.3","Engine Room Fresh Water Piping (Φ50mm) to Be Renewed Subject to Condition","Metre",2]
["2.2.4","Engine Room Bilge Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
["2.2.5","Engine Room Hydraulic Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
["2.2.6","Engine Room Sewage Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
["2.2.7","Engine Room Compressed Air Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
["2.2.8","Engine Room Fuel Piping (Φ50mm) to Be Renewed Subject to Condition ","Metre",2]
[]
[2.3,"BILGES"]
["2.3.1","Entire Engine Room Bilges to Be Washed and Cleaned","m³",10]
["2.3.2","Bilges To Be Pumped Out After Cleaned","m³",10]
[]
[2.4,"FIRE PUMP STRUM BOXES & STRAINERS"]
["2.4.1","Fire Pump Strum Boxes To Be Opened, Hp Cleaned & Inspected","Each",2]
["2.4.2","Renew Strum Box Anodes (X2)","Each",2]
["2.4.3","Remove Strainer & Hp Wash","Each",2]
["2.4.4","Hoist Up Strainer Housing To Access Butterfly Valve, If Necessary","Each",2]
["2.4.5","Strum Box & Strainers To Be Painted With Coat Of Antifouling ","Each",2]
["2.4.6","Strum Boxes With Strainers To Be Boxed Up After Completion","Each",2]
["2.4.7","New Gaskets To Be Fitted (5mm Neoprene)","Each",2]
[]
[2.5,"KEEL COOLERS"]
["2.5.1","Flush Through Keel Coolers And Refill","Each",2]
["2.5.2","Renew Anodes (3kg)","Each",4]
["2.5.3","Light Scrapping (With Extreme Caution) To Remove Marine Growth Off Keel Coolers","Each",2]
[]
[2.6,"VARIOUS BRACKETS"]
["2.6.1","Brackets In ER To Be Renewed As Per Chief Engineers Instructions (200mm X 50mm MS)","Each",10]
["2.6.2","Brackets On Deck To Be Renewed As Per Masters Instructions (200mm X 50mm MS)","Each",10]
[]
[2.7,"MAIN FIRE PUMP"]
["2.7.1","Repack Glands & Test When Afloat (16mm Graphite Packing)","Each",2]
[]
[2.8,"HT & LT MAIN ENGINE ATTACHED PUMPS (MAN 8L 27/38)"]
["2.8.1","Service Attached Pumps & Supply & Renew Defectives Parts As Necessary","Each",4]
[]
["SUBTOTAL 1 (excl VAT)"]
[{"v":2.9,"d":"2.90"},"FUEL TRANSFER MAIN ENGINE ATTACHED PUMPS (MAN 8L 27/38)"]
["2.9.1","Service Attached Pumps & Supply & Renew Defectives Parts As Necessary","No.",2]
[]
[{"v":2.1,"d":"2.10"},"STANDBY LUBE OIL PUMPS (gp 185-125 G200)"]
["2.10.1","Service Pumps X 2 & Electric Motors X 2","No.",2]
["2.10.2","Supply & Renew Pump Couplings And Loctite ","No.",2]
["2.10.3","Rewind Motor, As Necessary","No.",1]
[]
[2.11,"STANDBY HT & LT FRESH WATER PUMPS (STORK CB50-160)"]
["2.11.1","Service Pumps X 2 & Electric Motors X 2","No.",2]
["2.11.2","Rewind Motor, As Necessary","No.",1]
[]
[2.12,"GENERAL SERVICE PUMPS (CH40-250 COMBIPRIME)"]
["2.12.1","Service Pumps X 2 & Electric Motors X 2 ","No.",2]
["2.12.2","Supply & Renew Seals & Any/All Defective Parts, As Necessary. (Impellor, housing, coupling etc)","No.",2]
["2.12.3","Rewind Motor, As Necessary","No.",1]
[]
[2.13,"FUEL TRANSFER PUMP (STORK KGE 15-6)"]
["2.13.1","Service Pump & Supply & Renew Defective Parts As Necessary & Electric Motor","Each",1]
["2.13.2","Rewind Motor, As Necessary","Each",1]
[]
[2.14,"SERVICING OF AUTO LUBE FILTER (MOATTI) AS PER OEM MANUAL (ALPHA LAVAL CCU 240 24 A05)"]
["2.14.1","Disassembly, Cleaning,  Inspection Of Components & Assembly Of The Centrifuge (Supply & Renew O-rings, Gaskets & Servicable Spares)","Each",2]
["2.14.2","Disassembly Of Filter & Assembly Of The Filter (After Cleaning & Inspection)","Each",2]
["2.14.3","Disassembly, Cleaning, Inspection Of Components & Assembly Of Filtering Unit (Suppy & Renew O-rings, Gaskets & Servicable)","Each",2]
["2.14.4","Disassembly, Cleaning, Inspection Of Components & Assembly Of The Hydraulic Motor (Suppy & Renew O-rings, Gaskets & Servicable Spares)","Each",2]
["2.14.5","Commissioning Of Filters After Completion Of Maintenance, As Per OEM Manual","Each",2]
["2.14.6","Detailed Report To Be Submitted","Each",1]
[]
[2.15,"DOMESTIC FRESH WATER PUMPS (TWIN BOOSTER SYSTEM CDA 150/100, 1.1KW, HEAD 4.5 BAR)"]
["2.15.1","Supply & Install Domestic Fresh Water Pumps","Each",2]
["2.15.2","Modify Piping To Suit, Prime And Place System Online","Each",2]
[]
[3,"ELECTRICAL"]
[]
[3.1,"SHORE SUPPLY TRANSFORMER (400V - 65KVA)"]
["3.1.1","Carry Out Service As Per OEM Manual","Sum",1]
[]
[3.2,"MARINE SWITCHBOARD"]
["3.2.1","Carry Out Infrared Thermography Under Load and Record Findings In A Form Of A Report.","Sum",1]
["3.2.2","Cleaning, Dust Removal, Checking & Tightning Of All Connections","Sum",1]
["3.2.3","Apply A Light, Specialized Electrical Lubricant to moving contact parts and mechanical interlocks","Sum",1]
[]
[3.3,"AIR CIRCUIT BREAKERS"]
["3.3.1","Air Circuit Breakers To Be Serviced As Per OEM Manual incl. Replacement of Defective Parts","No.",2]
[]
[4,"HULL AND SUPERSTRUCTURE WORK PREPARATION"]
[null,"*Cleaning Agent For Chemically Cleaning To Be Provided By Contractor  *MSDS Information To Be Provided For Chemicals"]
[]
[4.1,"HULL CLEANING"]
["4.1.1","Barnicles to be scraped off entire hull","m²",150]
["4.1.2","Entire hull to be pressure washed  (350bar) ","m²",1200]
["4.1.3","Port & Stbd Box Coolers Seachest ","Each",2]
["4.1.4","Port & Stbd Main Seachest ","Each",2]
["4.1.5","Port & Stbd Keel Coolers","Each",2]
["4.1.6","Spot Blast Affected Areas Of Hull Including Inner And Outer Gunnel","m²",600]
["4.1.7","Entire Exterior Hull Including Inner And Outer Gunnel To Be Pressure Washed (350bar) ","m²",1200]
["4.1.8","Remove Sea Chest Gratings For Cleaning, Blasting And Later Replaced (Remove Prior Blasting)","Each",22]
["4.1.9","Clean Dock, Barnicles, Paint Flakes & Blasting Debris To Be Disposed Of ","m²",350]
[]
[4.2,"ANODES"]
["4.2.1","Remove Existing Anodes ","Each",100]
["4.2.2","Replace Anodes With New After Paint Application","Each",100]
[]
[4.3,"PORT & STBD VOITH UNITS"]
["4.3.1","Remove Voith Inspections Covers","Each",2]
["4.3.2","Hp Wash Rotor Casings","Each",2]
["4.3.3","Cut Out Docking Platform For Dropping Of Blades","Each",4]
["4.3.4","Descale Voith Rotor Wells, Rotor Table Sides & Table Tops","Each",2]
["4.3.5","Degrease & Hp Wash Voith Rotor Wells And Tables (After Repairs)","Each",2]
["4.3.6","Paint Voith Rotor Wells & Tables (1 X Primer, 1 X Undercoat)","Each",2]
["4.3.7","Paint Rotor Casings (Seaquantum Ultra Dark Red) (2 X Coats)","Each",2]
["4.3.8","Reweld Docking Platform After Voith Repairs","Each",4]
["4.3.9","Crack Detecting Tests To Be Done On All Welds For The Platform Repairs (Submit Report)","Each",2]
["4.3.10","Refit Voith Inspection Covers, Fit New Gaskets ","Each",2]
["4.3.11","Mechanically Clean Voith Blades ","Each",10]
[]
["SUBTOTAL 2 (excl VAT)"]
[4.4,"DOCKING PLATFORM STRUTS"]
["4.4.1","Crack Detecting Tests To Be Done On All Welds (Submit Report)","Sum",2]
["4.4.2","Repairs To Be Done On Welds","per metre",10]
[]
[4.5,"SKEG"]
["4.5.1","Lower Plug On Skeg To Be Removed And Check For Water","Sum",1]
["4.5.2","Refit Plug & Renew Teflon Plug Washer, If Necessary","Sum",1]
[]
[4.6,"DOCKING GUARD"]
["4.6.1","Remove Lower Plug And Check For Water","Sum",1]
["4.6.2","Refit Plug & Renew Teflon Plug Washer, If Necessary","Sum",1]
[]
[4.7,"HULL THICKNESS"]
["4.7.1","Prep For Hull Thickness Testing (+/- 300 Spots To Be Spread Evenly Across Entire Underwater Area Of Hull)","Sum",1]
["4.7.2","Ultrasonic Thickness Testing To Be Conducted And Report Submitted","Sum",1]
[]
[4.8,"FENDERS"]
["4.8.1","Remove All Tyre Fenders And Land On Dock Floor","Each",16]
["4.8.2","Repair/Replace Lugs","Each",10]
["4.8.3","Refit Tyre Fenders On Completion Of Painting","Each",16]
[]
[4.9,"MAST, MONKEY ISLAND & WHEELHOUSE (INC. YARDARMS, LADDERS & RAILINGS)"]
["4.9.1","Chemically Clean","m²",400]
["4.9.2","Spot Blast Affected Areas","m²",10]
["4.9.3","Renew Corroded/Damaged Steelwork (50kg)","kg",50]
["4.9.4","Hp Wash After Mechanical Descale","m²",400]
[]
[{"v":4.1,"d":"4.10"},"BOAT DECK, SUPERSTRUCTURE, MAIN DECK & BOLLARDS (INC. LADDERS, RAILINGS & VENTS)"]
["4.10.1","Chemically Clean","m²",600]
["4.10.2","Spot Blast Affected Areas","m²",20]
["4.10.3","Renew Corroded/Damaged Steelwork (50kg)","kg",50]
["4.10.4","Hp Wash After Spot Blast","m²",200]
["4.10.5","Prime Affected Areas (Smartpack Red) First Coat","m²",20]
["4.10.6","Prime Affected Areas (Smartpack Grey) Second Coat","m²",20]
[]
[4.11,"WATER LINE TO GUNNNEL (INCLUDING INSIDE BULWARKS)"]
["4.11.1","Chemically Clean","m²",200]
["4.11.2","Spot Blast Affected Areas","m²",10]
["4.11.3","Hp Wash After Mechanical Descale","m²",200]
[]
[4.12,"WHEELHOUSE SLIDING WINDOWS"]
["4.12.1","Remove Sliding Windows","Each",8]
["4.12.2","Mechanically Descale Affected Areas Of Frames","m²",2]
["4.12.3","Repair Frames (3190MM x 825MM)","Each",8]
["4.12.4","Paint As Per Wheelhouse Paint Specs","m²",2]
["4.12.5","Renew Window Rubbers with Ethylene Propylene Diene Monomer (EPDM) - To Be Tested For Leaks On Completion","Sum",8]
["4.12.6","Refit Locking Mechanisms","Each",32]
["4.12.7","Manuafacture And Replace Broken Locking Mechanism As Per Sample","Each",35]
[]
[4.13,"EXHAUST FUNNELS"]
["4.13.1","Wash Down Exhaust Funnels To Remove Salt ( X2)","m²",35]
["4.13.2","Remove Heat Shield & Mechanically Descale Affected Areas Of Exhaust Funnel & Heat Shield","m²",10]
["4.13.3","Wash Out/Degrease Entire Inner Space Of Exhaust Funnels (X 2)","m²",35]
["4.13.4","Retightened All Bolts & Nuts On All Flanges, Mountings And Shock Dampers. (Top & Bottom Spaces)","Sum",2]
["4.13.5","Renew Corroded Steelwork (50kg)","kg",50]
[]
[5,"PAINTING"]
[]
[5.1,"MAST, MONKEY ISLAND & WHEELHOUSE (INC. YARDARMS, LADDERS & RAILINGS)"]
["5.1.1","Prime Affected Areas (Smartpack Red) First Coat","m²",10]
["5.1.2","Prime Affected Areas (Smartpack Grey) Second Coat","m²",10]
["5.1.3","Apply Top Coat As Per Paint Spec (Hardtop XP White) Complete 2 Coats","m²",400]
[]
[5.2,"WATER LINE TO GUNNNEL (INCLUDING INSIDE BULWARKS)"]
["5.2.1","Prime Affected Areas (Smartpack Red) First Coat","m²",200]
["5.2.2","Prime Affected Areas (Smartpack Grey) Second Coat","m²",200]
["5.2.3","Apply Top Coat As Per Paint Spec (Black) Complete 2 Coats","m²",450]
[]
[5.3,"HULL (INCLUDING SEA CHESTS)"]
["5.3.1","Apply Primer As Per Paint Spec (90 Aliminium)","m²",750]
["5.3.2","Apply Undercoat (Tie-Coat) As Per Paint Spec (Safeguard Universal Es Plum)","m²",750]
["5.3.3","Apply Antifouling As Per Paint Spec (Seaforce Active Plus Light Red)","m²",750]
["5.3.4","Apply Antifouling As Per Paint Spec (Seaforce Active Plus Dark Red)","m²",750]
["5.3.5","Draught And Plimsol Marks To Be Painted","m²",10]
["5.3.6","Paint Inspector To Oversee Paint Application & Issuing Of Antifouling Certification","Sum",1]
[]
["SUBTOTAL 3 (excl VAT)"]
[5.4,"EXHAUST FUNNELS"]
["5.4.1","Apply Full Coat As Per Paint Spec (1000c Aliminium)","m²",35]
["5.4.2","Apply Full Coat As Per Paint Spec (Solvalitt Black)","m²",35]
[]
[5.5,"ENGINE ROOM FAN SPACES"]
["5.5.1","Spot Blast Affected Area","m²",4]
["5.5.2","Prime Affected Areas As Per Paint Spec","m²",4]
["5.5.3","Apply Top Coat As Per Paint Spec (Hardtop Xp White) Complete ","m²",10]
["5.5.4","Renew Corroded Steelwork (50kg)","kg",50]
["5.5.5","Manufacture Dogs in 316 Stainless Steel And Replace Broken Dogs As Per Sample","Each",15]
[]
[5.6,"EXTRA'S"]
["5.6.1","Removal Of Debris","m²",5]
[]
[6,"TANKS"]
[null,"*Contractor To Provide For Gas Free Certificate Where Required."]
[null,"*All Water Tanks & Void Space Plugs To Be Opened & Replaced On Completion "]
[null,"*All Water Tanks & Void Space Plugs Teflon Plug Washers To Be Replaced"]
[]
[6.1,"FRESH WATER TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.1.1","Fresh Water Tank To Be Drained","Each",1]
["6.1.2","Open Fresh Water Tank And Ventilate","Each",1]
["6.1.3","Fresh Water Tank To Be Hp Cleaned","m²",38]
["6.1.4","Fresh Water Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.1.5","Fresh Water Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.1.6","New Gaskets To Be Made Up","Each",2]
["6.1.7","Fresh Water Manhole Covers To Be Refitted","Each",2]
["6.1.8","Inspect Condition Of Echo Sounder Cable Conduit Inside Tank","Each",1]
["6.1.9","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.2,"FOREPEAK TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.2.1","Forepeak Tank To Be Drained","Each",1]
["6.2.2","Open Forepeak Tank And Ventilate","Each",1]
["6.2.3","Forepeak Tank To Be Cleaned","m²",50]
["6.2.4","Forepeak To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.2.5","Forepeak To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.2.6","New Gasket To Be Made Up","Each",1]
["6.2.7","Forepeak Tank Manhole Cover To Be Refitted","Each",1]
["6.2.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.3,"AFTPEAK TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.3.1","Aftpeak Tank To Be Drained","Each",1]
["6.3.2","Open Aftpeak Tank And Ventilate","Each",1]
["6.3.3","Aftpeak Tank To Be Cleaned","m²",40]
["6.3.4","Aftpeak Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.3.5","Aftpeak Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.3.6","New Gasket To Be Made Up","Each",1]
["6.3.7","Aftpeak Tank Manhole Cover To Be Refitted","Each",1]
["6.3.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.4,"DOUBLE BOTTOM FUEL TANKS"]
["6.4.1","Open Double Bottom Fuel Tanks And Ventilate","Each",2]
["6.4.2","Gas Free Certificate To Be Issued Before Entry","Each",1]
["6.4.3","Double Bottom Fuel Tanks To Be Cleaned (X2)","m²",68]
["6.4.4","Double Bottom Fuel Tanks To Be Mechanically Descaled And Primed (1 Coat Tankguard Storage Light Red)","m²",10]
["6.4.5","Double Bottom Fuel Tanks To Be Touched Up As Required (1 Coat Tankguard Storage Light Grey)","m²",10]
["6.4.6","New Gaskets To Be Made Up","Each",2]
["6.4.7","Double Bottom Fuel Tanks Manhole Covers To Be Refitted","Each",2]
["6.4.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.5,"DIRTY OIL TANKS (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.5.1","Dirty Oil Tanks To Be Pumped Out","m²",5]
["6.5.2","Open Dirty Oil Tanks And Ventilate","Each",2]
["6.5.3","Dirty Oil Tanks To Be Cleaned","m²",16]
["6.5.4","Dirty Oil Tanks To Be Mechanically Descaled And Primed (1 Coat Tankguard Storage Light Red)","m²",4]
["6.5.5","Dirty Oil Tanks To Be Touched Up As Required (1 Coat Tankguard Storage Light Grey)","m²",4]
["6.5.6","New Gaskets To Be Made Up","Each",2]
["6.5.7","Dirty Oil Tank Manhole Covers To Be Refitted","Each",2]
["6.5.8","Replace Damaged Studs, As Necessary","Each",6]
[]
["SUBTOTAL 4 (excl VAT)"]
[6.6,"VOID SPACE (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.6.1","Void Space Tank To Be Cleaned","m²",10]
["6.6.2","Void Space Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",4]
["6.6.3","Void Space Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",4]
["6.6.4","New Gaskets To Be Made Up","Each",2]
["6.6.5","Void Space Tank Manhole Cover To Be Refitted","Each",2]
["6.6.6","Renew Flexi Hoses (Ø120 X 150mm, 5mm) & Heavy Duty Clamps On Keel Cooler Inside Tank","Each",4]
["6.6.7","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.7,"ANCHOR AND CHAIN"]
["6.7.1","Anchor And Chain To Be Dropped And Ranged","Sum",1]
["6.7.2","Anchor And Chain To Be Shot Blast If Required","Sum",1]
["6.7.3","Anchor And Chain To Be High Pressure Cleaned","Sum",1]
["6.7.4","Free Up Anchor Chain Swivel","Each",1]
["6.7.5","Chain Thickness Measurements To Be Taken (Submit Report) (5 Spots Per Shackle- 4 Shackles)","Spot",20]
["6.7.6","Anchor To Be Painted (1 Coat \"No Rust\", 1 Coat Red Oxide, 1 Coat Hardtop Black)","Each",1]
["6.7.7","Entire Chain To Be Painted With Boiled Linseed Oil (2 Coats) Allow For Adequate Drying Time Between Coats","Sum",1]
["6.7.8","Chain To Be Remarked (Red & White Paint)","Each",1]
["6.7.9","Chain And Anchor To Be Restowed","Sum",1]
["6.7.10","Spare Anchor To Be Removed, Derusted & Painted. (1 Coat \"No Rust\", 1 Coat Red Oxide, 1 Coat Black)","Each",1]
["6.7.11","Spare Anchor D-Shackle To Be Freed Up","Each",1]
[]
[6.8,"CHAIN LOCKER"]
["6.8.1","Manhole Cover To Be Removed","Each",1]
["6.8.2","Manhole Cover To Be Mechanically Descaled ","m²",0.5]
["6.8.3","Manhole Cover To Be Washed And Painted (Smartpack Red)","m²",1]
["6.8.4","Mud To Be Removed And Disposed Of","m²",1]
["6.8.5","Chain Locker To Be Hp Washed ","m²",4]
["6.8.6","Chain Locker To Be Mechanically Descaled","m²",1]
["6.8.7","Chain Locker To Be Painted Complete  (Smartpack Red)","m²",4]
["6.8.8","Grids To Be Removed, Hp Washed And Painted (Smartpack Red) Then Refitted","Each",4]
["6.8.9","Renew Corroded Steelwork (50kg)","kg",50]
["6.8.10","Manhole Cover To Be Refitted With New Gasket","Each",1]
[]
[7,"DECK WORK"]
[]
[7.1,"ANCHOR WINDLASS x 1"]
["7.1.1","Spot Blast Affected Areas","m²",1]
["7.1.2","Apply Primer As Per Paint Spec  ","m²",2]
["7.1.3","Apply Top Coat As Per Paint Spec (1 Coat  Hardtop As Green/Black )","m²",1]
["7.1.4","Renew All Hydraulic Pipes & Fittings As Necessary","Each",5]
["7.1.5","Service Hydraulic Motor On Deck (Pay Special Attention To Coupling)","Sum",1]
["7.1.6","Service Hydraulic Power Pack (Pay Special Attention To Coupling)","Sum",1]
["7.1.7","Service Control Valve","Each",1]
[]
[7.2,"PORT HOLES x 7"]
["7.2.1","Mechanically Descale Affected Areas ","m²",1]
["7.2.2","Repair Sealing Surface If Necessary","Each",7]
["7.2.3","Paint Sealing Surface & Window Boxes As Per Wheelhouse Paint Spec","m²",1]
["7.2.4","Supply & Renew Rubber Seals with Ethylene Propylene Diene Monomer (EPDM) - To Be Tested For Leaks On Completion","Each",7]
[]
[8.1,"MISCELLANEOUS WORK SUBJECT TO APPROVED QUOTE ON REQUEST BY TNPA REPRESENTATIVE"]
[]
["8.1.1","Budget R100 000 For Unplanned Work Identified After Inspection","Sum",1,{"v":100000,"d":"R100,000.00"},{"v":100000,"d":"R100,000.00"}]
["8.1.2","Budget For Skilled Labour ","hrs.",20]
["8.1.3","Budget For Semi-Skiled Labour ","hrs.",20]
["8.1.4","Budget For Machine Shop Cost","hrs.",20]
["8.1.5","Assist CMEO And Voith Technician With Voith Health Check For 4hrs Per Day","Days",2]
["8.1.6","Signage And Stickers To Be Replaced After Painting Completed","Each",100]
["8.1.7","Budget For Skilled Labour Overtime For 3 Saturdays And 3 Sundays for 4hrs Per Day","Days",6]
["8.1.8","Scaffolding","Days",14]
["8.1.9","She File, She Plan And Risk Assessment (On award)","Sum",1]
[]
[8.2,"GENERAL CLEANING"]
["8.2.1","Provide Semi Skilled Labour 8 Hrs For Cleaning And Assisting TNPA Engine Room Staff","Days",10]
[]
[8.3,"METAL WORK"]
["8.3.1","Metal For Repairs","Ton",0.5]
[]
[9,"SUNDRIES"]
[]
[9.1,"DISBURSEMENTS"]
["9.1.1","Travelling Expenses (Monday to Sunday)","Weeks",6]
["9.1.2","Accomodation (Monday to Sunday)","Weeks",6]
["9.1.3","Other Disbursements (Breakdown of details to be included in proposal)","Weeks",6]
[]
["SUBTOTAL 5 (excl VAT)"]
[]
[]
[null,"NB: SUBTOTALS AT THE BOTTOM OF EACH PAGE TO BE CARRIED OVER TO PRICING SUMMARY"]
[]
[null,null,"TASK 1 PRICING SUMMARY"]
[null,null,"Subtotal 1 (excl VAT)",null,"Subtotal 1"]
[null,null,"Subtotal 2\n(excl VAT)",null,"Subtotal 2"]
[null,null,"Subtotal 3\n(excl VAT)",null,"Subtotal 3"]
[null,null,"Subtotal 4\n(excl VAT)",null,"Subtotal 4"]
[null,null,"Subtotal 5\n(excl VAT)",null,"Subtotal 5"]
[null,null,"Total excl VAT",null,"Total excl VAT"]
[null,null,"Add 15% VAT"]
[null,null,"Total incl VAT"]
{"$rows_empty":15}
[" DRYDOCKING IN PORT OF EAST LONDON  - 2026/2027"]
["TASK 2 - TUG LIZIBUKO"]
["Item no","Description","Unit","Qty","Rate","Amount\n(excl VAT)"]
[1,"SERVICES AND SURVEYS"]
[]
[1.1,"SERVICES REQUIRED"]
["1.1.1","Provision of Fire Watch Man (8hrs/day)","Days",2]
["1.1.2","Provision of Hot Work Permit (8hrs/day)","Days",2]
["1.1.3","Provision of Non Destructive, Crack and Thickness Testing Where Needed","per/metre",10]
["1.1.4","Mobile Crane (1 Ton) (4hrs/day)","Days",3]
[]
[2,"ENGINE ROOM WORK"]
[]
[2.1,"VALVES"]
["2.1.1","Remove, Overhaul and Assemble Discharge Valves as Per South African Maritime Safety Authority Requirements and;"]
["2.1.2","Remove, Overhaul and Assemble Suction Valves as Per Samsa Requirements and;"]
["2.1.3","Renew all gaskets (non-metallic) "]
["2.1.4","Pressure Test Certificates for Valves to Be Supplied for the following valves "]
[null,"All valves to be inspected by Surveyor, assembled and pressure tested/Certified to 4 bar. "]
[null,"LIST OF VALVES"]
["V1","Black Water Overboard Valve  100 NB","No.",1]
["V2","Sewage Plant Overboard Valve 25 NB","No.",1]
["V3","Grey Water Overboard Valve   50 NB","No.",1]
["V4","A/C Plant Overboard Valve   32 NB","No.",1]
["V5","General Service Pump Isolating Valve  100 NB","No.",1]
["V6","Aft General Service Overboard Discharge Valve  80 NB","No.",1]
["V7","Fwd General Service Overboard Discharge Valve  80 NB","No.",1]
["V8","Oily Water Separator Overboard Valve  25 NB","No.",1]
["V9","Galley Overboard Valve  50 NB","No.",1]
["V10","Starboard Fire Pump Isolating Valve (Butterfly - To Be Cleaned In Place)  303 NB","No.",1]
["V11","Port Fire Pump Isolating Valve (Butterfly - To Be Cleaned In Place)  303 NB","No.",1]
["V12","Main Sea Chest Vent Valves 50 NB","No.",2]
["V13","Voith Vent Valves 25 NB","No.",2]
["V14","Service Hydraulic Fuel Drop Valves ","No.",4]
[]
[2.2,"PIPING (Quote on schedule 40 for all)"]
["2.2.1","Engine Room Sea Water Piping to Be Renewed Subject to Condition ","Metre",2]
["2.2.2","Engine Room Lubricating Oil Piping to Be Renewed Subject to Condition","Metre",2]
["2.2.3","Engine Room Fresh Water Piping to Be Renewed Subject to Condition","Metre",2]
["2.2.4","Engine Room Bilge Piping to Be Renewed Subject to Condition ","Metre",2]
["2.2.5","Engine Room Hydraulic Piping to Be Renewed Subject to Condition ","Metre",2]
["2.2.6","Engine Room Sewage Piping to Be Renewed Subject to Condition ","Metre",2]
["2.2.7","Engine Room Compressed Air Piping to Be Renewed Subject to Condition ","Metre",2]
["2.2.8","Engine Room Fuel Piping to Be Renewed Subject to Condition ","Metre",2]
[]
[2.3,"BILGES"]
["2.3.1","Entire Engine Room Bilges to Be Washed and Cleaned","m³",10]
["2.3.2","Bilges To Be Pumped Out After Cleaned","m³",10]
[]
[2.4,"FIRE PUMP STRUM BOXES & STRAINERS"]
["2.4.1","Fire Pump Strum Boxes To Be Opened, Hp Cleaned & Inspected","Each",2]
["2.4.2","Renew Strum Box Anodes (X2)","Each",2]
["2.4.3","Remove Strainer & Hp Wash","Each",2]
["2.4.4","Hoist Up Strainer Housing To Access Butterfly Valve, If Necessary","Each",2]
["2.4.5","Strum Box & Strainers To Be Painted With Coat Of Antifouling ","Each",2]
["2.4.6","Strum Boxes With Strainers To Be Boxed Up After Completion","Each",2]
["2.4.7","New Gaskets To Be Fitted (5mm Neoprene)","Each",2]
[]
[2.5,"KEEL COOLERS"]
["2.5.1","Flush Through Keel Coolers And Refill","Each",2]
["2.5.2","Renew Anodes (3kg)","Each",4]
["2.5.3","Light Scrapping (With Extreme Caution) To Remove Marine Growth Off Keel Coolers","Each",2]
[]
[2.6,"VARIOUS BRACKETS"]
["2.6.1","Brackets In ER To Be Renewed As Per Chief Engineers Instructions (200mm X 50mm MS)","Each",10]
["2.6.2","Brackets On Deck To Be Renewed As Per Masters Instructions (200mm X 50mm MS)","Each",10]
[]
[2.7,"MAIN FIRE PUMP"]
["2.7.1","Repack Glands & Test When Afloat (16mm Graphite Packing)","Each",2]
[]
[2.8,"HT & LT MAIN ENGINE ATTACHED PUMPS (MAN 8L 27/38)"]
["2.8.1","Service Attached Pumps & Supply & Renew Defectives Parts As Necessary","Each",4]
[]
["SUBTOTAL 1 (excl VAT)"]
[2.9,"FUEL TRANSFER MAIN ENGINE ATTACHED PUMPS (MAN 8L 27/38)"]
["2.9.1","Service Attached Pumps & Supply & Renew Defectives Parts As Necessary","No.",2]
[]
[{"v":2.1,"d":"2.10"},"STANDBY LUBE OIL PUMPS (gp 185-125 G200)"]
["2.10.1","Service Pumps X 2 & Electric Motors X 2","No.",2]
["2.10.2","Supply & Renew Pump Couplings And Loctite","No.",2]
["2.10.3","Rewind Motor, As Necessary","No.",1]
[]
[2.11,"STANDBY HT & LT FRESH WATER PUMPS (STORK CB50-160)"]
["2.11.1","Service Pumps X 2 & Electric Motors X 2","No.",2]
["2.11.2","Rewind Motor, As Necessary","No.",1]
[]
[2.12,"GENERAL SERVICE PUMPS (CH40-250 COMBIPRIME)"]
["2.12.1","Service Pumps X 2 & Electric Motors X 2 ","No.",2]
["2.12.2","Supply & Renew Seals & Any/All Defective Parts, as necessary. (Impellor, housing, coupling etc)","No.",2]
["2.12.3","Rewind Motor, As Necessary","No.",1]
[]
[2.13,"FUEL TRANSFER PUMP (STORK KGE 15-6)"]
["2.13.1","Service Pump & Supply & Renew Defective Parts As Necessary & Electric Motor","Each",2]
["2.13.2","Rewind Motor, As Necessary","Each",1]
[]
[2.14,"SERVICING OF AUTO LUBE FILTER (MOATTI) AS PER OEM MANUAL (ALPHA LAVAL CCU 240 24 A05)"]
["2.14.1","Disassembly, Cleaning,  Inspection Of Components & Assembly Of The Centrifuge (Supply & Renew O-rings, Gaskets & Servicable Spares)","Each",2]
["2.14.2","Disassembly Of Filter & Assembly Of The Filter (After Cleaning & Inspection)","Each",2]
["2.14.3","Disassembly, Cleaning, Inspection Of Components & Assembly Of Filtering Unit (Suppy & Renew O-rings, Gaskets & Servicable)","Each",2]
["2.14.4","Disassembly, Cleaning, Inspection Of Components & Assembly Of The Hydraulic Motor (Suppy & Renew O-rings, Gaskets & Servicable Spares)","Each",2]
["2.14.5","Commissioning Of Filters After Completion Of Maintenance, As Per OEM Manual","Each",2]
["2.14.6","Detailed Report To Be Submitted","Each",1]
[]
[2.15,"DOMESTIC FRESH WATER PUMPS (TWIN BOOSTER SYSTEM CDA 150/100, 1.1KW, HEAD 4.5 BAR)"]
["2.15.1","Supply & Install Domestic Fresh Water Pumps","Each",2]
["2.15.2","Modify Piping To Suit, Prime And Place System Online","Each",2]
[]
[3,"ELECTRICAL"]
[]
[3.1,"SHORE SUPPLY TRANSFORMER (400V - 65KVA)"]
["3.1.1","Carry Out Service As Per OEM Manual","Sum",1]
[]
[3.2,"MARINE SWITCHBOARD"]
["3.2.1","Carry Out Infrared Thermography Under Load and Record Findings In A Form Of A Report.","Sum",1]
["3.2.2","Cleaning, Dust Removal, Checking & Tightning Of All Connections","Sum",1]
["3.2.3","Apply A Light, Specialized Electrical Lubricant to moving contact parts and mechanical interlocks","Sum",1]
[]
[3.3,"AIR CIRCUIT BREAKERS"]
["3.3.1","Air Circuit Breakers To Be Serviced As Per OEM Manual incl. Replacement of Defective Parts","No.",2]
[]
[4,"HULL AND SUPERSTRUCTURE WORK PREPARATION"]
[null,"*Cleaning Agent For Chemically Cleaning To Be Provided By Contractor  *MSDS Information To Be Provided For Chemicals"]
[]
[4.1,"HULL CLEANING"]
["4.1.1","Barnicles to be scraped off entire hull","m²",150]
["4.1.2","Entire hull to be pressure washed  (350bar) ","m²",1200]
["4.1.3","Port & Stbd Box Coolers Seachest ","Each",2]
["4.1.4","Port & Stbd Main Seachest ","Each",2]
["4.1.5","Port & Stbd Keel Coolers","Each",2]
["4.1.6","Spot Blast Affected Areas Of Hull Including Inner And Outer Gunnel","m²",600]
["4.1.7","Entire Exterior Hull Including Inner And Outer Gunnel To Be Pressure Washed (350bar) ","m²",1200]
["4.1.8","Remove Sea Chest Gratings For Cleaning, Blasting And Later Replaced (Remove Prior Blasting)","Each",22]
["4.1.9","Clean Dock, Barnicles, Paint Flakes & Blasting Debris To Be Disposed Of ","m²",350]
[]
[4.2,"ANODES"]
["4.2.1","Remove Existing Anodes (64 X Hull + 20 Vsp Units + 4 X Sea Strainers . Total 100)","Each",100]
["4.2.2","Replace Anodes With New After Paint Application","Each",100]
[]
[4.3,"PORT & STBD VOITH UNITS"]
["4.3.1","Remove Voith Inspections Covers","Each",2]
["4.3.2","Hp Wash Rotor Casings","Each",2]
["4.3.3","Cut Out Docking Platform For Dropping Of Blades","Each",4]
["4.3.4","Paint Rotor Casings (Seaquantum Ultra Dark Red) (2 X Coats)","Each",2]
["4.3.5","Reweld Docking Platform After Voith Repairs","Each",4]
["4.3.6","Crack Detecting Tests To Be Done On All Welds For The Platform Repairs ( Submit Report)","Each",2]
["4.3.7","Refit Voith Inspection Covers, Fit New Gaskets (Gaskets Supplied By Tnpa)","Each",2]
["4.3.8","Mechanically Clean Voith Blades ","Each",10]
[]
[4.4,"DOCKING PLATFORM STRUTS"]
["4.4.1","Crack Detecting Tests To Be Done On All Welds (Submit Report)","Each",2]
["4.4.2","Repairs To Be Done On Welds","Per/Metre",10]
[]
["SUBTOTAL 2 (excl VAT)"]
[4.5,"SKEG"]
["4.5.1","Lower Plug On Skeg To Be Removed And Check For Water","Sum",1]
["4.5.2","Refit Plug & Renew Teflon Plug Washer If Necessary","Sum",1]
[]
[4.6,"DOCKING GUARD"]
["4.6.1","Remove Lower Plug And Check For Water","Sum",1]
["4.6.2","Refit Plug & Renew Teflon Plug Washer If Necessary","Sum",1]
[]
[4.7,"HULL THICKNESS"]
["4.7.1","Prep For Hull Thickness Testing (+/- 300 Spots To Be Spread Evenly Across Entire Underwater Area Of Hull)","Sum",1]
["4.7.2","Ultrasonic Thickness Testing To Be Conducted And Report Submitted","Sum",1]
[]
[4.8,"FENDERS"]
["4.8.1","Remove All Tyre Fenders And Land On Dock Floor","Each",16]
["4.8.2","Repair/Replace Lugs","Each",10]
["4.8.3","Refit Tyre Fenders On Completion Of Painting","Each",16]
[]
[4.9,"MAST, MONKEY ISLAND & WHEELHOUSE (INC. YARDARMS, LADDERS & RAILINGS)"]
["4.9.1","Chemically Clean","m²",400]
["4.9.2","Spot Blast Affected Areas","m²",10]
["4.9.3","Renew Corroded/Damaged Steelwork (50kg)","kg",50]
["4.9.4","Hp Wash After Spot Blast","m²",400]
[]
[{"v":4.1,"d":"4.10"},"BOAT DECK, SUPERSTRUCTURE, MAIN DECK & BOLLARDS (INC. LADDERS, RAILINGS & VENTS)"]
["4.10.1","Chemically Clean","m²",400]
["4.10.2","Spot Blast Affected Areas","m²",10]
["4.10.3","Renew Corroded/Damaged Steelwork (50kg)","kg",50]
["4.10.4","Hp Wash After Spot Blast","m²",400]
["4.10.5","Prime Affected Areas (Smartpack Red) First Coat","m²",10]
["4.10.6","Prime Affected Areas (Smartpack Grey) Second Coat","m²",10]
[]
[4.11,"WATER LINE TO GUNNNEL (INCLUDING INSIDE BULWARKS)"]
["4.11.1","Chemically Clean","m²",200]
["4.11.2","Spot Blast Affected Areas","m²",10]
["4.11.3","Hp Wash After Spot Blast","m²",200]
[]
[4.12,"WHEELHOUSE SLIDING WINDOWS"]
["4.12.1","Remove Sliding Windows","Each",8]
["4.12.2","Mechanically Descale Affected Areas Of Frames","m²",2]
["4.12.3","Repair Frames (3190MM x 825MM)","Each",8]
["4.12.4","Paint As Per Wheelhouse Paint Specs","m²",2]
["4.12.5","Renew Window Rubbers with Ethylene Propylene Diene Monomer (EPDM) - To Be Tested For Leaks On Completion","Sum",8]
["4.12.6","Refit Locking Mechanisms","Each",32]
["4.12.7","Manufacture And Replace Broken Locking Mechanism As Per Sample","Each",35]
[]
[4.13,"EXHAUST FUNNELS"]
["4.13.1","Wash Down Exhaust Funnels To Remove Salt ( X2)","m²",35]
["4.13.2","Remove Heat Shield & Mechanically Descale Affected Areas Of Exhaust Funnel & Heat Shield","m²",10]
["4.13.3","Wash Out/Degrease Entire Inner Space Of Exhaust Funnels (X 2)","m²",35]
["4.13.4","Retightened All Bolts & Nuts On All Flanges, Mountings And Shock Dampers. (Top & Bottom Spaces)","Sum",2]
["4.13.5","Renew Corroded Steelwork (50kg)","kg",50]
[]
[5,"PAINTING"]
[]
[5.1,"MAST, MONKEY ISLAND & WHEELHOUSE (INC. YARDARMS, LADDERS & RAILINGS)"]
["5.1.1","Prime Affected Areas (Smartpack Red) First Coat","m²",10]
["5.1.2","Prime Affected Areas (Smartpack Grey) Second Coat","m²",10]
["5.1.3","Apply Top Coat As Per Paint Spec Complete 2 Coats","m²",400]
[]
[5.2,"WATER LINE TO GUNNNEL (INCLUDING INSIDE BULWARKS)"]
["5.2.1","Prime Affected Areas (Smartpack Red) First Coat","m²",200]
["5.2.2","Prime Affected Areas (Smartpack Grey) Second Coat","m²",200]
["5.2.3","Apply Top Coat As Per Paint Spec (Black) Complete 2 Coats","m²",450]
[]
[5.3,"HULL (INCLUDING SEA CHESTS)"]
["5.3.1","Apply Primer As Per Paint Spec (90 Aliminium)","m²",750]
["5.3.2","Apply Undercoat (Tie-Coat) As Per Paint Spec (Safeguard Universal Es Plum)","m²",750]
["5.3.3","Apply Antifouling As Per Paint Spec (Seaforce Active Plus Light Red)","m²",750]
["5.3.4","Apply Antifouling As Per Paint Spec (Seaforce Active Plus Dark Red)","m²",750]
["5.3.5","Draught And Plimsol Marks To Be Painted","m²",10]
["5.3.6","Paint Inspector To Oversee Paint Application & Issuing Of Antifouling Certification","Sum",1]
[]
[5.4,"EXHAUST FUNNELS"]
["5.4.1","Apply Full Coat As Per Paint Spec (1000c Aliminium)","m²",35]
["5.4.2","Apply Full Coat As Per Paint Spec (Solvalitt Black)","m²",35]
[]
["SUBTOTAL 3 (excl VAT)"]
[5.5,"ENGINE ROOM FAN SPACES"]
["5.5.1","Spot Blast Affected Area","m²",4]
["5.5.2","Prime Affected Areas As Per Paint Spec","m²",4]
["5.5.3","Apply Top Coat As Per Paint Spec (Hardtop Xp White) Complete ","m²",10]
["5.5.4","Renew Corroded Steelwork (50kg)","kg",50]
["5.5.5","Manufacture Dogs in 316 Stainless Steel And Replace Broken Dogs As Per Sample","Each",15]
[]
[5.6,"EXTRA'S"]
["5.6.1","Removal Of Debris","m²",5]
[]
[6,"TANKS"]
[null,"*Contractor To Provide For Gas Free Certificate Where Required."]
[null,"*All Water Tanks & Void Space Plugs To Be Opened & Replaced On Completion "]
[null,"*All Water Tanks & Void Space Plugs Teflon Plug Washers To Be Replaced"]
[]
[6.1,"FRESH WATER TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.1.1","Fresh Water Tank To Be Drained","Each",1]
["6.1.2","Open Fresh Water Tank And Ventilate","Each",1]
["6.1.3","Fresh Water Tank To Be Hp Cleaned","m²",38]
["6.1.4","Fresh Water Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.1.5","Fresh Water Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.1.6","New Gaskets To Be Made Up","Each",2]
["6.1.7","Fresh Water Manhole Covers To Be Refitted","Each",2]
["6.1.8","Inspect Condition Of Echo Sounder Cable Conduit Inside Tank","Each",1]
["6.1.9","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.2,"FOREPEAK TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.2.1","Forepeak Tank To Be Drained","Each",1]
["6.2.2","Open Forepeak Tank And Ventilate","Each",1]
["6.2.3","Forepeak Tank To Be Cleaned","m²",50]
["6.2.4","Forepeak To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.2.5","Forepeak To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.2.6","New Gaskets To Be Made Up","Each",1]
["6.2.7","Forepeak Tank Manhole Cover To Be Refitted","Each",1]
["6.2.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.3,"AFTPEAK TANK (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.3.1","Aftpeak Tank To Be Drained","Each",1]
["6.3.2","Open Aftpeak Tank And Ventilate","Each",1]
["6.3.3","Aftpeak Tank To Be Cleaned","m²",40]
["6.3.4","Aftpeak Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",10]
["6.3.5","Aftpeak Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",10]
["6.3.6","New Gaskets To Be Made Up","Each",1]
["6.3.7","Aftpeak Tank Manhole Cover To Be Refitted","Each",1]
["6.3.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.4,"DOUBLE BOTTOM FUEL TANKS"]
["6.4.1","Open Double Bottom Fuel Tanks And Ventilate","Each",2]
["6.4.2","Gas Free Certificate To Be Issued Before Entry","Each",1]
["6.4.3","Double Bottom Fuel Tanks To Be Cleaned (X2)","m²",68]
["6.4.4","Double Bottom Fuel Tanks To Be Mechanically Descaled And Primed (1 Coat Tankguard Storage Light Red)","m²",10]
["6.4.5","Double Bottom Fuel Tanks To Be Touched Up As Required (1 Coat Tankguard Storage Light Grey)","m²",10]
["6.4.6","New Gaskets To Be Made Up","Each",2]
["6.4.7","Double Bottom Fuel Tanks Manhole Covers To Be Refitted","Each",2]
["6.4.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.5,"DIRTY OIL TANKS (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.5.1","Dirty Oil Tanks To Be Pumped Out","m²",5]
["6.5.2","Open Dirty Oil Tanks And Ventilate","Each",2]
["6.5.3","Dirty Oil Tanks To Be Cleaned","m²",16]
["6.5.4","Dirty Oil Tanks To Be Mechanically Descaled And Primed (1 Coat Tankguard Storage Light Red)","m²",4]
["6.5.5","Dirty Oil Tanks To Be Touched Up As Required (1 Coat Tankguard Storage Light Grey)","m²",4]
["6.5.6","New Gaskets To Be Made Up","Each",2]
["6.5.7","Dirty Oil Tank Manhole Covers To Be Refitted","Each",2]
["6.5.8","Replace Damaged Studs, As Necessary","Each",6]
[]
[6.6,"VOID SPACE (O² Readings To Be Taken On Every Entry And Log To Be Kept For SAMSA)"]
["6.6.1","Void Space Tank To Be Cleaned","m²",10]
["6.6.2","Void Space Tank To Be Mechanically Descaled And Primed (1 Coat Tankguard 412 Red)","m²",4]
["6.6.3","Void Space Tank To Be Touched Up As Required (1 Coat Tankguard 412 White)","m²",4]
["6.6.4","New Gaskets To Be Made Up","Each",2]
["6.6.5","Void Space Tank Manhole Cover To Be Refitted","Each",2]
["6.6.6","Renew Flexi Hoses (Ø120 X 150mm, 5mm) & Heavy Duty Clamps On Keel Cooler Inside Tank","Each",4]
["6.6.7","Replace Damaged Studs, As Necessary","Each",6]
[]
["SUBTOTAL 4 (excl VAT)"]
[6.7,"ANCHOR AND CHAIN"]
["6.7.1","Anchor And Chain To Be Dropped And Ranged","Sum",1]
["6.7.2","Anchor And Chain To Be Shot Blast If Required","Sum",1]
["6.7.3","Anchor And Chain To Be High Pressure Cleaned","Sum",1]
["6.7.4","Free Up Anchor Chain Swivel","Each",1]
["6.7.5","Chain Thickness Measurements To Be Taken (Submit Report) (5 Spots Per Shackle- 4 Shackles)","Spot",20]
["6.7.6","Anchor To Be Painted (1 Coat \"No Rust\", 1 Coat Red Oxide, 1 Coat Hardtop Black)","Each",1]
["6.7.7","Entire Chain To Be Painted With Boiled Linseed Oil (2 Coats) Allow For Adequate Drying Time Between Coats","Sum",2]
["6.7.8","Chain To Be Remarked (Red & White Paint)","Each",1]
["6.7.9","Chain And Anchor To Be Restowed","Sum",1]
["6.7.10","Spare Anchor To Be Removed, Derusted & Painted. (1 Coat \"No Rust\", 1 Coat Red Oxide, 1 Coat Black)","Each",1]
["6.7.11","Spare Anchor D-Shackle To Be Freed Up","Each",1]
[]
[6.8,"CHAIN LOCKER"]
["6.8.1","Manhole Cover To Be Removed","Each",1]
["6.8.2","Manhole Cover To Be Mechanically Descaled ","m²",0.5]
["6.8.3","Manhole Cover To Be Washed And Painted (Smartpack Red)","m²",1]
["6.8.4","Mud To Be Removed And Disposed Of","m²",1]
["6.8.5","Chain Locker To Be Hp Washed ","m²",4]
["6.8.6","Chain Locker To Be Mechanically Descaled","m²",1]
["6.8.7","Chain Locker To Be Painted Complete  (Smartpack Red)","m²",4]
["6.8.8","Grids To Be Removed, Hp Washed And Painted (Smartpack Red) Then Refitted","Each",4]
["6.8.9","Manhole Cover To Be Refitted With New Gasket","kg",1]
["6.8.10","Renew Corroded Steelwork (50kg)","Each",50]
[]
[7,"DECK WORK"]
[]
[7.1,"ANCHOR WINDLASS x 1"]
["7.1.1","Spot Blast Affected Areas","m²",1]
["7.1.2","Apply Primer As Per Paint Spec  ","m²",2]
["7.1.3","Apply Top Coat As Per Paint Spec (1 Coat  Hardtop As Green/Black )","m²",1]
["7.1.4","Renew All Hydraulic Pipes & Fittings As Necessary","Each",5]
["7.1.5","Service Hydraulic Motor On Deck (Pay Special Attention To Coupling)","Sum",1]
["7.1.6","Service Hydraulic Power Pack (Pay Special Attention To Coupling)","Sum",1]
["7.1.7","Service Control Valve","Each",1]
[]
[7.2,"PORT HOLES x 7"]
["7.2.1","Mechanically Descale Affected Areas ","m²",1]
["7.2.2","Repair Sealing Surface If Necessary","Each",7]
["7.2.3","Paint Sealing Surface & Window Boxes As Per Wheelhouse Paint Spec","m²",1]
["7.2.4","Supply & Renew Rubbers with Ethylene Propylene Diene Monomer (EPDM) - To Be Tested For Leaks On Completion","Each",7]
[]
[8,"MISCELLANEOUS WORK"]
[]
["8.1.1","Budget R100 000 For Unplanned Work Identified After Inspection","Sum",1,{"v":100000,"d":"R100,000.00"}]
["8.1.2","Budget For Skilled Labour ","hrs.",20]
["8.1.3","Budget For Semi-Skiled Labour ","hrs.",20]
["8.1.4","Budget For Machine Shop Cost","hrs.",20]
["8.1.5","Assist CMEO And Voith Technician With Voith Health Check For 4hrs Per Day","Days",2]
["8.1.6","Signage And Stickers To Be Replaced After Painting Completed","Each",100]
["8.1.7","Budget For Skilled Labour Overtime For 3 Saturdays And 3 Sundays for 4hrs Per Day","Days",6]
["8.1.8","Scaffolding","Days",14]
["8.1.9","She File, She Plan And Risk Assessment (On award)","Sum",1]
[]
[8.2,"GENERAL CLEANING"]
["8.2.1","Provide Semi Skilled Labour 8 Hrs For Cleaning And Assisting TNPA Engine Room Staff","Days",10]
[]
[8.3,"METAL WORK"]
["8.3.1","Metal For Repairs","Ton",0.5]
[]
[9,"SUNDRIES"]
[]
[9.1,"DISBURSEMENTS"]
["9.1.1","Travelling Expenses (Monday to Sunday)","Weeks",6]
["9.1.2","Accomodation (Monday to Sunday)","Weeks",6]
["9.1.3","Other Disbursements (Breakdown of details to be included in proposal)","Weeks",6]
[]
["SUBTOTAL 5 (excl VAT)"]
[]
[]
[null,"NB: SUBTOTALS AT THE BOTTOM OF EACH PAGE TO BE CARRIED OVER TO PRICING SUMMARY"]
[]
[null,null,"TASK 2 PRICING SUMMARY"]
[null,null,"Subtotal 1 (excl VAT)",null,"Subtotal 1"]
[null,null,"Subtotal 2\n(excl VAT)",null,"Subtotal 2"]
[null,null,"Subtotal 3\n(excl VAT)",null,"Subtotal 3"]
[null,null,"Subtotal 4\n(excl VAT)",null,"Subtotal 4"]
[null,null,"Subtotal 5\n(excl VAT)",null,"Subtotal 5"]
[null,null,"Total excl VAT",null,"Total excl VAT"]
[null,null,"Add 15% VAT"]
[null,null,"Total incl VAT"]
[null,"NB: TASK 1 AND TASK 2 PRICING SUMMARY TOTALS TO BE CARRIED OVER TO FINAL PRICING SUMMARY"]
[]
[null,"FINAL PRICING SUMMARY"]
[null,"Task 1 Summary (Ex VAT)    :"]
[null,"Task 2 Summary (Ex VAT)    : "]
[null,"Subtotal (Ex VAT)                :            "]
[null,"15% VAT                           : "]
[null,"Total (incl. VAT)              : "]
{"$rows_empty":11}
[null,"Compiled by:                                                                                Supported by:"]
[]
[]
[null,"___________________                                                                 ___________________"]
[null,"Claudette Bailey                                                                            Monde Ngeva"]
[null,"Marine Technical Manager -Engine: Ngqura                                 Marine Technical Manager -Deck: Ngqura"]
[null,"Transnet National Ports Authority                                                  Transnet National Ports Authority"]
[null,"Date:                                                                                               Date:"]
[]
[]
[null,"Recommended / Not Recommended by:"]
[]
[]
[null,"___________________"]
[null,"Xolisile Mfekayi"]
[null,"Marine Operations Manager: Ngqura"]
[null,"Transnet National Ports Authority"]
[null,"Date:"]