NEC3 Engineering & Construction Contract

| Between | NTCSA SOC Ltd (Reg No. 2021/539129/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________) |  |
| for | Security Upgrade of Perimeter fence, Access Control and CCTV System at Simmerpan Complex Insert title of the works |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data [Insert at award stage] | [ ] |
| Part C2 | Pricing Data | [4] |
| Part C3 | Scope of Work | [32] |
| Part C4 | Site Information | [3] |
| CONTRACT No. | [Insert at award stage] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] | [ ] |
| C1.2a | Contract Data provided by the Employer | [16] |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | [ ] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Security Upgrade of Perimeter fence, Access Control and CCTV System at Simmerpan Complex for a period of 24 months

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| Options A | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | Sub total | R [●] |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | ## General |  |  |  |  |
|  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |
|  |  | A: Priced contract with activity schedule |  |  |  |
|  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |
|  | and secondary Options |  |  |  |  |
|  |  | X1: Price adjustment for inflation |  |  |  |
|  |  | X2 Changes in the law |  |  |  |
|  |  | X7: Delay damages |  |  |  |
|  |  | X16: Retention |  |  |  |
|  |  | X18: Limitation of liability |  |  |  |
|  |  | Z: Additional conditions of contract |  |  |  |
|  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |
| 10.1 | The Employer is (Name): | NTCSA SOC Ltd (reg no: 2021/539129/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |
|  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |
| 10.1 | The Project Manager is: (Name) | TBC |  |  |  |
|  | Address | TBC |  |  |  |
|  | Tel | TBC |  |  |  |
|  | Fax | TBC |  |  |  |
|  | e-mail | TBC |  |  |  |
| 10.1 | The Supervisor is: (Name) | TBC |  |  |  |
|  | Address | TBC |  |  |  |
|  | Tel No. | TBC |  |  |  |
|  | Fax No. | TBC |  |  |  |
|  | e-mail | TBC |  |  |  |
| 11.2(13) | The works are | Upgrade, replacement, and integration of Simmerpan complex security of perimeter fences, access control and CCTV systems |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register | Risks to be identified at the project risk meeting |  |  |  |
| 11.2(15) | The boundaries of the site are | The boundaries of the NTCSA property at Simmerpan complex |  |  |  |
| 11.2(16) | The Site Information is in | Part 4: Site Information |  |  |  |
| 11.2(19) | The Works Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |
| 12.2 | The law of the contract is the law of | the Republic of South Africa |  |  |  |
| 13.1 | The language of this contract is | English |  |  |  |
| 13.3 | The period for reply is | 2 weeks |  |  |  |
| 2 | The Contractor's main responsibilities | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |
| 3 | Time |  |  |  |  |
| 11.2(3) | The completion date for the whole of the works is | TBC. |  |  |  |
| 11.2(9) | The key dates and the conditions to be met are: | Condition to be met |  |  | key date |
|  |  | 1 | Security clearance of personnel |  | TBC |
|  |  | 2 | Submission of SHEQ implementation file |  | TBC |
|  |  | 3 | Security & Safety Induction |  | TBC |
| 30.1 | The access dates are: | Part of the Site |  | Date |  |
|  |  | 1 | Simmerpan complex | TBC |  |
| 31.1 | The Contractor is to submit a first programme for acceptance within | 2 weeks of the Contract Date. |  |  |  |
| 31.2 | The starting date is | TBC |  |  |  |
| 32.2 | The Contractor submits revised programmes at intervals no longer than | TBC |  |  |  |
| 35.1 | The Employer is not willing to take over the works before the Completion Date. |  |  |  |  |

| ## 4 | ## Testing and Defects |  |
| --- | --- | --- |
| 42.2 | The defects date is | 52 weeks after Completion of the whole of the works. |
| 43.2 | The defect correction period is | 2 weeks |
| ## 5 | ## Payment |  |
| 50.1 | The assessment interval is | between the 25 day of each successive month. |
| 51.1 | The currency of this contract is the | South African Rand. |
| 51.2 | The period within which payments are made is | 3 weeks. |
| 51.4 | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |
| ## 6 | ## Compensation events |  |
| 60.1(13) | The place where weather is to be recorded is: | Germiston, South Africa |
|  | The weather measurements to be recorded for each calendar month are, | the cumulative rainfall (mm) |
|  |  | the number of days with rainfall more than 10 mm |
|  |  | the number of days with minimum air temperature less than 0 degrees Celsius |
|  |  | the number of days with snow lying at 09:00 hours South African Time |
|  |  | and these measurements: |
|  | The weather measurements are supplied by | The Contractor as verified by the Supervisor. |
|  | The weather data are the records of past weather measurements for each calendar month which were recorded at: | Germiston |
|  | and which are available from: | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |
| ## 7 | ## Title | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |
| ## 8 | ## Risks and insurance |  |
| ## 80.1 | These are additional Employer's risks | 1. Project delays |
|  |  | 2. Force Majeures (Unforeseen & Uncontrollable circumstances) |
|  |  | 3. Cost Overruns |
| ## 9 | ## Termination | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |
| ## 10 | ## Data for main Option clause |  |
| A | Priced contract with activity schedule |  |
| ## 11 | ## Data for Option W1 |  |
| W1.1 | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |
|  | Address | TBC |
|  | Tel No. | TBC |
|  | Fax No. | TBC |
|  | e-mail | TBC |
| W1.2(3) | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |
| W1.4(2) | The tribunal is: | arbitration. |

| W1.4(5) | The arbitration procedure is |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |
| --- | --- | --- | --- | --- | --- |
|  | The place where arbitration is to be held is |  | Johannesburg, South Africa |  |  |
|  | The person or organisation who will choose an arbitrator if the Parties cannot agree a choice or if the arbitration procedure does not state who selects an arbitrator, is |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |
| ## 12 | ## Data for secondary Option clauses |  |  |  |  |
| X1 |  | Price adjustment for inflation |  |  |  |
| X1.1(a) | The base date for indices is |  | [●]. |  |  |
| X1.1(c) | The proportions used to calculate the Price Adjustment Factor are: |  | proportion | linked to index for | Index prepared by |
|  |  |  | 0. [●] | [●] | [●] |
|  |  |  | 0. [●] | [●] | [●] |
|  |  |  | 0. [●] | [●] | [●] |
|  |  |  | 0. [●] | [●] | [●] |
|  |  |  | 0. [●] | [●] | [●] |
|  |  |  | [●] | non-adjustable |  |
|  | Total |  | 1.00 |  |  |
| X2 | Changes in the law |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. only South African law |  |  |
| X7 | Delay damages (but not if Option X5 is also used) |  |  |  |  |
| X7.1 | Delay damages for Completion of the whole of the works are |  | 0.1% per day up to a maximum of 10% contract value |  |  |
| X15 | Limitation of the Contractor’s liability for his design to reasonable skill & care |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |
| X16 | Retention (not used with Option F) |  |  |  |  |
| ## X16.1 |  |  |  |  |  |
|  | The retention percentage is |  | 10% will be retained on each approved Assessment Certificate. |  |  |
| X18 | Limitation of liability |  |  |  |  |
| X18.1 | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: |  | R0.0 (zero Rand) |  |  |
| X18.2 | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: |  | the amount of the deductibles relevant to the event |  |  |
| X18.3 | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to |  | The greater of - the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date. |  |  |

| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design which arise before the Defects Certificate is issued, - Defects due to manufacture and fabrication outside the Site, - loss of or damage to property (other than the works, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |
| --- | --- | --- | --- |
| X18.5 |  | The end of liability date is | (i) 3 (Three) years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |
| Z |  | The Additional conditions of contract are | Z1 to Z15 always apply. |
| Z1 | Cession delegation and assignment |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |

fgdgdfg

| Z2 | Joint ventures |  |
| --- | --- | --- |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |
| Z4 | Confidentiality |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |
| Z7.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4710303126 on each invoice he submits for payment. |  |
| Z8 | Notifying compensation events |  |
| Z8.1 | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |

| Z9 | Employer’s limitation of liability |
| --- | --- |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |
| Z9.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |
| Z10.1 | or had a business rescue order granted against it. |
| Z11 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |
| Z11.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |

| Z12 | Ethics |  |
| --- | --- | --- |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| Affected Party |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |
| Coercive Action |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |
| Collusive Action |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |
| Committing Party |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees, |
| Corrupt Action |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |
| Fraudulent Action |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |
| Obstructive Action |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |
| Prohibited Action |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |
| Z12.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |
| Z12.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |
| Z12.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |
| Z12.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |
| Z13 | Insurance |  |
| Z 13.1 | Replace core clause 84 with the following: |  |

| Insurance cover | 84 |  |
| --- | --- | --- |
|  | 84.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 84.2 | The Contractor provides the insurances stated in the Insurance Table A. |
|  | 84.3 | The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate. |

|  |  | ### INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage to the works, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance. Loss of or damage to Equipment; The replacement cost. Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| --- | --- | --- |
| Z 13.2 |  | Replace core clause 87 with the following: The Employer provides the insurances stated in the Insurance Table B. |
|  |  | #### INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z14 | Nuclear Liability |  |
| --- | --- | --- |
| Z14.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z14.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.3 | Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z14.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z15 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |

| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’srequirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| --- | --- | --- |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z15.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z15.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z15.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z15.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z15.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z15.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z15.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

C1.2 Contract Data

# Part two - Data provided by the Contractor

Notes to a tendering Contractor:

- Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 11.2(8) | The direct fee percentage is | % |
|  | The subcontracted fee percentage is | % |
| 11.2(18) | The working areas are the Site and |  |
| 24.1 | The Contractor's key persons are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | 2 Name: |  |
|  | Job |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |

|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 11.2(3) | The completion date for the whole of the works is |  |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register |  |  |  |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: |  |  |  |  |
| 31.1 | The programme identified in the Contract Data is |  |  |  |  |
| A | Priced contract with activity schedule |  |  |  |  |
| 11.2(20) | The activity schedule is in |  |  |  |  |
| 11.2(30) | The tendered total of the Prices is | (in figures) (in words), excluding VAT |  |  |  |
|  | ## Data for Schedules of Cost Components | Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013). |  |  |  |
| A | Priced contract with activity schedule | Data for the Shorter Schedule of Cost Components |  |  |  |
| 41 in SSCC | The percentage for people overheads is: | % |  |  |  |
| 21 in SSCC | The published list of Equipment is the last edition of the list published by |  |  |  |  |
|  | The percentage for adjustment for Equipment in the published list is | Minus % |  |  |  |
| 22 in SSCC | The rates of other Equipment are: | Equipment | Size or capacity |  | Rate |
| 61 in SSCC | The hourly rates for Defined Cost of design outside the Working Areas are | Category of employee |  | Hourly rate |  |
|  | Note: Hourly rates are estimated ‘cost to company of the employee’ and not selling rates. |  |  |  |  |
|  | Please insert another schedule if foreign resources may also be used |  |  |  |  |
| 62 in SSCC | The percentage for design overheads is | % |  |  |  |
| 63 in SSCC | The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are: |  |  |  |  |

# Part 2: Pricing Data

ECC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A | 2 |
| C2.2 | The activity schedule | Activity Schedule file attached |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for each group of completed activities and each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

# Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

# Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high-level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

# Preparing the activity schedule

Generally it is the tendering Contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

C2.2 the activity schedule

Refer to the activity schedule in excel format named –

.

# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information | 29 |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) | 2 |
|  | Total number of pages | 32 |

# C3.1: Employer’s works Information

Contents

Part 3: Scope of Work………………………………………………………………………………………………….27

C3.1: Employer’s works Information………………………………………………………………………………….28

1	Description of the works	……………………………………………………………………………..………30

1.1	Executive overview…………………………………………………………………………………...………30

1.2	Employer’s objectives and purpose of the works………………………………………………………….30

1.3	Details of the Scope of Work…………………………………………………………………………..……30

1.3.1	CCTV system…………………………………………………………………………………..……30

1.3.2	Simmerpan security perimeter fence………………………………………………………..……31

1.3.3	Alarm system………………………………………………………………………………..………31

1.3.4	Access Control Systems……………………………………………………………………………31

1.3.5	Zero Control Building……………………………………………………………………………….32

1.3.6	System Integration………………………………………………………………………………….32

1.3.7	PSIM interfaces	…………………………………………………………………………..…………32

1.3.8	Trenching and cable routes…………………………………………………..……………………32

1.4	Interpretation and terminology………………………………………………………………………..…..…33

1.5	Definitions……………………………………………………………………………………………………..34

1.6	Role and Responsibilities……………………………………………………………………………………34

1.6.1	Contracts Manager………………………………………………………………………………….34

1.6.2	Architectural Practitioner………………………………………………………………………...…34

1.6.3	Engineering Practitioner	……………………………………………………………………………34

1.6.4	Contractor……………………………………………………………………………………...…….34

2	Management and start up……………………………………………………………………………………36

2.1	Management meetings………………………………………………………………………………..……..36

2.2	Documentation control………………………………………………………………………………….……37

2.3	Health and safety risk management………………………………………………………………………..	40

2.4	Environmental constraints and management……………………………………………………………..	41

2.5	Quality assurance requirements…………………………………………………………………………….	41

2.6	Programming constraints…………………………………………………………………………………….	41

2.7	Contractor’s management, supervision and key people………………………………………….………	42

2.8	Invoicing and payment……………………………………………………………………………………….	42

2.9	Insurance provided by the Employer……………….............................................................................	43

2.10	Contract change management…………………………………………………………………………..	43

3	Engineering and the Contractor’s design…………………………………………………………………..44

3.1	Employer’s design……………………………………………………………………………………………	44

3.2	Parts of the works which the Contractor is to design…………………………………………………….	45

3.3	Procedure for submission and acceptance of Contractor’s design…………………………………….	45

3.4	Other requirements of the Contractor’s design…………………………………………………………...	47

3.5	Use of Contractor’s design………………………………………………………………………………….	47

3.6	Design of Equipment………………………………………………………………………………………...	47

3.7	Equipment required to be included in the works………………………………………………………….	47

3.8	As-built drawings, operating manuals and maintenance schedules……………………………………	48

4	Procurement…………………………………………………………………………………………………..49

4.1	People………………………………………………………………………………………………………….	49

4.1.1	Minimum requirements of people employed on the Site………………………………………..49

4.1.2	BBBEE and preferencing scheme…………………………………………………...……………49

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)………………….…………..49

4.2	Subcontracting………………………………………………………………………………………………..	53

4.2.1	Preferred subcontractors…………………………………………………………………………...53

4.2.2	Subcontract documentation, and assessment of subcontract tenders………………………..53

4.2.3	Limitations on subcontracting……………………………………………………………………...53

4.3	Plant and Materials…………………………………………………………………………………………..	53

4.3.1	Quality………………………………………………………………………………………………..53

4.3.2	Plant & Materials provided “free issue” by the Employer……………………………………….53

4.3.3	Contractor’s procurement of Plant and Materials………………………………………………..53

4.3.4	Spares and consumables…………………………………………………………………………..53

4.4	Tests and inspections before delivery……………………………………………………………………..	53

4.5	Marking Plant and Materials outside the Working Areas………………………………………………...	53

5	Construction…………………………………………………………………………………………………...54

5.1	Temporary works, Site services & construction constraints…………………………………………….	54

5.1.1	Employer’s Site entry and security control, permits, and Site regulations……………………54

5.1.2	Restrictions to access on Site, roads, walkways and barricades……………………………...54

5.1.3	People restrictions on Site; hours of work, conduct and records………………………………54

5.1.4	Health and safety facilities on Site………………………………………………………………...54

5.1.6	Title to materials from demolition and excavation	………………………………………………54

5.1.7	Cooperating with and obtaining acceptance of Others………………………………………….54

5.1.8	Publicity and progress photographs………………………………………………………………54

5.1.9	Contractor’s Equipment…………………………………………………………………………….54

5.1.10	Equipment provided by the Employer…………………………………………………………….55

5.1.11	Site services and facilities………………………………………………………………………….55

5.1.12	Facilities provided by the Contractor……………………………………………………………...55

5.1.13	Existing premises, inspection of adjoining properties and checking work of Others……….. 55

5.1.14	Survey control and setting out of the works……………………………………………………...55

5.1.15	Excavations and associated water control……………………………………………………….55

5.1.16	Underground services, other existing services, cable and pipe trenches and covers……….55

5.1.19	Giving notice of work to be covered up…………………………………………………………...55

5.1.20	Hook ups to existing works…………………………………………………………………...……55

5.2	Completion, testing, commissioning and correction of Defects…………………………………………	56

5.2.1	Work to be done by the Completion Date………………………………………………………..56

5.2.2	Use of the works before Completion has been certified………………………………………..56

5.2.3	Materials facilities and samples for tests and inspections……………………………………...56

5.2.4	Commissioning………………………………………………………………………………………56

5.2.5	Start-up procedures required to put the works into operation………………………………….57

5.2.6	Take over procedures………………………………………………………………………………57

5.2.7	Access given by the Employer for correction of Defects………………………………………..57

5.2.8	Performance tests after Completion………………………………………………………………57

5.2.9	Training and technology transfer	………………………………………………………………….57

5.2.10	Operational maintenance after Completion………………………………………………………57

6	Plant and Materials standards and workmanship…………………………………………………………58

6.1	Investigation, survey and Site clearance………………………………………………………………….	58

6.2	Building works………………………………………………………………………………………………..	58

6.3	Civil engineering and structural works…………………………………………………………………….	58

6.4	Electrical & mechanical engineering works……………………………………………………………….	58

6.5	Process control and IT works……………………………………………………………………………….	58

6.6	Other [as required]…………………………………………………………………………………...……… 58

7	List of drawings……………………………………………………………………………………………….59

7.1	Drawings issued by the Employer………………………………………………………………………….	59

C3.2	Contractor’s Works Information……………………………………………..………………………………60

- Description of the works

  - Executive overview

Simmerpan is a national key point and requires maximum security. The security system at Simmerpan Complex is obsolete and has reached end of life. The physical security system components such as biometric readers, CCTV cameras, public address system, electric fence, lighting within the perimeter and other security systems have reached their end of life as a result they need a replacement with the latest IP based security system to safeguard Eskom assets and ensure maximum security. Other compatible security components that are still under warranty must be reused and incorporated into the new security system

This document must be read in conjunction with the requirements as specified in 240-185000336 Security upgrade of perimeter fence, access control and CCTV system at Simmerpan Complex Technical Specification.

  - Employer’s objectives and purpose of the works

The objective of the works information is to provide a scope of work in which the Contractor shall supply the physical security system equipment to replace the existing one based on the requirements provided by client.

The works must include but not be limited to:

- Supply of rational assessment and rational designs, competent management, supervision and labour, integration, parts and equipment to be installed, materials, consumables and construction equipment, tools, transportation, handling, hauling, stockpiling, loading, testing, certification etc., in all aspects to provide for the execution of the works in accordance with SANS 10137 requirements.

- Supply rational assessment and rational designs, competent management, supervision and labour, integration, parts and equipment to be installed, materials, consumables and construction equipment, tools, transportation, handling, hauling, stockpiling, loading, testing, certification etc., in all aspects to provide for the execution of the works in accordance with SANS 10137 requirements.

- Supply the physical security system equipment to replace the existing one based on the requirements provided by client.

- Providing a competent Supervisor available at the site during the execution of the works. Such Supervisor acts for and represents the Contractor and therefore, all instructions given to him/her by the Employer are binding.

  - Details of the Scope of Work

### CCTV system

- Check that the existing CCTV system and associated equipment can be reused and confirm that maintenance support is available from the OEMs.

- Install latest advanced CCTV cameras (with video motion detection and thermal functionality) including PTZ cameras at recommended locations (Buildings and along perimeter fence).

- Visual inspection of all major equipment components including cabling & connections for signs of deterioration or damage.

- Replace all CCTV system equipment (Monitors, NVR’s, switches, cabling, DVR, etc.) and Physical Access Control infrastructure.

- Check camera functioning and positioning of cameras for appropriate field of view to ensure all blind spots are covered and adjust if necessary.

- Link all CCTV IP cameras to onsite security control building (Zero Control centre) and integrate them to the existing PSIM system.

- Assess recording and playback quality.

- Replacement of all non-functioning security equipment, components, and systems and restore them to operational status.

- There are 11 existing dome cameras installed in the buildings. Test, link and integrate the cameras to the central point.

- Install new advanced dome cameras on the corridors of the buildings.

### Simmerpan security perimeter fence

The Contractor submits detailed design reports and associated drawings containing the following:

- Check that the existing access control system can be reused and confirm that maintenance support is available.

- Verify the connection between the main power supply and the backup battery to ensure sufficient power is being supplied to the panel.

- Visually inspect all field devices for Access Control System

- Walk test devices either manually and/or using a card in the case of readers.

- Test operation of readers.

- Verify the functionality of maglocks and their associated status indication LEDs.

- Verify communication between the server and field devices (including door controllers).

- Check all readers installed on all doors, replace and install new readers where there are none in place.

- Verify correct operation of doors during a fire emergency.

- Test the system for all alarms and ensure that alarms desired are received by the monitoring system.

- Carry out minor adjustments were required.

- Conduct basic re-training of the users on how to use the system more effectively and efficiently.

- The electric fence must be refurbished and rewired (where necessary) in line with 240- 78980848.

- Install an intrusion pre-detection system in line with 240-170000691.

- Install a PA system in line with 240-170000098.

### Alarm system

All buildings shall have an alarm system/panel for aggregation of associated alarms.

### Access Control Systems

Note: The access control system includes Buildings entrances, Boom gates and spikes, Turnstiles, Gates and Roller shutter Doors and biometric readers.

- Check that the existing access control system, including Turnstile, can be reused and confirm that maintenance support is available.

- Check battery backup operation and whether it can be reused or replaced.

- Check all terminations and cables for wear and tear. Reuse where possible and replace where necessary.

- Install boom gates and spikes where required.

- Check that insulation of all cables is in good condition and rectify as required.

- Simulate fault logic to check for alarms and errors.

- Perform any other function to ensure optimal operation of the security systems.

- Inspect, test and replace the existing shutter doors where necessary.

- Installation of emergency buttons (to release the roller shutter doors).

- Upgrade the existing boom gates to the advanced technology.

- Provide workstation (PC) for access control at the reception main gate for visitor management.

- All the laboratories and stores must have a special access control with ability to monitor all the people who visited the laboratory in line with class 3 system coded access card in line with 240- 102220945.

### Zero Control Building

- Remove existing video wall and install new video wall to monitor the security systems on site. The video wall will also be used for monitoring of future sites, as such only a small viewing pane shall be dedicated to Simmerpan site monitoring.

- Install new Network Video Recorders.

- Install access control equipment devices, including servers.

- Install the new servers and backup devices.

- All server configurations must be backed up.

- Check that all the cameras can be monitored and controlled at zero control.

- Upgrade access card printing machines and decoding machines, supply with the latest version.

- Check existing UPS functionality and upgrade or augment if necessary. UPS to be designed for 8 hours standby.

- Interface the installed system to the existing PSIM as per the guideline in Annex D (SOW 240-185000336).

### System Integration

All the systems shall be integrated as per 240-170000096. The system shall achieve the cause and-effect matrix in Annex B at minimum. (SOW 240-185000336).

### PSIM interfaces

The centralized PSIM infrastructure is located at Zero Control in Simmerpan (refer to LAD and BRS: DEM_2412993 & 2425114). For this enquiry the Tenderers are required to supply, install, configure and commission interfaces for integration to the PSIM system already installed at Zero Control in Germiston, refer to Annex D (SOW 240-185000336) for PSIM interfaces integration requirements and guideline.

### Trenching and cable routes

The supplier shall assume that trenching between buildings outlined in Annex E (SOW 240-185000336) will be in place. Additional trenching that will be required will be for around the site perimeter for running of power and communication cables (estimated length is 3 km).

  - Interpretation and terminology

The following abbreviations are used in this Works Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| NTCSA | National Transmission Company of South Africa (a subsidiary of Eskom) |
| OEM | Original Equipment Manufacturer |
| COC | Certificate of Compliance |
| ECC3 | NEC 3 Engineering and Construction contract |
| TRE | Transmission Real Estate |
| NEC | New Engineering Contract |
| ISO | International Organisation for Standardisation |
| SANS | South African National Standards |
| SABS | South African Bureau of Standards |
| QM | Quality Management |
| SHEQ | Safety, Health, Environment & Quality |
| MS | Microsoft |
| CAD | Computer Aided Draughting |
| EMP | Environmental Management Plan |
| LED | Light-emitting diode |
| ITP | Inspection and Test plan |
| SOW | Scope of Works |
| CCTV | Closed-circuit television |
| PTZ | Pan-tilt-zoom |
| IP | IP Internet protocol |
| PA | Public address systems |
| NVR | Network video recorder |
| DVR | Digital video recorder |
| PSIM | Physical Security Information Management |

  - Definitions

| Definition | Description |
| --- | --- |
| Competent person | Person who is qualified by virtue of his education, training, experience and contextual knowledge to make a determination regarding the performance of a building or part thereof in relation to a functional regulation or to undertake such duties as may be assigned to him in terms of the National Building regulations. |
| Rational assessment | Assessment by a competent person of the adequacy of the performance of a solution in relation to requirements including as necessary, a process of reasoning, calculation and consideration of accepted analytical principles, based on a combination of deductions from available information, research and data, appropriate testing and service experience |
| Rational design | Design by a competent person involving a process of reasoning and calculation and which may include a design based on the use of a standard or other suitable document. |

  - Role and Responsibilities

### Contracts Manager

The Contracts Manager is responsible to incorporate the Technical Specification into a contract based on the NEC conditions of contract.

### Architectural Practitioner

The Architectural Practitioners are responsible to review the completed contract to ensure that the Technical Specification has been incorporated correctly.

### Engineering Practitioner

The Engineering Practitioners are responsible to review the completed contract to ensure that the Technical Specification has been incorporated correctly.

### Contractor

The Contractor shall supply the following:

- Performs concept design and submits a concept design report with associated drawings and product data.

- Performs all detail designs required for the supply and installation of the IP based CCTV cameras, access control system, electric fence, PA system, perimeter intrusion pre-detection system, alarm system, turnstiles, access control doors, and intrusion pre-detection system etc., and interfaces to the PSIM system.

- Performs detailed site investigations accompanied by NTCSA representative to evaluate, decommission the current system, determine the fibre path to be used, make the server room ready for installation of the new system, prior to commencement of the work. All the security system components that are compatible with the new systems like fences, cameras, biometric systems etc.

- must be integrated to the new system. Submits report with results of the detailed investigation. The report shall include recommendations for structural modifications, all calculations and equipment models used.

- Implements the necessary modifications and upgrades based on the outcome of the investigations to ensure that the new security technologies are fit for purpose.

- Assess and provides a list of security components that will be scrapped and a list of components that will be reused. Assess and verify all the CCTV camera mounting positions and identify the new poles and mounting positions that will be used. Whenever reinforcing needs to be done, it must be identified in the assessment phase.

- Assess and remove the current install base that will not be part of the new security system.

- Remove the old servers, cabinets and old cable trays, routers, switches, and prepare the server room for the new installation.

- Performs the inspections and remove the old video wall in preparation for the new industrial grade IP based video wall.

- Replace the damaged equipment including all the security related network components at all the gates and replace them with operational equipment.

- Identify all the plug points and ensure that they are in line with the relevant SABS standards.

- Identify the power requirement and ensure that all the main switches and circuit breakers including the surge arrestors are installed to avoid the overloading of the security system. The Electrical certificate of compliance (COC) must be issued after such an investigation and installation.

- Identify, test and ensure that the voltage to the new system is in line with the relevant SABS standards and that the earthing is done in accordance with the Eskom’s requirements.

- All SHEQ requirements are to be adhered to in all activities.

- Contractor to make use of their own Cherry picker (or alternative) for the installation.

- Management and start up.

  - Management meetings

General

Formal routine meetings shall be held throughout the duration of the contract. Should the requirement arise for any other additional meeting such meetings will be schedule accordingly. These meetings provide a forum for review of Contractors’ operations, assessment of progress and schedule, discussion and resolution of problems facing the Contractor and Project Manager and coordination of the activities of all parties concerned.

All safety meetings will be held as per attached SHE specification.

Pre-Construction kick off meeting.

The kick off meeting will take place prior to the Contractor mobilising to site between Employer and the Contractor. This meeting will be held at a location to be determined by the Employer.

Minutes of Meeting

The Project manager will prepare minutes of meeting for all meetings held between Employer and Contractor. The Minutes of Meeting contain all significant aspects of the meeting recorded together with any actions placed and is presented to the Contractor for signature within 7 working days after the meeting. The Contractor needs to sign off the minutes as acceptance within 3 working days. After the Contractor has signed the minutes of meeting, the minutes are to be officially published.

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register, SHEQ, technical clarification and compensation events | To be advised by the Project Manager | Simmerpan and/or Microsoft Teams | Employer, Contractor, Supervisor, and SHEQ and other representatives as required. |
| Overall contract progress and feedback | To be advised by the Project Manager | Simmerpan and/or Microsoft Teams | Employer, Contractor, Supervisor, and other representatives as required. |
| Risk register, SHEQ, technical clarification and compensation events | To be advised by the Project Manager | Simmerpan and/or Microsoft Teams | Employer, Contractor, Supervisor, and SHEQ and other representatives as required. |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or

instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

  - Documentation control

The language of all documentation is in English. The Contractor includes the Employer’s drawing number in the drawing title block. This requirement only applies to design drawings developed by the Contractor and its Sub-Contractors. Drawing numbers are assigned by the Employer as drawings are developed.

Documentation control by the Employer will be done using the NTCSA project group standard documentation management system and using OpenText for electronic filing.

All correspondence from the Employer to the Contractor will be referenced using the following reference.

YYYMMMDD_Type_DocumentTitle_Uniqueidentifier_WBS_Revision.File Extension

The naming convention is explained as follows.

- YYYMMDD refers to the date of the document in the format Year/Month/Date. This is the date of approval if the document is approved. For a new document that has just been created, it will be the date that the document was created on.

- Type refers to the latest folder/collection level in the WBS filing structure in which the document is published.  Hence it refers to the folder/collection location of the documents.  This is in line with the current practice within Tx RE of including the folder name in the naming of files/documents.

The various types to choose from are on the left-hand side as follows:

- Incoming Correspondence				(Communication)

- Outgoing Correspondence				(Communication)

- Presentation						(Meetings)

- Minutes						(Meetings)

- Project Audit Report					(Project Reporting)

- Weekly Report (Historic)				(Project Reporting)

- Technical Report					(Engineering and Design)

- Designs and Proforma Bill of Materials			(Engineering and Design)

- Specification						(Engineering and Design)

- Project Schedule					(Schedule Management)

- Tender						(Commercial Management)

- Contract						(Commercial Management)

- Risk							(Risk Management)

- Insurance						(Risk Management)

- Safety and Health					(SHEQ)

- Environment						(SHEQ)

- Quality						(SHEQ)

- Invoices and Payments				(Financial Management)

- Project Monthly Expenditure/Cash flows		(Financial Management)

- Finalisation						(Financial Management)

- Incoming Transmittal Form				(Transmittals)

- Outgoing Transmittal Form				(Transmittals)

- Site Personnel Details					(Human Resource Management)

- Task Schedule						(Human Resource Management)

- Commissioning and Handover				(Commissioning and Handover)

- Photo							(Photos

- Project Close-out					(Project Close-out

- Revision refers to the revision status of the document that has been approved.

- File Extension refers to the file types such as doc, pdf, tif, xls, ppt, mpp.  This is by default indicated on the file name.

Summary of the documentation required from the Contractor before and during construction which includes the following.

| Document | Before | During |
| --- | --- | --- |
| Programme | x | x |
| Resource Schedule | x | x |
| Health and Safety Plan | x |  |
| Quality Assurance Plan | x |  |
| Method Statements | x |  |
| Material Inventory |  | x |
| Drawing Register | x | x |
| Progress Schedule |  | x |
| Application for payment |  | x |
| Weather Data | x | x |
| Monthly Safety Report |  | x |
| Progress Photographs |  | x |

Contractual correspondence

- Properly compiled letters on official company letter head or forms attached to an email and not as a message in an email itself.

- Alpha numeric identification- reference: Date/ Simmerpan Complex security upgrade/ communication Number

- All correspondence to be addressed to the Project Manager

Contractual forms to be used (To be forwarded to Contractor)

- ECC- Early Warning by Contractor

- ECC- Notification of CE (Compensation Event) by the Contractor

Site Communications

Contractor site diary signed daily by the Supervisor.

Contractor daily site diary (Minimum requirements on Contractor daily Site Diary are):

Contract No.

Date

Work hours- Start, Finish and Overtime

Rainfall (mm)

Temperature

Visitors to site

Contractor employees on site and description (site Agent, Foreman, Skilled, Etc)

List of Plant and Equipment

Brief description of the day’s activities

Toolbox talk topic.

Daily site diary should be signed daily by the Employer- Site manager/ Supervisor and Contractor-Contract Manager/ Site Agent

Daily Contractor’s attendance registers to be attached to the daily site diary.

Site Instructions issued by the Supervisor.

Site Memorandums addressed to the Supervisor.

  - Health and safety risk management

In addition to the requirements of the laws governing health and safety, NTCSA may have some additional requirements particular to the works and the Working Areas for this contract.  The text below provides for these being attached as an Annexure to this Works Information.

The Contractor shall comply with Issued Safety, Health and Environmental Specification for the Security Upgrade of Perimeter fence, Access Control and CCTV System at Simmerpan Complex contained in Annexure (SHE Specification 559-1177047958) to this Works Information and other applicable legal requirements.

The Contractor shall ensure SHEQ department approve the safety file before commencement of work and 37.2 agreement are signed by both parties.

The Contractor must ensure that all his personnel attend a health and safety induction course prior to starting with their wake. The induction course can, on request, be provided by Employer and will be valid for the duration of the services.

Safety risk management has the right and authority to visit and inspect the Contractor’s workplace on site establishments to ensure that tools, machinery and equipment comply with the minimum safety requirement.

The Employer’s representative is entitled to instruct the Contractor to stop work, without penalty to the employer, while the Contractors’ personnel failed to comply with Eskom Life Saving Rules, procedures and standard and other legal requirements contravene health and safety regulations. The Employers representative is entitled to cause the Contractor to discipline his employees and to conduct a disciplinary action and submit a report to the employee representative. The Contractor shall implement additional health and safety precautions when necessary.

The Contractor provides all his personnel with the required personal protective equipment.

Risk assessment, Pre-job briefs, post-job briefs and job observation will be conducted for all jobs.

The Employer follows an accident prevention policy that includes the investigation of all incidents involving personnel and property. This is done with the intention of introducing control measures to prevent a recurrence of the same incident. The Contractor is expected to fully cooperate to achieve this objective. The Employers representative must be informed immediately of any incident and any damage to property or equipment may be reported to the Employers representative within 24 hours

The Contractor complies with the occupational health and Safety Act, 1983, and regulations the act and all safety procedures issued by the Employer. The Contractor must furthermore comply with the employer safety health and environmental requirements for Contractors.

The Contractor ensures all personnel are provided with risk based personal protective equipment for free of charge and with company logo.

The Contractor will not be allowed to transport any of its workers in open vehicle to and from side as prescribed in the Eskom NTCSA safety policy.

The Contractor shall adhere to Eskom lifesaving rule.

  - Environmental constraints and management

The Contractor to have an Environmental Management System in place that will ensure that the requirements are effectively implemented and managed.

The Contractor is required to ensure that all goods, services or works supplied in terms of the contract conform to all applicable environmental legislation.

The Contractor to have an environmental management system in place that will ensure that the requirements of the environmental management plan are effectively implemented and managed.

Campsite establishment and de-establishment are to be managed in accordance with specification.

The layout should be such that it facilitates a circular traffic route that eliminates the need to reverse when loading and off-loading.

The Contractor complies with the environmental criteria and constraints stated in Annexure (SHE Specification 559-1177047958)

  - Quality assurance requirements

The Contractor complies with the quality criteria stated in the 240-105658000 Supplier Quality Management Specification attached to this Works Information. The Contractor is to provide a quality inspection and test plan for the design, manufacture, delivery, and installation as stated in the Scope of Work, for approval.

  - Programming constraints

Tenderers will be evaluated with due consideration to the resources (both personnel and equipment) committed to the project as indicated in the tender programme. All proposed Subcontractors and Suppliers are to be identified at tender stage and will be included in the evaluation process.

The programme is to be submitted for acceptance in accordance with Core Clause 31 in the ECC3, in terms of which resources to complete each activity must be clearly identified. The programme is to be submitted within two weeks of the starting date. It is suggested that Gannt or bar chart formats be used for project planning, while progress graphs/schedules be submitted at monthly meetings to monitor progress.

The programme is to include the following information.

- Method statements which identify the equipment and other resources which the Contractor plans to use for the execution of the various activities of the project.

- Planned sectional completion dates as required as well as the completion date for the whole of the works.

- The order and timing of the operations which the Contractor plans to do in order to provide the works.

provisions for:

- Float

- Time risk allowances

- Health, Safety and Quality requirements

- Environmental compliance requirements

The Contractor submits the first programme to the Project Manager for acceptance within two (2) weeks of the starting date. The programme must be in Primavera or Microsoft Project format.

The Contractor revises the programme as required in accordance with Core Clause 32 of ECC3. Each time the programme is revised, the Contractor is to submit a revised forecast rate of invoicing to the Project Manager.

  - Contractor’s management, supervision and key people

The Contractor submits an organogram which clearly indicates the people resources that will be utilised for this project. The organogram must clearly indicate lines of authority as well as lines of communication.

Site staff as well as head office staff must be indicated. It must state any additional constraining requirements on Contractor’s supervision and key people that are not already stated in other sections such as for Health and Safety. The Person carrying out and signing off any designs and installation needs to be a Competent Person with the required professional registration.

  - Invoicing and payment

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor addresses the tax invoice to NTCSA SOC Ltd and include on each invoice the following information:

- Name and address of the Contractor and the Project Manager;

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4710303126;

- Description of service provided for each item invoiced based on the Price List;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

- NTCSA order number must be clearly indicated on the invoice with the line number on the order for billing.

- Only PDF invoices must be submitted.

- Each PDF file should contain one invoice, one debit, and credit note only as NTCSA’s SAP system does not support more than one PDF being linked into workflow at a time.

- Only one PDF file per email (one invoice or debit note or credit note).

- Send all invoices in PDF straight from your system to an NTCSA email address (see the email address below).

- When it comes to foreign invoices, suppliers will be required to physical deliver the hard copies of original documents to the respective documentation management centers – though invoices emailed. NTCSA is still seeking clarity from the South African Reserve Bank for foreign invoices and currency. Current requirements are that these manual invoices should be submitted. Invoice copy can be sent to the email address indicated below.

- All submitted invoices electronically must comply with the Tax Requirements.

- If there is a Cost Price Adjustment on the invoice, NTCSA recommends separate invoice for CPA to avoid delays on payment, if there are issues for the CPA.

- Introduction of electronic invoicing does not guarantee payment but will ensure visibility of all invoices and ensure that no invoices get lost. If the goods receipt is not done, the invoice will be parked, and the system will automatically send an email to the end user to do good receipt. This is also tracked by NTCSA through the park invoice report.

- The Contractor can request a park invoice report from the Finance Shared Services (FSS) contact centre which can then be followed up and corrected.

- The Contractor is welcome to forward the details of invoices corrected to the FSS contact centre.

- All invoices for payment must be submitted to invoicesntcsalocal@ntcsa.co.za.

  - Insurance provided by the Employer

Insurance related queries for this project can be addressed to the Project Manager who will then refer the query to the applicable NTCSA specialist with regards to insurance matters for this project. The insurance policy provided by the Employer will be dealt with as specified in Clause 86.1.

  - Contract change management.

This is not applicable.

- Engineering and the Contractor’s design

  - Employer’s design

Employer’s operating philosophy / user requirement specification (URS) / performance specification to which the Contractor is to comply when he is required to design the works. Refer to Technical Specification – 240-185000336.

- Overview of functional specification

- Scope of work

- High Level Integration

    - Local vs remote monitoring and control capabilities

    - Software and network config files.

    - Cause and effect matrices (e.g. if alarm on fence, lights and image sent to control)

- System Architecture (to include Logical and physical design, networking and bandwidth requirements, Information flow, Physical security information management, User access profile management and enrolment process, cyber security controls e.g. firewalls, DMZ, System support remote access authentication etc.).

- Lifespan of System and product software versions (include 10-year life span support).

- Recommended Maintenance (Procedures, Spares and FMECA- Failure mode effects and criticality analysis, tools and test equipment, training requirements-engineering and field operations)

- System commission and acceptance testing procedure (commissioning results to be provided prior to system handover).

- Annex A – Drawings

    - Site layout

    - CCT Field of view

    - Site Security Zoning

    - System Configuration

    - Security LAN and Fibre Reticulation

    - Cable and trench layout

    - Power reticulation

    - Control Panels

    - Electric fence and energizers

    - Security control room drawings/configuration

    - Perimeter intrusion pre-detection system

    - Access Control system

    - PA system

- Annex B – Equipment Specifications and data sheets

- Access Control system including (at minimum)

        - Access Controlle

        - Card Readers

        - Biometric Readers

        - Maglocks

        - Break Glass Units

        - Door Contacts

- Perimeter intrusion pre-Intrusion Detection system

- Camera Surveillance System including (at miimum)

        - Cameras

        - Video Recorders

        - Client Workstations

- Alarm System (if it is a separate controller)

- Lighting Control interfaces

- Electric fence and Energizer

- PSIM interfaces

- Data storage equipment

- Turnstiles

- Boom gates

- Gate motors

- Power Supplies (including UPS sizing)

- Network Switches

- Fibre Converters

- Enclosures & Racks

- PA systems

- Security LAN and firewalls

- Annex C- Bill of Materials

  - Parts of the works which the Contractor is to design

Please refer to technical specifications

  - Procedure for submission and acceptance of Contractor’s design

All project documents are submitted to the Project Manager with a transmittal note according to Project / Plant Specific Technical Documents and Records Management Work Instruction (240-76992014). In order to portray a consistent image, it is important that all documents used within the project follow the same standards of layout, style and formatting as described in the Work Instruction.

In addition, the Contractor adheres to the following:

- Project Handover Documentation Management Procedure (240-66920003).

- Project Documentation Deliverable Requirement Specification (240-65459834).

- Technical Documentation Classification and Designation Standard (240-54179170)

The Contractor submits all documentation to the Project Manager as well as the Project’s Documentation Centre as follows:

- Electronic copies are submitted to NTCSA Documentation Centre through SharePoint transmittal site that will be provided during contract award.

- Hard copies are submitted to the Project Manager accompanied by a Transmittal Note.

The Contractor submits concept and detailed design reports and associated drawings containing the following:

    - Concept Design

The Contractor shall during tendering submit a concept design report and associated drawings as it will be applied to a generic site. The concept design shall at minimum contain details listed in Annex C (240-185000336). In addition to the details in Annex C (240-185000336), the concept design report shall cover the following information (at minimum):

- Details regarding the modifications required to the building, poles and fence, structural and other.

- Specifications, codes and standards used in the designs.

- Loads and forces.

- Design criteria/ parameters used.

- Design Philosophy.

- Materials used.

- All assumptions made.

- All software input and output files incl. design models; and

- All references/ sources of information used.

- Concept layout drawings indicating equipment placement.

    - Detail design

The Contractor shall after contract award submit a detailed design and associated drawings as it will be applied to the applicable site. The detailed design shall at minimum contain details listed in Annex C (240-185000336). The detailed design shall be based on the scope or work outlined above and the following documents:

- 240-86738968: Specification for Integrated Security Alarm.

- 240-91190304: Specification for CCTV Surveillance with Intruder Detection.

- 240-102220945: Specification for Integrated Access Control System (IACS) for Eskom

- Sites.

- 240-170000096: Rev 1 Physical Security Integrated Standard.

- 240-170000614 Cyber Security Controls Guide for Physical Security Systems.

- 240-78980848: Specification for Non-Lethal Energized Perimeter Detection System.

- (NLEPDS) Electrical Components (excludes civil components).

- 240-170000098 Security Public Address Systems for Substations and Telecoms sites.

- 240-170000691 Standard for Intrusion pre-detection systems used at Eskom sites.

- 240-170000723 Generic technical requirements for physical security technologies contract.

- 0.54/8282 rev 5 Non-lethal fence Plan, sections and details.

The Employer requires a period of one (1) week for the review of the Concept design and two (2) weeks for the review of the Detail Design.

The following documents are to be supplied by The Contractor within the pre-determined schedule:

- Functional description of the system

- Operation and Maintenance Instruction manual.

- Original Manufacturers product documents.

- Commissioning procedure

- Handover certificates

- Inspection and Test Procedures

- And other project related documents

  - Other requirements of the Contractor’s design

Any proposed design change by Contractor must be forwarded to the Project Manager for approval prior to the commencement. All Design change management are performed in accordance to the latest revision of the Eskom Project Engineering Change Management Procedure (240-53114026).

This should be done 14 days prior to the Contractor’s planned start date. The Project Manager will liaise with the applicable engineering representative and manage the process of approval. The Contractor will be notified in writing by the Project Manager when the proposal has been approved and when work can commence.

  - Use of Contractor’s design

Upon acceptance of the Contractor’s designs, copyright will pass to the Employer.

  - Design of Equipment

Contractor submits particulars of the design of an item of equipment for the Project Manager for acceptance if the Project Manager instructs them to.

  - Equipment required to be included in the works

There is no specific requirement for specialist equipment to be provided by the Contractor for the works. The Contractor must supply all equipment he deems necessary to complete the works.

Accredited access equipment personnel:

The Contractor indicates the method of accessing certain areas and the equipment to be used, especially for accessing work areas above ground level.

Should scaffolding be used by The Contractor, The Contractor to use suitably qualified personnel for the erection, use, dismantling and inspection of access scaffolding. The Contractor shall comply with SANS 10085

Use of all other access equipment shall be subject to approval by the Employer prior to such equipment being allowed on site.

Personnel handling and inspecting equipment shall be in possession of the respective valid accredited training certificates for the respective equipment.

Personnel handling and inspecting equipment shall have valid accredited training certificates.

  - As-built drawings, operating manuals and maintenance schedules

As-built drawings required, must be marked up by the Contractor in conjunction with the Engineer. The final completion certificate for the works will not be issued by the Project Manager unless all as-built drawings have been received if required. The Contractor should take note that the 50% retention release is subject to the Employer having received the As-built drawings and maintenance manual.

As built/Floor plan drawings supplied by The Contractor to the Employer for all areas where changes have applied.

Terminal equipment locations and proposed cable routes shall be indicated on these drawings.

The Contractor uses red lines on drawings to show areas as per the Eskom convention for marking up drawings.

Operating manuals to supplied by the Contractor to the Employer and offer training.

- Procurement

Contractors refers to the NTCSA Holdings Standard Conditions of Tender, Johannesburg 2007 as included elsewhere in this document.

  - People

### Minimum requirements of people employed on the Site

    - Police clearance is required for personnel that the Contractor utilises on the site as the site location is a National Key Point due to its proximity to the National Control Centre.

### BBBEE and preferencing scheme

NB: The following documents are required to claim preference points:

-Valid B-BBEE certificate issued by a SANAS accredited verification agency / sworn affidavit / CIPC affidavit

-“proof of B-BBEE status level of contributor” means-

(a) the B-BBEE status level certificate issued by an authorised body or person; or

(b) a sworn affidavit as prescribed by the B-BBEE Codes of Good Practice; or

(c) any other requirement prescribed in terms of the Broad-Based Black Economic

Empowerment Act.

Transformation – BBBEE Improvement or Retention Plan

Transformation remains an area of focus, where Eskom continuously strives to align itself with national transformation imperatives to unlock growth, drive industrialization, create employment and contribute to skills development.

Eskom encourages its suppliers to constantly strive to improve their B-BBEE rating. Whereas Tenderer/s will be allocated points in terms of a preference point system based on specific goals, NTCSA also requests that tenderer/s submits their B-BBEE improvement or retention plan within 30 days of signing the contract.

Tenderer/s are therefore requested to indicate the extent to which they will maintain (only if the respondent is a Level 1) or may improve/maintain their B-BBEE status over the contract period if their B-BBEE status is level 2 or 3. Tenderer/s with a B-BBEE status level 4 at the time of contract award, shall migrate and achieve as a non-negotiable a milestone of B-BBEE Level 3 by the end of the first year of the contract and thereafter improve their B-BBEE status level or migrate by one level higher.

Tenderer/s with a B-BBEE recognition status of Level 5 to Level 8 or non-compliant at the time of contract award, shall migrate and achieve as a non-negotiable a milestone of Level 4 by the end of the first year of the contract and thereafter improve at least one B-BBEE Level higher of each year from the second year of the contract.

Tenderer/s are requested to submit their B-BBEE Improvement Plan as an essential document within 30 days of signing the contract.

NB: A valid B-BBEE certificate or Sworn Affidavit is a condition for contract award, if your company’s annual Total Revenue is R10 Million or less you qualify as an Exempted Micro Enterprise therefore you can submit Sworn Affidavit. If your annual Total Revenue is R50 Million or less, you qualify as Qualifying Small Enterprise and must comply with all of the elements of QSE score card relevant to your sector unless an entity is at least 51% Black owned you are required to obtain a Sworn affidavit. If your Annual Total Revenue is above R50m you need to submit a Valid B-BBEE certificate.

    - Supplier Development Localisation and Industrialisation

Section 1: Objective Criteria:

NB: The following documents are required to claim preference points:

-Valid B-BBEE certificate issued by a SANAS accredited verification agency / sworn affidavit / CIPC affidavit

-“proof of B-BBEE status level of contributor” means-

(a) the B-BBEE status level certificate issued by an authorised body or person; or

(b) a sworn affidavit as prescribed by the B-BBEE Codes of Good Practice; or

(c) any other requirement prescribed in terms of the Broad-Based Black Economic

Empowerment Act.

Section 2: Other SDL&I Objectives in line with RDP Goals

Designated sectors

| Commodity | Local Content Threshold – 100% |
| --- | --- |
| Wires | 100% |
| Cables | 90% |

Note: SBD 6.2 Declaration Form and Annexure C, D&E are mandatory for contract award.

CIDB level

The required CIDB grading is 6EB or higher.

Section 3: SDL&I Objectives in line with Reconstruction and Development Programme (RDP) Goals

Tenderers who complete and submit the objectives as required, but who do not meet NTCSA’s targets, will not be disqualified. SDL&I objectives do not form part of scoring, but commitments will form part of contractual obligations.

Transformation – BBBEE Improvement or Retention Plan

Transformation remains an area of focus, where NTCSA continuously strives to align itself with national transformation imperatives to unlock growth, drive industrialization, create employment and contribute to skills development.

NTCSA encourages its suppliers to constantly strive to improve their B-BBEE rating. Whereas Tenderer/s will be allocated points in terms of a preference point system based on specific goals, NTCSA also requests that tenderer/s submits their B-BBEE improvement or retention plan within 30 days of signing the contract.

Tenderer/s are therefore requested to indicate the extent to which they will maintain (only if the respondent is a Level 1) or may improve/maintain their B-BBEE status over the contract period if their B-BBEE status is level 2 or 3. Tenderer/s with a B-BBEE status level 4 at the time of contract award, shall migrate and achieve as a non-negotiable a milestone of B-BBEE Level 3 by the end of the first year of the contract and thereafter improve their B-BBEE status level or migrate by one level higher.

Tenderer/s with a B-BBEE recognition status of Level 5 to Level 8 or non-compliant at the time of contract award, shall migrate and achieve as a non-negotiable a milestone of Level 4 by the end of the first year of the contract and thereafter improve at least one B-BBEE Level higher of each year from the second year of the contract.

Tenderer/s are requested to submit their B-BBEE Improvement Plan as an essential document within 30 days of signing the contract.

NB: A valid B-BBEE certificate or Sworn Affidavit is a condition for contract award, if your company’s annual Total Revenue is R10 Million or less you qualify as an Exempted Micro Enterprise therefore you can submit Sworn Affidavit. If your annual Total Revenue is R50 Million or less, you qualify as Qualifying Small Enterprise and must comply with all of the elements of QSE score card relevant to your sector unless an entity is at least 51% Black owned you are required to obtain a Sworn affidavit. If your Annual Total Revenue is above R50m you need to submit a Valid B-BBEE certificate.

B-BBEE requirements

All tenderers must at a minimum maintain their B-BBEE status throughout the contract period.

Skills Development

Tenderers are required to propose against the following training initiatives:

| Skills Type | NTCSA Target | Supplier's Proposal |
| --- | --- | --- |

Job Opportunities:

Tenderers are required to submit proposals for the type and number of jobs that will be created and retained in South Africa as a direct result of being awarded a contract.

| Proposed number of Jobs to be created | Number of Jobs to be Retain |
| --- | --- |

Note:

Preference must be given to local community to avoid disruption of the project.

Qualifying candidates shall be currently unemployed graduates from university, Technical and Vocational Education and Training (TVET) Colleges and/or Matriculates. The skills development candidates shall be representative of the population demographics of South Africa and be sourced from within the vicinity of the station

Procurement spends on entities with a minimum 51% black ownership

The winning tenderer is encouraged to procure/spend on designated groups on the following paid invoices for both:

- the indirect expenses (e.g. overheads) on goods and services supplied to the contractor/supplier by designated groups; and

- direct spend on goods and services supplied by the subcontractors for the execution of the scope of work.

Activities, as a proportion of the local procurement content, which may be subcontracted to designated black owned enterprises must be submitted in a table below.

| Procurement from Designated Group | NTCSA Target | Tenderer Proposal |
| --- | --- | --- |
| Black Owned | 4.0% |  |
| Black Women Owned | 3.0% |  |
| Black Youth Owned | 2.0% |  |
| Black Persons with Disability | 1.0% |  |

Section 4: SDL&I penalty and performance security:

NTCSA will apply a penalty of 2.5% of the Contract Value for failure to meet SDL&I obligations.

For the duration of the contract, NTCSA will retain 2.5% of every invoice (excluding VAT) as security for the fulfilment of all SDL&I Obligations. The retained amounts shall only be released to the Contractor upon:

- NTCSA receives the SDL&I progress report/s from the Contractor.

- Fulfilment of all SDL&I obligations by the Contractor.

- Submission of an approved compliance report by SDL&I Department.

Section 5: Reporting and Monitoring:

- The Suppliers shall on a quarterly basis submit a report to NTCSA in accordance with Data Collection Template on their compliance with the SDL&I obligations described above.

- NTCSA to review the SDL&I reports submitted by the suppliers within 30 (thirty) days of receipt of the reports and notify the Suppliers in writing if their SDL&I obligations have not been met.

- Upon notification by NTCSA that the Suppliers have not met their SDL&I obligations, the suppliers shall be required to implement corrective measures to meet those SDL&I obligations before the commencement of the following report, failing which Retention clauses shall be invoked.

- Every contract shall be accompanied by the SDL&I Implementation Schedule, which must be completed by the suppliers and returned to SDL&I representative for acceptance 28 days after contract award. This will be used as a reference document for monitoring, measuring and reporting on the supplier’s progress in delivering on their stated SDL&I commitments.

  - Subcontracting

### Preferred subcontractors

The Employer does not have any preferred Sub-Contractors that the Contractor must use. The Contractor must source products that are to specification. The Contractor to notify NTCSA in the event of using any Sub-Contractor. A Sub-Contractor cannot subcontract work to another Sub-Contractor.

### Subcontract documentation, and assessment of subcontract tenders

The Employer expects the Contractor to manage his Sub-Contractors in the same way that the Employer manages the Contractor. Special attention must be given to the management of the Sub-Contractors SHEQ compliance in the same way that the Employer manages the Contractor.

It is recommended that the Contractor make use of the NEC contracting system to ensure a contracting standard throughout.

The Employer to approve all Sub-Contractors and suppliers that the Contractor employs for this contract.

### Limitations on subcontracting

Sub-contracting will be allowed, and list of proposed Sub-Contractors must be included in the tender document as part of technical returnable. All Sub-Contractors to be approved by the Project Manager prior to appointment by the Contractor.

  - Plant and Materials

### Plant & Materials provided “free issue” by the Employer

No equipment or materials are provided “free issue” to the Contractor for this contract. All equipment and material necessary for the works are to be provided by the Contractor.

### Contractor’s procurement of Plant and Materials

All transportation to site of equipment and material required for this project will be by means of road transport. The Contractor must familiarise himself with the road conditions to Simmerpan complex.

manage such storage areas as to ensure safety compliance as well as security of any equipment and material.

### Spares and consumables

Replacement components are to be readily available. The Contractor guarantees that all components are available in South Africa in the foreseeable future for at least 20 years.

  - Tests and inspections before delivery

Not Applicable.

Material must be off loaded and stored separately in areas allocated for this purpose. The Contractor must

  - Marking Plant and Materials outside the Working Areas

There are no requirements for the “Marking” of equipment and materials outside the Working Areas

- Construction

  - Temporary works, Site services & construction constraints

### Employer’s Site entry and security control, permits, and Site regulations

The Employer will provide access control for the Site. All persons and vehicles entering or exiting Simmerpan complex may be subjected to searches, and the Employer reserves the right to refuse entrance to the site, to any person not meeting security and/or access requirements. From time to time, and as required, the Employer will issue policies and procedures regarding Site security and access control. These policies and procedures shall be strictly adhered to by the Contractor. The Employer shall be entitled, at his discretion, to amend or relax the Site security and/or access requirements to deal with emergencies or other circumstances justifying such amendment or relaxation. Any breach of security must be reported to the Employer immediately.

### Restrictions to access on Site, roads, walkways and barricades

The Contractor’s Personnel and any visitors on the Site must be in possession of a valid identification card supplied by the Contractor.   The Employer furthermore may remove from the Site (or from any other places, if any, as may be specified under the Contract as forming part of the Site) any person who ceases, for any reason, to have legitimate business thereon.

### People restrictions on Site; hours of work, conduct and records

The Contractor must clearly indicate any shift work or extended working hour work that is required in order to meet with the required completion and milestone completion dates of the contract. The Project Manager and SHEQ manager’s permission must be obtained prior to working such hours. Permission will only be granted if the longer hours worked have been accepted in writing by the Department of Labour.

### Health and safety facilities on Site

The Contractor must refer to:  Safety, Health and Environmental Specification for the works.

### Title to materials from demolition and excavation

The removal and disposal of any old material and equipment from site is the responsibility of the Contractor.

### Cooperating with and obtaining acceptance of Others

Except as directed by the Employer, the Contractor shall in no way interfere with, remove, adjust or operate equipment and/or materials of or being supplied or operated by Other Contractors, should third parties be in the same work environment. The Contractor shall, at all times, keep the work of Other Project Contractors free from damage.

### Publicity and progress photographs

This is not applicable.

### Contractor’s Equipment

The Contractor keeps a daily record of all equipment and machinery on site. The information must be captured in such a way that differentiation is made between hired and owned equipment. The record must also clearly indicate when equipment is working and who the operator of the said equipment was for the recorded shift. These records are verified and signed off by the Engineer on a daily basis and this document must be available on site at all times.

The Contractor provides the following to complete the Works:

- All scaffolding required

- Any equipment necessary to complete the Works

- Lifting facilities

- Man-power required to temporarily move stored equipment and material when painting and preparing walls and floors

The Contractor supplies, installs, maintains, and removes all temporary construction facilities and utilities necessary to provide the Works.

### Equipment provided by the Employer

No equipment will be provided by the Employer. The Contractor provides all equipment and tools required to complete the works.

### Site services and facilities

The Employer, at his expense, arranges for, develop and maintain the various facilities and services at or near the Site, as applicable. The services and facilities provided by the Employer are listed below:

•	Electricity;

•	Water supply; and

•	Sanitary Services.

### Facilities provided by the Contractor

Contractor is responsible for site establishment and de-establishment at project completion.

Contractor to provide containers for storage of material and offices.

Contractor will provide all material and equipment.

Contractor to provide generator in case of outages/loadshedding

### Existing premises, inspection of adjoining properties and checking work of Others

The Contractor surveys the existing equipment before any repairs, procurement, fabrication or installation.

### Survey control and setting out of the works

Not Applicable

### Excavations and associated water control

Not Applicable

### Underground services, other existing services, cable and pipe trenches and covers

Refer to technical specification.

### Giving notice of work to be covered up

### The Contractor must refer to:  Safety, Health, and Environmental Specification for the works.

### Hook ups to existing works

### The Contractor must refer to:  Safety, Health, and Environmental Specification for the works.

  - Completion, testing, commissioning and correction of Defects

### Work to be done by the Completion Date

On or before the Completion Date the Contractor shall have done everything required to Provide the Works except for the work listed below which may be done after the Completion Date but in any case, before the dates stated.  The Project Manager cannot certify Completion until all the work except that listed below has been done and is also free of Defects which would have, in his opinion, prevented the Employer from using the works and Others from doing their work.

|  | Item of work | To be completed by |
| --- | --- | --- |
|  | All as-built drawings | Within one week after Completion |

### Use of the works before Completion has been certified

### Clause 35.2 in ECC3 provides that the Employer may use any part of the works before Completion has been certified but if he does so he takes over the part of the works except if the use is for a reason stated in the Works Information.

### Materials facilities and samples for tests and inspections

Any samples that must be provided are to be provided by the Contractor once the contract has been awarded.

The Contractor must supply materials facilities and samples for tests as prescribed in the relevant

SANS practice code.

The Contractor includes the following on his ITP to be witnessed by the Engineer:

- Acceptance of all relevant documents and drawings.

- Inspection of modifications before the installation

- Final inspection before the handover to the Employer.

- Inspection to ensure that all required records are available.

### Commissioning

The Contractor does comprehensive pre-commissioning, commissioning as well as quality monitoring on all systems and is to provide the following:

- On completion of the works, full testing shall be carried out on the installation to ensure compliance to all relevant standards.

- The Contractor shall provide all instruments and equipment required for commissioning and testing of the installations at completion.

- On completion of the installation, an Electrical Certificate of Compliance (CoC) shall be issued for the

- installation in terms of the Occupational Health and Safety Act, (OHS Act 85 of 1993).

- The competent person shall perform illumination measurements. Illumination measurement reports shall be produced and submitted to the Employer. Measurements shall be performed once the installation has been completed.

- The Contractor shall be responsible to replace faulty equipment for the duration of the offered guarantee periods

### Start-up procedures required to put the works into operation.

There are no requirements or start-up procedures required from the Contractor to put the works into operation.

### Take over procedures.

Take over of the Works shall be in accordance of NEC ECC3 hand over certification and projects execution hand over document

The Contractor advises the Project Manager when the works will be available for final inspection and provide assistance where required.

By completion date in the contract data, the Contractor shall complete all work required. The Project Manager prior to release of retention money shall approve all the completed works. The Contractor maintenance the works until the defects date.

### Access given by the Employer for correction of Defects

Clause 43.4 of the NEC will apply.

### Performance tests after Completion

This is not applicable.

### Training and technology transfer

Compliance to the SD&L requirements

### Operational maintenance after Completion

This is not applicable.

- Plant and Materials standards and workmanship

  - Investigation, survey and Site clearance

Refer to technical specification.

  - Building works

This is not applicable.

  - Civil engineering and structural works

This is not applicable.

  - Electrical & mechanical engineering works

Refer to technical specifications 240-185000336 for requirements.

  - Process control and IT works

Refer to technical specifications 240-185000336 for requirements.

  - Other [as required]

None

- List of drawings

  - Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

Note:  Some drawings may contain both Works Information and Site Information.

| Drawing number | Revision | Title |
| --- | --- | --- |
| N/A |  |  |

# C3.2	Contractor’s Works Information

This section of the Works Information will always be contract specific depending on the nature of the works. It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1. Typical subheadings could be a) Contractor’s design b) Plant and Materials specifications and schedules c) Other

# Part 4: Site Information

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page |  |
| C4 | Site Information |  |
|  | Total number of pages | 3 |

# Part 4: Site Information

Core clause 11.2(16) states

“Site Information is information which

- describes the Site and its surroundings and

- is in the documents which the Contract Data states it is in.”

In Contract Data, reference has been made to this Part 4 of the contract for the location of Site Information.

# General description

### The Site

- The works shall be performed at the boundaries of Simmerpan complex in Germiston.

- Access to the site can be gained off Power Road Eskom Simmerpan / National Control. Contractor adheres to all procedures set for access to the station, including acquiring security clearance where necessary.

- The building where the work will take place is situated within the boundaries of Simmerpan Complex and all Eskom rules and regulations shall be adhered to when operating in this area.

- The Contractor is to inspect the site and building in order to ascertain the conditions and extent of his risk.

- The Contractor should indicate work sequence and the limitations of access when submitting the programme to NTCSA.

### Security

- There is security at Simmerpan and is responsible for access control.

# Existing buildings, structures, and plant & machinery on the Site

The works have interfaces and hook up points with existing facilities. Activities in the scope of work are to be carried out on existing structures or facilities; thus site information is as built.

# Subsoil information

No geotechnical reports or borehole records are required under this contract.

# Hidden services

Before any work commences, it will be the responsibility of the Contractor to verify and ascertain the position of any other existing services on site. Once these are indicated to the Contractor they shall be deemed “known”. Any costs incurred for repairs to any “known” services due to Contractor’s fault/damage shall be for the Contractor’s account.

# Other reports and publicly available information

No public information available, Supplier should prepare their own design, method of work and programme.

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za