NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________) |  |
| for | The design, manufacture, testing, quality assurance, training of Eskom personnel, delivery to Eskom sites or warehouses, off-loading and if required, erection, commissioning, decommissioning and disposal of valve-regulated lead acid cells and vented lead acid cells. The scope includes battery enclosures, battery stands, accessories and its ancillary equipment on an "as and when require" basis for Distribution - (For a period of five years). |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | 02 |
| Part C2 | Pricing Data | 33 |
| Part C3 | Scope of Work | 37 |
| Part C4 | Site Information | 59 |
| CONTRACT No. | [ ] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance | 3 |
| C1.2a | Contract Data provided by the Employer | 6 |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | 29 |
| C1.3 | Proforma Guarantees | 30 |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

The design, manufacture, testing, quality assurance, training of Eskom personnel, delivery to Eskom sites or warehouses, off-loading and if required, erection, commissioning, decommissioning and disposal of valve-regulated lead acid cells and vented lead acid cells. The scope includes battery enclosures, battery stands, accessories and its ancillary equipment on an "as and when require" basis for Distribution - (For a period of five years).

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| Options A | The offered total of the Prices exclusive of VAT is | As per rates |
| --- | --- | --- |
|  | Value Added Tax @ 15% is | As per rates |
|  | The offered total of the amount due inclusive of VAT is | As per rates |
|  | (in words) |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer | Eskom Holding SOC, Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |
| Name & signature of witness |  |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

| ## Clause |  | ## Statement |  | ## Data |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |  |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |  |  |  |  |  |
|  |  |  |  | A: Priced contract with activity schedule |  |  |  |  |  |  |  |
|  |  | dispute resolution Option |  | W1: Dispute resolution procedure |  |  |  |  |  |  |  |
|  |  | and secondary Options |  |  |  |  |  |  |  |  |  |
|  |  |  |  | X1: Price adjustment for inflation |  |  |  |  |  |  |  |
|  |  |  |  | X2: Changes in the law X3: Multiple currencies |  |  |  |  |  |  |  |
|  |  |  |  | X4: Parent company guarantee (if applicable) |  |  |  |  |  |  |  |
|  |  |  |  | X7: Delay damages X13: Performance Bond (if applicable) |  |  |  |  |  |  |  |
|  |  |  |  | X15: Limitation of Contractor’s liability for design to reasonable skill and care |  |  |  |  |  |  |  |
|  |  |  |  | X16: Retention |  |  |  |  |  |  |  |
|  |  |  |  | X18: Limitation of liability |  |  |  |  |  |  |  |
|  |  |  |  | Z: Additional conditions of contract |  |  |  |  |  |  |  |
|  |  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) |  | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |  |  |  |  |
| 10.1 |  | The Employer is (Name): |  | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state-owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |  |  |
|  |  | Address |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |  |  |
| 10.1 |  | The Project Manager is: (Name) |  | As per works order |  |  |  |  |  |  |  |
|  |  | Address |  |  |  |  |  |  |  |  |  |
|  |  | Tel No. |  |  |  |  |  |  |  |  |  |
|  |  | Fax No. |  |  |  |  |  |  |  |  |  |
|  |  | e-mail |  |  |  |  |  |  |  |  |  |
| 10.1 |  | The Supervisor is: (Name) |  | As per works order |  |  |  |  |  |  |  |
|  |  | Address |  |  |  |  |  |  |  |  |  |
|  |  | Tel No. |  |  |  |  |  |  |  |  |  |
|  |  | Fax No. |  |  |  |  |  |  |  |  |  |
|  |  | e-mail |  |  |  |  |  |  |  |  |  |
| 11.2(13) |  | The works are |  | The design, manufacture, testing, quality assurance, training of Eskom personnel, delivery to Eskom sites or warehouses, off-loading and if required, erection, commissioning, decommissioning and disposal of valve-regulated lead acid cells and vented lead acid cells. The scope includes battery enclosures, battery stands, accessories and its ancillary equipment on an "as and when require" basis for Distribution – (For a period of five years) |  |  |  |  |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register |  | 1. Design Complications 2. Reliability and performance of equipment 3. Sea freight risks 4. Inadequate storage 5. Transportation damage 6. Supplier Failure to deliver 7. Late Deliveries 8. Weather 9. Labour strikes. 10. Safety files. 12.COVID 19 Pandemic Additional risks will be managed by the Parties as they arise. |  |  |  |  |  |  |  |
| 11.2(15) |  | The boundaries of the site are |  | Different per substations |  |  |  |  |  |  |  |
| 11.2(16) |  | The Site Information is in |  | Part 4: Site Information |  |  |  |  |  |  |  |
| 11.2(19) |  | The Works Information is in |  | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |  |  |  |  |
| 12.2 |  | The law of the contract is the law of |  | the Republic of South Africa |  |  |  |  |  |  |  |
| 13.1 |  | The language of this contract is |  | English |  |  |  |  |  |  |  |
| 13.3 |  | The period for reply is |  | 1 week |  |  |  |  |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities |  | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |  |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is |  | 31 August 2030 |  |  |  |  |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: |  | Condition to be met |  |  |  | key date |  |  |  |
|  |  |  |  | 1 | Delivery lead times |  |  | It is estimated that the orders will be completed within the agreed lead times per batteries per order. |  |  |  |
| 30.1 |  | The access dates are: |  | Part of the Site |  |  |  | Date |  |  |  |
|  |  |  |  | 1 | To be advised and provided |  |  | As and when required basis |  |  |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within |  | 1 week of the order placed. |  |  |  |  |  |  |  |
| 31.2 |  | The starting date is |  | October 2025 or from the date of the last signature on this document. |  |  |  |  |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than |  | 1 week. |  |  |  |  |  |  |  |
| 35.1 |  | The Employer is not willing to take over the works before the Completion Date. |  | - The employer shall be deemed to have taken over the works after successful completion on an initial discharge test for supply and delivery only The Employer shall be deemed to have taken over works on successful completion of the 5-hour discharge test on batteries. A tax invoice shall be issued at this time. |  |  |  |  |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |  |  |  |  |  |
| 42.2 |  | The defects date is |  | 5 years after delivery or installation of the goods relative to each purchase order. |  |  |  |  |  |  |  |
| 43.2 |  | The defect correction period is |  | 2 weeks |  |  |  |  |  |  |  |
|  |  | except that the defect correction period for |  | N/A |  |  |  |  |  |  |  |
|  |  | and the defect correction period for |  | N/A |  |  |  |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |  |  |  |  |  |
| 50.1 |  | The assessment interval is |  | between the 25th day of each successive month, provided the assessment is completed within 1 week of the actual work done. |  |  |  |  |  |  |  |
| 51.1 |  | The currency of this contract is the |  | South African Rand (ZAR). |  |  |  |  |  |  |  |
| 51.2 |  | The period within which payments are made is |  | For contracts valued below R50 000 000 (Fifty Million Rand) including VAT, Eskom is committed to paying Suppliers within 30 days of receipt of undisputed invoices. For contracts valued above R50 000 000 (Fifty Million Rand) including VAT, Eskom is committed to paying suppliers within 60 days of receipt of undisputed invoices. |  |  |  |  |  |  |  |
| 51.4 |  | The interest rate is |  | the publicly quoted prime rate of interest (calculated on a 365-day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |  |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |  |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: |  | Not applicable |  |  |  |  |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, |  | the cumulative rainfall (mm) |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with rainfall more than 10 mm |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |  |  |
|  |  |  |  | the number of days with snow lying at 09:00 hours South African Time |  |  |  |  |  |  |  |
|  |  |  |  | and these measurements: |  |  |  |  |  |  |  |
|  |  | The weather measurements are supplied by |  | South African Weather Bureau |  |  |  |  |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: |  | The weather Bureau offices closest to the works |  |  |  |  |  |  |  |
|  |  | and which are available from: |  | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |  |  |  |  |  |  |  |
| 60.1(13) |  | Assumed values for the ten year return weather data for each weather measurement for each calendar month are: |  | As stated in Annexure A to this Contract Data provided by the Employer. Note: If this arrangement is used, delete the rows above for 60.1(13) and delete this note. |  |  |  |  |  |  |  |
| ## 7 |  | ## Title |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks |  | None. |  |  |  |  |  |  |  |
| ## 9 |  | ## Termination |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |  |  |  |  |  |
| A |  | Priced contract with activity schedule |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| 50.7 |  | The exchange rates are those published in |  | South African Reserve Bank (SARB) |  |  |  |  |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |  |  |  |  |  |
| W1.1 |  | The Adjudicator is |  | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: |  | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |  |  |  |  |  |  |  |
| W1.4(2) |  | The tribunal is: |  | arbitration. |  |  |  |  |  |  |  |
| W1.4(5) |  | The arbitration procedure is |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |
|  |  | The place where arbitration is to be held is |  | South Africa |  |  |  |  |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |  |  |  |  |  |
| X1 |  | Price adjustment for inflation |  |  |  |  |  |  |  |  |  |
| X1.1(a) |  | The base date for indices is |  | 1 month prior to tender closing date – May 2025 |  |  |  |  |  |  |  |
| X1.1(c) |  | The proportions used to calculate the Price Adjustment Factor are: |  |  |  | The prices will be fixed and firm for the first 12 months and thereafter be escalated as per approved pricing schedule. Refer to Pricing Schedule – “CPA Formula” |  |  |  |  |  |
| X2 |  | Changes in the law |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| X3 |  | Multiple currencies |  | To be confirmed with Treasury Department before contract award |  |  |  |  |  |  |  |
| X3.1 |  | The Employer will pay for these items or activities in the currencies stated |  | Items & activities |  |  | Other currency |  |  | Maximum payment in other currency |  |
|  |  |  |  | [●] |  |  | [●] |  |  | [●] |  |
| X3.1 |  | The exchange rates are those published in |  | [●] on [●] (date) |  |  |  |  |  |  |  |
|  |  |  |  | The items & activities will be paid in the other currency - to a foreign Bank account nominated by the Contractor - to a valid SARB approved CFC account in South Africa - in accordance with an alternative payment method agreed with the Employer before the Contract Date. (select one of the three methods as agreed with successful tenderer and delete the others and this note) |  |  |  |  |  |  |  |
| X4 |  | Parent company guarantee |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| X7 |  | Delay damages (but not if Option X5 is also used) |  |  |  |  |  |  |  |  |  |
| X7.1 |  | Delay damages for Completion of the whole of the works are |  | 0.5% of the affected portion of the total of the Prices per purchase order, per completed 1 working day of delay. The total delay damages shall not exceed 15% of the purchase order. |  |  |  |  |  |  |  |
| X13X13 |  | Performance bond |  |  |  |  |  |  |  |  |  |
| X13.1X13.1 |  | The amount of the performance bond is |  | 10% bond per Purchase Order to be issued for the purpose of the manufacturing period two weeks after Order acknowledgment by the Contractor and expires at completion of manufacturing of the goods. |  |  |  |  |  |  |  |
| X15 |  | Limitation of the Contractor’s liability for his design to reasonable skill & care |  | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |
| X16 |  | Retention |  |  |  |  |  |  |  |  |  |
| X16.1 |  | The retention free amount is |  | None |  |  |  |  |  |  |  |
|  |  | The retention percentage is |  | 2.5% Retention Bond of the purchase order value to be issued and submitted together with the invoice for payment and will be valid for the Defects Period. |  |  |  |  |  |  |  |
| X18 |  | Limitation of liability |  |  |  |  |  |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: |  | R0.0 (zero Rand) |  |  |  |  |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: |  | the amount of the deductibles relevant to the event described in the insurance policy format selected in the data of clause 84.1 above , which policy is available on request from Eskom Insurance Management Services. |  |  |  |  |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to |  | The greater of the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date. |  |  |  |  |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: |  | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for Defects due to his design which arise before the Defects Certificate is issued, Defects due to manufacture and fabrication outside the Site, loss of or damage to property (other than the works, Plant and Materials), death of or injury to a person and infringement of an intellectual property right. |  |  |  |  |  |  |  |
| X18.5 |  | The end of liability date is |  | (i) five (5) years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |  |  |  |
| Z |  | The Additional conditions of contract are |  | Z1 to Z15 always apply. |  |  |  |  |  |  |  |
| Z1 |  | Cession delegation and assignment |  |  |  |  |  |  |  |  |  |
| Z1.1 |  | The Contractor does not cede, delegate, or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |  |  |
| Z1.2 |  | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |  |  |
| Z2 |  | Joint ventures |  |  |  |  |  |  |  |  |  |
| Z2.1 |  | If the Contractor constitutes a joint venture, consortium, or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |  |  |
| Z2.2 |  | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |  |  |
| Z2.3 |  | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |  |  |  |
| Z4 |  | Confidentiality |  |  |  |  |  |  |  |  |  |
| Z4.1 |  | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |  |  |
| Z4.2 |  | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |  |  |  |  |  |  |  |  |
| Z4.3 |  | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |  |  |
| Z4.4 |  | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |  |  |
| Z4.5 |  | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |  |  |
| Z5 |  | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |  |  |
| Z5.1 |  | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |
| Z7 |  | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |  |  |
| Z7.1 |  | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |  |  |
| Z7.2 |  | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |  |  |
| Z7.3 |  | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |  |  |
| Z8 |  | Notifying compensation events |  |  |  |  |  |  |  |  |  |
| Z8.1 |  | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |  |  |  |  |
| Z9 |  | Employer’s limitation of liability |  |  |  |  |  |  |  |  |  |
| Z9.1 |  | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |  |  |
| Z9.2 |  | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |  |  |  |  |  |  |  |  |  |
| Z10 |  | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |  |  |
| Z10.1 |  | or had a business rescue order granted against it. |  |  |  |  |  |  |  |  |  |
| Z11 |  | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |  |  |
| Z11.1 |  | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |  |  |  |
| Z12 | Ethics |  |  |  |  |  |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |  |  |  |  |  |
| Affected Party |  |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |  |  |  |  |  |  |  |
| Coercive Action |  |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |  |
| Collusive Action |  |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |  |
| Committing Party |  |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees, |  |  |  |  |  |  |  |
| Corrupt Action |  |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |  |  |  |  |  |  |
| Fraudulent Action |  |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |  |  |  |  |  |  |
| Obstructive Action |  |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |  |  |  |  |  |  |
| Prohibited Action |  |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |  |  |  |  |  |  |  |
| Z12.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |  |  |  |  |  |  |
| Z12.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |  |  |  |  |  |  |  |  |
| Z12.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |  |  |  |  |  |  |
| Z12.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |  |  |  |  |  |  |  |  |
| Z13 | Insurance |  |  |  |  |  |  |  |  |  |
| Z 13.1 | Replace core clause 84 with the following: |  |  |  |  |  |  |  |  |  |

| Insurance cover | 84 |  |
| --- | --- | --- |
|  | 84.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 84.2 | The Contractor provides the insurances stated in the Insurance Table A. |
|  | 84.3 | The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate. |
|  |  | ### INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage to the works, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance. Loss of or damage to Equipment; The replacement cost. Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| Z 13.2 |  | Replace core clause 87 with the following: The Employer provides the insurances stated in the Insurance Table B. |
|  |  | #### INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

C1.2 Contract Data

# Part two - Data provided by the Contractor

Notes to a tendering contractor:

- Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |  |  |  |
|  | Address |  |  |  |  |
|  | Tel No. |  |  |  |  |
|  | Fax No. |  |  |  |  |
| 11.2(8) | The direct fee percentage is | % |  |  |  |
|  | The subcontracted fee percentage is | % |  |  |  |
| 11.2(18) | The working areas are the Site and | As per purchase order |  |  |  |
| 24.1 | The Contractor's key persons are: |  |  |  |  |
|  | 1 Name: |  |  |  |  |
|  | Job: |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  | 2 Name: |  |  |  |  |
|  | Job |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |  |
| 11.2(3) | The completion date for the whole of the works is | As per Eskom’s requirements stated on purchase order |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register | As set out in the risk register |  |  |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: | As set out in the Employers works information section 3 |  |  |  |
| 31.1 | The programme identified in the Contract Data is | As per Eskom’s requirements stated on the purchase order |  |  |  |
| A | Priced contract with activity schedule |  |  |  |  |
| 11.2(20) | The activity schedule is in | C2 ECC3 Pricing Data |  |  |  |
| 11.2(30) | The tendered total of the Prices is | In C1.1 ECC3 Offer and acceptance letter |  |  |  |
|  | ## Data for Schedules of Cost Components | Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013). |  |  |  |
| A | Priced contract with activity schedule | Data for the Shorter Schedule of Cost Components |  |  |  |
| 41 in SSCC | The percentage for people overheads is: | % |  |  |  |
| 21 in SSCC | The published list of Equipment is the last edition of the list published by | N/A |  |  |  |
|  | The percentage for adjustment for Equipment in the published list is | Minus % |  |  |  |
| 22 in SSCC | The rates of other Equipment are: | Equipment | Size or capacity |  | Rate |
|  |  | N/A |  |  |  |
| 61 in SSCC | The hourly rates for Defined Cost of design outside the Working Areas are | Category of employee |  | Hourly rate |  |
|  | Note: Hourly rates are estimated ‘cost to company of the employee’ and not selling rates. |  |  |  |  |
|  | Please insert another schedule if foreign resources may also be used |  |  |  |  |
| 62 in SSCC | The percentage for design overheads is | % |  |  |  |
| 63 in SSCC | The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are: |  |  |  |  |

C1.3 Forms of Securities

# Pro formas for Bonds & Guarantees

## For use with the NEC3 Engineering & Construction Contract (June 2005)

The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:

Option X4:	Parent company guarantee

Option X13:	Performance Bond

Each of these secondary Options requires a bond or guarantee “in the form set out in the Works Information”.    Pro forma documents for these bonds and guarantees are provided here for convenience but are to be treated as part of the Works Information.

Option X16:	Retention (not used with Option F)

The Contractor may provide a Retention Money Guarantee in the form stated here.  When the Employer receives and accepts a Retention Money Guarantee exactly in the form stated he will instruct the Project Manager not to assess any amount be retained in terms of secondary Option X16.

The Contractor shall guarantee his ASGI-SA Obligations by providing the Employer with an ASGI-SA Guarantee in the form provided here.

The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.

# Pro forma Parent Company Guarantee (for use with Option X4)

(to be reproduced exactly as shown below on the letterhead of the Contractor’s Parent Company)

| Eskom Holdings SOC Ltd Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs,

## Parent Company Guarantee for Contract No

With reference to the above numbered contract made or to be made between

| Eskom Holdings SOC Ltd | (the Employer) and |
| --- | --- |
| {Insert registered name and address of the Contractor} | (the Contractor), for |
| {Insert details of the works from the Contract Data} | (the works). |

| I/We the undersigned |  |
| --- | --- |
| on behalf of the Contractor’s parent company |  |
| of physical address |  |

and duly authorised thereto do hereby unconditionally guarantee to the Employer that the Contractor shall Provide the Works in accordance with the above numbered Contract.

- If for any reason the Contractor fails to Provide the Works, we hereby agree to cause to Provide the Works at no additional cost to the Employer.

- If we fail to comply with the terms of this Deed of Guarantee, the Employer may itself procure such performance (whether or not the Agreement be formally determined).  The Employer is to notify us and we shall indemnify the Employer for any additional cost or expense it incurs.

- Our liability shall be as primary obligor and not merely as surety and shall not be impaired or discharged by reason of any arrangement or change in relationship made between the Contractor and the Employer and/or between us and Contractor; nor any alteration in the obligations undertaken by the Contractor or in the terms of the Agreement; nor any indulgence, failure, delay by you as to any matter; nor any dissolution or liquidation or such other analogous event of the Contractor.

- The Employer shall not be obliged before taking steps to enforce the terms of this Deed of Guarantee to obtain judgement against the Contractor in any court or other tribunal, to make or file any claim in liquidation (or analogous proceedings) or to seek any remedy or proceed first against the Contractor.

- This Deed of Guarantee shall be governed by and construed in accordance with the laws of the Republic of South Africa and we hereby submit to the non-exclusive jurisdiction of the High Court of South Africa.

| Signed at |  | on this |  | day of |  | 200_ |
| --- | --- | --- | --- | --- | --- | --- |

| Signature(s) |  |  |
| --- | --- | --- |
| Name(s) (printed) |  |  |
| Position in parent company |  |  |
| Signature of Witness(s) |  |  |
| Name(s) (printed) |  |  |

# Pro forma Performance Bond – Demand Guarantee (for use with Option X13)

(to be reproduced exactly as shown below on the letterhead of the Contractor’s Parent Company)

| Eskom Holdings SOC Ltd Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Performance Bond – Demand Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] Contract Reference: …… [Drafting Note: Contractor contract reference number to be inserted]

# In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. [.]as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

  - “Eskom” - means Eskom Holdings SOC Ltd, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30].

  - “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand);

  - “Project” - means [insert if applicable.].

# At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

# A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a Group Executive, Divisional Executive, Senior General Manager, General Manager  or its delegate;

  - state the amount claimed (“the Demand Amount’);

  - state that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

# Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

# The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between Eskom and the Contractor.

# Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

# Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

# This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

# The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________________________

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

Bank’s seal or stamp

# Pro forma Retention Money Guarantee (may be used when Option X16 applies)

(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

| Eskom Holdings SOC Limited Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]

- In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

  - “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30

  - “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

  - “Project” - means the…………………………………..

- At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

- A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a director of Eskom or his authorised delegate.

  - state the amount claimed (“the Demand Amount’);

  - state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

- Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

- The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

- Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

- Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

- This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

- The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________  Bank’s seal or stamp

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

Pro forma Retention Money Guarantee (may be used when Option X16 applies)

(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

| Eskom Holdings SOC Limited Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]

- In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

  - “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30

  - “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

  - “Project” - means the…………………………………..

- At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

- A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a director of Eskom or his authorised delegate.

  - state the amount claimed (“the Demand Amount’);

  - state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

- Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

- The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

- Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

- Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

- This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

- The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________  Bank’s seal or stamp

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

# Part 2: Pricing Data

ECC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A | 02 |
| C2.2 | The activity schedule | 01 |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for each group of completed activities and each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

# Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

# Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

# Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

C2.2 the activity schedule

VALVE-REGULATED LEAD-ACID CELLS (VRLA) BATTRIES

| Item No. | Description | Forecast Quantity | Unit Price Excluding VAT | Unit Price Including 15% VAT |
| --- | --- | --- | --- | --- |
| 1. | 2V, Flat Plate, Valve Regulated, Lead Acid, Gel Cell, C10 = Range from 50Ah to 4600Ah. | 3496 |  |  |

# VRLA Batteries for Reclosers

| Item No. | Description | Forecast Quantity | Unit Price Excluding VAT | Unit Price Including 15% VAT |
| --- | --- | --- | --- | --- |
| 1. | Tavrida Recloser: 12V/18Ah | 3532 |  |  |
| 2. | Nulec Recloser: 24V/7.8Ah | 10128 |  |  |
| 3. | Schneider Recloser: 24V/13.2Ah | 3725 |  |  |
| 4. | Form 5 Recloser: 24V/7.8Ah | 910 |  |  |
| 5. | Form 4C Recloser: 24V/7.8Ah | 890 |  |  |
| 6. | Noja RC15 Recloser: 12V/26Ah | 1652 |  |  |
| 7. | EnTec Recloser: 2x12V/18Ah | 1284 |  |  |
| 8. | Nulec (PTCC) Recloser: 12V 7.5Ah | 2760 |  |  |
| 9. | Nulec (ADVC) Recloser: 12V 12Ah | 1920 |  |  |
| 10. | Tavrida Recloser: 12V 26Ah | 420 |  |  |
| 11. | Noja RC15 Recloser: 12V 26Ah 1 | 1 |  |  |
| 12. | EnTec Recloser: 12V 18Ah | 1 |  |  |
| 13. | Noja Recloser: 12V/26Ah | 1 |  |  |
| 14. | Entec Recloser: 24V/18Ah | 1 |  |  |

# Vented Lead Acid Cells (VLA)

| Item No. | Description | Forecast Quantity | Unit Price Excluding VAT | Unit Price Including 15% VAT |
| --- | --- | --- | --- | --- |
| 1. | 2V, Flat Plate, Vented Lead Acid Cell, C10 = Range from 50Ah to 4600Ah. | 11802 |  |  |

Refer to “Pricing activity schedule” for VALVE-REGULATED LEAD-ACID CELLS (VRLA) BATTRIES

# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information | 1 |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) | 1 |
|  | Total number of pages | 3 |

# C3.1: Employer’s works Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s works Information	2

1	Description of the works	5

1.1	Executive overview	5

1.2	Employer’s objectives and purpose of the works	5

1.3	Interpretation and terminology	5

2	Management and start up.	5

2.1	Management meetings	5

2.2	Documentation control	6

2.3	Health and safety risk management	6

2.4	Environmental constraints and management	7

2.5	Quality assurance requirements	7

2.6	Programming constraints	7

2.7	Contractor’s management, supervision and key people	7

2.8	Invoicing and payment	7

2.9	Insurance provided by the Employer	8

2.10	Contract change management	8

2.11	Provision of bonds and guarantees	8

2.12	Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor	8

2.13	Training workshops and technology transfer	8

3	Engineering and the Contractor’s design	9

3.1	Employer’s design	9

3.2	Parts of the works which the Contractor is to design	9

3.3	Procedure for submission and acceptance of Contractor’s design	9

3.4	Other requirements of the Contractor’s design	9

3.5	Use of Contractor’s design	9

3.6	Design of Equipment	9

3.7	Equipment required to be included in the works	10

3.8	As-built drawings, operating manuals and maintenance schedules	10

4	Procurement	11

4.1	People	11

4.1.1	Minimum requirements of people employed on the Site	11

4.1.2	BBBEE and preferencing scheme	11

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	11

4.2	Subcontracting	11

4.2.1	Preferred subcontractors	11

4.2.2	Subcontract documentation, and assessment of subcontract tenders	11

4.2.3	Limitations on subcontracting	12

4.2.4	Attendance on subcontractors	12

4.3	Plant and Materials	12

4.3.1	Quality	12

4.3.2	Plant & Materials provided “free issue” by the Employer	12

4.3.3	Contractor’s procurement of Plant and Materials	12

4.3.4	Spares and consumables	12

4.4	Tests and inspections before delivery	13

4.5	Marking Plant and Materials outside the Working Areas	13

4.6	Contractor’s Equipment (including temporary works).	13

4.7	Cataloguing requirements	13

5	Construction	14

5.1	Temporary works, Site services & construction constraints	14

5.1.1	Employer’s Site entry and security control, permits, and Site regulations	14

5.1.2	Restrictions to access on Site, roads, walkways and barricades	14

5.1.3	People restrictions on Site; hours of work, conduct and records	14

5.1.4	Health and safety facilities on Site	14

5.1.5	Environmental controls, fauna & flora, dealing with objects of historical interest	14

5.1.6	Title to materials from demolition and excavation	14

5.1.7	Cooperating with and obtaining acceptance of Others	15

5.1.8	Publicity and progress photographs	15

5.1.9	Contractor’s Equipment	15

5.1.10	Equipment provided by the Employer	15

5.1.11	Site services and facilities	15

5.1.12	Facilities provided by the Contractor	15

5.1.13	Existing premises, inspection of adjoining properties and checking work of Others	15

5.1.14	Survey control and setting out of the works	16

5.1.15	Excavations and associated water control	16

5.1.16	Underground services, other existing services, cable and pipe trenches and covers	16

5.1.17	Control of noise, dust, water and waste	16

5.1.18	Sequences of construction or installation	16

5.1.19	Giving notice of work to be covered up	16

5.1.20	Hook ups to existing works	16

5.2	Completion, testing, commissioning and correction of Defects	17

5.2.1	Work to be done by the Completion Date	17

5.2.2	Use of the works before Completion has been certified	17

5.2.3	Materials facilities and samples for tests and inspections	17

5.2.4	Commissioning	17

5.2.5	Start-up procedures required to put the works into operation	17

5.2.6	Take over procedures	18

5.2.7	Access given by the Employer for correction of Defects	18

5.2.8	Performance tests after Completion	18

5.2.9	Training and technology transfer	18

5.2.10	Operational maintenance after Completion	18

6	Plant and Materials standards and workmanship	19

6.1	Investigation, survey and Site clearance	19

6.2	Building works	19

6.3	Civil engineering and structural works	19

6.4	Electrical & mechanical engineering works	20

6.5	Process control and IT works	20

6.6	Other [as required]	20

7	List of drawings	21

7.1	Drawings issued by the Employer	21

C3.2	Contractor’s Works Information	22

- Description of the works

  - 1.1 Executive overview

The scope of works includes the design, manufacture, assembly and integration, supply and testing, quality assurance, delivery to site or stores, offloading, optional erection, commissioning and decommissioning and disposal of Vented Lead Acid and Valve Regulated lead Acid batteries.

The supply of associated battery cabinets, battery stands, battery racks, spares, tools, accessories, ancillary equipment (e.g. battery management systems (BMS) and/or fire detection and suppression systems, where applicable); and provision of product specific technical training also form part of the scope of works.

The Contractor shall provide skilled labour, engineering knowledge and management experienced in fulfilling the scope of works.

All of the works shall be instructed by means of Purchase Orders issued by the Employer at any time during the term of the contract.  The Price for each item shall be taken from the Price List.  Technical, quality, and workmanship requirements for the works are described in quality control procedures (QCPs) provided by the Contractor and accepted by the Employer before work is carried out.

  - 1.2 Employer’s objectives and purpose of the works

The main objective of the works is to ensure that technical acceptable Vented Lead Acid (VLA) and Valve Regulated Lead Acid (VRLA) batteries are supplied to Eskom for the installation at various sites.

The main function of batteries is to provide standby power / backup power to essential loads when the normal primary AC power supply is not available.

Technical Standard: 240-56260034, Stationary Vented Lead Acid Batteries Standard.

Technical Standard: 240-51999453, Standard Specification for Valve-Regulated Lead Acid Cells

  - 1.3 Interpretation and terminology

The following abbreviations are used in this Works Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| AFC | Approved for construction |
| OBL | Outside battery limits |

- Management and start up.

  - 2.1 Management meetings

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | As and when required | Teleconference or Eskom site concerned or Contractor’s/Employer’s premises | Eskom: Design Engineer, Project Manager, Clerk of Work, SHEQ representatives Contractor: Relevant Contractor Representatives |
| Overall contract progress and feedback | Quarterly | Teleconference or Eskom site concerned or Contractor’s/Employer’s premises | Eskom: Contracts Manager, Procurement Specialist, Technical representatives, Contractor: Key customer executive, Design manager, Quality manager, Finance representative. |
| Project Meetings | As and when required | Eskom site concerned | Eskom: Design Engineer, Project Manager, Clerk of Work, SHEQ representatives Contractor: Relevant Contractor Representatives |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

Note: “Eskom reserves the right to place the technically compliant products on the product database upon it meeting the threshold set for technical/functional evaluation”. “Eskom reserves the right not to perform a technical/functional evaluation on a product that has been added to the product database as this product has previously been found to be technically compliant.”

  - 2.2 Documentation control

All contractual communications will be in the form of properly compiled letters or forms attached to e mails and not as a message in the e mail itself.

The Contractor shall keep records of all test and quality reports for each order and submit a hard copy of these, inclusive of the applicable technical drawings, with each consignment. Electronic copies of these documents shall be readily available on request.

The Contractor shall duly maintain an order condition report (readily available on request) that shall assist in effective and efficient management of all orders. The contents shall be mutually agreed between the Employer and Contractor.

The Contractor shall duly maintain a field failure report (readily available on request) that shall assist in effective and efficient management of all non-conformance reports and equipment performance issues. The contents shall be mutually agreed between the Employer and Contractor.

Documentation shall be exchanged freely between the relevant parties except that all correspondence relating to or affecting contract pricing shall be routed through the Contracts Manager.

  - 2.3 Health and safety risk management

In addition to the requirements of the laws governing health and safety, Eskom may have some additional requirements particular to the works and the Working Areas for this contract.  The text below provides for these being attached as an Annexure to this Works Information. PLEASE ALSO READ CORE CLAUSE 27.4 TOGETHER WITH Z7 IN THE ADDITIONAL CONDITIONS OF CONTRACT TO MAKE SURE THAT WHATHEVER IS INCLUDED IN THE ANNEXURE FOLLOWS ON FROM THOSE CLAUSES.

The Divisional/Regional Safety Risk Manager or his representative having jurisdiction over the works must provide the relevant safety, health and environmental (SHE) criteria for incorporation into this Works Information. The SHE specification / scope must be signed off by the Divisional/Regional Safety Risk Manager or his representative confirming that the applicable safety criteria have been taken into account.

The Commodity Manager / Buyer must refer the tender to the Divisional/Regional Safety Risk Manager or his representative in order to evaluate against enquiry-specific safety criteria.

The Divisional Safety Risk Managers who will be responsible for the allocation of resources to assist P&SCM with the above processes are as follows:

- Distribution (Snr Manager Corporate Hyg): Rudi Kruger

- Distribution (Middle Manager SHEQ): Paulene Pirthi

- Distribution - Cape Coastal Cluster (Middle Manager SHEQ): Lindelwa Ntamo

The Contractor shall comply with the health and safety requirements contained in Annexure ___________ to this Works Information.

SHE will be exempted, for Task Orders in which ERI (Rotran) will be responsible for the transport of the goods from the Contractor’s works to the Employer’s site.

Where a purchaser order requires delivery and offloading by the Contractor, the Contractor and his representatives shall comply with the health and safety requirements contained in the following legal requirements and other requirements; Eskom standards and procedures:

- Basic Conditions of Employment Act, 1997 (No. 75 of 1997)

- Employment Equity Act, 1998 (Act No. 55 of 1998)

- Labour Relations Act, 1995 (Act No. 66 of 1995)

- Occupational Health and Safety Act, 1993 and Regulations (Act No. 85 of 1993)

- Compensation for Occupational Injuries and Diseases Act, 1993 (Act No. 130 of 1993)

- National Environmental Management Act, 1998 (Act No.107 of 1998)

- National Environmental Management: Waste Act, 2008 (Act No. 59 of 2008)

- National Road Traffic Act, 1996 (Act No. 93 of 1996)

- National Building Regulations & Building Standards Act, 1977 (Act No. 103 of 1977)

- Companies Act, 2008 (Act No. 71of 2008)

- SANS ISO 45001: 2018 – Occupational Health and Safety Management systems Requirements with guidance for use

- SANS 10400-A:2022 Ed4 – The application of the National Building Regulations

- SANS 10108:2023 Ed7 – The classification of hazardous locations and the selection of equipment for use in such locations.

- SANS 62485-1:2015 Ed1 – Safety requirements for secondary batteries and battery installations.

- SANS 10086-1:2023 Ed4.2 – The installation, inspection and maintenance of equipment used in explosive atmosphere.

- SANS 10142-1:2024 Ed3.2 – The wiring of premises

- SANS 1186-1:2015 Symbolic Safety Signs

- Eskom Maintenance of batteries Task Manual (240-118705836)

- Eskom Battery Room Standard (240-56177186)

- Eskom Procurement and Supply Chain Management Procedure (32-1034)

- Eskom Contract and Contractor OHS Management Standard Rev3 (32-726)

- Eskom Environmental, Occupational Health and Safety Incident Management Procedure Rev9 (32-95)

- Eskom Substance Abuse Procedure Rev4 (32-37)

- Eskom Life-Saving Rules Procedure (240-62196227)

- Eskom Vehicle and Driver Safety Management Procedure Rev7 (240-62946386)

- Eskom Safety, Health, Environment, and Quality (SHEQ) Policy (32-727)

- Eskom Personal Protective Equipment Standard Rev2 (240-44175132)

- Eskom OHS Roles and Responsibilities and Statutory Appointment Standard (240-62582234)

- Eskom Occupational Health and Safety Risk Assessment Procedure (32-520)

- Eskom Occupational Hygiene Hazard Identification and Risk Assessment Standard (240-114036246)

- Eskom Medical Surveillance Procedure (240-84733329)

- Eskom Occupational Health and Safety Act: Section 37(2) Agreement – Form (240-77037682)

- Annexure B: Acknowledgement form for Eskom SHE Rules and other Requirements (240-77471499)

- Eskom Emergency Planning Standard (32-123)

- Eskom Fire Risk Management (32-124)

- Eskom Waste Management Standard (32-245)

- Eskom NEC3 Contract – awarded Contractor sign with Eskom

  - 2.4 Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints stated in Annexure ________

The Contractor shall comply with the National Environmental Management Act 1998 (Act 107 of 1998) and all applicable legislation.  The Contractor is required to ensure that all goods, services or works supplied in terms of this tender also conform to the Eskom SHEQ Policy, as amended. When required to work on Site, the Employer’s environmental management requirements shall be adhered to by the Contractor and his representatives.

  - 2.5 Quality assurance requirements

The Contractor’s ISO 9001:2015 Certificate or equivalent must be supplied with tender documents. If the Contractor is not certified, the objective evidence of a developed and fully implemented Quality Management System that conforms to ISO 9001:2015 requirements shall be submitted.

The Contractor shall comply with the Employer's Quality Requirements as specified in the Supplier Quality Management Specification 240 – 105658000 (QM-58). Form A (Tender and contract quality requirements for QM 58 and Quality Requirements for ISO 9001 standard) of this Specification indicates the specific application thereof.

All Quality Control documentation must be submitted to the Employer at least one month before project start. Quality Control Plans must include hold and witness points, must clearly state 3rd party interventions and quality/test specifications where applicable.

The Quality Control documentation that will be handed over within 30 days of order placement by the successful Contractor to the Employer and shall consist of the following:

Quality Control Plan

The Quality Control Plan shall consist of the following as a minimum and shall be accepted by the Quality representative of the Contractor prior to commencement of work and shall be sent to Eskom for approval. The QCP will also include welding procedures where applicable.

A covering page, table of contents and QCP which includes and makes provision for the following but not limited to:-

- QCP unique number.

- Revision number.

- Page number

- Provision for QCP approval signatures by the Contractor (Supervisor and Quality Controller) and Eskom System Engineer and/ or Eskom QC.

- Provision to incorporate all inspection reports or any form of records to prove conformity to requirements.

- High level description of work in execution including Item/ component/ system/ sub-system.

- Provision for nomination of intervention points for each activity as per SOW.

- Provision for review and approval signatures and dates by the Contractor (Supervisor and Quality Controller) and Eskom System Engineer and/ or Eskom QC.

- Provision for final acceptance/ releases approval signatures by the Contractor (Supervisor and Quality Controller) Eskom System Engineer and/ or Eskom QC.

Test Reports

Where tests were performed, they shall be recorded and the positions of measurements are traceable to the specific area of testing against the records. Therefore, the Contractor will submit all test reports that has been performed in the form of Data Pack.

Procedures

Contractor to submit all work procedures/instructions/ Method Statement before any work commences. These must be submitted together with QCP for approval.

  - 2.6 Programming constraints

Microsoft Project 2010 (or later version) or mutually agreed method or format shall be used as the programming system (application).  The program shall provide planned completion dates of milestones for each product component.

The Contractor shall include reasonable time for the Employer’s acceptance of each sub-product (e.g. protection scheme) per order and for testing of the complete integrated solution, indicating such times on the programme.

  - 2.7 Contractor’s management, supervision and key people

Contractor to state all relevant key persons

  - 2.8 Invoicing and payment

The Z clauses make reference to invoicing procedures stated here in this Service Information. Also include a list of information which is to be shown on an invoice.

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd and include on each invoice the following information:

Name and address of the Contractor and the Project Manager;

The contract number and title;

Contractor’s VAT registration number;

The Employer’s VAT registration number 4740101508;

Description of service provided for each item invoiced based on the Price List;

Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

(add other as required)

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

  - 2.9 Insurance provided by the Employer

First read ECC3 Core Clause 87.1 and then add anything necessary for the management of insurance related issues such as a cross reference to where procedures for making claims can be found.  Also provide contact details for persons capable of being able to answer any insurance related queries the Contractor may have, as well as to whom the information required by Marine Insurance may be addressed.

  - 2.10 Contract change management

To be managed via NEC proforma (standard forms and letters)

  - 2.11 Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

  - 2.12 Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor

Contractor to maintain record keeping of all documentation which can be accessed via Employer.

  - 2.13 Training workshops and technology transfer

The Contractor shall provide product training (theory and practical with a competency assessment) on the Installation, Site Acceptance Testing, Commissioning and Maintenance of the offered equipment.  Training shall be undertaken at the Contractor’s works, but also by agreement at the Employer’s offices around South Africa, with the Contractor’s Travel and Subsistence costs being addressed via the applicable contract line items.

The Contractor shall make all required equipment and tools available during the training sessions.

All offered training material shall conform to the prescribed Eskom format.

# 3 Engineering and the Contractor’s design

  - 3.1 Employer’s design

All Goods and services to be delivered on this contract will be developed, tested and accepted via an engineering phase with the Contractor. The engineering phase will form part of this contract. All Intellectual Property relating to the developed solutions rests with the Employer and is used by the Contractor with permission for the duration of the contract.

The following standards are applicable:

- 240-56360034, Stationary Vented Lead Acid Batteries Standard

- 240-51999453, Standard Specification for Valve-Regulated Lead Acid Cells

- Eskom Maintenance standards

- Associated Technical Schedules A&B

  - 3.2 Parts of the works which the Contractor is to design

The Contractor shall perform the detail manufacturing, assembly and integration drawings to fulfil all the requirements of this contract.

The Contractor’s design shall conform to engineering best practices, OHSAct and SANS 10142 requirements.

All artefacts developed as part of this transaction / contract shall be Eskom’s intellectual property (IP).

All technical drawings shall comply with Eskom drawing standard

  - 3.3 Procedure for submission and acceptance of Contractor’s design

Where existing approved Employer designs exist, the Contractor shall supply the Goods in accordance with these designs. The Contractor may be required to re-design aspects of these designs due to component obsolescence or integration issues.  Any such design changes shall be subject to acceptance by the Employer.

The Contractor shall submit all order specific design documentation for acceptance by the Employer.  All such documents shall have been signed off by an ECSA-registered professional person who is qualified by training and experience to do so.

The Employer’s response shall be received by the Contractor within the period of reply, or as agreed otherwise by the parties.

All equipment designs shall be done as part of the engineering development phase (initial stages) of this contract. The technical drawings and prototypes shall be accepted during this phase of the contract.

All technical drawings shall comply with Eskom drawing standard.

  - 3.4 Other requirements of the Contractor’s design

The Contractor shall maintain a record of all electronic devices supplied on this contract.  The record shall include product designations, serial numbers and manufactured dates.  Details shall be kept of the part/model numbers, serial numbers and firmware versions of all electronic devices.  The record shall be available to the Employer at no charge on request.

The Contractor shall maintain a record of all settings and configurations of all devices delivered on this contract.  This shall apply to the total contract duration.

All artefacts developed as part of this transaction / contract shall be Eskom’s intellectual property (IP).

All technical drawings shall comply with Eskom drawing standard.

The Contractor shall provide all the information of the Goods and Services in compliance with Eskom’s material management standard. This information shall be provided in the required format (as per the standard templates) for the relevant SAP numbers to be generated and Buyers Guides compiled.

  - 3.5 Use of Contractor’s design

The Employer shall hold the Intellectual Property rights to all application specific designs and documentation developed by the Contractor or his subcontractor(s) in relation to this contract.

The Contractor shall not use, without the written permission of the Employer, any application specific designs and documentation associated with this contract with any Other Parties.

The Employer shall be entitled to copy part or all of the above application specific designs and documentation to be used in other designs, possibly with other Suppliers.

  - 3.6 Design of Equipment

Not applicable.

  - 3.7 Equipment required to be included in the works

None

  - 3.8 As-built drawings, operating manuals and maintenance schedules

The Contractor shall retain an electronic copy of project documentation issued to Employer.

As-built drawings for each commodity shall be provided to the Employer by the Contractor for each purchase order.

Application-specific settings/configuration files shall be provided to the Employer by the Contractor in native format for each Purchase Order specifying such services.

All applicable operating manuals and maintenance schedules for the offered equipment shall be made available electronically (searchable “.pdf” files).

The Contractor shall compile all the maintenance documents (Maintenance Engineering Standard, Maintenance Implementation Standard, Task Manuals, Check sheets, Job plans, etc.)  in applicable Eskom format.

# 4 Procurement

# Refer to commercial documents provided at stage.

  - 4.1 People

    - 4.1.1 Minimum requirements of people employed on the Site

Specify any constraints relating to people employed to Provide the Works; for example permits for foreigners, training (other than H & S), use of labour from designated areas and industrial relations.

    - 4.1.2 BBBEE and preferencing scheme

Specify constraints which Contractor must comply with after contract award in regard to any Broad Based Black Economic Empowerment (B-BBEE) or preferencing scheme measures.

    - 4.1.3 Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

Not applicable

  - 4.2 Subcontracting

As per SDL&I requirements provided at tender stage.

  - 4.3 Plant and Materials

    - 4.3.1 Quality

Defective cells shall be replaced with new cells. Minor repairs to be completed by Contractor on other items.

    - 4.3.2 Plant & Materials provided “free issue” by the Employer

Not Applicable

    - 4.3.3 Contractor’s procurement of Plant and Materials

The Employer may require warranties from suppliers to be in favour of the Employer and not just to the Contractor during the life of the contract.  Also include requirements for vendor data which the Employer may need after Completion of the whole of the works.

Contractor to comply to the cataloguing requirements as noted in the Technical Works Information.

    - 4.3.4 Spares and consumables

Contractor to ensure sufficient spares are available as per technical specifications.

  - 4.4 Tests and inspections before delivery

All batteries shall be capacity tested before delivery as part of the Factory Acceptance Tested (FAT).

As per Task Order, inclusive of all factory acceptance tests and quality inspections.

All equipment shall be Factory Acceptance Tested (FAT) in accordance with the following requirements:

- Individual Products: Completed products shall be subject to pre-commissioning tests, in terms of equipment, wiring, instantiated configuration and functional tests, in the factory, witnessed at the Employer’s discretion, by the Employer’s representatives.

- Integrated Solution: The integrated solution shall be subject to pre-commissioning tests, in terms of equipment, wiring, instantiated interoperable configuration and functional tests, in the factory, witnessed at the Employer’s discretion, by the Employer’s representatives.

The Contractor, in addition to the above-mentioned minimum tests and inspections, conducts any tests deemed necessary to prove the performance and serviceability of the goods.

The Employer and or his representative may witness the applicable tests at the Contractor’s Works. Procedures for these tests are made available to the Employer’s representative for inspection prior to testing.

For all other witness and hold points agreed on the Quality Control Plan and Contract Quality Plan, the Contractor will advise the date and time for witnessing by the Purchaser, giving reasonable notice.

The following shall apply where the production equipment / integrated solutions included in a Task Order have not undergone FAT however design documentation and drawings have been approved and signed off in the development phase of the contract. The equipment shall undergo a FAT to test all aspects that vary from the variant already subjected to full FAT. The Employer shall witness and accept the FATs.

  - 4.5 Marking Plant and Materials outside the Working Areas

Not Applicable

  - 4.6 Contractor’s Equipment (including temporary works).

Not Applicable

  - 4.7 Cataloguing requirements by the Contractor

## Cataloguing is applicable, with reference to requirements for cataloguing that need to be satisfied by the Contractor (consult Procurement Instruction Number 1 of 2018 – Incorporating Cataloguing into the Procurement Environment, Unique Identifier 240-1289988974). Also refer to the “Technical Works Information”

# 5 Construction

  - 5.1 Temporary works, Site services & construction constraints

    - 5.1.1 Employer’s Site entry and security control, permits, and Site regulations

Contractor to ensure adherence to all Eskom requirements and controls regarding access to Eskom premises.

Contractor to adhere to all safety requirements on Eskom sites.

    - 5.1.2 Restrictions to access on Site, roads, walkways and barricades

Access control at Eskom sites to be adhered to. Detail to access to sites will be provided when issuing purchase orders.

    - 5.1.3 People restrictions on Site; hours of work, conduct and records

Detail to restrictions to sites will be provided when issuing purchase orders.

    - 5.1.4 Health and safety facilities on Site

Refer to H & S requirements.

    - 5.1.5 Environmental controls, fauna & flora, dealing with objects of historical interest

Refer to environmental requirements.

    - 5.1.6 Title to materials from demolition and excavation

Not Applicable

    - 5.1.7 Cooperating with and obtaining acceptance of Others

Detail will be provided when issuing purchase orders.

    - 5.1.8 Publicity and progress photographs

Detail will be provided when issuing purchase orders.

    - 5.1.9 Contractor’s Equipment

Detail will be provided when issuing purchase orders. Contractor to ensure all equipment and tools to complete the works are provided.

    - 5.1.10 Equipment provided by the Employer

Not Applicable

    - 5.1.11 Site services and facilities

    - Contractor shall provide everything else necessary for Providing the Works

    - 5.1.12 Facilities provided by the Contractor

Contractor of such facilities on the Site and requirements for drawings of Site facilities, as necessary.

    - 5.1.13 Existing premises, inspection of adjoining properties and checking work of Others

Not applicable

    - 5.1.14 Survey control and setting out of the works

Not applicable

    - 5.1.15 Excavations and associated water control

Not applicable

    - 5.1.16 Underground services, other existing services, cable and pipe trenches and covers

Not applicable

    - 5.1.17 Control of noise, dust, water and waste

Contractor to perform due care when working at sites to minimise and control noise, dust and waste.

    - 5.1.18 Sequences of construction or installation

Sequence of installation as per Contractor’s methodology and due care to be taken with working with others on site.

    - 5.1.19 Giving notice of work to be covered up

Not applicable

    - 5.1.20 Hook ups to existing works

Contractor to liaise with Eskom representative should any constraints hinder the works

  - 5.2 Completion, testing, commissioning and correction of Defects

    - 5.2.1 Work to be done by the Completion Date

As per the work order.

On or before the Completion Date the Contractor shall have done everything required to Provide the Works except for the work listed below which may be done after the Completion Date but in any case before the dates stated.  The Project Manager cannot certify Completion until all the work except that listed below has been done and is also free of Defects which would have, in his opinion, prevented the Employer from using the works and Others from doing their work.

|  | Item of work | To be completed by |
| --- | --- | --- |
|  | As built drawings of | Within days after Completion |
|  | Performance testing of the works in use as specified in paragraph of this Works Information. | See performance testing requirements. |

    - 5.2.2 Use of the works before Completion has been certified

Not applicable

    - 5.2.3 Materials facilities and samples for tests and inspections

The Contractor shall provide all facilities and samples for this purpose.

    - 5.2.4 Commissioning

All commissioning shall be completed according to the Eskom standard.

    - 5.2.5 Start-up procedures required to put the works into operation

Shall be completed according to the Eskom standard.

    - 5.2.6 Take over procedures

Shall be completed according to the Eskom standard.

    - 5.2.7 Access given by the Employer for correction of Defects

As per the instruction from the Project Manager.

    - 5.2.8 Performance tests after Completion

Shall be completed according to the Eskom standard.

    - 5.2.9 Training and technology transfer

The Contractor shall provide product training (theory and practical with a competency assessment) on the Installation, Site Acceptance Testing, Commissioning and Maintenance of the offered equipment.  Training shall be undertaken at the Contractor’s works, but also by agreement at the Employer’s offices around South Africa, with the Contractor’s Travel and Subsistence costs being addressed via the applicable contract line items.

The Contractor shall make all required equipment and tools available during the training sessions.

All offered training material shall conform to the prescribed Eskom format.

    - 5.2.10 Operational maintenance after Completion

Not applicable

# 6 Plant and Materials standards and workmanship

Not applicable

  - 6.1 Investigation, survey and Site clearance

Not applicable

  - 6.2 Building works

Not Applicable.

  - 6.3 Civil engineering and structural works

Not Applicable

  - 6.4 Electrical & mechanical engineering works

At work order stage.

  - 6.5 Process control and IT works

Not applicable

  - 6.6 Other [as required]

# Not applicable.
7 List of drawings

  - 7.1 Drawings issued by the Employer

At work order stage.

# C3.2	Contractor’s Works Information

This section of the Works Information will always be contract specific depending on the nature of the works. It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1. Typical sub headings could be a) Contractor’s design b) Plant and Materials specifications and schedules c) Other

This section could also be compiled as a separate file.

# Part 4: Site Information

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 2 |
| C4 | Site Information |  |
|  | Total number of pages |  |

# Part 4: Site Information

Core clause 11.2(16) states

“Site Information is information which

describes the Site and its surroundings and

is in the documents which the Contract Data states it is in.”

In Contract Data, reference has been made to this Part 4 of the contract for the location of Site Information.

- General description

- The equipment will need to be installed at either a green fields site (new) or brown field (existing) site.

- The sites include substations, telecommunications sites (including sites in mountainous terrains – remote sites), office buildings and grid-tied or off-grid renewable sites.

- The sites are located across South Africa.

- Site specific details will be provided by the Design Engineer / Project Manager when the project is executed.

- Existing buildings, structures, and plant & machinery on the Site

The site-specific information e.g. location, access, interfaces, etc. will be shared with the supplier by the responsible Design Engineer / Project Manager when the project is executed.

- Subsoil information

The site-specific information e.g. location, access, interfaces, etc. will be shared with the supplier by the responsible Design Engineer / Project Manager when the project is executed.

- Hidden services

The site-specific information e.g. location, access, interfaces, etc. will be shared with the supplier by the responsible Design Engineer / Project Manager when the project is executed.

- Other reports and publicly available information

Not applicable

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za