{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":55,"n_cols":40,"rows_kept":55,"merged":[[0,0,2,1],[0,2,2,8],[0,9,2,9],[0,10,2,10],[3,1,3,2],[3,3,3,10],[3,11,3,12],[3,17,3,20],[3,22,3,29],[4,13,4,14],[4,15,5,15],[4,18,4,19],[4,20,5,20],[4,27,4,28]]}
[" Date:    ",null,"2019-02-01",{"$nulls":6},"Prepared by:   ","N. Ngema; P Van Biljon; L Moolman",{"$nulls":9},"Revision:",0,{"$nulls":15},1,"P","I"]
[{"$nulls":20},"Revision date:","2019-04-01",{"$nulls":15},2,"F","II"]
[{"$nulls":37},3,"I","III"]
["1: List activity","2:  Hazard identification",null,"3:  Risk identification",{"$nulls":7},"4:  Assess & Analyse Risks",{"$nulls":5},"4: Evaluate Risk",{"$nulls":4},"5:  Reduce & Eliminate Risk",{"$nulls":14},4,"Ti","IV"]
["List activity\n(When applicable)","Hazard nr","Hazard Identification","Risk Nr","Associated risk \n(Risk identification)","Risk type","Exposed group/employees","Exposure patterns","Cause(s) of the risk","Risk Owner"," Conditions(Routine/Non-routine)","What are the Consequences?","Existing Controls","First determine Consequence and then the Likelihood of that Consequence.",null,"Risk Priority Rating",null,"Additional Controls or Tasks Aimed at improving Existing Controls","First determine Consequence and then the Likelihood of that Consequence.",null,"Risk Priority Rating","Monitoring  Mechanisms","Control Owner","Legal and Other Requirements","Initial Target Date","Revised Target Date","Current Status","Independent Verification\n(i.e. Confirmation that the objectives have been met)",null,"Comments",{"$nulls":7},5,"N"]
["List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task.","#","A hazard is anything that is likely to lead to an event that will have an adverse impact on achieving an objective. A hazard can pose more than one risk.","#","A physical event occurs or could occur in relation to the hazard","Safety or health","Who is exposed to the hazard i.e.  Employees, visitors, members of the public, etc.","The frequency and duration  the person/group is exposed to the hazard e.g. Daily for 3 hrs.","What causes the risk to come into effect?","Who is accountable for making sure the controls and monitors are:\n-  in place,\n-  implemented,\n-  regularly reviewed for effectiveness.","Indicate Yes or No.Yes if routine and No if non-routine  These short-term changes to conditions that could not be reasonably anticipated e.g. Emergencies","What is the expected adverse impact on the objective?","Include:\n- Preventative Controls\n(controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and\n- Reactive Controls \n(controls implemented to reduce the immediate impact of the risk occurring)    ","Consequence","Likelihood",null,"RCE\nRisk Control Effectiveness","Include:\n- Preventative Controls\n(controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and\n- Reactive Controls \n(controls implemented to reduce the immediate impact of the risk occurring)  ","Consequence","Likelihood",null,"How we know if we are succeeding. Include comments on effectiveness.\nThis may include i.e. measurements, inspections, supervision where necessary.","Person allocated the responsibility for implementing the agreed controls ","Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control.","Once a date has been agreed to, this  can not be changed","Used if, for any reason, a Target Date is revised.  Use the Comments field to explain.","Pending,\nIn Progress,\nComplete","Date Done:","By whom:"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.1,"Pulling chains on live equipment - accidental start","1.1.1","Abrasions, amputations,","Safety ","Artisans, utility and Technician","5 - 8 Hours Daily","Poor planning for the job and trying to recover time","Mikateko Matlole","Yes",null,"Plant in operation, Risk assessment,PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 2",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.2,"Noise","1.2.1","Noise Induced Hearing Loss","Health","Artisans, utility and Technician","6 - 8 Hours Daily","Failure to use or wear the appropriate hearing protection. Not using or wearing the hearing protection. Poor plant maintenance.","Mikateko Matlole","Yes",null,"Noise zones; medical surveillance and PPE(hearing protection)",4,2,"III","P","Maintain and enforce the current control measures. Provide awareness on exposure to noise",{"$nulls":5},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 3",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.3,"Working with tools","1.3.1","Struck by or pinched by tools or equipment","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Fatigue, sub-standard tools or limited space","Mikateko Matlole","Yes",null,"Risk Assessment; Correct tools & PPE",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 4",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.4,"Flying Ash","1.4.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Leaking conditioners","Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 5",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.5,"Access to plant - walking","1.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Poor housekeeping","Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 6",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners, degrating sump pumps and stubshaft replacements.",1.6,"Manual handling","1.6.1","Muscle injury","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","inadequate risk assessment","Mikateko Matlole","Yes",null,"Limited Access Register - Permit system; Risk Assessment; Correct tools",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 7",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.1,"Pulling chains, fitting flights ","2.1.1","Muscle injury","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","inadequate risk assessment","Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 8",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.2,"Flying Ash","2.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Leaking conditioners","Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 9",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.3,"Noise","2.3.1","Noise Induced Hearing Loss","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Failure to use or wear the appropriate hearing protection. Not using or wearing the hearing protection. Poor plant maintenance.","Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 10",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.4,"Fire","2.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Mills and pf","Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 11",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.5,"Access to plant - walking","2.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Uneven surfaces and slippery floor","Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 12",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",2.6,"Workspace","2.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Limited workspace","Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 13",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.1,"Hot ash and steam from back of SSC.","3.1.1","Dermal burns","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","SSC","Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",3,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 14",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.2,"Flying Ash","3.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily","Contract","Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 15",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.3,"Noise","3.3.1","Noise Induced Hearing Loss","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 16",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.4,"Fire","3.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 17",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.5,"Access to plant - walking","3.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 18",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",3.6,"Workspace","3.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 19",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.1,"Conveyor ",null,"Caught between moving parts","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",4,3,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 20",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.2,"Flying Ash","4.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 21",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.3,"Noise","4.3.1","Noise Induced Hearing Loss","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 22",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.4,"Fire","4.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 23",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.5,"Access to plant - walking","4.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 24",{"$nulls":5},"SSC"]
["Mechanical fitting components to submerged scraper conveyor and grizzlies. Chain, flights, tensioners and stubshaft replacements.",4.6,"Workspace","4.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 25",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",4.7,"Using hand tools","4.7.1","Injuring fingers","Safety","Artisans, utility men, technicians","3-  4 Hours Daily",null,"Mikateko Matlole","Yes",null,"Risk Assessment; Correct tools, PPE and pay attention to the task at hand",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 50",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.1,"Plant generated heat","5.1.1","Fatique/work stress/dehyrdartion/heat stroke","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",4,5,"I","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 26",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.2,"Flying Ash","5.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 27",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.3,"Noise","5.3.1","Noise Induced Hearing Loss","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 28",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.4,"Fire","5.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 29",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.5,"Access to plant - walking","5.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 30",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",5.6,"Workspace","5.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 31",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.1,"Trapped steam in pipeline ","6.1.1","Thermal burns ","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 32",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.2,"Flying Ash","6.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 33",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.3,"Noise","6.3.1","Noise Induced Hearing Loss","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 34",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.4,"Fire","6.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 35",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.5,"Access to plant - walking","6.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 36",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",6.6,"Workspace","6.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 37",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.1,"Rigging and slinging (<1000kg) - valves ","7.1.1","Abrasions","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",3,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 38",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.2,"Flying Ash","7.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 39",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.3,"Noise","7.3.1","Noise Induced Hearing Loss","Health","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 40",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.4,"Fire","7.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 41",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.5,"Access to plant - walking","7.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 42",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",7.6,"Workspace","7.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 43",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.1,"Gen plant areas","8.1.1","Falling resulting into a fatality","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Permit system; Risk Assessment; PPE",5,4,"I","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 44",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.2,"Flying Ash","8.2.1","lungs infections and dust in eyes","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety goggles and dust masks",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 45",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.3,"Noise","8.3.1","Noise Induced Hearing Loss","Health","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE",4,2,"III","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 46",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.4,"Fire","8.4.1","Injuries","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Fire protection system in places",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 47",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.5,"Access to plant - walking","8.5.1","Slip and fall","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"PPE; Risk Assessment",4,3,"II","P",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 48",{"$nulls":5},"SSC"]
["Mechanical fitting components to super heater. Control valve replacement and repairs. ",8.6,"Workspace","8.6.1","Falling from height","Safety","Artisans, utility men, technicians","6 - 8 Hours Daily",null,"Mikateko Matlole","Yes",null,"Safety harness",4,1,"IV","F",{"$nulls":6},"OHS Act s13, \nOHS Act s8(2)(f) \nOHS Act s8(2)(e)\nHCSR 15\nGSR 49",{"$nulls":5},"SSC"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}