Specifications for an Illustrator Service Provider to Support Development of a Book Called Poetic Inquiry as Research: A Decolonial Guide.

Background

The Human Sciences Research Council has been commissioned by Bristol University Press to write a book called “Poetic Inquiry as Research: A Decolonial Guide”. This will be a short, practical, how-to textbook of 30-40,000 words, with 6 chapters. Individual chapters will be written by collaborators, and the overall book edited by two people.

Poetic Inquiry is a creative, arts-based approach to doing research. We seek the services of an illustrator or fine artist who can work with the editors and authors to develop inspiring artwork, drawings, sketches, photos, or images, or other graphic/visual representation of the text. It is our intention that the artwork in this “how-to- book” will engage and stimulate readers, enhance key ideas and learnings and attract and enhance the target audiences experience of the book.

Scope of work

- Meet with the Editors and Authors of the Book to understand the overall aims, objectives and target audience for the book.

- First rough draft of the book available for Illustrator to start thinking about look and feel.

- Work with Editors and Authors to discuss key chapter image that would depict the essence of that chapter (1 main image per chapter for each of the 6 chapters).

- No cover image is required as this will be generated by the Publisher so that this book has the same look and feel of other books in this Imprint.

- Develop draft designs with support of Editors and Authors such as pictures, diagrams, figures, tables, graphics that would enhance the textual data contained in that chapter (between 4-6 of these embedded in each chapter in each of the 6 chapters).

Schedule and Deliverables – confirm below timeline in proposal, failure to confirm below timeline will result in disqualification

- Meet with Editors and Authors once you have been appointed.

- Rough draft of book made available to Illustrator by 15th February 2024

- Develop rough draft designs and discuss with Editors and Authors by 15th March 2024

- Submit final and approved designs by 15th April 2024

Evaluation Criteria

Concept	40

| Previous illustration and visual designs – minimum 4 previous designs (service providers must send electronical versions or link) - How the concepts and ideas are portrayed via illustration Excellent illustration – 40 points Good illustration – 30 points Fair illustration – 20 points Poor illustration – 10 points | 40 |
| --- | --- |

Capacity & competence 	60

| Proven experience in undertaking similar projects. Please send Illustrator CV (Minimum of five years of experience for Illustrator) 5 years = 10 points 7 years = 15 points 9+ years = 20 points | 20 |
| --- | --- |
| Experience of company in similar illustration work. Please send company profile Minimum of five years of experience 5 years = 10 points 7 years = 15 points 9+ years = 20 points | 20 |
| Letters of reference in a company letterhead indicating similar scope of work done in similar sectors and/or other sectors (references to be not more than 3 years old) 5+ relevant letters = 20 points 3 relevant letters = 15 points 1-2 relevant letters = 10 points | 20 |

Minimum threshold required 70%, all bidders that do not meet the minimum threshold will be disqualified.

You will be adjudicated based on the concept of how to undertake the work and how the project will be managed.