| ITEM | SUB-CLAUSE | DATA |
| --- | --- | --- |
| Employer’s name and address | 1.1.2.2 & 1.3 | Passenger Rail Agency of South Africa |
|  |  | Umjantshi House |
|  |  | 30 Wolmarans Street |
|  |  | Braamfontein, Johannesburg |
| Contractor’s name and address | 1.1.2.3 & 1.3 |  |
| Employer’s Representative name and address | 1.1.2.4 & 1.3 | Noloyiso Genu |
|  |  | No. 8 Station Street, Station Building, East London |
| Time for Completion of the Works | 1.1.3.3 | 90 days |
| Defects Notification Period | 1.1.3.7 | 12 Months from the date of Taking-over Certificate |
| Electronic transmission systems | 1.3 | Email |
| Governing Law | 1.4 | Law of the Republic of South Africa |
| Ruling Language | 1.4 | English |
| Language of communications | 1.4 | English |
| Time for access to the Site | 2.1 | TBC |
| Amount of Performance Security | 4.2 | 10% of the Contract Price |
| Allowed days for unforeseeable physical conditions | 4.12 | 30 calendar days |
| Normal working hours | 6.5 | 07:00 to 17:00 from Monday to Friday excluding Public Holidays in the Country and subject to compliance with South African laws. |
| Commencement of the Works | 8.1 | 07 Days after being given access to the site |
| Delay damages for the Works | 8.7 & 14.15(b) | Delay damages shall be 3 cents per R100 of the Contract Price excluding VAT per day or part thereof for the whole of the Works |
| Maximum amount of delay damages | 8.7 | 10% of the Contract Price |
| Latent Defects Liability Period | 11.12 | 5 Years |
| If there are Provisional sums: |  |  |
| Percentage for adjustment of Provisional sums | 13.5(b) |  |
| The Contract Price | 14.1 |  |
| Total advance payment | 14.2 | N/A |
| Number and timing of instalments | 14.2 | N/A |
| Repayment of advance payment | 14.2 | N/A |
| Currencies and proportions | 14.2 | South African Rands (ZAR) |
| Advance payment Guarantee provided by the Contractor | 14.2 | N/A |
| Percentage of retention | 14.3 | 10% of each and every Statement up to a maximum of 10% of the Contract Price |
| Limit of retention | 14.3 | 10% of the Contract Price |
| If Sub-Clause 14.5 applies |  |  |
| Plant and Materials for payment when in the Country | 14.5(a) | N/A |
| Plant and Materials for payment when properly stored On-Site | 14.5(b) | Effected payment shall be 100% of invoice value |
| Minimum amount of Interim Payment | 14.6 | N/A |
| Currency/currencies of payment | 14.15 | South African Rands (ZAR) |
| Consequence of Employer’s Risks | 17.4 | Seven calendar days |
| Limitation of Liability | 17.6 | Contract Price + 20% |
| Periods for submission of Insurance |  |  |
| - Evidence of insurance | 18.1 |  |
| - Relevant policies | 18.1 | Contract Works, Public Liability, Removal of Support, Professional Indemnity |
| Minimum amount of third party insurance | 18.3 | R10 000 000 |
| Consequences of Force Majeure | 19.4 | Extension of Time for Completion |
| The DAAB shall be | 20.2 | TBC |
| The DAAB appointing entity shall be | 20.3 | TBC |
| Arbitration Venue | 20.6 | TBC |