NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | Eskom Academy of Learning Kiosks and Distribution Boards Refurbishment Project Insert title of the works |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [●] |
| Part C2 | Pricing Data | [●] |
| Part C3 | Scope of Work | [●] |
| Part C4 | Site Information | [●] |
| CONTRACT No. | [Insert at award stage] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] | [●] |
| C1.2a | Contract Data provided by the Employer | [●] |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | [●] |
| C1.3 | Proforma Guarantees | [●] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Refurbishment of MWP and EAL Executive Boardrooms Projects

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the Options which do not apply

| Option A | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | Sub total | R [●] |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s vendor registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

[Instructions to the contract compiler:  (delete these two notes in the final draft of a contract)

- Please read the relevant clauses in the conditions of contract before you enter data.  The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.

- Some ECC3 options are always selected by Eskom Holdings SOC Ltd.   The remaining ECC3 options are identified by shading in the left hand column.  In the event that the option is not required select and delete the whole row.  Where the following symbol is used “[●]” - data is required to be inserted relevant to the specific option selected.]

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

| ## Clause |  | ## Statement | ## Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |  |  |
|  |  |  | A: Priced contract with activity schedule |  |  |  |  |  |
|  |  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |  |  |
|  |  | and secondary Options |  |  |  |  |  |  |
|  |  |  | X2 Changes in the law |  |  |  |  |  |
|  |  |  | X5: Sectional Completion |  |  |  |  |  |
|  |  |  | X7: Delay damages |  |  |  |  |  |
|  |  |  | X16: Retention |  |  |  |  |  |
|  |  |  | X17: Low performance damages |  |  |  |  |  |
|  |  |  | X18: Limitation of liability |  |  |  |  |  |
|  |  |  | Z: Additional conditions of contract |  |  |  |  |  |
|  |  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |  |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |
| 10.1 |  | The Project Manager is: (Name) | To be advised at contract award stage |  |  |  |  |  |
|  |  | Address | Megawatt Park, Maxwell Drive, Sandton, Johannesburg and Eskom Academy of Learning, Dale Road P/Bag X13, Midrand, 1685 |  |  |  |  |  |
|  |  | Tel | [●] |  |  |  |  |  |
|  |  | Fax | [●] |  |  |  |  |  |
|  |  | e-mail | [●] |  |  |  |  |  |
| 10.1 |  | The Supervisor is: (Name) | To be advised by the Employer (at contract award stage) |  |  |  |  |  |
|  |  | Address | Megawatt Park, Maxwell Drive, Sandton, Johannesburg and Eskom Academy of Learning, Dale Road P/Bag X13, Midrand, 1685 |  |  |  |  |  |
|  |  | Tel No. | [●] |  |  |  |  |  |
|  |  | Fax No. | [●] |  |  |  |  |  |
|  |  | e-mail | [●] |  |  |  |  |  |
| 11.2(13) |  | The works are | Refurbishment of MWP and EAL Executive boardrooms |  |  |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register | The contractor will need to be aware that some areas may be live/operational as well as electrified systems whilst the works are commencing. Access limitations to some areas which may results to expedited implementation schedule when access is granted Further risks to be identified at the initial project meeting and on an ongoing basis |  |  |  |  |  |
| 11.2(15) |  | The boundaries of the site are | The Megawatt Park (MWP) and Eskom Academy of Learning (EAL) Sites |  |  |  |  |  |
| 11.2(16) |  | The Site Information is in | Part 4: Site Information |  |  |  |  |  |
| 11.2(19) |  | The Works Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |  |  |
| 12.2 |  | The law of the contract is the law of | the Republic of South Africa |  |  |  |  |  |
| 13.1 |  | The language of this contract is | English |  |  |  |  |  |
| 13.3 |  | The period for reply is | Five (5) working days |  |  |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is | 7 months |  |  |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: | Condition to be met |  |  |  | key date |  |
|  |  |  | 1 | Notice of construction be given to Department of Labour |  |  | As per approved schedule |  |
|  |  |  | 2 | Security clearance of personnel’s and induction |  |  | As per approved schedule |  |
|  |  |  | 3 | Safety File Submission and induction |  |  | As per approved schedule. |  |
|  |  |  | 4 5 6 7 | Formal notification of area to work on and formal approval for shutdown. Design Freeze Four phases to be executed in sections Hand over |  |  | As per approved schedule.. As per approved schedule. As per approved schedule. As per approved schedule. |  |
| 30.1 |  | The access dates are: | Part of the Site |  |  |  | Date |  |
|  |  |  | 1 | Megawatt Park, Maxwell Drive, Sandton, Johannesburg and Eskom Academy of Learning with all regulation approvals to access and work |  |  | As per approved schedule. |  |
|  |  |  | 2 | Access to all identified sitess and Executive boardrooms as per the phasing |  |  | As per approved schedule. |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within | 2 weeks of the Contract Date. |  |  |  |  |  |
| 31.2 |  | The starting date is | The date on which the site is handed over |  |  |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than | 2 weeks. |  |  |  |  |  |
| 35.1 |  | The Employer is not willing to take over the works before the Completion Date. | Will be in sectional completion as per the approved schedule with the Project Manager. |  |  |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |  |  |
| 42.2 |  | The defects date is | 52 weeks after Completion of the whole of the works. |  |  |  |  |  |
| 43.2 |  | The defect correction period is | 2 weeks |  |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |  |  |
| 50.1 |  | The assessment interval is | On completion of each activity as per the accepted payment schedule. |  |  |  |  |  |
| 51.1 |  | The currency of this contract is the | South African Rand. |  |  |  |  |  |
| 51.2 |  | The period within which payments are made is | 4 weeks. |  |  |  |  |  |
| 51.4 |  | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: | Midrand, Gauteng and surrounding areas to the site |  |  |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, | the cumulative rainfall (mm) |  |  |  |  |  |
|  |  |  | the number of days with rainfall more than 10 mm |  |  |  |  |  |
|  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |
|  |  |  | the number of days with snow lying at 09:00 hours South African Time |  |  |  |  |  |
|  |  |  | and these measurements: |  |  |  |  |  |
|  |  | The weather measurements are supplied by | The South African Weather Bureau at the nearest station next to the site. |  |  |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: |  |  |  |  |  |  |
|  |  | and which are available from: Manufacturing and shipping delays resulting form COVID-19 lockdowns for which proof Addition to the Scope of Works by Eskom for which proof is: | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer The signed letter from the suppliers. Written instruction issued by the Eskom Representative stipulated in this Contract document. |  |  |  |  |  |
| 60.1(13) |  | Assumed values for the ten year return weather data for each weather measurement for each calendar month are: | As stated in Annexure A to this Contract Data provided by the Employer. Note: If this arrangement is used, delete the rows above for 60.1(13) and delete this note. |  |  |  |  |  |
| ## 7 |  | ## Title | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks | There are no additional risks |  |  |  |  |  |
| 84.1 |  | The Employer provides these additional insurances | as stated for “Format A” available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx (See Annexure B for basic guidance) |  |  |  |  |  |
| 84.1 |  | The Contractor provides these additional insurances: | as stated for “Format A” |  |  |  |  |  |
| 84.2 |  | The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Employer for an amount of | Suitable legal insurance that the Contractor will provide as proof to for this insurance in addition to that provided by the Employer. |  |  |  |  |  |
| 84.2 |  | The minimum limit of indemnity for insurance in respect of loss of or damage to property (except the works, Plant, Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract for any one event is | whatever the Contractor deems necessary in addition to that provided by the Employer. |  |  |  |  |  |
| 84.2 |  | The minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is | As prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of Indemnity of not less than R500 000 (Five hundred thousand Rands). |  |  |  |  |  |
| ## 9 |  | ## Termination | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |  |  |
| A |  | Priced contract with activity schedule | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |  |  |
| W1.1 |  | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |
|  |  | Address | TBA |  |  |  |  |  |
|  |  | Tel No. | TBA |  |  |  |  |  |
|  |  | Fax No. | TBA |  |  |  |  |  |
|  |  | e-mail | TBA |  |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |  |  |  |  |  |
| W1.4(2) |  | The tribunal is: | Arbitration. |  |  |  |  |  |
| W1.4(5) |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |
|  |  | The place where arbitration is to be held is | [Gauteng] South Africa |  |  |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |  |  |
| X2 |  | Changes in the law | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |
| X5 |  | Sectional Completion |  |  |  |  |  |  |
| X5.1 |  | The completion date for each section of the works is: | Section |  | Description |  | Completion date |  |
|  |  |  | 1 |  | Marang boardroom at MWP |  | As per approved schedule. |  |
|  |  |  | 2 |  | Huvo-Nkulu boardroom at MWP |  | As per approved schedule. |  |
|  |  |  | 3 |  | Kgorong boardroom at MWP |  | As per approved schedule. |  |
|  |  |  | 4 |  | Edison boardroom at EAL |  | As per approved schedule. |  |
|  |  |  | 5 |  | Management boardroom at EAL |  | As per approved schedule. |  |
| X5 & X7 |  | Sectional Completion and delay damages used together |  |  |  |  |  |  |
| X7.1 X5.1 |  | Delay damages for late Completion of the sections of the works are: | section |  | Description |  | Amount per day |  |
|  |  |  | 1 |  | Marang boardroom at MWP |  | R5000.00 |  |
|  |  |  | 2 |  | Huvo-Nkulu boardroom at MWP |  | R5000.00 |  |
|  |  |  | 3 |  | Kgorong boardroom at MWP |  | R5000.00 |  |
|  |  |  | 4 |  | Edison boardroom at EAL |  | R5000.00 |  |
|  |  |  | 5 |  | Management boardroom at EAL |  | R5000.00 |  |
|  |  | The total delay damages payable by the Contractor does not exceed: | Maximum of 20% of Contract Value |  |  |  |  |  |
| X16 |  | Retention (not used with Option F) |  |  |  |  |  |  |
| X16.1 |  | The retention free amount is | 0% of contract value |  |  |  |  |  |
|  |  | The retention percentage is | 10% deduction on assessment of each Payment Certificate |  |  |  |  |  |
| X17 |  | Low performance damages |  |  |  |  |  |  |
| X17.1 |  | The amounts for low performance damages are: | Amount |  |  | Performance level |  |
|  |  |  | R 200,000.00 or cost of low performance damages stated |  |  | Marang boardroom at MWP - Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP) |  |
|  |  |  | R 200,000.00 or cost of low performance damages stated |  |  | Huvo-Nkulu boardroom at MWP - Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP) |  |
|  |  |  | R 200,000.00 or cost of low performance damages stated |  |  | Kgorong boardroom at MWP - Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP) |  |
|  |  |  | R 200,000.00or cost of low performance damages stated |  |  | Edison boardroom at EAL - Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP) |  |
|  |  |  | R 200,000.00or cost of low performance damages stated |  |  | Management boardroom at EAL - Including and not limited to the following: Poor workmanship, inferior material quality or failure to follow accepted Method Statements and Quality Control Plans (QCP) |  |
| X18 |  | Limitation of liability |  |  |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: | R0.0 (zero Rand) |  |  |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: | the amount of the deductibles relevant to the event described in the insurance policy format selected in the data for clause 84.1 above, which policy is available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx |  |  |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to | The greater of - 10% of the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus R15M first amount payable in terms of the Employer’s assets policy. |  |  |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design which arise before the Defects Certificate is issued, - Defects due to manufacture and fabrication outside the Site, - loss of or damage to property (other than the works, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |  |  |  |  |  |
| X18.5 |  | The end of liability date is | (i) Seven 7 years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |  |
| Z |  | The Additional conditions of contract are | Z1 to Z12 always apply. |  |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |  |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |  |  |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |
| Z10.1 | or had a business rescue or a judicial management order granted against it. |  |  |  |  |  |  |  |
| Z11 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |
| Z11.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |  |

| Z12 | Ethics |
| --- | --- |

For the purposes of this Z-clause, the following definitions apply:

Affected Party		means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

Coercive Action		means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

Collusive Action		means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

Committing Party	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees,

Corrupt Action		means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

Fraudulent Action	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

Obstructive Action	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action and

Prohibited Action	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

Z 12.1 	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

Z 12.2 	The Employer may terminate the Contractor’s obligation to Provide the Works if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Works for this reason.

Z 12.3 	If the Employer terminates the Contractor’s obligation to Provide the Works for this reason, the procedures and amounts due on termination are respectively P1, P2 and P3, and A1 and A3.

Z 12.4 	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

# Annexure B:	Insurance provided by the Employer

These notes are provided as guidance to tendering contractors and the Contractor about the insurance provided by the Employer. The Contractor must obtain its own advice. Details of the insurance itself are available from the internet web link given below.

- For the purpose of works contracts, insurance provided by Eskom (the Employer) has been arranged on the basis of “project” or “contract” value, where the value is the total of the Prices at Completion of the whole of the works including VAT.

A “project” is a collection of contracts or work packages to be undertaken as part of a single identified capital expansion or refurbishment of a particular asset or facility.

A “contract” is a single contract not linked to or being part of a “project”.

- For ECC3 there are three main “formats” of cover and deductible structure; Format A, Format B and Format Dx.

Format A is for a project or contract value less than or equal to R350M (three hundred and fifty million Rand) inclusive of VAT.

Format B is for a project or contract value greater than R350M. (three hundred and fifty million Rand) inclusive of VAT.

In the case of contracts / packages within a project:

- For a contract / package of R50M which is part of a R400M project, Format B will apply

- For a contract / package of R250M which is part of a R6 billion project, Format B will apply;

- For a contract / package of R120M which is part of a R350M project Format A will apply;

For a contract which is not part of a project the same limits apply:

- For a contract of R50M, Format A will apply

- For a contract of R355M, Format B will apply.

Format Dx applies only to Distribution Division projects and contracts. If a Distribution Division project or contract exceeds the Format A limit, the Eskom Insurance Management Services [EIMS] need to be contacted for advice on how to formulate the insurance cover.  Cover and deductibles for Distribution Division are per the relevant policy available on the internet web link given below.

Format A generally applies to Transmission Division projects and contracts. If a Transmission Division project or contract exceeds the Format A limit, the Eskom Insurance Management Services [EIMS] need to be contacted for advice on how to formulate the insurance cover.

- Tendering contractors should note that cover provided by the Employer is only per the policies available on the internet web link listed below and may not be the cover required by the tendering contractor or as intended by each of the listed insurances in the left hand column of the Insurance Table in clause 84.2.  In terms of clause 84.1 “the Contractor provides the insurances stated in the Insurance Table except any insurance which the Employer is to provide”.  Hence the Contractor provides insurance which the Employer does not provide and in cases where the Employer does provide insurance the Contractor insures for the difference between what the Insurance Table requires and what the Employer provides.

- When the Marine Insurance is required the Contractor needs to obtain a copy of the latest edition of Eskom’s Marine Policies Procedures found at internet website given below.

- Further information and full details of all Eskom provided policies and procedures may be obtained from:

http://www.eskom.co.za/live/content.php?Item_ID=9248

# Annexure C:	The Employer’s Panel of Adjudicators

The following persons listed in alphabetical order of their surname have indicated their willingness to be included in the Eskom Panel of Adjudicators.  Their CV’s may be obtained by using the contact details provided.

| Name | Location | Contact details (phone & e mail) |
| --- | --- | --- |
| Nigel ANDREWS | Gauteng | +27 11 836-6760 nigela@quoin.net |
| Andrew BAIRD | Gauteng | +27 11 803 3008 andrewbaird@ecsconsult.co.za |
| Christopher BINNINGTON | Gauteng | +27 11 888-6141 cdb@bca.co.za |
| Peter HIGGINS | UK | +44 1293 873 868 peterhiggins@pdconsult.co.uk |
| Bruce LEECH | Gauteng | +27 11 290 4000 leech@counsel.co.za |
| Nigel NILEN | Gauteng | +27 11 465 3601; nilences@global.co.za |
| Peter THURLOW | Gauteng | +27 11 787 6226 info@thurlowassoc.com |

Information about the Panel and appointment of the selected Adjudicator is available from Eskom Supply Chain Operations management, by contacting Leighton Itholeng (Tel.: +27 (0)11 800 4031)

(Fax :+27 (0)86 668 0419) E-mail: Leighton.Itholeng@eskom.co.za

C1.2 Contract Data

# Part two - Data provided by the Contractor

[Instructions to the contract compiler:  (delete this notes before issue to tenderers with an enquiry)

Whenever a cell is shaded in the left hand column it denotes this data is optional.  If not required select and delete the whole row, otherwise insert the required Data.]

Notes to a tendering contractor:

- Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 11.2(8) | The direct fee percentage is | % |
|  | The subcontracted fee percentage is | % |
| 11.2(18) | The working areas are the Site and |  |
| 24.1 | The Contractor's key persons are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | 2 Name: |  |
|  | Job |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |
| 11.2(3) | The completion date for the whole of the works is |  |
| 11.2(14) | The following matters will be included in the Risk Register |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: |  |
| 31.1 | The programme identified in the Contract Data is |  |
| A | Priced contract with activity schedule |  |
| 11.2(20) | The activity schedule is in |  |
| 11.2(30) | The tendered total of the Prices is | (in figures) (in words), excluding VAT |
|  | ## Data for Schedules of Cost Components | Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013). |
| A | Priced contract with activity schedule | Data for the Shorter Schedule of Cost Components |

C1.3 Forms of Securities

# Pro formas for Bonds & Guarantees

## For use with the NEC3 Engineering & Construction Contract (June 2005)

[Note to contract compiler:

Once it has been decided which securities are required for this contract delete from this file the ones not required, revise the notes below accordingly and delete this note.]

The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:

Option X13:	Performance Bond

Each of these secondary Options requires a bond or guarantee “in the form set out in the Works Information”.    Pro forma documents for these bonds and guarantees are provided here for convenience but are to be treated as part of the Works Information.

Option X16:	Retention (not used with Option F)

The Contractor may provide a Retention Money Guarantee in the form stated here.  When the Employer receives and accepts a Retention Money Guarantee exactly in the form stated he will instruct the Project Manager not to assess any amount be retained in terms of secondary Option X16.

The Contractor shall guarantee his ASGI-SA Obligations by providing the Employer with an ASGI-SA Guarantee in the form provided here.

[Note to contract compiler:  If there are no ASGI-SA Obligations in this contract, delete the above statement]

The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.

# Pro forma Retention Money Guarantee (may be used when Option X16 applies)

(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

| Eskom Holdings SOC Limited Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]

- In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

  - “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30

  - “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

  - “Project” - means the…………………………………..

- At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

- A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a director of Eskom or his authorised delegate.

  - state the amount claimed (“the Demand Amount’);

  - state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

- Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

- The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

- Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

- Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

- This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

- The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________ Bank’s seal or stamp

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

# Part 2: Pricing Data

ECC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A |  |
| C2.2 | The activity schedule |  |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for - each group of completed activities and - each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

# Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

# Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

# Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

An activity schedule could have the following format:

| Item No. | Programme Reference | Activity description | Price |
| --- | --- | --- | --- |

C2.2 the activity schedule

Use this page as a cover page to the Contractor’s activity schedule.

# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 36 |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

# C3.1: Employer’s works Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s works Information	2

1	Description of the works	5

1.1	Executive overview	5

1.2	Employer’s objectives and purpose of the works	5

1.3	Interpretation and terminology	5

2	Management and start up.	5

2.1	Management meetings	5

2.2	Documentation control	6

2.3	Health and safety risk management	6

2.4	Environmental constraints and management	7

2.5	Quality assurance requirements	7

2.6	Programming constraints	7

2.7	Contractor’s management, supervision and key people	7

2.8	Invoicing and payment	7

2.9	Insurance provided by the Employer	8

2.10	Contract change management	8

2.11	Provision of bonds and guarantees	8

2.12	Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor	8

2.13	Training workshops and technology transfer	8

3	Engineering and the Contractor’s design	9

3.1	Employer’s design	9

3.2	Parts of the works which the Contractor is to design	9

3.3	Procedure for submission and acceptance of Contractor’s design	21

3.4	Other requirements of the Contractor’s design	9

3.5	Use of Contractor’s design	9

3.6	Design of Equipment	9

3.7	Equipment required to be included in the works	10

3.8	As-built drawings, operating manuals and maintenance schedules	10

4	Procurement	11

4.1	People	11

4.1.1	Minimum requirements of people employed on the Site	11

4.1.2	BBBEE and preferencing scheme	11

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	11

4.2	Subcontracting	11

4.2.1	Preferred subcontractors	11

4.2.2	Subcontract documentation, and assessment of subcontract tenders	11

4.2.3	Limitations on subcontracting	12

4.2.4	Attendance on subcontractors	12

4.3	Plant and Materials	12

4.3.1	Quality	12

4.3.2	Plant & Materials provided “free issue” by the Employer	12

4.3.3	Contractor’s procurement of Plant and Materials	12

4.3.4	Spares and consumables	12

4.4	Tests and inspections before delivery	13

4.5	Marking Plant and Materials outside the Working Areas	13

4.6	Contractor’s Equipment (including temporary works).	13

5	Construction	14

5.1	Temporary works, Site services & construction constraints	14

5.1.1	Employer’s Site entry and security control, permits, and Site regulations	14

5.1.2	Restrictions to access on Site, roads, walkways and barricades	14

5.1.3	People restrictions on Site; hours of work, conduct and records	14

5.1.4	Health and safety facilities on Site	14

5.1.5	Environmental controls, fauna & flora, dealing with objects of historical interest	14

5.1.6	Title to materials from demolition and excavation	14

5.1.7	Cooperating with and obtaining acceptance of Others	15

5.1.8	Publicity and progress photographs		15

5.1.9	Contractor’s Equipment	15

5.1.10	Equipment provided by the Employer	15

5.1.11	Site services and facilities	15

5.1.12	Facilities provided by the Contractor	15

5.1.13	Existing premises, inspection of adjoining properties and checking work of Others	15

5.1.14	Survey control and setting out of the works	16

5.1.15	Excavations and associated water control	16

5.1.16	Underground services, other existing services, cable and pipe trenches and covers	16

5.1.17	Control of noise, dust, water and waste	16

5.1.18	Sequences of construction or installation	16

5.1.19	Giving notice of work to be covered up	16

5.1.20	Hook ups to existing works	16

5.2	Completion, testing, commissioning and correction of Defects	17

5.2.1	Work to be done by the Completion Date	17

5.2.2	Use of the works before Completion has been certified	17

5.2.3	Materials facilities and samples for tests and inspections	17

5.2.4	Commissioning	17

5.2.5	Start-up procedures required to put the works into operation	17

5.2.6	Take over procedures	18

5.2.7	Access given by the Employer for correction of Defects	18

5.2.8	Performance tests after Completion	18

5.2.9	Training and technology transfer	18

5.2.10	Operational maintenance after Completion	18

6	Plant and Materials standards and workmanship	19

7	List of drawings	21

7.1	Drawings issued by the Employer	21

C3.2	Contractor’s Works Information	22

# Description of the works

# Executive overview

Eskom Real Estate plan to refurbish 5 boardrooms, 3 in Megawatt Park, and 2 in Eskom Academy of Learning. The technology, furniture, fittings and finishes which are currently being used are old and have reached the end of their lifespan.  A refurbishment for these boardrooms is required to update the look-and-feel for the boardrooms as well as to align with current trends for Executive boardrooms.

  - Employer’s objectives and purpose of the works

The purpose of the Works includes the following:

The Contractor to design and furnish 5 modern executive boardrooms in line with international best practice and Eskom Corporate Identity guidelines to replace the existing ones based on the requirements provided.

  - Interpretation and terminology

The following abbreviations are used in this Works Information:

| Definition | Description |
| --- | --- |
| Acceptance | The Employer accept the condition or design but does not take responsibility from the Contractor |
| Approval | Written agreement or authorization by Employer. All requests for approval must be submitted in writing and any proposed deviation from specified requirements must be fully justified and agreed by Employer. |
| Contractor | Refers to the corporation appointed to perform the engineering, procurement, and construction Works required for the project. |
| Design freeze | Is a binding decision that defines the whole product, its parts or parameters and allows the continuation of the design based on that decision (no further changes can be made to the design, it is cut-off for the engineers) |
| Employer | Refers to Eskom Holdings State Owned Company |
| Interface | Interface in these document means either to hard wired or software interaction between the Contractors and/or other Works |
| Maintenance | Maintenance can be defined as the function of keeping components or equipment in or restoring them to a serviceable condition so that they comply with design and statutory requirements and Employer standards. Maintenance includes the cleaning, removal of contaminants and waste, correct adjustment and setting, tightening, testing, fixing, refill, lubrication, rust prevention, touch up, refrigeration charge, servicing, inspection, replacement, re-installation, troubleshooting, calibration, condition determination, repair, modification, overhaul and rebuilding of equipment. Maintenance can be either preventative or corrective of nature. |
| Maintenance Management | Maintenance Management can be described as the management (planning, organising, leading and control) actions needed to ensure effective maintenance execution to provide the most efficient and optimum availability (capable of being used) and reliability (consistent quality) of the equipment installed. |
| Specification | The document/s forming part of the contract in which the methods of executing the various items of work to be done is described, as well as the nature and quality of the materials to be supplied and it includes technical schedules and drawings attached thereto as well as all samples and patterns |
| System | A set of things working together as parts of a mechanism or network in an organised manner or method such that the requirements of the System are achieved. |
| The Client | The end user will be Eskom who will be represented by Eskom Real Estate throughout the duration of the Project. |
| Unequipped spare | A functional unit that does not house any electrical components but is intended to be used in future by retrofitting/modifying the functional unit. |

The following abbreviations are used in this Works Information:

| Abbreviation | Description |
| --- | --- |
| ERE | Eskom Real Estate |
| ISO | International Organisation for Standardisation |
| SANS | South African National Standards |
| CI | Corporate Identity |
| EAL | Eskom Academy of Learning |
| MWP | Megawatt Park |
| AV | Audio Visual |
| IT | Information Technology |

# Management and start up.

  - Management meetings

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | Fortnightly | MWP | Employer, Contractor, Supervisor, and/or Consultants |
| Project Meetings | Weekly | MWP | Employer, Contractor, Supervisor, and/or Consultants |
| Stakeholder Forums | As required | MWP | Employer, Contractor, Supervisor, and/or Consultants |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings are recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

  - Documentation control

All contractual communications will be in the form of properly compiled letters or forms attached to e-mails and not as a message in the e mail itself. All of which will be copied to the Principal Agent/ Project Manager.

The Contractor will submit the following documents to the Employer for review, the Employer will review the documents for acceptance and inform the Contractor if the documents have been accepted or if it is not accepted and stating the reasons of not the accepting the documentation. The Employer will give the Contractor reasonable time which will be agreed to between the Contractor and the Employer to respond or re-submit the documents.

The documents are as follows:

| Title and purpose | Frequency |
| --- | --- |
| Weekly plan | Every Monday of the week (or as agreed) |
| Weekly progress report, reporting on actual work completed. | Every Friday of the week, reporting on the previous week’s progress (or as agreed) |
| Three weeks look ahead plan – detailing planned activity during the period | Monthly |
| Risk Register | Monthly |
| Permit to perform work | When required |

All correspondences of either commercial or technical nature, whether hard copy or email, either to Contractor or from Contractor shall clearly include the following information: contract number, subject matter, and document/ correspondence number.

All documents shall be drawn as specified by the Eskom Engineering Drawing Standard – Common Requirements, the document number is 240-86973501. In addition, a document list shall be delivered in Microsoft Excel format that contains the following fields: “document name”, “document type”, “version number”, “date created” and “created by”.

  - Health and safety risk management

The Contractor shall comply with the health and safety requirements Attached to this tender.

  - Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints.

  - Quality assurance requirements

- The Contractor demonstrates, provide and maintains a Quality Management System that is ISO 9001:2008 certified or compliant thereto. Compliance with the provisions of this clause in no way relieves the Contractor of the final responsibility to furnish an acceptable product and/or services.

- The Contractor agrees to control and professionally preserve and store appropriate documents, records, and recordings for a period of at least 3 years after termination of the agreement to guarantee the traceability of the services rendered and inspection thereof.

- The Contractor agrees to regularly update and implement all the latest technology available as well as the necessary improvements for the installation, production and organisation deemed necessary to meet the requirements of the agreement and in order to enhance all system capabilities and effectiveness to deliver high quality, cost-effective services.

- The delivered product and / or services shall be uniform in Quality and condition, sound and free from defects or external copyright or intellectual property rights, consistent with good industry practices and adhere to requested Eskom requirements, without deviation.

- Eskom shall have the right to conduct surveys and perform surveillance of the Contractor’s and/or Sub-Contractor facilities to evaluate their capability to comply with the requirements necessary to conform to contractual requirements.

- Eskom reserves the right to inspect, at reasonable times, any or all of the work included in the Works Information at the Contractor’s or Sub-Contractor’s premises or elsewhere. Verification by Eskom shall not absolve the Contractor of the responsibility to provide acceptable product and / or services, nor shall it preclude subsequent rejection by Eskom.

- The services must comply with the agreed specifications and the applicable directives and technical standards set out in the contract and annexures. Defects notified by Eskom shall be remedied by the Contractor upon demand by Eskom without undue delay and at no extra cost. The Contractor shall continuously monitor and identify non-conformances, both internal and external, as signals of opportunities for improvement making process and other relevant changes to prevent recurrence.

- The Contractor shall further identify potential problems before they occur by identifying deviations in patterns or trends in product, service or process performance.

- Nothing contained in the contract and/or scope of work and /or works information shall relieve in any way the Contractor from the obligation of quality control thereof.

- The Contractor guarantees that the quantity, quality and outward appearance of the delivered Product / services comply with the requirements of the contract and/or relevant specifications.

- The Contractor shall, on request, prove its ability to relate to the proposed scope of work which establishes the manner in which the Contractor intends to perform the Contract.

- The Contractor shall, on request, prove its organisational, logistics and support resources to ensure the requirements of the contract can and will be achieved.

- Eskom reserves the right to assess and measure, during the existence of the agreement, the qualifications, capability and competence of the key staff (assigned personnel ) in relation to the scope of work and to interview any / all Contractors to confirm the Quality evaluation.

- The professional personnel who will be conducting the service will be available on a continuous basis until the conclusion of the project.

- The Contractor shall demonstrate experience in comparable projects or specific aspects of the project and / or performance in similar projects, on request.

- The Quality of the service / product and the contents thereof will always be in accordance with professional standards.

- For the duration of the Contract, the professional staff rendering the service / product, must be and remain a member of his/her Professional Society (where available/applicable)

- The Contractor must, at all relevant times, scrutinise and be aware of Eskom’s requirements with specific focus on , inter alia , its philosophy , principles , strategies , practises , mission , vision , models, policies and practises.

- It is the Contractor’s obligation to ensure that their operations and the products and services it provides to Eskom comply with any applicable statutes and or regulations. Any non-compliance by the Contractor and the resultant corrective actions shall be the responsibility of the Contractor.

- The Contractor shall ensure that he complies with the works information and that appropriate quality requirements (as in the main contract) are included in subcontracts placed by Contractors to ensure subcontractor’s compliance with the works Information

- The Contractor shall execute the Works in accordance with Eskom’s Quality requirements set out in QM 58 document: Supplier Contract Quality Requirements Specification.

  - Programming constraints

A programme showing the key activities is to be submitted with the tender documents or once appointed within two weeks showing the following:

Provide Bar Chart outlining start and completion date for construction activities on site. All critical path items must be identified and outlined on the Bar Chart.

The order and timing of operations which the Contractor plans in order to provide the works.

Strict adherence to the programme will be monitored and updated on a fortnightly basis to achieve the completion dates and submitted to Eskom Project Co-ordinator. Non-conformance to the stated programme will be liable for delay damages. Any deviations on time and cost are subject to Eskom approval.

The Contractor provides the Project Programme in Microsoft Projects Format to the level 3 detail. The programme is to be updated weekly and submitted to the Project Manager for review.

  - Contractor’s management, supervision and key people

The Contractor provides the Employer with a detailed organogram of all staff and management on the contract, showing their lines of authority / communication, within two weeks of contract award. This is revised monthly and reflects any changes to the staff and management structure. The Employer reserves the right to audit and verify the structure. The Contractor has a full-time Safety and Health Officers onsite

  - Invoicing and payment.

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor submits his claim as per the NEC Payment Certificate format with supporting Activity Schedule on the assessment day. The Contract Number must be clearly visible on the NEC Payment Certificate. The Employer assesses the Payment certificates on actual work completed. Any issues regarding the claim are addressed by the Employer to the Contractor.

On acceptance of the Payment Certificate by the Employer the Contractor submits his invoice as agreed upon with the Employer. Payment will take place as per the NEC Conditions of Contract.

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment. The Contractor applies for payment with a tax invoice addressed to the Employer as follows:

The Contractor includes the following information on each tax invoice:

•	Name and address of the Contractor and the Project Manager

•	The contract number and title;

•	Contractor’s VAT registration number;

•	The Employer’s VAT registration number 4740101508;

•	The total Price for Work Done to Date which the Contractor has completed; excluding VAT, the VAT and the invoiced amount including VAT;

•	Other amounts to be paid to the Contractor;

•	Less amounts to be paid by or retained from the Contractor

The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd

Email all invoices to: invoiceseskomlocal@eskom.co.za  copies of all invoices shall be forwarded to the Project Manager

  - Insurance provided by the Employer

Contractor familiarises themselves with the Eskom Insurance Format A as provided in the Contract Data and make provision for all items that they are liable for.

  - Contract change management

The Employer instructs changes to the scope at any time, each instruction sets out the change and the date on which it becomes effective; and is issued to the Contractor in writing to be valid.

## Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee. Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

## Training workshops and technology transfer

Contractor shall provide training to Eskom’s technical team on how the installed equipment and systems must be operated. This training must be recorded.

# Engineering and the Contractor’s design

The Contractor provides detailed designs by registered engineers/technologists to the Project Manager for acceptance. These would have to be reviewed with possible amendments having to be made to comply with Eskom requirements. Adequate time is allowed on the project schedule for this.

  - Employer’s design

The Employer provides the following:

- Functional specification:

All to which the Contractor is to comply with when he is required to provide detailed design documents of the works.

The scope of works include the production of detail design drawings, procurement, manufacture, fabrication, quality control, supply, delivery, construction, installation, commissioning, testing, handing over, training and maintenance during the guarantee period of all materials and equipment necessary for the complete refurbishment of the executive boardrooms for EAL and MWP as indicated in this Works Information

The high-level scope is based on the following:

The Contractor supplies concept and detailed designs, including realistic 3D render visuals; competent management, supervision and labour, furnishings, and equipment to be installed, materials, consumables and construction equipment, tools, transportation, handling, testing, certification etc., in all aspects to provide for the execution of the works in accordance with the Employer’s requirements.

The Contractor makes provision for the supply and installation of all equipment, furniture and finishes specified, performing construction and modifications, where necessary, and the provision of skilled personnel to perform the works. The Contractor shall provide a competent supervisor available at both sites at all times during the execution of the works. Such supervisor shall act for and represent the Contractor and therefore, all instructions given to him/her by the Employer shall be binding.

The Contractor to design and furnish 5 modern executive boardrooms in line with international best practice and Eskom CI guidelines to replace the existing ones based on the requirements provided.

Performs concept designs and submits a concept design report with associated drawings, renderings and product data.

Performs all detail designs required for the supply and installation of all fittings and furnishings.

Safely removes with minimal damage to the building, all rubble from the site.

Performs and oversee the implementation of the refurbishment of the boardrooms.

Performs the inspections during the refurbishment of the boardrooms.

Provide as-built, operating and maintenance documentation.

During construction the Contractor shall provide or show reasonable means of dust control and or protection

The Contractor’s project team includes (but is not limited to) the following key resources:

- AV Specialist members

- IT Specialist members

- Architects

- Project Manager and Construction Manager

## Parts of the works which the Contractor is to design

The Contractor is responsible for the production of detailed design of the complete Works based on the Employer’s functional specification and that such designs are submitted to the Employer for approval prior to proceeding to technical specification development or next stage of the project.

The Contractor ‘s design is to comprise of design packages which will be reviewed and approved in accordance with Employer’s design review procedure 240-53113685. The design packages are to be developed in accordance with Employer’s Detail Design Report Template 240-49910707.

### General

- Design, engineering, manufacture, quality control, procurement, handling, shipment and transport to/from site, storage, offloading, construction and erection, finishing, installation, commissioning, testing, optimisation and handover of equipment, tools and materials for the works.

- The Contractor constructs and erects the works in accordance with the Contractor’s accepted design/proposal and takes cognisance of SANS 2001 and SANS 1200.

- All works are designed for constructability, reliability, and maintainability.

- The Contractor designs and procures all construction material and equipment required to perform the works.

- The Contractor identifies and includes all items required to form a complete, reliable, fit for purpose operating works, which complies with the requirements as stipulated in this Works Information.

- The Contractor provides all engineering calculations, drawings (hard and soft copy) models, inspection/quality reports, construction records, commissioning test reports, and other documentation as

- The Contractor provides dimensioned general arrangement drawings of the designed remedial works and detailed drawings of all components of the works, sufficiently detailed for the preparation of maintenance and operating procedures.

- The Contractor supplies drawings and documentation as specified in the Works Information.  This includes, but is not limited to, GA drawings, fabrication drawings (where applicable), construction drawings, as built drawings, maintenance and operating manuals for the fabrication and installation of the works.

- The Contractor’s appointed Supervisor provides technical oversight during fabrication and construction.

- Other Plant and Materials or items associated with this works is utilised with prior approval from the Project Manager.

- The Contractor performs Factory Acceptance Testing (FAT) and Site Acceptance Testing (SAT) of the Plant and Materials where required.

- The Contractor designs and provides all falsework and formwork and any other necessary temporary works for the safe execution of the works.

- The Contractor ensures all designs Documents, Construction Documents, Method Statements and Quality Documents are accepted by the Project Manager Prior to the commencing of the works

## Description of the existing Boardrooms

Megawatt Park is located in Sunninghill, the following are the executive boardrooms to be refurbished:

- Marang boardroom	   	- 12-seater

- Huvo-Nkulu boardroom 		- 26-seater

- Kgorong boardroom		- 24-seater

The Eskom Academy of Learning is located in Midrand, the following are the executive boardrooms to be refurbished:

- Edison boardroom		- 12-seater

- Management boardroom	- 18-seater

# Please refer to detailed layouts for all boardrooms in Annexure A

## General Design Principles

The facilities shall be designed:

- To be supportive of Eskom’s Corporate Identity principles

- To be flexible so as to support current and evolving technologies

- To be ergonomically suited to the users

- To facilitate inclusivity and accessibility

- To incorporate green building and sustainability principles.

## boardroom architectural specifications

| #### PLANNING |  |
| --- | --- |
| Site factors | - Meeting rooms to be accessible from office reception spaces and building entry points, and to provide equitable access. |
| Design occupancy | Min 9m2 for 4 people |
| #### INTERNAL WALLS |  |
| Wall Finish | All wall finishes are to be easily cleanable and maintainable. Painted surfaces are to be washable. Where visual projection takes place onto a wall, surface finish to be taken into account and detail to be provided for |
| #### FLOORS |  |
| General Selection Requirements | Provide for high traffic, low maintenance. |
| Preferred Material Selection | Carpet tiles - 500mm x 500mm |
| Carpet | Carpet finish to suit adjoining office space, floor transitions to be taken into account and detail to be provided |
| Other | Ducted Skirting to perimeter if required. |
| #### CEILINGS |  |
| Ceiling Finishes | Painted set plasterboard ceiling, or tiled grid system. |
| Ceiling Heights | Nominal min. 2700mm floor to ceiling height. |
| Ceiling Selection | White finish to suit room/building design |
| Acoustic Ceilings | - Internal Acoustic requirements for the space to be assessed. - Acoustic insulation requirements between spaces. |
| #### FURNITURE |  |
| General Design Principles | - Meeting table size and shape to suit room shape and size. - Quantity of meeting chairs to suit table. - Compliant with ergonomics |
| Recommended Table Selection | Source, design or build a table that has integrated all IT devices being used, that takes into consideration reaching ergonomics, optimum place setting and optimum shared space zones. The table should have a good weight “feeling” and finishing edges that will guide material selection. Material selection should take into account the environment and also compliment the other components of the room like the chairs and wall surfaces etc. The table in its final form shall have structural integrity that can perform in normal use, like body weight leaning or seating gestures without failing or toppling over. Table to suit the room dimensions, to comply with CI (Corporate Identity) |
| Recommended Chair Selection | Ergonomic leather chair suitable for up to 2 hours use. |
| The new Executive Boardroom chairs need to meet the following minimum requirements: Design; - Ergonomically assessed and certified. Warranty; - 5 years. Certification; - Approved and meets the valid standard of Ergonomics.. Mechanism; - Seat and backrest to follow the movements of the user synchronously thus ensuring the correct seated posture. - Infinite adjustment of the backrest counter pressure by means of side tension control, for body weight of approximately 120kg. - The synchronised movement can be locked in five positions. - Seat depth adjustment (5.0cm) by means of sliding seat (can be locked in five positions) - Seat tilt adjustment (-1 or -4 degrees). Arm Rests; - High end material that compliments tables and other components. Seat; - Ergonomically moulded upholstery, foam thickness: 4.0cm - Breathable polyurethane (PU) moulded foam, free from CFC and other harmful chemicals. Backrest; - High backrest made of high end material. - Mid-back backrest made of high end material. - High-high back backrest (customised) made of high end material. - Ergonomically formed, flexible high end material backrest frame - Backrest to support entire back and should have ability to recline. - Adjustable lumbar support. Headrest; - Fixed headrest. Upholstery covers; - Seat and backrest covered in genuine Nappa leather or high end material.. Colour; - TBC. Base; - 5 star castor base. Castors; - Load dependent blocked twin wheel castors (6.5cm) - Standard: hard castors for soft floors, example carpeted, floors.. Gas mechanism; - Gas height adjustment (40 to 52cm) - Safety gas unit tube to be black. The chairs are to comply with the following codes and standards: - SANS 1528-1, Furniture Part 1: Seating - SANS 1292, Castors for furniture - SANS 1324, Upholstery fabric A sample is to be provided for approval prior to procurement. |
| #### WINDOW COVERINGS |  |
| Blinds | - Motorised block-out (Light Transmission; 0%) blinds to external windows, colours to be as per CI, with manual override - Width of blinds to align with window framing mullions or glazing joints. |
| #### SIGNAGE |  |
| Door Signage | Door signage as per Eskom Signage specifications, to be affixed at the doors of each boardroom |
| #### ACOUSTICS |  |
| Noise level | Noise Level Within space should be considered |
| Noise emittance | Low - Medium. Consideration Required |
| Room to room | - Room to Room acoustics should be minimised. - Provide acoustic door seals to break out spaces, and between adjoining spaces. - Acoustic treatment within walls and ceiling spaces to be incorporated where required. |
| Room acoustics | - Room reverberation time to be considered. - Recommended mid frequency reverberation time of 0.6-0.8 seconds. |
| #### ILLUMINATION |  |
| Lighting / lux levels | - As per lighting specialist specifications and design simulation report as per SANS 10114-1 |
| Lighting controls | - Auto Off after 20 minutes - Switchable zones to suit AV - Dimming Capability - Movement Sensor - Manual Override |
| Other | Provide appropriate lighting over meeting table. luminaires will be controlled by occupancy sensors to manage energy efficiency. light fittings with a high efficiency factor will be used as per SANS 10114-1. ensure that all safety regulations and measures are applied and enforced during construction, repair and maintenance work on cabling, wiring, distribution boards, luminaires and power outlets. Earthing for the electrical system shall be provided in accordance with SANS 10292. |
| Natural Light | Natural daylight to room is desirable |
| #### POWER |  |
| Type, quantity and other | As per electrical engineer |
| Small power and lighting | Replace all Main distribution boards and sub-distribution boards feeding all the boardrooms and the installation shall be tested and a certificate of compliance shall be issued per distribution board in compliance with SANS 10142-1 (The wiring of premises - Part 1: Low-voltage installations). Power outlets should be sufficient for use. The socket outlets should be installed at a reach, table power sockets. Produce a wiring and small power layout drawings from the source to loads. The works shall be supervised by a full time registered “MASTER ELECTRICIAN”. |

## IT specifications

### System Architecture

#### Architectural Requirements:

Eskom is using Microsoft Teams and has also deployed Cisco videoconferencing systems, in business and operations areas.

The technologies that will be provided as part of this tender must:

a) The solution shall be based on open standards and where proprietary protocols are used, the supplier shall provide the details of proprietary protocols with associated limitations and benefits.

b)  At each phase of developing and providing Eskom with the solution, the supplier must first obtain Eskom approval for all technical and documentary deliverables before moving forward to the next phase.

c)  Provide detailed audio-visual architectural designs that will take into consideration the current existing systems and integrating them with new approved systems.

d)	After approval of the designs and specifications, must have experience and capability to implement and integrate the scope of work at the identified boardrooms.

### Functional Requirements

#### General Requirements

- Room must be scheduled in Outlook.

- User must be able to drive content from any device (companion mode).

- Room participant must be able to add another participant either internally or via PSTN.

- User must be able to follow the call on their own device (phone/laptop) in the room without getting audio feedback

- Ability for presenter to present content in the room.

- Analogue whiteboard or flip charts to be incorporated into Teams meeting for all participants to see.

- Enforce room capacity profiles.

- Availability of together mode and Front Row mode views.

Visibility of remote participants when asking questions i.e., raise hands when they would like to ask a question

- Include device that can automatically identify in-room participants on the transcriptions I (i.e., Intelligent speakers)

- Ability to join in meeting from another platform using MTR.  WebEx, Zoom etc

- Provide a room booking system and panels outside the room to facilitate venue bookings and schedules.

- Ability to use video and audio equipment to join meetings on other platforms such as WebEx; Zoom

- Secure device and traffic

- Avail comprehensive self-management.

- An end-to-end VC solution is required (designs, supply of all equipment, installation of all equipment and commissioning of each boardroom)

#### System Functions

General System Requirements:

a) The system shall support mobile devices including mobile phones, tablets, etc.

b) Eskom currently has a significant implementation of Cisco Video Conferencing endpoints and a Cisco back-end.     The supplier shall provide a solution that can seamlessly integrate both MS Teams Rooms and Cisco WebEx.

c) The solution shall be able to integrate with web-based conferencing application.

d) The system shall be able to connect to external sites (outside Eskom) through public networks (i.e., Internet/PSTN).

#### Endpoint Functions

All devices must be Microsoft Teams Certified.

a) Camera

Ability to supply camera for small to medium (12- 18 seater) and large (20 – 26 seater) boardrooms

- 4K Camera

- Microsoft and SIP Certified

- Speaker tracking

b) Display

- Large boardroom (20 – 26 seater)

1) 2 x 85 inch

2) Wireless presentation to the screen

- Medium boardroom (12- 18 seater)

1) 1 x 85 inch

2) Wireless presentation to the screen

c) Control PC

- Must be running a certified version of Teams Rooms and meet the minimum Microsoft (Windows 10 or later) requirements

d) Microphone

- Ceiling or Desk Mics

e) Audio Speakers

- Large Boardroom (20 – 26 seater)

1) The device shall be active or powered by external amplifier.

2) Ceiling/Wall mounted Speakers

3) Digital Signal Processor (DSP) to connect to the PC

- Medium boardroom (12- 18 seater)

1) Ceiling speakers when a ceiling mic is used

2) DSP to connect to the PC when a ceiling mic is used

f) Control Console (all boardrooms)

1) 10-inch touch screen

i) Wall mount Room schedule display unit (all boardrooms)

1) Touch screen

2) Teams certified room booking panel (must be able to hide meeting subject)

### Design Requirements

- The Eskom environment consists of several types of boardrooms (i.e., medium rooms allocate up to the maximum of 12 people, large rooms take up to 24+ people).

b) Camera:

1) The camera selection is according to the rooms mentioned above.

2) The camera is placed at an optimal position depending on the size of a room (i.e., wall mounted or placed on top of a screen).

3) The camera pick-up distance is consistent with the room specification and layout.

c) Display:

1) The size of the display is according to the size of the room.

2) Where more than one display is used it should be seamlessly integrated and stackable.

3) The display is wall mountable, frame mountable.

4) For larger rooms, the option of using screens versus projectors is based on the least-cost solution, without compromising on quality/user experience.

d) Codec :

1) The codec is frame mountable or moving pedestal stand where mobility is required.

e) Microphone:

1) The microphone is positioned either ceiling mounted, or table mounted depending on the size of the room.

2) Microphones is be placed near the speakers.

3) Microphone pick up distance is consistent with the room specification.

f) Audio Speaker:

1) The audio speakers is wall mountable where necessary depending on the size of the room.

### Network Connectivity

a)	The equipment supports Ethernet  interfaces for network connectivity, at minimum 100 Mbps.

b)	The equipment supports wireless connectivity.

c)	The equipment is IP addressable (i.e., support the Internet Protocol).

d)	The video conferencing system supports IP (IPv4 and IPv6)

### Security

a) Endpoint to endpoint encryption is supported.

b) User authentication complies to the Eskom Information Security Policy

### Training

a)	The supplier offers training on the design, use, operation, and maintenance of the system to Eskom staff.

### Support

a)	1st  line (system maintenance/low level) support is done in-house.

b)	The supplier offers 3rd line (specialised/high level) support on a 24/7 basis.

c)	The supplier has spares and is able to swap out and replace faulty equipment.

d)	Equipment has a minimum warranty three years, five years preferred.

e)	The supplier provides equipment management software.

## Procedure for submission and acceptance of Contractor’s design

### Documentation and Configuration Management

#### Document identification

All documents supplied by the Contractor are subject to the Employer’s acceptance. The language of all documentation is in English. The Contractor includes the Employer’s drawing number in the drawing title block. This requirement only applies to design drawings developed by the Contractor and his Sub-Contractors. Drawing numbers are assigned by the Employer as drawings are developed.

The Contractor is required to submit the Vendor Document Submission Schedule (VDSS) as per agreed dates to the delegated Employer’s Representative. The Employer pre-allocates document numbers on the VDSS and sends back to the Contractor through the delegated Employer’s Representative. The VDSS is revisable and changes are discussed and agreed upon by all parties. The Contractor’s VDSS indicates the format of documents submitted.

#### Document Submission

All project documents are submitted to the delegated Employer’s Representative with transmittal note according to Project / Plant Specific Technical Documents and Records Management Work Instruction (240-76992014). In order to portray a consistent image it is important that all documents used within the project follow the same standards of layout, style and formatting as described in the Work Instruction.

The Contractor is required to submit documents as hard copies and electronic copies in PDF and native CAD formats (.DGN or .DWG which must be compatible with Bentley Microstation). Both copies must be delivered to the Employer’s Representative with a transmittal note.

#### Email Subject

The Contractor submits all documentation to the Employer’s Representative in the following media:

- Electronic copies are submitted to Eskom Documentation Centre through generic email address (drmsharedservices@eskom.co.za). The email subject as a minimum has the following: (Station_Project Name_Discipline_Subject). Electronic copies that are too large for email are delivered on USB, large file transfer protocol and/or hard drives to the Project Documentation Centre. In a case where USB/hard drive has been submitted, a notification email, with the transmittal note attached, is sent to the project generic email address. The Employer’s Representative is copied on the email as well.

- Hard copies are submitted to the Employer’s Representative accompanied by the Transmittal Note.

#### As-built drawings, operating manuals and maintenance schedules

The Contractor is responsible for the compilation and the supply of all the documentation required during the various project stages and to provide the documentation programmed to link with the milestone dates.  Documentation and drawings are programmed for delivery to meet the milestone dates and in accordance with the agreed VDSS.

At Take-over the Contractor provides two full sets of as-built documentation as hard copies and electronic PDF and native CAD formats (.DGN or .DWG which must be compatible with Bentley Microstation) to the Employer.

All documentation, including reports, manuals, etc. is in the English language.

##### Documentation System

The Contractor’s document system is comprehensive in the management and control of the documentation based on a master document. Automatic prevention of duplication of numbering or ambiguity is built into the system.

All documentation submitted, by the Contractor, is accompanied by a signed documentation transmittal note.

The Contractor provides the following three weeks before the commissioning

As-built revision of all the design documents;

Operating and maintenance manuals where applicable.

Inspections and test records for the tests and inspections required.

##### Documentation Control

The Contractor implements a comprehensive document control of all documents, their revision status and of the document status in relation to the 'as built' and 'as designed' or commonly known as “Approved for Construction” status.  Procedures, document control, flow diagrams and indexes are included in this system. The drawing register contains the following information and is submitted monthly in a Microsoft Excel format to the Employer:

- Drawing number (Employer and Contractor’s number)

- Revision

- Approval status

- Location of drawing at that stage

- Drawing description

- Sheet number

- Transmittal number

- Date of submission

The following process will be followed during submission of documents:

- The Contractor submits the documents/drawings to the Project Manager

- The Project Manager’s Document Controller registers the documents.

- The Project Manager’s Document Controller will supply the documents/drawings to all relevant parties within the Project Manager’s project team.

- The Employer’s project team reviews the documents/drawings and will submit all comments or inputs to the Contractor for consideration.

- If the Project Manager finds major deficiencies in the submitted documents/drawings, the Contractor revises the documents/drawings and resubmits to the Project Manager.

- The Project Manager reviews the documents/drawings and if no major deficiencies are found, the Contractor organises a Design Review session.

- The Employer and the Contractor conduct a Design Review in accordance with 240-53113685, Design Review Procedure

- If any fundamental errors were found in the designs or further actions are required, the Contractor record all concerns raised and revises the designs.

- The Contractor organises a Design Review session once all designs were revised according to the concerns raised by the Employer.

- If no fundamental errors were found in the designs during the Design Review session, the Contractor compiles the Design Review minutes or report and submits it to the Project Manager

- The Project Manager’s Document Controller registers the report.

- The Project Manager’s project team reviews the Contractor report/minutes. If the report/minutes are not acceptable, the Contractor revises the report/minutes and resubmits to the Project Manager.

- The Employer’s Agent will accept the Contractor design once the report/minutes are accepted by the Employer’s project team.

- Work shall at all times be subject to full time supervision by a qualified and experienced site agent. This representative must be authorised and competent to receive instructions on behalf of the Contractor.

  - Other requirements of the Contractor’s design

The Contractor is to comply with all legislated safety requirements as well as Eskom’s health and safety standards.

  - Use of Contractor’s design

The Contractor grants to the Employer, with effect from the starting date, an irrevocable royalty-free non-exclusive licence to use all of the documents provided to provide the Works (including, but not limited to calculations, drawings, manuals, models and other documents of a technical nature), for any purpose whatsoever, including for the purpose of operating, repairing, maintaining, dismantling, re-assembling and making adjustments to all parts of the Works.

  - Design of Equipment

The minimum general components design criterion that is to be met is as follows:

- The new installations are to be designed to facilitate efficient manufacture, inspection, transportation, installation, maintenance and repairs.

- All equipment is to be designed to comply with all the legal requirements in respect of safety and the prevention of environmental pollution.

- The designed equipment shall satisfy any specific requirements contained in the relevant statutory codes and standards.

- To be supportive of Eskom’s Corporate Identity principles

- To be flexible so as to support current and evolving technologies

- To be ergonomically suited to the users

- To facilitate inclusivity and accessibility

- To incorporate green building and sustainability principles.

## Equipment to be included in the works

The Contractor is required to provide all Equipment required for the execution of the complete Works as detailed by the scope of work.

## As-built drawings, operating manuals and maintenance schedules

The operating and maintenance manuals are to be detailed enough to operate, maintain, dismantle, reassemble, adjust and repair all newly installed equipment and Materials.

As-built Drawings

The Contractor is to provide “As Built” drawings based on the shop drawings embodying all modifications made during construction.

Safety and operation drawings must also be included “. Two hard copies (A1 size) as well as PDF copies saved on a memory stick - of “As Built” drawings are to be submitted to the Employer for Acceptance.

# Procurement

The Contractor provides the following procurement services in performing the works:

•	Preparation of Employer approved supplier and Sub-Contractor’s lists for equipment and contracts to be submitted to the Employer for review and approval.

•	Follows the most cost and time saving procurement strategies.

•	Contract management services for the selection, appointment and management of Sub-Contractors, where required to execute the scope.

•	Obtains delivery dates from Sub-Contractors and suppliers in order to realize the Completion Date;

•	Receiving of invoices, verification thereof in terms of purchase orders and contract provisions, certification of invoices as being correct and payable and supply of correct invoices to the Employer

•	Management of and negotiating of all suppliers and Sub-Contractors compensation events and recommendations to the Employer as to the validity, amount and payment of such events.

•	Determination of penalties payable by suppliers and Sub-Contractors and recommendation to the Employer as to the enforcement of such penalties prior to any communication to suppliers and Contractors.

•	Ensuring that all suppliers and Sub-Contractors, from whom the Contractor procures equipment and materials do not retain, encumber or reserve title to such items.

  - People

    - Minimum requirements of people employed on the Site

- All Contractors personnel are subjected to access control conditions as per Eskom requirements.

- All workers employed on site comply with Eskom’s health and safety standards. Workers are not allowed to be transported on the back of vans or bakkies.

- Workers are restricted to the area of activity in close proximity to the construction.

- The Contractor recruits within the immediate District Municipality for general labour/ skills to execute the project.

### BBBEE and preferencing scheme

Contractor has a BBBEE status. Note below table:

| B-BBEE Status Level of Contributor | Number of points (80/20 system) |
| --- | --- |
| 1 | 20 |
| 2 | 18 |
| 3 | 16 |
| 4 | 12 |
| 5 | 8 |
| 6 | 6 |
| 7 | 2 |
| 8 | 1 |
| Non-compliant contributor | 0 |

### Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

Not applicable for this Contract

  - Subcontracting

    - Preferred subcontractors

The Contractor notifies the Project Manager in the event of using any Sub-contractor and provides the Project Manager with a list of all sub-contractors on the project. Subcontractors cannot subcontract work to another subcontractor. The choice of the proposed sub-contractor is subject to the Project Manager’s approval before using the services of such subcontractor. The Subcontractor must be familiar with the required work and should submit CV’s of past experience and have the necessary statutory accreditations.

The Contractor provides the Project Manager with the Health and Safety plans of all the sub-contractors on the project, before commencing the project.

The Contractor coordinates his activity with other subcontractors who would be directly employed by the Employer for parts of the work not included in the scope of work

    - Subcontract documentation, and assessment of subcontract tenders

The Contractor uses the NEC subcontractor agreements. All subcontractor quotations for which provisional sums or budgets have been allowed, is first approved by the Employer or his representative with documentary proof. This is done well in advance of the planned scheduling of the work.

    - Limitations on subcontracting

As per Eskom requirements, subcontracting will be limited to 30% as far as possible. The Employer is notified where subcontracting exceeds the 30% threshold prior to commencement of the specific subcontracting works.

    - Attendance on subcontractors

The contractor attends to the activities of all subcontractors including direct subcontractors.

  - Plant and Materials

    - Quality

Note: Hardware is Microsoft Teams Room certified. The Contractor provides an OEM letter stating that all equipment to be used are Microsoft Teams Room certified.

The Contractor will not use Materials which are generally recognised as being unsuitable or otherwise to be avoided for the purpose for which they are intended.

Only components of high reliability will be utilised, with a proven operating history, to enable the buildings to achieve required reliability and availability. Material design, engineering and manufacture will accord with the best modern practice applicable to high-grade products of the type to be furnished, so as to ensure the efficiency and reliability of the Works and the strength and suitability of the various parts for the Works.

Materials shall withstand ambient conditions and the variations of temperature arising under working conditions without distortion, deterioration or undue strains in any part.

No repair of defective materials will be permitted without the Project Manager’s Acceptance and any such repair, if Accepted, will be carried out to the satisfaction of the Employer.

The Project Manager is free to specify hold and witness points during the construction and on site testing stages of the project. The Contractor issues preliminary notification of such hold and witness points by fifteen working days advance notice to the Project Manager, and confirms such hold and witness points at least seven working days prior to the activity.

Typical hold points are listed below:

- Design Review

- Factory Acceptance Test

- Delivery to Site

- Erection

- Site Acceptance Test

- All manuals and drawings (in the specified format)

- Commissioning and testing

In addition to maintaining appropriate inspection and test records to substantiate conformance to requirements, the following records are safely stored for a minimum period of seven years following the final Completion of the Works:

- Construction, layout and component Acceptances

- Type and routine test certificates

- Construction (and as-built) drawings and Acceptances

After this period, the Contractor offers these records to the Employer (in writing) and obtains a disposal instruction.

Documentation regarding quality procedures is submitted within thirty days of Contract Award. The Employer will review and comment on the acceptability of these documents in a time frame as per the requirements of the contract for contractual correspondence. If controlled copies of these documents have been submitted to the Employer, then the controlled copy numbers may be quoted in the submission.

The Contractor adheres to:

Vendor Document Submittal Schedule (the schedule to be issued to the Contractor by the Employer)

    - Plant & Materials provided “free issue” by the Employer

None, all Materials are to be provided by the Contractor.

    - Contractor’s procurement of Plant and Materials

The Contractor takes all necessary steps to ensure that all Materials are adequately protected against damage during shipping, transport and storage.

Hoarding should be provided / erected around all material stored on site

### Spares and consumables

The supplier has spares and is able to swap out and replace faulty equipment.

## Tests and inspections before delivery

The Employer carries out quality inspections at his own discretion.

The Employer will inspect and approve stages of manufacture of all materials necessary to ensure the correct quality of Materials as prescribed in the accepted project quality plan.

All inspections and testing are to be performed in accordance with the Quality Control Procedure (QCP) developed by the Contractor after Acceptance by the Employer.

The Employer reserves the right to reject items that do not conform to the Employer’s requirements.

The following tests are conducted by the Contractor and are to be witnessed by the Employer at the manufacturer’s works or Contractor’s premises as a minimum requirement:

- Inspection of all equipment. Test to ensure all equipment is working in accordance with its purpose

  - Marking Plant and Materials outside the Working Areas

All Material paid for by the Employer is clearly labelled as being the Employer’s property.

## Contractor’s Equipment (including temporary works).

The Contractor provides the following to complete the works:

- All scaffolding where required during construction

- Any Equipment necessary to complete the works

- Lifting facilities

- All material to be used for hoarding purposes

The Contractor supplies, installs, maintains and removes all temporary construction facilities and utilities necessary to Provide the Works.

# Construction

## General

The Contractor is required to:

- Adhere to the South African Environment Protection Act, the waste management code of practice and the South African Occupational Health and Safety Act No. 85 of 1993, the regulations promulgated thereunder and Eskom Safety, Health, Environment and Quality (SHEQ) Policy 32-727 for all works.

- Submit a comprehensive method statement of the entire works to the Project Manager for acceptance prior to the start of the works

- Submit a project specific safety file to the Employer for comments / acceptance.

- Submit a detailed level 3 schedule for the works to the Project Manager for acceptance 2 weeks after contract award.

- Prepare earthworks for craneage access and working rigging areas if required.

- Dispose of all rubble at a waste disposal site to be approved by the Employer. The waste disposal site is selected to suit the classification of the materials to be disposed of. Certificates of disposal are submitted to the Employer.

- Continuously monitor the condition in demolition areas and surrounding areas for any hazardous substances and in such case, the Contractor is takes necessary precautionary measures.

- Manage his access to the working areas and the Site.

- Manage his activities on Site to ensure that no interference takes place between his work and that of others.

- Complete "Contract Activities Daily Reports".

- Liaise with the Project Manager regarding utilities and telephone facilities required for his Site establishment if required.

- Liaise with the Project Manager regarding the location of waste disposal sites and rubbish dumps,

- Maintain and promotes labour harmony on the Site and in the working environment.

- Immediately report any potential labour disharmony to the Project Manager.

- Not recruit or employ any personnel from the Employer and Others, without prior acceptance of the Project Manager.

## Construction and Erection

- The Contractor is responsible for the safety of all personnel involved in the works as well as the safety of all personnel at MWP and EAL affected by the construction of the works.

- The Contractor is responsible for the design, erection, maintenance and removal of all temporary or falsework required for the execution of the works.

- The Contractor takes all necessary precautions to ensure that none of the existing structures and services that are not in the scope of works is damaged during any demolition required. In the event that structures and services which are not in the scope of work is damaged, the Contractor is liable to repair or replace the damaged items at their own cost.

- All construction works complies with SANS 1200.

## Quality Management

- The Contractor submits a fully detailed Quality Control Plan (QCP) for acceptance within one week of the Contract Date.

- The Contractor submits a schedule of unpriced orders to be placed and this is updated regularly.

- The Contractor is responsible for defining the level of QA/QC (intervention Points) or inspection to be imposed on his Subcontractors and suppliers of material in the Quality Control Plans (QCPs). This level is based on the criticality of plant and materials, and is submitted to the Employer for acceptance.

- Product data sheets and product samples are submitted for review and acceptance by the Project Manager after contract award and prior to the commencement of work.

- All quality control documentation is submitted to the Project Manager within 7 days of Contract Date.

## Handover

The Contractor is responsible for the provision of a final data book.  The document contains all the relevant documentation, designs, drawings including as-built drawings, materials certificates, and product specifications on all products used, tests and results etc. which were applicable during the contract. The Contractor ensures that all relevant documentation is traceable and cross referenced where applicable.

### Data Book

- Apart from any statutory data packages required, the Contractor also compiles a data package of the relevant drawings, test certificates etc. which he submits to the Project Manager for acceptance. These include, but are not limited to:

- Document List

- Instruction for Work/Purchase Order

- Approved ITP’s, QCP’s

- Method statements and specification adhered to

- Rigging studies (if applicable)

- Risk assessments

- Approved Drawings

- Fabrication Drawings

- Material Certificates

- Approved NDT procedure

- NDT Reports / Results

- Certificate of Manufacture

- Inspection Reports

- Corrosion Protection Consumables Certificates

- Calibration Certificates

- Notifications

- Modifications

- Concessions

- TQ’s, ER’s and communication with Employer

- Non-conformance reports

- Internal Release Notes

- Transport notifications

- Additional

- Calculations for any temporary works that may be required for the safe execution of the works.

- Welding procedure specifications (where required)

- Welder qualifications

- Non-destructive weld test results

- Weld test certificates

- Steel grade certificates (where required)

- As-built data and drawings of the completed works upon handover. As-built drawings are submitted in PDF and native CAD formats (.DGN)

The contents are presented in a hard cover file or files.

The data packages are prepared on a daily basis for all completed work.

Two hard copies and one soft copy of the Data Book are handed to the Employer for acceptance.

Data Books are submitted for review and acceptance before completion of the works to the Employer.

  - Temporary works, Site services & construction constraints

    - Employer’s Site entry and security control, permits, and Site regulations

The site’s are located in a part of an existing campus (both EAL and MWP), with existing buildings all around, most buildings are currently occupied.

- The Contractor attends the Compulsory site meeting prearranged by the Employer prior to submitting tender.

- The Contractor ensures that he familiarizes himself with site conditions.

- Contractors access is limited to the areas as indicated in the scope and Contractor’s staff is prohibited from roaming in the rest of the facility.

- Eskom Holdings indemnifies themselves from any negligent events by the Contractor relating to the scope of the works within the contract period

- The Contractor, his staff and the Sub-contractors maintain identification at all times e.g. Uniforms etc.

- The Contractor is deemed to execute Safety Procedures to ensure the safety of his staff, Sub-contractors, Eskom staff during the Contract Period.

- Use of power and loud tools to be controlled and/or managed with Eskom office management team.

- The safety of the Contractors Employees, Subcontractors and building’s tenants takes preference over the scope of the works of this project.

- All site instructions to be approved and authorised in writing by the Project Manager. If this directive is not adhered to it could result in non-payment.

Access to the site

- The Employer provides the Contractor with an Access Certificate to formally provide access to the site.

- The Contractor ensures that he is familiar with conditions of access to the buildings, which includes constraints to limited parking and no goods lift is available in some of the blocks.

- The Contractor adheres to all the requirements which include, but not restricted to:

  - Identity cards with photographs

  - Cooperation in order to help Eskom provide the customer with a project schedule reflecting the period during which the construction and commissioning activities will take place.

- The Contractor will be responsible for external disputes which may occur regarding the works.

- The Contractor is when necessary or needed, required to make all the necessary arrangements with the Local Authorities via the Building Manager and or Eskom Representative.

    - Restrictions to access on Site, roads, walkways and barricades

Stated above.

    - People restrictions on Site; hours of work, conduct and records

Working after normal working hours and on weekends requires special permission. The Contractor shall give the Employer adequate notice if this is planned.

    - Health and safety facilities on Site

Refer to SHE specifications issued.

    - Environmental controls, fauna & flora, dealing with objects of historical interest

The Contractor shall ensure that all fauna and flora is preserved and protected during his activity on site. All such fauna and flora will be reinstated after completion of the work.

    - Title to materials from demolition and excavation

None.

### Cooperating with and obtaining acceptance of Others

Two week look-ahead schedule to be developed and submitted to Project Manager on a fortnight basis in order to make timeous arrangements for access into occupied buildings with the occupants concerned.

    - Publicity and progress photographs

The Contractor requests approval from Project Manager for any photography and progress photographs prior to undertaking.

    - Contractor’s Equipment

The Contractor keeps an inventory of equipment brought to site. This is verified and acknowledged by Eskom security to allow removal of such equipment when required by the contractor.

Security of materials on sites:

- The Contractor provides own security on site and is held liable for excess of insurance in case of theft or loss.

Material and Bill of Quantities

- Storage and security of material is the responsibility of the Contractor until the Final Completion Certificate is certified. The Contractor is responsible for all costs involved to expedite lost, damaged or stolen material.

    - Equipment provided by the Employer

The Contractor provides all equipment and tools required to complete the works.

### Site services and facilities

The Employer will provide power and water,

The Contractor shall make provision of waste disposal, and submit proof in a form of Waste Disposal Certificates to the Employer for approval

The Contractor shall provide everything else necessary for providing the Works.

### Facilities provided by the Contractor

A clearly demarcated site establishment area will be provided by the Contractor for the following:

- Suitable facilities for Contractor to store all material and equipment

- Suitable facilities for his employees for changing

- Facilities for the consumption of food

- Site offices

- Toilet/Ablution facilities

- Other temporary facilities required by the Contractor

    - Existing premises, inspection of adjoining properties and checking work of Others

Contractor is to investigate existence of any services before commencement of work. Care is to be taken when Contractor is doing demolitions so as not to damage the work of others

    - Survey control and setting out of the works

It is the Contractors responsibility to ensure accuracy when performing setting out of the works,

The Contractor shall provide adequate fastening to existing connection points.

    - Underground services, other existing services, cable and pipe trenches and covers

Where design or construction is potentially affected, the Contractor is required to conduct scanning and investigations to determine the existing services and provides this information as As-Built drawings to the Employer.

    - Control of noise, dust, water and waste

The Contractor takes all precautions necessary to prevent any noise and dust whilst carrying out the work.

### Sequences of construction or installation

N/A.

### Giving notice of work to be covered up

All project communication shall be in writing

### Hook ups to existing works

Contractor stipulates methodology for hooking-up when working in heights and provides notification to the SHE Officer in advance and obtain permission to proceed. The Contractor cannot not hook up for lifting, supporting or for any other reason to any position or existing works in the plant without a written approval by the Project Manager.

  - Completion, testing, commissioning and correction of Defects

    - Work to be done by the Completion Date

The following is mandatory.

The contract is deemed to be complete when the following have been completed in accordance with the scope of work:

- All the boardroom detailed designed installations have been completed with testing and commissioning actioned and accepted by the Employer.

- Signed erection and safety clearance certificates have been submitted.

- The final as-built drawings have been submitted.

- All documentation has been submitted including testing reports and the associated certificates received. All Quality Control Plan (QCP) documentation received.

- Technical, Operating, Maintenance manuals have been delivered

- All documentation and as-built drawings are coded and labelled.

- All guarantees and warranties for all equipment that formed part of the works.

    - Use of the works before Completion has been certified

N/A

    - Materials facilities and samples for tests and inspections

The Contractor provides all Materials, facilities and/or samples required for tests and inspections.

The Employer reserves the right to call for samples of the Equipment offered to inspect the workmanship as the work proceeds and to either accept or reject the Equipment or workmanship.

The Employer’s Acceptance of the workmanship or Equipment must in no way reduce the Contractor's liability to provide complete buildings.

The purpose of these inspections is to reduce the risk of non-compliant Equipment and Materials being transported to site. The presence of the Employer at the inspections does not reduce the Contractor’s responsibility to comply with the contract.

The Contractor is to make arrangements that these inspections are carried out within the boundaries of South Africa. Should any tests or inspections be required outside of the Gauteng Area, the Contractor is to allow in his Tender price for all costs (travel, accommodation, subsistence, etc) for two persons to attend such tests or inspections. Accommodation and subsistence arrangements are to be submitted to the Employer for Acceptance in writing

### Commissioning

Commissioning shall be done after Completion

### Start-up procedures required to put the works into operation

No alterations or adjustments will be made to the Works after functional checks are done without the Employer’s written permission.

At this stage the following must have been achieved:

- Installation and pre-commissioning completed.

- Testing report and the associated certificates received.

- Signed erection and safety clearance certificates received.

- Final Draft of the Technical, Operating, Maintenance manuals delivered.

- All Quality Control Plan (QCP) documentation received.

    - Take over procedures

The Employer takes over sections of the Works on Completion Dates of the Accepted Program.

### Access given by the Employer for correction of Defects

The Project Manager arranges the date and access to site for the Contractor to correct defects. The Contractor updates the site safety file and the records contained inside as per construction regulations. The Contractor will be responsible for ensuring that the area is barricaded before correcting any defects

### Training and technology transfer

After Completion of the contract, the Contractor is required to provide training and transfer system knowledge to the building owner/manager by submitting documented Design Intent, As-built drawings, Operational and Maintenance Manual, Commissioning Records, Commissioning Report and by providing training on all the systems to the building management staff to ensure that they have all the information and understanding needed to operate and maintain the features and systems in the building.

The Contractor is to provide on-site training and training material to the Engineers, Operators and Maintenance personnel prior to taking-over of the works. The training will preferably be offered during the commissioning and testing for end user personnel. The Contractor will, prior to handing over of the works, satisfy the Employer or authorized representative that maintenance and operational personnel are competent and adequately trained to maintain and operate the Plant and Materials supplied.

The training is to cover the following, however not limited to:

- Information provided in the design intent report (including energy/environmental features)

- Measures that can be taken to optimise energy efficiency

- Occupational health and safety (OH&S) issues

- Maintenance requirements and sourcing replacements

- Obtaining and addressing occupant satisfaction feedback

Steps for Conducting On-site Training are to include, but not limited to:

- Preparation

- Introduction

- Explanation

- Demonstration

- Practice Under Supervision

- Conclusion

The operating and maintenance manual must be available during the training of site staff. Site staff must also be made familiar with the contents of that manual.

### Operational maintenance after Completion

N/A

# Plant and Materials standards and workmanship

##### Drawings

The drawings include final general arrangements. Drawings include sections and details to fully identify design concepts, design loadings and any other special features.

Drawings are fully dimensioned and the dimension figures on the drawing are deemed to be correct, even if the drawings are not to scale. No dimensions are obtained from a drawing by scaling.

## Investigation, survey and Site clearance

Contractor shall investigate all existing services before commencement of the works.

All existing services shall be sufficiently protected before commencement of any demolition work

## Material Certificates

The Contractor provides a copy of the Materials Test certificates for all components included in the Data Books.

Codes and Standards

The design complies with the following codes and standards as a minimum

## General

- SANS 10400, The Application of the National Building Regulations

- 240-76992014	Project / Plant Specific Technical Documents and Records Management Work Instruction

- 240-86973501	Engineering drawing Standard

The latest edition, including all amendments up to date of tender of the following specifications, publications and codes of practice shall be read in conjunction with this specification and shall be deemed to form part thereof:

- Occupational Health and Safety Act 85 of 1993 and regulations as amended

Applicable National Standards

- SANS 10400      Series	the Application of the National Building Regulations

- SANS 1200        Series	Standardised specification for civil engineering construction

- Specifications for the basic office ergonomic chair, ISO 26800 of 2011

- Quality Office-certification as per ISO 9001:2000

- SANS 1528-1, Furniture Part 1: Seating

- SANS 1292, Castors for furniture

- SANS 1324, Upholstery fabric

- SANS 10142-1 (The wiring of premises - Part 1: Low-voltage installations)

- SANS 60598-1, Luminaires for interior lighting, street lighting and floodlighting

- SANS 61084-1, Cable trunking and ducting systems for electrical installations – Part 1: General requirements

Employer’s Design Standard:

- 240-56364535: Architectural Design and Green Building Compliance Manual

- 240-103414344: Corporate Identity Manual

- 240-157602340: Universal Access Specifications

- 240-52599753: 	 Workplace Space and Furniture Standard for Commercial Properties

  - Other [as required]

# List of drawings and Documents

## Drawings and Documents issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

Note:  Some drawings may contain both Works Information and Site Information.

| Drawing/Document number | Revision | Title |
| --- | --- | --- |
| 240-53113685 |  | Design Review Procedure |
| 240-56364535 |  | Architectural Design and Green Building Compliance Manual |
| 240-103414344 |  | Corporate Identity Manual |
| 240-157602340 |  | Universal Access Specifications |
| 240-52599753 |  | Workplace Space and Furniture Standard for Commercial Properties |

# C3.2	Contractor’s Works Information

The Contractor conducts the required site assessments (infrastructure for water, electrical supply etc.) to complete the detailed design.

The Contractor develops detailed design and construction drawings in accordance with the Employers concept information, Specifications and Standards.

The construction is completed in accordance with the Contractor’s accepted detailed design

The Contractor provides a methodology and schedule for the execution of the works.

The Contractor provides a cost for the full execution of the works.

The Contractor is responsible for obtaining any permission, approval, concession, permit or licence required prior to commencement of the works

The Contractor to produce as built drawings to be submitted to the Employer at the end of the project

# Part 4: Site Information

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C4 | Site Information |  |
|  | Total number of pages |  |

# Part 4: Site Information

# Description of the Site and its Surroundings

The boardrooms are located within the EAL and MWP campuses. These are live buildings operating daily.

# General description

# Please refer to detailed layouts for all boardrooms in Annexure A

# Hidden services

All existing services shall be verified and confirmed by the contractor before starting with the work. This shall also be discussed with the project team to plan accordingly and confirm before starting with the work.

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za