Eskom Holdings SOC Ltd

Contract number ______________

project and contract title: DAM APPROVED PROFESSIONAL PERSON (APP) SERVICES FOR ESKOM gENERATION PEAKING

	[image: image3.jpg]R Eskom






NEC3 Professional Services Contract (PSC3)

	Contract between


	Eskom Holdings SOC Ltd

(Reg No. 2002/015527/30)

	and


	[Insert at award stage]

(Reg No. ___________ )

	for


	THE PROVISION OF A DAM APPROVED PROFESSIONAL PERSON (APP) SERVICES FOR ESKOM GENERATION PEAKING
Insert title of the services

	
	

	Contents:
	
	No of pages

	Part C1
	Agreements & Contract Data
	[●]

	Part C2
	Pricing Data
	[●]

	Part C3
	Scope of Work:  The Scope
	[●]

	
	
	

	CONTRACT No.
	[Insert at award stage]

	
	

	
	

	
	


PART C1:
AGREEMENTS & CONTRACT DATA

	Document reference
	Title
	No of pages

	C1.1
	Form of Offer & Acceptance

[to be inserted from Returnable Documents at award stage]
	[●]

	C1.2a
	Contract Data provided by the Employer
	[●]

	C1.2b
	Contract Data provided by the Consultant

[to be inserted from Returnable Documents at award stage]
	[●]

	
	
	


C1.1 Form of Offer & Acceptance

Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Title of the Contract

The tenderer, identified in the Offer signature block, has

	either
	examined the documents listed in the Tender Data and addenda thereto as listed in the Returnable Schedules, and by submitting this Offer has accepted the Conditions of Tender.

	or
	examined the draft contract as listed in the Acceptance section and agreed to provide this Offer.


By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Consultant under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data. 

	The offered total of the Prices exclusive of VAT is 
	R     

	Value Added Tax @ 14% is
	R     

	The offered total of the Prices inclusive of VAT is
	R     

	(in words)      



If Option E or G apply, for each offered total insert in brackets, “(Not Applicable – Cost reimbursable)” 
This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Consultant in the conditions of contract identified in the Contract Data.

	Signature(s)


	
	
	

	Name(s)


	
	
	

	Capacity


	
	
	

	For the tenderer:


	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	

	
	


Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Consultant the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in: 

Part C1

Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2

Pricing Data

Part C3

Scope of Work: The Scope

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed and signed original copy of this document, including the Schedule of Deviations (if any).  

	Signature(s)


	
	
	

	Name(s)
	
	
	

	Capacity


	
	
	

	for the Employer


	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	


Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

Schedule of Deviations 

Note:

1.  To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

2. The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

3. A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

	No.
	Subject
	Details

	1
	     
	     

	2
	     
	     

	3
	     
	     

	4
	     
	     

	5
	     
	     

	6
	     
	     

	7
	     
	     

	
	
	


By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.  

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement. 

	
	For the tenderer:


	
	For the Employer



	Signature


	
	
	

	Name
	
	
	

	Capacity


	
	
	

	On behalf of
	(Insert name and address of organisation)


	
	(Insert name and address of organisation)



	Name & signature of witness
	
	
	

	Date
	
	
	


C1.2 PSC3 Contract Data

Part one - Data provided by the Employer
[Instructions to the contract compiler:  (delete these two notes in the final draft of a contract)

1. Please read the relevant clauses in the conditions of contract before you enter data.  The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.  

2. The PSC3 options are identified by shading in the left hand column.  In the event that the option is not required select and delete the whole row.  

3. Where the symbol “[●]”is used data is required to be inserted relevant to the clause and statement which requires it.]

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

	Clause
	Statement
	Data

	1
	General
	

	
	The conditions of contract are the core clauses and the clauses for main Option 
	

	
	
	A:

Priced contract with activity schedule

	
	dispute resolution Option
	W1:
Dispute resolution procedure

	
	and secondary Options 
	

	
	
	X1:

Price adjustment for inflation

	
	
	X2

Changes in the law

	
	
	X5:

Sectional Completion

	
	
	X7:

Delay damages

	
	
	X9:

Transfer of rights

	
	
	X10

Employer’s Agent

	
	
	X11:
Termination by the Employer

	
	
	X18:
Limitation of liability

	
	
	Z:

Additional conditions of contract

	
	of the NEC3 Professional Services Contract (April 2013)

	If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data

	10.1
	The Employer is (Name):
	Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa

	
	Address
	Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg

	11.2(9)
	The services are 
	Provision of a dam approved professional person (app) services for Eskom Generation Peaking

	11.2(10)
	The following matters will be included in the Risk Register
	· The small hydro station dams are only accessible by 4x4 vehicles due to bad road conditions.
· Minutes of early warning meetings and decisions resulting from risk reduction meetings

	11.2(11)
	The Scope is in  
	Part 3: Scope of Work

	12.2
	The law of the contract is the law of 
	The Republic of South Africa

	13.1
	The language of this contract is 
	English

	13.3
	The period for reply is
	5 working days

	13.6
	The period for retention is 
	5 years following Completion or earlier termination.

	2
	The Parties’ main responsibilities
	

	25.2
	The Employer provides access to the following persons, places and things
	access to
	access date

	
	Ingula Pumped Storage Scheme
	1
	Bedford Dam
	starting date of the contract

	
	Ingula Pumped Storage Scheme
	2
	Bramhoek Dam
	starting date of the contract

	
	Ingula Pumped Storage Scheme
	3
	Farm Dam
	starting date of the contract

	
	Small Hydro
	4
	Ncora Holding Dam
	starting date of the contract

	
	Small Hydro
	5
	First Falls Dam
	starting date of the contract

	
	Small Hydro
	6
	Second Falls Dam
	starting date of the contract

	
	Small Hydro
	7
	Mbashe Dam
	starting date of the contract

	3
	Time
	

	31.2
	The starting date is.
	[●] Planned 01 April 2026

	11.2(3)
	The completion date for the whole of the services is.
	[●] Planned 31 March 2031

	
	
	
	
	


	11.2(6)
	The key dates and the conditions to be met are:
	 

	
	 
	

	
	Condition to be met
	key date

	
	
	

	
	Ingula Pumped Storage Scheme - Bedford Dam
	2031 May 26

	
	 
	 

	
	Ingula Pumped Storage Scheme - Bramhoek Dam
	2031 June 25

	
	 
	 

	
	Ingula Pumped Storage Scheme - Farm Dam
	2031 July 25

	
	 
	 

	
	Small Hydro -  First Falls Dam
	2031 August 26

	
	 
	 

	
	Small Hydro -  Second Falls Dam
	2031 September 25

	
	 
	 

	
	Small Hydro - Mbashe Dam
	2031 October 27

	
	 
	 

	
	Small Hydro - Ncora Holding Dam
	2031 November 26


	
	
	
	
	

	
	
	
	
	

	31.1
	The Consultant is to submit a first programme for acceptance within 
	2 weeks of the Contract Date.

	32.2
	The Consultant submits revised programmes at intervals no longer than 
	1 Month.

	4
	Quality
	

	40.2
	The quality policy statement and quality plan are provided within
	2 week of the Contract Date.

	42.2
	The defects date is 
	52 weeks after Completion of the whole of the services.

	5
	Payment
	

	50.1
	The assessment interval is 
	On the 25th of every month.

	50.3
	The expenses stated by the Employer are
	Item
	Amount

	
	
	As per pricing Data Option A refer to C2.2
	[●]

	
	
	[●]
	[●]

	
	
	[●]
	[●]

	
	
	[●]
	[●]

	51.1
	The period within which payments are made is 
	30 days after receipt of an acceptable Tax invoice and all relevant supporting documentation. Compensation Events will take longer as this will have to go through additional processes.

	51.2
	The currency of this contract is the 
	South African Rand (ZAR)

	51.5
	The interest rate is 
	the publicly quoted prime rate of interest charged by [●] Standard Bank of South Africa Limited at the time an amount payable in SA Rand was due,

and 

the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove



	6
	Compensation events
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	7
	Rights to material
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	8
	Indemnity, insurance and liability
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	82.1
	The Consultant’s total liability to the Employer for all matters arising under or in connection with this contract, other than the excluded matters, is limited to
	The total of the Prices

	9
	Termination
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	10
	Data for main Option clause
	

	A
	Priced contract with activity schedule
	

	21.3
	The Consultant prepares forecasts of the total expenses at intervals of no longer than
	4 weeks.

	11
	Data for Option W1
	

	W1.1
	The Adjudicator is 
	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him.  (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). 

	W1.2(3)
	The adjudicator nominating body is: 
	the Chairman of the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering. (See www.ice-sa.org.za).

	W1.4(2)
	The tribunal is: 
	arbitration

	W1.4(5)
	The arbitration procedure is 
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	
	The place where arbitration is to be held is
	[●] South Africa

	
	The person or organisation who will choose an arbitrator 

· if the Parties cannot agree a choice or

· if the arbitration procedure does not state who selects an arbitrator, is
	the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.

	12
	Data for secondary Option clauses
	

	X1
	Price adjustment for inflation
	

	X1.1
	The index is 
	[●].

	
	The staff rates are

{state whether “Fixed at the Contract Date and are not variable with changes in salary paid to individuals” or “Variable with changes in salary paid to individuals”}
	[●]

	X2
	Changes in the law
	

	X2.1
	The law of the project is 
	South African Law

	X5
	Sectional Completion
	

	
	
	
	
	

	X5.1
	The completion date for each section of the services is:
	 

	
	
	section
	description
	completion date

	 
	
	
	
	

	
	
	 
	Ingula and Small Hydro Dams
	 

	
	 
	1
	Training of Employer’s staff
	2026 October 30

	
	
	2
	Liaison with authorities for the whole of the services
	As required in order to complete the scope of services

	
	
	3
	Providing designs, scope of works and technical specifications for the actions or recommendations
	As required in order to complete the scope of services

	
	 
	A
	Ingula Pumped Storage Scheme - Bedford Dam
	 

	
	 
	A1
	Dam Safety Evaluation Report
	2026 October 30

	
	 
	A2
	Dam Safety Evaluation Report
	2031 March 26

	
	 
	A3
	Undertake Stability Checks
	2026 December 01

	
	 
	A4
	Undertake stability checks
	2031 April 25

	
	 
	A5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2026 December 31

	
	 
	A6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 May 26

	
	 
	A7
	Review and update the existing Dam Information;Iincluded but not limited to EPP, Hydrology, Dam Break Analysis etc. and Issue the Assessment Report.
	2026 October 30

	
	 
	A8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2026 November 30

	
	 
	A9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 March 03

	
	 
	A10
	Inspections and reporting 
	2026 October 30

	
	 
	A11
	Inspections and reporting 
	2027 April 30

	
	 
	A12
	Inspections and reporting 
	2027 October 29

	
	 
	A13
	Inspections and reporting 
	2028 April 28

	
	 
	A14
	Inspections and reporting 
	2028 October 27

	
	 
	A15
	Inspections and reporting 
	2029 April 27

	
	 
	A16
	Inspections and reporting 
	2029 October 26

	
	 
	A17
	Inspections and reporting 
	2030 April 26

	
	 
	A18
	Inspections and reporting 
	2030 October 25

	
	 
	A19
	Inspections and reporting 
	2031 April 25

	
	 
	A20
	Conduct lidar and bathymetric survey and issue report.
	2028 April 28

	
	 
	 
	 
	 

	
	 
	B
	Ingula Pumped Storage Scheme - Bramhoek Dam
	 

	
	 
	B1
	Dam Safety Evaluation Report
	2026 November 30

	
	 
	B2
	Dam Safety Evaluation Report
	2031 April 25

	
	 
	B3
	Undertake Stability Checks
	2026 December 31

	
	 
	B4
	Undertake stability checks
	2031 May 26

	
	 
	B5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 January 29

	
	 
	B6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 June 25

	
	 
	B7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2026 November 30

	
	 
	B8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2026 December 30

	
	 
	B9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 March 31

	
	 
	B10
	Inspections and reporting 
	2026 October 30

	
	 
	B11
	Inspections and reporting 
	2027 April 30

	
	 
	B12
	Inspections and reporting 
	2027 October 29

	
	 
	B13
	Inspections and reporting 
	2028 April 28

	
	 
	B14
	Inspections and reporting 
	2028 October 27

	
	 
	B15
	Inspections and reporting 
	2029 April 27

	
	 
	B16
	Inspections and reporting 
	2029 October 26

	
	 
	B17
	Inspections and reporting 
	2030 April 26

	
	 
	B18
	Inspections and reporting 
	2030 October 25

	
	 
	B19
	Inspections and reporting 
	2031 April 25

	
	 
	B20
	Conduct lidar and bathymetric survey and issue report.
	2028 May 26

	
	 
	 
	 
	 

	
	 
	C
	Ingula Pumped Storage Scheme - Farm Dam
	 

	
	 
	C1
	Dam Safety Evaluation Report
	2026 December 30

	
	 
	C2
	Dam Safety Evaluation Report
	2031 May 26

	
	 
	C3
	Undertake Stability Checks
	2027 January 29

	
	 
	C4
	Undertake stability checks
	2031 June 25

	
	 
	C5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 February 26

	
	 
	C6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 July 25

	
	 
	C7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2026 December 30

	
	 
	C8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2027 January 29

	
	 
	C9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 April 30

	
	 
	C10
	Inspections and reporting 
	2026 October 30

	
	 
	C11
	Inspections and reporting 
	2027 April 30

	
	 
	C12
	Inspections and reporting 
	2027 October 29

	
	 
	C13
	Inspections and reporting 
	2028 April 28

	
	 
	C14
	Inspections and reporting 
	2028 October 27

	
	 
	C15
	Inspections and reporting 
	2029 April 27

	
	 
	C16
	Inspections and reporting 
	2029 October 26

	
	 
	C17
	Inspections and reporting 
	2030 April 26

	
	 
	C18
	Inspections and reporting 
	2030 October 25

	
	 
	C19
	Inspections and reporting 
	2031 April 25

	
	 
	C20
	Conduct lidar and bathymetric survey and issue report.
	2028 June 23

	
	 
	 
	 
	 

	
	 
	D
	Small Hydro -  First Falls Dam
	 

	
	 
	D1
	Dam Safety Evaluation Report
	2027 January 29

	
	 
	D2
	Dam Safety Evaluation Report
	2031 June 25

	
	 
	D3
	Undertake Stability Checks
	2027 February 26

	
	 
	D4
	Undertake stability checks
	2031 July 25

	
	 
	D5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 March 30

	
	 
	D6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 August 26

	
	 
	D7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2027 January 29

	
	 
	D8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2027 February 26

	
	 
	D9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 May 30

	
	 
	D10
	Inspections and reporting 
	2026 October 30

	
	 
	D11
	Inspections and reporting 
	2027 April 30

	
	 
	D12
	Inspections and reporting 
	2027 October 29

	
	 
	D13
	Inspections and reporting 
	2028 April 28

	
	 
	D14
	Inspections and reporting 
	2028 October 27

	
	 
	D15
	Inspections and reporting 
	2029 April 27

	
	 
	D16
	Inspections and reporting 
	2029 October 26

	
	 
	D17
	Inspections and reporting 
	2030 April 26

	
	 
	D18
	Inspections and reporting 
	2030 October 25

	
	 
	D19
	Inspections and reporting 
	2031 April 25

	
	 
	D20
	Conduct topographical survey
	2027 March 02

	
	 
	D21
	Conduct topographical survey
	2027 August 31

	
	 
	D22
	Conduct topographical survey
	2028 January 31

	
	 
	D23
	Conduct topographical survey
	2028 July 31

	
	 
	D24
	Conduct topographical survey
	2029 January 29

	
	 
	D25
	Conduct topographical survey
	2029 July 30

	
	 
	D26
	Conduct topographical survey
	2030 January 28

	
	 
	D27
	Conduct topographical survey
	2030 July 29

	
	 
	D28
	Conduct topographical survey
	2031 January 27

	
	 
	D29
	Conduct topographical survey
	2031 July 28

	
	 
	D30
	Conduct lidar and bathymetric survey and issue report.
	2028 July 21

	
	 
	 
	
	 

	
	 
	E
	Small Hydro -  Second Falls Dam
	 

	
	 
	E1
	Dam Safety Evaluation Report
	2027 February 26

	
	 
	E2
	Dam Safety Evaluation Report
	2031 July 25

	
	 
	E3
	Undertake Stability Checks
	2027 March 30

	
	 
	E4
	Undertake stability checks
	2031 August 26

	
	 
	E5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 April 29

	
	 
	E6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 September 25

	
	 
	E7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2027 February 26

	
	 
	E8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2027 March 30

	
	 
	E9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 June 30

	
	 
	E10
	Inspections and reporting 
	2026 October 30

	
	 
	E11
	Inspections and reporting 
	2027 April 30

	
	 
	E12
	Inspections and reporting 
	2027 October 29

	
	 
	E13
	Inspections and reporting 
	2028 April 28

	
	 
	E14
	Inspections and reporting 
	2028 October 27

	
	 
	E15
	Inspections and reporting 
	2029 April 27

	
	 
	E16
	Inspections and reporting 
	2029 October 26

	
	 
	E17
	Inspections and reporting 
	2030 April 26

	
	 
	E18
	Inspections and reporting 
	2030 October 25

	
	 
	E19
	Inspections and reporting 
	2031 April 25

	
	
	E20
	Conduct topographical survey
	2027 March 02

	
	 
	E21
	Conduct topographical survey
	2027 August 31

	
	 
	E22
	Conduct topographical survey
	2028 January 31

	
	 
	E23
	Conduct topographical survey
	2028 July 31

	
	 
	E24
	Conduct topographical survey
	2029 January 29

	
	 
	E25
	Conduct topographical survey
	2029 July 30

	
	 
	E26
	Conduct topographical survey
	2030 January 28

	
	 
	E27
	Conduct topographical survey
	2030 July 29

	
	 
	E28
	Conduct topographical survey
	2031 January 27

	
	 
	E29
	Conduct topographical survey
	2031 July 28

	
	 
	E30
	Conduct lidar and bathymetric survey and issue report.
	2028 August 18

	
	 
	 
	 
	 

	
	 
	F
	Small Hydro - Mbashe Dam
	 

	
	 
	F1
	Dam Safety Evaluation Report
	2027 March 30

	
	 
	F2
	Dam Safety Evaluation Report
	2031 August 26

	
	 
	F3
	Undertake Stability Checks
	2027 April 29

	
	 
	F4
	Undertake stability checks
	2031 September 25

	
	 
	F5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 May 31

	
	 
	F6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 October 27

	
	 
	F7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2027 March 30

	
	 
	F8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2027 April 29

	
	 
	F9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 July 30

	
	 
	F10
	Inspections and reporting 
	2026 October 30

	
	 
	F11
	Inspections and reporting 
	2027 April 30

	
	 
	F12
	Inspections and reporting 
	2027 October 29

	
	 
	F13
	Inspections and reporting 
	2028 April 28

	
	 
	F14
	Inspections and reporting 
	2028 October 27

	
	 
	F15
	Inspections and reporting 
	2029 April 27

	
	 
	F16
	Inspections and reporting 
	2029 October 26

	
	 
	F17
	Inspections and reporting 
	2030 April 26

	
	 
	F18
	Inspections and reporting 
	2030 October 25

	
	 
	F19
	Inspections and reporting 
	2031 April 25

	
	 
	F20
	Conduct topographical survey
	2027 March 02

	
	
	F21
	Conduct topographical survey
	2027 August 31

	
	 
	F22
	Conduct topographical survey
	2028 January 31

	
	 
	F23
	Conduct topographical survey
	2028 July 31

	
	 
	F24
	Conduct topographical survey
	2029 January 29

	
	 
	F25
	Conduct topographical survey
	2029 July 30

	
	 
	F26
	Conduct topographical survey
	2030 January 28

	
	 
	F27
	Conduct topographical survey
	2030 July 29

	
	 
	F28
	Conduct topographical survey
	2031 January 27

	
	 
	F29
	Conduct topographical survey
	2031 July 28

	
	 
	F30
	Conduct lidar and bathymetric survey and issue report.
	2028 September 15

	
	 
	 
	 
	 

	
	 
	G
	Small Hydro - Ncora Holding Dam
	 

	
	 
	G1
	Dam Safety Evaluation Report
	2027 April 29

	
	 
	G2
	Dam Safety Evaluation Report
	2031 September 25

	
	 
	G3
	Undertake Stability Checks
	2027 May 31

	
	 
	G4
	Undertake stability checks
	2031 October 27

	
	 
	G5
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2027 June 30

	
	 
	G6
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	2031 November 26

	
	 
	G7
	Reviewing and updating of existing Bedford dam information; include but not limited to EPP, Hydrology, dam break analysis etc. and issue the assessment report.
	2027 April 29

	
	 
	G8
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2027 May 31

	
	 
	G9
	Reviewing, updating and compilation of Bedford dam Operating and Maintenance manuals
	2031 September 02

	
	 
	G10
	Inspections and reporting 
	2026 October 30

	
	 
	G11
	Inspections and reporting 
	2027 April 30

	
	 
	G12
	Inspections and reporting 
	2027 October 29

	
	 
	G13
	Inspections and reporting 
	2028 April 28

	
	 
	G14
	Inspections and reporting 
	2028 October 27

	
	 
	G15
	Inspections and reporting 
	2029 April 27

	
	 
	G16
	Inspections and reporting 
	2029 October 26

	
	 
	G17
	Inspections and reporting 
	2030 April 26

	
	 
	G18
	Inspections and reporting 
	2030 October 25

	
	 
	G19
	Inspections and reporting 
	2031 April 25

	
	 
	G20
	Conduct topographical survey
	2027 March 02

	
	
	G21
	Conduct topographical survey
	2027 August 31

	
	 
	G22
	Conduct topographical survey
	2028 January 31

	
	 
	G23
	Conduct topographical survey
	2028 July 31

	
	 
	G24
	Conduct topographical survey
	2029 January 29

	
	 
	G25
	Conduct topographical survey
	2029 July 30

	
	 
	G26
	Conduct topographical survey
	2030 January 28

	
	 
	G27
	Conduct topographical survey
	2030 July 29

	
	 
	G28
	Conduct topographical survey
	2031 January 27

	
	 
	G29
	Conduct topographical survey
	2031 July 28

	
	 
	G30
	Conduct lidar and bathymetric survey and issue report.
	2028 October 13

	
	
	
	
	


	
	
	

	
	
	

	X5 & X7
	Sectional Completion and delay damages used together
	

	X7.1

X5.1
	Delay damages for late Completion of each section of the services are: 
	section
	Description (Amount per week or part thereof)
	Maximum % damages

	
	
	1
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	2
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	3
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	4
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	5
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	6
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	
	7
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	
	Remainder of the services
	
	1% of the Accepted Contract Amount
	20% of the final Contract Price in the aggregate

	X7
	Delay damages
	

	X7.1
	Delay damages for late Completion of the whole of the services are
	1% of the Accepted Contract Amount (Amount per week or part thereof). The maximum % damage is 20% of the final Contract Price in the aggregate.

	X9
	Transfer of rights
	Applicable as per core clause X9  PSC3 April 2013.

	X10
	The Employer’s Agent
	

	X10.1
	The Employer’s Agent is
	

	
	Name:
	Neil Davids

	
	Address
	15 Pasita Street, Rosenpark, 

Cape Town 7550, South Africa
Davidsnn@eskom.co.za

	
	The authority of the Employer’s Agent is
	to carry out all the actions of the Employer

	X11
	Termination by the Employer
	Applicable as per core clause X11 PSC3 April 2013.

	X18
	Limitation of liability
	

	X18.1
	The Consultant’s liability to the Employer for indirect or consequential loss is limited to:
	R0.00 (Zero Rand)

	X18.2
	The Consultant’s liability to the Employer for Defects that are not found until after the defects date is limited to:
	The total of the Prices



	X18.3
	The end of liability date is 
	Five years after Completion of the whole of the services/task order.

	Z
	The Additional conditions of contract are
	Z1 to Z14 always apply.

	
	

	Z1
	Cession delegation and assignment

	Z1.1
	The Consultant does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer.

	Z1.2
	Notwithstanding the above, the Employer may on written notice to the Consultant cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. 

	
	

	Z2
	Joint ventures

	Z2.1
	If the Consultant constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract.

	Z2.2
	Unless already notified to the Employer, the persons or organisations notify the Employer within two weeks of the Contract Date of the key person who has the authority to bind the Consultant on their behalf.

	Z2.3
	The Consultant does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Consultant in writing.

	
	

	Z3
	Change of Broad Based Black Economic Empowerment (B-BBEE) status

	Z3.1
	Where a change in the Consultant’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Consultant’s B-BBEE status, the Consultant notifies the Employer within seven days of the change.

	Z3.2
	The Consultant is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer.

	Z3.3
	Where, as a result, the Consultant’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Consultant’s obligation to Provide the Services.

	Z3.4
	Failure by the Consultant to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in core clause 91.  The payment on termination includes a deduction of the forecast of the additional cost to the Employer of completing the whole of the services in addition to the amounts due in terms of core clause 92.1.

	
	


	Z4
	Confidentiality

	Z4.1
	The Consultant does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Consultant, enters the public domain or to information which was already in the possession of the Consultant at the time of disclosure (evidenced by written records in existence at that time).  Should the Consultant disclose information to Others in terms of clause 23.1, the Consultant ensures that the provisions of this clause are complied with by the recipient.

	Z4.2
	If the Consultant is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer.

	Z4.3
	In the event that the Consultant is, at any time, required by law to disclose any such information which is required to be kept confidential, the Consultant, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure.  In the event that such protective order is not, or cannot, be obtained, then the Consultant may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed.

	Z4.4
	The taking of images (whether photographs, video footage or otherwise) of the Employer’s project works or any portion thereof, in the course of Providing the Services and after Completion, requires the prior written consent of the Employer.  All rights in and to all such images vests exclusively in the Employer.  

	
	

	Z5
	Waiver and estoppel: Add to core clause 12.3:

	Z5.1
	Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing.

	
	

	Z6
	Provision of a Tax Invoice.  Add to core clause 51

	Z6.1
	The Consultant (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment.

	
	

	Z7
	Notifying compensation events

	Z7.1
	Delete from the last sentence in core clause 61.3, “unless the Employer should have notified the event to the Consultant but did not”.

	
	

	Z8
	Employer’s limitation of liability

	Z8.1
	The Employer’s liability to the Consultant for the Consultant’s indirect or consequential loss is limited to R0.00 (zero Rand)

	
	

	Z9
	Termination: Add to core clause 90.1, at the second main bullet point, fourth sub-bullet point, after the words "against it":  

	Z9.1
	   or had a business rescue order granted against it.

	
	

	Z10
	Delay damages: Addition to secondary Option X7 Delay damages (if applicable in this contract)

	Z10.1
	If the Consultant’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Consultant’s obligation to Provide the Services.

	Z10.2
	If the Employer terminates in terms of this clause, the procedures on termination are those stated in core clause 91.  The payment on termination includes a deduction of the forecast of the additional cost to the Employer of completing the whole of the services in addition to the amounts due in terms of core clause 92.1.

	
	

	Z11
	Ethics

	For the purposes of this Z-clause, the following definitions apply:

	Affected Party
	means, as the context requires, any party, irrespective of whether it is the Consultant or a third party, such party’s employees, agents, or Subconsultants or Subconsultant’s employees, or any one or more of all of these parties’ relatives or friends,

	Coercive Action
	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

	Collusive Action
	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

	Committing Party
	means, as the context requires, the Consultant, or any member thereof in the case of a joint venture, or its employees, agents, or Subconsultants or the Subconsultant’s employees,

	Corrupt Action
	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

	Fraudulent Action
	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

	Obstructive Action
	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and

	Prohibited Action
	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

	Z11.1
	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

	Z11.2
	The Employer may terminate the Consultant’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Consultant did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Consultant’s obligation to Provide the Services for this reason.

	Z11.3
	If the Employer terminates the Consultant’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

	Z11.4
	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Consultant ensures that the Committing Party co-operates fully with an investigation.

	
	

	Z12
	Insurance

	Z12.1
	Replace core clause 81 with the following:

	81.1
	When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force.

	81.2
	The Consultant provides the insurances stated in the Insurance Table A from the starting date until the earlier of Completion and the date of the termination certificate.

	
	INSURANCE TABLE A

	
	Insurance against

Minimum amount of cover

For the period following Completion of the whole of the services or earlier termination

Liability of the Consultant for claims made against him arising out of his failure to use the skill and care normally used by professionals providing services similar to the services
To be confirmed during Clarification Meeting on 20 January 2026. 
6 years
Liability for death of or bodily injury to a person (not an employee of the Consultant) or loss of or damage to property resulting from an action or failure to take action by the Consultant
Loss of or damage to property:

The replacement cost where not covered by the Employer’s insurance

The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance
Bodily injury to or death of a person:

The amount required by the applicable law.

6 years
Liability for death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with this contract

The amount required by the applicable law

6 years


	81.3
	The Employer provides the insurances stated in the Insurance Table B.

	
	INSURANCE TABLE B

	
	Insurance against or name of policy

Minimum amount of cover or minimum limit of indemnity

Assets All Risk

Per the insurance policy document

Contract Works insurance

Per the insurance policy document

Environmental Liability

Per the insurance policy document
General and Public Liability

Per the insurance policy document
Transportation (Marine)

Per the insurance policy document
Motor Fleet and Mobile Plant

Per the insurance policy document
Terrorism

Per the insurance policy document
Cyber Liability

Per the insurance policy document

Nuclear Material Damage and Business Interruption

Per the insurance policy document

Nuclear Material Damage Terrorism

Per the insurance policy document




	

	

	Z13
	Intellectual Property – Eskom owning Intellectual Property

	“Intellectual Property”
	means (a) patents, trademarks, service marks, rights in designs, trade names, trade secrets, know how, copyrights and topography rights, in each case whether registered or not; (b) applications for registration of any of them; (c) rights under licences and consents in relation to any of them; (d) all forms of protection of a similar nature or having equivalent or similar effect to any of them which may subsist anywhere in the world.

	“Background Intellectual Property"
	means any and all Intellectual Property rights that are not Foreground Intellectual Property, and are owned or controlled by the relevant party or licensed to the relevant party prior to or outside of the services but required for the purposes of the services.

	“Foreground Intellectual Property”
	means all Intellectual Property rights and other matter capable of being the subject of intellectual property rights that is conceived, first reduced to practice or writing or developed in whole or in substantial part in the course of the execution of the services and rights which are developed substantially as a result of the services.  Any services will be developed, changed, modified and/or improved specifically for the Purposes will be Foreground Intellectual Property.  Any data or any other information relating to Employer’s proprietary information generated from the use of the Consultant’s Background Intellectual Property.

	“Intellectual Property”
	means (a) patents, trademarks, service marks, rights in designs, trade names, trade secrets, know how, copyrights and topography rights, in each case whether registered or not; (b) applications for registration of any of them; (c) rights under licences and consents in relation to any of them; (d) all forms of protection of a similar nature or having equivalent or similar effect to any of them which may subsist anywhere in the world.

	Z13.1
	The Consultant retains ownership of all Background Intellectual Property rights made by or on behalf of the Consultant as part of the services in information or material it uses in carrying out the services.

	Z13.2
	All Foreground Intellectual Property rights, contained in any developed materials which are created by the Consultant or on behalf of the Consultant, for the purposes of and in support of the execution of the services Employer’s IP vest with the Employer.

	Z13.3
	Any data or any other information relating to Employer’s proprietary information generated from the use of the Consultant’s Background Intellectual Property, the copyright therein shall be owned by the Employer.

	Z13.4
	The Consultant acknowledges that all rights, title, and interest in and to the Foreground Intellectual Property that may result or originate from or be developed in execution of the services vests in the Employer and that the Consultant has no claim of any nature in and to the Foreground Intellectual Property.  

	Z13.5
	The Consultant ensures that a copyright notice is incorporated or embossed or labelled on the Foreground Intellectual Property, where the Employer is reflected as the owner of the Foreground Intellectual Property.  

	Z13.6
	The Consultant is obliged to provide Foreground Intellectual Property manufacturing documents, designs, processes and/or specifications to the Employer before/on the completion date.

	Z13.7
	The Consultant procures that each Sub-Consultant executes all and any services and takes all and any other actions as may be required, in order to give effect to this Agreement.

	Z13.8
	The Employer retains all Background Intellectual Property rights in all documents made by or on behalf of the Employer including all documents and requirements provided prior to or during the execution of the services. The Consultant does not, without the written consent, of the Employer, copy, use or issue to a third party any of the Employer’s Background Intellectual Property documents and requirements except for the purposes of executing the services.

	Z13.9
	Either party procures that any third party executes confidentiality undertakings not to disclose to any other third parties, any of the Employer’s Background Intellectual Property and IP documents and requirements at all, in respect of the Employer, or the Background Intellectual Property, in respect of the Consultant.

	Z13.10
	Third Party Claims:

	Z13.10.1
	In the event of any claims being made or actions brought against the Employer, on the ground that the Consultant infringed any patent, trade mark or copyright, the Consultant is notified thereof and at its own expense, conducts all negotiations in consultation with the Employer for the settlement of the claim and litigation that may arise from such alleged infringement, provided that the Employer will not bear any financial burden or losses.

	Z13.10.2
	Save where the Consultant fails to take over the conduct of the negotiation or litigation within a reasonable time of the notification of the alleged infringement, the Employer does not make any admission which might be prejudicial to the Consultant’s position. The Employer, at the request and the cost of the Consultant affords it all reasonable technical assistance that the Employer is able to provide for the purpose of contesting any such claim or action.

	Z13.10.3
	Should it be held in any such action that any such protected rights have been infringed, as definitely stated by a judgment of the court before which the action is brought, the Consultant, at its own expense and in consultation with the Employer, either:

a. procures for Employer the right to continue to use the affected item or design, or

b. replaces the said affected item or design with a non-infringing item, or

c. provides a design of equivalent quality or modify such affected item or design so as to make it non-infringing without affecting the quality.

	Z13.10.4
	Notwithstanding anything contained in this contract, the foregoing sets forth the entire responsibility of Consultant with respect to claims relating to infringement.

	Z13.10.5
	Where it is alleged that the Employer has committed an infringement as intended vis-à-vis the Consultant as set out in the third party intellectual property infringement clause, the Employer has the same rights and obligations as the Consultant, mutatis mutandis, as regards such alleged infringement.

	Z13.10.6
	The Consultant herewith indemnifies the Employer and undertakes to keep the Employer indemnified against all claims of whatsoever nature, real or imagined, which may be made against the Employer arising from the infringement of any third party intellectual property rights.

	
	

	Z14
	Asbestos

	For the purposes of this Z-clause, the following definitions apply:

	AAIA
	means approved asbestos inspection authority.

	ACM
	means asbestos containing materials.

	AL
	means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL.

	Ambient Air
	means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet.

	Compliance Monitoring
	means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	OEL
	means occupational exposure limit.

	Parallel Measurements
	means measurements performed in parallel, yet separately, to existing measurements to verify validity of results.

	Safe Levels
	means  airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	Standard
	means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles.

	SANAS
	means the South African National Accreditation System.

	TWA
	means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA.

	Z14.1
	The Employer ensures that the Ambient Air in the area where the Consultant will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM.

	Z14.2
	Upon written request by the Consultant, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Consultant may perform Parallel Measurements and related control measures at the Consultant’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan.

	Z14.3
	The Employer manages asbestos and ACM according to the Standard.

	Z14.4
	In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe.

	Z14.5
	The Consultant’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable.

	Z14.6
	The Consultant continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001.

	Z14.7
	Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation.


C1.2 Contract Data

Part two - Data provided by the Consultant
[Instructions to the tendering consultant:  (delete these notes in the final draft of a contract)

1. The tendering consultant is advised to read both the NEC3 Professional Services Contract, April 2013 and the relevant parts of its Guidance Notes (PSC3-GN)
 in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 158 & 159 of the PSC3 April 2013 Guidance Notes.  

2. The number of the clause in the PSC3 which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.  

3. Whenever a cell is shaded in the left hand column it denotes this data is optional in PSC3 and would be required in relation to the option selected.  The Employer should already have made the selection and deleted the rows not required.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

	Clause
	Statement
	Data

	10.1
	The Consultant is (Name):
	     

	
	Address
	     

	
	Tel No.
	     

	
	Fax No.
	     

	22.1
	The key people are:
	

	
	1
Name:
	     

	
	
Job:
	     

	
	
Responsibilities:
	     

	
	
Qualifications:
	     

	
	
Experience:
	     

	
	2
Name:
	     

	
	
Job
	     

	
	
Responsibilities:
	     

	
	
Qualifications:
	     

	
	
Experience:
	     

	Only if required
	
	CV's (and further key persons data including CVs) are appended to Tender Schedule entitled     .

	11.2(3)
	The completion date for the whole of the services is
	     

	11.2(10)
	The following matters will be included in the Risk Register
	     

	11.2(13)
	The staff rates are:
	name/designation
	rate

	
	Either complete here or cross refer to a schedule in Part C2.2
	
	

	
	
	
	

	
	
	
	

	25.2
	The Employer provides access to the following persons, places and things
	access to
	access date

	
	Ingula Pumped Storage Scheme
	1
	Bedford Dam
	starting date

	
	Ingula Pumped Storage Scheme
	2
	Bramhoek Dam
	starting date

	
	Ingula Pumped Storage Scheme
	3
	Farm Dam
	starting date

	
	Small Hydro
	4
	Ncora Holding Dam
	starting date

	
	Small Hydro
	5
	First Falls Dam
	starting date

	
	Small Hydro
	6
	Second Falls Dam
	starting date

	
	Small Hydro
	7
	Mbashe Dam
	starting date

	31.1
	The programme identified in the Contract Data is
	     

	50.3
	The expenses stated by the Consultant are
	item
	amount

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	Refer to schedule C2.2
	

	A
	Priced contract with activity schedule
	

	11.2(14) 
	The activity schedule is in
	     

	11.2(18)
	The tendered total of the Prices is 
	R      (in figures) 

      (in words), excluding VAT 


Part 2: Pricing Data

PSC3 Option A

	Document reference
	Title
	No of pages

	C2.1
	Pricing assumptions: Option A
	[●]

	C2.2
	The activity schedule
	[●]


C2.1 Pricing assumptions: Option A
How work is priced and assessed for payment

Option A is a lump sum form of contract where the work to be done is broken down into well defined activities each listed in the activity schedule and priced by the tendering consultant as a lump sum. (See clause 11.2(18)).  

Only completed activities which are without Defects are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date. (See clause 11.2(15)).

The activity schedule may change after the Contract Date as a result of compensation events. (See clause 11.2(14)).

Function of the Activity Schedule

The Activity Schedule is only a pricing document. Clause 53.1 in Option A states: “Information in the Activity Schedule is not Scope”.  Specifications and descriptions of the service or any constraints on how it is to be done are included in the Scope and per Clause 21.1, “The Consultant Provides the Services in accordance with the Scope” and therefore not in accordance with the Activity Schedule.  

Link to the programme

Clause 31.4 states that “The Consultant provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering consultant will develop a high level programme first then resource each activity on the programme and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

Preparing the activity schedule

Generally it is the tendering consultant who prepares the activity schedule by breaking down the work described within the Scope into suitable activities which can be well defined, shown on a programme and priced as a lump sum.  

The description of each activity must be sufficient to determine exactly what work is included within it and to know when it has been completed. 

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Consultant to include in his activity schedule and be priced accordingly. 

It is assumed that in preparing his activity schedule the Consultant:
· Has taken account of the guidance given in the PSC3 Guidance Notes;

· Understands the function of the Activity Schedule and how work is priced and paid for;

· Is aware of the need to link the Activity Schedule to activities shown on each programme which he submits for acceptance by the Employer;

· Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Scope, as it was at the Contract Date, as well as correct Defects except correcting a Defect for which the Consultant is not liable;
· Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the service for the tendered total of the Prices. 
· Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Consultant estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event. 

However, the Consultant does not have to allow in his Prices for matters that may arise as a result of a compensation event. 

Expenses

Expenses are not included in the activity schedule items and are assessed separately at each assessment date, unless an additional condition of contract (Z clause) is included which requires that expenses be included within activity Prices and not paid separately.

Expenses associated with employing a staff member in Providing the Services are listed separately either by the Employer in Contract Data provided by the Employer or by the Consultant in Contract Data provided by the Consultant.  As only the expenses listed may be claimed by the Consultant, all other cost to the Consultant associated with Providing the Services must be included within the activity schedule prices or staff rates.

Rate adjustment for inflation of expenses is explained in the PSC3 Guidance Notes.

Staff rates

When a compensation event occurs changes to the affected Activity Schedule item or new priced items in the Activity Schedule are assessed as the actual Time Charge for work already done and the forecast Time Charge for work not yet done.  (See clause 63.1 and 63.14 in Option A)

The Time Charge is the sum of the products of each of the staff rates multiplied by the total staff time appropriate to that rate properly spent on work in this contract.  (Clause 11.2(13))

Tendering consultants are advised to consult the NEC3 Professional Services Contract Guidance Notes and Flow Charts before entering staff rates into Contract Data, or in C2.2 below.  

This is because staff rates can be established in one of three ways:

rates for named staff,

rates for categories of staff or

rates related to salaries paid to staff.

Rate adjustment for inflation, if necessary, can be based either on actual salary adjustments or by using Option X1: Price adjustment for inflation.  See pages 13 and 14 in the PSC3 Guidance Notes.

C2.2 the activity schedule
	Item

No.
	Programme Reference
	Activity description
	Frequncy
	Price (excl VAT)

	
	
	The following activities are to be Priced for all the Ingula and small hydro dams:
	
	

	1
	
	Training of Employer’s staff
	At the start of the contract
	

	2
	
	Liaison with authorities for the whole of the services
	As required in order to complete the scope of services. 
	

	3
	
	Providing designs, scope of works and technical specifications for the actions or recommendations
	As required in order to complete the scope of services.
	

	4
	
	Dam Safety Evaluation Report
	At the start and end of the contract
	

	5
	
	Undertake Stability Checks
	At the start and end of the contract
	

	6
	
	Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.
	At the start and end of the contract
	

	7
	
	Review and update the existing Dam Information;Iincluded but not limited to EPP, Hydrology, Dam Break Analysis etc. and Issue the Assessment Report.
	At the start of the contract
	

	8
	
	Reviewing, updating and compilation of Operating and Maintenance manuals
	At the start and end of the contract
	

	9
	
	Inspections and reporting
	Bi-annually
	

	10
	
	Providing designs, scope of works and technical specifications for the actions or recommendations
	As and when required
	

	11
	
	Conduct lidar and bathymetric survey and issue report.
	During the 2nd year of the contract
	

	
	
	
	
	

	
	
	The following activities are to be Priced for all the small hydro dams only:
	
	

	12
	
	Conduct topographical surveys
	Bi-annually
	

	
	
	
	
	

	
	
	Total of the Prices
	
	


This section can be used when the staff rates and expenses are considerable in number and more conveniently located here than in the Contract Data.  Entries in the Contract Data should refer to this section of Part 2.

Remember to state whether the staff rates and expenses exclude or include VAT. 

The staff rates are:

	No.
	Designation (or category) or name of staff member
	Rate per {hour, day, month} excluding VAT

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


The expenses are:

	No.
	Expense item
	Amount / rate excluding VAT

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


Part 3: Scope of Work

	Document reference
	Title
	No of pages

	
	This cover page
	1

	C3.1
	Employer’s Scope
	

	C3.2
	Consultant’s Scope

(insert at award stage or delete if not applicable)
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	Total number of pages
	


C3.1: Employer’s scope

Table of Contents


36Part 3: Scope of Work


37C3.1: Employer’s scope


391
Description of the services


391.1
Executive overview


391.2
Interpretation and terminology


402
Specification and description of the services


402.1
Details of Peaking Business Unit Dams


402.1.1
Ingula Pumped Storage Scheme dams


412.1.2
Small Hydros Dams


422.2
Scope of Services


422.2.1
Description of Services


432.2.2
Reporting


442.3
Project Engineering


442.4
Training


443
Constraints on how the Consultant Provides the Services.


443.1
Management meetings


453.2
Consultant’s key persons


453.3
Provision of bonds and guarantees


453.4
Documentation control and retention


453.4.1
Identification and communication


453.4.2
Retention of documents


453.5
Records and forecasting of expenses


453.6
Invoicing and payment


473.7
Contract change management


473.8
Inclusions in the programme


473.9
Quality management


473.9.1
System requirements


473.9.2
Quality Assurance Requirements


483.9.3
Information in the quality plan


483.10
The Parties use of material provided by the Consultant


483.10.1
Employer’s purpose for the material


483.10.2
Restrictions on the Consultant’s use of the material for other work


483.10.3
Transfer of rights if Option X 9 applies


493.11
Management of work done by Task Order


493.12
Health and safety


493.12.1
Key Performance Indicators


503.12.2
Contract Completion and sign off.


503.13
Procurement


503.13.1
BBBEE and preferencing scheme


503.13.2
Other constraints


503.13.3
Preferred subconsultants


513.13.4
Subcontract documentation, and assessment of subcontract tenders


513.13.5
Limitations on subcontracting


513.13.6
Attendance on Subconsultants


513.14
Working on the Employer’s property


513.14.1
Employer’s entry and security control, permits, and site regulations


523.14.2
People restrictions, hours of work, conduct and records


523.15
Cooperating with and obtaining acceptance of Others


523.16
Things provided by the Employer


523.17
Cataloguing requirements by the Consultant


524
List of drawings


524.1
Drawings issued by the Employer


535
Development Team:




1 Description of the services
1.1 Executive overview 
The Employer requires the provision of an Approved Professional Person (APP) for Ingula Pumped Storage Scheme (PSS) (Kwa-Zulu Natal) and the Small Hydro Power Stations (Eastern Cape), which are category II & Category III dams for a period of six (6) years. The Scope applies to the following dams:

· Ingula PSS:
· Bedford Dam (Category 3)
· Bramhoek Dam (Category 3)
· Farm Dam (Category 1)
· Small Hydros:
· Ncora Holding Dam (Category 2)
· First Falls Dam (Category 2) 
· Second Falls Dam (Category 2), and
· Mbashe Dam (Category 2)
The Scope entails dam inspections & evaluations, design work, continuous monitoring, reporting, and liaising with the Dam Safety Office (DSO) and close-out and sign-offs of various findings across the Ingula and Small Hydro dams. The Department of Water and Sanitation – Dam Safety Office (DWS-DSO) has authority, in terms of Chapter 12 of the Water Act and dams safety regulations (Regulations R.139) to authorise an APP for specific tasks, in the categories of design, operation & quality control or evaluation based on their experience in particular task the APP has applied for and the category rating of the dam.
1.2 Interpretation and terminology
The following abbreviations are used in this Scope:

	Abbreviation
	Meaning given to the abbreviation

	APP
	Approved Professional Person

	DSO
	Dam Safety Office of the Department of Water Affairs

	DWS
	Department of Water and Sanitation

	ECSA
	Engineering Council of South Africa

	FS
	Free State

	Gx
	Generation

	KZN
	KwaZulu-Natal

	QA
	Quality Assurance

	QC
	Quality Control

	QCP 
	Quality Control Plan

	PSS
	Pumped Storage Scheme

	SACPCMP
	South African Council for Project and Construction Management Professionals

	SHEQ
	Safety Health Environmental and Quality


2 Specification and description of the services
2.1 Details of Peaking Business Unit Dams
2.1.1 Ingula Pumped Storage Scheme dams
Ingula PSS is an Employer-owned peaking power plant which is located on the border of KwaZulu-Natal (KZN) and Free State (FS). Ingula has three (3) dams, two of which are for power generation; with the bottom dam (Bramhoek) in KZN and the top dam (Bedford) in FS. The PSS uses water from these dams to generate electricity during peak hours. Both dams are owned and operated by the Employer and registered with DWS as category III dams. Refer to Figure 1, Locality plan of Ingula, for the site locality of the Category III dams.

One additional dam at Ingula is the Ingula farm dam, which is not part of power generation but is used as a primary source of potable water. This dam is also situated on the KZN part of the station (bottom site). Table 1, Details of the Ingula Dams, below, provides more information on the three mentioned dams. 

Table 1: Details of the Ingula Dams

	Name
	Type of the Dam
	DWS Ref. Number
	Category
	Date of Last Inspection
	Nearest Town

	Bedford Dam
	Concrete Face Embankment Dam
	C801/60
	III
	2021
	Van Reenen 

	Bramhoek Dam
	Roller Compact Concrete Gravity Dam
	V102/03
	III
	2021
	Ladysmith

	Farm dam
	Earth dam
	V102/07
	I
	2012
	Ladysmith


[image: image1.png]Skeurkip

Ksboen
et
G e
o v &@‘\‘\ L
KIESBEEN
o ROAD Broamhook
Swinburms ©rgy
7
& 7
ien Rosnen
/
- /
7
e
P
s

Bedford

uPPER
RESERVOR

RESERVOIR

Nooitgedacht

G

Besters

(P275),

aivauna




Figure 1: Locality plan of Ingula

2.1.2 Small Hydros Dams

The small hydro dams are Employer-owned hydro stations that are located in the Eastern Cape. 1st falls and the 2nd falls dams are on the Umtata River, where 2nd falls is on the downstream of the 1st falls, with both dams downstream of the Umtata dam. Ncora hydro holding dam receives water from the main Ncora dam through the canals, and Mbashe dam is on the downstream of Ncora along the Mbashe River. 

1st falls and 2nd falls are not operational due to previous flooding incidents at the stations and vandalism by the local communities. Mbashe is also not operational due to siltation of the dam and other plant issues. Ncora is the only hydro station that is operational out of all these stations. The small hydros station dams are only accessible by 4x4s due to bad road conditions; the Consultant should consider this when Pricing for this contract. 
Refer to Figure 2, Locality Map of the Small Hydros Dams, for the site locality of the Small Hydro dams. 

Table 2: Details of the Small Hydros Dams

	Name
	Type of the Dam
	DWS Ref. Number
	Category
	Date of Last Inspection
	Nearest Town

	1st Falls Dam
	Concrete Gravity
	T201/07
	II
	2021
	Mthatha

	2nd Falls Dam
	Concrete Gravity
	T201/08
	II
	2021
	Mthatha

	Mbashe/ Colleywobbles dam
	Concrete Gravity
	T104/04
	II
	2021
	Elliotdale

	Ncora Hydro Holding Dam
	Earthfill embankment, plastic lined and protected by layer of reinforced screed
	S500/22
	II
	2021
	Cala/ Cofimvaba


[image: image2.png]IR &
s Second Falls

Ncora Hydro
Holding Dam

7258 Collywobbles Fadl
Dam





Figure 2: Locality Map of the Small Hydros Dams
2.2 Scope of Services
This document will outline the requirements in terms of the Scope of services by the Employer, to be executed by the APP in conducting the dam safety inspections. The Scope of services will include, but is not limited to the following:
I. Desktop studies

· The Consultant conducts a desk study review of all known literature, existing geotechnical information, and regional information available and associated foundation soils in the area, as well as all previous submissions made. 

II. Provision of the APP Services

· The Consultant provides an APP assisted by the appropriate professional team for the safety evaluation of each dam in accordance with Government Regulations for seven (7) dams at the Employer for a period of six (6) years. 
· The Consultant conducts the dam safety inspections, evaluations, as well as design of components, as and when required to close the findings previously raised or raised during their term.
· Assessment of the monitoring results and identification of issues arising from operation and maintenance.
· Site inspection of each dam, structures, hydraulic equipment and monitoring equipment.
III. Project Engineering Services 
· Conduct the design of components that may be required for implementation to close APP findings or similar.
2.2.1 Description of Services
The Employer intends to appoint an experienced APP as the Dam Owner for a period of six (6) years with his professional team that will be responsible for the dam safety evaluations according to Regulations 35 and 36 of the Dam Safety Regulations (No 139 of 2012). The purpose of this evaluation will be to identify any potential shortcomings in the condition of the dam, operating and maintenance procedures, emergency preparedness plan and assessment of monitoring results that might endanger human lives or damage property.
For Category III Dams, the APP must be supported by a team of specialists, who also need to be approved by the Dam Safety Office (DSO). 
The APP is required to conduct all activities as required by Chapter 12 of the National Water Act (No. 36 of 1998) on behalf of the dam owner to ensure compliance with the Act.

This will, as a minimum include but not limited to the following:

1. Conducting periodic site visits (biannually per site) for visual inspections of the existing dams as stated above (unless otherwise needed in emergency circumstances) and report on the findings.

2. Provides adequate resources, including the provision of equipment for the required Scope.
3. All findings are recorded within a report, and all risks and deficiencies identified are accompanied by the appropriate remedial works to make good, as well as a design (where required) and Scope of services for the execution of remedial works.

4. Review and provide information for updating of operations and maintenance manuals (as needed, as well as develop these manuals if required).

5. Provide responses to queries and mitigations for areas of concern on the existing dams (where needed).

6. Engage the DSO and other relevant authorities on behalf of the Employer for the dams as stated above.

7. Provide feedback on engagement with the DSO and other relevant authorities.

8. Assist in the production of the necessary close-out documentation for the dams.

9. Provide the necessary sign-offs as required for the close-out of the documentation and report findings for the dams.

10. Provide design services for any and all design work required at the dams. This will be as determined by the Employer’s Agent. All design work done by the APP entails the submission of all design information, design calculations, etc., to the Employer’s Agent for review and acceptance prior to payment of such task.  

11. The Consultant notes that the Employer shall use the Consultant’s design for any purpose in relation to the Scope of services at the Employer’s installations.

12. At the start of the Contract Date, the APP prepares a detailed initial assessment report for the dams based on the site inspection and the reviewed existing information (designs and operation documentation), which includes the status of all associated operational and safety risks with relevant mitigation actions and required timelines for action, in order to ensure the safety of the dams. 

13. The Consultant conducts both the Lidar survey and Bathymetric surveys for all seven (7) dams (including their stilling basins where applicable) to create a baseline.
14. The APP role will be required for a period of 72 months (six (6) years).

During the compilation of the dam safety Evaluation Report, the following issues must be addressed and noted in detail for the dams:

a. Obtain all relevant approvals from the DWS Dam Safety Office.

b. Re-evaluation and confirmation of the geology and foundation conditions of all the dams.

c. Re-evaluation and analysis of the flood hydrology in terms of the catchment size and conditions.

d. Re-evaluation of the flood spillways and present discharge capacity determination of the dams.

e. Re-evaluation of the outlet works system (including the spillways capacities) for all the dams and report the findings.
f. Re-evaluation and analysis of the present stability of all the dams. 

g. Re-evaluation of the ancillaries and mechanical equipment of the dams.

h. Re-evaluation of erosion protection on the dams and do the designs where applicable.

i. Re-evaluation of the existing Emergency Preparedness Plans for all the dams and update or develop one where applicable.

j. Review the dam safety monitoring instrument records against the O&M manuals for the dams.

k. Assessment of instrument reading and monitoring results and identification of any safety or performance issues.

l. Re-evaluation of the hazard potential status of the dams in terms of current downstream development and infrastructure.

m. Review of water release records against the Water Use License (where applicable).

n. General condition assessment and identification of issues arising from operation and maintenance.
2.2.2 Reporting

The Consultant reports as follows, following the dam safety evaluations:

· Prepare a draft dam safety report with recommendations and an action plan.

· Submit draft report to the Employer.
· Submit draft report to DWS.

· Review of the report by the Dam Safety Office

· Finalise Report

· Submit the final report, inclusive of the Implementation Plan 

The Consultant submits an inspection report following each site visit to cover:

· General report on the inspection with photographic evidence

· Assessment and condition of the dams, structures, hydraulic equipment and monitoring equipment

· Consultant compliance with the requirements of the O&M Manual

· Review of dam safety monitoring results

· Identification of issues arising from Operation and Maintenance 

· Identification of actions required by the Dam Owner

2.3 Project Engineering

The Consultant offers project engineering services for the execution of any Scope of services on the dams. These services include design work, quality control, quality assurance, factory acceptance testing, site acceptance testing and necessary approvals during the implementation of the services. For all the design work, the Consultant notes that it will be conducted in accordance with the Employer’s Design Review Procedure 240-53113685. Where the Consultant does the design for a new system or modifies the existing plant, he submits the drawings in both dgn and native pdf format to the Employer for review and acceptance. For modification of the existing plant, the Consultant updates the drawings to reflect the as-built status. The drawings are as per 240-86973501 Gx Engineering Drawing Standard.
2.4 Training
The Consultant is required to train staff on the services as shown below and includes training on the inspection and evaluations of dams. Training will include, but is not limited to, the following:

· Dam break analysis

· Dam inspections

· Dam safety evaluations & stability analysis

· Any other design services the Consultant may be doing for the Employer. 

The Consultant includes relevant equipment for the training of the Employer’s staff. 

The Consultant provides detailed proposals setting out the key aspects of training which will be provided for the Employer’s personnel on site, including the proposed training programmes.
The Consultant to Price for training for two of the Employer’s staff but the Employer reserves the right to reduce this to one of the Employer’s staff. 
3 Constraints on how the Consultant Provides the Services.
3.1 Management meetings

Regular meetings of a general nature may be convened and chaired by the Employer’s Agent as follows:

	Title and purpose
	Approximate time & interval
	Location
	Attendance by:

	Risk reduction meeting 
	As and when required 
	MS Teams
	Employer’s Agent, Consultant, and Others as required

	Compensation events
	As and when required 
	MS Teams
	Employer’s Agent, Consultant, and Others as required

	Overall contract progress and feedback
	Monthly
	MS Teams
	Employer’s Agent, Consultant, and Others as required

	Kick-off Meeting
	After contract award
	TBC
	Employer’s Agent, Consultant, and Others as required


Meetings of a specialist nature may be convened as specified elsewhere in this Scope or, if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the services.  Records of these meetings are submitted to the Employer’s Agent by the person convening the meeting within five (5) working days of the meeting.  
All meetings are recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register will not be used for the purpose of confirming actions or instructions under the contract, as these are done separately by the person identified in the conditions of contract to carry out such actions or instructions.  

3.2 Consultant’s key persons
The Consultant is to provide an organogram showing their people and their lines of authority/communication. The Consultant does not have the right to replace a key person at the Consultant’s will and can only replace the person if the replacement is acceptable to the Employer. Proof of qualifications for persons conducting the Scope of services to be provided to the Employer before commencement of any services, e.g. Engineer’s qualification, professional registration, etc., and so applies to the rest of the professional team.
3.3 Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Consultant is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.  

The Consultant will have professional indemnity insurance for their services.
3.4 Documentation control and retention
3.4.1 Identification and communication
a) Contractual Documentation
All contractual communication is addressed in writing to the Employer’s Agent on a letterhead of the Consultant’s company. Letters are typed, signed by the Consultant and delivered by emailed in pdf format to the Employer’s Agent.
b) Reports

All reports are compiled in Word format, in English, and submitted to the Employer’s Agent and Others as per the communication matrix electronically in pdf format. Signed hard copies (original) of inspection reports are submitted to the Main Documentation Centre after finalisation for purposes of record keeping. 
3.4.2 Retention of documents
The Consultant retains copies of drawings, specifications, reports and other documents which record the services. The time period for which the Consultant is to retain such documents is the period for retention stated in the Contract Data.
3.5 Records and forecasting of expenses
The Consultant keeps accounts and records of his expenses and allows the Employer to inspect them at any time within working hours. Accounts and records 52.1 Option A: Priced contract with activity schedule
3.6 Invoicing and payment
The following details shall be shown on or attached to each Invoice to show how the amount due has been assessed:
[List them]

The Consultant shall address the tax invoice to _________________________ and include on it the following information:

Name and address of the Consultant and the Employer’s Agent; 

The contract number and title;

Consultant’s VAT registration number;

The Employer’s VAT registration number 4740101508;
Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;
(add other as required)
1) Within one (1) week of receiving a Payment Certificate from the Employer’s Agent in terms of core clause 51.1, the Consultant submits a tax invoice to the Employer, showing the amount due for payment equal to that stated in the Employer’s Agent’s Payment Certificate. 

2) The Employer’s Agent should be copied on all electronic invoices emailed. 

3) Failure to submit the invoice to the correct address could result in payment delays. 

4) The Consultant’s Tax Invoices comply with the requirements as stated in clause Z7 of the Contract Data 

5) Invoices are submitted electronically to: 

· Local Eskom Invoices - invoiceseskomlocal@eskom.co.za 

· Foreign Eskom Invoices - invoiceseskomforeign@eskom.co.za 

6) The following details are required when submitting invoices and additional data: 

a) The subject line of your email should only contain your vendor number. 

b) Each PDF invoice should be named with your invoice number only. 

c) All electronic invoices are sent in PDF format only. 

d) Attach the proof of delivery to your invoice. 

e) Where applicable, supporting documents are attached to the scanned PDF invoice as one attachment. 

f) A copy of the signed assessment certificate 

g) Cost Price Adjustment (CPA) calculation sheet 

h) Retention Certificate, which is a retention invoice. 

i) Any other appropriate documents, e.g.

i. For shipping invoices, please ensure the following documents are attached. 

ii. Invoice (this should only reflect the shipping cost) 

iii. Commercial invoice 

iv. Delivery note

v. Your shipping costs calculation is relevant to that invoice – not a generic calculation (The amount of the shipping costs calculation has to balance on the amount on the invoice.) 

vi. Forwarding agent’s invoice 

vii. The customs document. 

j) Please do not attach unnecessary documents, as this will make the file too large. 

7) Other requirements: 

a) For foreign invoices, suppliers will still be required to physically deliver hard copies of original documents to the respective Document Management centres even though the invoices have been submitted electronically. 

b) Ensure compliance with the tax requirements for submitting invoices electronically. 

c) Each PDF should contain one credit note, one debit note, or one credit note only. More than one invoice can be submitted per email. 

d) Any CPA applicable is invoiced separately, allowing the rest of the invoices to be paid while CPA issues are resolved. 

8) Include the following information on the Invoice: 

a) Name and address of the Consultant and the Employer’s Agent 
b) The Contract number and title 

c) Consultant’s VAT registration number 

d) The Employer’s VAT registration number 4740101508 

e) The total amount invoiced, excluding VAT, the VAT and the invoiced amount including VAT 

f) Consultant's company registration number, if applicable 

g) Consultant’s banking details 

h) Name and address of the recipient 

i) Tax invoice number and date of issue 

j) Description of goods/services provided 

k) Quantity or volume of goods/services 

l) Period time for which the Tax Invoice is being rendered 

m) Relevant Task Order Number (commencing with a 45 prefix) 

n) Relevant line-item number 

o) State whether the value-added tax is included or excluded

3.7 Contract change management 
Design work will be dependent on the outcome of the reports and will be as and when required. 
3.8 Inclusions in the programme
Besides what is required under clause 31.2 the Consultant provide the following:
1) The programme is prepared using:

Microsoft Project (.mpp format) and must be submitted in native editable format and PDF.

2) The Consultant submits the baseline programme within five (5) working days of the Contract award date for acceptance.
3.9 Quality management
3.9.1 System requirements

Quality management for the services is under Eskom Supplier Quality Management Specification 240-105658000 (QM-58).

3.9.2 Quality Assurance Requirements 

a) The Consultant complies version of the ISO 9001:2015 Quality Management System requirements.

b) The Consultant defines the level of QA or inspection imposed on his subconsultant s and suppliers.

c) The Consultant prepares and submits quality check sheets as well as the Quality Control Plan. Quality acceptance criteria are included in these procedures.

d) All technical design and implementation documentation and QCPs are submitted to the Employer for acceptance (14) days before the commencement of any services or inspections, allowing the Employer the opportunity to provide the necessary intervention points if required.

e) The Consultant is made aware of the requirement that all documents or designs submitted for review to the Employer’s Agent for acceptance require a process of review.

f) The Consultant documents all inspections as part of the quality assurance and control procedures. These documents are handed to the Employer as records.

g) Submission of all quality requirements, to comply with section 3.7.1, Post Contract Award as stipulated in the Supplier Quality Management: Specification 240-105658000 to the Employer for acceptance at least thirty (30) days before the execution of the project.
h) On Completion of the project, the Consultant hands in all data books (Packs) before the Completion Certificate is issued.
i) Where the Consultant maintains an official Quality Management System, details of the level of the Consultant’s self-certification procedures are adopted concerning supplied materials and be accepted by the Employer’s Agent, before the commencement of services.
j) Where no certified Quality Management System exists, the Consultant plans all quality management procedures, carry out all quality control testing as required and make available records of such testing for the Employer’s Agent acceptance.
k) The Consultant will submit full details of the proposed quality management system and procedures for acceptance by the Employer’s Agent, who will have full access to all records, site trials and tests. 
l) The Consultant shall ensure that monitoring and measuring equipment are calibrated and verified to confirm serviceability before usage, and records of such will be kept on-site.

3.9.3 Information in the quality plan
The Quality Plan manages the overall quality of the project’s main activities and milestones. It lists detailed activities in order of execution, where each activity is described and references the associated work packages or specifications with witness, hold and verification points.

The Consultant is therefore required to ensure QCPs meet the following requirements as a minimum:

a) The Consultant defines the level of QC or inspection imposed on his subconsultant’s and suppliers. 

b) The QCPs are to have provisions for signatures indicating Completion by the Consultant and acceptance by the Employer at the end of each activity. 

c) The Consultant has the necessary equipment and qualified staff to carry out the quality control required to ensure compliance with the specification. 

d) The Consultant ensures that a complete Quality Control Plan (QCP) aligned with the Method Statement, and program for executing the services, is submitted to the Employer’s Agent and Client’s representative for review and acceptance before the services can commence. 

e) The programming of inspections, hold, and witness points is agreed between the Employer’s Agent and the Consultant before undertaking any of the services.
f) During reviews of the QCP, the Employer’s Agent provides the necessary intervention points, if required.

3.10 The Parties use of material provided by the Consultant
3.10.1 Employer’s purpose for the material
The rights over drawings, documents, designs and the like prepared by the Consultant shall vest in the Employer. The Z Intellectual Property clause substantiates the Employer’s entitlement to use any documents for the purposes stated in the Scope. In addition, all the services which include the designs, drawings, bill of quantities and Scope of services produced on this contract will be the property of the Employer. The Employer intends to use the detailed design provided by the Consultant with a bill of quantities for all components required to construct the new system.
3.10.2 Restrictions on the Consultant’s use of the material for other work
The Consultant may not use material produced under this contract for any other services.
3.10.3 Transfer of rights if Option X 9 applies
The Consultant to transfer rights over drawings, documents, designs and the like to the Employer after Completion of the services.
3.11 Management of work done by Task Order
Task orders will be issued according to the conditions of this contract.
3.12 Health and safety
The Consultant shall at all times comply with the health and safety requirements prescribed by law as they may apply to the services.  The Consultant shall do the following:
1. The Consultant shall comply with the health and safety requirements contained in OHS Specification and the approved safety file by the Employer. The Employer reserves the right to review the OHS Specification to address the Operational risks and the Consultant shall comply with the latest SHE Specification as amended at no cost for the duration of the contract. 
2. The section 37(2) agreement, as stipulated under the OHS Act no 85 of 1993 must be signed by the Consultant and the Employer’s Agent.
3. The Consultant’s OHS professional must conduct internal audits at planned intervals for the duration of the contract to monitor compliance with the contractual health and safety requirements.

4. The Employer’s Agent and Others conduct inspections at planned intervals for the duration of the contract to monitor compliance with the contractual health and safety and legal requirements.
5. The Consultant may be selected during internal and/or external Peaking Power Station audits to verify compliance with legal and contractual OHS requirements. The Contract Manager/Service Manager will communicate this at relevant time periods and the Consultant shall avail themselves for this audit.

6. In addition to the requirements of the applicable laws governing the occupational health and safety, Peaking Power Station OHS requirements particular to the service and the Affected Property for this contract shall be adhered to for the duration of the contract.

7. The minimum requirements for the Consultant to gain access to Peaking Power Station include the but are not limited to:

a. Valid Medical fitness certificate

b. Police clearance from SAPS or an accredited supplier/service provider linked to SAPS AFIS       system, not older than thirty (30) days. 

c. Identification document (RSA ID or equivalent)

d. National Driver's Licence (applicable to drivers)

e. Adherence to the Eskom Life-saving rules 3 and 4, Be Sober and Buckle up
	Rule
	Description of rule

	3
	BUCKLE UP

No person may drive any vehicle on Eskom business and/or on Eskom premises:

Unless the driver and all passengers are wearing seat belts

	4
	BE SOBER

No person is allowed to be under the influence of intoxicating liquor or drugs while on duty.


8. Applicable risk-based personal protective equipment (PPE).
9. Valid letter of good standing always (COIDA or equivalent). Access to the site to Provide the services will be denied should the Letter of good standing not be valid.
10. The Consultant/supplier who is working alone and not eligible to register with the compensation fund, shall provide the Employer with the member benefit statement of the insurance cover, which includes life and disability cover to the minimum fund of R500 000.Note: Induction will only take place after the above documents have been submitted and accepted by the Employer.
3.12.1 Key Performance Indicators

Consultant /supplier Management Key Performance Indicators (KPI’s)

1. Maintain Health and Safety file and compliance with the health and safety plan, Eskom OHS specification and applicable legislation as amended. 

2. Always maintain good housekeeping where the task is being executed and/or within the area of responsibility.

3. Consultant must develop, implement, and monitor near miss reporting strategy/programme (reporting of near misses). 

4. Comply with Planned Job Observation programmes.

5. Maintain Zero Fatalities for the duration of the contract.

6. At any given point, the OHS performance must be within the lost time injury (LTI) tolerance level as amended.

7. All incidents must be reported immediately or before the end of shift that the incident took place.

8. All incident investigations shall be completed within 30 days of the occurrence of an incident.

9. Incident investigation recommendations shall be closed within the recommended time frame recorded in the Incident investigation report.

10. Close audit findings as per the recommended time frames as per the audit report or action raised in SAP QIM.

11. Close Non-conformance as per the recommended time frames in SAP QIM.

Note: Monitoring of the above mentioned KPI’s will take place through regular audits and inspections.
3.12.2 Contract Completion and sign off.

On Completion of the project/contract, the Employer’s team (led by the Employer’s Agent) involved in the project together with the Consultant shall conduct the final meeting to identify the outstanding information/services prior to the contract close-out. Before the final invoice is paid/processed, the Employer’s Agent shall ensure that the following requirements are met:

a. Close all incidents and audit findings.

b. Clean the respective area and ensure good housekeeping where the Consultant was working.

c. Consultant shall submit safety statistics and a safety file to the Eskom Safety Department for closeout and filing. 

d. Completion of a closeout report (Annexure D form as per 32-726) to close the contractual services.

3.13 Procurement
The Consultant Provide the services, whether explicitly described or reasonably inferred from the Works Information, necessary for Completion.

During execution, the Consultant acts as a “builder” and/or “user of machinery” in terms of the Occupational Health and Safety Act (Act No. 85 of 1993) and its Construction Regulations. Prior to taking occupation of the Site or commencing any activity, the Consultant will obtain a Permit to Work from the Employer’s Agent in accordance with the Employer’s procedures.

The Consultant provides any temporary or expendable materials, barriers, or supports required to store and handle Plant and Materials on Site safely. The Consultant will ensure the safekeeping, protection, and security of all materials, equipment, and assets under its control until Completion.

3.13.1 BBBEE and preferencing scheme

1) The Consultant complies with and fulfils the Consultant’s obligations in respect of the Broad-Based Black Economic Empowerment 

2) The Consultant, as well as his subcontractors, provides valid B-BBEE certificates to the Employer’s Agent when updates are required.
3.13.2 Other constraints

None
3.13.3 Preferred subconsultants
None
3.13.4 Subcontract documentation, and assessment of subcontract tenders

1) The Consultant prepares subcontract documentation in a manner consistent with:

a. The main contract and this Works Information.

b. The Employer’s standards and expectations regarding quality, safety, compliance, and reporting.

2) The use of the NEC family of contracts (NEC3 ECS or NEC3 SC) for subcontracting is strongly recommended. If the Consultant proposes to use other forms of subcontract, this must be approved in writing by the Employer’s Agent prior to the issue of subcontract documentation.
3.13.5 Limitations on subcontracting

The Consultant must not subcontract more than 30% of the total value of the Contract without prior written approval from the Employer’s Agent. 

3.13.6 Attendance on Subconsultants
1) Any subcontractor is required to work under the direct supervision of the Consultant.

2) The Consultant’s organograms indicate the lines of authority and communication of all the Consultant’s site employees, including subcontractors.

3.14 Working on the Employer’s property
3.14.1 Employer’s entry and security control, permits, and site regulations
The Consultant shall comply with the security requirements for access to the Employer’s site.
1) Access to the Power Station is strictly controlled by the Employer’s security protocols and procedures. No personnel must be permitted onto the Site without prior security clearance and completion of the Employer’s mandatory Site Induction.

2) The Consultant must ensure that all employees, subcontractors, and visitors undergo and complete the full Site Induction prior to commencing any work on the Site. Attendance records must be maintained and submitted upon request.

3) It remains the Consultant’s responsibility to familiarise themselves with and fully comply with all current site rules, safety requirements, and access control protocols, including any updates or temporary changes issued by the Employer or Site Security.

4) A valid, approved Safety, Health and Environmental (SHE) File must be submitted and accepted by the Employer’s Safety Representative before any work or site establishment commences.

5) The Consultant must obtain and maintain all necessary permits and authorisations required to carry out the works, including but not limited to Permits to Work, Hot Work Permits, and Working at Heights Permits, where applicable. These permits must be available on-site at all times and presented during inspections.

6) Daily site entry and exit must be logged in accordance with the Employer’s requirements. 

7) The Consultant is required to appoint a competent Site Employer’s Agent who is permanently present on Site during all construction activities. This person must be responsible for ensuring workforce compliance with Site safety, environmental and security protocols.

8) The Consultant will attend daily coordination meetings with the Employer’s Agent prior to commencement of work for the day. During these meetings, work activities, access restrictions, interface coordination and safety considerations will be confirmed.

9) The Employer may revise site regulations and access procedures at any time in response to changing operational, environmental or security conditions. The Consultant is expected to cooperate fully with such changes without delay or claim.

10) No unauthorised photography, drone use, or public communication regarding the works must occur without the Employer’s prior written approval.

11) All Consultant personnel must carry valid identification at all times while on Site. Access to restricted areas will only be granted to personnel with appropriate authorisation.

12) The Employer reserves the right to deny access or remove any person from the Site for non-compliance with Site regulations, safety requirements, or for conduct deemed inappropriate or unsafe.

3.14.2 People restrictions, hours of work, conduct and records

The Consultant keeps records of his people working on the Employer’s property, including those of his Subconsultants.  State that the Employer’s Agent shall have access to these records at any time.  These records may be needed when assessing compensation events. 

The Employer’s site working hours are between 07:00 to 16:15 Monday to Thursday, and 07:00 to 12:00 on Fridays, no work on Weekends and public holidays.

3.15 Cooperating with and obtaining acceptance of Others

Not Applicable
3.16 Things provided by the Employer
The Employer will point out ablution fascilities.
There are no other fascilities provided by the Employer. 

3.17 Cataloguing requirements by the Consultant
None

4 List of drawings

4.1 Drawings issued by the Employer
This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.
All the available as-built drawings shall be shared with the Consultant in PDF format, the Consultant will, at his own cost, reproduce the hard copies to the size he wants. 

	Drawing number
	Revision
	Title

	
	
	Bedford dam O&M Manual

	
	
	Bramhoek dam O&M Manual

	
	
	Ncora dam drawings

	
	
	Colleywobbles dam drawings

	
	
	First falls dam drawings

	
	
	Second falls dam drawings


Bramhoek Dam





Bedford Dam








� Available from Engineering Contract Strategies Tel 011 803 3008 Fax 011 803 3009 and �HYPERLINK "http://www.ecs.co.za"��www.ecs.co.za� 


� Available from Engineering Contract Strategies Tel 011 803 3008 Fax 011 803 3009 or � HYPERLINK "http://www.ecs.co.za" �www.ecs.co.za� 





PSC3 
Page 1 of 43 
COVER PAGE
PART C1
Page 1 of 2 
AGREEMENTS AND CONTRACT DATA

