{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":2,"comments":32},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":2646,"n_cols":12,"rows_kept":2646,"flags":["formulas_cached_only"]}
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,"SABS"]
[1,"1200 A","FIXED CHARGE ITEMS"]
[{"$nulls":11}," "]
["1.1","8.3.1","Contractual Requirements.",null,null,"sum",1]
[]
["1.2","8.3.2","Establishment of facilities on site."]
[{"$nulls":8},"          "]
["1.2.1","8.3.2.1"," Facilities for Engineer"]
[]
[null,"PS.AB.3.2","a) Furnished office.",null,null,"sum",1]
[]
[null,"PS.AB.3.1","b) Nameboards (2 No.).",null,null,"sum",1]
[]
["1.2.2","8.3.2.2"," Facilities for Contractor"]
[]
[null,null,"a) Offices & storage sheds, workshops,",null,null,"sum",1]
[null,null,"laboratories, living accommodation, "]
[null,null,"ablution and latrine facilities, tools and"]
[null,null,"equipment, dealing with water, "]
[null,null,"communications, access and plant."]
[]
[null,"PS.11.3","b) Water supplies and electric power.",null,null,"sum",1]
[]
["1.3","8.3.4","Removal of site establishment.",null,null,"sum",1]
[]
["1.4","AH14.1","Contractors initial obligation in respect",null,null,"sum",1]
[null,null,"of Occupational Health and Safety Act"]
[null,null,"and Construction regulations. The"]
[null,null,"preparation of risk assessments, safe"]
[null,null,"working procedures, the Health & Safety"]
[null,null,"file, the Health & Safety plan, provision"]
[null,null,"of Personal Protective Equipment and"]
[null,null,"Clothing and any other health and"]
[null,null,"safety matters that the contractor"]
[null,null,"deems necessary."]
[]
["1.5","PEM 6","Compliance with Environmental",null,null,"sum",1]
[null,null,"Management Plan."]
[]
["1.6","C1.2.3.1","Contractors responsibility in terms of the ",null,null,"sum",1]
[null,null,"Policy for the use of Community Liaison"]
[null,null,"Officer, Local Labour and facilitation of"]
[null,null,"suitable communication mechanisms"]
[null,null,"between the community and the project "]
[null,null,"team."]
[]
["1.7","PS.1.3","Requirements for accommodation of traffic.",null,null,"sum",1]
[]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 1"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 A","FIXED CHARGE ITEMS"]
[]
["1.8","PS.2.4","Liaison with Telkom / Eskom / eThekwini ",null,null,"sum",1]
[null,null,"Electricity etc. to remove their services "]
[null,null,"i.e. pole, box, cable, etc."]
[]
["1.9","PS.31","Compliance with way leave requirements. ",null,null,"sum",1]
[]
["1.10","PS.25","Provision of security on site to guard ",null,null,"sum",1]
[null,null,"against any disruption of the works "]
[null,null,"throughout the duration of the contract."]
[]
["1.11","C1.2.3.3","Contractor's responsibility for executing the ",null,null,"sum",1]
[null,null,"Contract Participation Goal Plan. Rate to "]
[null,null,"include for all works required by the "]
[null,null,"contractor to achieve the CPG including, but "]
[null,null,"not limited to, engaging with CPG "]
[null,null,"contractors, attending to queries, assisting "]
[null,null,"in resolving conflict / rates disputes, "]
[null,null,"administering all payments for the "]
[null,null,"successful completion of the project."]
{"$rows_empty":29}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 2"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 A","TIME RELATED ITEMS"]
[]
["1.12","8.4.1","Contractual Requirements.",null,null,"sum",1]
[]
["1.13","8.4.2","Operation and maintenance of "]
[null,null,"facilities on site."]
[]
["1.13.1","8.4.2.1"," Facilities for Engineer"]
[]
[null,"PS.AB.3.2","a) Furnished office.",null,null,"sum",1]
[]
[null,"PS.AB.3.1","b) Nameboards (2 No.).",null,null,"sum",1]
[]
["1.13.2","8.4.2.2"," Facilities for Contractor"]
[]
[null,null,"a) Offices & storage sheds, workshops,",null,null,"sum",1]
[null,null,"laboratories, living accommodation, "]
[null,null,"ablution and latrine facilities, tools and"]
[null,null,"equipment, dealing with water, "]
[null,null,"communications, access and plant."]
[]
[null,"PS.11.3","b) Water supplies and electric power. ",null,null,"sum",1]
[]
["1.14","8.4.3","Supervision for duration of contract.",null,null,"sum",1]
[]
["1.15","8.4.4","Company and head office overhead costs.",null,null,"sum",1]
[]
["1.16","PSA 5.9","Accommodation of traffic.",null,null,"sum",1]
[]
["1.17","AH 14.2","Contractors time related obligation in ",null,null,"sum",1]
[null,null,"respect of Occupational Health and Safety"]
[null,null,"Act and Construction regulations."]
[]
["1.18","AH 14.3","Submission of the Health and Safety file",null,null,"sum",1]
[null,null,"on Completion of the works."]
[]
["1.19","PEM 6","Compliance with Environmental",null,null,"sum",1]
[null,null,"Management Plan."]
[]
["1.20","C1.2.3.1","Contractors responsibility in terms of  ",null,null,"Prov Sum",1,null,{"v":430000,"d":"430,000"}]
[null,null,"the Policy for the use of Community"]
[null,null,"Liaison Officer, Local Labour and"]
[null,null,"facilitation of suitable communication"]
[null,null,"mechanisms between the community "]
[null,null,"and the project team."]
[]
["1.21",null,"Overhead, charges and profit on 1.20 above.",null,null,"%",{"v":430000,"d":"430,000"}]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 3"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 A","TIME RELATED ITEMS"]
[]
["1.22","C1.2.3.3","Contractor's responsibility for executing the ",null,null,"sum",1]
[null,null,"Contract Participation Goal Plan."]
[]
["1.23",null,"Contractor's responsibility for executing the ",null,null,"sum",1]
[null,null,"Expanded Public Works Programme / Plan."]
{"$rows_empty":43}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 4"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 A"]
["1.24",null,"SUMS STATED PROVISIONALLY BY"]
[null,null,"THE ENGINEER."]
[]
[null,"8.5a","a) Repairs to damaged Telkom, ",null,null,"Prov Sum",1,null,{"v":350000,"d":"350,000"}]
[null,null,"Electrical and other services which "]
[null,null,"could not have reasonable foreseen or "]
[null,null,"prevented by the Contractor."]
[]
[null,"8.5b(1)","b) Relocation of existing services where ",null,null,"Prov Sum",1,null,{"v":450000,"d":"450,000"}]
[null,null,"ordered by the Engineer."]
[]
[null,"8.5a","c) Protection of visible and underground ",null,null,"Prov Sum",1,null,{"v":250000,"d":"250,000"}]
[null,null,"services as directed by the Engineer."]
[]
[null,"8.5b(1)","d) Provisional sum for stakeholder ",null,null,"Prov sum",1,null,{"v":425000,"d":"425,000"}]
[null,null,"management or facilitation / ISD consultant."]
[]
[null,"8.5a","e) Provisional sum for 24hour armed ",null,null,"Prov sum",1,null,{"v":1300000,"d":"1,300,000"}]
[null,null,"response security to the works."]
[]
[null,"8.5a","f) Reinstatement of road markings and ",null,null,"Prov Sum",1,null,{"v":150000,"d":"150,000"}]
[null,null,"traffic signs where ordered by the "]
[null,null,"Engineer."]
[]
[null,"8.5a","g) Property owner's claims pertaining to",null,null,"Prov Sum",1,null,{"v":350000,"d":"350,000"}]
[null,null,"disruption of access or egress to their "]
[null,null,"properties."]
[]
[null,"8.5b(1)","h) Survey of completed pipeline as ",null,null,"Prov Sum",1,null,{"v":200000,"d":"200,000"}]
[null,null,"ordered by the Engineer."]
[]
[null,"PS.A 8.11","i) Acceptance control testing as directed by",null,null,"Prov Sum",1,null,{"v":150000,"d":"150,000"}]
[null,null,"the Engineer."]
[]
[null,"8.5a","j) Purchase of material not available at the ",null,null,"Prov Sum",1,null,{"v":7000000,"d":"7,000,000"}]
[null,null,"Employer's Store or as instructed by the "]
[null,null,"Engineer."]
[]
[null,"8.5b(1)","k) Cathodic Protection (CP) Professional",null,null,"Prov Sum",1,null,{"v":500000,"d":"500,000"}]
[null,null,"Services Provider (PSP) and installation "]
[null,null,"supervision."]
[]
[null,"8.5b","m) Cathodic Protection installation.",null,null,"Prov Sum",1,null,{"v":7000000,"d":"7,000,000"}]
[]
[]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD",{"$nulls":7},{"v":18125000,"d":"18,125,000"}]
[{"$nulls":8},"BoQ 5"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  1        ",null,"PART: A","GENERAL"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["NO.","REFERS"]
[null,null,"BROUGHT FORWARD",{"$nulls":5},{"v":18125000,"d":"18,125,000"}]
[null,"SABS"]
[null,"1200 A"]
[null,null,"SUMS STATED PROVISIONALLY BY"]
[null,null,"THE ENGINEER."]
[]
[null,"8.5a","n) Crossing of existing watermains, telkom,",null,null,"Prov Sum",1,null,{"v":150000,"d":"150,000"}]
[null,null,"electricity etc. as directed by the Engineer."]
[]
[null,"8.5a","o) Supply of topsoil as directed by the ",null,null,"Prov Sum",1,null,{"v":150000,"d":"150,000"}]
[null,null,"Engineer."]
[]
[null,"8.5b","p) Claims resulting from standing time / ",null,null,"Prov Sum",1,null,{"v":3000000,"d":"3,000,000"}]
[null,null,"work stoppages due to social, "]
[null,null,"environmental or any other unforeseen "]
[null,null,"circumstances."]
[]
[null,"8.5a","q) Demolition of existing structures as ",null,null,"Prov Sum",1,null,{"v":400000,"d":"400,000"}]
[null,null,"directed by the Engineer and reistatement "]
[null,null,"thereof."]
[]
[null,"8.5a","r) Remove existing structures, drains,",null,null,"Prov Sum",1,null,{"v":350000,"d":"350,000"}]
[null,null,"services etc. not determined during design "]
[null,null,"stage."]
[]
[null,"8.5a","s) Provisional sum for completion of ",null,null,"Prov Sum",1,null,{"v":750000,"d":"750,000"}]
[null,null,"outstanding works not carried out on "]
[null,null,"Phase 1 which may be unknown to the "]
[null,null,"Employer. "]
[]
[null,null,"Design of lateral support as required by the ",null,null,"Prov Sum",1,null,{"v":500000,"d":"500,000"}]
[null,null,"Engineer"]
[]
[null,"8.5a","Cost of progress photographs submitted to",null,null,"Prov Sum",1,null,{"v":20000,"d":"20,000"}]
[null,null,"the Engineer via emails."]
[]
[]
[null,"8.5b(2)","Overhead, charges and profit on 1.24 above.",null,null,"%",{"v":23445000,"d":"23,445,000"}]
{"$rows_empty":14}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 6"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 2",null,"PART: C","SITE CLEARANCE"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
[2,"1200 C","SITE CLEARANCE"]
[]
["2.1","8.2.1","General clearance and grubbing along ",null,null,"m",2500]
[null,null,"pipeline route 10m wide."]
[]
[2.2,"8.2.2","Remove and grub large trees and tree "]
[null,null,"stumps of girth."]
[]
[null,null,"a) Over 1m up to and including 2m.",null,null,"No",15]
[]
[null,null,"b) Over 2m up to and including 3m.",null,null,"No",10]
[]
[null,null,"c) Over 3m up to and including 4m.",null,null,"No",5]
[]
[null,null,"d) Over 4m up to and including 5m.",null,null,"No",5]
[]
[2.3,null,"Remove sign posts and store for reuse. ",null,null,"No",10]
[]
[2.4,null,"Remove grass and store for reuse, 3m wide.",null,null,"m²",2500]
[]
[2.5,"PS.24","Remove precast concrete kerbs, channels",null,null,"m³",200]
[null,null,"and haunching.to tip.",{"$nulls":3},"."]
[]
[2.6,null,"Remove stormwater pipes and store for ",null,null,"m",50]
[null,null,"reuse. Maximum Ø = 600mm. "]
[]
[2.7,null,"Remove water reticulation pipes up",null,null,"m",200]
[null,null,"to 200mm Ø."]
[]
[null,null,"Remove brickwork stormwater manholes.",null,null,"No",5]
[null,null,"Maximum height 1.5m. Rate to include "]
[{"v":2.8,"d":"2.80"},null,"reinforced concrete base and roof slab."]
[]
[null,null,"Erect new jersey barriers on pipeline route",null,null,"m",5500]
[{"v":2.9,"d":"2.90"},null,"as directed by the Engineer. "]
[]
[null,null,"Remove new jersey barriers above.",null,null,"m",5500]
{"$rows_empty":14}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 7"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 3",null,"PART: DB","EARTHWORKS (PIPE TRENCHES)"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
["3","1200 DB","EARTHWORKS (PIPE TRENCHES)"]
[]
["3.1","8.3.2 a)","Excavate and backfill in soft materials,"]
[null,"PS.DB.","compact to 93% Mod AASHTO density"]
[null,"8.3.1","and dispose of surplus material for "]
[null,null,"500mm Ø steel pipe where depth is :-"]
[]
[null,null,"a) 0.0m and not exceeding 1m",null,null,"m",100]
[]
[null,null,"b) 1.0m and not exceeding 2m",null,null,"m",2000]
[]
[null,null,"c) 2.0m and not exceeding 3m",null,null,"m",500,null,"          "]
[]
[null,null,"d) 3.0m and not exceeding 4m",null,null,"m",100]
[]
["3.2","8.3.2 a)","Excavate and backfill in soft materials,"]
[null,"PS.DB.","compact to 93% Mod AASHTO density"]
[null,"8.3.1","and dispose of surplus material for "]
[null,null,"200mm Ø steel pipe where depth is :-"]
[]
[]
[null,null,"a) 0.0m and not exceeding 1m",null,null,"m",10]
[]
[null,null,"b) 1.0m and not exceeding 2m",null,null,"m",40]
[]
[null,null,"c) 2.0m and not exceeding 3m",null,null,"m",10]
[]
[null,null,"d) 3.0m and not exceeding 4m",null,null,"m",5]
[]
["3.3","8.3.2 b)","Extra over item (3.1) for hard material",null,null,"m³",400]
[null,null,"excavation. (Provisional.)"]
[]
["3.4","8.3.2 b)","Extra over item (3.1) for excavation in rock.",null,null,"m³",1500]
[null,null,"(Provisional)."]
[]
["3.5","PS.DB","Extra over item (3.1) for excavation in rock",null,null,"m³",300]
[null,"8.3.1","where the use of explosives are prohibited."]
[null,null,"(Provisional)"]
[]
["3.6",null,"Extra over item (3.1) for excavation in roads",null,null,"m³",500]
[null,null,"and paved areas."]
[]
["3.7",null,"Extra over item (3.1) for restricted ",null,null,"m²",8500]
[null,null,"excavation. (Provisional)."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 8"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 3           ",null,"PART : DB","EARTHWORKS (PIPE TRENCHES)"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 DB","EARTHWORKS (PIPE TRENCHES)"]
[]
["3.8",null,"Excavation ancillaries"]
[]
[null,"8.3.3 c)","a) Make up deficiency in backfill",null,null,"m³",1500]
[null,null,"material by importation from commercial"]
[null,null,"or off-site source. (Provisional)"]
[]
[null,"8.3.3.3","b) Extra over item (3.1) for compaction in",null,null,"m³",250]
[null,"PSDB ","road reserves to 98% Mod. AASHTO "]
[null,"5.7.1","Density."]
[]
[null,"PSDB ","c) Extra over item (3.1) for compaction of",null,null,"m³",2200]
[null,"5.7.1","bedding material to 100% Mod AASHTO"]
[null,null,"Density."]
[]
[null,"PS.DB.","d) Extra over item (3.1) for cement",null,null,"m³",100]
[null,"8.3.1","stabilized backfill. (Provisional)"]
[]
["3.9","PS.D","Provide lateral support for telephone ",null,null,"No",10]
[null,"8.3.7","poles, electric light poles, sign posts etc for"]
[null,null,"the duration of contract. "]
[]
["3.10","PS.2.2","Excavate by hand in all material to ",null,null,"m³",300]
[null,null,"expose unknown services as directed by"]
[null,null,"the Engineer. (Provisional)."]
[]
["3.11","PS.DB.","Shore trench opposite structure or service",null,null,"m²",8500]
[null,"8.3.2","regardless of depth."]
{"$rows_empty":17}
[null,null," "]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 9"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
["4","1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.1","PS.4.4","Collect from Hammarsdale Pipeyard,",null,null,"m",2700]
[null,null,"500mm Ø API 5L Grade X42, cement "]
[null,null,"mortar lined 3LPE coated x 9.14m lengths "]
[null,null,"4.5mm/6mm thick plate steel pipes. Rate to "]
[null,null,"include reinstatement of coating and lining. "]
[null,null,"± 4.5km from site to reservoir."]
[]
["4.2","PSL.8.2.1 ","Extraover item for supply of 4.5mm  thick ",null,null,"m",2368]
[null,null,"plate steel pipes. "]
[]
["4.3","PSL.8.2.1 ","Extraover item for supply of 6.0mm  thick ",null,null,"m",337]
[null,null,"plate steel pipes. "]
[]
["4.5","PSL.8.2.1 ","Supply and install Class 25, 200mm Ø ",null,null,"m",66]
[null,null,"mPVC pipes."]
[]
["4.6","PSL.8.2.1 ","Bed, lay and join the following 500mm Ø "]
[null,null,"steel pipes: bell-ended."]
[]
[null,null,"a) 4.5mm thick plate, ",null,null,"m",2368]
[]
[null,null,"b) 6mm thick plate.",null,null,"m",337]
[]
["4.7","PSL.8.2.1 ","Bed, lay and join the following 500mm Ø "]
[null,null,"steel pipes: plain-ended."]
[]
[null,null,"a) 4.5mm thick plate, ",null,null,"m",2368]
[]
[null,null,"b) 6mm thick plate.",null,null,"m",337]
[]
["4.8",null,"Inspection and acceptance of pipes, valves",null,null,"sum",1]
[null,null,"and precast units supplied by the Employer."]
[]
["4.9",null,"Remove existing 200mm Ø mPVC pipe.",null,null,"m",66]
[null,null,"Refer to drawing no. 56724 sheet 6 for "]
[null,null,"details."]
[null,null,"and precast units supplied by the Employer."]
[]
["4.9",null,"Remove existing 200mm Ø mPVC pipe.",null,null,"m",66]
[null,null,"Refer to drawing no. 56724 sheet 6 for "]
[null,null,"details."]
{"$rows_empty":8}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 10"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
["4","1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.10","PSL.8.2.4 ","Extra-over item 4.1, 4.2 & 4.3 for "]
[null,"PSL 3.4","fabrication and installation of the following "]
[null,null,"API5L Grade X42 steel pipe specials, "]
[null,null,"(rate to include for 4.5mm & 6mm plate "]
[null,null,"thickness) inclusive of flanges, gaskets, "]
[null,null,"washers and bolts where not supplied. Note:"]
[null,null,"Bolts and washers to be electro galvanized "]
[null,null,"and yellow passivated. Rate to also include "]
[null,null,"for drilling, welding, internal and external "]
[null,null,"corrosion protection, and the supply and "]
[null,null,"welding of jointing sleeves as required."]
[]
[null,null,"500mm Ø Bends "]
[]
[null,"PSL ","a) 0° to 5° (scarf)",null,null,"No",50]
[null,"3.4.4"]
[null,null,"b) 5° to 30° (1 mitre)",null,null,"No",35]
[]
[null,null,"c) 30° to 60° (2 mitre)",null,null,"No",20]
[]
[null,null,"d) 60° to 90° (3 mitre)",null,null,"No",5]
[]
["4.11",null,"Supply and install cradle and skids as ",null,null,"No",60]
[null,null,"detailed on drawing No. 56724 sheet 11."]
[]
["4.12",null,"Supply the following materials and install "]
[null,null,"steel pipe anchors as detailed on drawing "]
[null,null,"No. 56724 sheet 12."]
[]
[null,"PSL 3.4.5 ","a) Steel sheet anchor to be welded to the ",null,null,"No",40]
[null,null,"pipe at various angles up to 90°."]
[]
[null,null,"b) 200mm deep overbreak.",null,null,"m³",10]
[]
[null,null,"c) Cement stabilised backfill.",null,null,"m³",10]
[]
[null,null,"d) 25MPa base.",null,null,"m³",20]
{"$rows_empty":12}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 11"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.13",null,"Butterfly Valve Chambers"]
[null,null,"PN40"]
[null,null,"Supply all materials and construct valve",null,null,"No",4]
[null,null,"chambers. Refer to standard drawing "]
[null,null,"No. 56724 sheets 19. Rate to include"]
[null,null,"50mm thick blinding layer, 250mm thick"]
[null,null,"base, screed, 220mm brickwork, roof slab,"]
[null,null,"plastering, chamfers, drain pipe, slip joint,"]
[null,null,"sump, etc."]
[]
["4.13.1",null,"Extra over item 4.13 for the following "]
[null,null,"brickwork on all chambers:"]
[null,null,"a) 330mm brickwork ± 850mm",null,null,"sum",1]
[null,null,"b) 440mm brickwork ± 500mm",null,null,"sum",1]
[]
["4.13.2","PSL-3","Supply and install the following steel "]
[null,null,"specials. Rate to include for "]
[null,null,"reinstatement of coating and lining and"]
[null,null,"corrosion protection. "]
[]
[null,null,"a) 100mm Ø stub cut to suit, F.O.E. Item 1.",null,null,"No",8]
[]
[null,null,"b) 100mm Ø x 90° short radius bends ",null,null,"No",8]
[null,null,"F.O.E. Item 2."]
[]
[null,null,"c) 100mm Ø spool pieces cut to suit ",null,null,"No",8]
[null,null,"F.O.E. Item 3."]
[]
[null,null,"d) 100mm Ø wide x 4.5mm plate collar ",null,null,"No",8]
[null,null,"Item 4."]
[]
[null,null,"e) 100mm Ø wafer valve. Item 5.",null,null,"No",4]
[]
[null,null,"f) 50mm Ø gas socket welded to pipe.",null,null,"No",8]
[]
[null,null,"g) 50mm Ø ball-o-stop. ",null,null,"sum",8]
[]
[null,null,"h) 15mm Ø male stop end.",null,null,"No",8]
[]
[null,null,"i) 15mm Ø gas socket.",null,null,"No",8]
[]
[null,null,"j) 15mm Ø ball-o-stop.",null,null,"No",8]
[]
["4.13.3",null,"Supply and install 50mm Ø double purpose",null,null,"No",8]
[null,null,"air release valves."]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 12"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.13.4","PS.4.4","Collect from Springfield Water Store and",null,null,"No",4]
[null,null,"install 500mm Ø Butterfly valves. "]
[]
["4.13.5","PSL-3","Supply and install the following steel "]
[null,null,"specials for air vents detail:"]
[]
[null,null,"a) 10mm Ø mild steel studs",null,null,"No",8]
[]
[null,null,"b) 100mm Ø x 480mm long steel spool ",null,null,"No",4]
[null,null,"piece with a 100mm Ø x 90° long radius "]
[null,null,"bend F.O.E."]
[]
[null,null,"c) 100mm Ø x 370mm long steel spool ",null,null,"No",4]
[null,null,"piece with a 100mm Ø x 90° long radius "]
[null,null,"bend F.O.E."]
[]
[null,null,"d) 100mm Ø spool piece approximate",null,null,"No",4]
[null,null,"length 1100m."]
[]
[null,null,"e) 100mm Ø spool piece approximate",null,null,"No",4]
[null,null,"length 3000m."]
[]
[null,null,"f) 3 no. R8 bars welded across opening at",null,null,"No",24]
[null,null,"equal centres."]
[]
[null,null,"g) 100mm Ø x 90° long radius bends.",null,null,"No",8]
[]
["4.13.6",null,"Supply and install 15MPa, 400 x 400 x ",null,null,"No",8]
[null,null,"400mm concrete anchor blocks."]
[]
["4.13.7",null,"Supply and install \"calcamite\" step irons to ",null,null,"No",56]
[null,null,"be driven into predrilled 25mm Ø x 75mm "]
[null,null,"deep holes fixed with \"Epidemix 372\" or "]
[null,null,"similar approved epoxy adhesive."]
[]
["4.13.8",null," Supply and install Smart Lock heavy duty ",null,null,"No",4]
[null,null,"700mm Ø manhole access cover and frame "]
[null,null,"including key."]
[]
["4.13.9",null,"Supply and install 3 Ply Malthoid over 3mm",null,null,"sum",1]
[null,null,"over tempered hardboard. Rate to include"]
[null,null,"steel floating over mortar bed."]
[]
["4.13.10",null,"Supply all material and instal lifting holes as",null,null,"No",32]
[null,null,"detailed."]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 13"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.13.11",null,"Supply all materials and construct pipe/wall",null,null,"sum",1]
[null,null,"sealing detail."]
[]
["4.13.12",null,"Supply all materials and construct slab joint",null,null,"sum",1]
[null,null,"to be sealed with bituminous sealant ABE\""]
[null,null,"Bituminuos Putty\" or similar approved "]
[null,null,"sealant."]
[]
["4.14",null,"Air Valve Chamber (100mm Ø) "]
[null,null,"Off Road pipe. PN40"]
[null,null,"Outstanding work Phase1 "]
[null,null,"H45, H51 & H56"]
[]
["4.14.1","PSL-3.4","Fabricate, supply and install the following"]
[null,"PSL-8.2.2","air valve specials: Rate to include for"]
[null,null,"drilling, welding, internal & external "]
[null,null,"corrosion protection and lining & coating"]
[null,null,"where applicable. Refer to drawing No."]
[null,null,"56724 sheet 15 for details."]
[]
[null,null,"a) 100mm Ø x 200mm long spool piece ",null,null,"No",3]
[null,null,"F.O.E. Item B. "]
[]
[null,null,"b) 15mm Ø thread-O-Let Gas Socket.",null,null,"No",3]
[null,null,"Item C."]
[]
[null,null,"c) 100mm Ø Butterfly valve. Item E.",null,null,"No",3]
[]
[null,null,"d) 100mm Ø x 400mm Ø taper F.O.E. Item F.",null,null,"No",2]
[]
[null,null,"e) 15mm Ø male stop end Item H.",null,null,"No",3]
[]
[null,null,"f) 400mm Ø x 300mm long stub F.O.E. with ",null,null,"No",3]
[null,null,"a blank flange. Item G."]
[]
[null,null,"g) 15mm Ø ball-o-stop Female to male. ",null,null,"No",3]
[null,null,"Item D."]
[]
[null,null,"h) 100mm Ø air valve assembly. Item A.",null,null,"No",3]
[]
["4.14.2",null,"Supply and install 1250mm Ø precast ",null,null,"No",9]
[null,null,"concrete manhole rings 500mm deep."]
[]
["4.14.3",null,"Supply and install 1550mm Ø precast ",null,null,"No",3]
[null,null,"reinforced concrete roof slab."]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 14"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[]
["4","1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.14.4",null,"Supply and install 100mm thick, 25mm ",null,null,"m²",5]
[null,null,"crushed stone."]
[]
["4.14.5",null,"Supply and install 100mm thick umgeni ",null,null,"m²",5]
[null,null,"sand bedding."]
[]
["4.14.6",null,"Supply and install 100mm Ø steel pipe",null,null,"No",3]
[null,null,"epoxied into a 120mm Ø hole (cored "]
[null,null,"through slab) with suitable epoxy."]
[]
["4.14.7",null,"Supply and install 100mm Ø x 90° long",null,null,"No",3]
[null,null,"radius bend with 3 no. R8 bars welde across"]
[null,null,"opening at equal centres."]
[]
["4.14.8",null,"Supply and instal 400mm Ø x 100mm Ø",null,null,"No",2]
[null,null,"steel tapers."]
[]
["4.14.9",null,"Supply and install air valve marker posts.",null,null,"No",3]
[null,null,"Refer to drawing No. 56274 sheet 12 Plan"]
[null,null,"No. 32"]
[]
["4.14.10",null,"Supply and install Smart Lock heavy duty ",null,null,"No",2]
[null,null,"700mm Ø manhole access cover and frame "]
[null,null,"including key."]
[]
["4.14.11",null,"Supply and install \"calcamite\" step irons to ",null,null,"No",18]
[null,null,"be driven into predrilled 25mm Ø x 75mm "]
[null,null,"deep holes fixed with \"Lokset S 40\" or "]
[null,null,"similar approved epoxy adhesive."]
{"$rows_empty":19}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 15"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[]
["4","1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.15",null,"Air Valve Chamber (100mm Ø) "]
[null,null,"Off Road pipe. PN25  Phase 2."]
[]
["4.15.1","PSL-8.2.2","Fabricate, supply and install the following"]
[null,"PSL-3.4","air valve specials: Rate to include for"]
[null,null,"drilling, welding, internal & external "]
[null,null,"corrosion protection and lining & coating"]
[null,null,"where applicable. Refer to drawing No."]
[null,null,"56724 sheet 9 for details."]
[]
[null,null,"a) 100mm Ø x 200mm long spool piece ",null,null,"No",2]
[null,null,"F.O.E. Item B. "]
[]
[null,null,"b) 15mm Ø thread-O-Let Gas Socket.",null,null,"No",2]
[null,null,"Item C."]
[]
[null,null,"c) 100mm Ø Butterfly valve. Item E.",null,null,"No",2]
[]
[null,null,"d) 100mm Ø spool piece F.O.E. welded",null,null,"No",2]
[null,null,"centrally to a blank flange. Item F. ±600mm"]
[null,null,"long. Rate to include cutting of 100mm Ø"]
[null,null,"hole."]
[]
[null,null,"e) 15mm Ø male stop end Item H.",null,null,"No",2]
[]
[null,null,"f) 400mm Ø x 300mm long stub F.O.E. with ",null,null,"No",2]
[null,null,"a blank flange. Item G."]
[]
[null,null,"g) 15mm Ø ball-o-stop Female to male. ",null,null,"No",2]
[null,null,"Item D."]
[]
[null,null,"h) 100mm Ø air valve assembly. Item A.",null,null,"No",2]
[]
["4.15.2",null,"Supply and install 1250mm Ø precast ",null,null,"No",6]
[null,null,"concrete manhole rings 500mm deep."]
[]
["4.15.3",null,"Supply and install 1550mm Ø precast ",null,null,"No",2]
[null,null,"reinforced concrete roof slab."]
[]
["4.15.4",null,"Supply and install 100mm thick, 25mm ",null,null,"m²",5]
[null,null,"crushed stone."]
[]
["4.15.5",null,"Supply and install 100mm thick umgeni ",null,null,"m²",5]
[null,null,"sand bedding."]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 16"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.15.6",null,"Supply and install 100mm Ø steel pipe",null,null,"No",2]
[null,null,"epoxied into a 120mm Ø hole (cored "]
[null,null,"through slab) with suitable epoxy."]
[]
["4.15.7",null,"Supply and install 100mm Ø x 90° long",null,null,"No",2]
[null,null,"radius bend with 3 no. R8 bars welde across"]
[null,null,"opening at equal centres."]
[]
["4.15.8",null,"Supply and install air valve marker posts.",null,null,"No",2]
[null,null,"Refer to drawing No. 56274 sheet 12 Plan"]
[null,null,"No. 32"]
[]
["4.15.9",null,"Supply and install Smart Lock heavy duty ",null,null,"No",2]
[null,null,"700mm Ø manhole access cover and frame "]
[null,null,"including keys."]
[]
["4.15.10",null,"Supply and install \"calcamite\" step irons to ",null,null,"No",12]
[null,null,"be driven into predrilled 25mm Ø x 75mm "]
[null,null,"deep holes fixed with \"Lokset S 40\" or "]
[null,null,"similar approved epoxy adhesive."]
{"$rows_empty":28}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 17"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. ",null,null," "]
[]
["SECTION  4    ",null,"PART: L  ","MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.16",null,"Scour Valve Chamber (Off Road)"]
[null,null,"PN 25. Phase 2."]
[]
["4.16.1","PS.L-3.4","Supply and install the following Scour Steel"]
[null,"PSL-8.2.2","Specials. Rate to include drilling, welding, "]
[null,null,"internal & external corrosion protection and "]
[null,null,"reinstatement of lining & coating where "]
[null,null,"applicable. Refer to DWG No. 56724 "]
[null,null,"sheet 16  for details."]
[]
[null,null,"a) Saddle plates 4.5/6mm thick with a ",null,null,"No",3]
[null,null,"150mm Ø x 100mm long spool piece and a "]
[null,null,"150mm Ø  x 90° long radius bend F.O.E. "]
[]
[null,null,"b) 150mm Ø spool piece F.B.E. length to be ",null,null,"No",3]
[null,null,"determined on site."]
[]
[null,null,"c) 150mm Ø gate valves. ",null,null,"No",3]
[]
[null,null,"d)150mm Ø steel scour pipe F.B.E. with a ",null,null,"No",3]
[null,null,"45° bend, length to be determined on  site."]
[]
[null,null,"e) Spindle extension 32mm Ø cut to suit",null,null,"No",3]
[null,null,"mild steel rod with an end cap welded to "]
[null,null,"each end."]
[]
[null,null,"f) 40mm deep x 6 mm thick stainless steel ",null,null,"No",24]
[null,null,"plate including welding (Grade 316). "]
[]
[null,null,"g) 40mm  Ø x 1,6 mm thick stainless steel ",null,null,"No",18]
[null,null,"tube. (Grade 316). "]
[]
[null,null,"h) 250 x 290 x 6mm thick stainless steel ",null,null,"No",18]
[null,null,"plate. (Grade 316W). "]
[]
[null,null,"i) Mild Steel washer welded onto the spindle ",null,null,"No",16]
[null,null,"extension to be greater than 44mm."]
[]
[null,null,"j) 10mm stainless steel bolts (Grade 316)",null,null,"No",24]
[null,null,"to be epoxied into concrete with"]
[null,null,"\"Epidermix 350\" or similar approved epoxy."]
[]
[null,null,"k) 100mm Ø uPVC Class 6 pipe. Length to ",null,null,"m",24]
[null,null,"be determined on site."]
[]
["4.16.2",null,"Core 150mm Ø hole on roof slab for spindle",null,null,"No",3]
[null,null,"extension."]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 18"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. ",null,null," "]
[]
["SECTION  4    ",null,"PART: L  ","MEDIUM-PRESSURE PIPELINES"]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.16.3","PS.4.4","Collect from Springfield Water Store "]
[null,null,"and install the following : "]
[]
[null,null,"a) 32mm Ø spindle extension with end cap. ",null,null,"No",3]
[null,null,"Length to be determined on site."]
[]
[null,null,"b) 150mm Ø gate valve.",null,null,"No",3]
[]
[null,null,"c) No.5 valve covers. ",null,null,"No",3]
[]
["4.16.4",null,"Supply and install the following items:",null,null,"No",3]
[]
[null,null,"a) No.5 valve covers to be painted red. "]
[]
[null,null,"b) 1500mm I.D. x 500mm deep precast ",null,null,"No",9]
[null,null,"concrete manhole rings."]
[]
[null,null,"c) Precast circular reinforced concrete slab",null,null,"No",3]
[null,null,"150mm deep."]
[]
[null,null,"d) 100mm Ø steel pipe x 200mm long to be ",null,null,"No",3]
[null,null,"epoxied with 'prostruct 617' general purpose"]
[null,null,"epoxy adhesive or similar approved onto a "]
[null,null,"predrilled 120mm Ø hole."]
[]
[null,null,"e) 100mm Ø x 90° short radius bends with ",null,null,"No",3]
[null,null,"100mm Ø x 100mm long steel spool piece "]
[null,null,"and 3 x R8 bars welde across opening at "]
[null,null,"equal centres."]
[]
[null,null,"f) 100mm Ø flanged jet dispersers as ",null,null,"No",3]
[null,null,"detailed."]
[]
[null,null,"g) Calcamite step irons to be driven into",null,null,"No",27]
[null,null,"predrilled 25mm Ø x 75mm deep holes and"]
[null,null,"fixed with 'Epidermix 350' or similar "]
[null,null,"approved epoxy."]
[]
[null,null,"h) 50mm blinding layer (with 400mm thick ",null,null,"m²",18]
[null,null,"layer of 24mm crushed stone if soil "]
[null,null,"conditions are unstable)."]
[]
[null,null,"i) 150mm deep reinforced concrete slab.",null,null,"No",3]
[]
[null,null,"j) 230 x 230mm brick plinths",null,null,"No",3]
[]
[null,null,"k) 500 x 500 x 500mm grade 20/26MPa ",null,null,"No",5]
[null,null,"mass concrete thrust block."]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 19"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. ",null,null," "]
[]
["SECTION  4    ",null,"PART: L  ","MEDIUM-PRESSURE PIPELINES"]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.16.5",null,"Supply all materials and seal joints between ",null,null,"sum",1]
[null,null,"manhole rings with \"Expandite Butyl 300\" "]
[null,null,"with root inhibitor or similar approved."]
[]
["4.16.6",null,"Supply and instal 700mm Ø Smart Lock ",null,null,"No",3]
[null,null,"cover and frame including keys."]
[]
["4.16.7",null,"SCOUR TYPE S2. (Provisional)"]
[]
[null,"PS.L-3.4","Supply and install the following Scour Steel"]
[null,"PSL-8.2.2","Specials. Rate to include drilling, welding, "]
[null,null,"internal & external corrosion protection and "]
[null,null,"reinstatement of lining & coating where "]
[null,null,"applicable. Refer to DWG No. 56724 "]
[null,null,"sheet 10  for details."]
[]
[null,null,"a) Saddle plates 4.5/6mm thick with a ",null,null,"No",3]
[null,null,"150mm Ø x 100mm long spool piece and a "]
[null,null,"150mm Ø  x 90° long radius bend F.O.E. "]
[]
[null,null,"b) 150mm Ø spool piece F.B.E. length to be ",null,null,"No",3]
[null,null,"determined on site."]
[]
[null,null,"c) 150mm Ø gate valves. ",null,null,"No",3]
[]
[null,null,"d)150mm Ø steel scour pipe F.B.E. with a ",null,null,"No",3]
[null,null,"45° bend, length to be determined on  site."]
[]
[null,null,"e) Spindle extension 32mm Ø cut to suit",null,null,"No",3]
[null,null,"mild steel rod with an end cap welded to "]
[null,null,"each end."]
[]
["4.16.8","PS.4.4","Collect from Springfield Water Store "]
[null,null,"and install the following : "]
[]
[null,null,"a) 32mm Ø spindle extension with end cap. ",null,null,"No",3]
[null,null,"Length to be determined on site."]
[]
[null,null,"b) 150mm Ø gate valve.",null,null,"No",3]
[]
[null,null,"c) No.5 valve covers. ",null,null,"No",3]
[]
["4.16.9",null,"Supply and install the following items:",null,null,"No",3]
[]
[null,null,"a) No.5 valve covers to be painted red. "]
[]
[null,null,"b) 100mm Ø flanged jet dispersers as ",null,null,"No",3]
[null,null,"detailed."]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 20"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. ",null,null," "]
[]
["SECTION  4    ",null,"PART: L  ","MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.17",null,"Scour Valve Chamber (Off Road)"]
[null,null,"PN 40. Outstanding work Phase1."]
[]
["4.17.1","PS.L-3.4","Supply and install the following Scour Steel"]
[null,"PSL-8.2.2","Specials. Rate to include drilling, welding, "]
[null,null,"internal & external corrosion protection and "]
[null,null,"reinstatement of lining & coating where "]
[null,null,"applicable. Refer to DWG No. 56724 "]
[null,null,"sheet 16  for details."]
[]
[null,null,"a) Saddle plates 8mm thick with a ",null,null,"No",2]
[null,null,"150mm Ø x 100mm long spool piece and a "]
[null,null,"150mm Ø  x 90° long radius bend F.O.E. "]
[]
[null,null,"b) 150mm Ø spool piece F.B.E. length to be ",null,null,"No",2]
[null,null,"determined on site."]
[]
[null,null,"c) 150mm Ø gate valves. ",null,null,"No",2]
[]
[null,null,"d)150mm Ø steel scour pipe F.B.E. with a ",null,null,"No",2]
[null,null,"45° bend, length to be determined on  site."]
[]
[null,null,"e) Spindle extension 32mm Ø cut to suit",null,null,"No",2]
[null,null,"mild steel rod with an end cap welded to "]
[null,null,"each end."]
[]
[null,null,"f) 40mm deep x 6 mm thick stainless steel ",null,null,"No",16]
[null,null,"plate including welding (Grade 316). "]
[]
[null,null,"g) 40mm  Ø x 1,6 mm thick stainless steel ",null,null,"No",12]
[null,null,"tube. (Grade 316). "]
[]
[null,null,"h) 250 x 290 x 6mm thick stainless steel ",null,null,"No",12]
[null,null,"plate. (Grade 316W). "]
[]
[null,null,"i) Mild Steel washer welded onto the spindle ",null,null,"No",8]
[null,null,"extension to be greater than 44mm."]
[]
[null,null,"j) 10mm stainless steel bolts (Grade 316)",null,null,"No",16]
[null,null,"to be epoxied into concrete with"]
[null,null,"\"Epidermix 350\" or similar approved epoxy."]
[]
[null,null,"k) 100mm Ø uPVC Class 6 pipe. Length to ",null,null,"m",18]
[null,null,"be determined on site."]
[]
["4.16.2",null,"Core 150mm Ø hole on roof slab for spindle",null,null,"No",2]
[null,null,"extension."]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 21"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. ",null,null," "]
[]
["SECTION  4    ",null,"PART: L  ","MEDIUM-PRESSURE PIPELINES"]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.17.3","PS.4.4","Collect from Springfield Water Store "]
[null,null,"and install the following : "]
[]
[null,null,"a) 32mm Ø spindle extension with end cap. ",null,null,"No",2]
[null,null,"Length to be determined on site."]
[]
[null,null,"b) 150mm Ø gate valve.",null,null,"No",2]
[]
[null,null,"c) No.5 valve covers. ",null,null,"No",2]
[]
["4.17.4",null,"Supply and install the following items:",null,null,"No",2]
[]
[null,null,"a) No.5 valve covers to be painted red. "]
[]
[null,null,"b) 1500mm I.D. x 500mm deep precast ",null,null,"No",6]
[null,null,"concrete manhole rings."]
[]
[null,null,"c) Precast circular reinforced concrete slab",null,null,"No",2]
[null,null,"150mm deep."]
[]
[null,null,"d) 100mm Ø steel pipe x 200mm long to be ",null,null,"No",2]
[null,null,"epoxied with 'prostruct 617' general purpose"]
[null,null,"epoxy adhesive or similar approved onto a "]
[null,null,"predrilled 120mm Ø hole."]
[]
[null,null,"e) 100mm Ø x 90° short radius bends with ",null,null,"No",2]
[null,null,"100mm Ø x 100mm long steel spool piece "]
[null,null,"and 3 x R8 bars welde across opening at "]
[null,null,"equal centres."]
[]
[null,null,"f) 100mm Ø flanged jet dispersers as ",null,null,"No",2]
[null,null,"detailed."]
[]
[null,null,"g) Calcamite step irons to be driven into",null,null,"No",18]
[null,null,"predrilled 25mm Ø x 75mm deep holes and"]
[null,null,"fixed with 'Epidermix 350' or similar "]
[null,null,"approved epoxy."]
[]
[null,null,"h) 50mm blinding layer (with 400mm thick ",null,null,"m²",12]
[null,null,"layer of 24mm crushed stone if soil "]
[null,null,"conditions are unstable)."]
[]
[null,null,"i) 150mm deep reinforced concrete slab.",null,null,"No",2]
[]
[null,null,"j) 230 x 230mm brick plinths",null,null,"No",2]
[]
[null,null,"k) 500 x 500 x 500mm grade 20/26MPa ",null,null,"No",2]
[null,null,"mass concrete thrust block."]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 22"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  4    ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[null,"SABS"]
[null,"1200 L"," MEDIUM-PRESSURE PIPELINES"]
[]
["4.17.5",null,"Supply all materials and seal joints between ",null,null,"sum",1]
[null,null,"manhole rings with \"Expandite Butyl 300\" "]
[null,null,"with root inhibitor or similar approved."]
[]
["4.17.6",null,"Supply and instal 700mm Ø Smart Lock ",null,null,"No",2]
[null,null,"cover and frame including keys."]
[]
["4.18","PSL","Additional wrapping to steel pipe under ",null,null,"m",100]
[null,"3.9.2.3","corrosive conditions as directed by "]
[null,"A 4 (a) ","Engineer. (Provisional)"]
[null,"(iv) & (v)"]
["4.19",null,"Supply all materials fabricate and install ",null,null,"No",150]
[null,null,"cradles and skids. Refer to drawing "]
[null,null,"Number 56724 sheet 11 for details."]
[]
["4.20",null,"Supply all materials and construct sleeve ",null,null,"No",10]
[null,null,"ends for 1117mm Ø pipe as detailed"]
[null,null,"on drawing No. 56724 sheet 11."]
[]
["4.21",null,"Supply and install 5 liters of paint, stencil ",null,null,"No",60]
[null,null,"and paint and install PC concrete markers"]
[null,null,"for air valves, scour valves and route"]
[null,null,"indicators. Refer to DWG No. 56724 "]
[null,null,"sheet 12."]
[]
["4.22","PS.A 8.9","Cost of survey including as-built survey.",null,null,"sum",1]
[]
["4.23","PS.4.4","Return excess material to Springfield store.",null,null,"kg",2000]
[]
["4.24","PS.DB","Supply all material and construct 150mm",null,null,"m","200"]
[null," 5.5 (b)","thick x 1.1m, 19mm stone bedding "]
[null,null,"wrapped in type A3 geotextile filter "]
[null,null,"incl. 150mm overlap in filter. (Provisional)."]
[]
["4.25",null,"Flush 500mm Ø pipeline including all ",null,null,"m",2700]
[null,null,"connections."]
[]
["4.26","PS.L.7.3","Test new 500mm Ø steel pipeline including ",null,null,"m",2700]
[null,"PS.L.","all assemblies and connections."]
[null,"8.2.18"]
["4.27","PS.L.7.3","Test existing 500mm Ø pipeline including ",null,null,"m",1100]
[null,"PS.L.","all assemblies and connections."]
[null,"8.2.18"]
[]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 23"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.28",null,"Remove end cap and tie in to the existing ",null,null,"sum",1]
[null,null,"500mm Ø steel pipe laid under Phase 1. "]
[null,null,"Refer to drawing No. 56724 sheet 2."]
[]
["4.29","PSL","Remove end cap and tie in to the existing ",null,null,"sum",1]
[null,"8.2.21","500mm Ø steel pipe at PI-52. Refer to "]
[null,null,"drawing No. 56724 sheet 7."]
[]
["4.30","PSL","Tie in to the existing 500mm Ø steel pipe",null,null,"sum",1]
[null,"8.2.21","pipe at reservoir site. Refer to drawing "]
[null,null,"No. 56724 sheet 7."]
[]
["4.31",null,"Provide the necessary electrical equipment",null,null,"sum",1]
[null,null,"to produce a through flow of air whilst "]
[null,null,"working inside the pipeline."]
[]
["4.32",null,"Protection of existing buildings, structures, ",null,null,"sum",1]
[null,null,"etc."]
[]
["4.33",null,"Supply of stormwater pipes up to 600mm Ø",null,null,"m",250]
[null,null,"as directed by the Engineer."]
[]
["4.34","PS.23","Cost of progress photographs emailed",null,null,"No",200]
[null,null,"to the Engineer. "]
[]
["4.35",null,"Crack survey (photographic evidence) for ",null,null,"No","100"]
[null,null,"existing properties in the vicinity of pipeline"]
[null,null,"pre and post installation."]
{"$rows_empty":20}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 24"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.36","PS.L-3.4","Standard Inlet detail"]
[null,"PSL-8.2.2"]
["4.36.1",null,"Fabricate, supply and install the following "]
[null,null,"material for standard inlet. Rate to include "]
[null,null,"Schedule 40 API and Rilsan lining and "]
[null,null,"coating where required."]
[]
[null,null,"a) 300mm Ø inlet tee. ",null,null,"sum","1"]
[]
[null,null,"b) 300mm Ø slip-on flanges",null,null,"No","6"]
[]
[null,null,"c) 3mm thick gas socket.",null,null,"No",2]
[]
[null,null,"d) 300mm Ø spool pieces, 121mm long.",null,null,"No",3]
[]
[null,null,"e) 25mm Ø thread-O-let gas socket and plug.",null,null,"sum",1]
[]
[null,null,"f) 300mm Ø blank flange with 25mm Ø ",null,null,"No",1]
[null,null,"pre-drilled hole at the centre of flange."]
[]
[null,null,"g) Retaining ring: 8mm thick x 200mm Ø.",null,null,"No",1]
[]
[null,null,"h) Retaining ring: 8mm thick x 295mm Ø.",null,null,"No",1]
[]
[null,null,"i) 3 No 8mm Ø lifting handles welde around ",null,null,"sum",1]
[null,null,"retaining rings."]
[]
[null,null,"j) 385mm Ø x 3mm thick insertion rubber with",null,null,"No",1]
[null,null,"230mm Ø opening."]
[]
[null,null,"k) 10mm thick orifice plate x155mm Ø.",null,null,"No",1]
[]
[null,null,"l) 25mm Øx 90° elbow.",null,null,"No",2]
[]
[null,null,"m) 10mm Ø holes in diffuser.",null,null,"No",6]
[]
[null,null,"n) Grade 16 flange 460mm OD x 220mm ID",null,null,"No",1]
[null,null,"x 12mm thick to be welded all around "]
[null,null,"250mm x 200mm Ø taper."]
[]
[null,null,"o) 250mm x 200mm Ø concentric taper.",null,null,"No",1]
[]
[null,null,"p) 250mm Ø x 250mm long straight pipe ",null,null,"No",1]
[null,null,"welded to taper."]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 25"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
[null,null,"q) Inlet pipe brackets as detailed.",null,null,"sum","1"]
[]
[null,null,"r) 300mm Ø  x 1500mm long steel pipe with",null,null,"No",1]
[null,null,"a 45° bend."]
[]
[null,null,"s) 25mm Ø holes in 300mm Ø pipe.",null,null,"No",2]
[]
[null,null,"t) 120 x 120 x 8mm plate thickness web ",null,null,"No",4]
[null,null,"welded all round to 300mm Ø pipe"]
[]
[null,null,"u) 25mm Ø air suction pipe. Length to be ",null,null,"No",2]
[null,null,"determined on site."]
[]
[null,null,"v) M16 SS bolts grouted in concrete with ",null,null,"No",4]
[null,null,"suitable epoxy."]
[]
[null,null,"w) 300mm Ø schedule 40 API pipe 1110mm",null,null,"No",1]
[null,null,"long"]
[]
[null,null,"x) 500mm Ø hole in reservoir roof slab.",null,null,"No",1]
[]
[null,null,"y) 750mm x750mm x 18mm thick plate.",null,null,"No",1]
[]
[null,null,"z) Weld all around top and underside of ",null,null,"sum","1"]
[null,null,"18mm thick plate."]
[]
[null,null,"aa) Support bracket to sit on a layer of ",null,null,"sum","1"]
[null,null,"epidermix 338 epoxy (100mm wide x20mm "]
[null,null,"thick) in order to create a seal between the "]
[null,null,"bracket and top of reservoir roof."]
{"$rows_empty":18}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 26"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.37",null,"Meter Chamber"]
[]
[null,null,"Supply all materials and construct 300mm ",null,null,"sum",1]
[null,null,"Ø Meter Chamber, as detailed on drawing "]
[null,null,"No. 56724 sheet 14. Rate to include for "]
[null,null,"excavation, backfilling, grade 25/19 "]
[null,null,"footing, brickwork,  2 No. 100mm Ø "]
[null,null,"galvanised air vent pipes with flanges and "]
[null,null,"2 No. 90° bends, 75mm thick 19mm stone "]
[null,null,"carpet, step irons and thrust blocks."]
[null,null,"Cover and frame measured elsewhere."]
[]
["4.37.1","PS.L.3.4","Supply and install the following steel "]
[null,null,"specialsas per standard drawing "]
[null,null,"No. 57276 sheet 20. Rate to include for "]
[null,null,"reinstatement of coating and lining and "]
[null,null,"corrosion protection. "]
[]
[null,null,"a) 500 x 500mm Ø tees F.A.E. Item 2.",null,null,"No",2]
[]
[null,null,"b) 500 x 300mm Ø reducer. F.B.E.",null,null,"No",6]
[]
[null,null,"c) 500mm Ø spool piece. F.B.E. Item 3.",null,null,"No",1]
[]
[null,null,"d) 300mm Ø R.S.V.  Item 4.",null,null,"No",3]
[]
[null,null,"e) 300mm Ø spool pieces. Cut to suit. ",null,null,"No",4]
[null,null,"Item 6."]
[]
[null,null,"f) 300mm Ø x 90° long radius bends. F.B.E.",null,null,"No",4]
[null,null,"Item 7"]
[]
[null,null,"g) 300mm Ø spool piece. Cut to suit. ",null,null,"No",1]
[null,null,"F.B.E. Item 9."]
[]
["4.37.2",null,"Collect from Springfield store and install"]
[null,null,"the following:"]
[]
[null,null,"a) 300mm Ø meter.",null,null,"No",1]
[]
[null,null,"b) 300mm Ø dirt box.",null,null,"No",1]
[]
[null,null,"c) 300mm Ø RSV.",null,null,"No",1]
[]
[null,null,"d) Triangular meter marker.",null,null,"No",1]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 27"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.37.3",null,"Supply and install 2 No. 1200mm x ",null,null,"sum",1]
[null,null,"1200mm fabricated galvanised cover and"]
[null,null,"frame including stainless steel bolts, plates "]
[null,null,"equal angles and waterproofing."]
[]
["4.37.4",null,"Supply all materials and construct 100mm",null,null,"sum",1]
[null,null,"thick reinforced concrete slab. Rate to"]
[null,null,"include formwork and smooth wood float"]
[null,null,"finishing."]
[]
["4.38","PS.L.3.4","OFF TAKE CHAMBER "]
[null,null,"(Refer to drawing No. 57276 sheet 13 for "]
[null,null,"details.)"]
[]
["4.38.1",null,"Supply and install the following steel "]
[null,null,"specials. Rate to include reinstatement of "]
[null,null,"coating and lining and corrosion protection."]
[]
[null,null,"a) 500mmm Ø pipe 2800mm long F.B.E.",null,null,"No",1]
[null,null,"with collar plates and a 300mm  Ø branch "]
[null,null,"pipe F.O.E. with a blank flange cut "]
[null,null,"centrally 100mm Ø hole and a 100mm Ø"]
[null,null,"pipe  F.O.E. item 1."]
[]
[null,null,"b) 500mmm Ø pipe 3700mm long F.O.E.",null,null,"No",1]
[null,null,"with collar plate and 150mm Ø hole. Item 2."]
[]
[null,null,"c) 500mm Ø x 45° gusset bend F.O.E.",null,null,"No",1]
[null,null,"including collar plate welded to 1600mm Ø "]
[null,null,"pipe. Item 3."]
[]
[null,null,"d) 150mm Ø x 45° long radius bend F.O.E.",null,null,"No",1]
[null,null,"with a 100mm pipe F.O.E. Item 4."]
[]
[null,null,"e) 150mm Ø x 90° long radius bend with",null,null,"No",1]
[null,null,"spool pieces F.O.E each such that C/F"]
[null,null,"equals 300mm. Item 5."]
[]
[null,null,"f) 150mm Ø x 2700mm spool piece. Item 6",null,null,"No",1]
[]
[null,null,"g) 150mm Ø x 100mm spool piece. Item 7.",null,null,"No",1]
[]
[null,null,"h) 150mmm Ø tee F.A.R. Item 10.",null,null,"No",1]
[]
[null,null,"i) 150mm Ø x 300mm spool piece. Item 12.",null,null,"No",1]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 28"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
[null,null,"j) 150mm Ø x 1000mm spool piece F.B.E.",null,null,"No",1]
[null,null,"Item 13."]
[]
[null,null,"k) 150mm Ø jet disperser F.O.E. Item 14.",null,null,"No",1]
[]
[null,null,"l) 100mm Ø x 300mm spool piece. Item 16.",null,null,"No",1]
[]
[null,null,"m) 150mm Ø spool piece F.O.E. Item 19.",null,null,"No",1]
[]
[null,null,"n) 150mm Ø spool piece F.O.E. Item 20.",null,null,"No",1]
[]
[null,null,"o) 200mm Ø x 550mm long spool piece ",null,null,"No",1]
[null,null,"with a 90° short radius bend air vent "]
[null,null,"assembly. Item 21."]
[]
[null,null,"p) 1100 x 1100 x 12 collar plate Grade X52",null,null,"No",1]
[null,null,"with two 5mm holes."]
[]
["4.38.2",null,"Collect from Springfield water store and "]
[null,null,"install the following :"]
[]
[null,null,"a) 500mm Ø wafer butterfly valve and ",null,null,"No",1]
[null,null,"gearbox. PN25. Item 8."]
[]
[null,null,"b) 150mm Ø wafer butterfly valve and ",null,null,"No",1]
[null,null,"gearbox. PN25. Item 9."]
[]
[null,null,"c) 150mm Ø wedge gate valve. PN25. ",null,null,"No",1]
[null,null,"Item 11."]
[]
[null,null,"d) 100mm Ø air valve. PN25. Item 15.",null,null,"No",1]
[]
[null,null,"e) 100mm Ø wafer butterfly valve. PN25.",null,null,"No",1]
[null,null,"Item 17."]
[]
["4.38.3",null,"Break concrete walls ±300mm deep to ",null,null,"sum",1]
[null,null,"expose existing reinforcement to enable "]
[null,null,"continuous reinforcing."]
[]
["4.38.4",null,"Supply and install Smartlock cover and frame",null,null,"sum",1]
[null,null,"including keys."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 29"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null," MEDIUM-PRESSURE PIPELINES"]
[]
["4.38.5",null,"Supply and install the following items :"]
[]
[null,null,"a) GRP steps, landing and supports.",null,null,"sum",1]
[]
[null,null,"b) GRP access ladder, measured to suit.",null,null,"sum",1]
[]
[null,null,"c) GRP safety cage.",null,null,"sum",1]
[]
[null,null,"d) GRP hand rails, measured to suit.",null,null,"sum",1]
[]
[null,null,"e) 150 x 150 x 5 steel plates with 4 M10 ",null,null,"sum",1]
[null,null,"bolts grouted in floor."]
[]
[null,null,"f) Securex cover and frame.",null,null,"sum",1]
{"$rows_empty":34}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 30"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
["4.39",null,"PRESSURE REDUCING VALVE (PRV)"]
[]
["4.39.1",null,"Supply and instal the following items:"]
[]
[null,null,"a) 500 x 300mm Ø taper. Item 1.",null,null,"No",1]
[]
[null,null,"b) 300mm Ø x 900mm long spool piece ",null,null,"No",1]
[null,null,"F.B. E. Item 2."]
[]
[null,null,"c) 300mm Ø x 90° long radius bend. F.B.E",null,null,"No",2]
[null,null,"with 100mm spool pieces F.B.E. Item 3."]
[]
[null,null,"d) 300mm Ø spool piece, length to be ",null,null,"No",2]
[null,null,"determined on site. Item 4."]
[]
[null,null,"e) 300mm Ø x 400mm long spool piece ",null,null,"No",2]
[null,null,"F.B. E. Item 5."]
[]
[null,null,"f) 300mm Ø butterfly valve with matching ",null,null,"No",2]
[null,null,"flanges and bolts sets. Item 6."]
[]
[null,null,"g) 300mm Ø x 90° long radius bend. F.B.E.",null,null,"No",2]
[null,null,"Item 7."]
[]
[null,null,"h) 25mm Ø air valve. Item 8.",null,null,"No",2]
[]
[null,null,"i) 300mm Ø PRV. Item 9.",null,null,"sum",1]
[]
[null,null,"j) 300mm Ø spool piece F.B.E. 1065mm",null,null,"No",1]
[null,null,"long. Item 10."]
[]
["4.39.2",null,"Supply all meterials and construct the "]
[null,null,"following items:"]
[]
[null,null,"a) ± 2850 x 400 x 400 mm thrust block.",null,null,"sum",1]
[]
[null,null,"b) 600 x 200mm concrete strip footing."]
[]
[null,null,"c) 270mm brickwork .",null,null,"m²",30]
[]
[null,null,"d) 50mm concrete infill all round.",null,null,"m³","2,0"]
[]
[null,null,"e) 2no. 2125 x 1865 x 75mm deep roof slabs ",null,null,"sum",1]
[null,null,"with 4no. each lifting holes plugged and "]
[null,null,"sealed with  bituminous joint sealant"]
[null,null,"(ABE bitujoint putty) or similar approved."]
[]
[null,null,"e) High tensile steel reinforcement.",null,null,"kg","95,0"]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 31"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 4        ",null,"PART: L  "," MEDIUM-PRESSURE PIPELINES"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,null,"BROUGHT FORWARD"]
[]
[null,null,"f) 10mm drip mould.",null,null,"m",15]
[]
[null,null,"g) Mesh Ref. 395.",null,null,"m²",30]
[]
[null,null,"h) 1400m x 75mm precast concrete lintels.",null,null,"No",2]
[]
[null,null,"i) Tapered hardwood plug 65mm Ø ",null,null,"No",8]
[null,null,"85 x 150mm long."]
[]
["4.39.3",null,"Collect from Springfield Water Store and"]
[null,null,"install the following items:"]
[]
[null,null,"a) 1800 x 900mm trox door.",null,null,"No",1]
[]
[null,null,"b) Air vents.",null,null,"No",2]
{"$rows_empty":35}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 32"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION 5        ",null,"PART: G  "," CONCRETE"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"BROUGHT FORWARD"]
[null,"SABS"]
["5","1200 G","CONCRETE"]
[]
["5.1",null,"Formwork"]
[]
[null,null,"a) Smooth vertical formwork in walls.",null,null,"m²",30]
[]
[null,null,"b) Smooth vertical formwork in roof slab.",null,null,"m²","39,24"]
[]
[null,null,"c) Extra over item c) for roof slab panels",null,null,"sum",1]
[null,null,"including lifting holes."]
[]
[null,null,"d) Smooth horizontal formwork in roof slab.",null,null,"m²","19,62"]
[]
[null,null,"e) Wood float finish in roof slab.",null,null,"m²","19,94"]
[]
["5.2",null,"Reinforcement"]
[]
[null,null,"a) Mild steel ",null,null,"kg",5]
[]
[null,null,"b) High tensile steel",null,null,"kg",2030]
[]
["5.3",null,"Concrete"]
[]
[null,null,"a) Grade 30/19 mPa in walls",null,null,"m³",5]
[]
[null,null,"b) Grade 30/19 mPa in roof slab",null,null,"m³","4,0"]
[]
["5.4","SABS","Excavate and backfill in all materials,",null,null,"m³",80]
[null,"1200 DA","compact to 95% Mod AASHTO density"]
[null,"8.3.1","and use for embankment or backfill or "]
[null,null,"dispose as ordered for off take chamber:"]
{"$rows_empty":19}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 33"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  6        ",null,"PART: LB","BEDDING (PIPES)"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
["6","1200 LB","BEDDING (500mm Ø PIPES)"]
[]
["6.1","8.2.1","Provision of selected granular material for ",null,null,"m³",100]
[null,null,"bedding cradle compacted to 93% MOD"]
[null,null,"AASHTO density from trench excavation. "]
[]
["6.2","8.2.1","Provision of selected fill material ",null,null,"m³",750]
[null,null,"compacted to 93% MOD AASHTO density "]
[null,null,"from trench excavation. "]
[]
["6.3","8.2.2","Provision of selected granular material for ",null,null,"m³",200]
[null,null,"bedding cradle compacted to 100% MOD"]
[null,null,"AASHTO density from commercial sources."]
[]
["6.4","8.2.2","Provision of selected fill material ",null,null,"m³",1700]
[null,null,"compacted to 93% MOD AASHTO density "]
[null,null,"from commercial sources."]
[]
["6.5","8.2.4","Encasing of pipes in grade 15/19 MPa",null,null,"m³",150]
[null,null,"concrete (Provisional)"]
{"$rows_empty":31}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 34"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  7       ",null,"PART: LG  ","PIPE JACKING "]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS"]
[null,"1200 LG","PIPE JACKING "]
[null,null,"Under 400551 St"]
[]
["7.1","8.2.1","Jacking establishment"]
[]
[null,null,"a) Fixed charges",null,null,"sum",1]
[]
[null,null,"b) Time related charges",null,null,"sum",1]
[]
["7.2","8.2.2","Supply 1117mm nominal Ø Class 100D",null,null,"m",24.4]
[null,null,"concrete jacking pipes."]
[]
["7.3","8.2.3","Jacking of 1117mm Ø Class 100D concrete",null,null,"m",24.4]
[null,null,"pipes."]
[]
["7.4","8.2.4","Excavate in soft material for jacking ",null,null,"m³",36]
[null,null,"1117mm Ø pipes."]
[]
["7.5","8.2.4","Extra over item (7.4) for hard material",null,null,"m³",10]
[null,null,"excavation. "]
[]
["7.6","8.2.8","Extra over item (7.4) for excavation in hard",null,null,"m³",25]
[null,null,"rock. "]
[]
["7.7","8.2.9","Stabilization of unstable areas or"]
[null,null,"grouting of voids where ordered."]
[]
[null,null,"a) Provision and establishment of ",null,null,"sum",1]
[null,null,"equipment on site and removal on "]
[null,null,"completion of operation. "]
[]
[null,null,"b) Operation of equipment",null,null,"day",2]
[]
[null,null,"c) Materials used",null,null,"m³",20]
[]
["7.8","8.2.10","Standing time for pipe jacking gang",null,null,"hour",18]
[null,null,"and the jacking equipment."]
[null,null,"(Provisional)"]
[]
["7.9",null,"Grout external periphery of pipe on "]
[null,null,"completion of jacking. (Min. grout 5 Mpa).",null,null,"m³",15]
[]
["7.10",null,"Allow for keeping excavations free from ",null,null,"sum",1]
[null,null,"water."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 35"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  7       ",null,"PART: LG  ","PIPE JACKING "]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[null,"1200 LG"]
[null,null,"PIPE JACKING "]
[null,null,"Under PI33-PI34. (traffic circle)."]
[]
["7.11","8.2.1","Jacking establishment"]
[]
[null,null,"a) Fixed charges",null,null,"sum",1]
[]
[null,null,"b) Time related charges",null,null,"sum",1]
[]
["7.12","8.2.2","Supply 1117mm nominal Ø Class 100D",null,null,"m",34.16]
[null,null,"concrete jacking pipes."]
[]
["7.13","8.2.3","Jacking of 1117mm Ø Class 100D concrete",null,null,"m",34.16]
[null,null,"pipes."]
[]
["7.14","8.2.4","Excavate in soft material for jacking ",null,null,"m³",55]
[null,null,"1117mm Ø pipes."]
[]
["7.15","8.2.4","Extra over item (7.14) for hard material ",null,null,"m³",15]
[null,null,"excavation. "]
[]
["7.16","8.2.8","Extra over item (7.14) for excavation in rock. ",null,null,"m³",25]
[]
["7.17","8.2.9","Stabilization of unstable areas or"]
[null,null,"grouting of voids where ordered."]
[]
[null,null,"a) Provision and establishment of ",null,null,"sum",1]
[null,null,"equipment on site and removal on "]
[null,null,"completion of operation. "]
[]
[null,null,"b) Operation of equipment",null,null,"day",2]
[]
[null,null,"c) Materials used",null,null,"m³",20]
[]
["7.18","8.2.10","Standing time for pipe jacking gang",null,null,"hour",18]
[null,null,"and the jacking equipment."]
[null,null,"(Provisional)"]
[]
["7.19",null,"Grout external periphery of pipe on "]
[null,null,"completion of jacking. (Min. grout 5 Mpa).",null,null,"m³",25]
[]
["7.20",null,"Allow for keeping excavations free from ",null,null,"sum",1]
[null,null,"water."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 36"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  7       ",null,"PART: LG  ","PIPE JACKING "]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[null,"1200 LG"]
[null,null,"PIPE JACKING "]
[null,null,"Under PI31-PI32. (traffic circle)."]
[]
["7.21","8.2.1","Jacking establishment"]
[]
[null,null,"a) Fixed charges",null,null,"sum",1]
[]
[null,null,"b) Time related charges",null,null,"sum",1]
[]
["7.22","8.2.2","Supply 1117mm nominal Ø Class 100D",null,null,"m",21.96]
[null,null,"concrete jacking pipes."]
[]
["7.23","8.2.3","Jacking of 1117mm Ø Class 100D concrete",null,null,"m",21.96]
[null,null,"pipes."]
[]
["7.24","8.2.4","Excavate in soft material for jacking ",null,null,"m³",35]
[null,null,"1117mm Ø pipes."]
[]
["7.25","8.2.4","Extra over item (7.4) for hard material",null,null,"m³",10]
[null,null,"excavation. "]
[]
["7.26","8.2.8","Extra over item (7.4) for excavation in hard",null,null,"m³",15]
[null,null,"rock. "]
[]
["7.27","8.2.9","Stabilization of unstable areas or"]
[null,null,"grouting of voids where ordered."]
[]
[null,null,"a) Provision and establishment of ",null,null,"sum",1]
[null,null,"equipment on site and removal on "]
[null,null,"completion of operation. "]
[]
[null,null,"b) Operation of equipment",null,null,"day",2]
[]
[null,null,"c) Materials used",null,null,"m³",20]
[]
["7.28","8.2.10","Standing time for pipe jacking gang",null,null,"hour",18]
[null,null,"and the jacking equipment."]
[null,null,"(Provisional)"]
[]
["7.29",null,"Grout external periphery of pipe on "]
[null,null,"completion of jacking. (Min. grout 5 Mpa).",null,null,"m³",15]
[]
["7.30",null,"Allow for keeping excavations free from ",null,null,"sum",1]
[null,null,"water."]
[]
[]
[]
[]
[]
[]
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 37"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  7       ",null,"PART: LG  ","PIPE JACKING "]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[null,"1200 LG"]
[null,null,"PIPE JACKING "]
[null,null,"Under 62021 TRK"]
[]
["7.31","8.2.1","Jacking establishment"]
[]
[null,null,"a) Fixed charges",null,null,"sum",1]
[]
[null,null,"b) Time related charges",null,null,"sum",1]
[]
["7.32","8.2.2","Supply 1117mm nominal Ø Class 100D",null,null,"m",24.4]
[null,null,"concrete jacking pipes."]
[]
["7.33","8.2.3","Jacking of 1117mm Ø Class 100D concrete",null,null,"m",24.4]
[null,null,"pipes."]
[]
["7.34","8.2.4","Excavate in soft material for jacking ",null,null,"m³",36]
[null,null,"1117mm Ø pipes."]
[]
["7.35","8.2.4","Extra over item (7.14) for hard material ",null,null,"m³",10]
[null,null,"excavation. "]
[]
["7.36","8.2.8","Extra over item (7.14) for excavation in rock. ",null,null,"m³",25]
[]
["7.37","8.2.9","Stabilization of unstable areas or"]
[null,null,"grouting of voids where ordered."]
[]
[null,null,"a) Provision and establishment of ",null,null,"sum",1]
[null,null,"equipment on site and removal on "]
[null,null,"completion of operation. "]
[]
[null,null,"b) Operation of equipment",null,null,"day",2]
[]
[null,null,"c) Materials used",null,null,"m³",20]
[]
["7.38","8.2.10","Standing time for pipe jacking gang",null,null,"hour",18]
[null,null,"and the jacking equipment."]
[null,null,"(Provisional)"]
[]
["7.39",null,"Grout external periphery of pipe on "]
[null,null,"completion of jacking. (Min. grout 5 Mpa).",null,null,"m³",15]
[]
["7.40",null,"Allow for keeping excavations free from ",null,null,"sum",1]
[null,null,"water."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 38"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  7       ",null,"PART: LG  ","PIPE JACKING "]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS","BROUGHT FORWARD"]
[null,"1200 LG"]
[null,null,"PIPE JACKING "]
[null,null,"Under Access Road to Platform 15"]
[]
["7.41","8.2.1","Jacking establishment"]
[]
[null,null,"a) Fixed charges",null,null,"sum",1]
[]
[null,null,"b) Time related charges",null,null,"sum",1]
[]
["7.42","8.2.2","Supply 1117mm nominal Ø Class 100D",null,null,"m",51.24]
[null,null,"concrete jacking pipes."]
[]
["7.43","8.2.3","Jacking of 1117mm Ø Class 100D concrete",null,null,"m",51.24]
[null,null,"pipes."]
[]
["7.44","8.2.4","Excavate in soft material for jacking ",null,null,"m³",80]
[null,null,"1117mm Ø pipes."]
[]
["7.45","8.2.4","Extra over item (7.14) for hard material ",null,null,"m³",25]
[null,null,"excavation. "]
[]
["7.46","8.2.8","Extra over item (7.14) for excavation in rock. ",null,null,"m³",35]
[]
["7.47","8.2.9","Stabilization of unstable areas or"]
[null,null,"grouting of voids where ordered."]
[]
[null,null,"a) Provision and establishment of ",null,null,"sum",1]
[null,null,"equipment on site and removal on "]
[null,null,"completion of operation. "]
[]
[null,null,"b) Operation of equipment",null,null,"day",3]
[]
[null,null,"c) Materials used",null,null,"m³",30]
[]
["7.48","8.2.10","Standing time for pipe jacking gang",null,null,"hour",27]
[null,null,"and the jacking equipment."]
[null,null,"(Provisional)"]
[]
["7.49",null,"Grout external periphery of pipe on "]
[null,null,"completion of jacking. (Min. grout 5 Mpa).",null,null,"m³",30]
[]
["7.50",null,"Allow for keeping excavations free from ",null,null,"sum",1]
[null,null,"water."]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 39"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  8       ",null,"PART: DK","GABIONS AND PITCHING"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[null,"SABS "]
["8","1200 DK","GABIONS AND PITCHING"]
[]
["8.1","8.2.1","Surface preparation for bedding of gabions.",null,null,"m²"]
[]
["8.2","8.2.2","Supply 1x1x1m Class A galvanised wire ",null,null,"m³",28]
[null,null,"gabions."]
[]
["8.3","8.2.2","Supply 1x1x0.5m Class A galvanised wire ",null,null,"m³",3.5]
[null,null,"gabions."]
[]
["8.4","8.2.3","Extra over item 4 above for packing selected",null,null,"m²",30]
[null,null,"stone for exposed face."]
[]
["8.5","8.2.4","Supply and install non-woven geo-textile filter",null,null,"m²",50]
[null,null,"made from high quality polypropylene fibers."]
{"$rows_empty":36}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 40"]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
["SECTION  9       ",null,"REINSTATEMENT"]
[]
["ITEM ","PAYMENT ","                 DESCRIPTION",null,null,"UNIT","QUANTITY","RATE","AMOUNT"]
["No","REFERS"]
[]
["9",null,"REINSTATEMENT"]
[]
["9.1",null,"Reinstatement of ground surface on pipeline",null,null,"m²",6500]
[null,null,"route."]
[]
["9.2","PS.29","Reinstatement of channels and haunching to",null,null,"m³",100]
[null,null,"suit existing."]
[]
["9.3","PS.27","Reinstatement of sign posts.",null,null,"No",10]
[]
["9.4",null,"Reinstatement of stormwater pipes ",null,null,"m",50]
[null,null,"Maximum Ø = 600mm. "]
[]
["9.5",null,"Reinstatement of stormwater catchpits.",null,null,"No",5]
[]
["9.6",null,"Spread and level 150mm thick topsoil as ",null,null,"m²",1000]
[null,null,"directed by Engineer."]
[]
["9.7","PSDB-","Grassing to areas as directed by the",null,null,"m²",1500]
[null,"8.3.6.2","engineer."]
[]
["9.8",null,"Reinstatement of precast concrete kerbs and",null,null,"m",200]
[null,null,"channels including haunching."]
[{"$nulls":6},"."]
["9.9",null,"Reinstatement of brickwork stormwater ",null,null,"No",3]
[null,null,"manholes. Maximum height 1.5m. Rate to "]
[null,null,"include reinforced concrete base and roof "]
[null,null,"slab."]
{"$rows_empty":23}
["TOTAL CARRIED FORWARD"]
[{"$nulls":8},"BoQ 41"]
[]
["CONTRACT NO. WS 7589"]
[]
["HAMMARSDALE HIGH LEVEL RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  "]
["STEEL INLET MAIN, WARDS 4 AND 103. "]
[]
[]
[null,"SUMMARY OF THE BILL OF QUANTITIES"]
[]
[]
[null,"SECTION 1"," :","GENERAL",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 2"," :","SITE CLEARANCE",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 3"," :","EARTHWORKS (PIPE TRENCHES)",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 4"," :","MEDIUM PRESSURE PIPELINES",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 5"," :","CONCRETE ",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 6"," :","BEDDING ",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 7"," :","PIPE JACKING ",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 8",null,"GABIONS AND PITCHING",{"$nulls":3},"R………………………………….."]
[]
[]
[null,"SECTION 9",null,"REINSTATEMENT",{"$nulls":3},"R………………………………….."]
[]
[]
[]
[]
[null,"SUBTOTAL A",null,"   R…………………………………….."]
[]
[]
[null,"•  VALUE ADDED TAX"]
[]
[]
[]
[null,"Add 15% of subtotal A",null,"              R…………………………………….."]
[null,"(Provisional sum based on current rate of VAT)"]
[]
[null,"TOTAL CARRIED TO TENDER FORM",{"$nulls":3},"   R…………………………………….."]
{"$rows_empty":12}
[{"$nulls":8},"BoQ 42"]

{"sheet":"Sheet2","index":1,"n_rows":30,"n_cols":5,"rows_kept":30,"flags":["formulas_cached_only"]}
[]
[null,"CONTRACT NO. WS 7589"]
[]
[null,"HAMMARSDALE RESERVOIR INLET (PHASE 2) - CONSTRUCTION OF ±2700m OF  500mm Ø  STEEL INLET MAIN,"]
[null,"WARDS 4 AND 103. "]
[]
[null,null,"SUMMARY OF BILL OF QUANTITIES"]
[]
[]
[null,"SECTION 1",null,"GENERAL"]
[]
[null,"SECTION 2",null,"SITE CLEARANCE",{"v":0,"d":"0.00"}]
[]
[null,"SECTION 3",null,"EARTHWORKS ( PIPE TRENCHES)",{"v":0,"d":"0.00"}]
[]
[null,"SECTION 4",null,"MEDIUM PRESSURE PIPELINES",{"$error":"#REF!"}]
[]
[null,"SECTION 5",null,"BEDDING",{"v":0,"d":"0.00"}]
[]
[null,"SECTION 6",null,"PIPE JACKING",{"v":0,"d":"0.00"}]
[]
[null,"SECTION 7",null,"REINSTATEMENT",{"v":0,"d":"0.00"}]
[]
[null,"SECTION 8",null,"VARIATION ORDERS"]
[]
[{"$nulls":3},"SUBTOTAL",{"$error":"#REF!"}]
[]
[{"$nulls":3},"VAT",{"$error":"#REF!"}]
[]
[{"$nulls":3},"TOTAL",{"$error":"#REF!"}]

{"sheet":"Sheet3","index":2,"n_rows":82,"n_cols":6,"rows_kept":82,"flags":["formulas_cached_only"]}
{"$rows_empty":19}
[null,null,"Air Valve Chamber (100mm Ø) "]
[null,null,"Off Road pipe."]
[]
[null,"PSL-8.2.2","Fabricate, supply and install the following"]
[null,"PSL-3.4","air valve specials: Rate to include for"]
[null,null,"drilling, welding, internal and external "]
[null,null,"corrosion protection and lining and coating"]
[null,null,"where applicable. Refer to drawing No."]
[null,null,"60501 for details."]
[]
[null,null,"a) 100mm Ø x 200mm long spool piece "]
[null,null,"F.O.E. Item B. "]
[]
[null,null,"b) 15mm Ø thread-O-Let Gas Socket."]
[null,null,"Item C."]
[null,null,"c) 100mm Ø Butterfly valve. Item E."]
[]
[null,null,"h) 15mm Ø male stop end. Item H."]
[]
[null,null,"i) 600mm Ø x 300mm long stub F.O.E. "]
[null,null,"welded to a watermain with a blank flange."]
[null,null," Item G."]
[]
[null,null,"j) Wrap item H in Denso Ultraflex or similar "]
[null,null,"approved material including 150mm "]
[null,null,"extension on each side of wall."]
[]
[null,null,"k) 100mm Ø Galvanised Mild Steel (GMS) "]
[null,null,"pipe with 180° Class 6 bend and standard "]
[null,null,"thread end to protrude 20mm from roof slab."]
[]
[null,null,"l) Two thickened GMS flanges."]
[]
[null,null,"m) Two anchor bolts to be tightened to "]
[null,null,"prevent rotation. Rate to include drilling of "]
[null,null,"holes or forming voids on slab."]
[]
[null,null,"n) 110mm Ø PVC pipe sleeve ± 200mm"]
[null,null,"long."]
[]
[null,null,"o) 110mm Ø GMS end cap drilled with "]
[null,null,"42 No. 6mm holes and lined with fibreglass "]
[null,null,"mosquito gauze."]
[]
[null,null,"p) 300mm Ø x 500mm long uPVC Class 6 "]
[null,null,"pipe."]
[]
[null,null,"q) GRP access ladder. Length to "]
[null,null,"determined on site. Refer to standard "]
[null,null,"drawing No. 45005."]
[]
[null,null,"r) Smart Lock heavy duty 700mm Ø "]
[null,null,"manhole access cover and frame."]
[]
[null,"PSL-3","Collect from Springfield Store and install the"]
[null,null,"following PN25 specials:"]
[]
[null,null,"a) 100mm Ø air valve assembly. Item A.",null,null,"No"]
[]
[null,null,"b) 100mm Ø butterfly valve. Item E.",null,null,"No"]
[]
[null,null,"d) 15mm Ø ball-o-stop. Female to male. ",null,null,"No"]
[null,null,"Item D."]