NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC LIMITED (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | Unit 1 to 6 BFPT Condenser Total Re-Tubing at Matla Power Station. |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [●] |
| Part C2 | Pricing Data | [●] |
| Part C3 | Scope of Work | [●] |
| Part C4 | Site Information | [●] |
| CONTRACT No. | [Insert at award stage] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] | [●] |
| C1.2a | Contract Data provided by the Employer | [●] |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | [●] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Unit 1 to 6 BFPT Condenser Total Re-Tubing at Matla Power Station.

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| Options A | The offered total of the Prices exclusive of VAT is | R |
| --- | --- | --- |
|  | Sub total | R |
|  | Value Added Tax @ 15% is | R |
|  | The offered total of the amount due inclusive of VAT is | R |
|  | (in words) |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy of this document, including the Schedule of Deviations (if any).

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | CSI (Coorporate Social Investment) | The Contractor shall spent 2% of contract value on CSI. The list of CSI projects will be provided by Matla Power Station.. |
| 2 | Skilled and non-skilled employees | The Contractor will develop local skilled labour at Kriel. The employer shall hire non-skilled employees from Kriel community. The list of potential employees from Kriel community will be provided by Matla Power Station. |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

| ## Clause |  | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |
|  |  | Option A | A: Priced contract with Activity Schedule |  |  |  |
|  |  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |
|  |  | and secondary Options |  |  |  |  |
|  |  |  | X2: Changes in the law X5: Sectional Completion |  |  |  |
|  |  |  | X7: Delay Damages |  |  |  |
|  |  |  | X16: Retention |  |  |  |
|  |  |  | X17: Low performance damages |  |  |  |
|  |  |  | X18: Limitation of liability |  |  |  |
|  |  |  | Z: Additional conditions of contract |  |  |  |
|  |  | of the NEC3 Engineering and Construction Contract, June 2005 (ECC3) (with amendments June 2006) |  |  |  |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Limited (reg no: 2002/015527/30), a juristic person incorporated in terms of the company laws of the Republic of South Africa |  |  |  |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |
|  |  | Represented by: | Fannie Nkabinde |  |  |  |
|  |  | Tel No. | 017 612 6200 |  |  |  |
|  |  | Fax No. | 086 523 2715 |  |  |  |
| 10.1 |  | The Project Manager is: (Name) | Fannie nkabinde |  |  |  |
|  |  | Address | Matla Power Station |  |  |  |
|  |  | Tel | +27 17 612 6200 |  |  |  |
|  |  | Fax | +27 86 523 2715 |  |  |  |
|  |  | e-mail | nkabinfa@eskom.co.za |  |  |  |
| 10.1 |  | The Supervisor is: (Name) | TBA |  |  |  |
|  |  | Address | [●] |  |  |  |
|  |  | Tel No. | [●] |  |  |  |
|  |  | Fax No. | [●] |  |  |  |
|  |  | e-mail | [●] |  |  |  |
| 11.2(13) |  | The works are | Unit 1 to 6 BFPT Condenser Total Re-Tubing at Matla Power Station. |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register | 1. Non-c0mpliance to statutory SHE and legal requirement which could result to injuries, near misses and penalties. 2. Damage to tubes during installation and injuries to people. 3. Poor system performance due to poor workmanship |  |  |  |
| 11.2(15) |  | The boundaries of the site are | Matla Power Station, site allocated for this project |  |  |  |
| 11.2(16) |  | The Site Information is in | Part 4 of the scope of work |  |  |  |
| 11.2(19) |  | The Works Information is in | Part 3: Scope of work and all document and drawings to which it makes it reference. |  |  |  |
| 12.2 |  | The law of the contract is the law of | the Republic of South Africa |  |  |  |
| 13.1 |  | The language of this contract is | English |  |  |  |
| 13.3 |  | The period for reply is | 2 working days |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is | 30 March 2023 |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: | Condition to be met |  |  | key date |
|  |  |  | 1 2 3 4 5 6. | Site measurements Procurement & fabrication of equipment Supply all equipment Remove old equipment. Installation of new equipment Inspection & commissioning |  | As per accepted programme |
| 30.1 |  | The access dates are: | Part of the Site |  | Date |  |
|  |  |  | 1 | 01 February 2021 | After the contract awarded |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within | 1 week of the signed Contract Date. |  |  |  |
| 31.2 |  | The starting date is: | 01 February 2022 |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than | 2 days when there are changes of the key dates and other events |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |
| 42.2 |  | The defects date is | 52 weeks after Completion of each section and sectional completion certificate will be issued |  |  |  |
| 43.2 |  | The defect correction period is | 3 days |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |
| 50.1 |  | The assessment interval is | Between the 25 day of each successive month. |  |  |  |
| 51.1 |  | The currency of this contract is the | South African Rand. |  |  |  |
| 51.2 |  | The period within which payments are made is | 5 weeks. |  |  |  |
| 51.4 |  | The interest rate is | (i) zero percent above the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: | Matla Power Station main security area |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, | the cumulative rainfall (mm) |  |  |  |
|  |  |  | the number of days with rainfall more than 10 mm |  |  |  |
|  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius the number of days with minimum air temperature more than 35 degrees Celsius the number of days with snow lying at 09:00 hours South African Time |  |  |  |
|  |  | The weather measurements are recorded by | The Contractor |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: | Kriel |  |  |  |
|  |  | and which are available from: | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |  |  |  |
| ## 7 |  | ## Title | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |
| 80.1 |  | These are additional Employer's risks | None |  |  |  |
| 84.1 |  | The Employer provides these insurances from the Insurance Table | as stated for “Format A” / “Format B” / “Format Dx” {choose the applicable format then delete the others and delete this note} available on http://www.eskom.co.za/live/content.php?Item_ID=9248 (See Annexure C for basic guidance) |  |  |  |
| 84.1 |  | The Employer provides these additional insurances | as stated for “Format A” / “Format B” / “Format Dx” {choose the applicable format, then delete the others and delete this note} available on http://www.eskom.co.za/live/content.php?Item_ID=9248 (See Annexure C for basic guidance) |  |  |  |
| 84.2 |  | The minimum limit of indemnity for insurance in respect of loss of or damage to property (except the works, Plant, Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract for any one event is | whatever the Contractor deems necessary in addition to that provided by the Employer. |  |  |  |
| 84.2 |  | The minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is | As prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of Indemnity of not less than R500 000 (Five hundred thousand Rands). |  |  |  |
| ## 9 |  | ## Termination | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |
| A | Priced contract with activity schedule | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |
| 60.6 | The method of measurement is | As stated in Part C2.1, Pricing Assumptions. |  |  |  |  |
| ## 11 | ## Data for Option W1 |  |  |  |  |  |
| W1.1 | The Adjudicator is (Name) | The person selected from the Eskom Panel of Adjudicators listed in Annexure D to this Contract Data by the Party intending to refer a dispute to him. |  |  |  |  |
|  | Address | TBA |  |  |  |  |
|  | Tel No. | [●] |  |  |  |  |
|  | Fax No. | [●] |  |  |  |  |
|  | e-mail | [●] |  |  |  |  |
| W1.2(3) | The Adjudicator nominating body is: | the Chairman of the Joint Civils Division of the South African Institution of Civil Engineering. (See www.jointcivils.co.za) |  |  |  |  |
| W1.4(2) | The tribunal is: | arbitration. |  |  |  |  |
| W1.4(5) | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |
|  | The place where arbitration is to be held is | Johannesburg South Africa |  |  |  |  |
|  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |
| X2 | Changes in the law | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data |  |  |  |  |
| X5 X7 | Sectional Completion Delay Damages | Supply all equipment, remove old equipment, and install new equipment, inspection & commissioning. The contractor pays delay damages at the rate stated in the Contract Data from the Completion Date for each day until the earlier of Completion and the date on which the Employer takes over the works. |  |  |  |  |
| X16 | Retention | 5% of Contract value (pending work completion and provision of data books) |  |  |  |  |
| X17 | Low performance damages | See Annexure B |  |  |  |  |
| X18 | Limitation of liability |  |  |  |  |  |
| X18.1 | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: | R0.0 (zero Rand) |  |  |  |  |
| X18.2 | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: | the amount of the deductibles relevant to the event described in the insurance policy format selected in the data for clause 84.1 above, which policy is available on http://www.eskom.co.za/live/content.php?Item_ID=9248 |  |  |  |  |
| X18.3 | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to | The greater of the total of the Prices at the Contract Date and the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus R15M first amount payable in terms of the Employer’s assets policy. |  |  |  |  |
| X18.4 | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: | The Contractor’s total liability to the employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: The total of the prices other than for the additional excluded matters. The contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are for the additional excluded matters are not limited. - Loss of or damage to property(other than the work, Plant and Material) - Death of or injury to person and - Infringement of an intellectual property right. |  |  |  |  |
| X18.5 | The end of liability date is | (i) 1 year after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |
| Z | The Additional conditions of contract are | Z1 to Z12 always apply. |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry and the Electricity Distribution Industry. |  |  |  |  |  |
| Z2 | Joint ventures (Not applicable for this contract) |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |
| Z2.3 | The Contractor does not substantially alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |
| Z3 | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |
| Z3.1 | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |
| Z3.2 | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |
| Z3.3 | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |
| Z3.4 | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |
| Z4 | Ethics |  |  |  |  |  |
| Z4.1 | Any offer, payment, consideration, or benefit of any kind made by the Contractor, which constitutes or could be construed either directly or indirectly as an illegal or corrupt practice, as an inducement or reward for the award or in execution of this contract constitutes grounds for terminating the Contractor’s obligation to Provide the Works or taking any other action as appropriate against the Contractor (including civil or criminal action). (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z4.2 | The Employer may terminate the Contractor’s obligation to Provide the Works if the Contractor (or any member of the Contractor where the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations) is found guilty by a competent court, administrative or regulatory body of participating in illegal or corrupt practices. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) Such practices include making of offers, payments, considerations, or benefits of any kind or otherwise, whether in connection with any procurement process or contract with the Employer or other people or organisations and including in circumstances where the Contractor or any such member is removed from the an approved vendor data base of the Employer as a consequence of such practice. |  |  |  |  |  |
| Z4.3 | Notwithstanding the provisions of core clause 90.2, the procedures on termination in terms of this clause are P1, P2 and P3 as stated in the core clause 92 and the amount due is A1 and A3 as stated in core clause 93. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z5 | Confidentiality |  |  |  |  |  |
| Z5.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z5.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z5.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z5.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z5.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. (The provision of this clause shall apply equally where Employee or person acting on behalf of the Employer offers bribes or solicits payment from the contractor) |  |  |  |  |  |
| Z6 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |
| Z6.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |
| Z7 | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |
| Z7.1 | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2003 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |
| Z7.2 | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |
| Z8 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |
| Z8.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |
| Z8.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |
| Z8.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |
| Z9 | Notifying compensation events |  |  |  |  |  |
| Z9.1 | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |
| Z10 | Employer’s limitation of liability |  |  |  |  |  |
| Z10.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |
| Z10.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited to compensation as provided for under the compensation events stated in this contract. |  |  |  |  |  |  |
| Z11 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |
| Z11.1 | or had a judicial management order granted against it. |  |  |  |  |  |  |
| Z12 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |
| Z12.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |
| --- | --- | --- | --- | --- |
| Month | Average Rainfall (mm) | Average Number of days with rainfall | Absolute High [Low] temperature (C) | Average midday High [Low] temperature (C) |
| January |  |  |  |  |
| February |  |  |  |  |
| March |  |  |  |  |
| April |  |  |  |  |
| May |  |  |  |  |
| June |  |  |  |  |
| July |  |  |  |  |
| August |  |  |  |  |
| September |  |  |  |  |
| October |  |  |  |  |
| November |  |  |  |  |
| December |  |  |  |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

Annexure B:  Table of low performance damages (X17)

| Low Performance Damage Description | Value of Low Service Damages | Limit of Low Service Damage |
| --- | --- | --- |
| Performance delays not finishing as per agreed upon schedule submitted to the Project leader | 0.5% of contract cost per day | Limited to 10% of the Contract value |
| Submission of data-book as per QCP requirements | 0.5% of contract cost per day | Limited to 10% of the Contract value |
| Rework due to poor workmanship. | 1% of contract cost per day | Limited to 10% of the Contract value |
| Daily Progress Updated Schedule | 0.5% of contract cost per day | Limited to 10% of the Contract value |
| If the damages exceed 10% of Contract value the Contract will be terminated as per ECC clause 91.2 (R11) |  |  |

# Annexure C:	Insurance provided by the Employer

These notes are provided as guidance to tendering contractors and the Contractor about the insurance provided by the Employer. Details of the insurance itself are available from the internet web link given below.

- For the purpose of works contracts, insurance provided by Eskom (the Employer) has been arranged on the basis of “project” or “contract” value, where the value is the total of the Prices at Completion of the whole of the works including VAT.

A “project” is a collection of contracts or work packages to be undertaken as part of a single identified capital expansion or refurbishment of a particular asset or facility.

A “contract” is a single contract not linked to or being part of a “project”.

- For ECC3 there are three main “formats” of cover and deductible structure; Format A, Format B and Format Dx.

Format A is for a project or contract value less than or equal to R350M (three hundred and fifty million Rand) inclusive of VAT.

Format B is for a project or contract value greater than R350M .(three hundred and fifty million Rand) inclusive of VAT.

In the case of contracts / packages within a project:

- For a contract / package of R50M which is part of a R400M project, Format B will apply

- For a contract / package of R250M which is part of a R6 billion project, Format B will apply;

- For a contract / package of R120M which is part of a R350M project Format A will apply;

For a contract which is not part of a project the same limits apply:

- For a contract of R50M, Format A will apply

- For a contract of R355M, Format B will apply.

Format Dx applies only to Distribution Division projects and contracts. If a Distribution Division project or contract exceeds the Format A limit, the Eskom Insurance Management Services [EIMS] need to be contacted for advice on how to formulate the insurance cover.  Cover and deductibles for Distribution Division are per the relevant policy available on the internet web link given below.

Format A generally applies to Transmission Division projects and contracts. If a Transmission Division project or contract exceeds the Format A limit, the Eskom Insurance Management Services [EIMS] need to be contacted for advice on how to formulate the insurance cover.

- Tendering contractors should note that cover provided by the Employer is only per the policies available on the internet web link listed below and may not be the cover required by the tendering contractor or as intended by each of the listed insurances in the left hand column of the Insurance Table in clause 84.2.  In terms of clause 84.1 “the Contractor provides the insurances stated in the Insurance Table except any insurance which the Employer is to provide”.  Hence the Contractor provides insurance which the Employer does not provide and in cases where the Employer does provide insurance the Contractor insures for the difference between what the Insurance Table requires and what the Employer provides.

- When the Marine Insurance is required the Contractor needs to obtain a copy of the latest edition of Eskom’s Marine Policies Procedures found at internet website given below.

- Further information and full details of all Eskom provided policies and procedures may be obtained from:

http://www.eskom.co.za/live/content.php?Item_ID=9248

# Annexure D:	The Employer’s Panel of Adjudicators

The following persons listed in alphabetical order of their surname have indicated their willingness to be included in the Eskom Panel of Adjudicators.  Their CV’s may be obtained by using the contact details provided.

| Name | Location | Contact details (phone & e mail) |
| --- | --- | --- |
| Nigel ANDREWS | Gauteng | +27 11 836-6760 nigela@quoin.net |
| Andrew BAIRD | Gauteng | +27 11 803 3008 andrewbaird@ecsconsult.co.za |
| Christopher BINNINGTON | Gauteng | +27 11 888-6141 cdb@bca.co.za |
| Peter HIGGINS | UK | +44 1293 873 868 peterhiggins@pdconsult.co.uk |
| Bruce LEECH | Gauteng | +27 11 290 4000 leech@counsel.co.za |
| Nigel NILEN | Gauteng | +27 11 465 3601; nilences@global.co.za |
| Peter THURLOW | Gauteng | +27 11 787 6226 info@thurlowassoc.com |

Information about the Panel and appointment of the selected Adjudicator is available from Eskom Supply Chain Operations management, by contacting Leighton Itholeng (Tel.: +27 (0)11 800 4031)

(Fax :+27 (0)86 668 0419) E-mail: Leighton.Itholeng@eskom.co.za

C1.2 Contract Data

# Part two - Data provided by the Contractor

Notes to a tendering contractor:

- Please read both the NEC3 Engineering and Construction Contract (June 2005) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 152 to 154 of the ECC3 Guidance Notes.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 11.2(8) | The direct fee percentage is |  |
|  | The subcontracted fee percentage is |  |
| 11.2(18) | The working areas are the Site and | Matla Power Station premises |
| 24.1 | The Contractor's key persons are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | 2 Name: |  |
|  | Job |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled |
| 11.2(3) | The completion date for the whole of the works is |  |
| 11.2(14) | The following matters will be included in the Risk Register |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: | Attached scope of work |
| 31.1 | The programme identified in the Contract Data is |  |
| A | Priced contract with activity schedule |  |
| 11.2(20) | The activity schedule is in |  |
| 11.2(30) | The tendered total of the Prices is | (in figures) (in words), excluding VAT |

# Part 2: Pricing Data

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A |  |
| C2.2 | Activity Schedule |  |

C2 Pricing Data for an Activity Schedule

# C2.1 Pricing assumptions

How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, June 2005 Option A states:

Identified and defined terms

11.2	(20) 	The Activity Schedule is the activity schedule unless later changed in

accordance with this contract.

(27) 	The Price for Work Done to Date is the total of the Prices for

each group of completed activities and

each completed activity which is not in a group.

A completed activity is one which is without Defects which would either delay

or be covered by immediately following work.

(30) 	The Prices are the lump sum prices for each of the activities on the

Activity Schedule unless later changed in accordance with this contract.

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum. Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site

Information”. This confirms that instructions to do work or how it is to be done are not included in the Activity

Schedule but in the Works Information. This is further confirmed by Clause 20.1 which states, “The

Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not

Provide the Works in accordance with the Activity Schedule. The Activity Schedule is only a pricing

document.

Preparing the activity schedule

The tendering contractor shall prepare the activity schedule and should study the Guidance Notes

pages 19 and 20 before doing so. The Employer may have instructed the tendering contractor to include

particular activities (as listed) which he has specified and requires the Contractor to identify them in his activity schedule.

- It is the Contractor who prepares the Activity Schedule as part of his tender by breaking

down the work described within the Works Information into suitable activities which can be well defined, priced as a lump sum and shown on the programme. The Employer, in his Conditions of Tender or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

- The Prices are defined in clause 11.2(20) as the lump sum for each activity in the activity schedule

and the Price for Work Done to Date (PWDD) (the amount due to the contractor) is defined in clause

11.2(24) as the total of the Prices for each activity that has been completed. Hence activities in the activity schedule should be structured so as to provide an acceptable monthly cash flow as they are only assessed for payment on the assessment date if they have been completed.

- As the Contractor has an obligation to correct Defects (core clause 43.1) and there is no

compensation event for this unless the Defect was due to an Employer’s risk, the lump sum Prices must also include for the correction of Defects.

- If the Contractor has decided not to identify a particular activity, the cost to the Contractor of doing the work must be included in, or spread across, the other Prices in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- There is no adjustment to the lump sum activity schedule price if the amount, or quantity, of work

within that activity later turns out to be different to that which the contractor estimated at time of tender.

The only basis for a change to the Prices is as a result of a compensation event. See Clause 60.1.

- Hence the Prices tendered by the Contractor in the activity schedule are inclusive of everything

necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk.

- However, the Contractor does not have to allow in his Prices for matters that may arise as a result of a compensation event. It should be noted that the list of compensation events includes those arising as a result of an Employer's risk event listed in core clause 80.1.

# C2.2 Activity Schedule

The Price List is as follows:

| No. | Description |  | Unit | Per unit | Quantity for 6 units |
| --- | --- | --- | --- | --- | --- |
| 1 | P & G’s |  |  |  |  |
| 1.1 | Site establishment |  | Sum |  | 1 |
| 1.2 | SHEQ Requirements and documentation |  | Sum |  | 1 |
| 1.3 | Transport and Accommodation |  | Sum |  | 1 |
| 1.4 | Commissioning and testing |  | Sum |  | 1 |
| 1.5 | Site De-establishment |  | Sum |  | 1 |
| 2 | Tubes |  |  |  |  |
| 2.1 | Condenser tubes per BFPT |  | Sum | 3770 | 22620 |
|  | Number of condenser tubes per BFPT condenser = 3720 |  | Sum |  |  |
|  | Additional number of tubes to cater for damage per unit = 50 |  | Sum |  |  |
|  | Total per unit = 3770, Number of Units = 6 |  | Sum |  |  |
|  | Total for 6 Units = 22620 |  | Sum |  |  |
| 2.2 | Provision to replace stay bars. |  | Sum | 1 | 6 |
| 2.3 | Refurbishment of condenser water boxes. |  | Sum | 1 | 6 |
| 3 | Labour |  |  |  |  |
| 3.1 | Supply Engineering Manager; Project Manager and Systems Technician with a high level project schedule for the re-tube. | Sum |  | 1 | 6 |
| 3.2 | Install rigging equipment. | Sum |  | 1 | 6 |
| 3.3 | Opening of water box. | Sum |  | 1 | 6 |
| 3.4 | Rig Cooling water inlet and outlet pipe work to ground level. | Sum |  | 1 | 6 |
| 3.5 | Manage scaffold building (free issued by employer) where to build scaffolds for safe access. | Sum |  | 1 | 6 |
| 3.6 | Inspect support plates on steam space and re-weld damaged | Sum |  | 1 | 6 |
| 3.7 | Remove tube plugs installed on leaking tubes and internal cut from North side water box. | Sum |  | 1 | 6 |
| 3.8 | Start pulling cut tubes south side. | Sum |  | 1 | 6 |
| 3.9 | Transport Free Issue tubes from stores and onto lay down area. | Sum |  | 1 | 6 |
| 3.10 | Mechanically clean tube sheet faces. | Sum |  | 1 | 6 |
| 3.11 | Do “Z” pattern hole check on 10% of and record in order to calculate expansion percentage. | Sum |  | 1 | 6 |
| 3.12 | Perform a mock up and pull out test. | Sum |  | 1 | 6 |
| 3.13 | Install new free issued tubes. | Sum |  | 1 | 6 |
| 3.14 | Expand and cut back tube ends if required. | Sum |  | 1 | 6 |
| 3.15 | Close water box. | Sum |  | 1 | 6 |
| 3.16 | Rig cooling water pipe work into position and secure. | Sum |  | 1 | 6 |
| 3.17 | Fill unit with water and florescent dilution to detect leaking tubes when flood test is performed. | Sum |  | 1 | 6 |
| 3.18 | Witness flood test and re-expand leaking tubes should it be required. Supply plugs and plug leaking damaged tubes that cannot be expanded | Sum |  | 1 | 6 |
| 3.19 | Ensure a complete “punch list” was performed on all tasks relevant to the re-tube. | Sum |  | 1 | 6 |
| 3.20 | Remove all scrap from condenser area to scrap yard within the security borders of Matla Power Station | Sum |  | 1 | 6 |
| 3.21 | Sandblast and coat tube plate | Sum |  | 1 | 6 |
| 3.22 | Inspect water box coating and repair damaged areas | Sum |  | 1 | 6 |

Part 3: Scope of Work

See attached Appendix 1

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

C3:  Scope of Work

# C3.1 Works Information

1. Description of the works

## Executive Overview

Unit 1 to unit 6 BFPT   Condenser at Matla Power Station contains admiralty brass tubes. Over the decades these tubes have deteriorated to the point where replacement is necessary. Deteriorating water quality dictates that brass can no longer be used so it is therefore required that the condenser gets re-tubed with a more erosion and corrosion resistant material. Titanium grade 2 has satisfactory material properties to withstand the effects of the cooling water.

The scope of work covers the refurbishment of 100 % of unit 1 to unit 6 BFPT Condenser to ensure plant integrity and availability. The scope will include the installation of the tubes, refurbishment of the shell, tube plates, support plates, stay-bars, emergency drain baffles, air extraction lines and the air cooling zones.

All door seals to be replaced. Rubber lining on water boxes to be inspected and any damage be repaired with approved rubber lining repair method.

## Employer’s Objectives and purpose of the works

The objectives of the 100 % re-tube project are to eliminate the UCLF caused by tube failures, and improve the main condenser availability and reliability by removing the admiralty brass tubes (which are subject to continuous corrosion and leaks due to the aggressive chemistry of the circulating cooling water, and are prone to attack by ammonia in the boiler feed water), and replacing them with new tubes.

## Scope of the Works

Only tenders submitted by suitably experienced Contractors will be evaluated.   The Contractor shall submit a verifiable reference list of condenser retube projects.  The minimum acceptable criteria is that either the main Contractor or joint venture partner/s shall provide evidence that they have fully re-tubed more than one steam condenser for a turbine size greater than 100 MW, in the last 5 years.

This Works Information defines the minimum requirements to be achieved by the Contractor in carrying out the condenser re-tube work.

The Contractor removes the old tubes and installs the new tubes supplied by the Employer.

The Contractor refurbishes the condenser shell, tube plates, tube sheets, stay bars and drain baffles as is found to be necessary and as detailed elsewhere in this document. Replacement of door seals will be the responsibility of the Contractor.

It is the Contractor’s responsibility to acquaint him/her with the layout and construction of the condensers. All relevant and available condenser data is included in Table 3.

This Works Information details the minimum quality, testing, inspection, certification, and cleaning requirements, and these are to be supplemented by the Contractor’s suggested actions based on inspections.

The Contractor is responsible for compliance with all of the detailed requirements presented in this Works Information. Approval of any drawings, specifications, and procedures by the Employer or its representatives shall in no way relieve the Contractor of these responsibilities. In addition scale on the internal diameter of the tubes has reduced the tube inner diameter to the extent that it may be difficult the insert extraction spears.  Scrap tubes remain the property of the Employer who will dispose of them.

The following table outlines the high level scope of work:

Table: High Level Scope of Work

| Scope of Work | Responsible Person | Non Critical to contractor |
| --- | --- | --- |
| Transport of new tubes from storage area to condenser | Contractor |  |
| Application for permit to work | Eskom |  |
| Issue permit to work for condenser | Eskom |  |
| Isolation of condenser | Eskom |  |
| Installation of spades in CW ducts. Installation of blanks in all pipe openings at the bottom of the condenser. Material for and spading of openings | Eskom (main CW ducts) / Contractor (steam space) | Non critical |
| Opening of condenser waterbox doors will form part of the Contractor scope. This includes new door seals. The sealing surface must be vacuum blasted and coated with a 50 micro epoxy coating before the seal is reinstalled | Contractor | Non critical |
| Inspect -CW Cross Over Pipe Support Hanger Studs and Nuts and repair damaged ones as per inspection findings and recommendation from engineering | Contractor / Engineering to inspect Material to be supplied by Eskom | Non critical |
| Scaffolding requirements | Eskom / Contractor | Non critical |
| Load test of temporary crawl beams and rigging structures | Contractor (Employer to review results) |  |
| Load test of permanent crawl beams and rigging structures | Eskom |  |
| Inspect and repair rubber lining of both water box and crossover pipes | Contractor | Non critical |
| Weld repairs in steam space | Contractor | Non critical |
| Tubesheet inspection, Blast cleaning tubesheet to remove scale deposit and previous coating also blast 70 mm into each tube to remove scale | Contractor | Non critical |
| Removal of existing tubes | Contractor |  |
| Support plate inspection | Contractor |  |
| Tube to tubesheet joint mock up tests | Contractor |  |
| Tube installation and tube to tubesheet joint seal | Contractor |  |
| Re sleeving of over sided holed tubes (Make provision to re sleeve 200 per 1 BFPT Condenser ) | Contractor |  |
| Waterbox door seal procurement and installation | Contractor |  |
| Bullet test to be conducted on 100% of all tubes. | Contractor |  |
| Purchase plugs to cover a range of holes | Contractor |  |
| Tubesheet coating and tube flaring | Contractor |  |
| Removal of spades and blanks in steam space as well as CW spades. Final cleaning of steam space | Eskom /Contractor | Non-critical |
| Steam space (demin) high level test | Contractor/ Eskom |  |
| Adjustment of condenser Jacks | Eskom | Non critical |
| Tube side (CW) water box leak test | Contractor |  |
| Final inspection | Contractor/ Eskom |  |
| NDT testing to be done on 50% of all internal steam space welds | Contractor | Non-critical |
| Transport of scrap brass/titanium tubes to on site storage area. | Contractor |  |
| Supply and installation of tube sheet sleeves for oversize tube sheet holes | Contractor |  |
| Visual inspection of tube bundle tie rods anchor pin cap nuts for damage | Contractor |  |

NB: N exclusions will only be allowed on non-critical activities

2. Drawings

| Drawing number | Revision | Title |
| --- | --- | --- |
| 047/257 | N/A | Matla Power-Station Layout |

3. Specifications

| Title | Date or revision | Tick if publicly available |
| --- | --- | --- |
| General Specifications: |  |  |
| Health and Safety Specifications For Contracting Companies | OMOP 2605 | Yes |
| Eskom Life Saving Rules | 32-421 | Yes |
| Construction Regulations | 32-136 | Yes |
| Conflict of Interest Policy | 32-173 | Yes |
| Plant Safety Regulations |  | Yes |
| Technical specifications As per Engineering Scope of Works |  |  |

4. Constraints on how the Contractor Provides the Works

4.1 Meetings

The Contractor will comply with the project requirements as set by the Employer. The Contractor will provide a detailed feedback on progress every day during this project as requested by the Employers Representative. The Contractor will attend project meetings as will be communicated by the Employers Representative, up until Completion is achieved.

4.2 Use of standard forms

The contract will strictly be in accordance with the NEC ECC. Early warnings, compensation events etc. are to be notified to the delegated personnel.

## 4.3 Invoicing and payment

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment. The Contractor applies for payment with a tax invoice addressed to the Employer.

The Contractor includes the following information on each tax invoice:

Name and address of the Contractor

The contract number and title;

Contractor’s VAT registration number;

The Employer’s VAT registration number 4740101508;

The total Price for Work Done to Date which the Contractor has completed;

Other amounts to be paid to the Contractor;

Less amounts to be paid by or retained from the Contractor;

The change in the amount due since the previous payment being the invoiced amount - excluding VAT, the VAT and including VAT;

(add other as required)

The Contractor attaches the detail assessment of the amount due to each tax invoice showing the Price for Work Done to Date for each item in the Price List for work which he has completed.

All invoices are to be submitted to the Employer’s Representative for processing.

4.4 Records of Defined Cost

In order to substantiate the Defined Cost of compensation events, the Employer may require the Contractor to keep records of amounts paid by him for people employed by the Contractor, Plant and Materials, work subcontracted by the Contractor and Equipment. [See clause 11.2(5) and 63.2].

The Contractors Site Manager will complete a site daily log and this will be submitted to the Employers Representative for his signature before 12am of the following morning barring weekends. The Friday and weekend logs will be submitted before 12am Mondays. The log will include but not be limited to the following:

- Date and day.

- Weather.

- Site conditions.

- Work done.

- Labour on site.

- Any incidents during that period.

- Any communication that took place.

### 4.5 Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

Not applicable.

### 4.6  BBBEE and preferencing scheme

Not applicable.

4.7 Facilities to be provided by the Contractor

The Contractor is to provide all necessary in order to implement and comply with the Works Information.

4.8 Title to material from excavation and demolition

Add to clause 70.2. The Contractor has no title to any material removed in the Plant. All material removed is to be stored at a place indicated by the Employers Representative.

4.9 Design by the Contractor

Not applicable to this contract however the Contractor must give the Employer a ten (10) year warranty on the repair.

5. Requirements for the programme

The Contractor will provide a detailed programme every second day during the project or as requested by the Employers Representative. The Employer may terminate a contract if a detailed programme is not submitted as requested by the Employers Representative. The final contract programme and breakdown will be agreed upon within three (3) days after order placement by the Employer & the Contractor.

The Contractor shall supply together with the tender a computerized detail bar-chart programme indicating the sequence and duration of all activities and the required contractual completion dates.

5.1. Up to R35 000, 00

- Computerized barchart weekly (or otherwise negotiated) updated programme to monitor their actual progress against contractual dates.

5.2. Up to R350 000,00

- Computerized high level barchart on Micro Soft Projects.

- Listing report.

- Resource report.

- Weekly updated programme to monitor their actual progress against contractual dates.

5.3. More than R350 000,00

- Computerized logic network

- Network barchart

- Time analysis (print out listing)

- Weekly updated critical activities report

- Weekly updated resource report

- Weekly updated interface dates with other Contractors.

5.4. Activities on critical path

On request from the Employers Representative for work on critical path the Contractor must submit

- Computerized programme twice a day.

- However, should a logic change been executed by the Contractor, A revised network, bar-chart and time analysis must be submitted by the Contractor.

- Key dates are considered as part completion dates and failure by the Contractor to meet those dated could result in the imposition of penalties by Eskom.

- If any difficulties are foreseen in complying with the requirements of this document, these must be resolved with the Employers Representative  before the tender is submitted.

6. Services and other things provided by the Employer

| Item | Date by which it will be provided |
| --- | --- |
| Water connection /. Disconnection point. Water will be made available on request free of charge from water points on site. The Contractor will supply at his own cost all the necessary connections, fittings, piping etc. for this facility. Eskom does not guarantee continuity of supply and quality of the water and the Contractor shall make his own arrangements for alternative supplies where required. Any breakdown or reduction in the water supply will not be grounds for claims for additional time or compensation. Should the Contractor have any particular requirements with respect to water quality or supply these must be stated in his tender. |  |
| Electricity connection / disconnection. The Contractor to provide all necessary cabling, Certificate of Compliance (COC) etc. Electricity will be made available for construction purposes free of charge from power points, which will be indicated by the Employers Representative. The Contractor will be made responsible for the provision of the reticulation system from the point of supply. Both 220 (AC) Volt and 380 Volt (AC) are available on request. The Contractor’s requirements are to be stated in his tender. Eskom does not guarantee the quality of supply of the power and the Contractor shall make his own arrangements for alternative supplies where required. Any breakdown or reduction in the power supply will not be grounds for claims for additional time or compensation. |  |
| Site yard. A site will be made available to the contractor for his yard within the Power Station security area, but not adjacent to the work (the exact location is to be determined on site). The yard is to be considered as a raw site and the Contractor will arrange for temporary services. |  |
| Scaffolding and insulation. |  |
| Gas test and environmental certificate. |  |
| Sanitary facilities and refuse. The Contractor is to supply own sanitary facilities at his Contractor’s yard. Eskom’s sanitary facilities may be used as directed by the Employers Representative. A refuse control system will be established by the Contractor. All waste and refuse shall be collected and disposed of as directed by the Employers Representative, at the Matla Power Station refuse disposal site. |  |

C4:  Site Information

# C4.1: Information about the site at time of tender which may affect the work in this contract

## 1. Access limitations

The works is within the security area of the Power Station and access to the site will be governed by the terms and conditions laid down by the Station Security Officials from time to time. The Contractor shall satisfy himself as to these terms and conditions and shall price his works accordingly.

The Contractor shall liaise with the Power Station Security Staff in order to obtain temporary permits for his staff and vehicle, which will be working within the Station.

With the exception of Construction Plant the Contractor shall be restricted to having only one other vehicle on site for transporting his employees and materials. Any other need is to be granted by the Employers Representative.

Personnel and vehicles entering and leaving the site are subject to routine searches and substance abuse testing.

The Contractor will have to obtain a “gate permit” from the Employers Representative, before materials and equipment can be removed from the site. The “gate permit” gives and itemized list of materials and equipment to be removed from site.

The Contractor shall make his own assessment of, and shall allow in his rates for those access problems which may be encountered and no extra payment or claim of any kind will be allowed on account of difficulties of access to the Works.

## 2. Ground conditions in areas affected by work in this contract

Not applicable. The Contractor to specify any information required if necessary.

## 3. Hidden and other services within the site

All known services will be brought to the attention of the Contractor by Employers Representative. Should the Contractor encounter any other services in the work area, he will immediately bring them to the attention of the Employers Representative who will issue instructions as to what actions are to be taken.

The protection of all pipes, gauges and plant is of extreme importance. Should any damage take place, which is due to the Contractors negligence, another Contractor will be brought onto site to affect repairs.  All costs will be to the account of the Contractor who caused damage.

## 4. Details of existing buildings / facilities which Contractor is required to work on

Not applicable. The Contractor to specify any information required if necessary.

5. Inspection on site

The Contractor shall take note of, and allow in his price for any items which may not be clearly defined on the enquiry drawings and / or document / s submitted with this tender. He shall also ensure that surfaces to be protected are inspected in order to evaluate extent of surface preparation for which he will be responsible. All inspections with Matla Engineering are to be arranged 24 hours in advance.

6. Accommodation for employees

The Contractor is required to make sure of his own arrangements for the accommodation of his employees.  Accommodation is normally available at the single quarters near the Power Station for single men.  The Contractor is advised to contact Eskom’s Housing Manager at the Station concerning accommodation requirements, tariffs and conditions.

7. Telephone & telecommunications

A telephone is not available on site. Should the Contractor require one, he is to make his own arrangements with the relevant authorities. Arrangements may be made with the Employers Representative to use telephones of the Station if they are available. Calls from these will be charged for at prevailing GPO rates. Should the Contractor wish to use radio communication equipment on site, he will make his own arrangements with the relevant authorities. In this case though, he is required to liase with the Head of Security at the Station to ensure that there is no interference with existing channels or equipment.

8. First aid and fire fighting

Adequate first aid and fire fighting equipment to be provided by the Contractor who also may in cases of emergencies or accidents call upon the services of the first aid and fire fighting resources at the Power Station.

9. Welding on site

No welding will be allowed on site unless permission is granted in writing by the Employers Representative.

10. Safe plant isolations

It is the Contractor’s responsibility to liaise with the Employers Representative in respect of safe plant isolations and all Eskom plant to be considered as live unit, such liaison is confirmed in writing.

11. Security, fire protection and safety

The Contractor shall be responsible for ensuring the security of the works, and of his plant, equipment and materials. To that end he shall make adequate provision for access control, lighting and watchman to the works where required.

12. Fire protection

The provision of Eskom’s standard NWS 1494 “ Fire Prevention and Protection of Contractor’s premises at New Works sites” shall be applicable. The Contractor shall ensure that adequate fire fighting apparatus is provided at all his work sites, and that his staff is trained in the use of this apparatus.

13. Safety and incident prevention

The Contractor shall implement and maintain an active Site Safety and Accident Prevention Programme in accordance with the NOSA Standards Safety Regulations, NWS 1058 and the Safety Regulations as laid down in the Matla Safety Manual. The overriding regulations will however be the Occupation Health and Safety Act.

14. Safety

The Contractor shall comply with

- The Occupational Health and Safety Act, 1993, and all regulations made there under;

- All Eskom Safety and Operating Procedures.

The Contractor acknowledges that it is fully aware of the requirements of all the above and undertakes to employ only people who have been duly authorised in terms thereof and who have received sufficient safety training to ensure that they can comply therewith.

The Contractor undertakes not to do, or not to allow anything to be done which will contravene any of the provisions of the Act, Regulations or Safety and Operating Procedures.

The Contractor shall appoint a person who will liaise with the Eskom Safety Officer responsible for the premises relevant to this contract.

Do safety audits at the Contractor’s premises, its work-places and on its employees;

Refuse any employee, sub-contractor or agent of the Contractor access to its premises if such person has been found to commit any unlawful act or any unsafe working practice or is found to be not authorised or qualifies in terms of the Act;

Issue the Contractor with a work stop order or a compliance order should Eskom become aware of any unsafe working procedures or conditions or any non-compliance with the Act, Regulations and Procedures referred to in 1 above by the Contractor or any of its employees, sub-contractors or agents.

The Contractors safety file is to be submitted for approval to Matla’s Safety Officer within three (3) days after order placement.

15. General

Contractor shall make provision in his rates for all costs involved in compliance with Security Requirements, Fire Protection, Safety and Accident Prevention. Eskom in this regard will entertain no claims for additional compensation.

16. Quality requirements

The Contractor shall be required to demonstrate by means of a Quality Plan that this organisation is so structured that all the requirements of the specification will be properly monitored and controlled.  The Quality Plan and Control procedures are to be carried out in accordance with the Quality Control document NWS 1841/C1 and the Matla Quality Manual for Contractor. The Quality Control document is to be submitted for approval to Matla Engineering within three (3) days after order placement by the Contractor.

No work may commence unless the Quality Control document has been approved in writing and a copy submitted to the Employers Representative. The Contractor, in conjunction with Matla Engineering must sign off all Quality Control documents after completing all work on site. The Contractor to submit a copy of the final signed off document to the Employers Representative within 1 week after Completion of the works.

17. Tender

Tender on the supplied Scope of Work shall be fixed and firm unless otherwise specified. The Tenderers shall include for compliance with all the provisions and requirements of site regulations and procedures in his pricing.

Any work not in the Scope of Work will be carried out only when the Contractor has received a signed variation order from Eskom.

17.1. Consumables

The Contractor shall allow in his tender price for any consumables that might be required for the execution of the work.

17.2. Transport

The Contractor shall make his own arrangements for transport of material and/or personnel on or to site in accordance with the site procedures and regulations.

The tenderer shall include in his tender price for any special tools and equipment to be used on site for the execution of the works.

Eskom carries no responsibility for unforeseen delays unless such a delay is negotiated within 24 hours of the occurrence and written agreement is submitted by Eskom.

19. Communication

The Contractor shall address all communications (after contract award) including telefaximilies to:

Project Manager

Matla Power Station

Private Bag X5012

Kriel

2271

Att		:

All communications from the Contractor shall carry the Enquiry Number or Contract Number after Contract Award, as well as the Title of the Works. All communication by the Contractors shall go through the buyer.

They shall be headed with the subject of the communications, and be numbered sequentially on the basis of the subject of the communication.

No recruiting is allowed on Eskom property. (Eskom property includes the area outside the main security gate).

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009