{"text_format":"3","workbook":"xls","n_sheets":8,"sheets":["Summary","1. P & G","2. Main Inverter","3. Main Solar","4. Main Elec Instal.","5. Coll. Inverter","6. Coll. Elec Instal.","7. General "],"not_rendered":{"external_links":1,"defined_names":9},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Summary","index":0,"n_rows":21,"n_cols":3,"rows_kept":21,"merged":[[1,0,1,1],[2,0,2,2]],"flags":["formulas_cached_only"]}
[]
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING & COLLECTIONS BUILDING"]
[]
["SUMMARY PAGE"]
[]
["ITEM No.","DESCRIPTION","   AMOUNT"]
[""]
[1,"SECTION 1: Preliminary and Generals",0]
[2,"SECTION 2: Inverter Installation Main Building",0]
[3,"SECTION 3: Solar Installation Main Building",0]
[4,"SECTION 4: Electrical Installation Main Building",0]
[5,"SECTION 5: Inverter Installation Collections Building",0]
[6,"SECTION 6: Electrical Installation Collections Building",0]
[7,"SECTION 7: General. Main and Collections Building",{"v":20000,"d":"20,000.00"}]
[]
[null,"SUBTOTAL",{"v":20000,"d":"R20,000.00"}]
[null,"Contingency (15%)",{"v":23000,"d":"R23,000.00"}]
[null,"TOTAL Excl VAT",{"v":43000,"d":"R43,000.00"}]
[null,"Add 15% VAT",{"v":6450,"d":"6,450.00"}]
[null,"TOTAL CARRIED FORWARD TO FORM OF OFFER",{"v":49450,"d":"R49,450.00"}]

{"sheet":"1. P & G","index":1,"n_rows":47,"n_cols":6,"rows_kept":47,"merged":[[0,0,0,1],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[46,0,46,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING & COLLECTIONS BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 1: Preliminary & Generals"]
[]
[1.1,"Compliance with General Conditions of Contract, Insurances, Sureties, Travelling, Accomodation, Out of Town Allowances, etc","Month",3,null,{"v":0,"d":"0.00"}]
[]
[1.2,"Establishment on site and provision of buildings and storage facilities including de-establishment of site, cleaning and tidying up in the course of the contract","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[1.3,"Full time contract management and supervision of the works including liason with other Contractors and submission of installation programme, including weekly revisions thereto from time to time or as may be required by the Engineer","Month",3,null,{"v":0,"d":"0.00"}]
[]
[1.4,"Provision of Shop Drawings and Builders Work Drawings for approval","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[1.5,"Liaison with Local Authority, compliance with O.H.S. Act, Local By-Laws and any other statutory regulations","Month",3,null,{"v":0,"d":"0.00"}]
[]
[1.6,"Liason with SAIAB and compliance with SAIAB corporate and safety regulations and any other SAIAB requirments","Month",3,null,{"v":0,"d":"0.00"}]
[]
[]
[1.7,"Security and Identification. The tenderer must price for his staff to wear distinctive overalls / work clothes, bibs and hard hats for the duration of the contract. Name tags must also be provided to all employees on site whether in work clothes or not","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[1.8,"Provide a Health and Safety Plan in accordance with the OHS Act, Construction Regulations, attand H&S meetings called by the Client, report on compliance with H&S Plan","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[1.9,"Provide for additional H&S requirments. Working at Heights Certificates, climbing gear and any additional PPE requirments deemed necessary by the contractor","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[{"v":1.1,"d":"1.10"},"Any additional items not specifically mentioned or included in the Bill of Quantities and for which the Tenderer may wish to detail","Sum",1,null,{"v":0,"d":"0.00"}]
{"$rows_empty":20}
[" TOTAL CARRIED FORWARD TO SUMMARY",{"$nulls":4},0]

{"sheet":"2. Main Inverter","index":2,"n_rows":134,"n_cols":6,"rows_kept":134,"merged":[[0,0,0,1],[1,0,1,1],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[62,0,62,4],[63,0,64,0],[63,1,64,1],[63,2,64,2],[63,3,64,3],[63,4,64,4],[63,5,64,5],[65,0,65,4],[133,0,133,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 2: Inverter Installation"]
[]
[2.1,"Inverter"]
[null,"50kW, 3 Phase, True Hybrid Bi-Directional Inverter, IP65 c/w Wifi moudule, mounting bracket & all accessories, as per Sunsynk or equal approved"]
["2.1.1","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["2.1.2","Install","No.",2,null,{"v":0,"d":"0.00"}]
[]
[2.2,"Battery"]
[null,"61kW HV (615V) LiFePO4 Battery, as per Sunsynk or equal approved"]
["2.2.1","Supply ","No.",4,null,{"v":0,"d":"0.00"}]
["2.2.2","Install","No.",4,null,{"v":0,"d":"0.00"}]
[]
[2.3,"Battery Protection & Cables"]
[null,"200A Frame Size; Fuse Switch Disconnector, 1500V"]
["2.3.1","Supply ","No.",4,null,{"v":0,"d":"0.00"}]
["2.3.2","Install","No.",4,null,{"v":0,"d":"0.00"}]
[]
[null,"DC Blade Fuse Link (NH1) - 200A, 1500V"]
["2.3.3","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["2.3.4","Install","No.",8,null,{"v":0,"d":"0.00"}]
[]
[null,"200A DC Battery Cable, 1500V"]
["2.3.5","Supply ","m",80,null,{"v":0,"d":"0.00"}]
["2.3.6","Install","m",80,null,{"v":0,"d":"0.00"}]
[]
[null,"Battery Cable Connector","No.",8,null,{"v":0,"d":"0.00"}]
["2.3.7","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["2.3.8","Install"]
[]
[null,"Battery Cable Lug","No.",8,null,{"v":0,"d":"0.00"}]
["2.3.9","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["2.3.10","Install"]
[]
[2.4,"AC Protection DB"]
["2.4.1","Supply and install AC Inverter Distribution Board as per Drawing No. E2310_NRF_202\t","No.",1,null,{"v":0,"d":"0.00"}]
[]
[2.5,"Cable Ladder"]
[null,"Supply and Install Hot dip galvanised Medium duty CABLE LADDER mounted to P2000, C/W clamps, hangers, splices, end caps and joints, as per OL "]
[null,"600mm Straight"]
["2.5.1","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["2.5.2","Install","m",20,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm 90° internal/external/rising/falling bends "]
["2.5.3","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["2.5.4","Install","No.",2,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm Tee"]
["2.5.5","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["2.5.6","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[2.6,"Wire Mesh Cable Tray"]
[null,"Hot dip galvanised  WIRE MESH CABLE TRAY mounted to P2000, including hangers clamps, hangers, splices and joints, as per OL, for Indoor DC wiring"]
[null,"100mm Straight"]
["2.6.1","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["2.6.2","Install","m",20,null,{"v":0,"d":"0.00"}]
[]
[]
[]
[" TOTAL CARRIED FORWARD TO NEXT PAGE",{"$nulls":4},0]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[" TOTAL BROUGHT FORWARD FROM PREVIOUS PAGE",{"$nulls":4},0]
[]
[null,"100mm 90° internal/external/rising/falling bends "]
["2.6.3","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["2.6.4","Install","No.",8,null,{"v":0,"d":"0.00"}]
{"$rows_empty":63}
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},0]

{"sheet":"3. Main Solar","index":3,"n_rows":190,"n_cols":6,"rows_kept":190,"merged":[[0,0,0,1],[1,0,1,1],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[67,0,67,4],[68,0,69,0],[68,1,69,1],[68,2,69,2],[68,3,69,3],[68,4,69,4],[68,5,69,5],[70,0,70,4],[130,0,130,4],[131,0,132,0],[131,1,132,1],[131,2,132,2],[131,3,132,3],[131,4,132,4],[131,5,132,5],[133,0,133,4],[189,0,189,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 3: Solar Installation"]
[null,"Supply and Install Tier 1 Solar panels on pitched mounting structures, secured to concrete ballasts"]
[]
[3.1,"Solar Panels"]
[null,"550W Tier 1 Solar Panel"]
["3.1.1","Supply ","No.",88,null,{"v":0,"d":"0.00"}]
["3.1.2","Install","No.",88,null,{"v":0,"d":"0.00"}]
[]
[3.2,"Mounting Structures"]
[null,"Supply and install pitched mounting structures to flat  roof with concrete ballast support c/w all fixings and accssessories"]
[]
[null,"Dome 6.15 SD"]
["3.2.3","Supply","No.",208,null,{"v":0,"d":"0.00"}]
["3.2.4","Install","No.",208,null,{"v":0,"d":"0.00"}]
[]
[null,"MK2"]
["3.2.5","Supply ","No.",416,null,{"v":0,"d":"0.00"}]
["3.2.6","Install","No.",416,null,{"v":0,"d":"0.00"}]
[]
[null,"Socket Head Bolt serrated M8×20"]
["3.2.7","Supply ","No.",416,null,{"v":0,"d":"0.00"}]
["3.2.8","Install","No.",416,null,{"v":0,"d":"0.00"}]
[]
[null,"Dome 6.15 Peak"]
["3.2.9","Supply ","No.",208,null,{"v":0,"d":"0.00"}]
["3.2.10","Install","No.",208,null,{"v":0,"d":"0.00"}]
[]
[null,"Dome Mat S 380"]
["3..11","Supply ","No.",416,null,{"v":0,"d":"0.00"}]
["3.2.12","Install","No.",416,null,{"v":0,"d":"0.00"}]
[]
[null,"S-Dome 6.15 Windbreaker LS"]
["3.2.13","Supply ","No.",192,null,{"v":0,"d":"0.00"}]
["3.2.14","Install","No.",192,null,{"v":0,"d":"0.00"}]
[]
[null,"Thread-forming metal screw 4,8×20"]
["3.2.15","Supply ","No.",416,null,{"v":0,"d":"0.00"}]
["3.2.16","Install","No.",416,null,{"v":0,"d":"0.00"}]
[]
[null,"K2 Basic Rail 22; 4.40m"]
["3.2.17","Supply ","No.",70,null,{"v":0,"d":"0.00"}]
["3.2.18","Install","No.",70,null,{"v":0,"d":"0.00"}]
[]
[null,"Dome Flat Connector Set"]
["3.2.19","Supply ","No.",52,null,{"v":0,"d":"0.00"}]
["3.2.20","Install","No.",52,null,{"v":0,"d":"0.00"}]
[]
[null,"Single Rail 36 RailConnector Set"]
["3.2.21","Supply ","No.",24,null,{"v":0,"d":"0.00"}]
["3.2.22","Install","No.",24,null,{"v":0,"d":"0.00"}]
[]
[null,"Single Rail Climber Set 36/50"]
["3.2.23","Supply ","No.",132,null,{"v":0,"d":"0.00"}]
["3.2.24","Install","No.",132,null,{"v":0,"d":"0.00"}]
[]
[null,"K2 Solar Cable Manager"]
["3.2.25","Supply ","No.",88,null,{"v":0,"d":"0.00"}]
["3.2.26","Install","No.",88,null,{"v":0,"d":"0.00"}]
[]
[]
[]
[]
[]
[" TOTAL CARRIED FORWARD TO NEXT PAGE",{"$nulls":4},0]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[" TOTAL BROUGHT FORWARD FROM PREVIOUS PAGE",{"$nulls":4},0]
[]
[null,"Dome Speed Spacer Large"]
["3.2.27","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["3.2.28","Install","No.",2,null,{"v":0,"d":"0.00"}]
[]
[null,"MAT-S  TOOL "]
["3.2.29","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["3.2.30","Install","No.",2,null,{"v":0,"d":"0.00"}]
[null,null,"No."]
[null,"Dome Clamp EC Set 30-50"]
["3.2.31","Supply ","No.",186,null,{"v":0,"d":"0.00"}]
["3.2.32","Install","No.",186,null,{"v":0,"d":"0.00"}]
[]
[null,"Dome Speed Porter"]
["3.2.33","Supply ","No.",176,null,{"v":0,"d":"0.00"}]
["3.2.34","Install","No.",176,null,{"v":0,"d":"0.00"}]
[]
[null,"Single Rail 36; 4.40 m"]
["3.2.35","Supply ","No.",33,null,{"v":0,"d":"0.00"}]
["3.2.36","Install","No.",33,null,{"v":0,"d":"0.00"}]
[]
[3.3,"Solar DC Cable & Connectors"]
[]
[null,"Supply and Install Solar DC cable wire to Cable Tray"]
[]
[null,"6mm² Solar DC 1000V Cable - Red"]
["3.3.1","Supply ","No.",660,null,{"v":0,"d":"0.00"}]
["3.3.2","Install","No.",660,null,{"v":0,"d":"0.00"}]
[]
[null,"6mm² Solar DC 1000V Cable - Black"]
["3.3.3","Supply ","No.",660,null,{"v":0,"d":"0.00"}]
["3.3.4","Install","No.",660,null,{"v":0,"d":"0.00"}]
[]
[null,"MC4 connectors"]
["3.3.5","Supply ","No.",22,null,{"v":0,"d":"0.00"}]
["3.3.6","Install","No.",22,null,{"v":0,"d":"0.00"}]
[]
[3.4,"Earthing of Panels"]
[null,"Earthing of all panels c/w 4mm² PVC insulated copper earth wire, lugs and copper earth spike ","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[]
[3.5,"Solar Protection"]
["3.5.1","Supply and install Weatherproof IP66 Solar DC Combiner box, c/w fuse holders, fuses, surge protection, wiring , labeling, etc.","each",1]
[]
["3.5.2","Supply and install IP54 Solar DC Combiner box, c/w fuse holders, fuses, surge protection, wiring , labeling, etc.","each",1]
[]
[3.6,"P- Channel"]
[null,"Supply and install Hot dip galvanised P- CHANNEL with cover, including propriety suspension clamps, hangers, splices, end caps and joints, as per Oline OL or similar approved. "]
[]
[null,"P9000 straight"]
["3.6.1","Supply ","m",3,null,{"v":0,"d":"0.00"}]
["3.6.2","Install","m",3,null,{"v":0,"d":"0.00"}]
{"$rows_empty":7}
[" TOTAL CARRIED FORWARD TO NEXT PAGE",{"$nulls":4},0]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[" TOTAL BROUGHT FORWARD FROM PREVIOUS PAGE",{"$nulls":4},0]
[]
[null,"P9000 DB outlet"]
["3.6.3","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.6.4","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[3.7,"Cable Tray "]
[null,"Supply and Install Hot dip galvanised perforated Hedium Duty CABLE TRAY with cover, mounted to concreate ballast or P2000, including propriety, clamps, hangers, splices, end caps and joints, as per OL PT38 for Outdoor DC Wiring"]
[]
[null,"200mm Straight"]
["3.7.1","Supply ","m",100,null,{"v":0,"d":"0.00"}]
["3.7.2","Install","m",100,null,{"v":0,"d":"0.00"}]
[]
[null,"200mm 90° internal/external/rising/falling bends "]
["3.7.3","Supply ","No.",10,null,{"v":0,"d":"0.00"}]
["3.7.4","Install","No.",10,null,{"v":0,"d":"0.00"}]
[]
[null,"200mm Tee"]
["3.7.5","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.7.6","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[3.8,"Wire Mesh Cable Tray"]
[null,"Hot dip galvanised  WIRE MESH CABLE TRAY mounted to P2000, including hangers clamps, hangers, splices and joints, as per OL, for Indoor DC wiring"]
[null,"300mm Straight"]
["3.8.1","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["3.8.2","Install","m",20,null,{"v":0,"d":"0.00"}]
[]
[null,"300mm 90° internal/external/rising/falling bends "]
["3.8.3","Supply ","No.",4,null,{"v":0,"d":"0.00"}]
["3.8.4","Install","No.",4,null,{"v":0,"d":"0.00"}]
[]
[null,"300mm Tee"]
["3.8.5","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.8.6","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[3.9,"Cable Ladder"]
[null,"Supply and Install Hot dip galvanised Heavy Duty CABLE LADDER with cover, including clamps, hangers, splices, end caps and joints, as per OL for bridge between Equipment Room and Main Building"]
[null,"600mm Straight"]
["3.9.1","Supply ","m",5,null,{"v":0,"d":"0.00"}]
["3.9.2","Install","m",5,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm 90° internal/external/rising/falling bends "]
["3.9.3","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.9.4","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm Tee"]
["3.9.5","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.9.6","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[null,"Vertical Support for 600mm cable ladder"]
["3.9.7","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["3.9.8","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[]
[]
[]
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},0]

{"sheet":"4. Main Elec Instal.","index":4,"n_rows":57,"n_cols":6,"rows_kept":57,"merged":[[0,0,0,1],[1,0,1,1],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[56,0,56,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 4: Electrical Installation"]
[]
[4.1,"Cables"]
[null,"Supply and Installation of Multicore PVC SWA ECC cable with stranded copper conductors to SANS 1507 drawn into cable sleeves, installed on cable trays/ladders or in sleeves and ducts"]
[]
[null,"70mm² 4 Core PVC SWA ECC for Normal feed to Inverter & Essential feed form Inverter to MLVP + Generator feed to Inverter"]
["4.1.1","Supply ","m",90,null,{"v":0,"d":"0.00"}]
["4.1.2","Install","m",90,null,{"v":0,"d":"0.00"}]
["4.1.3","Terminations","No.",4,null,{"v":0,"d":"0.00"}]
[]
[null,"25mm² 4 Core PVC SWA ECC cable for Normal feed to Inverters No. One (1) & (2) from Inverter AC DB"]
["4.1.4","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["4.1.5","Install","m",20,null,{"v":0,"d":"0.00"}]
["4.1.6","Terminations","No.",4,null,{"v":0,"d":"0.00"}]
[]
[4.2,"Circuit Breaker"]
[null,"Supply and Installation of Moulded Case Circuit breaker (MCCB) in MLVP for Normal feed to Inverter DB"]
["4.2.1","200A, 10kA, MCCB installed in existing Main DB, C/W bridging conductors ","No.",1,null,{"v":0,"d":"0.00"}]
[]
[4.3,"Existing MLVP"]
["4.3.1","Allowance for modification of MLVP to accommodate item 4.2.1 above, C/W colour coding, voltage indicators, safety/warning labels, as per SANS 10141-2 ","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[4.4,"Cable Labels"]
["4.4.1","Labelling of all cables on both ends with numbering beads or non-corroding straps to indicate their connection points","Sum",1,null,{"v":0,"d":"0.00"}]
{"$rows_empty":28}
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},0]

{"sheet":"5. Coll. Inverter","index":5,"n_rows":133,"n_cols":6,"rows_kept":133,"merged":[[0,0,0,1],[1,0,1,1],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[62,0,62,4],[63,0,64,0],[63,1,64,1],[63,2,64,2],[63,3,64,3],[63,4,64,4],[63,5,64,5],[65,0,65,4],[132,0,132,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - COLLECTIONS BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 5: Inverter Installation"]
[]
[5.1,"Inverter"]
[null,"50kW, 3 Phase, True Hybrid Bi-Directional Inverter, IP65 c/w Wifi moudule, mounting bracket & all accessories, as per Sunsynk or equal approved"]
["5.1.1","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["5.1.2","Install","No.",2,null,{"v":0,"d":"0.00"}]
[]
[5.2,"Battery"]
[null,"61kW HV (615V) LiFePO4 Battery, as per Sunsynk or equal approved"]
["5.2.1","Supply ","No.",4,null,{"v":0,"d":"0.00"}]
["5.2.2","Install","No.",4,null,{"v":0,"d":"0.00"}]
[]
[5.3,"Battery Protection & Cables"]
[null,"200A Frame Size; Fuse Switch Disconnector, 1500V"]
["5.3.1","Supply ","No.",4,null,{"v":0,"d":"0.00"}]
["5.3.2","Install","No.",4,null,{"v":0,"d":"0.00"}]
[]
[null,"DC Blade Fuse Link (NH1) - 200A, 1500V"]
["5.3.3","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["5.3.4","Install","No.",8,null,{"v":0,"d":"0.00"}]
[]
[null,"200A DC Battery Cable, 1500V"]
["5.3.5","Supply ","m",80,null,{"v":0,"d":"0.00"}]
["5.3.6","Install","m",80,null,{"v":0,"d":"0.00"}]
[]
[null,"Battery Cable Connector","No.",8,null,{"v":0,"d":"0.00"}]
["5.3.7","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["5.3.8","Install"]
[]
[null,"Battery Cable Lug","No.",8,null,{"v":0,"d":"0.00"}]
["5.3.9","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["5.3.10","Install"]
[]
[5.4,"AC Protection DB"]
["5.4.1","Supply and install AC Inverter Distribution Board as per Drawing No. E2310_NRF_202\t","No.",1,null,{"v":0,"d":"0.00"}]
[]
[5.5,"Cable Ladder"]
[null,"Supply and Install Hot dip galvanised Medium duty CABLE LADDER mounted to P2000, C/W clamps, hangers, splices, end caps and joints, as per OL "]
[null,"600mm Straight"]
["5.5.1","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["5.5.2","Install","m",20,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm 90° internal/external/rising/falling bends "]
["5.5.3","Supply ","No.",2,null,{"v":0,"d":"0.00"}]
["5.5.4","Install","No.",2,null,{"v":0,"d":"0.00"}]
[]
[null,"600mm Tee"]
["5.5.5","Supply ","No.",1,null,{"v":0,"d":"0.00"}]
["5.5.6","Install","No.",1,null,{"v":0,"d":"0.00"}]
[]
[5.6,"Wire Mesh Cable Tray"]
[null,"Hot dip galvanised  WIRE MESH CABLE TRAY mounted to P2000, including hangers clamps, hangers, splices and joints, as per OL, for Indoor DC wiring"]
[null,"100mm Straight"]
["5.6.1","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["5.6.2","Install","m",20,null,{"v":0,"d":"0.00"}]
[]
[]
[]
[" TOTAL CARRIED FORWARD TO NEXT PAGE",{"$nulls":4},0]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[" TOTAL BROUGHT FORWARD FROM PREVIOUS PAGE",{"$nulls":4},0]
[]
[null,"100mm 90° internal/external/rising/falling bends "]
["5.6.3","Supply ","No.",8,null,{"v":0,"d":"0.00"}]
["5.6.4","Install","No.",8,null,{"v":0,"d":"0.00"}]
{"$rows_empty":62}
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},0]

{"sheet":"6. Coll. Elec Instal.","index":6,"n_rows":57,"n_cols":6,"rows_kept":57,"merged":[[0,0,0,1],[1,0,1,1],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[56,0,56,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - COLLECTIONS BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
[null,"SECTION 6: Electrical Installation"]
[]
[6.1,"Cables"]
[null,"Supply and Installation of Multicore PVC SWA ECC cable with stranded copper conductors to SANS 1507 drawn into cable sleeves, installed on cable trays/ladders or in sleeves and ducts"]
[]
[null,"70mm² 4 Core PVC SWA ECC for Normal feed to Inverter & Essential feed form Inverter to MLVP + Generator feed to Inverter"]
["6.1.1","Supply ","m",90,null,{"v":0,"d":"0.00"}]
["6.1.2","Install","m",90,null,{"v":0,"d":"0.00"}]
["6.1.3","Terminations","No.",4,null,{"v":0,"d":"0.00"}]
[]
[null,"25mm² 4 Core PVC SWA ECC cable for Normal feed to Inverters No. One (1) & (2) from Inverter AC DB"]
["6.1.4","Supply ","m",20,null,{"v":0,"d":"0.00"}]
["6.1.5","Install","m",20,null,{"v":0,"d":"0.00"}]
["6.1.6","Terminations","No.",4,null,{"v":0,"d":"0.00"}]
[]
[6.2,"Circuit Breaker"]
[null,"Supply and Installation of Moulded Case Circuit breaker (MCCB) in MLVP for Normal feed to Inverter DB"]
["6.2.1","200A, 10kA, MCCB installed in existing Main DB, C/W bridging conductors ","No.",1,null,{"v":0,"d":"0.00"}]
[]
[6.3,"Existing MLVP"]
["6.3.1","Allowance for modification of MLVP to accommodate item 4.2.1 above, C/W colour coding, voltage indicators, safety/warning labels, as per SANS 10141-2 ","Sum",1,null,{"v":0,"d":"0.00"}]
[]
[6.4,"Cable Labels"]
["6.4.1","Labelling of all cables on both ends with numbering beads or non-corroding straps to indicate their connection points","Sum",1,null,{"v":0,"d":"0.00"}]
{"$rows_empty":28}
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},0]

{"sheet":"7. General ","index":7,"n_rows":58,"n_cols":6,"rows_kept":58,"merged":[[0,0,0,1],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[57,0,57,4]],"flags":["formulas_cached_only"]}
["NRF SAIAB MAKANDA"]
["HYBRID PV INSTALLATION - MAIN BUILDING & COLLECTIONS BUILDING"]
["ITEM","DESCRIPTION","UNIT","QTY","RATE","TOTAL"]
[]
["7.1","General"]
["7.1.1","Housekeeping, sundry items, consumable stocks such as circuit beads engraving, labels etc.","Sum",1,null,{"v":0,"d":"0.00"}]
[]
["7.1.2","Provide for the earthing of the installation in accordance with wiring code, including cable trays, ladders and wire baskets, etc.","Sum",1,null,{"v":0,"d":"0.00"}]
[]
["7.1.3","Testing of complete installation in terms of the regulations - SANS 10142-1","Sum",1,null,{"v":0,"d":"0.00"}]
[]
["7.1.4","Provision for Operating and Maintenance manuals, as per the specification ","Sum",1,null,{"v":0,"d":"0.00"}]
[]
["7.1.5","Provision for Maintence. Two site visits per year to inspect, clean, test & optomize the two (2) off  installations on behalf of the Employer during the Thirty Six (36) Months Maintenance Period from the date of Final Completion of the entire works, as specified in Annexure 9","Sum",1,null,{"v":0,"d":"0.00"}]
[]
["7.1.6","Training of Client's representative (s) at \"practical completion,\" equivalent to four (4) hours","Hrs",4,null,{"v":0,"d":"0.00"}]
[]
["7.1.7","Provision for issuing of Certificate of Compliance","Sum",2,null,{"v":0,"d":"0.00"}]
[]
["7.2","Provisional Sum"]
["7.2.1","Provisional amount of R 20 000-00 for additional data sampling and monitoring of Two (2) systems","Sum",1,null,{"v":20000,"d":"20,000.00"}]
{"$rows_empty":36}
[" TOTAL CARRIED FORWARD TO SUMMARY PAGE",{"$nulls":4},{"v":20000,"d":"20,000.00"}]