Eskom Holdings SOC Ltd

Contract No. _________
For the Structural Assessment Studies and Mechanical Designs of the Ash Plant Machines OF Kendal Power Station.

Part 2: Pricing Data

PSC3 Option A
	Document reference
	Title
	No of pages

	C2.1
	Pricing assumptions: Option A
	[●]

	C2.2
	The activity schedule
	[●]


C2.1 Pricing assumptions: Option A
1. How work is priced and assessed for payment
Option A is a lump sum form of contract where the work to be done is broken down into well defined activities each listed in the activity schedule and priced by the tendering consultant as a lump sum. (See clause 11.2(18)).  
Only completed activities which are without Defects are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date. (See clause 11.2(15)).
The activity schedule may change after the Contract Date as a result of compensation events. (See clause 11.2(14)).

2. Function of the Activity Schedule
The Activity Schedule is only a pricing document. Clause 53.1 in Option A states: “Information in the Activity Schedule is not Scope”.  Specifications and descriptions of the service or any constraints on how it is to be done are included in the Scope and per Clause 21.1, “The Consultant Provides the Services in accordance with the Scope” and therefore not in accordance with the Activity Schedule.  
3. Link to the programme

Clause 31.4 states that “The Consultant provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering consultant will develop a high level programme first then resource each activity on the programme and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.
4. Preparing the activity schedule
Generally it is the tendering consultant who prepares the activity schedule by breaking down the work described within the Scope into suitable activities which can be well defined, shown on a programme and priced as a lump sum.  
The description of each activity must be sufficient to determine exactly what work is included within it and to know when it has been completed. 
The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Consultant to include in his activity schedule and be priced accordingly. 

It is assumed that in preparing his activity schedule the Consultant:
· Has taken account of the guidance given in the PSC3 Guidance Notes;

· Understands the function of the Activity Schedule and how work is priced and paid for;

· Is aware of the need to link the Activity Schedule to activities shown on each programme which he submits for acceptance by the Employer;

· Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Scope, as it was at the Contract Date, as well as correct Defects except correcting a Defect for which the Consultant is not liable;
· Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the service for the tendered total of the Prices. 
· Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Consultant estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event. 
However, the Consultant does not have to allow in his Prices for matters that may arise as a result of a compensation event. 
5. Expenses

Expenses are not included in the activity schedule items and are assessed separately at each assessment date, unless an additional condition of contract (Z clause) is included which requires that expenses be included within activity Prices and not paid separately.
Expenses associated with employing a staff member in Providing the Services are listed separately either by the Employer in Contract Data provided by the Employer or by the Consultant in Contract Data provided by the Consultant.  As only the expenses listed may be claimed by the Consultant, all other cost to the Consultant associated with Providing the Services must be included within the activity schedule prices or staff rates.

Rate adjustment for inflation of expenses is explained in the PSC3 Guidance Notes.

6. Staff rates

When a compensation event occurs changes to the affected Activity Schedule item or new priced items in the Activity Schedule are assessed as the actual Time Charge for work already done and the forecast Time Charge for work not yet done.  (See clause 63.1 and 63.14 in Option A)
The Time Charge is the sum of the products of each of the staff rates multiplied by the total staff time appropriate to that rate properly spent on work in this contract.  (Clause 11.2(13))
Tendering consultants are advised to consult the NEC3 Professional Services Contract Guidance Notes and Flow Charts before entering staff rates into Contract Data, or in C2.2 below.  

This is because staff rates can be established in one of three ways:

· rates for named staff,

· rates for categories of staff or

· rates related to salaries paid to staff.

Rate adjustment for inflation, if necessary, can be based either on actual salary adjustments or by using Option X1: Price adjustment for inflation.  See pages 13 and 14 in the PSC3 Guidance Notes.

C2.2 the activity schedule
Use this page as a cover page to the Consultant’s activity schedule or include here in this format:
	Item
No 
	Description 
	Unit
	Est. Qty
	Rate Each


	Total Price


	1
	Visual Inspection and Report Acceptance
	LE
	1
	
	

	2
	Structural Assessment and Report Acceptance
	LE
	1
	
	

	3
	Conceptual Designs and Approvals of Mechanical scope
	LE
	1
	
	

	4
	Conceptual Designs and Approvals of Chutes
	LE
	1
	
	

	5
	Detail Designs and Approvals of Mechanical scope
	LE
	1
	
	

	6
	Detail Designs and Approvals of Chutes 
	LE
	1
	
	

	7
	Configuration Management and submission of final drawings 
	LE
	1
	
	

	
	
	
	
	
	

	Total Price Excluding VAT
	


Note: 

The above mentioned tendered prices are exclusive of Value Added Tax (VAT) and CPA, but inclusive of all costs related to this works.
	Contractor:
........................................................
PRINT NAME AND SURNAME
	..............................................................
SIGNATURE
	..................................................
DATE


Price List

HEALTH AND SAFETY
	Item
	Description
	Qty
	Price ea/

person
	Total price

	1
	Medicals (only if annual medical certificate expired)
	
	
	

	2
	Health and Safety File
	1
	
	

	3
	Safety Training employees
	
	
	

	4
	Health and Safety Officer (if >40 employees)
	
	
	

	5
	Hard hats with strips (Hooked on the hats itself not inside)
	
	
	

	6
	Overalls
	
	
	

	7
	Gloves
	
	
	

	8
	Shoes (Safety boots)
	
	
	

	9
	Hearing protection
	
	
	

	10
	Safety goggles
	
	
	

	11
	Safety harnesses (with big hooks not small hooks)
	
	
	

	12
	First Aid box for every 50 employees
	
	
	

	13
	Dust musk
	
	
	

	14
	Site Establishment
	
	
	

	15
	Site De-establishment
	
	
	

	16
	Thermal Suit 
	
	
	

	17
	Special underwear – only cotton 
	
	
	

	18
	Flash Suit 
	
	
	

	*19
	Training: Appointed Operator - ORHVS (8 days)
	N/A
	Offer by Eskom
	N/A

	*20
	Training: Appointed Person - PSR (10 days)
	N/A
	Offer by Eskom
	N/A

	*21
	Training: Responsible Person - ORHVS & PSR (18 days)
	N/A
	Offer by Eskom
	N/A

	*22
	Training: Authorised Supervisor - PSR (2.5 days)
	N/A
	Offer by Eskom
	N/A

	TOTAL VALUE FOR HEALTH AND SAFETY FOR THE WHOLE CONTRACT PERIOD
	


The above prices excludes VAT

* Training: 1) Includes Manual, Assessment Documents, Theoretical Training, Practical Training & Panel Test.



     2) Receipt must be provided to the Instructor as proof of payment before training will commence. 

     3) Payments to be made to the Finance Department, Kendal Power Station. GL Account 750400 / 



    CC 311407

It is compulsory for the Contractor to visit Kendal Safety Department after contract award and before any work may commence to:

1)
be appointed in writing, and

2)
sign an Agreement according to Section 37(2) of the Occupational Health and Safety Act No 85

Suppliers are not, under any circumstances, to deviate from the required stipulated format for the provision of pricing.

	Contractor:

___________________________

PRINT NAME AND SURNAME
	____________________________

SIGNATURE
	____________________

DATE


ESKOM 

KENDAL POWER STATION

RATE SCHEDULE FOR ANY COMPENSATION EVENT CALCULATIONS

Price List

Rates Schedule to apply on an “as and when required basis” for any maintenance work outside the scope of this contract and for any compensation event calculations.

	Item
	Description
	Base Rate per Hour

Normal Time

(Excl. Profit & Overheads)
	Rate per hour Normal time

(Base rate Incl. Profit & Overheads)
	Rate per hour Overtime &

Saturday

(Base rate times 1.5%)
	Rate per hour

Sundays & Public Holidays

(Base rate times 2)

	1
	Project Administrator 
	
	
	
	

	2
	Mechanical Engineer
	
	
	
	

	3
	Civil Engineer
	
	
	
	

	4
	Geotechnical Engineer
	
	
	
	

	5
	Structural Engineer
	
	
	
	

	6
	Safety Officer 
	
	
	
	

	7
	Project Manager
	
	
	
	

	8
	Project Planner
	
	
	
	


Note: 

The above-mentioned tendered prices are exclusive of Value Added Tax (VAT) and CPA, but inclusive of all costs related to this works.

	Contractor:
........................................................
PRINT NAME AND SURNAME
	..............................................................
SIGNATURE
	..................................................
DATE


This section can be used when the staff rates and expenses are considerable in number and more conveniently located here than in the Contract Data.  Entries in the Contract Data should refer to this section of Part 2.

Remember to state whether the staff rates and expenses exclude or include VAT. 


DOCUMENT C2.1
PAGE 2
PRICING DATA




Part C2: Pricing Data
PAGE 1
C2 PSc3/a Cover

