{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["KZN"],"not_rendered":{"images":1},"read":"whole","date_system":"1900"}

{"sheet":"KZN","index":0,"n_rows":37,"n_cols":16,"rows_kept":37,"merged":[[0,0,1,1],[5,3,6,3],[5,4,6,4],[5,5,6,5]]}
["Annexure A: Bills of Quantities for the Rollout of Mobile Ramps on Ten (10) Stations in KwaZulu Natal"]
[]
[]
[]
[]
[{"$nulls":3},"UNITS","QUANTITY","RATE","Durban","Umlazi","Zwelethu","Lindokuhle","Moses Mabhida","Umgeni","Temple","Kenville","Effingham","Tembalihle"]
["ACTIVITY NUMBER","TASK/ACTIVITY","PERCENTAGE CLAIMABLE AT END OF MILESTONE DELIVERY  \n\na. Delivery milestones for Mobile Ramps will be undertaken as per activities 1 to 5. \n\nb. Payment will be effected on successfully completed milestones below. \n\n"]
[]
[1,"CONCEPT STAGE \n\ni. Submission of concept to RSR for Approval\nii. Receive Approval from RSR \n\n\n",{"v":0.2,"d":"20%"},"No.",1]
[]
[2,"DESIGN STAGE\n\ni. Presentation of Designs to RSR and Approval thereof, including signing off by competent personnel at PRASA\n\n\n",{"v":0.15,"d":"15%"},"No.",1]
[]
[3," INSTALLATION \n\ni. Installation of RSR approved mobile ramps\n",{"v":0.4,"d":"40%"},"No.",1]
[]
[4,"TESTING AND COMMISSIONING\n\ni. Testing Certificates issuance\nii. Training of PRASA personnel  \n",{"v":0.15,"d":"15%"},"No.",1]
[]
[5,"OPERATION, MONITORING AND MAINTENACE\n\ni. Handover of Mobile Ramps\nii. Close Out Reports, Handover Certificates, and presentation of As Built Drawings ",{"v":0.1,"d":"10%"},"No.",1]
[]
[6,"PROVISION OF SECURITY SERVICES\n\nProvision of PSIRA accredited security at each station for the duration of the mobile ramp installation until handover to PRASA",null,"No.",1]
[" "]
[7,"DISBURSEMENTS\n\nDisbursements to cover for all travel to sites, meetings and applications for approvals as well as project documentation (reports).",null,"No.",1]
[]
[8,"SUB-TOTAL A (Excl VAT)"]
[]
[9,"Add contigencies at 10% of total Excl. VAT\n\nContigencies will be used upon approval from PRASA, may the need arise. "]
[]
[10,"SUB-TOTAL B (ITEM 8 + ITEM 9 ABOVE)"]
[]
[11,"VAT @ 15% ON ITEM 10 ABOVE"]
[]
[12,"GRAND TOTAL (ITEM 10 + ITEM 11)"]
[]
[]
[null,"Notes:"]
[null," 1. The amount to be reflected on the invoice must be based on actual work done, and portifolio of evidence must be submitted to PRASA Project Manager."]
[null,"2. Payments will be made per milestone."]
[null,"3. Refer to Annexure 1 for details of all the activities to be carried out under each life cycle phase. "]