Eskom Holdings SOC Ltd

Contract No. _________

project or contract title




	[image: image1.jpg]R Eskom






NEC3 Term Service Contract (TSC3)
	Between


	ESKOM HOLDINGS SOC Ltd 

(Reg No. 2002/015527/30)

	and


	[Insert at award stage]

(Reg No. ___________ )

	for


	Provision of MPS265 Mill Major

Overhaul for 30 Mills or 36 Months
Insert title of the service

	
	

	Contents:


	
	No of pages

	Part C1
	Agreements & Contract Data
	[●]

	Part C2
	Pricing Data
	[●]

	Part C3
	Scope of Work
	[●]

	
	
	

	CONTRACT No.
	[Insert at award stage]

	
	

	
	

	
	


PART C1:
AGREEMENTS & CONTRACT DATA

	Contents:


	
	No of pages

	C1.1
	Form of Offer and Acceptance 
	[●]

	C1.2a
	Contract Data provided by the Employer
	[●]

	C1.2b
	Contract Data provided by the Contractor
	[●]

	C1.3
	Proforma Guarantees
	[●]


C1.1 Form of Offer & Acceptance

Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Provision of MPS265 Mill Major Overhaul for 30 Mills or 36 Months

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data. 

Delete the row for the Options which do not apply

	Options A 
	The offered total of the Prices exclusive of VAT is 
	R [●]

	
	Value Added Tax @ 15% is
	R [●]

	
	The offered total of the amount due inclusive of VAT is

	R [●]

	
	(in words) [●]



This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

	Signature(s)


	
	
	

	Name(s)


	
	
	

	Capacity


	
	
	

	For the tenderer:

	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	

	Tenderer’s CIDB registration number: 
	


Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in: 

Part C1

Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2

Pricing Data

Part C3

Scope of Work: Service Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed and signed original copy of this document, including the Schedule of Deviations (if any).  

	Signature(s)


	
	
	

	Name(s)
	
	
	

	Capacity


	
	
	

	for the Employer


	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	


Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

Schedule of Deviations to be completed by the Employer prior to contract award

Note:

1.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.
2. The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

3. A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

	No.
	Subject
	Details

	1
	[●]
	[●]

	2
	[●]
	[●]

	3
	[●]
	[●]

	4
	[●]
	[●]

	5
	[●]
	[●]

	6
	[●]
	[●]

	7
	[●]
	[●]

	
	
	


By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.  

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement. 

	
	For the tenderer:


	
	For the Employer



	Signature


	
	
	

	Name
	
	
	

	Capacity


	
	
	

	On behalf of
	(Insert name and address of organisation)


	
	(Insert name and address of organisation)



	Name & signature of witness
	
	
	

	Date
	
	
	


C1.2 TSC3 Contract Data

Part one - Data provided by the Employer
	Clause
	Statement
	Data

	1
	General
	

	
	The conditions of contract are the core clauses and the clauses for main Option: 
	

	
	
	A:

Priced contract with price list

	
	dispute resolution Option
	W1:
Dispute resolution procedure

	
	and secondary Options
	

	
	
	X1:

Price adjustment for inflation

	
	
	X2

Changes in the law

	
	
	X3:

Multiple currencies

	
	
	X4:

Parent company guarantee

	
	
	X17:
Low service damages

	
	
	X18:
Limitation of liability

	
	
	X19:
Task Order

	
	
	Z:

Additional conditions of contract

	
	of the NEC3 Term Service Contract April 2013
 (TSC3)
	If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data

	10.1
	The Employer is (name):
	Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state-owned company incorporated in terms of the company laws of the Republic of South Africa

	
	Address
	Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg

	10.1
	The Service Manager is (name): 
	[●]

	
	Address
	Medupi Power Station

Steenbokpan Road

Lephalale 0555

	
	Tel
	[●]

	
	e-mail
	[●]

	11.2(2)
	The Affected Property is
	Medupi Power Station (Unit one to six)

	11.2(13)
	The service is 
	MPS265 MILL MAJOR OVERHAULS

	11.2(14)
	The following matters will be included in the Risk Register
	· As identified by the parties from time to time and recorded on the risk register. The risk will then be discussed in the contract risk meeting
· Requirements for Employment of local workforce 

· Localisation requirements for use of local transport

	11.2(15)
	The Service Information is in 
	Part 3: Scope of Work and all documents and drawings to which it makes reference.

	12.2
	The law of the contract is the law of 
	the Republic of South Africa

	13.1
	The language of this contract is 
	English

	13.3
	The period for reply is
	5 working days

	2
	The Contractor’s main responsibilities
	Data required by this section of the core clauses is also provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data

	21.1
	The Contractor submits a first plan for acceptance within
	One week after issuing Task Order or any other period agreed by Parties

	3
	Time
	

	30.1
	The starting date is.
	TBC

	30.1
	The service period is
	36 months or 30 Mills

	4
	Testing and defects
	As per NEC3 TSC Core clause 4

	5
	Payment
	

	50.1
	The assessment interval is 
	between the 25th day of each successive month.

	51.1
	The currency of this contract is the 
	South African Rand

	51.2
	The period within which payments are made is
	60 calendar days after receipt of valid tax invoice weeks.

	51.4
	The interest rate is 


	the publicly quoted prime rate of interest (calculated on a 365-day year) charged by from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands.

	6
	Compensation events
	As per NEC3 TSC Core clause 6

	7
	Use of Equipment Plant and Materials
	As per NEC3 TSC Core clause 7

	8
	Risks and insurance
	

	80.1
	These are additional Employer's risks  
	Only the risks listed under sub-clause 80.1 of the NEC3 TSC

	
	
	

	9
	Termination
	As per NEC3 TSC Core clause 9

	10
	Data for main Option clause
	

	A
	Priced contract with price list
	

	20.5
	The Contractor prepares forecasts of the final total of the Prices for the whole of the service at intervals no longer than 
	4 weeks.

	11
	Data for Option W1
	

	W1.1
	The Adjudicator 
	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him.  (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA).

	
	Address
	1st Floor, Maisels Chamber, 4 Protea Place, Sandton

	
	Tel No.
	011 320 0600

	
	Fax No.
	011 320 0533

	
	e-mail
	info@arbitration.co.za

	W1.2(3)
	The Adjudicator nominating body is: 
	the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the Institution of Civil Engineers (London) (see www.ice-sa.org.za ) or its successor body.

	W1.4(2)
	The tribunal is: 
	arbitration

	W1.4(5)
	The arbitration procedure is 
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	
	The place where arbitration is to be held is
	Republic of South Africa

	
	The person or organisation who will choose an arbitrator 

· if the Parties cannot agree a choice or
· if the arbitration procedure does not state who selects an arbitrator, is
	the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.

	12
	Data for secondary Option clauses
	

	X1
	Price adjustment for inflation
	

	X1.1
	The base date for indices is 
	the month before the month in which the enquiry closed. CPA does not apply for the first twelve (12) months of the contract period. CPA will apply from month 13 of the contract.



	
	The proportions used to calculate the Price Adjustment Factor are:
	proportion
	linked to index for
	Index prepared by

	
	
	0.
	[●]
	[●]

	
	
	0.
	[●]
	[●]

	
	
	0.
	[●]
	[●]

	
	
	0.
	[●]
	[●]

	
	
	0.
	[●]
	[●]

	
	
	0.15
	non-adjustable
	

	
	
	1.00


	
	

	X2
	Changes in the law
	As per Secondary Option X2 of the NEC3 TSC.

	X3
	Multiple currencies
	

	X3.1


	The Employer will pay for these items or activities in the currencies stated
	Items & activities
	Other currency
	Maximum payment in other currency

	
	
	[●]
	     
	     

	
	
	[●]
	     
	     

	
	
	[●]
	     
	     

	
	
	[●]
	     
	     

	X3.1
	The exchange rates are those published in
	[●] on [●] (date)

	
	
	The items & activities will be paid in the other currency 
- to a foreign Bank account nominated by the Contractor 

- to a valid SARB approved CFC account in South Africa

- in accordance with an alternative payment method agreed with the Employer before the Contract Date.

(select one of the three methods as agreed with the successful tenderer prior to contract award and delete the others and this note)

	X4
	Parent company guarantee
	As per Secondary Option X4 of the NEC3 TSC.

	X17
	Low service damages
	

	X17.1
	The service level table is in
	

	
	Item
	Description of Non-compliance to Employer`s Requirement
	Damages Payable by Contractor

	X17.1.1
	PSR authorization within 3 months of the contract award
	Unavailability of Responsible Person (RP) beyond 7 days of being notified of non-compliance. 
	5% of monthly fixed cost of RP provided by the Employer per day

	X17.1.2
	PSR authorization within 3 months of the contract award
	Unavailability of Responsible Person (RP) beyond 60 days of being notified of non-compliance
	10% of monthly fixed cost of RP provided by the Employer per day

	X17.1.3
	Response time for urgent breakdowns on a Mill Returning from Rebuild with 72 Hrs
	Unavailability of crew beyond 1 hour of being notified of urgent breakdowns during office hours
	5% of monthly fixed cost per incident/ call-out.

	X17.1.4
	Response time for weekend standby
	Unavailability of crew beyond 45 minutes of being notified to report to the control room.
	1% of monthly fixed cost per incident/ call-out.

	X17.1.5
	Defect Remedial work 
	The Contractor shall be responsible and held liable for any defects arising from maintenance and or operational faults 24 hours after an intervention, provided that the equipment has been placed into service.
	Make good. Premature failures and remedial work will be done at the Contactor`s cost. 

NCR process shall be instituted.

	X17.1.6
	Complete Mill Major Overhaul Repairs including RCF (Raw Coal Feeder) works within 25 calendar days from permit acceptance date.
	Execute all Rebuild/Overhaul works in the set time frames
	5% of the Task Order value for any delays beyond 25 days which are in the Contractor Control 

	X17.1.7
	Poor Mill Performance after Rebuild/Overhaul
	Improve QC process to ensure Mill performs reliably after Overhaul without any rebuild/overhaul related breakdowns until the first 1000 hrs Service 
	2% of the Task Order value for any delays beyond 25 days which are in the Contractor Control

	X18
	Limitation of liability
	

	X18.1
	The Contractor’s liability to the Employer for indirect or consequential loss is limited to
	R0.0 (zero Rand)

	X18.2
	For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to
	the amount of the deductibles relevant to the event 

	X18.3
	The Contractor’s liability for Defects due to his design of an item of Equipment is limited to
	The greater of 

· the total of the Prices at the Contract Date

and 

· the amounts excluded and unrecoverable from the Employer’s insurance (other than the resulting physical damage to the Employer’s property which is not excluded) plus the applicable deductibles

	X18.4
	The Contractor’s total liability to the Employer, for all matters arising under or in connection with this contract, other than the excluded matters, is limited to
	the total of the Prices other than for the additional excluded matters.
The Contractor’s total liability for the additional excluded matters is not limited. 

The additional excluded matters are amounts for which the Contractor is liable under this contract for
· Defects due to his design, plan and specification,
· Defects due to manufacture and fabrication outside the Affected Property, 

· loss of or damage to property (other than the Employer’s property, Plant and Materials),

· death of or injury to a person and
· infringement of an intellectual property right.

	X18.5
	The end of liability date is 
	12 months after the end of the service period.

	X19
	Task Order
	

	X19.5
	The Contractor submits a Task Order programme to the Service Manager within 
	5 days of receiving the Task Order

	Z
	The additional conditions of contract are
	Z1 to Z14 always apply.

	
	

	Z1
	Cession delegation and assignment

	Z1.1
	The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer.

	Z1.2
	Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. 

	
	

	Z2
	Joint ventures

	Z2.1
	If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract.

	Z2.2
	Unless already notified to the Employer, the persons or organisations notify the Service Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf.

	Z2.3
	The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing.

	
	

	Z3
	Change of Broad Based Black Economic Empowerment (B-BBEE) status

	Z3.1
	Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change.

	Z3.2
	The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Service Manager within thirty days of the notification or as otherwise instructed by the Service Manager.

	Z3.3
	Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Service.

	Z3.4
	Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P4 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93.

	
	

	Z4
	Confidentiality

	Z4.1
	The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time).  Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient.

	Z4.2
	If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Service Manager.

	Z4.3
	In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure.  In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed.

	Z4.4
	The taking of images (whether photographs, video footage or otherwise) of the Affected Property or any portion thereof, in the course of Providing the Service and after the end of the service period, requires the prior written consent of the Service Manager.  All rights in and to all such images vests exclusively in the Employer.  

	Z4.5
	The Contractor ensures that all his subcontractors abide by the undertakings in this clause.

	
	

	Z5
	Waiver and estoppel: Add to core clause 12.3:

	Z5.1
	Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Service Manager or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing.

	
	

	Z6
	Health, safety and the environment:  Add to core clause 27.4

	Z6.1
	The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the service. Without limitation the Contractor:

· accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Affected Property;

· warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of the service; and

· undertakes, in and about the execution of the service, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	Z6.2
	The Contractor, in and about the execution of the service, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	
	

	Z7
	Provision of a Tax Invoice and interest.  Add to core clause 51

	Z7.1
	Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Service Information, showing the amount due for payment equal to that stated in the payment certificate.

	Z7.2
	If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice.  Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made.

	Z7.3
	The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment.

	
	

	Z8
	Notifying compensation events

	Z8.1
	Delete the last paragraph of core clause 61.3 and replace with:

If the Contractor does not notify a compensation event within eight weeks of becoming aware of the event, he is not entitled to a change in the Prices.

	
	

	Z9
	Employer’s limitation of liability

	Z9.1
	The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand)

	Z9.2
	The Contractor’s entitlement under the indemnity in 82.1 is provided for in 60.1(12) and the Employer’s liability under the indemnity is limited to compensation as provided for in core clause 63 and X19.11 if Option X19 Task Order applies to this contract. 

	
	

	Z10
	Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it":  

	Z10.1
	   or had a business rescue order granted against it.

	
	

	Z11
	Ethics

	For the purposes of this Z-clause, the following definitions apply:

	Affected Party
	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

	Coercive Action
	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

	Collusive Action
	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

	Committing Party
	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees,

	Corrupt Action
	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

	Fraudulent Action
	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

	Obstructive Action
	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and

	Prohibited Action
	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

	Z11.1
	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

	Z11.2
	The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason.

	Z11.3
	If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

	Z11.4
	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.


Z12

Insurance
Z _12_.1
Replace core clause 83 with the following:
	Insurance cover
	83
	

	
	83.1
	When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force.



	
	83.2
	The Contractor provides the insurances stated in the Insurance Table A from the starting date until the earlier of Completion and the date of the termination certificate. 
INSURANCE TABLE A
Insurance against
Minimum amount of cover or minimum limit of indemnity
Loss of or damage caused by the Contractor to the Employer’s property
The replacement cost where not covered by the Employer’s insurance.

The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.
Loss of or damage to Plant and Materials
The replacement cost where not covered by the Employer’s insurance.

The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.
Loss of or damage to Equipment
The replacement cost where not covered by the Employer’s insurance.

The Employer’s policy deductible as at Contract Date, where covered by the Employer’s insurance.
The Contractor’s liability for loss of or damage to property (except the Employer’s property, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Service
Loss of or damage to property

The replacement cost

Bodily injury to or death of a person

The amount required by the applicable law.

Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract
The amount required by the applicable law



	
	
	

	
	
	


Z __12.2
Replace core clause 86 with the following:

	Insurance by the Employer
	86
	

	
	86.1
	The Employer provides the insurances stated in the Insurance Table B

	
	
	

	
	
	INSURANCE TABLE B
Insurance against or name of policy

Minimum amount of cover or minimum limit of indemnity

Assets All Risk

Per the insurance policy document

Contract Works insurance

Per the insurance policy document

Environmental Liability

Per the insurance policy document

General and Public Liability

Per the insurance policy document

Transportation (Marine)

Per the insurance policy document

Motor Fleet and Mobile Plant

Per the insurance policy document

Terrorism

Per the insurance policy document

Cyber Liability

Per the insurance policy document

Nuclear Material Damage and Business Interruption

Per the insurance policy document

Nuclear Material Damage Terrorism

Per the insurance policy document




	Z13
	Nuclear Liability

	Z13.1
	The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS.

	Z13.2
	The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z13.3
	Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z13.4
	The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter.

	Z13.5
	The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned.

	
	

	Z14
	Asbestos

	For the purposes of this Z-clause, the following definitions apply:

	AAIA
	means approved asbestos inspection authority.

	ACM
	means asbestos containing materials.

	AL
	means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL.

	Ambient Air
	means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet.

	Compliance Monitoring
	means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	OEL
	means occupational exposure limit.

	Parallel Measurements
	means measurements performed in parallel, yet separately, to existing measurements to verify validity of results.

	Safe Levels
	means  airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	Standard
	means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles.

	SANAS
	means the South African National Accreditation System.

	TWA
	means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA.

	Z14.1
	The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM.

	Z14.2
	Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan.

	Z14.3
	The Employer manages asbestos and ACM according to the Standard.

	Z14.4
	In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe.

	Z14.5
	The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable.

	Z14.6
	The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001.

	Z14.7
	Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation.


C1.2 Contract Data

Part two - Data provided by the Contractor
Completion of the data in full, according to Options chosen, is essential to create a complete contract.

	Clause
	Statement
	Data

	10.1
	The Contractor is (Name):
	     

	
	Address
	     

	
	Tel No.
	     

	
	Fax No.
	     

	11.2(8)
	The direct fee percentage is
	     %

	
	The subcontracted fee percentage is
	     %

	11.2(14)
	The following matters will be included in the Risk Register
	     

	11.2(15)
	The Service Information for the Contractor’s plan is in:
	     

	21.1
	The plan identified in the Contract Data is contained in:
	     

	24.1
	The key people are:
	

	
	1

Name:
	     

	
	

Job:
	     

	
	

Responsibilities:
	     

	
	

Qualifications:
	     

	
	

Experience:
	     

	
	2

Name:
	     

	
	

Job
	     

	
	

Responsibilities:
	     

	
	

Qualifications:
	     

	
	

Experience:
	     

	
	
	     

	
	
	CV's (and further key person's data including CVs) are in      .

	A
	Priced contract with price list
	

	11.2(12)
	The price list is in
	     

	11.2(19)
	The tendered total of the Prices is
	R     


C1.3 Forms of Securities 

Pro formas for Guarantees

For use with the NEC3 Term Service Contract (TSC3)
Pro forma Parent Company Guarantee (for use with Option X4)

(to be reproduced exactly as shown below on the letterhead of the Contractor’s Parent Company)
	Eskom Holdings SOC Ltd

Megawatt Park

Maxwell Drive

Sandton

Johannesburg
	Date:
	


Dear Sirs,

Parent Company Guarantee for Contract No  

With reference to the above numbered contract made or to be made between 

	Eskom Holdings SOC Ltd
	(the Employer) and

	{Insert registered name and address of the Contractor}
	(the Contractor), for

	{Insert details of the works from the Contract Data}
	(the works).


	I/We the undersigned 
	

	on behalf of the Contractor’s parent company 
	

	of physical address
	


and duly authorised thereto do hereby unconditionally guarantee to the Employer that the Contractor shall Provide the Service in accordance with the above numbered Contract.

1. If for any reason the Contractor fails to Provide the Service, we hereby agree to cause to Provide the Service at no additional cost to the Employer.

2. If we fail to comply with the terms of this Deed of Guarantee, the Employer may itself procure such performance (whether or not the Agreement be formally determined).  The Employer is to notify us and we shall indemnify the Employer for any additional cost or expense it incurs.

3. Our liability shall be as primary obligor and not merely as surety and shall not be impaired or discharged by reason of any arrangement or change in relationship made between the Contractor and the Employer and/or between us and Contractor; nor any alteration in the obligations undertaken by the Contractor or in the terms of the Agreement; nor any indulgence, failure, delay by you as to any matter; nor any dissolution or liquidation or such other analogous event of the Contractor.

4. The Employer shall not be obliged before taking steps to enforce the terms of this Deed of Guarantee to obtain judgement against the Contractor in any court or other tribunal, to make or file any claim in liquidation (or analogous proceedings) or to seek any remedy or proceed first against the Contractor.

5. This Deed of Guarantee shall be governed by and construed in accordance with the laws of the Republic of South Africa and we hereby submit to the non-exclusive jurisdiction of the High Court of South Africa.

	Signed at
	
	on this
	
	day of 
	
	202_


	Signature(s)
	
	

	Name(s) (printed)
	
	

	Position in parent company


	
	

	Signature of Witness(s)


	
	

	Name(s) (printed)
	
	


Part 2: Pricing Data

TSC3 Option A

	Document reference
	Title
	No of pages

	C2.1
	Pricing assumptions: Option A
	2

	C2.2
	The price list 
	[●]


C2.1 Pricing assumptions: Option A

1. How work is priced and assessed for payment

Clause 11 in NEC3 Term Service Contract (TSC3) core clauses and Option A states:

	Identified and defined terms
	11

11.2
	(12) The Price List is the price list unless later changed in accordance with this contract.



	
	
	(17) The Price for Services Provided to Date is the total of 

· the Price for each lump sum item in the Price List which the Contractor has completed and

· where a quantity is stated for an item in the Price List, an amount calculated by multiplying the quantity which the Contractor has completed by the rate.



	
	
	(19) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate.




This confirms that Option A is a priced contract where the Prices are derived from a list of items of service which can be priced as lump sums or as expected quantities of service multiplied by a rate or a mix of both.

2. Function of the Price List

Clause 54.1 in Option A states: “Information in the Price List is not Service Information”.  This confirms that instructions to do work or how it is to be done are not included in the Price List but in the Service Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Service in accordance with the Service Information”. Hence the Contractor does not Provide the Service in accordance with the Price List.   The Price List is only a pricing document.  

Link to the Contractor’s plan

Clause 21.4 states “The Contractor provides information which shows how each item description on the Price List relates to the operations on each plan which he submits for acceptance”.  Hence when compiling the price list, the tendering contractor needs to develop his first clause 21.2 plan in such a way that operations shown on it can be priced in the price list  and result in a satisfactory cash flow in terms of clause 11.2(17). 

3. Preparing the price list
Before preparing the price list, both the Employer and tendering contractors should read the TSC3 Guidance Notes pages 14 and 15.  In an Option A contract, either Party may have entered items into the price list either as a process of offer and acceptance (tendering) or by negotiation depending on the nature of the service to be provided.  Alternatively the Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in the price list to be prepared and priced by him. 

It is assumed that in preparing or finalising the price list the Contractor:
· Has taken account of the guidance given in the TSC3 Guidance Notes relevant to Option A;

· Understands the function of the Price List and how work is priced and paid for;

· Is aware of the need to link operations shown in his plan to items shown in the Price List;

· Has listed and priced items in the price list which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Service Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;
· Has priced work he decides not to show as a separate item within the Prices or rates of other listed items in order to fulfil the obligation to complete the service for the tendered total of the Prices. 
· Understands there is no adjustment to items priced as lump sums if the amount, or quantity, of work within that item later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the (lump sum) Prices is as a result of a compensation event. 

3.1. Format of the price list
(From the example given in an Appendix within the TSC3 Guidance Notes)

Entries in the first four columns in the price list in section C2.2 are made either by the Employer or the tendering contractor. 

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tendering contractor enters the amount in the Price column only, the Unit, Expected Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for an item of work which is the rate for the work multiplied by the quantity completed, the tendering contractor enters the rate which is then multiplied by the Expected Quantity to produce the Price, which is also entered.

If the Contractor is to be paid a Price for an item proportional to the length of time for which a service is provided, a unit of time is stated in the Unit column and the expected length of time (as a quantity of the stated units of time) is stated in the Expected Quantity column.

C2.2 the price list


	SCOPE
	Item No
	QTY per Mill
	DESCRIPTION OF ITEMS REQUIRED 
	STOCK NUMBER
	Unit For 3 Year's - 36 Months
	Total QTY
 (30 Mills)
	Rate Per Item
	QS Estimates

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	1.0 PRELIMINARIES & GENERAL:
	
	
	
	
	 

	 
	Item No
	QTY per Mill
	1.1 PRELIMINARIES & GENERAL:
	 
	 
	 
	Rate Per Item
	 R                           -   

	 
	1.1.1
	 
	Health and Safety File
	 
	No
	1
	 
	 

	 
	1.1.2
	 
	Safety PPE - 2 x Sets Per Person Per Year for 3 Years (23 employees)
	 
	No
	138
	 
	 

	 
	1.1.3
	 
	Medical Clearance - 1 x Per Person Per Year for 3 Years (23 employees)
	 
	No
	69
	 
	 

	 
	1.1.4
	 
	Medical or Close Out - 1 Per Person (23 employees)
	 
	No
	23
	 
	 

	 
	1.1.5
	 
	Cell phones Three (3) for 3 Years
	 
	Month
	108
	 
	 

	 
	1.1.6
	 
	Travelling HWH from Maropong/Town to ESKOM Laydown - 2 x 16 Seater Bus                                           (25km x 2 Per Day - To Eskom & Back to Maropong/Town)
	km is for 2 x Busses, But Rate for 1 x Bus
	km
	109500
	 
	 

	 
	1.1.7
	 
	Travelling HWH from Laydown to Plant - 2 x 16 Seater Bus                                                                                                                                                                                                                                                                                    (5km x 2 Per Day - From Laydown To plant & Back)
	km is for 2 x Busses, But Rate for 1 x Bus
	km
	21900
	 
	 

	 
	1.1.8
	 
	Light driven vehicle from Maropong/Town to ESKOM Laydown - 2 x Vehicles                                                                                                                                                                                                                                                             (25km x 2 Per Day - To Eskom & Back to Maropong/Town)
	km is for 2 x Vehicles, But Rate for 1 x Vehicle
	km
	3600
	 
	 

	 
	1.1.9
	 
	Light driven vehicle from Laydown to Plant - 2 x Vehicles                                                                                                                                                                                                                                                                                            (5km x 2 Per Day - From Laydown To plant & Back)
	km is for 2 x Vehicles, But Rate for 1 x Vehicle
	km
	720
	 
	 

	 
	1.1.10
	 
	Consumables, Tools And Equipment
	 
	Year
	3
	 
	 

	PLEASE NOTE: None off the following will be Paid or Priced for. These Items MUST be Part of The Tenderer/Contractor Company "Overheads" and WILL NOT Be Entertained as Compensation Events (CE's)
	1. Accommodation: All Employees MUST be Local.
	 
	 
	 
	 
	 

	
	2.Security Clearances: Tenderer/Contractor MUST make sure That ALL Employees MUST be Security Cleared
	 
	 
	 
	 
	 

	
	3. Insurances: Tenderer/Contractor MUST make sure that ALL Insurances according to NEC3 Contract & According to Law is in place.
	 
	 
	 
	 
	 

	
	4.Site Establishment & De-Establishment: Contractor will be presumed to be Local.
	 
	 
	 
	 
	 

	
	5.Storage Containers, Site Offices, Ablutions, Staff Kitchen, Etc.: This will be supplied by ESKOM Finance.
	 
	 
	 
	 
	 

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	TOTAL PRELIMINARIES & GENERAL
	 R                      -   

	 
	 
	1.0
	SUB TOTAL: PRELIMINARIES & GENERAL OVERHEAD & PROFIT PERCENTAGE
	 
	 
	 
	Rate Per Item
	 

	 
	 
	 
	Overhead Percentage: This Should Be Included In The Itemised Prices Above
	 
	%
	0.0%
	 
	 

	 
	 
	 
	Profit Percentage: This Should Be Included In The Itemised Prices Above
	 
	%
	0.0%
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	1.0 TOTAL: PRELIMINARIES & GENERAL INCLUDING: OVERHEAD & PROFIT %                                                                                                                                                                                                                                              (Carried Over To BOQ Summary)
	 R                                         -   

	
	
	
	
	
	
	
	
	

	 
	 
	 
	2.0 LABOUR:
	 
	 
	 
	 
	 

	 
	Item No
	QTY per Mill
	2.1  LABOUR:      NORMAL TIME DAY (48 Hours per Week x 52,143 Weeks Per Year For 3 Years)                                                                   PLEASE NOTE: (6 Days Week, Monday to Saturday 48 Hrs Per Work Week)
	 
	 
	Rate Per Item
	 R                           -   

	 
	2.1.1
	 
	Site Manager (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.2
	 
	Clerk/Secretary (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.3
	 
	Safety Officer (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.4
	 
	Mechanical Fitter (6)
	 
	hr
	45051.55
	 
	 

	 
	2.1.5
	 
	Semi-Skilled Assistant (4)
	 
	hr
	30034.37
	 
	 

	 
	2.1.6
	 
	C&I Technician (2)
	 
	hr
	15017.18
	 
	 

	 
	2.1.7
	 
	QC/QA Coordinator (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.8
	 
	Mechanical Supervisors (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.9
	 
	Rigger (1)
	 
	hr
	7508.59
	 
	 

	 
	2.1.10
	 
	Boilermaker (2)
	 
	hr
	15017.18
	 
	 

	 
	2.1.11
	 
	Welder A Class (2)
	 
	hr
	15017.18
	 
	 

	 
	2.1.12
	 
	Driver (Crane/Forklift/Truck) (1)
	 
	hr
	7508.59
	 
	 

	TO BE RATE ONLY ON TENDER/CONTRACT
	2.2 OVERTIME: ONLY IF & WHEN NEEDED WITH PERMISSION
	 
	 
	 
	Rate Per Item
	N/A

	 
	2.2.1
	 
	Site Manager (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.2
	 
	Clerk/Secretary (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.3
	 
	Safety Officer (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.4
	 
	Mechanical Fitter (3)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.5
	 
	Semi-Skilled Assistant (4)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.6
	 
	C&I Technician (2)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.7
	 
	QC/QA Coordinator (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.8
	 
	Mechanical Supervisors (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.9
	 
	Rigger (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.10
	 
	Boilermaker (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.11
	 
	Welder A Class (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.2.12
	 
	Driver/Operator (Crane/Forklift/Truck) (1)
	 
	hr
	0.00
	 
	N/A

	TO BE RATE ONLY ON TENDER/CONTRACT
	2.3 PUBLIC HOLIDAYS / SUNDAYS
	 
	 
	 
	Rate Per Item
	N/A

	 
	2.3.1
	 
	Safety Officer (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.2
	 
	Mechanical Fitter (3)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.3
	 
	Semi-Skilled Assistant (4)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.4
	 
	C&I Technician (2)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.5
	 
	QC/QA Coordinator (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.6
	 
	Mechanical Supervisors (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.7
	 
	Rigger (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.8
	 
	Boilermaker (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.9
	 
	Welder A Class (1)
	 
	hr
	0.00
	 
	N/A

	 
	2.3.10
	 
	Driver/Operator (Crane/Forklift/Truck) (1)
	 
	hr
	0.00
	 
	N/A

	TO BE RATE ONLY ON TENDER/CONTRACT
	2.4 STANDBY 
	 
	 
	 
	Rate Per Item
	N/A

	 
	2.4.1
	 
	Safety Officer (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.2
	 
	Mechanical Fitter (3)
	 
	period
	0.00
	 
	N/A

	 
	2.4.3
	 
	Semi-Skilled Assistant (4)
	 
	period
	0.00
	 
	N/A

	 
	2.4.4
	 
	C&I Technician (2)
	 
	period
	0.00
	 
	N/A

	 
	2.4.5
	 
	QC/QA Coordinator (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.6
	 
	Mechanical Supervisors (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.7
	 
	Rigger (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.8
	 
	Boilermaker (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.9
	 
	Welder A Class (1)
	 
	period
	0.00
	 
	N/A

	 
	2.4.10
	 
	Driver/Operator (Crane/Forklift/Truck) (1)
	 
	period
	0.00
	 
	N/A

	TO BE RATE ONLY ON TENDER/CONTRACT
	2.5 NIGHT SHIFT ALLOWANCE (15% of Rate)
	 
	 
	 
	Rate Per Item
	N/A

	 
	2.5.1
	 
	Mechanical Fitter (3)
	 
	hr
	0.00
	 
	N/A

	 
	2.5.2
	 
	C&I Technician (4)
	 
	hr
	0.00
	 
	N/A

	 
	2.5.3
	 
	Semi-Skilled Assistant (2)
	 
	hr
	0.00
	 
	N/A

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	TOTAL LABOUR
	 R                      -   

	 
	 
	2.0
	SUB TOTAL: LABOUR OVERHEAD & PROFIT PERCENTAGE
	 
	 
	 
	Rate Per Item
	 

	 
	 
	 
	Overhead Percentage: This Should Be Included In The Itemised Prices Above
	 
	%
	0.0%
	 
	 

	 
	 
	 
	Profit Percentage: This Should Be Included In The Itemised Prices Above
	 
	%
	0.0%
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	2.0 TOTAL: LABOUR INCLUDING: OVERHEAD & PROFIT %                                                                                                                                                                                                                                                                                 (Carried Over To BOQ Summary)
	 R                                         -   

	
	
	
	
	
	
	
	
	

	 
	 
	 
	3.0 SPARES: MILL FEEDERS
	STOCK NUMBER
	Unit For 3 Year's - 36 Months
	Total QTY
 (30 Mills)
	Rate Per Item
	QS Estimates

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	Item No
	QTY per Mill
	3.1 MILL FEEDERS SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	MILL FEEDER SPARES
	Rate Per Item
	 R                           -   

	 
	3.1.1
	1
	Endless belt conveyor, Flexowell F80N, 1000mm wide, 80mm skirting, Type GF-N100-L300
	694385
	No
	0
	 
	 

	 
	3.1.2
	2
	COC Take-up spindle/shaft
	 
	No
	40
	 
	 

	 
	3.1.3
	2
	Take-up tensioning rod nut
	 
	No
	80
	 
	 

	 
	3.1.4
	2
	Coal feeder Back-up Ring, 150mm Diameter x 50mm
	 
	No
	80
	 
	 

	 
	3.1.5
	2
	Coal feeder Seal Ring, 180mm Diameter x 15mm
	 
	No
	80
	 
	 

	 
	3.1.6
	2
	Labyrinth seal, 180mm Diameter x 16mm -drive shaft (Radial seal)
	 
	No
	80
	 
	 

	 
	3.1.7
	5
	RCF Roller table idlers, Ml 63.5, SW 15, RL 500 - completed set
	 
	No
	100
	 
	 

	 
	3.1.8
	2
	RCF Bed depth limiter bar
	 
	No
	80
	 
	 

	 
	3.1.9
	1
	RCF Bed depth limiter spindle
	 
	No
	40
	 
	 

	 
	3.1.10
	1
	Coal detector flap
	 
	No
	10
	 
	 

	 
	3.1.11
	2
	Coal detector flap bearing
	 
	No
	20
	 
	 

	 
	3.1.12
	1
	Inspection doors seals - Rubber gasket 5mm
	 
	No
	40
	 
	 

	 
	3.1.13
	1
	COC Scraper chain, Axle base 4225mm; conveyor chain 10 x 38mm; chain pitch 146.8mm
	 
	No
	40
	 
	 

	 
	3.1.14
	46
	RCF idlers - Ramsey 10-20-1, single idler
	 
	No
	460
	 
	 

	 
	3.1.15
	12
	Coal bunker shut off valve High pressure packing, 20 x 15mm RivaMid K83
	 
	No
	480
	 
	 

	 
	3.1.16
	1
	Compensator; MTRL: Rubber EPDM; 13mm thick; 500C; 3.5 bar; 40mm axial compression; 20mm axial extension; 10mm lateral movement
	 
	No
	15
	 
	 

	 
	3.1.17
	1
	RCF Drive pulley
	 
	No
	10
	 
	 

	 
	3.1.18
	1
	COC Non drive shaft - EN19 Steel, Take up rod - Clean-out shaft 
	New design
	No
	20
	 
	 

	 
	3.1.19
	1
	RCF outlet gate - Shut-off gate valve, HPE, Type AS 800 x 1000mm
	 
	No
	20
	 
	 

	 
	3.1.20
	1
	Coal bunker shut off gate spindle -, Round steel, 60mm diameter, C45
	 
	No
	40
	 
	 

	 
	3.1.21
	1
	Coal bunker shut off gate spindle -, Round steel, 80mm diameter, C45
	 
	No
	40
	 
	 

	 
	3.1.22
	1
	Bottom RCF outlet gate bearing - Two-hole flange bearing, Type PCJT 30-N, EN-GJL
	 
	No
	40
	 
	 

	 
	3.1.23
	2
	Coal Feeder Cleanout Conveyor Take Up Disc Spring; Type: Spring; Dimensions: ID 28.5 x OD 56 x THK 2mm; Material: Chrome Vanadium; DIN 2093; For use on Mills; Part No: SF-TAP
	671089
	No
	40
	 
	 

	 
	3.1.24
	2
	Clean out shaft Take up bearing; Inside Diameter: 50mm; Housing size: WD 115 x LG 148mm; Slot width: 16mm; Frame: WD 16 x LG 400 x HT 102mm; Rolling Element: Ball; Housing Material: Cast Iron; Style: Eccentric  Locking Collar; Part No: TTUE50
	640013
	No
	40
	 
	 

	 
	3.1.25
	2
	Clean-out shaft bearing sea ring; Type: Needle; Inside Diameter: 50mm; Outside Diameter: 60mm; Width: 25mm; Material: Carbon Chromium Steel; Bore Shape: Circular; DIN 620; IR Series; Part No: IR 50 x 60 x 25mm
	671083
	No
	40
	 
	 

	 
	3.1.26
	2
	Seal, Ring, Type: Radial Shaft; Inside Diameter: 60mm; Outside Diameter: 80mm; Thickness: 7.7mm; Material: NBR; Application: Mills; Rubber NBR 80 Shore A; Case SAE 1008; Spring SAE 1070; Radial Shaft Seal with Rubber Covered O.D Short; Flexibly Suspended; Spring Located Sealing Lip and Additional Dust Lip; Pump Seal Type N; Part No: TCN11
	671084
	No
	40
	 
	 

	
	
	
	
	
	
	
	0
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	TOTAL MILL FEEDERS SPARES
	 R                      -   

	 
	 
	3.0
	SUB TOTAL: MILL FEEDERS SPARES OVERHEAD & PROFIT PERCENTAGE
	 
	 
	 
	Rate Per Item
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	Overhead Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	Profit Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	3.0 TOTAL: MILL FEEDERS SPARES INCLUDING: OVERHEAD & PROFIT %                                                                                                                                                                                                                                                            (Carried Over To BOQ Summary)
	 R                                         -   

	
	
	
	
	
	
	
	
	

	 
	 
	 
	4.0 SPARES: MILL REBUILDS
	STOCK NUMBER
	Unit For 3 Year's - 36 Months
	Total QTY
 (30 Mills)
	Rate Per Item
	QS Estimates

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	Item No
	QTY per Mill
	4.1 CT2 MOD SPARES:
	 
	 
	 
	 
	 

	CT2 MOD SPARES
	Rate Per Item
	 R                           -   

	 
	4.1.1
	3
	Loading frame wear protection set (2 x side, 1 x bottom), 
	New design
	No
	60
	 
	 

	Replace if damaged
	4.1.2
	2
	Modified CT2 scraper assembly set: CMP/MED/19/03/001 and ENF/MED/21/10/008
	New design
	No
	40
	 
	 

	 
	4.1.3
	1
	Plenum chamber floor outer barrel liner assembly: ENF/MED/21/11/012
	New design
	No
	20
	 
	 

	 
	4.1.4
	1
	Mill Static Cowl B114116-35-11-IG04-00081/82
	 
	No
	40
	 
	 

	 
	4.1.5
	1
	Pulley coupling, Type: elastic coupling, Nor-Mex E112
	New design
	No
	40
	 
	 

	 
	4.1.6
	2
	Fastening flange with drive station bearings, 350mm diameter x 72.5mm x 4 holes
	New design
	No
	80
	 
	 

	 
	4.1.7
	1
	RCF Take-up pulley
	New design
	No
	0
	 
	 

	 
	4.1.8
	2
	Take-up bearings, TTUE 55
	640014
	No
	80
	 
	 

	 
	4.1.9
	3
	Inner roller seal air pipe wear protection, item 301 & 302 in  B114116-35-35-IG04-00001-AB
	New design
	No
	120
	 
	 

	 
	4.1.10
	1
	Split labyrinth seal assembly: Full set with accessories according to B114116-35-11-IG04-00002
	New design
	No
	10
	 
	 

	 
	4.1.11
	1
	Gearbox Desiccant breather Heavy duty with protection against dropping & splashing water; 2 x stainless steel filters; Galvanized; 1.4571 material; G1" threads
	New design
	No
	20
	 
	 

	 
	4.1.12
	1
	Hydraulic filter
	New design, 719243
	No
	0
	 
	 

	 
	Item No
	QTY per Mill
	4.2 MILL HOUSING REPAIRS (Liners) SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	MILL HOUSING REPAIRS (Liners) SPARES
	40
	 
	 
	Rate Per Item
	 R                           -   

	Rebuild side wall liners 
	4.2.1
	4
	Liner plate, 2900 (±100) x 1800 (±50) x 12mm (W x L x T), Material: 8mm Composite wear plate, hard-faced with 4mm HRC62 on inside diameter, rolled to 2200mm (±100mm) ID
	 
	No
	40
	 
	 

	Rebuild main inspection door 
	4.2.2
	48
	M16 x 40mm Hex Head, Mat 8.8, galvanised
	 
	No
	1920
	 
	 

	
	4.2.3
	1
	Sealing Cord Square 15 x 15 x 3800mm, Ceramic Fibre With Inconel Core 500°C
	 
	No
	40
	 
	 

	
	4.2.4
	38
	Locking Edge Washer VSK 16mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	1520
	 
	 

	Rebuild inspection door 
	4.2.5
	64
	M24 x 75mm Hex Head Bolt, Mat 8.8, galvanised
	 
	No
	2560
	 
	 

	
	4.2.6
	1
	Sealing Cord Square 15 x 15 x 9600mm, Ceramic Fibre With Inconel Core 500°C
	 
	No
	40
	 
	 

	
	4.2.7
	64
	Locking Edge Washer VSK 24mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	2560
	 
	 

	Rebuild Roller Access door 
	4.2.8
	48
	M20 Hex Nuts, Mat 8, galvanised
	 
	No
	1920
	 
	 

	
	4.2.9
	48
	M20 x 70mm Hex Head Bolt, Mat 8.8 galvanised
	 
	No
	1920
	 
	 

	
	4.2.10
	48
	Locking Edge Washer VSK 20mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	1920
	 
	 

	
	4.2.11
	3
	Sealing form IBCDN400,PM6 PN6, 2mm thick, Mat: Synthetic 
	 
	No
	120
	 
	 

	Replace Scraper Compartment Door
	4.2.12
	48
	M12 x 35mm Hex Head Screw, Mat:8.8 galvanised
	 
	No
	1920
	 
	 

	
	4.2.13
	48
	Locking Edge Washer VSK 12mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	1920
	 
	 

	
	4.2.14
	2
	Sealing Cord Square 15 x 15 x 1800mm, Ceramic Fibre With Inconel Core 500°C
	 
	No
	80
	 
	 

	 
	4.2.15
	2
	Scraper bolts & washers set M30 x 70mm
	 
	No
	80
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.3 INSTALLATION OF GRINDING TRACK SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	INSTALLATION OF GRINDING TRACK SPARES
	Rate Per Item
	 R                           -   

	Install track segments (213)
	4.3.1
	26
	Spring Plate Clamping Screw D54 / 30.5 x 30mm, Mat: 1.0503 (C45)
	 
	No
	1040
	 
	 

	
	4.3.2
	26
	Clamping Screw M30 x 392 /317mm, Galvanized, Mat: 1.0060 (including arrangements)
	 
	No
	1040
	 
	 

	
	4.3.3
	104
	Disk Spring 80 x 41 x 3mm, Galvanized, Mat: 1.8159 (51CrV4) Chromium-Vanadium Steel Washer - Disc Spring Washer
	 
	No
	4160
	 
	 

	
	4.3.4
	52
	Support Ring SU 30 - 35 - 1.4, Mat: T
	 
	No
	2080
	 
	 

	
	4.3.5
	26
	O Ring 30 x 3mm, Mat: Viton
	 
	No
	1040
	 
	 

	
	4.3.6
	26
	M30 Hex Nut, Galvanized, Mat: 5
	 
	No
	1040
	 
	 

	
	4.3.7
	26
	M30 Hex Nut, Galvanized, Mat: 8
	 
	No
	1040
	 
	 

	Install clamping ring bolts + torque (191)
	4.3.8
	13
	Hex Socket Head Cap Screw M30 x 380mm, Galvanized, Mat: 8.8
	 
	No
	520
	 
	 

	
	4.3.9
	13
	M30 Hex Nut , Galvanized, Mat: 8
	 
	No
	520
	 
	 

	
	4.3.10
	13
	Spring Lock Washer B30.5, Galvanized, Mat: Spring Steel, DIN 128
	 
	No
	520
	 
	 

	Install centre cover plate (212)
	4.3.11
	13
	Hex Screw M20 x 80mm, Galvanized, Mat: 8.8
	 
	No
	520
	 
	 

	
	4.3.12
	13
	Locking Washer VSK 20mm, Galvanized, Mat: Spring Steel
	 
	No
	520
	 
	 

	
	4.3.13
	1
	Sealing D 1520 / 1300 x 3mm, Mat: Klinger -Sil
	 
	No
	40
	 
	 

	Install centre cone (212)
	4.3.14
	7
	Hex Screw M20 x 65mm, Galvanized, Mat: 8.8 EN ISO 4017
	 
	No
	280
	 
	 

	
	4.3.15
	7
	Locking Washer VSK 20mm, Galvanized, Mat: Spring Steel
	 
	No
	280
	 
	 

	Install turn buckles (212)
	4.3.16
	7
	Hex Screw M20 x 65mm, Galvanized, Mat: 8.8 EN ISO 4017
	 
	No
	280
	 
	 

	
	4.3.17
	7
	Locking Washer VSK 20mm, Galvanized, Mat: Spring Steel
	 
	No
	280
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.4 REPAIR SEAL AIR COVERING SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	REPAIR SEAL AIR COVERING SPARES
	Rate Per Item
	 R                           -   

	Weld in new roll plate (193)
	4.4.1
	4
	6mm Rolled Plate 265JR, 378.2 x 2744 x 6mm (H x D x T) quarter segment
	 
	No
	160
	 
	 

	
	4.4.2
	12
	Hex Head Screw M16 x 50mm, Galvanized, Mat: 1.7709 (21CrMoV5-7) EN ISO 4017
	 
	No
	480
	 
	 

	
	4.4.3
	12
	Locking Edge Washer VSK 16mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	480
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.5 NOZZLE RING REPLACEMENT SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	NOZZLE RING REPLACEMENT SPARES
	Rate Per Item
	 R                           -   

	Install new nozzle ring (176)
	4.5.1
	26
	Hex Socket Head Cap Screw M24 x 55mm, Galvanized, Mat: 1.7709 (21CrMoV5-7)
	 
	No
	1040
	 
	 

	
	4.5.2
	26
	Spring Lock Washer Cylindrical Heads 24mm, Galvanized, Mat: Spring Steel
	 
	No
	1040
	 
	 

	Install dam ring (176)
	4.5.3
	24
	Hex Socket Head Cap Screw M20 x 50mm, Galvanized, Mat: 1.7709 (21CrMoV5-7)
	 
	No
	960
	 
	 

	
	4.5.4
	24
	Locking Edge Washer VSKZ 20mm, Galvanized, Mat: Spring Steel
	 
	No
	960
	 
	 

	Shim displacer ring 4+2mm (174)
	4.5.5
	12
	Hex Socket Head Cap Screw M20 x 70mm, Galvanized, Mat: 1.7709 (21CrMoV5-7)
	 
	No
	480
	 
	 

	
	4.5.6
	12
	Nord Lock Washer DNL 20mm, Galvanized, Mat: Spring Steel. EN 10204 2.2
	 
	No
	480
	 
	 

	 
	4.5.7
	1
	Displacer Shims 1 set (1, 2, 3, 4, 5mm)
	 
	No
	40
	 
	 

	Install displacer liners + 16mm graphite seal (174)
	4.5.8
	12
	Plate 12  Dimension 341.9 x 1135.7mm, Mat: CR 4000 (Rolled Displacer Covering Cone)
	 
	No
	120
	 
	 

	
	4.5.9
	36
	Hex Head Screw M20 x 50mm, Galvanized, Mat: 1.7709 (21CrMoV5-7)
	 
	No
	1440
	 
	 

	
	4.5.10
	36
	Washer 20mm, Galvanized, Mat: 1.0401 (C15)
	 
	No
	1440
	 
	 

	
	4.5.11
	36
	Hex Nut M20, Galvanized, Mat: 1.7258 (24CrMo5)
	 
	No
	1440
	 
	 

	
	4.5.12
	36
	Wear Protection Cap D 66 x 28.5mm, Mat: 1.0577 (S355J2)
	 
	No
	1440
	 
	 

	
	4.5.13
	1
	Sealing Cord Square 25 x 25 x 14000mm Ceramic Fibre With Inconel Core 500°C
	 
	No
	40
	 
	 

	
	4.5.14
	12
	Epoxy
	 
	No
	240
	 
	 

	
	4.5.15
	1
	Genkem Glue for Gland Packing  1 Litre Tin
	 
	No
	40
	 
	 

	 
	4.5.16
	12
	Displacer supports
	 
	No
	0
	 
	 

	
	4.5.17
	1
	Split Displacer Ring Assembly, 1 x off complete ring (2 x off halve-splits), ENF/MED/21/05/002 
	 
	No
	10
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.6 INSTALLATION OF GRINDING ROLLERS SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	INSTALLATION OF GRINDING ROLLERS SPARES
	Rate Per Item
	 R                           -   

	Replace pan and rollers 
	4.6.1
	6
	Guide Rollers, Round 176 x 160mm (L x D), Mat: EN 1.0060 (ST60-2K)
	 
	No
	120
	 
	 

	
	4.6.2
	6
	Pendulum Joint Lower part pan, 226 x 207 x 97mm, Mat: EN 1.0553
	 
	No
	90
	 
	 

	
	4.6.3
	6
	Pendulum Joint Side part pan, 197 x 93 x 29mm, Mat: EN 1.0553
	 
	No
	120
	 
	 

	Replace centre bracket connector (Pendulum Joint/ Butt straps) (292/293)
	4.6.4
	18
	Spring Type Straight Pin 35 x 95mm, Galvanized, Mat: 1.0970 EN ISO 8752 (Bottom)
	 
	No
	720
	 
	 

	
	4.6.5
	18
	Washer With Tap 21mm, Galvanized, Mat: 1.0401  (C15) DIN 93 
	 
	No
	720
	 
	 

	
	4.6.6
	18
	Hex Head Screw M20 x 140mm, Galvanized, Mat: 8.8 EN ISO 4017
	 
	No
	720
	 
	 

	
	4.6.7
	12
	Spring Type Straight Pin 40 x 70mm, Galvanized, Mat: 1.0970 EN ISO 8752 (Top)
	 
	No
	480
	 
	 

	
	4.6.8
	12
	Washer With Tap 25mm, Galvanized, Mat: 1.0401 DIN 93
	 
	No
	480
	 
	 

	
	4.6.9
	12
	Hex Head Screw M24 x 120mm, Galvanized, Mat: 8.8 EN ISO 4017
	 
	No
	480
	 
	 

	
	4.6.10
	24
	Hex Head Screw Reduced Shank M42 x 330mm, Galvanized, Mat: 8.8 EN ISO 4014
	 
	No
	960
	 
	 

	
	4.6.11
	6
	Plate 12, Dimension 65 x 283mm, Mat: 1.0038, Retaining Bracket 283 x 65 x 12mm EN 10029
	 
	No
	120
	 
	 

	
	4.6.12
	6
	Plate 10, Dimension 55 x 202mm, Mat: 1.0038, Retaining Plate Bracket Yoke 202 x 55 x 10mm EN 10029
	 
	No
	120
	 
	 

	
	4.6.13
	6
	Plate, Lower Centring Bracket, 50mm, Mat: EN 1.0038, 260 x 223 x 103mm
	 
	No
	90
	 
	 

	
	4.6.14
	6
	Plate, Upper Centring Bracket, 50mm thick, Mat:EN 1.0038, 294 x 179 x 50mm
	 
	No
	90
	 
	 

	 
	4.6.15
	18
	Grinding roller plugging bolts M24 x 40mm with spring washer
	 
	No
	720
	 
	 

	 
	4.6.16
	30
	Butt Strap Pin  35 x 95mm, Galvanized, Mat: 1.0970 EN ISO 8752 (Shellock Pins)
	 
	No
	1200
	 
	 

	 
	4.6.17
	3
	Butt Strap (Top)
	 
	No
	90
	 
	 

	 
	4.6.18
	3
	Butt Strap (Bottom)
	 
	No
	90
	 
	 

	Replace vertical seal air pipe (3) (244)
	4.6.19
	24
	Hex Head Screw M16 x 55mm, Galvanized, Mat: 8.8
	 
	No
	960
	 
	 

	
	4.6.20
	24
	Hex Nut M16, Galvanized, Mat: 8
	 
	No
	960
	 
	 

	
	4.6.21
	12
	Hex Head Screw M12 x 30mm, Galvanized, Mat: 8.8 EN ISO 4014
	 
	No
	480
	 
	 

	
	4.6.22
	12
	Locking Edge Washer VSK 12mm, Galvanized, Mat: Spring Steel EN 10204 2.2
	 
	No
	480
	 
	 

	Replace shocks (6) (Pendulum alignment) (292/293)
	4.6.23
	24
	Hex Head Screw M42 x 110mm, Galvanized, Mat: 8.8
	 
	No
	960
	 
	 

	
	4.6.24
	24
	Safety Plate 43, Galvanized, Mat: 1.0401, DIN 93, EN 10204 2.2
	 
	No
	960
	 
	 

	
	4.6.25
	3
	Plate 160, Dimension 401.5 x 415mm, Mat: 1.0553, Upper Part 1: 415 x 401.5 x 153.21mm, Upper pans
	 
	No
	45
	 
	 

	
	4.6.26
	3
	Plate 160, Dimension 415 x 416.6mm, Mat: 1.0553, Upper Part 2: 416.6 x 415 x 153.21mm, upper pans
	 
	No
	45
	 
	 

	
	4.6.27
	3
	Plate 35, Dimension 73 x 160.3mm, Mat: 1.0553, Upper Part 2: 160.3 x 73 x 29mm
	 
	No
	45
	 
	 

	
	4.6.28
	24
	Hex Head Screw Reduced Shank M42 x 330mm, Galvanized, Mat: 8.8 EN ISO 4014
	 
	No
	960
	 
	 

	
	4.6.29
	6
	Hexagon Slotted and Castle Nut M45, Galvanized, Mat: 5, DIN 935, EN 10204 2.2
	 
	No
	240
	 
	 

	
	4.6.30
	6
	Split pin 8 x 80mm, Mat: 1.0401 (C15), EN ISO 1234
	 
	No
	240
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.7 INSPECTION OF TIE ROD ENDS SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	INSPECTION OF TIE ROD ENDS SPARES
	Rate Per Item
	 R                           -   

	Replace ball carrier (331)
	4.7.1
	3
	Ball Carrier 75 x 75 x 70mm Round 75 H8, Mat: OVAK0 825
	 
	No
	60
	 
	 

	
	4.7.2
	3
	Ball D 75 Hardened, Mat: Roller Bearing Steel
	 
	No
	120
	 
	 

	 
	4.7.3
	3
	Tension rod 34CrNiMo6M B114116-35-33-IG04-00002-AF 
	 
	No
	75
	 
	 

	 
	4.7.4
	3
	Articulated head guide bracket B114116-35-33-IG04-00027-AA
	694028
	No
	60
	 
	 

	Replace guides and rollers 
	4.7.5
	12
	Guide Disc, Round disc, 75 x 25mm (D x T),
	 
	No
	480
	 
	 

	
	4.7.6
	6
	Guide Rollers, 102 x 55mm (L x D)
	 
	No
	240
	 
	 

	
	4.7.7
	1
	6m Long Equal leg Angle iron, 120 x 120 x 10mm, Mat: Carbon Steel S355JR
	 
	No
	40
	 
	 

	
	4.7.8
	1
	1m Long Flat bar 100 x 10mm, Mat: Carbon Steel S355JR
	 
	No
	40
	 
	 

	
	4.7.9
	18
	Chamfered M24 Flat Washer, Mat: DIN 9021
	 
	No
	720
	 
	 

	
	4.7.10
	18
	M24 Hex Nut, ISO 1500/DIN 934 Grade 8.8
	 
	No
	720
	 
	 

	
	4.7.11
	1
	M24 threaded bar 2000mm, DIN 939 Grade 8.8
	 
	No
	40
	 
	 

	
	4.7.12
	12
	M12 x 40mm Studs, DIN 939 Grade 8.8
	 
	No
	480
	 
	 

	
	4.7.13
	12
	M12 Hex Nuts ISO 1500/DIN 934 Grade 8.8
	 
	No
	480
	 
	 

	
	4.7.14
	12
	Chamfered M12 Flat Washer, Mat: DIN 9021
	 
	No
	480
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.8 REPLACEMENT OF GUIDE AND THRUST PLATES SPARES:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	REPLACEMENT OF GUIDE AND THRUST PLATES SPARES
	Rate Per Item
	 R                           -   

	Loosen thrust plate liners in pairs and rotate upside down (275)
	4.8.1
	12
	Washer B 25, Galvanized, Mat: cu EN ISO 7089
	 
	No
	480
	 
	 

	
	4.8.2
	6
	Hex Nut M24, Galvanized Mat: 8 EN ISO 4032
	 
	No
	240
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.9 INSTALLATION OF THRUST PLATES SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	INSTALLATION OF THRUST PLATES SPARES
	Rate Per Item
	 R                           -   

	Install shims 5+1mm 
	4.9.1
	3
	Thrust Plate against Loading Frame, 358 x 385 x 52mm (L x W x T), Mat: XCr18  0.84/61039
	 
	No
	60
	 
	 

	
	4.9.2
	3
	Thrust Plate against Mill Housing, 842 x 320 x 38mm (L x W x T), Mat: Abrasion Resistant White Cast Iron, 22 to 27 % High Chromium Alloy
	 
	No
	60
	 
	 

	
	4.9.3
	3
	Mill Frame Thrust Plate Terminal Strip 358 x 50 x 30mm Material S355 AR+JR
	 
	No
	120
	 
	 

	
	4.9.4
	12
	M24 x 100mm SKT CSK Screw, Grade 10.9
	 
	No
	480
	 
	 

	
	4.9.5
	12
	M24 Flat Washer, B25, Copper 44 x 25 x 5mm
	 
	No
	480
	 
	 

	
	4.9.6
	12
	M24 Hex Nut, Grade 8
	 
	No
	480
	 
	 

	 
	4.9.7
	3
	Mill Housing Guide Plate 842 X 50 X 30mm Material S355 AR+JR
	 
	No
	60
	 
	 

	 
	4.9.8
	3
	Mill Frame Guide Plate 305 X 358 X 50mm Material EN-GJS-400-15
	 
	No
	60
	 
	 

	 
	4.9.9
	3
	Mill Frame Guide Plate Terminal Strip 305 X 358 X 50mm Material S355 AR+JR
	 
	No
	120
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.10 INSTALLATION OF SEAL LABYRINGTH AND RETRO SEAL SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	INSTALLATION OF SEAL LABYRINGTH AND RETRO SEAL SPARES
	Rate Per Item
	 R                           -   

	Install labyrinth flange (112)
	4.10.1
	1
	34m Long Rope Gasket 20mm Ceramic Fibre with glass core 
	 
	No
	40
	 
	 

	
	4.10.2
	1
	1L Genkem General Purpose, Contact Adhesive
	 
	No
	40
	 
	 

	
	4.10.3
	40
	Nord Lock Washer DNL 20mm Galvanized, Mat: Spring Steel
	 
	No
	1600
	 
	 

	
	4.10.4
	40
	Hex Head Screw, M20 x 60mm, Galvanized, Mat: 1.7709  (21CrMoV5-7)
	 
	No
	1600
	 
	 

	
	4.10.5
	48
	Hex Nut M20  Galvanized, Mat: 8
	 
	No
	1920
	 
	 

	
	4.10.6
	48
	Stud M20 x 70mm, Galvanized, Mat: 1.7709  (21CrMoV5-7)
	 
	No
	1920
	 
	 

	
	4.10.7
	48
	Nord Lock Washer DNL 20mm, Galvanized, Mat: Spring Steel
	 
	No
	1920
	 
	 

	Install retro seal 
	4.10.8
	1
	Retro Seal, 2220 x 2176 x 16mm (OD x ID x T), Mat EN 1.0038
	 
	No
	20
	 
	 

	
	4.10.9
	2
	Joint for ring for additional sealing, 120 x 23 x 12mm (L x W x T), rolled to 2220mm diameter
	 
	No
	80
	 
	 

	
	4.10.10
	1
	8m Long Braided Square Graphite Packing, 10 x 10mm
	 
	No
	40
	 
	 

	
	4.10.11
	12
	M12 Allen Socket Head Screw
	 
	No
	480
	 
	 

	
	4.10.12
	4
	M10 Allen Socket Head Screw Grade
	 
	No
	160
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.11 SEAL AIR FAN REPAIRS SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	SEAL AIR FAN REPAIRS SPARES
	Rate Per Item
	 R                           -   

	Repair Seal Air fan
	4.11.1
	1
	Fan Impeller, 
	 
	No
	15
	 
	 

	
	4.11.2
	1
	Coupling, Flender, Flexible N-Eupex, Type B 140
	 
	No
	20
	 
	 

	
	4.11.3
	1
	Block Bearing Seal air fan - A-HRZ10C/224/950/5; DRAWING NO: 71079A1-BLK60NS
	 
	No
	20
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.12 SPARES REQUIRED: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	SPARES REQUIRED
	Rate Per Item
	 R                           -   

	 
	4.12.1
	1
	ENF HP Vane Wheel – Version 5 S Vane, CMP/KUS/20/09/001, Patent no: 2016/03621
	 
	No
	20
	 
	 

	 
	4.12.2
	1
	Main Mill Motor Flexible Claw Coupling: BOKU-N H1600 (FLEXIBLE PIN TYPE)
	722319
	No
	30
	 
	 

	 
	4.12.3
	1
	Grinding Track Segment Driving Pin
	 
	No
	30
	 
	 

	 
	4.12.4
	6
	Pendulum Set Assembly 6 sets (3 left & 3 right):  WD 140 x LG 872mm
	706929
	No
	0
	 
	 

	 
	4.12.5
	6
	Refurbishment of Pendulum Set Assembly 6 sets (3 left & 3 right):  WD 140 x LG 872mm
	706929
	No
	30
	 
	 

	 
	4.12.6
	3
	Tie-rod boot covers
	723073
	No
	20
	 
	 

	 
	4.12.7
	3
	Hydraulics Boot/Bellow Covers Bellow for hydraulic cylinder; FBG-260/200-224,5/824,5
	655538
	No
	60
	 
	 

	 
	4.12.8
	1
	Static Classifier Return Cone Ceramic tile, HV1200 B114116-35-35-IG04-00054
	527178
	No
	180
	 
	 

	 
	4.12.9
	1
	MPS Mill Central Cone Covering, S235JRG2 or VRN 400 or equivalent
	 
	No
	10
	 
	 

	 
	4.12.10
	20
	Protection Caps Cone
	 
	No
	800
	 
	 

	 
	4.12.11
	2
	Cone Gasket Sheet Sealing D 1520 / 1300 x 3mm, Mat: Klinger -Sil
	 
	No
	50
	 
	 

	SCOPE
	Item No
	QTY per Mill
	4.13 MILL REJECT BOX SPARES: 
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	MILL REJECT BOX SPARES
	Rate Per Item
	 R                           -   

	Refurbish Mill Reject Box
	4.13.1
	1
	Mill Reject Box Grating – (MIDDLE), Mill Reject Box Grating (RHS) - P Grid RH Section; Dimensions: 380 x 970mm; Opening Size: 25 x 25mm; Material: 316L Stainless Steel (316L S/S); Bearer Bar Size: 20 x 3mm
	716560
	No
	25
	 
	 

	
	4.13.2
	1
	Mill Reject Box Grating (RHS) - P Grid RH Section; Dimensions: 380 x 970mm; Opening Size: 25 x 25mm; Material: 316L Stainless Steel (316L S/S); Bearer Bar Size: 20 x 3mm
	 
	No
	25
	 
	 

	
	4.13.3
	1
	Mill Reject Box Grating (LHS) - P Grid RH Section; Dimensions: 380 x 970mm; Opening Size: 25 x 25mm; Material: 316L Stainless Steel (316L S/S); Bearer Bar Size: 20 x 3mm
	716567
	No
	25
	 
	 

	
	4.13.4
	1
	Refurbishment of Top and Bottom Gate (Including repair kits for both top and bottom Gate)
	 
	No
	0
	 
	 

	
	4.13.5
	1
	Reject Top Gate 6mm Square Graphite Packing 
	 
	No
	25
	 
	 

	
	4.13.6
	1
	Reject Box 25mm Gland Packing (off cuts) 
	 
	No
	25
	 
	 

	
	4.13.7
	24
	M20 x 70mm Hex s/screws Reject Top Gate
	 
	No
	600
	 
	 

	 
	4.13.8
	48
	M12 x 30mm Hex s/screws (Scraper Doors)
	 
	No
	1200
	 
	 

	 
	4.13.9
	48
	M16 x 40mm Hex s/screws + spring washers (Inspection Door)
	 
	No
	1200
	 
	 

	 
	4.13.10
	24
	M20 x 80mm Hex s/screws + spring washers (Round Inspection Door)
	 
	No
	600
	 
	 

	 
	4.13.11
	84
	M12 x 35mm Allen Cap s/screws + spring washers (Tyre Covers)
	 
	No
	2100
	 
	 

	 
	4.13.12
	8
	M8 x 30m Hex s/screws + spring washers (Coupling Covers)
	 
	No
	200
	 
	 

	 
	4.13.13
	12
	PF Pipe Ceramic Twisted Rope (12mm)
	 
	No
	480
	 
	 

	 
	4.13.14
	1
	16mm Gland Packing (Inspection Door)
	 
	No
	40
	 
	 

	 
	4.13.15
	3
	Wear Plate No.5 Side Roller
	 
	No
	60
	 
	 

	 
	4.13.16
	12
	Wear Plate No.5 Fasteners Protection Discs
	 
	No
	480
	 
	 

	 
	4.13.17
	6
	Hard facing Pylon (Hot Air) Protection Covers
	 
	No
	240
	 
	 

	 
	4.13.18
	6
	Classifier Top Support Tube (Inner Side) + Sockets
	 
	No
	240
	 
	 

	 
	4.13.19
	6
	Classifier Bottom Support Tube (Inner Side) + Sockets
	 
	No
	240
	 
	 

	 
	4.13.20
	6
	PF Pipe Rectangular Centralizing Plates
	 
	No
	240
	 
	 

	 
	4.13.21
	6
	Inner Seal Air Elbow Pipe Support Tubes 
	 
	No
	240
	 
	 

	 
	4.13.22
	3
	Seal Air Tubes and Guide Bushes 
	 
	No
	30
	 
	 

	 
	4.13.23
	68
	Maintenance Door M24 x 40mm with Spring Washer
	 
	No
	2720
	 
	 

	
	
	
	
	
	
	
	0
	

	
	
	
	
	
	TOTAL MILL REBUILD SPARES
	 R                      -   

	 
	 
	4.0
	SUB TOTAL: MILL REBUILD SPARES OVERHEAD & PROFIT PERCENTAGE
	 
	 
	 
	Rate Per Item
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	Overhead Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	Profit Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	4.0 TOTAL: MILL REBUILD SPARES INCLUDING: OVERHEAD & PROFIT %                                                                                                                                            (Carried Over To BOQ Summary)
	 R                                         -   

	
	
	
	
	
	
	
	
	

	 
	 
	 
	5.0 EQUIPMENT AND TOOLS
	STOCK NUMBER
	Unit For 3 Year's - 36 Months
	Total QTY
 (30 Mills)
	Rate Per Item
	QS Estimates

	 
	Item No
	QTY per Mill
	5.1 EQUIPMENT AND TOOLS:
	 
	 
	Total QTY
 (30 Mills)
	 
	 

	EQUIPMENTS AND TOOLS
	 
	 R                           -   

	 
	 
	 
	 
	 
	 
	 
	Rate per Day
	QS Estimates

	 
	5.1.1
	1
	50Ton Mobile Crane to conduct rebuild on all 40 Mills 
	 
	25 days of Rebuild
	900.00
	 
	 

	 
	5.1.2
	1
	Tractor and Trailer 
	 
	25 days of Rebuild
	900.00
	 
	 

	 
	5.1.3
	1
	2.5T Forklift 
	 
	25 days of Rebuild
	900.00
	 
	 

	 
	5.1.4
	1
	Low Bed Truck As & When Needed
	 
	5 days of Rebuild
	0.00
	 
	 

	 
	5.1.5
	1
	Low Bed Trailer As & When Needed
	 
	5 days of Rebuild
	0.00
	 
	 

	 
	5.1.6
	1
	Cherry Pickers As & When Needed
	 
	5 days of Rebuild
	0.00
	 
	 

	 
	5.1.7
	1
	Sky Jacks As & When Needed
	 
	5 days of Rebuild
	0.00
	 
	 

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	TOTAL EQUIPMENT AND TOOLS
	 R                      -   

	 
	 
	5.0
	SUB TOTAL: EQUIPMENT AND TOOLS OVERHEAD & PROFIT PERCENTAGE
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	Overhead Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	Profit Percentage
	 
	%
	10.0%
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 

	5.0 TOTAL: EQUIPMENT AND TOOLS INCLUDING: LABOUR & OVERHEAD & PROFIT %                                                                                                                                                                                                                                (Carried Over To BOQ Summary)
	 R                                         -   

	
	
	
	
	
	
	
	
	

	GRAND TOTAL: PRELIMINARIES, LABOUR, 30 FREEDER SPARES, 30 MILLS SPARES & TOOLS AND EQUIPMENT                                                                                                                                                                                (Including Overhead & Profit Percentages Where Necessary)   (Carried Over To BOQ Summary)
	 R                                         -   




Part 3: Scope of Work 
	Document reference
	Title
	No of pages

	
	This cover page
	1

	C3.1
	Employer’s Service Information
	

	C3.2
	Contractor’s Service Information

(insert at award stage or delete if not applicable)
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	Total number of pages
	


C3.1: Employer’s service Information

Contents


Part 3: Scope of Work
21
C3.1: Employer’s service Information
22
1
Description of the service
24
1.1
Executive overview
24
1.2
Employer’s requirements for the service
24
1.2.1
Contract Roles and Responsibilities
25
1.2.2
Continuous Improvement
28
1.2.3
Management and Reporting
28
1.2.4
Project Implementation
28
1.2.5
Manpower Requirements
28
1.2.6
Re-commissioning
29
1.2.7
Contractor’s Management, Meetings and Key People
29
1.3
Interpretation and terminology
30
2
Management strategy and start up.
31
2.1
The Contractor’s plan for the service
31
2.2
Key Performance Indicators (KPI’s)
31
2.3
Management meetings
31
2.4
Contractor’s management, supervision and key people
32
2.5
Provision of bonds and guarantees
32
2.6
Documentation control
32
2.7
Assessment, Invoicing and payment
33
2.8
Contract change management
34
2.9
Records of Defined Cost to be kept by the Contractor
34
2.10
Training workshops and technology transfer
34
2.11
Design and supply of Equipment
34
2.12
Things provided at the end of the service period for the Employer’s use
34
2.12.1
Equipment
34
2.12.2
Information and other things
34
2.13
Management of work done by Task Order
34
3
Health and safety, the environment and quality assurance
35
3.1
Health and safety risk management
35
3.1.1
General
35
3.2
Environmental constraints and management
36
3.3
Quality assurance requirements
37
3.3.1
Quality Requirements
37
3.3.2
QCP’s, Safe Work Procedures and Job Observations
37
3.3.3
Quality
37
4
Procurement
37
4.1
People
37
4.1.1
Minimum requirements of people employed (Refer to Technical Evaluation Criteria)
37
4.1.2
BBBEE and preferencing scheme
37
4.1.3
Accelerated Shared Growth Initiative – South Africa (ASGI-SA) /SDL & I
37
4.2
Subcontracting
39
4.2.1
Preferred subcontractors
39
4.2.2
Subcontract documentation, and assessment of subcontract tenders
39
4.2.3
Limitations on subcontracting
39
4.2.4
Attendance on subcontractors
39
4.3
Plant and Materials
39
4.3.1
Specifications
39
4.3.2
Correction of defects
39
4.3.3
Contractor’s procurement of Plant and Materials
39
4.3.4
Tests and inspections before delivery
40
4.3.5
Plant & Materials provided “free issue” by the Employer
40
4.3.6
Cataloguing requirements by the Contractor
40
5
Working on the Affected Property
40
5.1
Employer’s site entry and security control, permits, and site regulations
40
5.1.1
Permits
40
5.2
People restrictions, hours of work, conduct and records
40
5.2.1
Time Clocking
40
5.2.2
Hours of work
41
5.3
Health and safety facilities on the Affected Property
41
5.4
Cooperating with and obtaining acceptance of Others
41
5.5
Records of Contractor’s Equipment
41
5.6
Equipment provided by the Employer
41
5.7
Site services and facilities
41
5.7.1
Provided by the Employer
41
5.7.2
Provided by the Contractor
42
5.8
Control of noise, dust, water and waste
42
5.9
Hook ups to existing works
42
5.10
Tests and inspections
42
5.10.1
Description of tests and inspections
42
5.10.2
Materials facilities and samples for tests and inspections
42
6
List of drawings
42
6.1
Drawings issued by the Employer
42


1 Description of the service
1.1 Executive overview 

Medupi Power Station has a requirement of 30 mills to be refurbished on all units for a period of 36 months. This will improve the reliability of the milling plant and hence Medupi UCLF. The Contractor shall execute preventative and corrective maintenance as described in the scope of work on this document. Medupi Documents Identifier: 240-143499237 Rev 4 Medupi Power Station MPS265 Mill Major Overhaul Scope of Work Rev 4.
The station is expected to perform at 92% UCF, 6% PCLF and 2% UCLF, and the specified Milling Plant Maintenance activities and Management strategy must support this requirement.

This document specifies MPS265 Mill Major Overhaul Scope of Work activity requirements for Medupi Power Station
It is therefore imperative that the successful and suitably qualified Contractor aligns his/her organisation fully to these specified scope activities and processes set out in this document.

1.2 Employer’s requirements for the service
Refer to Medupi Documents Identifier: 240-143499237 Rev 4 Medupi Power Station MPS265 Mill Major Overhaul Scope of Work Rev 4 for all the Employer’s requirements pertaining to the contract. (Below is an overview or extract of the Employer and Contractor roles and responsibilities in regard to the contract). 
1.2.1 Contract Roles and Responsibilities
a) The Contractor shall be required to perform major overhaul of one mill within a period of 25 Calendar Days.

b) The Employer is responsible for all Electrical, Performance and Testing, Commissioning as well as Control and Instrumentation Scope of Work as required.

c) The Employer is responsible for Total Fluid Management, i.e., draining and re-filling of oil and any greasing requirement.

d) The Employer and Contractor in this SOW is committed towards the following:

• Retention of critical skills

• Continuous cost reduction

• Health & Environment Safety

• Transfer of operational experience and skills.

· The Contractor shall be responsible for calibration of plant C&I equipment and to provide calibration certificates after as and when required.

e) The Contractor is required to provide all Personal Protective Equipment necessary to complete the work.

f) It is the responsibility of the Contractor to clean the mill internally before entry and commencement of the rebuild/overhaul.

g) The Contractor shall compile improvement programmes to enhance plant performance and achieve cost reductions and the Employer will approve such programmes. The Contractor shall be responsible for all equipment alignment requirements within this scope of work. 

h) The Contractor shall be responsible for all mechanical maintenance work as per Employer’s instructions (refer to Appendix A.3), processes and systems, including work resulting from inspections and tests within the applicable plant areas.

i) The Contractor shall be responsible for mill commissioning after handover and shall provide both mechanical and C&I resources for commissioning of the mill.

j) Handover of the mill shall be deemed completed after the mill has been successfully commissioned and has been running stable for 7 days (168 hrs) after commissioning. There shall be no mill trip during this proving period of 168hrs. PF sampling shall be undertaken by the Employer after 72hrs of running, it is expected that the results should be withing specification (240-123581452)
k) The Contractor is responsible to oversee clean air curve test conducted by the Employer. P&T is done by the Employer according to 3.1.1(b) (240-161447098).

l) The Contractor shall be responsible for all equipment requirements within this scope of work as per protocols.

m) The Contractor shall make use of local black economic empowerment through the use of black business. The Contractor during the duration of the contract shall train persons from the local community in relation to the works; such proof shall be given to the Employer for verification and acceptance.

n) Performance is measured by the Employer against those areas which contribute to the Employer’s business and the Contractor shall be compensated accordingly, (e.g., safety, time management and workmanship).

o) The following complementary services to improve Plant and labour performance can be defined as follows;

• Project Management

• Value engineering

• Commercial Management

• Technical advice 
•  IR Management

• Operational and production process review
p) The Contractor is to ensure that any service rendered does not interfere with the Employer’s scheduled work and should align himself with the Employer’s work control management process.
q) Should the Employer become aware of any changes to the activity schedule (programme of notifications), the Employer may issue the Contractor with a revised programme.

r) The contract entered into with the Contractor is non-exclusive and work against this contract can only be performed upon receipt of a Task Order.

s) All works and safety documentation will be subject to anytime inspection from the Employer.

t) Please note that equipment will only form part of the works once the respective area has been commissioned and handed over to Generation. The Contractor shall take cognisance of the fact that the contract start date can deviate.

u) The Contractor will only mobilize a crew per mill scheduled for refurbishment upon receipt of a Task Order from the Employer, which will be supervised by the Contractor. This contract is for the overhaul of 40 mills over 36 months.

v) Spillage is viewed to be very important for plant housekeeping as well as Environmental Management. Any spillage caused as a result of the Contractor’s activities during the rebuild shall be contained and cleaned by the Contractor.

w) Housekeeping shall be maintained throughout. Upon handover, the Contractor shall take responsibility to conduct effective housekeeping all-round the mill to render the mill in clean, safe and serviceable condition.

x) The Contractor shall ensure the integrity of plant labelling and ensure KKS labelling is not damaged during the execution of the work and if needed to be removed it will be reinstated in its original position or any position determined by the employer.

y) The Contractor must ensure that they have responsible persons (RP) (in terms of PSR) for any work performed on plant. This requires individuals to successfully complete a written and oral examination based on the Plant Safety Regulations.

z) All mechanical fitters and supervisors (above semi-skilled) to be trained and authorised (in terms of PSR and ORHVS) within 3 months of the contract award date. Training will be supplied by the Employer.
aa) The Contractor must ensure that all personnel successfully complete a written examination for the relevant regulation based on the Fossil Fuel Firing Regulations (FFFR). Training will be provided by the Employer.

bb) Before any work starts on site the Contractor is responsible to submit their Safety File to the Employer for review and acceptance. The Contractor shall ensure the integrity of plant labelling and that deficiency with regards to KKS labelling is reported immediately.

cc) The Contractor is also responsible for their employees’ annual medical checks which must be up to date and also kept in the Safety File. Site Induction must be done before any work is done by any Contractor on site.

dd) The Contractor shall be expected to mobilize its crew/s within 2 weeks of receiving the Task Order/s.

ee) The Contractor shall present a monthly dashboard on maintenance key performance indicators according to BS EN15341, which will be discussed and agreed with the Employer prior to commencement of the contract.

ff) The Contractor shall ensure that he has all the necessary hand tools (including pneumatic), welding machines, welding consumables and other consumables as well as lifting equipment (including a pick and carry crane, 50 ton or above) required to complete the job. Note: All other special tools will be supplied by the Employer.

• Note: All lifting equipment supplied by the Contractor must have the appropriate certification which is valid for the duration of the overhaul. Copies of all documentation will be kept available at the mill where the Contractor is busy performing the work and in the Contractor’s office for review by the Employer at any time.

• The Contractor shall supply all the spares agreed upon during negotiations that will be required by the Employer as per the attached list, Appendix A.
1.2.2 Continuous Improvement 

· The Contractor shall implement a program of continuous improvement to optimise plant performance and reduce system and equipment failures. 

· The Contractor shall participate in improvement programs as stipulated by the employer. 

1.2.3  Management and Reporting 

· The Contractor to be represented at all Employer’s monthly contract and safety meetings. 

· The Contractor to be represented at any ad-hoc meetings that may arise in order to address any production or safety related matters. 

· Liaison meetings shall be held with the Employer’s Representative or his/her delegate on a weekly basis to discuss progress any technical details, or concerns.
1.2.4 Project Implementation 

a) The Contractor shall supply a project implementation plan including at least the following; 

i. Site establishment 

ii. Manpower plan 

iii. Organogram 

iv. Skills required and associated cost per skill (e.g. artisan, site manager, etc.). 

1.2.5 Manpower Requirements

a) The successful Contractor shall utilise/provide skilled and suitably qualified staff with current experience in the following but not limited disciplines.

i. Working knowledge of SAP R/3 system

ii. Occupational Health and Safety Act 85 of 1993

iii. NEC contract management

iv. Quality Management Control and Assurance procedures

v. Plant Safety regulation authorisation

vi. Spares optimisation

vii. Procedure writing

viii. BOM compilation

b) The Contractor shall make use of local black economic empowerment through the use of black business and recruitment of locals. Specialized skills that are not available locally maybe sourced non-locally after providing evidence of non-availability of the specialized skills. The Eskom Stakeholder Office (ESO) will give guidance on the recruitment process to be followed. The Contractor is requested to liaise with the Contract Manager for contact details of the ESO.
c) All staff brought onto site in connection with this work scope should be able to fluently speak, understand and write in English.

d) Employer’s Site Entry and Security Controls, permits, and site regulations (Police Clearance) All Contractor personnel are to undertake Police Clearance. Certificates must be provided to the Site Service Manager. The Site Service Manager reserves the right to refuse entry to all persons whose criminal records indicate that their presence on site might create an unsafe and insecure environment to specific Power Station. The process shall be repeated every 12 months for low-risk employees (Risk Rating 5, 4) and every 6 months for medium to high-risk employees 
(Risk Rating 3). The following website can be used to guide the process. http://www.saps.gov.za/service/applying_clearance_certificate.php 
e) The Contract shall provide proof of verification of all its Employees qualifications 30 days after contract award.

f) The Contractor ensures that all staff being brought onto Medupi site has a valid fitness certificate based on the specified plant man-job specification.

g) The Contractor shall employ in and about the execution of the works only such persons that are careful, competent and efficient in their specific trades and callings and the Employer shall be at liberty to object to and require the Contractor to remove from the works forthwith any person employed by the Contractor in or about the execution of the works who, in the opinion of the Employer, misconducts himself or is incompetent or negligent in the proper performance of his/her duties and such person shall not again be employed for the works without the written permission of the Employer.

h) Provide daily supervision of all related plant through trained and competent personnel to ensure that inspections & work activities are conducted daily.

i) Ensures proper behaviour of personnel under his/her supervision.

j) The Contractor must ensure that monthly IR meetings are conducted with his/her IR Manager and Employees on site.

k) Ensures training of all personnel under his/her supervision. The training required will include but not limited to Eskom safety training requirements, related plant training if deemed necessary.

l) Ensures high morale of staff and competency.
1.2.6 Re-commissioning 

a) All Plant equipment maintained shall be re-qualified as per site specific procedure (237-0081) after any maintenance intervention. 

b) The Contractor shall be responsible or held liable for any defects arising from maintenance/operational faults over a period of 7 days (168 hrs) after a major overhaul of the equipment the Contractor worked on. 

1.2.7 Contractor’s Management, Meetings and Key People 

a) Before work starts on site, an inaugural meeting is held with the Contractor and the Employer, to explain in detail all requirements of the Site Regulations. 

b) The Contractor is issued with a file of current Site Regulations on arrival. The file remains the property of the Employer and the Contractor is responsible for its maintenance and updating to include new or revised regulations as issued by the Employer. 

c) The Contractor must ensure that all personnel operating mobile equipment and vehicles are authorised, this includes but not limited to; 

• Forklifts 

• Mobile cranes 

• Cherry Pickers 

• Sky Jacks 

d) The Contractor shall be responsible for the regular inspections and daily equipment checks of the mobile equipment and vehicles including record keeping. 

e) The Contractor must ensure that all personnel performing work on the plant are authorised, this includes but not limited to; 

· Confine space locations 

· Working at heights 

· Heat stress areas 

· Scaffolding 

· Hazardous substances 

1.3 Interpretation and terminology
	Contractor: 
	Service Provider contracted for providing specific service to Eskom, Medupi Power Station

	Employer:
	Eskom, or Eskom Medupi Power Station


The following abbreviations are used in this Service Information:

	Abbreviation
	Explanation

	BOM
	Bill of Material

	BS
	British Standard

	C&I
	Control and Instrumentation

	DCS
	Distributed Control System

	DIN
	German Institute of Standard

	DP
	Differential Pressure

	ISO
	International Standards Organisation

	KKS
	Kraftwerk Kennzeichen System

	KPI’s
	Key Performance Indicators

	NEC
	New Engineering Contract

	ORHVS
	Operating Regulations for High Voltage Systems

	PAS 55
	Publically Available Specification 55

	PCLF
	Planned Capability Loss Factor

	PF
	Pulverized Fuel

	PSR
	Plant Safety Regulations

	SANS
	South African Bureau of Standards

	SAP
	Systems, Applications, Products (Plant Maintenance, Procurement, Finance and Materials Management) integrated maintenance management system.

	SOW
	Scope of Work

	STEP
	Station Thermal Efficiency Program

	UCF
	Unit Capability Factor

	UCLF
	Unplanned Capability Loss Factor


2 Management strategy and start up.
2.1 The Contractor’s plan for the service
The Contractor’s plan must be in line with the 240-143499237 Rev 4  Medupi Power Station MPS265 Mill Major Overhaul Scope of Work, as well as all the applicable maintenance strategy documents and the plant maintenance schedules. The Contractor must note that the maintenance strategies and the plant maintenance schedules will be provided by the Employer.

2.2 Key Performance Indicators (KPI’s)

The Employer uses KPI’s to determine the successful performance of the plant area.  The Contractor is required to perform maintenance in order to meet these targets.  The KPI’s are Subject to change on an Annual basis.  The Service Level Table in Section 5 Below contains Penalties that are Tied to theses KPI’s.
	Business Objectives or KPI
	Action

	Mill Major Overhaul
	Complete Mill Major Overhaul Repairs including RCF (Raw Coal Feeder) works within 25 calendar days from permit acceptance date. 

	Mill Commissioning and Start Up monitoring 
	· Commission the Mill with assistance of Eskom Gx Commissioning Team within 12 hrs of permit clearance.

· Monitor the Mill start up and perform PF Clean Air curve to ensure reliability of the Mill post Overhaul


	Reduce Mill downtime period during Overhaul
	Effort Must be taken by the Contractor to ensure the duration for Mill overhaul of 25 is maintained or even reduced to ensure plant availability. 


2.3 Management meetings

Regular meetings of a general nature may be convened and chaired by the Supply Manager as follows:

	Title and purpose
	Approximate time & interval
	Location
	Attendance by:

	Monthly Contractual meeting, Overall Contract progress, assessments, Contract risk discussion and feedback
	Monthly
	Medupi Power Station
	Contract Managers, Site Manager, Contract Site Manager, Gx Contract Supervisors, Secretary 

	Monthly Integrated Risk Management meetings
	Monthly
	Medupi Power Station
	MMD Line Managers, MMD Technicians, All MMD Site Managers, All mmd Safety and quality officers

	Monthly Executive SHEQ meeting
	Monthly
	Medupi Power Station
	Medupi EXCO, Medupi Safety Management, Medupi Line Managers, All Site Managers, Medupi Departmental SHE Reps

	Prioritization meetings
	Daily(Monday – Friday)
	Medupi Power Station
	Production managers ,Contractors , Supervisors ,Technicians


Meetings of a specialist nature may be convened as specified elsewhere in this Service Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the service.  Records of these meetings shall be submitted to the Service Manager by the person convening the meeting within five days of the meeting.  

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.  

2.4 Contractor’s management, supervision and key people
· Site Manager

· Supervisors 

· Safety Officers

· Drivers or Equipment Operators

· Responsible Persons

· Quality Inspector

a) The Contractor’s shall ensures that only competent persons be allowed to work on plant. The Employer’s Service Manager is entitled to verify the qualifications of the Contractor.

b) The Contractor must be knowledgeable about the condition and scope of work contained in this contract and capable of executing the scope of work.

c) The services manager may, having stated reasons, instruct the Contractor to remove a key person. The Contractor then arranges that, after one day, the key person has no further connection with the work included in this contract.

d) The Contractor may not replace any of the key persons without prior written request and approval thereof from the Service Manager.
2.5 Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.  

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Service Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract. 

2.6 Documentation control

The Contractor implements the following procedures or paperwork over the first month of this Contract:

· Business Organisation Chart

· Safety procedures

The following policies, procedures and specifications will be complied by at all times

· Site Regulations – Medupi site Regulations

· BIA/RM/STD/01 – Safety, health and environmental requirements to be met by Contractors

· Hot work procedures

· All specifications produced via the RCM or Medupi maintenance process

· Eskom Medupi Site transport requirements

· Construction Regulations

· Medupi Maintenance Quality Manual

· Occupational, health and Safety Act

· Eskom Life saving Rules

· BIA/QA/STD/01 – Quality requirements for engineering and construction works

· All Relevant Medupi Power Station standards, policies and procedures

· All quality, health, environmental and safety costs are included in the contract price

2.7 Assessment, Invoicing and payment
Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Service Manager’s payment certificate.  

Invoices can be submitted using emails to invoiceseskomlocal@eskom.co.za
· Assessments to be submitted 10 days after Mill has been returned to services and has satisfied all the X17 Clauses requirements so that if there any penalties they may be discussed during the assessment finalisation. 

· Ensure that the Eskom order number is clearly indicated on your invoice together with the line number on the order you are billing for. 

· All Electronic invoices must be sent in PDF format only. 

· Each PDF file should contain one invoice; or one debit note; or one credit note only as Eskom’s SAP system does not support more than one PDF being linked into workflow at a time. 

· Your E-mail may contain more than one PDF file (e.g. 2 invoices on 2 separate PDF files in one e-mail) 

· For Foreign invoices, suppliers will still be required to physically deliver hard copies of original documents to the respective documentation management centers even though you have e-mailed those invoices 

· A PDF file that was created directly from a system meets the definition of original document and is allowed (including saving documents from excel to PDF, word to PDF etc.)

· An Invoice that was printed and then scanned to PDF by the Vendor is not acceptable as this is not an original tax invoice by SARS definition but a copy. 

· The following wording needs to appear on the invoice: “Your invoice is encrypted in order to comply with SARS requirements that invoices and statements sent electronically are tamperproof.” 

· If there is Cost Price Adjustment (CPA) on your invoice we recommend that you issue a separate invoice for CPA so that if there are any issues on the CPA the rest of the invoice can be paid while resolving the CPA issues. 

· You do not require a goods receipt (GR) number to submit your invoices. When the GR number is received you can then send the GR number to the FSS contact center at FSS@eskom.co.za or 011 800 5060. 

· All queries and follow up on invoice payments should made by contacting the FSS Contact Centre:   Tel: 011 800 5060 

Payment will be made within 30 Days after receipt of an acceptable invoice at the address stated in the order and the acceptance of the goods by Eskom.   Payments are made on Friday's only. and include on each invoice the following information:

and include on each invoice the following information:

Name and address of the Contractor and the Service Manager; 

The contract number and title;

Contractor’s VAT registration number;

The Employer’s VAT registration number 4740101508;

Description of service provided for each item invoiced based on the Price List;

Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

(add other as required)

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

2.8 Contract change management 
Refer to NEC TSC Core clause 6, in the event any change to the Contract needs to be managed.
2.9 Records of Defined Cost to be kept by the Contractor
The Contractor is required to keep record and submit proof of all the actuals, in order to be verified at the completion of the Payment Certificate and assessment, should the Service Manager request to do so.
2.10 Training workshops and technology transfer

Training and transfer of skills will be provided by either the Contractor or the Employer, part of the following training will be provided by the Employer as stated in the Medupi Document Identifier: 240-160541815

1. Plant Safety Regulations (PSR)

2. Operating Regulations for High Voltage
2.11 Design and supply of Equipment

Equipment supplied must be in safe working order at all times, irrespective whether the equipment is supplies by the Employer or Contractor. Regular maintenance must be done on all equipment used to execute the service required.

2.12 Things provided at the end of the service period for the Employer’s use

2.12.1 Equipment

Any equipment (assets) bought during the service period will be transferred to the Employer at the end of the service period

2.12.2 Information and other things

In the event that the information and other things are required, it will be discussed by the two Parties, and the provision of information and other things will be mutually agreed upon.
2.13 Management of work done by Task Order

· A Task Order starting with 45* series number will be issued to the Contractor at the beginning of every month for the service. 

· In the case of emergency repairs outside the SOW started in Medupi Document Identifier: 240-160541765, different Task Order will be send to the Contractor for the works. Respond to the issued Task Order must be dealt with as per secondary option X19 of the agreement.
3 Health and safety, the environment and quality assurance

3.1 Health and safety risk management
3.1.1 General

· The Contractor must ensure that all his personnel attend a Health and Safety Induction Course prior to starting with their work. The Induction Course can, on request, be provided by the Employer and will be valid for the duration of one year.

· The Contractor must ensure that all his employees have a valid medical for the duration of the contract. Medicals need to be done yearly.

· Safety Risk Management has the right and authority to visit and inspect the Contractor's workplace or site establishment to ensure that tools, machinery and equipment comply with the minimum safety requirements.

· Station OHS Manager shall be entitled to instruct the Contractor to stop work, without penalty to the Employer, where the Contractor's personnel fail to confirm to safety standards or contravene health and safety regulations. The Station OHS Manager is entitled to cause the Contractor to discipline his employees and to submit disciplinary action, and submit a report to Station OHS Manager. The Contractor shall implement additional health and safety precautions where necessary.

· The Contractor will provide all his personnel with the required personal protective equipment (PPE). 

· Risk Assessments, Pre-Job Briefs, Post – Job Briefs & Job Observations will be conducted for all jobs.

· All Construction Regulation - safety requirements should also be adhered to.
· Safety Plan
· Medicals
· Fall Protection Plan (For all activities conducted at height)
· 16.1 and 16.2 appointments

3.1.2 Fire Precautions

· Any tampering with the Employer's fire equipment is strictly forbidden.

· All exit doors, fire escape routes, walkways, stairways, stair landings and access to electrical distribution boards must be kept free of obstruction, and not be used for work or storage at any time. 

· Firefighting equipment must remain accessible at all times.

· In case of a fire, report the location and extent of the fire to the Electrical Operating Desk at extension 014 762 2555/6911 or Fire and Emergency at 078 100 5614.

· Take the necessary action to safe guard the area to prevent injury and spreading of the fire.


3.1.3 Reporting of accidents

· The Employer follows an accident prevention policy that includes the investigation of all accidents involving personnel and property. This is done with the intention of introducing control measures to prevent a recurrence of the same incidents. 

· The Contractor is expected to fully co-operate to achieve this objective. The Station OHS Manager must be informed immediately of any incidents and any damage to property or equipment must be reported within 24 hours.

· NOTE! This report does not relieve the Contractor of his legal obligation to report certain incidents to the Department of Employment and Labour, or to keep records in terms of the Occupational Health and Safety Act, and Compensation for Occupational Injuries and Diseases Act.


3.1.4 Barricading 
The Contractor will provide and install barricades and warning devices to ensure that equipment and persons are not exposed to danger or to prevent access to the area where there is offloading and/or loading of material or a risky activity is in progress.


3.1.4 Speed Limit

All vehicles must be driven with due consideration for personnel and property. A maximum speed limit of 40 kilometres per hour will be adhered to on the premises at all times, and 20 kilometres per hour in all high traffic areas like the boiler, PJFF etc.


3.1.5 Safety

· The Contractor complies with the Occupational Health and Safety Act, 1993, (the Act) and all Safety procedures issued by the Employer.  The Contractor must furthermore comply with the Employer’s Safety, health and Environmental requirements for Contractors, BIA/RM/STD/ 240-73416879, which is available from the Medupi Documentation Centre.

· The Contractor will carry out work according to Procedure GGR 0992 (Plant Safety Regulations). The Contractor will qualify his supervisors to take out permits on the Employer’s permit to work system in order to always have one authorised person available to take out permits per shift.

· The Contractor will conform to all rules and regulations applicable to Plant Safety and shall complete a proper risk assessment and Worker’s Register prior to working on the plant.

· The Contractor will ensure that his representatives are duly authorised in terms of the Plant Safety Regulations as a responsible person upon commencement of work.

· The Employer shall on request from the Contractor isolate required plant from all sources of danger as described in the Plant Safety Regulations.

· The Employer will provide the Plant Safety Regulation training to the Contractor.

· The Employer shall make a copy of the Plant Safety Regulations available to the Contractor.

· The Contractor will attend monthly safety meetings, and conduct monthly safety meetings with staff.

· The Contractor provides all personal safety equipment, including safety belts and harnesses

· The Contractor will appoint a full time safety officer for the entire duration of the contract.

· The Contractor will adhere to the Eskom Lifesaving rules.

· The Contractor will not be allowed to transport any of its workers in open vehicles to and from site as prescribed in the Eskom safety policy. 

3.2 Environmental constraints and management

· The Contractor should adhere to the Medupi Power Station Environmental Management System that must meet the requirements of ISO 14001:2004.

· The Contractor will be responsible for complying to any current and new environmental requirements, relevant to the Works Information, that may come into effect as part of Medupi Power Station’s EMS for the duration of this contract.

· If there is uncertainty around any environmental issues, the Environmental Department at Medupi Power Station may be contacted for assistance and clarity.

· The Contractor shall comply with any legal and other statutory requirements that the station complies to in accordance with the applicable law.
3.3 Quality assurance requirements

3.3.1 Quality Requirements

The Supplier shall comply with the Eskom’s QM 58 (240-105658000) Supplier Quality Management Specification

· Quality requirements include visual inspection by the Employer, who will be entitled to witness progress of work at any time. The Employer shall also have the right to stop work and re-instruct the Contractor, who will comply with the requests.

· The Employer may, by arrangement, inspect completed work. If, in opinion of the Employer, the work does not comply with the quality requirements expected from the Contractor, the Employer shall instruct the Contractor to rectify the faults. The Contractor will comply with the instructions.
3.3.2 QCP’s, Safe Work Procedures and Job Observations

· QCP’s with action plans, safe work procedures and job observations shall be produced at the request of the Employer. QCP’s must be signed and approved by quality controller / Cleaning Supervisor.

3.3.3 Quality
· The Contractor will comply with the Employer’s Quality Requirements as specified in procedure BIA/QA/STD/01 latest revision, which is available from the Documentation Centre or the internal Medupi Web site.

· All Quality Control documentation must be submitted to the Employer’s Representative for acceptance prior to any work commencing.

4 Procurement
4.1 People

4.1.1 Minimum requirements of people employed (Refer to Technical Evaluation Criteria)
4.1.2 BBBEE and preferencing scheme

The company shall maintain or improve upon their current B-BBEE Contribution level for the duration of the contract. The supplier will be required to submit a new B-BBEE certificate within 3 months, should ownership of the company change during the life of the contract.

The Contractor is expected to submit a valid B-BBEE Verification Certificate from a SANAS accredited Verification Agency each year. Failure to submit such a Certificate may be regarded as the breach of the contract by the Employer

4.1.3 Accelerated Shared Growth Initiative – South Africa (ASGI-SA) /SDL & I

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s SD&L Compliance Schedule.

4.1.3.1 Local Content and Production

This works/service is a non-designated sector and therefore no local production threshold is applicable to qualify for further evaluation.  Tenderers will also be encouraged to utilise local and local to site resources.
4.1.3.2 Skills Development (not weighted criteria)

Eskom intends to improve Skills Development by ensuring that technical support is directed towards enhancing supply capacity and capability within the industry or sector of operation. By doing this the capacity and competitiveness of the local supply base will be increased and the goals of shared growth, employment creation, poverty reduction and skills development will be achieved. Skills development candidates should be from the vicinity of the station.
The Contractor will be required to train at least the following learners per annum,
	Skills Type
	Eskom Target
	Entry Level
	Output
	Tenderers Proposal

	Boiler Marker
	5
	N3 / Matric plus at least 2 years’

experience
	Trade Test
	

	Mechanical Fitters
	5
	N2/Grade 12 or

Equivalent
	Trade Test
	

	Riggers
	5
	N2/Grade 12 or

Equivalent
	Trade Test
	


The Contractor shall keep accurate records and provide the Service Manager with reports on the Contractor’s actual delivery against the above stated SD&L criteria

The Contractor’s failure to comply with his SD&L obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract


4.1.3.3 Retention

a. Eskom shall be permitted to retain 2.5% (two and half percent) of the invoices (excluding VAT) as security for the fulfilment by the tenderers of their SD&L obligations. 

b. Once Eskom has verified that tenderers have fulfilled their SD & L obligations, the 2.5% retained shall be approved for reimbursement by Eskom to suppliers within 90 (ninety) days of verification by Eskom.

4.1.3.4 Reporting

a. The tenderers shall on a monthly /quarterly basis submit a report to Eskom in accordance with Data Collection Template on their compliance with the SD& L obligations described above.

b. Eskom shall review the quarterly reports submitted by the tenderers within 60 (sixty) days of receipt of the reports and notify the tenderers in writing if their SD&L obligations have not been met.

c. Upon notification by Eskom that the tenderers have not met their SD&L obligations, the tenderers shall be required to implement corrective measures to meet those SD&L obligations before the commencement of the following quarter, failing which retention clauses shall be invoked.

d. Every contract shall be accompanied by the SD&L implementation schedule which must be completed by the tenderers and returned to SD&L representative for acceptance before contract award. This will be used as a reference document for monitoring, measuring and reporting on the tenderer’s progress in delivering on their stated SD&L commitments.

4.2 Subcontracting

4.2.1 Preferred subcontractors
Eskom will do business with the suppliers that are prepared to sub-contract 30% of the contract value to EME or QSE’s that are at least 51% Black Owned from rural / underdeveloped area / township.

4.2.2 Subcontract documentation, and assessment of subcontract tenders

1. Subcontracting agreement (signed by both parties) with subcontractor company registration documents (CK, CSD, B-BBEE certificate or sworn affidavit).

2. Copies of sub-contracting contracts (agreements) or copies of letters from the tenderer to the sub-contractors, stating the intent to sub-contract. Both documents should be signed by the Tenderer and the Sub-contractor(s) earmarked.

4.2.3 Limitations on subcontracting

30% of the scope of work will be subcontracted to the above subcontractor.

4.2.4 Attendance on subcontractors
Not applicable

4.3 Plant and Materials

4.3.1 Specifications
Plant and materials provided by the Contractor and the preventative maintenance thereof will be the responsibility of the Contractor.

4.3.2 Correction of defects

The intention of the Contract is preventative maintenance first and foremost however corrective maintenance can be results of the component failure. In the event where plant component have failed, this will be dealt with in accordance with the maintenance strategies and plant maintenance schedule to restore the components to its original state i.e. by repairing and or replacing components. This will be governed by as per core clause 4, testing and defects

4.3.3 Contractor’s procurement of Plant and Materials

Replacement materials/components will be kept as the Employer’s Inventory/stock and issued as stock items when required. The Contractor must inform the Employer immediately of any constraints experienced during the procurement process of plant and materials whenever required to procure any materials.

4.3.4 Tests and inspections before delivery

· It is the Contractor’s responsibility to ensure the machinery and equipment intended for use on this contract are inspected, tested and certified prior to delivery to site.

· Regular inspections can be carried out by the Employer on an as and when required basis.

· The Contractor and the Employer must maintain communication regarding the test and inspections that must be done, and give feedback on the result obtained. The Contractor must inform the Employer in time for a test or inspection to be arranged and done before doing the work that will obstruct the test or inspection.
4.3.5 Plant & Materials provided “free issue” by the Employer
Both parties shall agree if there is any Plant and Material that the Contractor require to execute work. All other Plant and Materials are to be provided by the Contractor.
4.3.6 Cataloguing requirements by the Contractor
Not applicable 
5 Working on the Affected Property

5.1 Employer’s site entry and security control, permits, and site regulations
The Entry to site is only approved once the following is adhered to: 

1. The Contractors Safety file is to be approved by the Employer’s Safety department.

2. All personnel must undergo screening for Criminal records and outstanding warrants

3. Site-specific induction is to be done by all personnel.

5.1.1 Permits

1. The Contractor will ensure that he/she is informed of all the requirements of Eskom’s Plant Safety Regulations and ORHVS and that he/she at all times comply to the requirements of these Regulations.

2. The Contractor ensures his supervisors are trained and authorised as Authorised Supervisors.  

3. Training is provided by Eskom Medupi and is done according to a schedule, thus arrangements need to be made with the Service Manager well in advance.

4. The  Contractor will have at least three Responsible Persons as per Plant Safety Regulations.

5. Two supervisors should be authorised within 3 months of contract award.

5.2 People restrictions, hours of work, conduct and records

5.2.1 Time Clocking

1 The Contractor uses a biometric time clocking system

2 No clocking will result in non-payment.  If a person clocked in but not out or did not clock in, but clocked out, the person will not receive payment for that specific day.

3 Proof of clocking to be submitted to the Employer from files directly generated from the clocking system (no manual intervention)
5.2.2 Hours of work

· All work will be coordinated by the Employer. Working times can be subject to change, the Employer will inform The Contractor well in advance.

· A standby roster will be determined by the parties.

· The Contractor will align his operating shifts to that of the Employer’s five shift cycle.

1. Normal working hours is Eskom working hours: However the Contractor may adjust the working times to ensure the duration of 25 days is not impacted to complete the Mill Major Overhaul

a. Monday to Thursday 
07:00 - 16:15
b. Fridays


07:00 - 12:00 (No lunch break)
2. Outage working hours is :

a. Monday to Friday 
07:00 - 19:00
3. All Timesheets are to be kept for records purposes i.e. man-hours worked safely etc.

4. Other hours will be determined as per critical path activities during outages/breakdowns.

5. Overtime to be approved by the Service Manager
6. Daily time sheet must be kept up to date of normal and overtime worked at all times.

7. All overtime worked must comply with Eskom rest period requirements
5.3 Health and safety facilities on the Affected Property

There is a medical station on site and a fire and rescue service for assistance with serious incidents and treatment of all serious injuries during normal working hours.  Emergency services are available during normal working hours by dialling 6911 or 2555 from any site phone or else 014 (medical centre) 014  (fire and rescue) and also available after hours by dialling 6911/2555 from any site phone or else contacting the Electrical Operating Desk (EOD) at 014 762 2555 or 6911(all hours).  However, the Contractor is expected to handle all minor incidents in-house by providing a first aider and a first aid kit.  
5.4 Cooperating with and obtaining acceptance of Others

Proper co-ordination and work planning must be done when working in any area where others are performing work or activities.  Interfacing may be required with the site maintenance personnel and others.
5.5 Records of Contractor’s Equipment

1. The Contractor to declare all equipment and tools via a pre-set up list at the main entrance, where removal permit will be issued by Security personnel.

2. Contractor need to have a list of inventory of their equipment on site.  

3. Proof of site entrance needs to be provided before equipment can be removed from
5.6 Equipment provided by the Employer
Equipment provided by the Employer is to be signed out on the tools register and returned in a serviceable condition.

5.7 Site services and facilities
5.7.1 Provided by the Employer
Sanitary services, water, compressed air and electricity shall be provided by Eskom at fixed points on the plant. There is also a tuck-shop on site but both only operate on week days and are for the Contractor’s own cost.
5.7.2 Provided by the Contractor
The Contractor is to supply all the personal protective equipment, transport, accommodation, tools, equipment and consumables to perform all the required tasks on site.
5.8 Control of noise, dust, water and waste 

Noisy equipment and tools emitting noise more than 105 dB (A) may not be supplied/utilised by the supplier.

5.9 Hook ups to existing works

Hooking up on heights is a non-negotiable lifesaving rule of Eskom, Medupi Power Station applies Zero Tolerance to non-compliance of the rule or any other lifesaving rule. The same disciplinary process and procedure will be followed when any of the lifesaving rules have been breached.
5.10 Tests and inspections

5.10.1 Description of tests and inspections
The test and inspection to be carried out by the Contractor, the Employer and others will be determined and communicated by the Employer when Contract commenced.

5.10.2 Materials facilities and samples for tests and inspections 
The materials facilities and samples for test and inspection to be carried out by the Contractor, the Employer and others will be determined and communicated by the Employer when the Contract commences.

6 List of drawings

6.1 Drawings issued by the Employer
This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

	Drawing  number
	Revision
	Title

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


� This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.


� Available from Engineering Contract Strategies Tel 011 803 3008 Fax 086 539 1902 � HYPERLINK "http://www.ecs.co.za" �www.ecs.co.za� 







DOCUMENT C2.1
PAGE 2
PRICING DATA




Part C2: Pricing Data
PAGE 1
C2 TSC3 Cover

_1772884914.unknown

