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PART C1 	PAGE 2 OF 107 	AGREEMENTS & CONTRACT DATA
C1.1 Form of Offer & Acceptance

[bookmark: _Toc238537826][bookmark: _Toc240874357]Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

[bookmark: _Toc240874358]REMEDIAL REPAIRS TO THE POLLUTION CONTROL DAMS, FUEL CONTAINMENT AREAS, ASSOCIATED STORMWATER INFRASTRUCTURE, BERM AND HAZARDOUS-WASTE SKIP CONTAINMENT AREA AT GOURIKWA POWER STATION.
The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data. 

Delete the Options which do not apply
	Options B
	The offered total of the Prices exclusive of VAT is
	R [●]

	
	Value Added Tax @ 15% is
	R [●]

	
	The offered total of the amount due inclusive of VAT is[footnoteRef:1] [1:  This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.] 

	R [●]

	
	(in words) [●]




This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

	Signature(s)

	
	
	

	Name(s)

	
	
	

	Capacity

	
	
	

	For the tenderer:

	

	
Name & signature of witness
	(Insert name and address of organisation)
	
	

Date
	

	Tenderer’s CIDB registration number (if applicable) 
	




PART C1.1 	PAGE 2 OF 107 	FORM OF OFFER AND ACCEPTANCE
[bookmark: _Toc238537828][bookmark: _Toc240874359]Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in: 

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).  

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.


	Signature(s)

	
	
	

	Name(s)
	

	
	

	Capacity

	
	
	

	for the Employer

	

	
Name & signature of witness
	(Insert name and address of organisation)
	
	

Date
	



Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.
[bookmark: _Toc238537829][bookmark: _Toc240874360]
Schedule of Deviations to be completed by the Employer prior to contract award
Note:
1.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.
2. The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.
3. A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

	No.
	Subject
	Details

	1
	[●]
	[●]

	2
	[●]
	[●]

	3
	[●]
	[●]

	4
	[●]
	[●]

	5
	[●]
	[●]

	6
	[●]
	[●]

	7
	[●]
	[●]

	
	
	




By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.  

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement. 


	
	For the tenderer:

	
	For the Employer


	Signature

	
	
	

	Name
	

	
	

	Capacity

	
	
	

	On behalf of
	(Insert name and address of organisation)



	
	(Insert name and address of organisation)


	Name & signature of witness
	
	
	

	
Date
	
	
	




C1.2 ECC3 Contract Data

[bookmark: _Toc238537830][bookmark: _Toc240874361]Part one - Data provided by the Employer

	[bookmark: _Toc238537831][bookmark: _Toc240874362]Clause
	[bookmark: _Toc238537832][bookmark: _Toc240874363]Statement
	[bookmark: _Toc238537833][bookmark: _Toc240874364]Data

	1
	[bookmark: _Toc238537834][bookmark: _Toc240874365]General
	

	
	The conditions of contract are the core clauses and the clauses for main Option 
	
B:		Priced contract with bill of quantities

	
	
	

	
	dispute resolution Option
	W1:	Dispute resolution procedure

	
	and secondary Options 
	X1:		Price adjustment for inflation

	
	
	X2		Changes in the law

	
	
	X15:	Contractor design liability limited to reasonable skill and care

	
	
	X16:	Retention

	
	
	Z:		Additional conditions of contract

	
	of the NEC3 Engineering and Construction Contract, April 2013 (ECC3)
	


	10.1
	The Employer is (Name):
	Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa

	
	Address
	Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg

	10.1
	The Project Manager is: (Name)
	Rowan Francis

	
	Address
	15 Pasita Street, Rosenpark, Durbanville , 7550 

	
	Tel
	TBC

	
	e-mail
	Franciro@eskom.co.za

	10.1
	The Supervisor is: (Name)
	TBC

	
	Address
	TBC

	
	Tel No.
	TBC

	
	Fax No.
	TBC

	
	e-mail
	TBC

	11.2(13)










	The works are 















	The inspection, cleaning, assessment, remedial repair, testing, construction and reinstatement of pollution-control dams, fuel-containment structures, associated stormwater drainage infrastructure, berm and erosion-protection works and the hazardous-waste skip containment area at Gourikwa Power Station.
The works include:
a. detailed condition assessment and remedial repair of the Gourikwa Clean Water Dam and Dirty Water Dam;
b. repair of associated concrete, reinforcement, cracks, joints, waterstops, sealants and drainage infrastructure;
c. repair and resealing of fuel-tank bunds and tank-to-foundation interfaces associated with Gas 1 Tanks C and D and OCGT Tanks A and B;
d. inspection, flushing, cleaning and re-inspection of underground clean and dirty stormwater drainage systems;
e. extension of the existing berm and reinstatement of eroded areas adjacent to the Gourikwa dams;
f. construction of the hazardous-waste skip containment area; and
g. all related work described in the Works Information.

	11.2(14)
	The following matters will be included in the Risk Register
	

1. Staged access, operational release and dewatering of the Gourikwa Clean Water Dam and Dirty Water Dam and other affected work areas. 
2. Concealed or additional defects revealed following dewatering, cleaning, exposure or detailed condition assessment. 
3. Hydrocarbon-contaminated water, sludge and other contaminated or hazardous material, including classification, temporary containment, handling, transport and lawful disposal. 
4. Interfaces with Gourikwa Power Station operations, existing Plant and Others. 
5. Site access, security, induction, permits, isolations and work-area release requirements. 
6. Environmental risks associated with loss of containment, contaminated water, hydrocarbons and construction activities. 
7. Availability and sequencing of the Clean Water Dam, Dirty Water Dam, fuel-containment areas, stormwater drainage systems, berm work area and hazardous-waste containment work area. 
8. Existing ground conditions and founding conditions applicable to the hazardous-waste skip containment area. 
9. Weather and erosion risks affecting the berm extension and reinstatement of eroded areas. 
10. Interfaces associated with the operation, placement and removal of hazardous-waste skips during construction and after Completion

	11.2(15)
	The boundaries of the site are 
	The areas within Gourikwa Power Station identified in Part C3: Works Information and Part C4: Site Information, including the Clean Water Dam, Dirty Water Dam, associated fuel-containment areas, stormwater drainage infrastructure, berm and erosion-repair areas and hazardous-waste skip containment work area applicable to the works

	11.2(16)
	The Site Information is in 
	Part C4: Site Information

	11.2(19)
	The Works Information is in  
	Part C3: Scope of Work and all documents and drawings to which it makes reference.

	12.2
	The law of the contract is the law of 
	the Republic of South Africa

	13.1
	The language of this contract is 
	English

	13.3
	The period for reply is
	Two (2) weeks

	[bookmark: _Toc238537835][bookmark: _Toc240874366]2
	[bookmark: _Toc238537836][bookmark: _Toc240874367]The Contractor's main responsibilities
	Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. 

	[bookmark: _Toc238537837][bookmark: _Toc240874368]3
	[bookmark: _Toc238537838][bookmark: _Toc240874369]Time
	

	11.2(3)
	The completion date for the whole of the works is
	
30 September 2028

	11.2(9)
	The key dates and the conditions to be met are:
	Condition to be met
	key date

	
	
	1
	None
	-

	30.1
	The access dates are:
	Part of the Site
	Date

	[bookmark: OLE_LINK1][bookmark: OLE_LINK2]
	
	1
	Gourikwa Power Station, including the Clean Water Dam, Dirty Water Dam, fuel-containment areas, associated stormwater infrastructure, berm/erosion work area and hazardous-waste skip containment work area
	the starting date , subject to the operational release of the applicable work area

	31.1
	The Contractor is to submit a first programme for acceptance within 
	
Two (2) weeks of the Contract Date.

	31.2
	The starting date is
	01 April 2027

	32.2
	The Contractor submits revised programmes at intervals no longer than 
	
Four (4) weeks.

	35.1
	The Employer is not willing to take over a Section before the Completion Date for that Section.
	


[bookmark: _Toc238537839][bookmark: _Toc240874370]

	4
	[bookmark: _Toc238537840][bookmark: _Toc240874371]Testing and Defects
	

	42.2
	The defects date is 
	52 weeks after Completion of the whole of the works.

	43.2
	The defect correction period is 
	Two (2) weeks

	
	except that the defect correction period for 
	One (1) day for a Defect creating an immediate:

· safety risk;
· environmental pollution risk;
· loss-of-containment risk; or
· uncontrolled discharge risk

	
	and the defect correction period for 
	One (1) week for a Defect preventing the safe operation or intended use of:

· the Clean Water Dam;
· the Dirty Water Dam;
· a fuel-containment area;
· a tank-to-foundation interface;
· a stormwater drainage system;
· the berm or erosion-control works; or
· the hazardous-waste skip containment area.

	[bookmark: _Toc238537841][bookmark: _Toc240874372]5
	[bookmark: _Toc238537842][bookmark: _Toc240874373]Payment
	

	50.1
	The assessment interval is 
	between the 25th day of each successive month. ( One (1) month)

	51.1
	The currency of this contract is the 
	South African Rand.

	51.2
	The period within which payments are made is 
	
Four (4) weeks.

	51.4
	The interest rate is 
	the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and 

(ii) the LIBOR rate applicable at the time for amounts due in other currencies.  LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove.

	[bookmark: _Toc238537843][bookmark: _Toc240874374]6
	[bookmark: _Toc238537844][bookmark: _Toc240874375]Compensation events
	

	60.1(13)
	The place where weather is to be recorded is:
	Gourikwa Power Station, Mossel Bay, Western Cape.

	
	The weather measurements to be recorded for each calendar month are, 
	
the cumulative rainfall (mm)

	
	
	the number of days with rainfall more than 10 mm

	
	
	the number of days with minimum air temperature less than 0 degrees Celsius

	
	
	the number of days with snow lying at 09:00 hours South African Time

	
	
	and these measurements:

	
	The weather measurements are supplied by
	the Contractor using official data obtained from the South African Weather Service.

	
	The weather data are the records of past weather measurements for each calendar month which were recorded at: 
	The South African Weather Service weather station nearest to Gourikwa Power Station which provides the measurements stated above and for which sufficient historical records are available to determine the frequency required by clause 60.1(13).

	
	and which are available from: 
	the South African Weather Bureau

	60.1(13)

	Assumed values for the ten year return weather data for each weather measurement for each calendar month are:
	Not applicable. Historical weather records available from the South African Weather Service are used for the assessment of weather under clause 60.1(13).



	[bookmark: _Toc238537845][bookmark: _Toc240874376]7
	[bookmark: _Toc238537846][bookmark: _Toc240874377]Title
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	[bookmark: _Toc238537847][bookmark: _Toc240874378]8
	[bookmark: _Toc238537848][bookmark: _Toc240874379]Risks and insurance
	

	80.1
	These are additional Employer's risks  
	1. None

	[bookmark: _Toc238537849][bookmark: _Toc240874380]9
	[bookmark: _Toc238537850][bookmark: _Toc240874381]Termination
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	[bookmark: _Toc238537851][bookmark: _Toc240874382]10
	[bookmark: _Toc238537852][bookmark: _Toc240874383]Data for main Option clause
	

	B
	Priced contract with bill of quantities
	

	60.6
	The method of measurement is 
	the Civil Engineering Standard Method of Measurement, Third Edition (CESMM3), published by the Institution of Civil Engineers and amended as stated in Part C2.1, Pricing Assumptions.

	[bookmark: _Toc238537853][bookmark: _Toc240874384]11
	[bookmark: _Toc238537854][bookmark: _Toc240874385]Data for Option W1
	

	W1.1
	The Adjudicator is 
	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him.  (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA).

	W1.2(3)
	The Adjudicator nominating body is:
	the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body.

	W1.4(2)
	The tribunal is: 
	arbitration.

	W1.4(5)
	The arbitration procedure is 
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	
	The place where arbitration is to be held is
	Cape Town, South Africa

	
	The person or organisation who will choose an arbitrator 
· if the Parties cannot agree a choice or
· if the arbitration procedure does not state who selects an arbitrator, is
	

the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.

	[bookmark: _Toc238537855][bookmark: _Toc240874386]12
	[bookmark: _Toc238537856][bookmark: _Toc240874387]Data for secondary Option clauses
	

	X1
	Price adjustment for inflation
	

	X1.1(a)
	The base date for indices is 
	Base date Indices are the month before the tender closing dat.

	X1.1(c)
	The proportions used to calculate the Price Adjustment Factor are:
	
proportion
	
linked to index for
	
Index prepared by
	

	
	
	0.85%
	Table D4 - CPI
	SEIFSA
	

	
	
	0.15%
	non-adjustable
	
	

	
	
	1.00
	
	
	

	X2
	Changes in the law
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.
	
	

	X15
	Limitation of the Contractor's liability for his design to reasonable skill and care
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.

	X16
	Retention
	

	X16.1
	The retention free amount is 
	R0.

	
	The retention percentage is
	5%

	Z
	The Additional conditions of contract are
	
Z1 to Z15 always apply.

	
	

	Z1
	Cession delegation and assignment

	Z1.1
	The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer.

	Z1.2
	Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. 

	
	

	Z2
	Joint ventures

	Z2.1
	If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract.

	Z2.2
	Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf.

	Z2.3
	The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing.

	
	

	Z3
	Change of Broad Based Black Economic Empowerment (B-BBEE) status

	Z3.1
	Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change.

	Z3.2
	The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager.

	Z3.3
	Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works.

	Z3.4
	Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93.

	
	

	Z4
	Confidentiality

	Z4.1
	The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time).  Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient.

	Z4.2
	If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager.

	Z4.3
	In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure.  In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed.

	Z4.4
	The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager.  All rights in and to all such images vests exclusively in the Employer.  

	Z4.5
	The Contractor ensures that all his subcontractors abide by the undertakings in this clause.

	
	

	Z5
	Waiver and estoppel: Add to core clause 12.3:

	Z5.1
	Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing.

	
	

	Z6
	Health, safety and the environment:  Add to core clause 27.4

	Z6.1
	The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor:
accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site;
warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and
undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	Z6.2
	The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	
	

	Z7
	Provision of a Tax Invoice and interest.  Add to core clause 51

	Z7.1
	Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate.

	Z7.2
	If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice.  Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made.

	Z7.3
	The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment.

	
	

	Z8
	Notifying compensation events

	Z8.1
	Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”.

	
	

	[bookmark: OLE_LINK5][bookmark: OLE_LINK6]Z9
	Employer’s limitation of liability

	Z9.1
	The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand)

	Z9.2
	The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited.

	
	

	Z10
	Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it":  

	Z10.1
	   or had a business rescue order granted against it.

	
	

	Z11
	Addition to secondary Option X7 Delay damages (if applicable in this contract)

	Z11.1
	If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table.

	
	



	Z12
	Ethics

	For the purposes of this Z-clause, the following definitions apply:

	Affected Party
	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

	Coercive Action
	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

	Collusive Action
	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

	Committing Party
	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees,

	Corrupt Action
	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

	Fraudulent Action
	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

	Obstructive Action
	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and

	Prohibited Action
	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

	Z12.1
	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

	Z12.2
	The Employer may terminate the Contractor’s obligation to Provide the Works if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Works for this reason.

	Z12.3
	If the Employer terminates the Contractor’s obligation to Provide the Works for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

	Z12.4
	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

	
	

	Z13
	Insurance

	Z 13.1
	Replace core clause 84 with the following:



	Insurance cover
	84
	

	
	
	

	
	84.1
	When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force.

	
	
	

	
	84.2
	The Contractor provides the insurances stated in the Insurance Table A.

	
	
	

	
	84.3
	The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate.

	
	
	

	
	
	[bookmark: _Toc238537857][bookmark: _Toc240874388]INSURANCE TABLE A
	Insurance against
	Minimum amount of cover or minimum limit of indemnity

	Loss of or damage to the works, Plant and Materials
	The replacement cost where not covered by the Employer’s insurance

The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance

	Loss of or damage to Equipment
	The replacement cost

	Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract
	Loss of or damage to property
Employer’s property
The replacement cost where not covered by the Employer’s insurance

The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance

Other property
The replacement cost

Bodily injury to or death of a person 
The amount required by applicable law

	Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract
	The amount required by the applicable law

	Liability arising from any negligent act, error or omission in the Contractor’s design, design-related advice, calculations, specifications, drawings, methodologies, technical submissions or other professional services provided in connection with the works, including design undertaken by Subcontractors and consultants appointed by the Contractor.
	R10 000 000 for any one claim and in the aggregate during any one period of insurance. The insurance is maintained from before the Contractor or any of its Subcontractors commences design until five years after Completion of the whole of the works. The retroactive date is no later than the date on which the Contractor or its Subcontractor first undertakes design for the works. Any deductible or excess is borne by the Contractor.




	
	
	

	Z 13.2
	
	Replace core clause 87 with the following:
The Employer provides the insurances stated in the Insurance Table B.

	
	
	

	
	
	

	
	
	

	
	
	INSURANCE TABLE B
	Insurance against or name of policy
	Minimum amount of cover or minimum limit of indemnity

	Assets All Risk
	Per the insurance policy document

	Contract Works insurance
	Per the insurance policy document

	Environmental Liability
	Per the insurance policy document

	General and Public Liability
	Per the insurance policy document

	Transportation (Marine)
	Per the insurance policy document

	Motor Fleet and Mobile Plant
	Per the insurance policy document

	Terrorism
	Per the insurance policy document

	Cyber Liability
	Per the insurance policy document

	Nuclear Material Damage and Business Interruption
	Per the insurance policy document

	Nuclear Material Damage Terrorism
	Per the insurance policy document






	Z14
	Intellectual Property – Eskom owning Intellectual Property

	“Intellectual Property”
	means (a) patents, trade marks, service marks, rights in designs, trade names, trade secrets, know how, copyrights and topography rights, in each case whether registered or not; (b) applications for registration of any of them; (c) rights under licences and consents in relation to any of them; (d) all forms of protection of a similar nature or having equivalent or similar effect to any of them which may subsist anywhere in the world.

	“Background Intellectual Property"
	means any and all Intellectual Property rights that are not Foreground Intellectual Property, and are owned or controlled by the relevant party or licensed to the relevant party prior to or outside of the works but required for the purposes of the works.

	“Foreground Intellectual Property”
	means all Intellectual Property rights and other matter capable of being the subject of intellectual property rights that is conceived, first reduced to practice or writing or developed in whole or in substantial part in the course of the execution of the works  and rights which are developed substantially as a result of the works.  Any works that will be developed, changed, modified and/or improved specifically for the Purposes will be Foreground Intellectual Property.  Any data or any other information relating to Employer’s proprietary information generated from the use of the Contractor’s Background Intellectual Property.

	Z14.1
	The Contractor retains ownership of all Background Intellectual Property rights made by or on behalf of the Contractor as part of the works in information or material it uses in carrying out the works.

	Z14.2
	All Foreground Intellectual Property rights, contained in any developed materials which are created by the Contractor or on behalf of the Contractor, for the purposes of and in support of the execution of the works (Employer’s IP) vest with the Employer.  

	Z14.3
	Any data or any other information relating to Employer’s proprietary information generated from the use of the Contractor’s Background Intellectual Property, the copyright therein shall be owned by the Employer.

	Z14.4
	The Contractor acknowledges that all rights, title, and interest in and to the Foreground Intellectual Property that may result or originate from or be developed in execution of the works vests in the Employer and that the Contractor has no claim of any nature in and to the Foreground Intellectual Property.  

	Z14.5
	The Contractor ensures that a copyright notice is incorporated or embossed or labelled on the Foreground Intellectual Property, where the Employer is reflected as the owner of the Foreground Intellectual Property.  

	Z14.6
	The Contractor is obliged to provide Foreground Intellectual Property manufacturing documents, designs, processes and/or specifications to the Employer before/on the Completion date.

	Z14.7
	The Contractor procures that each Sub-Contractor executes all and any works, and takes all and any other actions as may be required, in order to give effect to this Agreement.

	Z14.8
	The Employer retains all Background Intellectual Property rights in all documents made by or on behalf of the Employer including all documents and requirements provided prior to or during the execution of the works.  The Contractor does not, without the written consent, of the Employer, copy, use or issue to a third party any of the Employer’s Background Intellectual Property documents and requirements except for the purposes of executing the works.

	Z14.9
	Either party procures that any third party executes confidentiality undertakings not to disclose to any other third parties, any of the Employer’s Background Intellectual Property and IP documents and requirements at all, in respect of the Employer, or the Background Intellectual Property, in respect of the Contractor.

	
	

	Z14.10
	Third Party Claims:

	Z14.10.1
	In the event of any claims being made or actions brought against the Employer, on the ground that the Contractor infringed any patent, trade mark or copyright, the Contractor is notified thereof and at its own expense, conducts all negotiations in consultation with the Employer for the settlement of the claim and litigation that may arise from such alleged infringement, provided that the Employer will not bear any financial burden or losses.

	Z14.10.2
	Save where the Contractor fails to take over the conduct of the negotiation or litigation within a reasonable time of the notification of the alleged infringement, the Employer does not make any admission which might be prejudicial to the Contractor’s position. The Employer, at the request and the cost of the Contractor affords it all reasonable technical assistance that the Employer is able to provide for the purpose of contesting any such claim or action.

	Z14.10.3
	Should it be held in any such action that any such protected rights have been infringed, as definitely stated by a judgment of the court before which the action is brought, the Contractor, at its own expense and in consultation with the Employer, either:
a. procures for Employer the right to continue to use the affected item or design, or
b. replaces the said affected item or design with a non-infringing item, or
c. provides a design of equivalent quality or modify such affected item or design so as to make it non-infringing without affecting the quality.

	Z14.10.4
	Notwithstanding anything contained in this contract, the foregoing sets forth the entire responsibility of Contractor with respect to claims relating to infringement.

	Z14.10.5
	Where it is alleged that the Employer has committed an infringement as intended vis-à-vis the Contractor as set out in the third party intellectual property infringement clause, the Employer has the same rights and obligations as the Contractor, mutatis mutandis, as regards such alleged infringement.

	Z14.10.6
	The Contractor herewith indemnifies the Employer and undertakes to keep the Employer indemnified against all claims of whatsoever nature, real or imagined, which may be made against the Employer arising from the infringement of any third party intellectual property rights.

	
	

	Z15
	Asbestos

	For the purposes of this Z-clause, the following definitions apply:

	AAIA
	means approved asbestos inspection authority.

	ACM
	means asbestos containing materials.

	AL
	means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL.

	Ambient Air
	means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet.

	Compliance Monitoring
	means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	OEL
	means occupational exposure limit.

	Parallel Measurements
	means measurements performed in parallel, yet separately, to existing measurements to verify validity of results.

	Safe Levels
	means  airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	Standard
	means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles.

	SANAS
	means the South African National Accreditation System.

	TWA
	means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA.

	Z15.1
	The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Works conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM.

	Z15.2
	Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan.

	Z15.3
	The Employer manages asbestos and ACM according to the Standard.

	Z15.4
	In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe.

	Z15.5
	The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable.

	Z15.6
	The Contractor continues to Provide the Works, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Works, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001.

	Z15.7
	Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation.
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[bookmark: _Toc238537858][bookmark: _Toc240874389]Part two - Data provided by the Contractor


Notes to a tendering contractor:

1. Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN)[footnoteRef:2] in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes. [2:  Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za ] 

2. The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data
3. [bookmark: Text530]Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

	[bookmark: _Toc238537859][bookmark: _Toc240874390]Clause
	[bookmark: _Toc238537860][bookmark: _Toc240874391]Statement
	[bookmark: _Toc238537861][bookmark: _Toc240874392]Data

	10.1
	The Contractor is (Name):
	[bookmark: Text531]     

	
	Address
	[bookmark: Text532]     

	
	Tel No.
	[bookmark: Text533]     

	
	Fax No.
	[bookmark: Text534]     

	11.2(8)
	The direct fee percentage is
	     %

	
	The subcontracted fee percentage is
	[bookmark: Text434]     %

	11.2(18)
	The working areas are the Site and
	[bookmark: Text526]     

	24.1
	The Contractor's key persons are:
	

	
	1	Name:
	[bookmark: Text527]     

	
		Job:
	     

	
		Responsibilities:
	     

	
		Qualifications:
	[bookmark: Text366]     

	
		Experience:
	[bookmark: Text367]     

	
	2	Name:
	     

	
		Job
	     

	
		Responsibilities:
	     

	
		Qualifications:
	     

	
		Experience:
	     

	
	
	[bookmark: Text529]CV's (and further key persons data including CVs) are appended to Tender Schedule entitled     .

	11.2(3)
	The completion date for the whole of the works is
	
[bookmark: Text370]     

	11.2(14)
	The following matters will be included in the Risk Register
	
[bookmark: Text435]     

	11.2(19)
	The Works Information for the Contractor’s design is in:
	
[bookmark: Text368]     

	31.1
	The programme identified in the Contract Data is
	
[bookmark: Text369]     

	B
	Priced contract with bill of quantities
	

	11.2(21)
	The bill of quantities is in
	[bookmark: Text372]     

	11.2(31) 
	The tendered total of the Prices is 
	[bookmark: Text212]      (in figures) 

[bookmark: Text284]      (in words), excluding VAT 

	
	[bookmark: _Toc238537862][bookmark: _Toc240874393]Data for Schedules of Cost Components
	Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013).

	B
	Priced contract with bill of quantities
	Data for the Shorter Schedule of Cost Components

	41 in SSCC
	The percentage for people overheads is:
	[bookmark: Text377]     %

	21 in SSCC
	The published list of Equipment is the last edition of the list published by
	
[bookmark: Text378]     

	
	The percentage for adjustment for Equipment in the published list is
	
[bookmark: Text379]Minus      %

	22 in SSCC
	The rates of other Equipment are:
	Equipment
	Size or capacity
	Rate

	
	
	[bookmark: Text535]     
	     
	     

	
	
	[bookmark: Text536]     
	     
	     

	
	
	[bookmark: Text537]     
	     
	     

	
	
	[bookmark: Text538]     
	     
	     

	
	
	[bookmark: Text539]     
	     
	     

	61 in SSCC
	The hourly rates for Defined Cost of design outside the Working Areas are
	
Category of employee
	
Hourly rate

	
	Note:  Hourly rates are estimated ‘cost to company of the employee’ and not selling rates.  
	     
	     

	
	Please insert another schedule if foreign resources may also be used
	     
	     

	
	
	     
	     

	
	
	     
	     

	62 in SSCC
	The percentage for design overheads is
	     %

	63 in SSCC
	The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are:
	


[bookmark: Text374]     
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Pro formas for Bonds & Guarantees

For use with the NEC3 Engineering & Construction Contract 



The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:


Option X16:	Retention 

The Contractor may provide a Retention Money Guarantee in the form stated here.  When the Employer receives and accepts a Retention Money Guarantee exactly in the form stated he will instruct the Project Manager not to assess any amount be retained in terms of secondary Option X16.


The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.  




[bookmark: _Toc238537863][bookmark: _Toc240874394]Pro forma Retention Money Guarantee (may be used when Option X16 applies)
(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

	Eskom Holdings SOC Limited
Megawatt Park
Maxwell Drive
Sandton
Johannesburg 
	



Date:
	



Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]

1. [bookmark: _Toc238537864][bookmark: _Toc240874395]In this Guarantee the following words and expressions shall have the following meanings:-

1.1 “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

1.2 “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

1.3 “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

1.4 “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

1.5 “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30

1.6 “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

1.7 “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

1.8 “Project” - means the…………………………………..

2. [bookmark: _Toc238537865][bookmark: _Toc240874396]At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

3. [bookmark: _Toc238537866][bookmark: _Toc240874397]A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

3.1 be signed on behalf of Eskom by a director of Eskom or his authorised delegate.

3.2 state the amount claimed (“the Demand Amount’);

3.3 state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

4. [bookmark: _Toc238537867][bookmark: _Toc240874398]Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

4.1 is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

4.2 is not, and shall not be construed to be, accessory or collateral on any basis whatsoever. 

5. [bookmark: _Toc238537868][bookmark: _Toc240874399]The Bank’s obligations in terms of this Guarantee:

5.1 shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

5.2 shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

6. [bookmark: _Toc238537869][bookmark: _Toc240874400]Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract. 

7. [bookmark: _Toc238537870][bookmark: _Toc240874401]Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

8. [bookmark: _Toc238537871][bookmark: _Toc240874402]This Guarantee:

8.1 shall expire on the Expiry Date until which time it is irrevocable;

8.2 is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

8.3 shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

8.4 shall be regarded as a liquid document for the purpose of obtaining a court order; and

8.5 shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

8.6 Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

9. [bookmark: _Toc238537872][bookmark: _Toc240874403]The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________  Bank’s seal or stamp

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

PART C1.3	PAGE 2 OF 2 	FORMS OF SECURITIES
[bookmark: _Toc238537873][bookmark: _Toc240874404]Part 2: Pricing Data
ECC3 Option B










	Document reference
	Title
	No of pages

	C2.1
	Pricing assumptions: Option B
	     

	C2.2
	The bill of quantities
	     









PART C2	PAGE 41 OF 106 	PRICING DATA OPTION B
C2.1 Pricing assumptions: Option B

[bookmark: _Toc238537874][bookmark: _Toc240874405]How work is priced and assessed for payment
Clause 11 in NEC3 Engineering and Construction Contract (ECC3) Option B states:

	Identified and defined terms
	11
11.2
	
(21) The Bill of Quantities is the bill of quantities as changed in accordance with this contract to accommodate implemented compensation events and for accepted quotations for acceleration.


	
	
	(28) The Price for Work Done to Date is the total of 

the quantity of the work which the Contractor has completed for each item in the Bill of Quantities multiplied by the rate and
a proportion of each lump sum which is the proportion of the work covered by the item which the Contractor has completed.

Completed work is work without Defects which would either delay or be covered by immediately following work.


	
	
	(31) The Prices are the lump sums and the amounts obtained by multiplying the rates by the quantities for the items in the Bill of Quantities.




This confirms that Option B is a re-measurement contract and the bill comprises only items measured using quantities and rates or stated as lump sums.  Value related items are not used.  Time related items are items measured using rates where the rate is a unit of time.
[bookmark: _Toc238537875][bookmark: _Toc240874406]Function of the Bill of Quantities
Clause 55.1 in Option B states, “Information in the Bill of Quantities is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Bill, but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Bill of Quantities.  The Bill of Quantities is only a pricing document.  
[bookmark: _Toc238537876][bookmark: _Toc240874407]Guidance before pricing and measuring
Employers preparing tenders or contract documents, and tendering contractors are advised to consult the sections dealing with the bill of quantities in the NEC3 Engineering and Construction Contract Guidance Notes before preparing the bill of quantities or before entering rates and lump sums into the bill. 

There is no general provision in Option B for payment for materials on Site before incorporation into the works.  If secondary Option X14 Advanced payment has not been used then the tendering contractor may obtain the same effect by inserting appropriate items in the method related charges where the method of measurement allows, or alternatively making allowance in the rates of the bill of quantities for the financing of Plant and Materials until they are incorporated in the works.

When compensation events arise, the default position is that the Bill of Quantities is not used to calculate the cost effect of the event.  Defined Cost and the resulting Fee is used and Defined Cost includes all components of cost which the Contractor is likely to incur, including so called P & G items.  Rates and lump sums from the Bill of Quantities, or from any other source, may be used instead of Defined Cost and the Fee only if the Contractor and Project Manager agree.  If they are unable to agree, then Defined Cost plus Fee is used.   
[bookmark: _Toc238537877][bookmark: _Toc240874408]Measurement and payment
[bookmark: _Toc238537878][bookmark: _Toc240874409]Symbols
The units of measurement described in the Bill of Quantities are metric units abbreviated as follows:
[add or delete as required] 

	Abbreviation
	Unit

	%
	Percent

	h
	Hour

	ha
	Hectare

	kg
	Kilogram

	kl
	Kilolitre

	km
	Kilometre

	km-pass
	kilometre-pass

	kPa
	Kilopascal

	kW
	Kilowatt

	l
	Litre

	m
	Metre

	mm
	Millimetre

	m2
	square metre

	m2-pass
	square metre pass

	m3
	cubic metre

	m3-km
	cubic metre-kilometre

	MN
	Meganewton

	MN.m
	meganewton-metre

	MPa
	Megapascal

	No.
	Number

	sum
	Lump sum

	t
	tonne (1000kg)



[bookmark: _Toc238537879][bookmark: _Toc240874410]General assumptions
[bookmark: _Toc238537880][bookmark: _Toc240874411]Unless otherwise stated, items are measured net in accordance with the drawings, and no allowance has been made in the quantities for waste.
[bookmark: _Toc238537881][bookmark: _Toc240874412]The Prices and rates stated for each item in the Bill of Quantities shall be treated as being fully inclusive of all work, risks, liabilities, obligations, overheads, profit and everything necessary as incurred or required by the Contractor in carrying out or providing that item.    
[bookmark: _Toc238537882][bookmark: _Toc240874413]An item against which no Price is entered will be treated as covered by other Prices or rates in the bill of quantities.  
[bookmark: _Toc238537883][bookmark: _Toc240874414]The quantities contained in the Bill of Quantities may not be final and do not necessarily represent the actual amount of work to be done.  The quantities of work assessed and certified for payment by the Project Manager at each assessment date will be used for determining payments due.
[bookmark: _Toc238537884][bookmark: _Toc240874415]The short descriptions of the items of payment given in the bill of quantities are only for the purposes of identifying the items.  Detail regarding the extent of the work entailed under each item is provided in the Works Information.

[bookmark: _Toc238537885][bookmark: _Toc240874416]Departures from the method of measurementOnly use this section if the statement for Option B in the Contract Data, “The method of measurement is ________ amended as follows” refers the reader to this section rather than include the amendments within the Contract Data statement.  Otherwise delete this heading.  In any case delete this note when complied with. 
[bookmark: _Toc238537886][bookmark: _Toc240874417]Amplification of or assumptions about measurement items
The following is provided to assist in the interpretation of descriptions given in the method of measurement.  In the event of any ambiguity or inconsistency between the statements in the method of measurement and this section, the interpretation given in this section shall be used. 
Unless otherwise stated in the Bill of Quantities, rates and Prices include all labour, Plant and Materials, Contractor’s Equipment, temporary works, access arrangements, protection, preparation, handling, storage, transport, supervision, quality control, testing, curing, waste handling, disposal, reinstatement and all other work necessary to complete the relevant item in accordance with the Works Information.
Quantities are remeasured from the actual work completed in accordance with CESMM3 and the measurement descriptions stated in the Bill of Quantities. Rate-only items are used only where the applicable work is required and instructed or otherwise becomes measurable in accordance with the contract.
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C2.2 the bill of quantities


	Item No.
	Description
	Unit
	Quantity
	Rate (R)
	Amount (R)

	1. PRELIMINARY AND GENERAL – OVERALL WORKS

	1.1 Scheduled fixed-charge items

	1.1.1
	Contractual requirements and contract administration for the whole of the works.
	Sum
	1
	
	

	
	
	
	
	
	

	1.1.2
	Mobilisation and Site establishment for the whole of the works, including establishment as required by the Accepted Programme
	Sum
	1
	
	

	1.1.3
	Setting out of the works
	Item
	1
	
	

	1.1.4
	Health and safety fixed obligations, including initial plans, risk assessments, statutory appointments, safe work procedures, PPE and health and safety file requirements
	


Sum
	


1
	
	

	
	
	
	
	
	

	1.1.5
	Environmental compliance fixed obligations, including initial Environmental Management Plan and activity-specific environmental planning
	Sum
	1
	
	

	
	
	
	
	
	

	1.1.6
	Quality management fixed obligations, including initial Quality Plan, QCP/ITP preparation and document-control setup
	Sum
	1
	
	

	
	
	
	
	
	

	1.1.7
	Final de-establishment, removal of temporary facilities and reinstatement of all work and establishment areas
	Sum
	1
	
	

	1.2 Scheduled time-related items – quantity to equal the overall contract duration stated in the Contract Data

	1.2.1
	Contractual requirements and contract administration – time related
	Month
	18
	
	

	1.2.2
	Contractor facilities and temporary services required for the whole of the works, including offices, storage, welfare facilities, temporary water and power arrangements, communications and access facilities – time related
	Month
	18
	
	

	
	
	
	
	
	

	1.2.3
	Contract management and supervision for the whole of the works, including sufficient supervision at simultaneously active work areas at Gourikwa Power Station
	Month
	18
	
	

	
	
	
	
	
	

	1.2.4
	Transport, accommodation, mobilisation and logistics for Contractor personnel, Plant, Materials and Contractor’s Equipment required for the works at Gourikwa Power Station
	Month
	18
	
	

	
	
	
	
	
	

	1.2.5
	Security of Contractor's Plant, Materials, Equipment and personnel – time related
	Month
	18
	
	

	
	
	
	
	
	

	1.2.6
	Quality management and document control – time related
	Month
	18
	
	

	
	
	
	
	
	

	1.2.7
	Health and safety compliance – time related
	Month
	18
	
	

	
	
	
	
	
	

	1.2.8
	Environmental compliance – time related
	Month
	18
	
	

	P&G SUBTOTAL	 R

	2. GOURIKWA – BERM EXTENSION AND EROSION REPAIRS

	2.1
	Clear vegetation, rubbish, debris and brush from the berm/erosion work area
	m²
	250
	
	

	
	
	
	
	
	

	2.2
	Strip, preserve, re-spread and lightly compact topsoil to the berm and erosion-repair areas as required by the Works Information
	m²
	250
	
	

	
	
	
	
	
	

	2.3
	Reuse suitable excavated material in berm/landscape filling
	m³
	20
	
	

	
	
	
	
	
	

	2.4
	Supply and place G5 gravel material in berm works and compact as required by the Works Information
	m³
	60
	
	

	
	
	
	
	
	

	2.5
	Supply and place selected clay material and compact to at least 93% Mod AASHTO
	m³
	15
	
	

	
	
	
	
	
	

	2.6
	Compact natural or excavated ground surfaces
	m²
	300
	
	

	
	
	
	
	
	

	2.7
	Modified AASHTO density/compaction tests
	No
	18
	
	

	
	
	
	
	
	

	2.8
	Establish accepted local indigenous vegetation by hand seeding or approved equivalent method
	m²
	250
	
	

	
	
	
	
	
	

	2.9
	Provide and install erosion blankets or equivalent temporary erosion-control measures
	m²
	250
	
	

	
	
	
	
	
	

	2.10
	Maintain landscaping and erosion-control works for three months until vegetation is established
	Item
	1
	
	

	3. GOURIKWA – DAMS: DEWATERING, ASSESSMENT AND CLEANING

	3.1
	Bulk dewatering of the Gourikwa Clean Water Dam after operational release, including temporary pumping, hoses, tanks/transfer arrangements and residual-water control
	No
	1
	
	

	
	
	
	
	
	

	3.2
	Bulk dewatering of the Gourikwa Dirty Water Dam after operational release, including temporary pumping, hoses, tanks/transfer arrangements and residual-water control
	No
	1
	
	

	
	
	
	
	
	

	3.3
	Detailed condition assessment, measurement, photographs and Defect Mapping – Clean Water Dam, excluding separately measured NDT
	No
	1
	
	

	
	
	
	
	
	

	3.4
	Detailed condition assessment, measurement, photographs and Defect Mapping – Dirty Water Dam, excluding separately measured NDT
	No
	1
	
	

	
	
	
	
	
	

	3.5
	Non-destructive testing of Gourikwa dam concrete using the methods required by the Works Information
	No
	2
	
	

	
	
	
	
	
	

	3.6
	Condition-assessment report and proposed remedial measures – Clean Water Dam, professionally signed as required
	Item
	1
	
	

	
	
	
	
	
	

	3.7
	Condition-assessment report and proposed remedial measures – Dirty Water Dam, professionally signed as required
	Item
	1
	
	

	
	
	
	
	
	

	3.8
	Controlled cleaning and degreasing of Gourikwa Clean Water Dam internal surfaces
	m²
	3520
	
	

	
	
	
	
	
	

	3.9
	Controlled cleaning and degreasing of Gourikwa Dirty Water Dam internal surfaces
	m²
	5000
	
	

	
	
	
	
	
	

	3.10
	Unblock subsoil drainage sump or associated drainage blockage identified during the condition assessment, including removal and lawful management of removed material
	No
	Rate only
	
	

	4. GOURIKWA – CONCRETE, REINFORCEMENT AND CRACK REPAIRS TO DAMS

	4.1
	Remove defective or spalled concrete to sound substrate
	m²
	800
	
	

	
	
	
	
	
	

	4.2
	Clean and treat exposed reinforcement
	m²
	300
	
	

	
	
	
	
	
	

	4.3
	Replace defective or significantly section-loss reinforcement
	kg
	20
	
	

	
	
	
	
	
	

	4.4
	Apply accepted bonding system and polymer-modified/non-shrink structural repair mortar to prepared spalled areas
	m²
	800
	
	

	
	
	
	
	
	

	4.5
	Remove delaminated or deeply defective concrete to sound material
	m³
	20
	
	

	
	
	
	
	
	

	4.6
	Provide and place 30 MPa replacement concrete or accepted micro-concrete for deep repairs
	m³
	20
	
	

	
	
	
	
	
	

	4.7
	Additional reinforcement of various diameters for deep repairs
	kg
	100
	
	

	
	
	
	
	
	

	4.8
	Route/cut and prepare cracks to the accepted repair profile for flexible or mortar repair systems
	m
	1000
	
	

	
	
	
	
	
	

	4.9
	Replace defective reinforcement exposed during crack repairs
	kg
	20
	
	

	
	
	
	
	
	

	4.10
	Clean and treat reinforcement exposed during crack repairs
	m²
	200
	
	

	
	
	
	
	
	

	4.11
	on-shrink structural repair mortar specifically for routed/local crack repairs not measured under item 4.4 or 4.6
	m³
	20
	
	

	
	
	
	
	
	

	4.12
	Low-viscosity epoxy injection repair to non-moving cracks, including preparation, packers and injection
	m
	Rate only
	
	

	5. GOURIKWA – DAM JOINT, WATERSTOP AND SEALANT REPAIRS

	5.1
	Remove defective existing joint sealant and backing material from dam joints
	m
	6000
	
	

	
	
	
	
	
	

	5.2
	Remove and replace defective/displaced expansion board or compressible joint filler
	m
	6000
	
	

	
	
	
	
	
	

	5.3
	Grind and prepare joint substrates; remove oil, algae, biofilm and loose material
	m
	2000
	
	

	
	
	
	
	
	

	5.4
	Provide and install closed-cell backing rod or bond-breaker tape where required
	m
	800
	
	

	
	
	
	
	
	

	5.5
	Prime where required and install accepted elastomeric sealant system to prepared dam joints
	m
	6000
	
	

	
	
	
	
	
	

	5.6
	Replace compromised waterstops or joint tapes where required
	m
	650
	
	

	6. GOURIKWA – FUEL-TANK BUND JOINT REPAIRS: TANKS C, D, A AND B

	6.1
	Remove defective existing bund-joint sealant/backing and prepare joint faces
	m
	3000
	
	

	
	
	
	
	
	

	6.2
	Provide and install closed-cell backing rod or bond-breaker tape compatible with fuel-oil exposure
	m
	3000
	
	

	
	
	
	
	
	

	6.3
	Prime where required and install accepted fuel-resistant elastomeric sealant system to bund floor and wall joints
	m
	3000
	
	

	
	
	
	
	
	

	6.4
	Replace compromised waterstops or joint tapes in fuel-tank bunds where required
	m
	1000
	
	

	7. GOURIKWA – TANK-TO-FOUNDATION INTERFACE SEALING: TANKS C, D, A AND B

	7.1
	Inspect and remove existing annular sealant, debris and contaminants at tank-to-foundation interfaces
	m
	189.1
	
	

	
	
	
	
	
	

	7.2
	Mechanically/solvent clean steel and concrete substrates at tank-to-foundation interfaces
	m
	189.1
	
	

	
	
	
	
	
	

	7.3
	Provide bond breaker or backing material where required
	m
	189.1
	
	

	
	
	
	
	
	

	7.4
	Install accepted fuel-resistant elastomeric sealant and finish to a water-shedding profile
	m
	189.1
	
	

	8. GOURIKWA – UNDERGROUND STORMWATER DRAINAGE

	8.1
	Pre-cleaning non-intrusive condition assessment of underground clean and dirty stormwater drainage using cage-protected drone, camera system or another accepted method
	m
	5000
	
	

	
	
	
	
	
	

	8.2
	Pre-cleaning inspection report, route records, photographs and video deliverables
	Item
	1
	
	

	
	
	
	
	
	

	8.3
	Controlled flushing/cleaning of underground drains using high-pressure jetting, vacuum-assisted flushing or another accepted method, including collection and control of flushed material and wastewater
	m
	5000
	
	

	
	
	
	
	
	

	8.4
	Post-cleaning inspection of cleaned drainage sections
	m
	5000
	
	

	
	
	
	
	
	

	8.5
	Post-cleaning inspection report, route records, photographs and video deliverables
	Item
	1
	
	

	9. GOURIKWA – HAZARDOUS-WASTE SKIP CONTAINMENT AREA

	9.1
	Clear and grub the containment footprint
	m²
	27.09
	
	

	
	
	
	
	
	

	9.2
	Strip and remove topsoil to 150 mm depth
	m³
	4.0635
	
	

	
	
	
	
	
	

	9.3
	Excavate in earth to approximately 200 mm below NGL, subject to Employer drawing and verified Site levels
	m³
	5.418
	
	

	
	
	
	
	
	

	9.4
	Rip and recompact 150 mm of the founding layer
	m²
	27.09
	
	

	
	
	
	
	
	

	9.5
	Supply, place and compact G7 filling to at least 95% Mod AASHTO
	m³
	4.0635
	
	

	
	
	
	
	
	

	9.6
	Compaction testing of the prepared founding layer, including test reports demonstrating compliance with 95% Mod AASHTO.
	No
	2
	
	

	
	
	
	
	
	

	9.7
	Additional excavation and removal of unsuitable founding material where required
	m³
	Rate only
	
	

	
	
	
	
	
	

	9.8
	Additional G7 replacement material for unsuitable founding material where required
	m³
	Rate only
	
	

	
	
	
	
	
	

	9.9
	50 mm 10 MPa blinding concrete beneath slab where required
	m²
	27.09
	
	

	
	
	
	
	
	

	9.10
	30 MPa reinforced concrete in 200 mm containment slab
	m³
	5.418
	
	

	
	
	
	
	
	

	9.11
	Ref 617 reinforcement mesh to top and bottom layers of slab
	m²
	54.18
	
	

	
	
	
	
	
	

	9.12
	Finish slab to the required 1:100 falls toward the low-point sump
	m²
	27.09
	
	

	
	
	
	
	
	

	9.13
	Construct low-point sump and interfaces in accordance with the Employer drawing
	Item
	1
	
	

	
	
	
	
	
	

	9.14
	140 mm brick masonry bund wall
	m²
	8.112
	
	

	
	
	
	
	
	

	9.15
	Brick reinforcement to masonry bund wall
	m
	81.12
	
	

	
	
	
	
	
	

	9.16
	Steel dowels/wall ties fixed to reinforced-concrete slab
	No
	51
	
	

	
	
	
	
	
	

	9.17
	15–20 mm cement-sand plaster to internal bund-wall surfaces
	m²
	12.6504
	
	

	
	
	
	
	
	

	9.18
	Prepare internal slab and wall surfaces for chemical-resistant coating system
	m²
	33
	
	

	
	
	
	
	
	

	9.19
	Provide and apply accepted chemical-resistant epoxy coating system to internal slab and wall surfaces, minimum total DFT 500 microns, including primers and all coats required by the accepted system
	m²
	33
	
	

	
	
	
	
	
	

	9.20
	Concrete cube-strength testing and records for containment slab
	Item
	1
	
	

	
	
	
	
	
	

	9.21
	Coating DFT measurement, calibration evidence and compliance records
	Item
	1
	
	

	
	
	
	
	
	

	9.22
	Minimum 24-hour water-retention test and test record after coating cure
	Item
	1
	
	

	GOURIKWA SUBTOTAL	R

	10. RATE-ONLY ENVIRONMENTAL / WASTE ITEMS

	
	
	
	
	
	

	10.1
	Off-Site transport and lawful disposal of hazardous or hydrocarbon-contaminated solid waste arising at Gourikwa where required by the Works Information and not otherwise included in a measured item
	t
	Rate only
	
	

	
	
	
	
	
	

	TOTAL OF THE PRICES (EXCLUDING VAT)
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1 [bookmark: _Toc137798038][bookmark: _Toc229128241][bookmark: _Toc240874420]Description of the works
1.1 [bookmark: _Toc137798039][bookmark: _Toc229128242][bookmark: _Toc240874421]Executive overview
1 Gourikwa Power Station is located near Mossel Bay in the Western Cape and comprises five (5) diesel-fired open-cycle gas turbine units. Fuel is supplied to the Power Station through a dedicated pipeline from PetroSA.
2 The works comprise inspection, maintenance, remedial repair and construction works associated with the pollution-control dams, fuel-containment infrastructure, underground stormwater drainage systems, erosion-control works and hazardous-waste skip containment infrastructure at Gourikwa Power Station.
3 The principal works include:
a. detailed condition assessment of the Gourikwa Clean Water Dam and Dirty Water Dam after dewatering;
b. assessment and repair of concrete deterioration, including spalling, delamination, exposed reinforcement and cracking;
c. assessment and repair of joint movement, joint sealants, waterstops and expansion-joint components;
d. repair and replacement of joint sealants within the fuel-tank bunds;
e. replacement of sealant at the tank-to-foundation interfaces;
f. cleaning and degreasing of the Clean Water Dam and Dirty Water Dam;
g. inspection, flushing and cleaning of the underground clean and dirty stormwater drainage systems;
h. extension of the existing berm and reinstatement of erosion-damaged areas north of the Clean Water Dam; and
i. construction of a permanent impermeable hazardous-waste skip containment area.
4 The works apply to:
· Gourikwa Clean Water Dam, with an approximate surface area of 3 520 m²;
· Gourikwa Dirty Water Dam, with an approximate surface area of 5 000 m²;
· Gas 1 Tanks C and D and their associated bunds;
· OCGT Tanks A and B and their associated bunds;
· the associated underground clean and dirty stormwater drainage systems;
· the existing berm and erosion-affected areas north of the Clean Water Dam; and
· the hazardous-waste skip containment work area.
5 The Gourikwa fuel tanks and associated bunds applicable to the works are:
	Tank
	Diameter
	Bund size

	Gas 1 Tank C
	15 050 mm
	31 300 × 52 300 mm

	Gas 1 Tank D
	15 050 mm
	31 300 × 52 300 mm

	OCGT Tank A
	15 050 mm
	31 300 × 52 300 mm

	OCGT Tank B
	15 050 mm
	31 300 × 52 300 mm


6 The hazardous-waste skip containment area comprises a permanent impermeable secondary containment area designed to accommodate two 6 m³ hazardous-waste skips. The principal construction comprises a reinforced concrete slab, masonry bund walls, internal plaster, chemical-resistant epoxy coating and a low-point sump for controlled removal of accumulated liquid.
1.2 [bookmark: _Toc240874422]Employer’s objectives and purpose of the works
1 The Employer’s objective is to restore and maintain the structural integrity, watertightness, environmental containment and operational performance of the dirty-water management and fuel-containment infrastructure at Gourikwa Power Station. 
2 The works are intended to address deterioration of concrete structures, joint failures, drainage deficiencies and erosion identified during previous inspections and to restore the condition and functionality of the affected dams, bunds, drainage systems and associated civil infrastructure. 
3 At Gourikwa Power Station, dirty and treated water systems ultimately discharge to the surrounding environment. Effective containment, drainage and controlled operation are therefore required to reduce the risk of uncontrolled pollution and environmental non-compliance. 
4 The purpose of the works is to:
a. determine the condition of the Gourikwa Clean Water Dam and Dirty Water Dam following dewatering and detailed inspection;
b. identify, record and classify defects affecting the dams and associated concrete structures;
c. repair concrete deterioration, cracks, reinforcement defects, joints, waterstops and sealants identified within the scope;
d. restore the integrity of the fuel-tank bunds and tank-to-foundation sealing systems;
e. inspect, clean and restore the hydraulic capacity of the underground clean and dirty stormwater drainage systems;
f. extend the existing berm and reinstate erosion-damaged areas to reduce uncontrolled surface runoff entering the Clean Water Dam; and
g. provide a permanent impermeable hazardous-waste skip containment area to reduce the risk of soil contamination from oily or hazardous runoff
1.3 [bookmark: _Toc137798041][bookmark: _Toc229128244][bookmark: _Toc240874423]Interpretation and terminology
1 The defined terms in the conditions of contract and Contract Data have the meanings given to them in the NEC3 Engineering and Construction Contract.
2 The following abbreviations are used in this Works Information:
	Abbreviation
	Meaning given to the abbreviation

	AFC
	Approved for Construction

	AIA
	Approved Inspection Authority

	CoC
	Certificate of Compliance

	DWS
	Department of Water and Sanitation

	EMP
	Environmental Management Plan

	GRK
	Gourikwa Power Station

	H&S
	Health and Safety

	HIRA
	Hazard Identification and Risk Assessment

	HSE
	Health, Safety and Environment

	ITP
	Inspection and Test Plan

	MSDS
	Material Safety Data Sheet, where this terminology appears in existing documents

	NCR
	Non-conformance Report

	NDT
	Non-destructive Testing

	OCGT
	Open-cycle Gas Turbine

	OHS Act
	Occupational Health and Safety Act 85 of 1993, as amended

	O&M
	Operations and Maintenance

	PCD
	Pollution-control Dam

	PI
	Professional Indemnity

	PPE
	Personal Protective Equipment

	QA
	Quality Assurance

	QC
	Quality Control

	QCP
	Quality Control Plan

	RFI
	Request for Information

	SANS
	South African National Standard

	SDS
	Safety Data Sheet

	SHE
	Safety, Health and Environment

	SOW
	Scope of Work

	TDS
	Technical Data Sheet

	WIR
	Works Inspection Request

	WMS
	Work Method Statement



[bookmark: _Toc137798042][bookmark: _Toc229128245][bookmark: _Toc240874424]

2 Management and start up.
2.1 [bookmark: _Toc137798043][bookmark: _Toc229128246][bookmark: _Toc240874425]Management meetings
1 To support effective administration of the Contract, the Contractor attends and participates in management meetings convened by the Project Manager.
2 The purposes of management meetings are to:
a. coordinate progress and upcoming work,
b. review the Accepted programme, constraints and recovery actions,
c. manage risks, Early Warnings and (where applicable) compensation events,
d. coordinate site access requirements, permits and interfaces,
e. review quality planning, inspections/hold points and close-out deliverables,
f. confirm key contractual communication obligations.
3 The Contractor provides suitably experienced attendees with delegated authority to make decisions and commit resources as required.
4 Meeting records (minutes and/or an action register) are prepared by the person convening the meeting and circulated within five (5) Working Days. Meeting records do not substitute for formal notifications, instructions or other communications issued in accordance with Clause 13 of the Contract.
5 Meetings may be held on-site or via Microsoft Teams (or equivalent), depending on the nature of the discussion and the parties’ availability.
6 The Project Manager may convene additional meetings where required to address technical, programme-related, commercial or interface matters.
7 The following meetings may be convened (frequency adjusted by the Project Manager to suit the risk and stage of the Works):
2.1.1 [bookmark: _Toc240874426]Project kick-off meeting
Held before commencement of site works to confirm key people, communication routes, programme approach, access/permit constraints, sequencing expectations, quality requirements and key hold points:
	Interval 
	Location 
	Attendance by:

	Once-off meeting 
	MSTEAMS or on-site 
	Project Manager, Contractor, Project Supervisor, Project Engineer, Power Station Manager and Others as required


2.1.1.1 Implementation meetings for specific progress/QC, and feedback
1 The implementation meeting is held between the Contractor and the Employer’s implementation support team, to report on implementation progress and review any risks, issues and Employer actions that need to be resolved in order to ensure smooth implementation of the Project. 
2 The Contractor’s QC representatives provide reports from each meeting to the Employer’s Project Engineer. 
3 This report will cover: 
a. Scheduled QC inspections for the period identified in the meeting. 
b. Any new QC-related issues identified since the last report, their status and action plan for resolution. 
c. Status and progress on previously reported quality issues.
4 Implementation meetings format: 
	Title and purpose
	Approximate time 
& interval
	Location
	Attendance by:

	Risk register and compensation events 
	As required 
	MSTEAMS or on-site 
	Project Manager, Contractor, Project Supervisor, Quantity Surveyor and Project Engineer

	Overall contract progress and feedback 
	Minimum Bi-weekly or as required by the Project Manager.
	MSTEAMS or on-site 
	Project Manager, Contractor, Supervisor, and Project Engineer 

	Installation progress meetings 
	Daily 
	on-site 
	Contractor, Supervisor, and relevant Engineer when required 


[bookmark: _Toc221691179][bookmark: _Toc222215798]
2.1.2 [bookmark: _Toc227065345][bookmark: _Toc240874427]Meetings of a specialist nature
1 The Project Manager (or the Contractor, subject to the Project Manager being notified) may convene specialist meetings to address:
a. design review/clarifications,
b. temporary works/access / lifting coordination,
c. interface management with Others,
d. QCP/ITP reviews and technical compliance matters,
e. safety audits and technical risk discussions.
2 Attendance, frequency and location are fit-for-purpose and recorded. Records are submitted to the Project Manager within five (5) Working Days after the meeting.
2.1.3 [bookmark: _Toc221691180][bookmark: _Toc222215799][bookmark: _Toc227065346][bookmark: _Toc240874428]Post-implementation meeting for project feedback and review
1 A once-off close-out meeting may be held (if required) to review outstanding punch-list items, documentation, warranties/guarantees, lessons learned and final handover requirements: 
	Interval 
	Location 
	Attendance by:

	Once-off 
	MSTEAMS or on-site
	Project Manager, Contractor, Project Supervisor, Project Engineer, Power Station Manager and Others as required


2.2 [bookmark: _Toc222215800][bookmark: _Toc227065347][bookmark: _Toc240874429][bookmark: _Toc137798050][bookmark: _Toc229128253]Documentation control
1 The Contractor establishes and maintains a structured document-management system for all contract documentation throughout the contract and until submission of the final records required by this Works Information.
2 The Contractor maintains a current document register covering all submissions and records required by this Works Information. The register identifies, as a minimum:
a. document title and number;
b. affected asset or work area at Gourikwa Power Station;
c. revision;
d. date submitted;
e. purpose or status of submission;
f. whether acceptance or another response is required;
g. response received and date; and
h. current document status.
3 All contractual communications, Contractor design submissions, inspection records and technical records are uniquely numbered, dated, revision-controlled and communicated in a form which can be read, copied and recorded.
4 The document-management system provides traceability, revision control, document-status control, transmittal records, evidence of receipt and identification of superseded documents.
5 The Contractor complies with the following Employer document-control requirements where applicable to the documents being produced:
a. 240-86973501 – Engineering Drawing Standard – Common Requirements;
b. 240-54179170 – Classification and Designation of Technical Documentation; and
c. 32-644 – Documentation Management Standard.
6 Documentation:
a. is prepared in South African English using SI units;
b. is legible and professionally prepared;
c. is signed by authorised or appropriately qualified persons where required;
d. identifies the contract number and affected asset or work area at Gourikwa Power Station;
e. is submitted without password protection, write protection or other access restrictions; and
f. is submitted in searchable PDF format unless an editable or native format is required by this Works Information.
7 Editable or native formats are provided for programmes, drawings, registers, schedules, spreadsheets, as-built information and other records for which the Employer requires the source file for subsequent use.
8 Each document submission is accompanied by a uniquely numbered transmittal identifying:
a. the contract number and title;
b. affected asset or work area at Gourikwa Power Station;
c. document title and number;
d. revision;
e. date of issue;
f. purpose or status of issue; and
g. whether acceptance or another response is required.
9 A contractual communication identifies, as applicable:
a. the contract number and title;
b. the Contractor's unique communication reference;
c. the relevant previous communication reference;
d. the relevant clause of the conditions of contract; and
e. whether a reply is required.
10 A notification which the conditions of contract require is communicated separately from other communications in accordance with clause 13.7.
11 Formal contractual communications issued electronically are transmitted as controlled PDF documents or through the Employer's nominated contract-management system. The communication is not issued solely in the body of an email.
12 Communications and submissions are addressed to the person required by the conditions of contract or this Works Information. Copying another Employer representative does not transfer or alter the contractual function of the Project Manager or Supervisor.
13 Meeting minutes, informal comments, discussions and technical correspondence do not replace an instruction, notification, acceptance, certificate or other communication required by the conditions of contract.
14 The Contractor retains evidence of transmission and receipt of its submissions and communications.
15 Contractor design submissions are controlled in accordance with Section 3.3. Where Project Manager acceptance of Contractor design is required, the Contractor does not proceed with the relevant work until that design has been accepted in accordance with the conditions of contract.
16 Before Completion, the Contractor submits a complete indexed set of the final records required by this Works Information for the completed works.
17 Unless otherwise stated in this Works Information, one complete electronic set of final records is provided for the works. Where the Employer requires a hardcopy data book, one complete indexed hardcopy set is also provided, clearly identified with the contract number, contract title and revision.
2.3 [bookmark: _Toc221691182][bookmark: _Toc222215801][bookmark: _Toc227065348][bookmark: _Toc240874430]Communication Requirements
1 All communications from the Contractor required under the Contract are addressed to the Project Manager in accordance with the NEC ECC.
2 Every contractual communication (including notifications, replies, submissions and requests) clearly states:
a. the Employer’s contract number (e.g., 46000xxxxx);
b. the contract title;
c. any relevant previous reference(s) (e.g., the Project Manager’s reference being replied to);
d. the ECC clause under which the communication is issued (where applicable);
e. whether a reply is required and by when (where applicable); and
f. The Contractor’s unique letter/reference number.
3 In accordance with ECC clause 13.7, each notification/communication deals with one issue only. Separate issues are issued as separate communications.
4 All document deliverables transmitted for review, acceptance, record or information are accompanied by:
a. formal covering communication; and
b. a document transmittal listing each document title/number, revision, status and purpose of issue.
5 Where hardcopy deliverables are required by the Works Information, each hardcopy submission is accompanied by a hardcopy copy of the covering communication and/or document transmittal.
6 Where communications are submitted electronically:
a. The letter title is reflected in the email subject line.
b. One letter/communication per email (with its attachments and transmittal); and
c. contractual communications are attached as controlled documents (PDF), not issued only in the email body.
7 Copying additional recipients does not change the requirement that contractual communications are addressed to the Project Manager.
2.4 [bookmark: _Toc222215802][bookmark: _Toc227065349][bookmark: _Toc240874431]Health and safety risk management
1 The Contractor complies with:
a. the Occupational Health and Safety Act, 1993 (Act 85 of 1993) and applicable regulations;
b. the Employer’s occupational health and safety requirements issued as part of the contract;
c. applicable Gourikwa Power Station safety rules and procedures;
d. the health and safety requirements applicable to the works; and
e. the health and safety requirements of this Works Information.
2 The Contractor remains responsible for the health and safety of its employees, Subcontractors and other persons affected by the manner in which it Provides the Works.
3 Before commencing physical work on a Site, the Contractor:
a. submits the required project-specific health and safety plan and supporting documentation for review in accordance with the Employer’s occupational health and safety requirements;
b. establishes and maintains the required health and safety file;
c. provides the statutory appointments applicable to the work;
d. provides evidence of a valid Letter of Good Standing where required by law;
e. provides medical certificates of fitness applicable to the work to be performed;
f. completes the required Site induction and access processes;
g. completes any agreement required in terms of section 37(2) of the Occupational Health and Safety Act; and
h. obtains the permits, authorisations or work-area releases required before commencing the relevant activity.
4 The Contractor provides competent health and safety resources appropriate to the nature, extent and risk of the works.
5 The Contractor prepares, maintains and implements task-specific risk assessments, Method Statements, safe work procedures and emergency arrangements for the activities it performs.
6 The Contractor reviews and updates its health and safety documentation when:
a. the nature or sequence of the work changes;
b. Site conditions or work-area conditions change;
c. additional hazards are identified;
d. an incident, near miss or non-conformance identifies the need for additional controls; or
e. an applicable statutory or Site requirement requires revision.
7 Without limiting the Contractor’s obligation to identify and manage all hazards associated with its work, the Contractor’s health and safety planning addresses the risks associated with the applicable works, including:
a. dewatering and work in or adjacent to pollution-control dams and containment areas;
b. contaminated water, sludge, hydrocarbons and other potentially contaminated materials;
c. cleaning and degreasing activities;
d. concrete breaking, cutting, drilling, grinding and repair activities;
e. excavation, foundation preparation, backfilling and compaction;
f. construction of reinforced concrete slabs and masonry containment walls;
g. application and handling of sealants, primers, epoxy resins, coatings and other chemical products;
h. work adjacent to fuel-storage and fuel-containment infrastructure;
i. underground stormwater drainage inspection and flushing activities;
j. movement of construction vehicles, Equipment and Plant within Gourikwa Power Station;
k. lifting and handling activities required to Provide the Works;
l. temporary works and access arrangements;
m. interaction with the Employer, Others and operating plant; and
n. weather conditions affecting the safe execution of the work.
8 The Contractor provides and maintains the PPE, safety Equipment, emergency Equipment, barricading, signage and other controls required by its risk assessments, applicable law and the Employer’s Site requirements..
2.4.1 [bookmark: _Toc222215803][bookmark: _Toc227065350][bookmark: _Toc240874432]Audits, inspections and station audits
1 The Contractor conducts health and safety inspections and internal audits at intervals appropriate to the work being performed and retains records of the findings and corrective actions.
2 The Employer may inspect or audit the Contractor’s compliance with the contractual and statutory health and safety requirements.
3 The Contractor provides reasonable access to the relevant work areas, health and safety records and personnel for these inspections and audits.
4 The Contractor corrects identified non-conformances within the period required by the applicable statutory requirement or the Employer’s health and safety process.
5 The Contractor’s responsibility for health and safety is not reduced by an inspection, audit, review or comment by the Employer.
2.4.2 [bookmark: _Toc222215804][bookmark: _Toc227065351][bookmark: _Toc240874433]Minimum access prerequisites and induction
1 Minimum requirements for Contractor personnel to gain access to Gourikwa Power Station include, but are not limited to:
a. valid medical fitness certificate;
b. police clearance (SAPS or accredited AFIS-linked provider) not older than three (3) months;
c. identification document (RSA ID or equivalent);
d. valid driver’s licence (where applicable);
e. adherence to Eskom Life-Saving Rules;
f. applicable risk-based PPE;
g. valid letter of good standing at all times (COIDA or equivalent). Access is denied if invalid.
h. where a Contractor/supplier/consultant is working alone and is not eligible to register with the compensation fund:
i. a member benefit statement confirming insurance cover, including life and disability, with a minimum fund of R500,000.
2 Induction is conducted only after the above documents have been submitted and accepted by the Employer. The Contractor allows approximately two (2) hours for induction (unless otherwise advised by the Employer).
2.4.3 [bookmark: _Toc222215805][bookmark: _Toc227065352][bookmark: _Toc240874434]Daily control requirements (site discipline)
1 The Contractor signs on to the workers’ register each morning and signs off each afternoon.
2 A Responsible Person (RP) is appointed by the site and is responsible for the work area. The RP controls access to the work area, confirms the area remains safe for work, and verifies that all personnel sign in and out.
3 The Contractor notifies the RP of the daily work plan and intended work fronts before commencing work for the day.
4 The Contractor conducts a toolbox talk each morning before commencing work, covering at least: the day’s tasks, hazards, controls, interfaces, exclusion zones, dropped-object controls, weather considerations and lessons learned from the previous day.
5 Where required by station arrangements, the Contractor provides a representative to attend daily morning coordination meetings.
2.4.4 [bookmark: _Toc222215806][bookmark: _Toc227065353][bookmark: _Toc240874435]Key performance indicators and reporting (HSE)
The Contractor monitors, manages and reports health and safety performance for the duration of the Contract. As a minimum, the Contractor:
1 maintains a Health and Safety File and ensures compliance with the approved health and safety plan, the Eskom OHS specification and applicable legislation;
2 maintains good housekeeping in all working areas and site establishment areas;
3 implements and monitors a near-miss reporting programme;
4 implements Behavioural Safety Observations (BSO) and Planned Job Observations (PJO) as required by the OHS Specification/Requirements;
5 targets a zero-harm outcome and maintains performance within the Employer’s injury tolerance levels (including LTI tolerance) as defined in the OHS Specification/Requirements;
6 reports all incidents immediately or before the end of the shift in which the incident occurred;
7 completes incident investigations within seven (7) days of the incident (unless otherwise required by the Employer’s procedures);
8 Closes incident investigation recommendations within the timeframes stated in the investigation report.
9 Closes audit findings and non-conformances within the timeframes stated by the Employer’s procedure and/or audit report.
10 The Employer monitors these KPIs through audits and site inspections.
2.4.5 [bookmark: _Toc222215807][bookmark: _Toc227065354][bookmark: _Toc240874436]Contract completion and sign-off (HSE close-out)
1 Upon completion of the Works, the Parties may conduct a final close-out meeting to identify and address any remaining HSE gaps before contract close-out.
2 Before Completion (or as otherwise instructed), the Contractor:
a. closes all incidents, investigations, non-conformances and audit findings relevant to the Works;
b. cleans all site establishment areas and work areas and leaves them in a safe, orderly condition;
c. submits final safety statistics and the completed safety file to the Employer’s BU Safety department for close-out and filing; and
d. completes the required close-out report (including Annexure D form as per 32-726, where applicable to this Contract).
2.5 [bookmark: _Toc222215808][bookmark: _Toc227065355][bookmark: _Toc240874437]Environmental constraints and management
1 The Contractor includes in its rates and Prices all costs required to comply with the environmental requirements stated in this Works Information, applicable law and the environmental requirements applicable at Gourikwa Power Station.
2 The Contractor recognises that the works are carried out within environmentally sensitive operating Power Station Sites. The Contractor manages its activities in accordance with environmentally sound principles and the environmentally sensitive operating environment at Gourikwa Power Station.
3 The Contractor complies with all applicable national, provincial and municipal environmental legislation, regulations and by-laws, including, as applicable:
a. National Environmental Management Act, 1998 (Act 107 of 1998);
b. National Environmental Management: Waste Act, 2008 (Act 59 of 2008);
c. National Water Act, 1998 (Act 36 of 1998);
d. applicable norms and standards issued in terms of the National Environmental Management: Waste Act; and
e. applicable Employer environmental procedures, policies and Site requirements.
4 The Contractor applies the environmental duty of care and takes reasonable measures to prevent pollution, environmental degradation and unnecessary disturbance resulting from its activities.
5 Any environmental incident, spill, uncontrolled discharge or event which has caused or may cause an environmental impact is immediately reported to the Project Manager and the applicable Site environmental representative. The Contractor implements the applicable Site incident-response and emergency requirements.
6 The Contractor maintains and implements an Environmental Policy and an Environmental Management Plan appropriate to the works. The Environmental Management Plan is submitted to the Project Manager within fourteen (14) calendar days after the Contract Date.
7 The Contractor submits an activity-specific environmental Method Statement to the Project Manager for acceptance not less than fourteen (14) calendar days before commencing an activity which presents a material environmental risk. The Method Statement addresses, as applicable:
a. Site establishment and layout;
b. pollution-prevention measures;
c. waste and contaminated-water management;
d. hazardous substances and chemicals;
e. spill prevention and response;
f. incident and emergency management;
g. dust control; and
h. rehabilitation and reinstatement.
8 The Contractor demarcates its Site establishment, laydown, storage and working areas and confines its activities to the areas made available for the works. On completion, temporary facilities, waste, surplus materials and contamination resulting from the Contractor's activities are removed and affected areas are reinstated.
9 Fuel-storage facilities provided by the Contractor are bunded to at least 110% of the applicable storage capacity. Fuel-dispensing areas and other temporary areas with a pollution potential are provided with an impermeable surface and appropriate containment measures.
10 Cleaning, servicing, maintenance and repair of the Contractor's vehicles are carried out off Site unless a specifically designated facility has been made available or accepted for this purpose.
11 The Contractor provides suitable enclosed temporary sanitation facilities where Site facilities are not made available and manages these facilities so that they do not cause pollution or nuisance.
12 A current Safety Data Sheet is available for each chemical, hazardous substance or potentially hazardous material brought onto Site. Chemicals, fuels, oils, sealants, resins, coatings and other potentially polluting materials are stored and handled in accordance with the Safety Data Sheet, manufacturer requirements and applicable Site requirements.
13 The Contractor protects groundwater, rivers, streams, aquifers, wetlands, drainage systems and watercourses against direct or indirect pollution arising from its activities.
14 Garbage, sewage, cementitious material, oils, fuels, chemicals, silt, contaminated runoff, wastewater, sludge and other pollutants are not discharged into the environment, clean stormwater system or watercourse.
15 Contaminated water, sludge, wash water and flushing effluent arising from the dam, containment and drainage works are contained, handled and disposed of in accordance with the accepted environmental Method Statement and the applicable Site requirements.
16 The Contractor does not work within a river flood line, stream, watercourse or wetland unless the work is required to Provide the Works, the proposed environmental controls have been accepted and any statutory authorisation required by applicable law has been obtained.
17 Waste generated by the Contractor is minimised, separated and managed according to the applicable waste stream. This includes, as applicable, general waste, recyclable waste, construction rubble, scrap metal, oils and grease, contaminated material and hazardous waste.
18 Waste is stored in suitable labelled containers or designated temporary storage areas which prevent leakage, dispersion and access by animals. Eating areas used by Contractor personnel are provided with suitable waste bins.
19 The Contractor does not bury, dump or burn waste, vegetation, litter or refuse on Site.
20 Waste requiring off-Site disposal is transported and disposed of at a facility authorised to receive the relevant waste stream. The Contractor provides the Project Manager with the applicable waste manifests, disposal certificates or other proof of lawful disposal.
21 The removal, damage or disturbance of indigenous flora outside areas necessarily affected by the works is prohibited.
22 The Contractor protects fauna occurring within or adjacent to the Site. Hunting, trapping, snaring, poisoning, shooting, nest disturbance, egg collecting and feeding of wild animals are prohibited. Domestic pets and livestock belonging to Contractor personnel are not permitted on Site.
23 Pesticides or herbicides are not used on Site without the Project Manager's acceptance and compliance with the applicable environmental requirements.
24 The Contractor implements effective dust-control measures for excavation, cutting, grinding, stockpiling, vehicle movement and other dust-generating activities.
25 The Contractor takes reasonable precautions to prevent fires resulting from its activities and complies with applicable Power Station fire-prevention and hot-work requirements.
26 The Contractor ensures that its employees and Subcontractors are informed of the environmental requirements applicable to their work and uses appropriate briefings, notices and signage to reinforce these requirements.
27 Environmental records required by applicable law, the Employer's Site requirements or this Works Information, including waste-disposal records and environmental incident records, are retained and included in the final records for the relevant Section where applicable.
28 Acceptance of an environmental Method Statement, or any environmental inspection or review by the Employer, does not reduce the Contractor's responsibility for complying with the environmental requirements of the contract.
2.6 [bookmark: _Toc222215809][bookmark: _Toc227065356][bookmark: _Toc240874438]Quality assurance requirements
1 Quality management for the Works is under Eskom Supplier Quality Management Specification 240-105658000 (QM-58).
2.6.1 [bookmark: _Toc240874439]Quality Assurance Requirements
1 The Contractor complies with the current version of the ISO 9001:2015 Quality Management System requirements. 
2 The Contractor defines the level of QA or inspection imposed on his subcontractors and suppliers. 
3 The Contractor prepares and submits fitment/installation procedures with quality check sheets as well as the Quality Control Plan. Quality acceptance criteria are included in these procedures. 
4 All technical design and implementation documentation and QCPs are submitted to the Employer for acceptance fourteen (14) days before the commencement of any Works or inspections, allowing the Employer the opportunity to provide the necessary intervention points if required. 
5 The Contractor is made aware of the requirement that all documents or designs submitted for review to the Project Manager for acceptance require a process of review. 
6 The Contractor documents all inspections as part of the quality assurance and control procedures. These documents are handed to the Employer as records. 
7 Submission of all quality requirements, to comply with section 3.7.1, Post Contract Award as stipulated in the Supplier Quality Management Specification 240-105658000, is made to the Employer for acceptance at least thirty (30) days before the execution of the project. 
8 On completion of the project, the Contractor hands in all data books (Packs) before the Completion Certificate is issued. 
9 Where the Contractor maintains an official Quality Management System, details of the level of the Contractor’s self-certification procedures adopted concerning supplied materials are submitted to the Project Manager for acceptance before commencement of the relevant work. 
10 Where no certified Quality Management System exists, the Contractor plans all quality management procedures, carries out all quality control testing as required and makes available records of such testing to the Supervisor for inspection and review. 
11 The Contractor submits full details of the proposed quality management system and procedures to the Project Manager for acceptance. The Supervisor has access to all relevant records, Site trials and tests. 
12 The Contractor ensures that monitoring and measuring Equipment are calibrated and verified to confirm serviceability before usage, and records of such are kept on Site. 
2.6.2 [bookmark: _Toc240874440]Quality Control Plan
The Quality Control Plan manages the overall quality of the project’s main activities and milestones. It lists detailed activities in order of execution where each activity is described and references the associated work packages or specifications with witness, hold and verification points.
The Contractor is therefore required to ensure QCPs meet the following requirements as a minimum:
1 The Contractor defines the level of QC or inspection imposed on his subcontractors and suppliers. 
2 The QCPs have provisions for signatures indicating Completion by the Contractor and acceptance by the Employer at the end of each activity. 
3 The Contractor has the necessary Equipment and qualified staff to carry out the quality control required to ensure compliance with the specification. 
4 The Contractor ensures that a complete Quality Control Plan (QCP), aligned with the Method Statement and programme for executing the work, is submitted to the Project Manager and Supervisor for review and acceptance before the Works can commence. 
5 The programming of inspections, Hold Points and Witness Points is agreed between the Employer and the Contractor before undertaking any of the Works. 
6 During reviews of the QCP, the Employer provides the necessary intervention points, if required. 
7 The Quality Control Plans and Inspection and Test Plans incorporate the inspection, testing and quality requirements stated in the applicable requirements of this Works Information and the Manufacturer's requirements for the accepted materials and proprietary systems. 
8 Repair materials and proprietary systems are submitted before use with the applicable Technical Data Sheets, Safety Data Sheets, Manufacturer's instructions, compatibility information and compliance certificates. 
9 The Contractor maintains traceable quality records appropriate to the work performed, including, where applicable:
a. material and product batch numbers;
b. delivery and material certificates;
c. substrate and surface-preparation records;
d. mixing and application records;
e. ambient and substrate conditions;
f. curing records;
g. inspection and test results;
h. calibration certificates;
i. photographs;
j. non-conformance and corrective-action records; and
k. Manufacturer or specialist applicator records required by this Works Information.
10 Work which will be covered or become inaccessible is not covered until the Supervisor has been given the required notice and reasonable opportunity to inspect the work. 
11 The Contractor gives the Supervisor at least five (5) Working Days' notice of a planned Witness Point or Hold Point unless another notice period is stated in the accepted Quality Control Plan or Inspection and Test Plan. 
12 The Contractor does not proceed beyond a Hold Point until the required inspection or test has been completed and the Supervisor has confirmed release of the Hold Point. 
13 Without limiting the requirements of this Works Information, the quality controls applicable to the works include: 
a. condition assessment, inspection, NDT and Defect Mapping of the pollution-control dams and associated structures;
b. preparation and repair of concrete, reinforcement, cracks, joints and sealant systems;
c. inspection and flushing of underground stormwater drainage systems;
d. inspection and testing of fuel-containment repairs;
e. concrete strength testing;
f. coating dry-film-thickness measurements; and
g. Manufacturer compliance certificates.
14 Measuring, inspection and test Equipment used to demonstrate compliance is suitable for its intended purpose and has current calibration traceable to recognised standards. Calibration records are made available to the Supervisor. 
15 The quality requirements apply equally to work carried out outside the Site where Plant and Materials, testing, preparation or other work forming part of the works is undertaken. 
16 The Contractor gives the Project Manager and Supervisor reasonable access to the Contractor's and its Subcontractors' relevant quality records and to inspections and tests associated with the works. 
17 The Contractor submits quality and test records progressively as the works proceed and does not defer compilation of these records until Completion. 
18 Non-conforming work or Plant and Materials is identified, controlled and recorded. The Contractor records the corrective action taken and closes the non-conformance before the affected work is incorporated into or covered by subsequent work. 
19 The complete quality records for the works, including required test results, material certificates, inspection records, non-conformance close-out records, warranties, guarantees and other quality documentation required by this Works Information, form part of the final records required before Completion. 
20 Inspection, testing, witnessing, review or release of a Hold Point by the Supervisor, and acceptance of a submission by the Project Manager, does not reduce the Contractor's responsibility to Provide the Works in accordance with the contract
2.7 [bookmark: _Toc222215810][bookmark: _Toc227065357][bookmark: _Toc240874441]Programming constraints 
1 The Contractor prepares, submits and maintains programmes in accordance with clauses 31 and 32 of the conditions of contract and the requirements stated in the Contract Data.
2 The programme is prepared using Microsoft Project in native .mpp format and is accompanied by a PDF copy.
3 Each programme submitted for acceptance:
a. shows the starting date, Key Dates, access dates where applicable, and the Completion Date for the whole of the works;
b. shows the order, timing, duration and logic of the activities necessary to Provide the Works;
c. identifies the critical path, available float and time risk allowances;
d. includes, as applicable:
· mobilisation, Site access, induction, permits and Site establishment;
· release of each work area by the Employer;
· dewatering and residual-water management activities applicable to the relevant work area;
· cleaning and degreasing required before inspection;
· detailed condition assessments, NDT, Defect Mapping and preparation of the required reports;
· submission, acceptance and, where required, resubmission of Contractor design, proposed remedial measures, Method Statements, material submissions, Quality Control Plans and Inspection and Test Plans;
· procurement and delivery of Plant and Materials;
· inspection points, Witness Points and Hold Points;
· concrete, reinforcement, crack, joint and sealant repairs;
· fuel-containment and tank-to-foundation interface repairs;
· inspection, flushing and re-inspection of underground stormwater drainage systems;
· construction of the Gourikwa berm extension and erosion repairs;
· construction of the Gourikwa hazardous-waste skip containment areas;
· curing periods and restrictions on loading, immersion or return to service;
· inspections and testing;
· correction of Defects;
· preparation and submission of professional reports and required sign-off;
· preparation of as-built and Completion documentation;
· reinstatement and handover; and
· Completion of the whole of the works;
e. shows the dates by which the Contractor requires:
· access to each relevant part of the Site;
· operational release of each work area;
· information from the Employer;
· attendance by the Supervisor at planned Hold Points and Witness Points;
· acceptance or other decisions from the Project Manager; and
· work to be carried out by the Employer or Others;
f. allows for the period for reply stated in the Contract Data for submissions requiring acceptance or another contractual response;
g. shows procurement lead times, delivery periods and Manufacturer-required application, curing and testing periods for the proposed repair, sealant, concrete and coating systems;
h. shows the interfaces between the works and ongoing Power Station operations; and
i. shows the principal resources and Contractor’s Equipment required for significant activities and work areas at Gourikwa Power Station.
4 The Contractor submits the first programme for acceptance within the period stated in the Contract Data.
5 The Contractor submits revised programmes at intervals no longer than the period stated in the Contract Data and whenever otherwise required by the conditions of contract.
6 Each revised programme:
a. shows actual progress achieved;
b. identifies work completed and work remaining;
c. shows the effect of implemented compensation events;
d. identifies changes to logic, sequence, durations or resources;
e. shows the current forecast Completion Date for the whole of the works;
f. identifies delays, constraints and proposed recovery measures; and
g. shows the current status of activities to be carried out by the Employer and Others.
7 The Contractor provides an updated short-term look-ahead programme at a progress meeting where required by the Project Manager. The look-ahead programme does not replace a programme required under clause 32.
8 No permanent repair to a pollution-control dam commences until the condition-assessment report and proposed remedial measures required by this Works Information have been accepted.
9 The Contractor does not assume that the Clean Water Dam, Dirty Water Dam, fuel-containment areas, drainage systems, berm work area and hazardous-waste skip containment work area will be available simultaneously. The Contractor coordinates the sequence of the works with the Employer and shows the required access and operational interfaces on the programme.
10 Work which materially affects Gourikwa Power Station operations, Site access, fuel-containment arrangements, environmental controls, drainage systems, permits or isolations is coordinated with the Employer and shown on the Accepted Programme before the affected activity commences.
11 The programme includes the Manufacturer-required curing, protection and return-to-service periods applicable to the Plant and Materials used in the works.
12 Acceptance of a programme does not constitute acceptance of Contractor design, a Method Statement, proposed remedial measures or a change to the Works Information and does not reduce the Contractor's responsibility to Provide the Works
2.8 [bookmark: _Toc222215811][bookmark: _Toc227065358][bookmark: _Toc240874442]Contractor’s management, supervision and key people
1 The Contractor ensures that the works are managed and supervised by competent and suitably experienced personnel appropriate to the nature and extent of the works.
2 Within two (2) weeks after the Contract Date, the Contractor submits an organogram showing:
a. the key people named in the Contract Data;
b. the persons responsible for overall contract management and Site supervision;
c. the persons responsible for health and safety, quality and environmental management;
d.  lines of authority and communication within the Contractor’s organisation; and
e. reporting and coordination arrangements with Subcontractors.
3 The Contractor provides a competent Site Supervisor whenever physical work is being carried out at Gourikwa Power Station.
4 The Site Supervisor:
a. has sufficient authority to direct and coordinate the Contractor’s activities on Site;
b. is familiar with the Works Information, Accepted Programme and Site requirements;
c. coordinates the Contractor’s people, Subcontractors, Plant and Materials and Contractor’s Equipment; and
d. acts as the Contractor’s day-to-day Site contact for the Project Manager and Supervisor.
5 Where the Contractor carries out physical work at more than one work area at the same time, the Contractor provides sufficient supervision for each active work area.
6 The Contractor ensures that its management and supervisory personnel are available for meetings, inspections, testing and other activities relevant to their responsibilities.
7 Replacement of a key person named in the Contract Data is dealt with in accordance with clause 24.1 of the conditions of contract.
8 The Contractor notifies the Project Manager before changing a person carrying out a principal Site-management or supervisory role and provides the name, role and relevant experience of the replacement.
9 The Contractor maintains adequate management and supervision throughout the execution of the works
2.9 [bookmark: _Toc222215812][bookmark: _Toc227065359][bookmark: _Toc240874443]Invoicing and payment
1 Within one week of receiving a payment certificate from the Project Manager in terms of clause 51.1, the Contractor submits a tax invoice to the Employer, showing the amount due for payment equal to that stated in the Project Manager’s payment certificate. 
2 The Project Manager is to be copied in on all electronic invoices emailed. 
3 Failure to submit the invoice to the correct address could result in payment delays. 
4 The Contractor’s Tax Invoices comply with the requirements as stated in clause Z7 of the Contract Data 
5 Invoices are submitted electronically to: 
· Local Eskom Invoices - invoiceseskomlocal@eskom.co.za 
· Foreign Eskom Invoices - invoiceseskomforeign@eskom.co.za 
6 The following details are required when submitting invoices and additional data: 
a. The subject line of your email should only contain your vendor number. 
b. Each PDF invoice should be named only with your invoice number. 
c. All electronic invoices are sent in PDF format only. 
d. Attach the proof of delivery to your invoice. 
e. Where applicable, supporting documents are attached to the scanned PDF invoice as one attachment. 
f. A copy of the signed assessment certificate 
g. CPA calculation sheet 
h. Retention Certificate, which is a retention invoice. 
i. Any other appropriate documents, e.g. 
i. For shipping invoices, please ensure the following documents are attached. 
ii. Invoice (this should only reflect the shipping cost) 
iii. Commercial invoice 
iv. Delivery note
v. Your shipping cost calculation is relevant to that invoice—not a generic one (the amount of the shipping cost calculation has to balance with the amount on the invoice). 
vi. Forwarding agent’s invoice 
vii. The customs document. 
j. Please do not attach unnecessary documents, as this will make the file too large. 
7 Other requirements: 
a. For foreign invoices, suppliers will still be required to physically deliver hard copies of original documents to the respective Document Management centres, even though the invoices have been submitted electronically. 
b. Ensure compliance with the tax requirements for electronically submitting invoices. 
c. Each PDF should contain one credit note, one debit note, or one credit note only. More than one invoice can be submitted per email. 
d. Any CPA-applicable invoices are invoiced separately, so that if there are issues with the CPA, the rest of the invoices can be paid while the CPA issues are resolved. 
8 Include the following information on the Invoice: 
e. Name and address of the Contractor and the Project Manager 
f. The contract number and title 
g. Contractor’s VAT registration number 
h. The Employer’s VAT registration number 4740101508 
i. The total amount invoiced, excluding VAT, the VAT and the invoiced amount including VAT 
j. Contractor's company registration number, if applicable 
k. Contractor’s banking details 
l. Name and address of the recipient 
m. Tax invoice number and date of issue 
n. Description of goods/services provided 
o. Quantity or volume of goods/services 
p. Period time for which the Tax Invoice is being rendered 
q. Relevant line-item number 
r. State whether the value-added tax is included or excluded
2.10 [bookmark: _Toc222215813][bookmark: _Toc227065360][bookmark: _Toc240874444]Insurance provided by the Employer
Insurance provided by the Employer is as stated in clause Z13 of the Contract Data, including Insurance Table B.
2.11 [bookmark: _Toc222215814][bookmark: _Toc227065361][bookmark: _Toc240874445]Contract change management 
Contract change management is carried out strictly in accordance with Core Clause 6 (Compensation events) and Core Clause 16 (Early warning). In addition, the following applies:
1 The Project Manager maintains and issues updates to the Early Warning Register / Risk Register and records compensation event matters for contract administration and tracking.
2 Either Party gives an Early Warning as soon as it becomes aware of any matter which could increase the total of the Prices, delay Completion, delay meeting a Key Date, or impair the performance of the Works in use. Early Warning matters are discussed and managed through the Early Warning/risk process.
3 Compensation Events are notified by the Party required to do so under the Contract. Notifications are issued as formal communications in accordance with Clause 13.
4 Quotations (Clause 62) For each Compensation Event where a quotation is required:
a. The Contractor submits a formal quotation within the required time, clearly stating:
i. The event reference and description.
ii. the forecast time effect (including impact on the Accepted programme);
iii. the forecast cost effect (including supporting records and assumptions); and
iv. any supporting information required by the Project Manager.
b. The Project Manager assesses and responds in writing in accordance with Clause 62.
5 Any change affecting the Works Information, the Prices/Bill of Quantities, or the Accepted programme is managed through the ECC processes and must be formally recorded through the relevant NEC communications and actions. The Contractor does not implement changes that alter the Scope/Works Information unless and until instructed/accepted by the Project Manager in accordance with the Contract.
6 The Contractor notifies the Project Manager in writing of any proposed subcontractor changes and provides the reason and any potential impact on quality, programme, safety and interfaces. The Contractor does not implement such changes where the Contract requires acceptance, unless accepted by the Project Manager.
7 Any changes to delivery dates, milestones or sequencing arising from Early Warnings and/or Compensation Events are reflected in the next programme submission and, where applicable, in the revised programme submitted with a quotation.
2.12 [bookmark: _Toc222215815][bookmark: _Toc227065362][bookmark: _Toc240874446]Provision of bonds and guarantees
No performance bond or other contract security is required unless stated otherwise in the Contract Data. Product warranties, Manufacturer guarantees and other quality-related guarantees required by the Works Information are not contract securities and are provided as part of the applicable quality and Completion documentation.
2.13 [bookmark: _Toc222215816][bookmark: _Toc227065363][bookmark: _Toc240874447]Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor
The Contractor keeps and maintains proper records of Defined Cost, payments and assessments of Compensation Events, in accordance with Clause 52.2 of the Conditions of Contract.
The following records are kept to a minimum:
	Type of Cost
	Type of Record

	People employed by the Contractor (labour)
	Signed timesheets, payroll reports, payslips

	People employed by Subcontractors (labour)
	Signed timesheets, certified payroll reports from Subcontractors

	Equipment owned or hired
	Equipment hire agreements, delivery notes, usage logs, plant daily reports and actual paid invoices

	Plant and Materials
	Delivery notes, invoices, stock issue records, material usage records and actual paid invoices

	Works subcontracted by the Contractor
	Subcontract agreements, invoices, proof of payment, and relevant correspondence

	Other Third-Party Costs
	Third-party invoices, proof of payment

	Accommodation
	Invoices, proof of payment

	Transport and Logistics
	Vehicle logs, fuel records, transport invoices

	Testing and Certification
	Test certificates, inspection reports, laboratory results, calibration certificates

	Insurance Costs (if reimbursable)
	Insurance policy documents, premium invoices, proof of payment


2.14 [bookmark: _Toc222215817][bookmark: _Toc227065364][bookmark: _Toc240874448]Training workshops and technology transfer
1 No formal training workshops or structured technology-transfer programme are required under this contract.
2 Before Completion, the Contractor provides the Employer with the product-specific information necessary for the future inspection, maintenance and repair of the completed works, including, where applicable:
a. Manufacturer’s inspection and maintenance recommendations;
b. recommended inspection intervals;
c. cleaning and maintenance requirements;
d. curing and return-to-service limitations;
e. compatible repair and replacement materials;
f. precautions applicable to sealants, coatings and proprietary repair systems;
g. procedures for identifying deterioration or failure;
h. recommended methods for future local repairs; and
i. applicable warranties, guarantees, Technical Data Sheets and compliance certificates.
3 The Contractor explains the submitted information to the Employer’s nominated operations, maintenance or engineering personnel as part of the handover of the relevant Section.
4 The information required by this section forms part of the Completion documentation for the works.
3 [bookmark: _Toc137798055][bookmark: _Toc229128258][bookmark: _Toc240874449]Engineering and the Contractor’s design
1 The works comprise remedial works to existing structures and infrastructure and construction of additional civil infrastructure at Gourikwa Power Station.
2 The Employer provides the existing asset information, permanent works requirements and drawings identified in this Works Information and Section 7.
3 The Contractor designs only those parts of the works expressly identified in Section 3.2.
4 The Contractor’s inspection, measurement, condition assessment, NDT, Defect Mapping, preparation of Method Statements and preparation of technical records do not, by themselves, constitute Contractor design.
5 Where this Works Information requires the Contractor to assess an existing condition and propose remedial measures, the Contractor is responsible for the engineering content of the proposed remedial measure to the extent stated in Section 3.2.
6 The Contractor notifies the Project Manager as soon as it becomes aware of:
a. an ambiguity or inconsistency in the Employer’s information, drawings, Site Information or this Works Information; or
b. a requirement which the Contractor considers to be illegal or impossible.
7 The Contractor does not alter an Employer-provided permanent requirement unless the Project Manager instructs a change to the Works Information.
8 Acceptance of Contractor design, proposed remedial measures, Method Statements or other technical submissions does not reduce the Contractor’s responsibility for the design which it is required to provide.
3.1 [bookmark: _Toc240874450][bookmark: _Toc137798057][bookmark: _Toc229128260]Employer’s design
1 The Employer’s design comprises the existing permanent works, permanent works requirements and existing asset information identified in this Works Information and the drawings listed in Section 7. 
2 The Employer’s design information includes, as applicable:
a. the existing Gourikwa Clean Water Dam;
b. the existing Gourikwa Dirty Water Dam;
c. the associated concrete structures, joints, sumps and drainage infrastructure;
d. the existing fuel-containment structures associated with Gas 1 Tanks C and D;
e. the existing fuel-containment structures associated with OCGT Tanks A and B;
f. the existing tank foundations and tank-to-foundation interfaces;
g. the existing clean and dirty underground stormwater drainage systems;
h. the existing berm and the permanent requirements for its extension and erosion reinstatement; and
i. the permanent design and requirements for the hazardous-waste skip containment area.
3 The Employer’s existing drawings and information define the existing assets and interfaces against which the Contractor carries out the inspection, remedial and construction works. 
4 The hazardous-waste skip containment area is based on the Employer’s permanent design requirements, including Drawing 18.85/6134, comprising the reinforced concrete slab, masonry bund walls, plaster, chemical-resistant coating, low-point sump and associated construction requirements stated in this Works Information. 
5 The Employer does not provide the final defect-specific permanent repair design for defects whose nature, extent or condition can only be determined after dewatering, cleaning, exposure, inspection or testing. 
6 The Contractor verifies accessible dimensions, interfaces and existing conditions relevant to the work before commencing the affected activity. 
7 Where the Contractor identifies that an actual Site condition differs materially from the Employer’s information, it:
a. records the condition;
b. notifies the Project Manager; and
c. does not proceed with work which would conceal or prejudice assessment of the condition until the matter has been addressed.
8 Verification of dimensions, interfaces and existing conditions does not make the Contractor responsible for the adequacy of the Employer’s design.
3.2 [bookmark: _Toc240874451]Parts of the works which the Contractor is to design
1 The Contractor designs only the parts of the works identified in this section. 
2 The Contractor designs the temporary works and temporary arrangements necessary to Provide the Works, including, as applicable:
a. temporary access and working arrangements;
b. temporary support and protection;
c. temporary pumping, storage and transfer arrangements associated with dewatering and residual-water control; and
d. other temporary works necessary for the safe execution of the works.
3 Following dewatering, inspection and assessment of the Gourikwa Clean Water Dam and Dirty Water Dam, the Contractor prepares the condition-assessment reports and proposed remedial measures required by this Works Information. 
4 The proposed remedial measures include the engineering selection or detailing necessary to address the actual defects identified during the detailed condition assessment, including, where applicable:
a. repair of concrete deterioration, spalling and delamination;
b. treatment or replacement of affected reinforcement;
c. repair of cracks having regard to their classification as structural or non-structural and moving or non-moving;
d. repair of joints, joint sealants, waterstops, expansion boards and associated joint components;
e. repair of defects identified within associated concrete structures and the subsoil drainage sump; and
f. other remedial measures arising directly from findings recorded in the accepted condition-assessment report.
5 For joint and sealant repairs, the Contractor selects and proposes the joint sealant system to be used, subject to the performance requirements stated in this Works Information. 
6 The proposed joint sealant system:
a. accommodates the required joint movement;
b. is resistant to hydrocarbons, intermittent immersion and ultraviolet exposure;
c. includes the required backing material or bond-breaker arrangement;
d. includes primer where required by the Manufacturer; and
e. is compatible with the existing substrate and adjoining joint components.
7 For crack repairs, the Contractor assesses and classifies each crack before repair and selects the repair method appropriate to the crack classification and condition. 
8 The crack-repair method is based on the requirements stated in this Works Information, including, where applicable:
a. low-viscosity epoxy resin repair for appropriate non-moving cracks;
b. routed or formed joints and flexible sealant where required; and
c. injection repair using packers and manual or mechanical injection methods where applicable.
9 The Contractor designs or selects proprietary repair systems only to the extent necessary to satisfy the technical and performance requirements stated in this Works Information and the Manufacturer’s specifications. 
10 The Contractor does not redesign the permanent hazardous-waste skip containment area or the permanent berm geometry unless the Project Manager instructs a change to the Works Information. The Employer has already defined the permanent containment-area design basis and the principal berm requirements. 
11 The following activities are not Contractor design merely because the Contractor prepares or performs them: 
a. visual inspection;
b. NDT;
c. Defect Mapping;
d. measurement and photography of defects;
e. preparation of Method Statements;
f. Quality Control Plans and Inspection and Test Plans; and
g. preparation of inspection and test records.
12 Where a document listed in paragraph 11 contains a design element falling within paragraphs 2 to 9, only that design element is treated as Contractor design. 
13 The Contractor does not change an existing permanent requirement or the Employer’s design intent unless the Project Manager instructs a change to the Works Information.
3.3 [bookmark: _Toc240874452]Procedure for submission and acceptance of Contractor’s design
1 The Contractor submits the particulars of the Contractor’s design identified in Section 3.2 to the Project Manager for acceptance in accordance with clause 21.2 of the conditions of contract.
2 The Contractor submits each design sufficiently early to allow for the period for reply stated in the Contract Data and any required resubmission before the relevant work is due to commence on the Accepted Programme.
3 Each Contractor design submission identifies the relevant asset or work area and includes, as applicable:
a. the purpose and extent of the design;
b. the relevant requirements of this Works Information and Employer drawings;
c. the existing conditions and design inputs relied upon;
d. assumptions used in developing the design;
e. drawings, sketches, details and dimensions necessary to define the design;
f. design calculations where required to demonstrate adequacy;
g. proposed Plant and Materials and applicable Technical Data Sheets;
h. performance characteristics and compatibility of the proposed system;
i. interfaces with the Employer’s design, existing structures and other parts of the works;
j. installation, application or construction requirements necessary for the design to perform as intended; and
k. inspection, testing and acceptance criteria applicable to the completed design.
4 Contractor design submissions are prepared and checked by persons competent for the design being undertaken. Where applicable law requires professional registration for a particular design, the design is prepared or reviewed and signed by an appropriately registered person.
5 The Contractor clearly distinguishes between:
a. Contractor design submitted for acceptance;
b. Method Statements and construction procedures;
c. product or material submissions; and
d. inspection, testing and quality records.
6 A submission which contains both Contractor design and methodology clearly identifies the design component requiring acceptance under clause 21.2.
7 Contractor design may be submitted in parts in accordance with clause 21.3, provided each part contains sufficient information for that part of the design to be assessed.
8 Where the Project Manager does not accept a Contractor design, the Contractor revises and resubmits the design taking account of the reasons stated by the Project Manager.
9 A revised submission:
a. identifies the previous submission and revision;
b. identifies the changes made; and
c. responds to the reasons previously stated for non-acceptance.
10 The Contractor does not proceed with the relevant work until the Project Manager has accepted the applicable Contractor design.
11 A change proposed by the Contractor to an accepted Contractor design is submitted to the Project Manager for acceptance before the change is implemented.
12 A Contractor design submission which requires a change to the Employer’s design or another requirement of the Works Information is clearly identified as such. The Contractor does not implement the proposed change unless the Project Manager instructs the change to the Works Information.
13 Technical review, comment or recommendation by the Employer’s engineering personnel does not constitute acceptance of Contractor design unless acceptance is communicated by the Project Manager in accordance with the conditions of contract.
14 The Supervisor is provided with the accepted Contractor design where it is relevant to inspection, testing, Hold Points, Witness Points or the identification of Defects.
15 The Contractor retains the accepted Contractor design and all subsequent accepted revisions as part of the final records for the works.
16 Acceptance of Contractor design by the Project Manager does not reduce the Contractor’s responsibility for its design or its responsibility to Provide the Works in accordance with the contract..
3.4 [bookmark: _Toc137798059][bookmark: _Toc229128262][bookmark: _Toc240874453]Other requirements of the Contractor’s design
1 The Contractor’s design identified in Section 3.2:
a. complies with applicable law, the requirements of this Works Information and the standards applicable to the relevant work;
b. is compatible with the existing concrete, reinforcement, waterstops, joint fillers, tank steel, sealants and other adjoining materials with which it interfaces;
c. is suitable for the applicable service exposure, including contaminated water, hydrocarbons, intermittent immersion, ultraviolet exposure, weathering and other environmental conditions at Gourikwa Power Station;
d. accommodates the assessed movement of cracks, joints and interfaces where movement is expected;
e. restores the required watertightness, durability and functional performance of the affected structure;
f. does not damage embedded waterstops, reinforcement, adjoining Plant and Materials or existing structures;
g. does not obstruct intended drainage paths or create water traps; and
h. addresses transitions and interfaces between existing and new materials and between different repair or sealing systems.
2 Where the Contractor selects a proprietary repair or sealant system, the components forming the system are chemically and physically compatible and are used within the limitations stated by the Manufacturer.
3 Where products or components from different Manufacturers are proposed as part of one system, the Contractor demonstrates their compatibility as part of the Contractor design submission.
4 Temporary works designed by the Contractor take account of the loads, Site conditions, existing structures, operational interfaces and construction sequence applicable to their use and are capable of being removed without damage to the permanent works.
5 The Contractor’s design does not change a requirement of the Employer’s design or this Works Information unless the Project Manager instructs the resulting change to the Works Information
3.5 [bookmark: _Toc137798060][bookmark: _Toc229128263][bookmark: _Toc240874454]Use of Contractor’s design
1 In addition to the rights stated in clause 22.1 of the conditions of contract and the intellectual-property provisions of the Contract Data, the Employer may use and copy the Contractor’s design for the construction, Completion, operation, inspection, maintenance, repair, alteration, replacement and future modification of the affected assets.
2 The Contractor obtains from its designers, Subcontractors, Manufacturers and suppliers the rights necessary to permit the Employer to exercise the rights stated in this section.
3 The Contractor provides the final accepted Contractor design and all subsequent accepted revisions as part of the final records required for the works.
3.6 [bookmark: _Toc137798061][bookmark: _Toc229128264][bookmark: _Toc240874455]Design of Equipment
1 [bookmark: _Toc137798062][bookmark: _Toc229128265]The Contractor remains responsible for the design, suitability, stability, safe use, operation and maintenance of its Contractor’s Equipment and temporary arrangements used to Provide the Works.
2 This includes, as applicable:
a. scaffolding and working platforms;
b. temporary access systems;
c. pumps, hoses and temporary tanks used for dewatering and water transfer;
d. lifting and material-handling Equipment;
e. temporary containment arrangements;
f. inspection drones or camera systems;
g. high-pressure jetting Equipment;
h. vacuum-assisted flushing Equipment; and
i. other Contractor’s Equipment required to Provide the Works.
3 Where instructed by the Project Manager in accordance with clause 23.1 of the conditions of contract, the Contractor submits particulars of the design of its Equipment.
4 The particulars include, as applicable:
a. drawings and relevant calculations;
b. safe working loads, capacities and operating limits;
c. certificates and statutory inspection records;
d. Manufacturer’s information and operating requirements; and
e. inspection and maintenance requirements necessary for safe use.
5 The Contractor ensures that Contractor’s Equipment requiring statutory inspection, testing, certification or authorisation is not used until the applicable requirements have been satisfied.
6 Review, inspection or acceptance of information relating to Contractor’s Equipment does not reduce the Contractor’s responsibility for its design, suitability, condition or safe use.
3.7 [bookmark: _Toc240874456]Equipment required to be included in the works
1 [bookmark: _Toc137798063][bookmark: _Toc229128266]None. 
2 Inspection, pumping, temporary water-storage, access, cleaning, drainage-inspection, high-pressure jetting, vacuum-flushing and other Equipment used by the Contractor to Provide the Works remains Contractor’s Equipment and is not incorporated into the permanent works.
[bookmark: _Toc240874457]

3.8 As-built drawings, operating manuals and maintenance schedules
1 The Contractor maintains the information necessary to prepare accurate as-built records as the works proceed. 
2 Before Completion, the Contractor submits the final as-built and handover information applicable to the works in accordance with the document-format requirements stated in Section 2.2. 
3 The final as-built information includes, as applicable:
a. final Defect Maps and repair-location schedules showing the location and type of completed repairs;
b. marked-up and final as-built drawings showing permanent changes made during the works;
c. joint, crack and repair schedules identifying the completed repair, installed material or system and relevant product or batch reference;
d. final drainage-route information showing inspected and cleaned sections, access points and identified residual defects or limitations; and
e. the final accepted Contractor design and revisions required under Section 3.
4 The Contractor submits the photographs, drainage-inspection videos, inspection reports, test records, material certificates, quality records, waste records, warranties and other Completion records required by this Works Information as part of the final records. 
5 No separate operating manual is required for permanent mechanical or process Equipment under this contract. 
6 For proprietary repair and sealant systems incorporated into the works, the Contractor provides the Employer with the applicable:
a. Manufacturer’s Technical Data Sheets;
b. inspection and maintenance recommendations;
c. recommended inspection intervals;
d. cleaning requirements;
e. compatible materials for future maintenance or repair;
f. restrictions or precautions affecting future use or maintenance; and
g. warranties or guarantees.
7 The information required by paragraph 6 is coordinated with the handover and technology-transfer information required under Section 2.14. 
8 As-built drawings identify the final installed or repaired condition and do not merely reproduce the Employer’s original drawings where the actual works differ. 
9 Completion is not achieved until the material as-built and handover information required by this Works Information has been submitted in a complete and usable form.
4 [bookmark: _Toc137798064][bookmark: _Toc229128267][bookmark: _Toc240874458]Procurement
4.1 [bookmark: _Toc137798065][bookmark: _Toc229128268][bookmark: _Toc240874459]People
4.1.1 [bookmark: _Toc137798066][bookmark: _Toc229128269][bookmark: _Toc240874460]Minimum requirements of people employed on the Site
1 [bookmark: _Toc137798067][bookmark: _Toc229128270]The Contractor provides people who are competent, suitably trained and experienced for the activities they perform. 
2 People carrying out specialist activities, including:
a. condition assessment;
b. NDT;
c. concrete repair;
d. crack assessment and injection;
e. joint, waterstop and sealant repair and installation;
f. drainage inspection and flushing;
g. cleaning and degreasing; and
h. contaminated-water, sludge and waste handling,
i. have demonstrated competence appropriate to the activity.
3 Where a proprietary material or repair system requires installation by trained, approved or experienced applicators, the Contractor provides evidence of the applicable training, experience or Manufacturer authorisation before the relevant work commences. 
4 Professional services and statutory functions are carried out by persons having the qualifications, professional registration or statutory competency required by applicable law or expressly required elsewhere in this Works Information. 
5 Structural integrity reports and other professional engineering reports required by this Works Information are prepared and signed by a Professional Civil Engineer or Professional Civil Engineering Technologist, as applicable to the work being assessed. 
6 The Contractor provides evidence of competency, qualifications, professional registration, Manufacturer authorisation or training when required by the Project Manager or Supervisor for work within that person’s contractual function. 
7 The requirements of this section apply equally to the Contractor’s employees and the employees of its Subcontractors..
4.1.2 [bookmark: _Toc240874461]BBBEE and preferencing scheme
1 The Contractor complies with the B-BBEE and preferential-procurement obligations, commitments and undertakings which form part of this contract.
2 The Contractor complies with the requirements concerning changes to its B-BBEE status stated in the Contract Data.
4.2 [bookmark: _Toc137798068][bookmark: _Toc229128272][bookmark: _Toc240874462]Subcontracting
4.2.1 [bookmark: _Toc137798069][bookmark: _Toc229128273][bookmark: _Toc240874463]Preferred subcontractors
1 No preferred or nominated Subcontractors are identified by the Employer.
2 The Contractor selects its Subcontractors subject to clause 26 of the conditions of contract and the requirements of this Works Information.
3 Subcontracting does not reduce the Contractor’s responsibility to Provide the Works in accordance with the contract.
4.2.2 [bookmark: _Toc137798070][bookmark: _Toc229128274][bookmark: _Toc240874464]Subcontract documentation, and assessment of subcontract tenders
1 The Contractor submits the name of each proposed Subcontractor to the Project Manager for acceptance in accordance with clause 26.2.
2 The Contractor submits the proposed conditions of contract for each subcontract for acceptance where required by clause 26.3.
3 Where an NEC contract is proposed and the Project Manager instructs the Contractor to do so, the Contractor submits the proposed subcontract contract data for acceptance in accordance with clause 26.4.
4 The Contractor ensures that each subcontract contains requirements sufficient to enable the Contractor to comply with the obligations applicable to the subcontracted work, including, where relevant:
a. health and safety;
b. environmental management;
c. quality assurance, inspections and testing;
d. Contractor design;
e. confidentiality and intellectual property;
f. programme and coordination;
g. Site access and security;
h. records and Completion documentation; and
i.  insurance and statutory requirements.
5 The Contractor does not include conditions in a subcontract which prevent or restrict compliance with this contract.
6 Where specialist competence, Manufacturer authorisation, professional registration or another qualification is required by this Works Information, the Contractor demonstrates that the proposed Subcontractor meets that requirement before the relevant work commences.
4.2.3 [bookmark: _Toc137798071][bookmark: _Toc229128275][bookmark: _Toc240874465]Limitations on subcontracting
1 No additional percentage or value limitation on subcontracting is imposed by this Works Information.
2 The Contractor remains responsible for ensuring that all subcontracted work is carried out by competent persons and organisations meeting the requirements of Section 4.1 and the applicable requirements of this Works Information.
3 The Contractor does not subcontract work to a person or organisation which does not possess the competency, statutory authorisation, professional registration or Manufacturer approval expressly required for that work.
4.2.4 [bookmark: _Toc137798072][bookmark: _Toc229128276][bookmark: _Toc240874466]Attendance on subcontractors
1 The Contractor provides the management, supervision, coordination, access arrangements, permits, temporary services, facilities, protection, setting out, quality control and records necessary for its Subcontractors to carry out their work. 
2 The Contractor coordinates its Subcontractors with the Employer, Others and other Subcontractors so that subcontracted activities do not adversely affect safety, operations, quality or the Accepted Programme. 
3 The Contractor remains the contractual point of responsibility for the performance and coordination of its Subcontractors
4.3 [bookmark: _Toc137798073][bookmark: _Toc229128277][bookmark: _Toc240874467]Plant and Materials
4.3.1 [bookmark: _Toc137798074][bookmark: _Toc229128278][bookmark: _Toc240874468]Quality
1 Plant and Materials incorporated into the works are new, undamaged, within their applicable shelf life and suitable for the intended use, substrate and service exposure. 
2 Plant and Materials comply with the requirements of this Works Information, the accepted Contractor design where applicable, and the Manufacturer’s requirements. 
3 Repair materials and components forming part of a system are chemically and physically compatible. 
4 Repair mortars are suitable for the existing concrete and provide the strength, durability and performance required by this Works Information. 
5 Sealants, primers, backing materials, coatings and associated components are compatible with the substrate, adjoining materials and the environmental or chemical exposure applicable to the relevant structure. 
6 Plant and Materials which are damaged, contaminated, incorrectly stored, expired or lacking required traceability are not incorporated into the works
4.3.2 [bookmark: _Toc137798075][bookmark: _Toc229128279][bookmark: _Toc240874469]Plant & Materials provided “free issue” by the Employer
1 [bookmark: _Toc137798076][bookmark: _Toc229128280]The Employer provides no free-issue Plant or Materials under this Works Information.
2 The Contractor provides all Plant and Materials required to Provide the Works.
3 Any subsequent provision of Plant or Materials by the Employer is dealt with through the applicable instruction and contract procedures
4.3.3 [bookmark: _Toc240874470]Contractor’s procurement of Plant and Materials
1 The Contractor procures, transports, handles, stores and protects Plant and Materials so that their quality and suitability are maintained until incorporation into the works. 
2 Proprietary repair, sealant and coating products are stored, prepared, mixed, applied and cured in accordance with the Manufacturer’s current written instructions and the accepted technical submission. 
3 Materials are not used after expiry of their shelf life or usable pot life. 
4 Plant and Materials requiring controlled storage are stored within the temperature, moisture, contamination-control and other conditions stated by the Manufacturer. 
5 Materials are kept in identifiable containers or packaging with Manufacturer, product, batch and expiry information traceable to the quality records required under Section 2.6. 
6 The Contractor submits the relevant Technical Data Sheets, Safety Data Sheets, certificates and Manufacturer information before the material is incorporated into the works where required by Section 2.6
4.3.4 [bookmark: _Toc137798077][bookmark: _Toc229128281][bookmark: _Toc240874471]Spares and consumables
1 No permanent spares are required unless expressly stated elsewhere in this Works Information. 
2 The Contractor provides all consumables required to Provide the Works. 
3 Unused Contractor consumables and surplus Plant and Materials are removed from the Site at Completion unless otherwise instructed by the Project Manager.
4.4 [bookmark: _Toc137798078][bookmark: _Toc229128282][bookmark: _Toc240874472]Tests and inspections before delivery
1 Before delivery to the Working Areas, the Contractor provides the certificates, batch records, test reports and other pre-delivery quality records required by this Works Information, the accepted Quality Control Plan or Inspection and Test Plan. 
2 The records include, as applicable:
a. Manufacturer’s certificates and compliance documentation;
b. batch and traceability records;
c. reinforcement certificates;
d. ready-mixed concrete or concrete constituent certificates;
e. sealant, primer, backing material, repair mortar, epoxy and other proprietary repair-system certificates; and
f. other pre-delivery test evidence required for the relevant Plant and Materials.
3 The Contractor gives the Supervisor reasonable notice of any pre-delivery test or inspection identified as a Witness Point or Hold Point in the accepted Quality Control Plan or Inspection and Test Plan. 
4 The Supervisor may inspect Plant and Materials at the Manufacturer’s premises, supplier’s premises, storage facility or another Working Area before delivery or incorporation into the works. 
5 Plant and Materials are not delivered for incorporation into the works where a required pre-delivery Hold Point has not been released. 
6 Where this Works Information requires a particular Plant or Material to be tested or inspected before delivery, the Contractor does not bring that Plant or Material to the Working Areas until the Supervisor has notified the Contractor that it has passed the required test or inspection. 
7 Inspection, witnessing or review by the Supervisor does not constitute acceptance of Plant and Materials which do not comply with the contract and does not reduce the Contractor’s responsibility for their quality or suitability
4.5 [bookmark: _Toc137798079][bookmark: _Toc229128283][bookmark: _Toc240874473]Marking Plant and Materials outside the Working Areas
1 Plant and Materials intended for incorporation into the works and kept outside the Working Areas are identified sufficiently to maintain traceability to this contract. 
2 Where applicable, the identification includes:
a. the contract number;
b. the relevant asset or work area;
c. the Manufacturer or supplier;
d. the product or material description;
e. batch, heat, lot or serial number; and
f. the relevant inspection, test or quality record reference.
3 Identification is maintained until the Plant and Materials are delivered to the Working Areas and incorporated into the works. 
4 Marking, tagging or other identification does not damage or impair the suitability of the Plant and Materials. 
5 Where Manufacturer packaging already provides adequate traceability, additional physical marking of the Plant or Materials is not required
4.6 [bookmark: _Toc137798080][bookmark: _Toc229128284][bookmark: _Toc240874474]Contractor’s Equipment (including temporary works).
1 The Contractor provides all Contractor’s Equipment necessary to Provide the Works. 
2 Contractor’s Equipment is:
a. suitable for the activity for which it is used;
b. maintained in a safe and serviceable condition;
c. operated by competent persons;
d. inspected, tested and certified where required by applicable law, Manufacturer requirements or this Works Information; and
e. used in a manner which does not damage the existing works, Plant and Materials, structures or the environment.
3 Contractor’s Equipment used for dewatering, water transfer, drainage inspection, flushing, high-pressure cleaning, concrete repair, lifting, access and temporary works is selected to suit the relevant Site conditions and operational constraints at Gourikwa Power Station. 
4 Equipment used in or adjacent to contaminated water, sludge, hydrocarbons or other contaminated material is cleaned, maintained and managed so that contamination is not spread to unaffected areas. 
5 The Contractor provides drip trays, spill-control measures and other containment measures appropriate to Contractor’s Equipment where leakage of fuel, oil, hydraulic fluid or other substances could contaminate the Site. 
6 Contractor’s Equipment which is unsafe, defective, uncertified where certification is required, or unsuitable for the intended use is not used in Providing the Works. 
7 The Contractor removes its Contractor’s Equipment, temporary facilities and associated waste from the Site when no longer required and at Completion, unless otherwise instructed by the Project Manager. 
8 The requirements of this section do not reduce the Contractor’s responsibilities for the design of Contractor’s Equipment and temporary works stated in Section 3.6
4.7 [bookmark: _Toc240874475]Cataloguing requirements by the Contractor
Not applicable.
5 [bookmark: _Toc137798082][bookmark: _Toc229128285][bookmark: _Toc240874476]Construction 
5.1 [bookmark: _Toc137798083][bookmark: _Toc229128286][bookmark: _Toc240874477]Temporary works, Site services & construction constraints
5.1.1 [bookmark: _Toc137798084][bookmark: _Toc229128287][bookmark: _Toc240874478]Employer’s Site entry and security control, permits, and Site regulations
1 The Contractor complies with the access, induction, security, permit, isolation and Site-regulation requirements applicable at Gourikwa Power Station. 
2 The Contractor obtains the applicable permit, authorisation or work-area release required before commencing the relevant activity. 
3 Access to the Site or a work area does not constitute operational release of the affected:
a. Gourikwa Clean Water Dam;
b. Gourikwa Dirty Water Dam;
c. fuel-containment area;
d. tank-to-foundation interface;
e. underground clean or dirty stormwater drainage system;
f. berm and erosion-repair work area;
g. hazardous-waste skip containment work area; or
h. other affected asset,
for the Contractor to commence work.
4 The Contractor coordinates the required access, permits, isolations and operational releases sufficiently in advance to comply with the Accepted Programme. 
5 The Contractor ensures that its employees and Subcontractors comply with the access, induction, security and permit requirements applicable to the area in which they work. 
6 Contractor personnel and vehicles remain within the areas and routes made available by the Employer and comply with Site security instructions. 
7 Plant, Materials, Contractor’s Equipment and other items brought onto or removed from the Site are subject to the Employer’s applicable security and access-control requirements. 
8 Where an activity requires an isolation, permit-to-work, confined-space control, hot-work control or other Site-specific authorisation, the Contractor does not commence that activity until the required authorisation is in place. 
9 Compliance with Site access, security, induction or permit requirements does not relieve the Contractor from complying with the health and safety, environmental, quality and other requirements of this Works Information.
5.1.2 [bookmark: _Toc137798085][bookmark: _Toc229128288][bookmark: _Toc240874479]Restrictions to access on Site, roads, walkways and barricades
1 The Contractor restricts its activities to the areas of the Site made available by the Employer for the works. 
2 The Contractor uses only the access routes, roads, walkways, laydown areas and work areas authorised by the Employer. 
3 The Contractor does not obstruct:
i. operational roads;
j. emergency access routes;
k. pedestrian walkways;
l. access to operating Plant;
m. firefighting equipment;
n. drainage routes; or
o. other areas required for Power Station operations,
4 unless the obstruction has been agreed with the Employer and suitable temporary arrangements are in place.
5 The Contractor provides and maintains barricades, warning signs, temporary barriers and other controls appropriate to the hazards created by the works. 
6 Open excavations, exposed edges, open chambers, drainage access points, dewatered structures and other hazardous areas are protected against unauthorised or accidental access. 
7 Barricading and temporary access arrangements are maintained in a safe condition and are removed when no longer required. 
8 Where the works affect an existing road, walkway or access route, the Contractor:
a. coordinates the restriction with the Employer before implementation;
b. provides safe alternative access where required; and
c. reinstates the affected area after completion of the work.
9 The Contractor prevents mud, debris, repair materials, contaminated material and waste generated by the works from obstructing or contaminating roads, walkways and drainage routes. 
10 The Contractor does not store Plant, Materials, Contractor’s Equipment or waste outside designated areas or in a manner which interferes with Power Station operations. 
11 The Contractor complies with any additional temporary access restrictions or traffic-control requirements communicated by the Employer for operational or safety reasons
5.1.3 [bookmark: _Toc137798086][bookmark: _Toc229128289][bookmark: _Toc240874480]People restrictions on Site; hours of work, conduct and records
1 The Contractor complies with the working hours, access restrictions, conduct requirements and other personnel rules applicable at Gourikwa Power Station. 
2 Work outside the normal working hours applicable at Gourikwa Power Station, including work on weekends, public holidays or during restricted operational periods, is subject to prior arrangement with the Employer and the applicable access, permit and operational requirements. 
3 The Contractor allows for the applicable Site working-hour and access constraints in the Accepted Programme. 
4 The Contractor makes attendance records available to the Project Manager or Supervisor on request. 
5 The Contractor manages the access and conduct of its Subcontractors and ensures that they comply with the same Site restrictions and requirements applicable to the Contractor. 
6 Contractor personnel comply with the Employer’s Site rules relating to security, conduct, prohibited activities and use of Site facilities.
5.1.4 [bookmark: _Toc137798087][bookmark: _Toc229128290][bookmark: _Toc240874481]Health and safety facilities on Site 
1 The Contractor provides and maintains the first-aid, emergency, welfare, washing, hygiene and decontamination facilities required for its activities, the number of people employed and the hazards identified in its risk assessments. 
2 The Contractor provides the PPE and emergency Equipment required by applicable law, the Employer’s Site requirements and Section 2.4. 
3 Facilities made available by the Employer, if any, are identified in the Site Information or communicated through the applicable Site arrangements and do not reduce the Contractor’s statutory or contractual health and safety responsibilities.
5.1.5 [bookmark: _Toc137798088][bookmark: _Toc229128291][bookmark: _Toc240874482]Environmental controls, fauna & flora, dealing with objects of historical interest 
1 Environmental controls and requirements relating to soil, water, vegetation, fauna, waste, pollution prevention and rehabilitation are stated in Section 2.5. 
2 The Contractor confines disturbance to the areas required to Provide the Works and protects existing vegetation, drainage routes and adjoining environmental features from unnecessary disturbance. 
3 The Contractor does not remove, damage or unnecessarily disturb vegetation or fauna outside the areas required for the works. 
4 Where the Contractor discovers an object of value or historical interest within the Site, it notifies the Project Manager and deals with the object in accordance with clause 73.1 of the conditions of contract..
5.1.6 [bookmark: _Toc137798089][bookmark: _Toc229128292][bookmark: _Toc240874483]Title to materials from demolition and excavation
1 The Contractor obtains no title to materials arising from demolition, excavation, removal, cleaning or repair activities unless expressly stated otherwise in this Works Information or instructed by the Project Manager. 
2 The Contractor does not reuse, remove for sale, sell or otherwise dispose of such materials for its own benefit. 
3 Materials classified or managed as waste are handled, stored, transported and disposed of in accordance with Section 2.5 and applicable law. 
4 Contaminated concrete, soil, sludge, joint materials, sealants, debris and other contaminated material arising from the works are treated as waste unless the Project Manager instructs otherwise. 
5 Materials which the Employer identifies for retention or recovery are protected and handed over at the location instructed by the Project Manager
5.1.7 [bookmark: _Toc137798090][bookmark: _Toc229128293][bookmark: _Toc240874484]Cooperating with and obtaining acceptance of Others
1 The Contractor co-operates with the Employer and Others carrying out work in or adjacent to the Working Areas. 
2 The Contractor coordinates its activities so that the works do not unnecessarily interfere with:
a. operation and maintenance activities at Gourikwa Power Station;
b. work being carried out by the Employer or Others;
c. access to operating Plant and infrastructure;
d. Site traffic and emergency access; and
e. environmental, safety and security controls.
3 The Contractor provides information reasonably required by the Employer or Others for coordination of interfaces with the works. 
4 The Contractor obtains any statutory approval, permit, consent or acceptance required for work for which it is responsible. 
5 Where Contractor design requires approval, consent or acceptance by a statutory authority or other person, the Contractor obtains that approval, consent or acceptance in accordance with clause 27.1 of the conditions of contract. 
6 The Contractor allows for coordination with the Employer and Others in its programme where such coordination is necessary to Provide the Works. 
7 Cooperation with or review by Others does not reduce the Contractor’s responsibility to Provide the Works in accordance with the contract. 
8 Where an instruction or requirement from Others conflicts with the contract or may affect the Contractor’s ability to Provide the Works, the Contractor notifies the Project Manager before implementing the affected requirement.
5.1.8 [bookmark: _Toc137798091][bookmark: _Toc229128294][bookmark: _Toc240874485]Publicity and progress photographs 
1 The Contractor does not take photographs, video footage, drone imagery or other images of the works or Site without the prior written consent of the Project Manager in accordance with clause Z4.4 of the Contract Data. 
2 Where photographs, videos or other images are required by this Works Information for condition assessment, Defect Mapping, inspection, quality control, testing or as-built records, the Contractor obtains the required written consent before commencing the applicable image-recording activities. 
3 Images taken for contract purposes:
a. comply with the applicable Gourikwa Power Station security and access requirements;
b. are limited to what is reasonably required for the contractual record;
c. identify the relevant asset or work area, date and activity where practicable;
d. are indexed and retained as controlled contract records; and
e. are included in the applicable inspection, quality or Completion records.
4 The Contractor does not use images of the Site or works for publicity, advertising, social media, marketing, media communication or any external publication without the Employer’s prior written consent. 
5 Drone use is subject to the Project Manager’s prior written consent and all applicable Site, security, safety and statutory requirements.
5.1.9 [bookmark: _Toc137798092][bookmark: _Toc229128295][bookmark: _Toc240874486]Contractor’s Equipment
1 The Contractor positions, operates, stores and removes Contractor’s Equipment so that it does not:
a. obstruct access to operating Plant, roads, walkways, emergency routes or drainage systems;
b. interfere with Gourikwa Power Station operations;
c. damage existing structures, services, surfacing or environmental controls; or
d. create an unacceptable safety, environmental or operational risk.
2 The Contractor uses only those areas made available by the Employer for the storage, parking or operation of Contractor’s Equipment.
3 Contractor’s Equipment is not left unattended in operational or restricted areas unless the applicable Site requirements permit this.
4 The Contractor coordinates the use of large, mobile or lifting Equipment with the Employer where its operation may affect access, security, operations or other work on Site.
5 Temporary hoses, cables, pumping lines and similar Equipment crossing roads or walkways are protected, routed or barricaded so that safe access is maintained.
6 The Contractor removes Contractor’s Equipment from an affected work area when it is no longer required or when required to restore access or operational use.
7 The requirements of this section are additional to the requirements of Section 4.6 Contractor’s Equipment.
5.1.10 [bookmark: _Toc137798093][bookmark: _Toc229128296][bookmark: _Toc240874487]Equipment provided by the Employer
1 [bookmark: _Toc137798094][bookmark: _Toc229128297]The Employer provides no Equipment for the Contractor’s use in Providing the Works unless expressly stated elsewhere in this Works Information. 
2 Where the Employer subsequently makes Equipment available for the Contractor’s use, the conditions of use, responsibility, access, operation and return of that Equipment are agreed or instructed before use. 
3 The Contractor does not assume the availability of Employer-owned lifting Equipment, vehicles, pumps, tools, access Equipment or other operational Equipment. 
4 Any use of Employer-provided Equipment does not reduce the Contractor’s responsibility to Provide the Works in accordance with the contract.
5.1.11 [bookmark: _Toc240874488] Site services and facilities
1 Except where expressly stated in this Works Information or the Site Information, the Employer does not provide Site services or temporary facilities for use by the Contractor. 
2 The Contractor provides all temporary services, connections, distribution systems, storage, lighting and other facilities necessary to Provide the Works. 
3 Where an Employer water-supply point is made available, the Contractor provides all hoses, tanks, pumps, fittings, temporary connections and distribution necessary from the identified supply point to its work area. 
4 The Contractor does not connect to, alter or interfere with an Employer electrical, water, drainage, fire-protection, fuel, telecommunications or other service without the required Site authorisation and permits. 
5 The Employer does not guarantee the continuity, pressure, flow rate or uninterrupted availability of any temporary service made available to the Contractor unless expressly stated otherwise in the Site Information. 
6 The Contractor makes adequate contingency arrangements for interruption or temporary unavailability of any Employer service on which it elects to rely. 
7 Waste collection, handling, temporary storage, transport and disposal are carried out in accordance with Section 2.5. The Contractor does not assume that an Employer waste-transfer or disposal facility is available unless the Site Information expressly identifies that facility and the applicable conditions of use. 
8 Laydown, storage and Site-establishment areas are limited to areas made available by the Employer. The Contractor does not assume exclusive use of an area unless expressly stated. 
9 The Contractor provides everything else necessary to Provide the Works.
5.1.12 [bookmark: _Toc137798095][bookmark: _Toc229128298][bookmark: _Toc240874489]Facilities provided by the Contractor
1 The Contractor provides, maintains and removes the temporary facilities necessary to Provide the Works, except for facilities expressly stated in this Works Information or the Site Information as being provided by the Employer. 
2 The Contractor provides, as applicable to the works:
a. Site offices and administration facilities;
b. storage areas and secure stores;
c. laydown and material-preparation areas;
d. welfare and hygiene facilities;
e. temporary lighting;
f. temporary water-storage and distribution facilities;
g. temporary power-generation or distribution facilities where required;
h. waste-storage and segregation areas;
i. spill-control and environmental-protection facilities;
j. temporary access and working platforms; and
k. other temporary facilities necessary for the safe and efficient execution of the works.
3 The location of temporary facilities is subject to the areas made available by the Employer and the applicable Site, safety, environmental and security requirements. 
4 The Contractor does not erect, connect, alter or extend temporary facilities in a manner that interferes with existing Plant, services, roads, drainage, access routes or Power Station operations. 
5 Temporary facilities are maintained in a clean, safe and serviceable condition for the period they are required. 
6 The Contractor removes its temporary facilities and associated temporary services when no longer required and reinstates the affected areas before Completion. 
7 Removal and reinstatement include, as applicable, removal of temporary foundations, connections, barriers, storage areas, waste and contamination arising from the Contractor’s use of the area.
5.1.13 [bookmark: _Toc137798096][bookmark: _Toc229128299][bookmark: _Toc240874490]Existing premises, inspection of adjoining properties and checking work of Others
1 The Contractor does not assume that existing Employer offices, workshops, stores, welfare facilities, ablutions, parking areas or other premises are available for its use unless expressly made available by the Employer. 
2  Where the Employer permits the Contractor to use an existing premise or facility, the Contractor:
a. uses it only for the purpose for which it is made available;
b. complies with the applicable Site, safety, environmental and security requirements;
c. keeps the premise or facility clean and in a serviceable condition;
d. does not alter or modify it without the Employer’s prior authorisation; and
e. returns it in substantially the condition in which it was made available, fair wear and tear excepted.
3 Existing structures and infrastructure forming part of the works, including the Gourikwa Clean Water Dam, Gourikwa Dirty Water Dam, associated drainage infrastructure, fuel-containment areas, tank foundations, berm and erosion-repair areas and hazardous-waste skip containment work area, are not facilities provided for the Contractor’s general use. 
4 Damage caused by the Contractor to Employer premises, facilities or existing infrastructure is repaired by the Contractor.
5.1.14 [bookmark: _Toc137798097][bookmark: _Toc229128300][bookmark: _Toc240874491]Survey control and setting out of the works
1 The Contractor is responsible for setting out the works from the dimensions, levels, locations and other information stated in this Works Information and the drawings listed in Section 7. 
2 Before commencing the affected work, the Contractor verifies the accessible Site dimensions, levels and interfaces relevant to the setting out. 
3 The Contractor verifies and records, as applicable:
a. existing Site levels;
b. drainage falls and interfaces;
c. locations and limits of identified repairs;
d. existing joints, cracks and other features forming the basis of remedial work;
e. tank-to-foundation interfaces; and
f. operational clearances and access constraints affecting construction.
g. berm alignment, levels, tie-in points and erosion-repair limits;
h. hazardous-waste skip containment area position, slab levels, bund-wall alignment and dimensions; and
i. low-point sump position and falls within the containment area.
4 Where repair locations, joint positions or defect extents can only be established after cleaning, dewatering or detailed inspection, the Contractor records and marks the affected locations before commencing the applicable repair. 
5 The Contractor maintains sufficient setting-out and survey records to demonstrate the location and extent of the completed works. 
6 Setting-out and survey records relevant to permanent repairs form part of the quality and as-built records required by this Works Information. 
7 Where the Contractor identifies an inconsistency between the actual Site condition and the dimensions, levels or setting-out information contained in the Employer’s information, it notifies the Project Manager before proceeding with the affected work. 
8 Verification or setting out by the Contractor does not make the Contractor responsible for the adequacy of the Employer’s design or for providing permanent-design dimensions, levels or geometry which are not stated in this Works Information.
5.1.15 [bookmark: _Toc137798098][bookmark: _Toc229128301][bookmark: _Toc240874492]Excavations and associated water control
1 The Employer coordinates the operational release of each pollution-control dam and identifies the applicable Gourikwa Power Station requirements governing the permitted transfer, treatment, storage or disposal route for water removed from the dam. 
2 Following the required operational release, the Contractor carries out the bulk dewatering required to enable the detailed inspection, cleaning and remedial works stated in this Works Information. 
3 The Contractor provides the pumps, hoses, temporary pipework, tanks, temporary containment and other Contractor’s Equipment necessary for the dewatering operation. 
4 The Contractor does not discharge, transfer or dispose of water from a pollution-control dam except through a route permitted by the applicable Gourikwa Power Station water-management arrangements, environmental authorisations and Section 2.5. 
5 Following bulk dewatering, the Contractor controls residual water and water entering the released Working Area so that safe access, cleaning, inspection, preparation, repair, curing and testing can be carried out. 
6 The Contractor prevents water from entering prepared or curing repair areas and manages temporary pumping, hoses, tanks and containment so that contaminated water is not released to the environment or clean stormwater system. 
7 Contaminated water, sludge, sediment, wash water and other material arising from dewatering or water-control activities are managed in accordance with Section 2.5. 
8 Where excavation is required for the Gourikwa works, the Contractor protects the excavation against collapse, flooding, erosion and damage resulting from its activities and maintains it in a safe condition until backfilling or permanent construction is completed. 
9 The Contractor controls water entering excavations or opened work areas so that the founding material, existing structure and prepared repair surfaces are not softened, eroded, contaminated or otherwise damaged. 
10 Where unexpected groundwater, contaminated material, buried structures or another Site condition is encountered which may affect the works, the Contractor records the condition and notifies the Project Manager before proceeding with the affected work.
11 Excavation and founding preparation for the hazardous-waste skip containment area are carried out in accordance with the permanent requirements of this Works Information, including removal of topsoil where applicable, excavation to the required formation, ripping and recompaction of the founding layer, replacement of unsuitable material with G7 where required, and compaction to the specified density.
12 The Contractor protects prepared founding material against softening, erosion, contamination and disturbance before placement of the blinding layer and reinforced concrete slab.
5.1.16 [bookmark: _Toc137798099][bookmark: _Toc229128302][bookmark: _Toc240874493]Underground services, other existing services, cable and pipe trenches and covers
1 The Contractor uses existing manholes and access chambers, where practicable, for the non-intrusive inspection of the underground stormwater drainage systems and verifies the relevant drainage route before flushing.
2 Before excavation, drilling or other intrusive work, the Contractor identifies and marks accessible underground and above-ground services within or adjacent to the affected work area using the available Site information, drawings, visible service features and suitable detection methods where required.
3 No excavation or intrusive work proceeds until the applicable service-clearance, permit and isolation requirements have been satisfied.
4 Existing pipes, cables, drainage systems, oil-water separators, manholes, sumps, ducts and other services remain operational unless the Project Manager instructs otherwise and the applicable Gourikwa Power Station requirements permit the interruption.
5 The Contractor does not disconnect, divert, relocate, alter or permanently cover an existing service unless the Project Manager instructs the change to the Works Information.
6 The Contractor protects existing services against damage arising from its excavation, construction, drainage-flushing, lifting, access and Contractor’s Equipment activities.
7 Where work is carried out in close proximity to an existing service, the Contractor uses appropriate excavation and construction methods to prevent damage to the service and to maintain safe access to it.
8 Where an unidentified or incorrectly located service is encountered, the Contractor:
a. stops the affected work where continued work could damage the service or create a safety or operational risk;
b. protects the exposed service and work area;
c. records the condition and location; and
d. notifies the Project Manager before proceeding with the affected work
9 Damage to an existing service caused during the Contractor’s activities is immediately reported to the applicable Site representative and the Project Manager. The Contractor makes the area safe and carries out the required repair or reinstatement in accordance with the applicable Site requirements and the contract.
10 Any permanent alteration to an existing service forming part of the completed works is recorded in the applicable as-built documentation
5.1.17 [bookmark: _Toc137798100][bookmark: _Toc229128303][bookmark: _Toc240874494]Control of noise, dust, water and waste 
1 The Contractor carries out the works so that noise, dust, water, waste and other emissions arising from its activities are controlled and do not cause unnecessary nuisance, pollution, contamination or interference with Gourikwa Power Station operations.
2 The Contractor complies with the environmental requirements stated in Section 2.5.
3 The Contractor controls dust generated by activities including:
a. concrete cutting, breaking, drilling and grinding;
b. removal of deteriorated concrete and joint materials;
c. surface preparation;
d. handling of dry repair materials; and
e. movement of vehicles or Contractor’s Equipment over unsealed surfaces.
4 Dust-control measures do not result in contaminated runoff, damage to prepared surfaces or interference with the application of repair materials.
5 The Contractor manages water arising from:
a. dewatering;
b. cleaning and degreasing;
c. high-pressure cleaning or flushing;
d. drainage inspection and cleaning;
e. surface preparation; and
f. other construction activities,
so that contaminated water is not discharged to the clean stormwater system, soil or environment.
6 Water, sludge, sediment, hydrocarbons, contaminated absorbent material, removed sealant, deteriorated concrete, packaging and other waste arising from the works are collected, segregated, temporarily stored, transported and disposed of in accordance with Section 2.5 and applicable law.
7 Waste is not buried, burned or disposed of on Site except through an authorised waste-management arrangement.
8 Waste storage areas and containers are suitable for the waste being stored and are managed to prevent leakage, windblown material, scavenging and contamination of surrounding areas.
9 Hazardous or contaminated waste is kept separate from general waste and is handled in accordance with the applicable classification, storage, transport and disposal requirements.
10 The Contractor retains the waste records, disposal certificates and other documentation required by Section 2.5 and includes them in the final records.
11 The Contractor controls noise generated by its activities and complies with applicable Site requirements governing noisy work.
12 Where noisy work may interfere with Power Station operations, communication or other work in the area, the Contractor coordinates the activity with the Employer before commencing the affected work.
13 Work areas are kept reasonably clean and free of accumulated waste and debris throughout the execution of the works.
14 On completion of work in an area, the Contractor removes temporary materials, waste, debris and contamination arising from its activities and leaves the area in a clean and serviceable condition
5.1.18 [bookmark: _Toc137798101][bookmark: _Toc229128304][bookmark: _Toc240874495]Sequences of construction or installation
1 [bookmark: _Toc137798102][bookmark: _Toc229128305]Except for the sequence constraints stated in this section, the Contractor determines the detailed sequence of its activities and shows it on the Accepted Programme.
2 For pollution-control dam remedial works, the Contractor does not commence permanent repairs until:
a. the applicable access, permits and operational release have been obtained;
b. the dam has been dewatered sufficiently to permit the required inspection;
c. cleaning and degreasing required for inspection have been completed;
d. the required condition assessment, NDT and Defect Mapping have been completed;
e. the condition-assessment report and proposed remedial measures have been submitted and accepted as required by this Works Information; and
f. the applicable quality submissions and Hold Points have been established.
3 Following acceptance of the proposed remedial measures, the Contractor sequences the repairs so that preparation, installation, curing, inspection and testing are completed without contamination, damage or premature exposure of the repair system.
4 Underground drainage inspection and flushing is sequenced so that
a. the initial condition is recorded before flushing;
b. flushing is carried out only after the applicable discharge and water-management arrangements are in place; and
c. the relevant drainage section is re-inspected after flushing.
5 Fuel-containment and tank-to-foundation interface repairs are sequenced so that:
a. the applicable work area is operationally released;
b. existing Plant and adjoining surfaces are protected;
c. defective joint or sealant materials are removed and the exposed condition is inspected;
d. the applicable repair or sealant system has been accepted where acceptance is required;
e. the substrate is prepared and applicable Hold Points are released;
f. the repair or sealant system is installed in accordance with the accepted submission and Manufacturer’s requirements;
g. the required curing period is completed before the repaired area is exposed to service conditions; and
h. the completed repair is inspected, recorded and reinstated before handover.
6 Where concrete, crack, joint, waterstop or reinforcement repairs are carried out, the Contractor sequences the work so that:
a. the defect is exposed and assessed before repair;
b. the repair extent is established before permanent repair materials are placed;
c. preparation and cleaning are completed before application of repair materials;
d. the applicable inspection or Hold Point is completed before the repair is concealed;
e. curing and protection requirements are maintained; and
f. the completed repair is inspected and recorded.
7 For the berm extension and erosion-repair works, the Contractor sequences the work so that:
a. the work area is set out and existing conditions are recorded before disturbance;
b. the existing berm tie-in area is prepared and the extension is keyed and benched into the existing berm;
c. the founding area is prepared and the required G5 material is placed and compacted;
d. the clay layer is placed and compacted to the specified minimum density;
e. the berm is profiled to achieve the required drainage falls;
f. eroded areas are backfilled and stabilised;
g. topsoil is placed where required; and
h. vegetation and temporary erosion-control measures are established before the affected area is handed over.
8 For construction of the hazardous-waste skip containment area, the Contractor sequences the work so that:
a. the work area is set out and existing services and interfaces are confirmed;
b. clearing, topsoil removal and excavation are completed;
c. the founding layer is ripped, re-compacted and improved with G7 material where required;
d. the required compaction tests are completed before the foundation is covered;
e. the blinding layer is placed where required;
f. slab reinforcement, spacers, stools, embedded items and wall dowels or ties are inspected before concrete placement;
g. the reinforced concrete slab is cast, finished and cured;
h. masonry bund walls are constructed after the slab has achieved sufficient strength;
i. plaster and screed are completed and cured;
j. surfaces are prepared before application of the chemical-resistant coating system;
k. the coating system is applied and cured in accordance with the Manufacturer’s requirements;
l. coating-thickness measurements and Manufacturer compliance records are completed;
m. the containment area is subjected to the required minimum 24-hour water-retention test; and
n. the work is reinstated, cleaned and made ready for operational use.
5.1.19 [bookmark: _Toc240874496]Giving notice of work to be covered up
1 The Contractor gives the Supervisor notice before covering, enclosing, backfilling, sealing, coating or otherwise making work inaccessible for inspection.
2 Unless another period is stated in the accepted Quality Control Plan or Inspection and Test Plan, the Contractor gives the Supervisor at least five (5) Working Days’ notice before the relevant work is covered or becomes inaccessible:
3 The notice identifies:
a. the relevant asset or work area;
b. the work to be inspected;
c. the applicable drawing, repair detail, QCP or ITP reference;
d. the proposed date and time of covering or concealment; and
e. the relevant Hold Point or Witness Point, where applicable.
4 The Contractor does not proceed beyond a Hold Point until the required inspection or test has been completed and the Supervisor has confirmed release of the Hold Point
5 The requirement applies, as applicable, to:
a. prepared concrete repair surfaces before placement of repair material;
b. exposed reinforcement before repair concrete or mortar is placed;
c. prepared cracks before injection, sealing or filling;
d. prepared joints before installation of backing material, primer or sealant;
e. waterstops, joint components and expansion materials before they become concealed;
f. tank-to-foundation interface preparation before installation of the sealant system;
g. underground or concealed drainage repairs before closure or reinstatement; and
h. other work identified in the accepted QCP or ITP.
i. prepared founding material for the hazardous-waste skip containment area before placement of blinding or slab construction;
j. reinforcement, mesh, spacers, stools, dowels, wall ties and embedded items before concrete placement;
k. prepared masonry/plaster/screed substrates before application of the chemical-resistant coating system, where identified as a Hold Point or Witness Point in the accepted QCP or ITP;
l. berm founding preparation, keyed/benched tie-in areas and compacted material layers before subsequent layers are placed; and
m. other work identified in the accepted QCP or ITP.
6 Where work is covered or made inaccessible without the required notice or release, the Contractor exposes or opens the work if instructed by the Supervisor and makes good the affected area after inspection.
7 Inspection or release of work before it is covered does not reduce the Contractor’s responsibility to Provide the Works in accordance with the contract
5.1.20 [bookmark: _Toc137798103][bookmark: _Toc229128306][bookmark: _Toc240874497]Hook ups to existing works
1 No permanent mechanical, electrical, control or process hook-ups to existing Power Station systems are required unless expressly stated in this Works Information or an Employer drawing.
2 The Contractor does not connect to, disconnect, alter, isolate or interfere with an existing Power Station service or system without the applicable Site authorisation, permit and operational release.
3 Temporary connections required for water, power, drainage, pumping, waste transfer or other construction purposes are coordinated with the Employer and comply with Sections 5.1.11 and 5.1.16.
4 Before making a connection to an existing system, the Contractor verifies the accessible interface and confirms that the proposed connection will not adversely affect the existing system or Power Station operations.
5 The Contractor protects existing services and systems during temporary connection and use and removes temporary connections when no longer required.
6 Following removal of a temporary connection, the Contractor reinstates the affected existing system or interface to a safe and serviceable condition.
7 Any permanent connection or alteration not already required by the Works Information is carried out only following an instruction by the Project Manager
5.2 [bookmark: _Toc137798104][bookmark: _Toc229128307][bookmark: _Toc240874498]Completion, testing, commissioning and correction of Defects
5.2.1 [bookmark: _Ref137703695][bookmark: _Toc137798105][bookmark: _Toc229128308][bookmark: _Toc240874499]Work to be done by the Completion Date
1 On or before the Completion Date, the Contractor has done everything required to Provide the Works, except for work which this Works Information expressly states may be done after Completion.
2 Before Completion, the Contractor has:
a. completed all physical works required by this Works Information;
b. completed the required dewatering, cleaning, degreasing, inspections, condition assessments, NDT and Defect Mapping;
c. completed the accepted remedial repairs to the Gourikwa Clean Water Dam and Dirty Water Dam;
d. completed the required repairs to concrete, reinforcement, cracks, joints, waterstops, expansion-joint components and sealant systems;
e. completed the required repairs and resealing of the fuel-containment areas and tank-to-foundation interfaces;
f. completed the required inspection, flushing, cleaning and post-inspection of the underground clean and dirty stormwater drainage systems;
g. completed the berm extension and reinstatement of erosion-damaged areas;
h. completed construction of the hazardous-waste skip containment area, including the reinforced concrete slab, masonry bund walls, plaster/screed, chemical-resistant coating system and low-point sump;
i. completed all required testing, inspections, Hold Points and Witness Points;
j. completed the required compaction tests, concrete strength testing, coating-thickness measurements and water-retention testing applicable to the hazardous-waste skip containment area;
k. corrected Defects which would prevent the Employer from using the works for their intended purpose;
l. completed all required reinstatement and environmental close-out;
m. removed temporary works, waste, surplus Plant and Materials and Contractor’s Equipment which are not required for correction of Defects;
n. left the Working Areas clean, safe and ready for operational use; and
o. completed the handover requirements stated in this Works Information
3 Before Completion, the Contractor has submitted the final records required by this Works Information, including, as applicable:
a. accepted professional and structural integrity reports;
b. final condition-assessment reports;
c. Defect Maps and repair-location schedules;
d. drainage inspection videos and reports
e. inspection and test records;
f. material and product certificates;
g. calibration records;
h. non-conformance and corrective-action close-out records;
i. waste classification, transport and disposal records;
j. warranties and guarantees;
k. Manufacturer’s Technical Data Sheets and maintenance recommendations;
l. final accepted Contractor design and revisions;
m. as-built drawings and records required under Section 3.8; and
n. the completed quality data books or packs required under Section 2.6.
o. compaction test results for the hazardous-waste containment and berm works, where applicable;
p. concrete cube strength results;
q. coating dry-film-thickness records and Manufacturer compliance certificates;
r. water-retention test records for the hazardous-waste skip containment area; and
s. records confirming completed berm and erosion-control reinstatement.
4 Final records required for Completion are submitted in a complete, indexed and usable form.
5 No item of work is identified in this Works Information as being permitted to remain outstanding after Completion.
6 The Project Manager certifies Completion when the Contractor has done all the work which the Works Information states is to be done by the Completion Date and has corrected notified Defects which would have prevented the Employer from using the works and Others from doing their work.
5.2.2 [bookmark: _Toc137798106][bookmark: _Toc229128309][bookmark: _Toc240874500]Use of the works before Completion has been certified
1 The Employer may use or return to operational service a completed or substantially completed part of the works before Completion of the whole of the works where operational requirements require this.
2 Such use may include, as applicable:
a. return to service of the Gourikwa Clean Water Dam or Dirty Water Dam;
b. return to service of a fuel-containment area;
c. return to service of a repaired tank-to-foundation interface;
d. use of an inspected, flushed or repaired drainage section;
e. use of the completed hazardous-waste skip containment area; or
f. use of the completed berm and erosion-repair works.
3 Before the Employer uses or returns an affected part of the works to service, the Contractor completes the inspections, testing, curing and other technical requirements necessary for that part to be safely and properly used.
4 The Contractor provides the records reasonably required to confirm that the affected part is ready for operational use.
5 Use of a part of the works by the Employer before Completion of the whole of the works does not, by itself:
g. constitute Completion of the whole of the works;
h. constitute acceptance of Defects or non-compliant work;
i. relieve the Contractor from correcting Defects; or
j. reduce the Contractor’s obligations under the contract.
6 Where early operational use affects the Contractor’s remaining activities, access, sequence or programme, the Contractor and Project Manager deal with the effect in accordance with the conditions of contract
5.2.3 [bookmark: _Toc137798107][bookmark: _Toc229128310][bookmark: _Toc240874501]Materials facilities and samples for tests and inspections 
1 The Contractor provides all labour, materials, samples, safe access, lighting, measuring Equipment, calibrated instruments, temporary facilities and other resources necessary to carry out the tests and inspections required by this Works Information and the accepted Quality Control Plan or Inspection and Test Plan.
2 The Contractor provides, as applicable:
a. concrete cube specimens and the arrangements necessary for testing them;
b. test samples and representative material samples;
c. access, platforms and lighting required for inspection;
d. temporary filling, pumping, hoses, tanks and other water-handling arrangements where required for testing or inspection; and
e. records and certificates necessary to demonstrate the results of the test or inspection.
f. compaction-test arrangements and records for the berm and hazardous-waste containment founding layers;
g. concrete cube specimens and test arrangements for the hazardous-waste skip containment slab;
h. coating dry-film-thickness measuring equipment and records; and
i. water-retention testing arrangements for the hazardous-waste skip containment area.
3 Where an Employer water-supply point is made available in accordance with Section 5.1.11, the Contractor may use that supply subject to the applicable Site arrangements. Availability of an Employer water-supply point is not guaranteed and does not reduce the Contractor’s responsibility to provide sufficient water required for its tests and inspections.
4 The Contractor provides all hoses, temporary storage, pumping and transfer arrangements necessary for water used in its tests and inspections.
5 Following completion of a test or inspection involving water, the Contractor removes, transfers or disposes of the water through a route permitted by applicable Gourikwa Power Station and environmental requirements. Water is not discharged to the environment or clean stormwater system without the applicable authorisation.
6 The Contractor gives the Supervisor the notice required by Section 2.6 and Section 5.1.19 before each planned test or inspection.
7 Where a test or inspection identifies a Defect, the Contractor corrects the Defect and repeats the affected test or inspection in accordance with clause 40.4 of the conditions of contract.
8 The Contractor submits the results and supporting records for each required test and inspection as part of the quality and Completion records for the works.
9 Unless expressly stated otherwise in this Works Information, the Employer does not provide materials, samples, testing Equipment or temporary testing facilities for the Contractor’s tests and inspections.
5.2.4 [bookmark: _Toc137798108][bookmark: _Toc229128311][bookmark: _Toc240874502]Commissioning
1 Before an affected part of the works is returned to operational service, the Contractor completes the inspections, tests, curing periods and quality records applicable to that work.
2 The Contractor demonstrates, where applicable, that:
a. repaired concrete surfaces and structural repairs have been completed and inspected;
b. crack, joint, waterstop and sealant repairs have been completed in accordance with the accepted repair method and Manufacturer’s requirements;
c. tank-to-foundation interface repairs are complete and ready for service;
d. fuel-containment repairs are complete and free from visible defects;
e. underground stormwater drainage sections have been inspected, flushed or cleaned and re-inspected as required;
f. berm and erosion-control works have been completed and reinstated; and
g. the hazardous-waste skip containment area has completed the required concrete strength testing, coating-thickness verification, Manufacturer compliance checks and minimum 24-hour water-retention test.
3 Completion of these checks does not constitute Completion unless all other requirements for Completion stated in this Works Information and the conditions of contract have been met.
4 The Contractor provides the Supervisor and Project Manager with the applicable inspection, test and quality records required to demonstrate that the affected work is ready for use.
5 Return of an asset or part of the works to operational service does not constitute Completion of the whole of the works unless the requirements for Completion have also been satisfied.
6 Where a test or inspection required before return to service identifies a Defect, the Contractor corrects the Defect and repeats the affected test or inspection before the work is returned to service
5.2.5 [bookmark: _Toc137798109][bookmark: _Toc229128312][bookmark: _Toc240874503]Start-up procedures required to put the works into operation
1 No separate mechanical, electrical, control or process start-up procedure is required under this contract.
2 Before an affected part of the works is returned to operational use, the Contractor ensures that:
a. the applicable inspections and tests have been completed;
b. required curing periods have been completed;
c. Defects which would prevent safe or intended use have been corrected;
d. temporary works, temporary connections and Contractor’s Equipment which are no longer required have been removed;
e. the affected area has been cleaned and reinstated;
f. the required quality, test and handover records are available; and
g. the affected asset or work area is ready for use in accordance with this Works Information.
3 The Contractor does not independently return an Employer asset to operational service. Return to service is coordinated with the Employer and the applicable Gourikwa Power Station representative.
4 Where an affected part of the works is used before Completion of the whole of the works, Section 5.2.2 applies
5.2.6 [bookmark: _Toc137798110][bookmark: _Toc229128313][bookmark: _Toc240874504]Take over procedures
1 [bookmark: _Toc137798111][bookmark: _Toc229128314]Take over of the works is carried out in accordance with clause 35 of the conditions of contract and the Contract Data.
2 Before the anticipated take over of the works, the Contractor participates with the Employer in a joint handover inspection.
3 The handover inspection confirms, as applicable:
a. the status of the completed works;
b. notified Defects and any remaining minor items which do not prevent Completion;
c. that temporary works and Contractor’s Equipment not required after take over have been removed;
d. that the Working Areas have been cleaned and reinstated;
e. that applicable safety, environmental and work-area permits or temporary controls have been closed out or transferred as required;
f. that the Completion and handover records required by Sections 5.2.1 and 3.8 have been submitted; and
g. that the affected assets and work areas are suitable for return to the Employer.
4 The joint handover inspection does not replace or alter the requirements for Completion stated in Section 5.2.1.
5 The Employer is not required to take over the works before the Completion Date where this is stated in the Contract Data.
6 Where the Employer has used or taken over a part of the works before Completion of the whole of the works, the applicable provisions of clause 35 and Section 5.2.2 apply.
7 The Project Manager certifies the date upon which the Employer takes over the works, or a part of the works, and its extent in accordance with clause 35.3.
8 Take over does not relieve the Contractor of its obligations concerning Defects, warranties, guarantees or other obligations which continue after take over.
5.2.7 [bookmark: _Toc240874505]Access given by the Employer for correction of Defects
1 Where access to or use of a part of the works which the Employer has taken over is required for correction of a Defect, the Project Manager arranges the necessary access and use in accordance with clause 43.4 of the conditions of contract.
2 Access for Defect correction remains subject to the security, induction, permit, isolation, environmental and operational requirements applicable at Gourikwa Power Station.
3 The Contractor advises the Project Manager and Supervisor of the access, work area, isolation and operational requirements necessary to correct the Defect and coordinates the proposed correction with them.
4 For a Defect creating an immediate safety, environmental pollution or containment risk, the Contractor participates in urgent coordination with the Employer so that the affected area can be made safe and the Defect corrected within the applicable defect correction period.
5 The Contractor:
a. protects Power Station operations and adjacent assets while correcting the Defect;
b. maintains the required health, safety and environmental controls;
c. removes temporary arrangements and waste arising from the correction;
d. reinstates any area disturbed by the correction; and
e. provides the inspection, test and revised as-built or quality records applicable to the corrected work.
6 Correction of a Defect after take over does not constitute new or additional work where the correction is required under the Contractor’s obligations under the contract.
5.2.8 [bookmark: _Toc137798112][bookmark: _Toc229128315][bookmark: _Toc240874506]Performance tests after Completion
1 No performance tests are required after Completion unless expressly stated elsewhere in this Works Information.
2 All inspections, tests and verification required to demonstrate compliance with the Works Information are completed before Completion, except where the conditions of contract expressly permit otherwise.
3 Where a Defect is corrected after Completion and the corrected work requires testing or inspection to demonstrate compliance, the Contractor carries out the applicable test or inspection as part of the Defect correction.
4 Any such test or inspection after Completion does not constitute a separate performance-testing regime and does not alter the Contractor’s obligations concerning Defects.
5.2.9 [bookmark: _Toc137798113][bookmark: _Toc229128316][bookmark: _Toc240874507]Training and technology transfer
1 No separate formal operator-training programme is required under this contract.
2 The Contractor completes the product-specific handover, explanation and technology-transfer requirements stated in Section 2.14 before Completion.
3 Any Manufacturer-required demonstration or explanation associated with the inspection, maintenance or future repair of a proprietary repair or sealant system is included in the handover required by Section 2.14 and does not constitute a separate training programme.
5.2.10 [bookmark: _Toc137798114][bookmark: _Toc229128317][bookmark: _Toc240874508]Operational maintenance after Completion
1 The Contractor is not required to provide routine operational maintenance of the works after Completion unless expressly stated elsewhere in this Works Information.
2 After Completion, the Contractor remains responsible for:
a. correction of Defects in accordance with the conditions of contract;
b. obligations arising from applicable warranties and guarantees; and
c. providing any outstanding clarification reasonably required in relation to Manufacturer maintenance recommendations already submitted under Section 3.8.
3 Routine inspection, operation and maintenance of the repaired dams, fuel-containment areas, tank-to-foundation interfaces and drainage systems after Completion are the Employer’s responsibility unless otherwise instructed through the contract.
4 [bookmark: _Toc137798115][bookmark: _Toc229128318]Nothing in this section reduces the Contractor’s obligations during the Defects period.
6 [bookmark: _Toc240874509]Plant and Materials standards and workmanship
6.1 [bookmark: _Toc137798116][bookmark: _Toc229128319][bookmark: _Toc240874510]Investigation, survey and Site clearance
1 The Contractor carries out the investigation, survey, Site verification and clearance necessary before commencing the affected permanent work.
2 The Contractor reviews the Employer’s drawings, available as-built information, Site Information, previous inspection information and other relevant information provided for the works.
3 The Contractor verifies accessible dimensions, levels and interfaces relevant to the work in accordance with Sections 5.1.13, 5.1.14 and 5.1.16.
4 Following dewatering and operational release, the Contractor carries out a detailed condition assessment of the Gourikwa Clean Water Dam and Dirty Water Dam.
5 The condition assessment includes, as applicable:
a. visual inspection of dam floors, walls, joints, sumps and associated concrete structures;
b. measurement and recording of identified defects;
c. photographs and Defect Mapping;
d. identification of cracking, spalling, delamination and exposed reinforcement;
e. assessment of joints, sealants, waterstops and expansion-joint components;
f. hammer tapping; and
g. Schmidt hammer testing.
6 The Contractor records the location, extent, nature and severity of the identified defects.
7 A condition-assessment report is prepared for each dam and includes the inspection methodology, areas inspected, Defect Maps, photographs, NDT results, defect classifications, measured quantities and proposed remedial measures.
8 No permanent remedial repair to a pollution-control dam commences until the applicable condition-assessment report and proposed remedial measures have been accepted in accordance with this Works Information.
9 Before flushing, the Contractor carries out a non-intrusive condition inspection of the underground clean and dirty stormwater drainage systems.
10 The inspection records the drainage route, blockages, sediment, sludge, visible defects and available photographic or video evidence.
11 Following flushing and cleaning, the Contractor re-inspects the affected drainage sections.
12 The Contractor inspects and verifies the existing condition and accessible dimensions of the fuel-containment and tank-to-foundation interfaces before commencing the affected work.
13 Before construction of the hazardous-waste skip containment area, the Contractor verifies the work-area location, existing ground levels, accessible services and interfaces relevant to the Employer’s design.
14 Site clearance is limited to that necessary to Provide the Works.
15 Vegetation, debris, contamination, failed sealants, defective concrete, topsoil and other material are removed only to the extent required by this Works Information.
16 Existing Plant, structures, services and environmental features not forming part of the work are protected against damage.
17 Removed material and waste are managed in accordance with Sections 2.5 and 5.1.17.
6.2 [bookmark: _Toc137798117][bookmark: _Toc229128320][bookmark: _Toc240874511]Building works
1 Building works under this contract are limited to the masonry, plastering, screeding and associated finishing works forming part of the hazardous-waste skip containment area.
2 The Contractor constructs the bund walls using brick masonry in accordance with the dimensions and requirements stated in this Works Information and the Employer’s drawing.
3 The Contractor provides and installs the wall reinforcement, ties, dowels or other connections required by the Employer’s design.
4 The internal faces of the bund walls are finished with cement-sand plaster of the thickness required by this Works Information.
5 The internal floor is finished to the required falls necessary to direct liquid towards the low-point sump in accordance with the Employer’s design.
6 Masonry, plaster and screed work is carried out on properly prepared substrates and is cured, protected and finished in accordance with the applicable standards and Manufacturer’s requirements.
7 Completed masonry and plastered surfaces are true, sound and free from defects that would impair the performance of the chemical-resistant coating system.
8 The Contractor does not apply the chemical-resistant coating system until the substrate has achieved the condition required by the coating Manufacturer.
6.3 [bookmark: _Toc137798118][bookmark: _Toc229128321][bookmark: _Toc240874512]Civil engineering and structural works
6.3.1 [bookmark: _Toc240874513]General
1 Civil engineering and structural works are carried out in accordance with this Works Information, the drawings listed in Section 7, accepted Contractor design where applicable, the quality requirements in Section 2.6 and the applicable standards stated in Section 6.6.
2 Permanent remedial work to a pollution-control dam commences only after the applicable condition assessment has been completed and the proposed remedial measures have been accepted as required by this Works Information.
3 Existing structures, Plant, services and adjoining areas are protected against damage.
4 New and repair materials are compatible with the existing substrate and intended service exposure.
5 The civil and structural works include, as applicable:
a. remedial works to the Gourikwa Clean Water Dam and Dirty Water Dam;
b. concrete, reinforcement and crack repairs;
c. joint, waterstop and sealant repairs;
d. fuel-containment repairs;
e. tank-to-foundation interface sealing;
f. underground stormwater drainage inspection and cleaning;
g. berm extension and erosion reinstatement; and
h. construction of the hazardous-waste skip containment area.
6.3.2 [bookmark: _Toc240874514]Joint, waterstop and sealant repairs to Clean Water Dam and Dirty Water Dam 
1 The Contractor removes defective existing sealant and backing material from affected joints.
2 Existing joint faces are prepared by removing:
a. loose or unsound material;
b. existing sealant residue;
c. oil and grease;
d. algae and biofilm;
e. dust; and
f. other contaminants which may affect adhesion.
3 Joint preparation does not unnecessarily damage:
a. sound concrete arrises;
b. reinforcement;
c. embedded waterstops; or
d. other sound joint components.
4 The Contractor inspects the exposed:
a. waterstop;
b. expansion board or compressible joint filler;
c. backing material; and
d. adjoining concrete.
5 Defective or displaced expansion boards, joint fillers, waterstops or joint tapes are repaired or replaced where required by the accepted remedial measure.
6 Closed-cell backing rod or bond-breaker tape is installed where required.
7 Primer is applied where required by the Manufacturer.
8 The replacement sealant:
a. is elastomeric;
b. accommodates the assessed joint movement;
c. is suitable for intermittent immersion where applicable;
d. is resistant to hydrocarbons where applicable;
e. is resistant to ultraviolet exposure where exposed; and
f. is compatible with the existing concrete and adjoining joint components.
9 The completed joint provides a continuous, durable and watertight seal.
6.3.3 [bookmark: _Toc240874515]Crack repairs
1 Cracks are assessed and classified before repair.
2 The assessment determines, as applicable:
a. whether the crack is structural or non-structural;
b. whether the crack is moving or non-moving;
c. the crack width, depth and extent;
d. whether water, vegetation or other contamination is present; and
e. the repair method appropriate to the assessed condition.
3 Cracks wider than 0.2 mm are repaired unless otherwise determined in the accepted remedial assessment.
4 Cracks running along existing joints are cut and prepared to form a joint having a minimum width of 10 mm and are repaired using the applicable accepted joint-sealant system.
5 Where a crack has been assessed as non-moving and repair by local concrete repair is appropriate:
a. the crack is opened by cutting a slot approximately 20 mm to 30 mm wide and up to 50 mm deep along the surface of the dry crack; and
b. the resulting repair is completed in accordance with Section 6.3.4.
6 For dry cracks on horizontal surfaces repaired by gravity-fed resin:
a. the crack is widened using a diamond blade to form a V-shaped reservoir approximately 10 mm deep;
b. the surface is cleaned to remove loose material and dust;
c. an accepted low-viscosity crack-injection resin is placed in the reservoir and allowed to penetrate the crack by capillary action; and
d. after the resin has set, excess material is removed to provide a smooth and uniform finished surface.
7 Where crack injection is used:
a. the full length of the crack is wire-brushed to remove laitance and loose material;
b. 10 mm diameter holes are drilled approximately 70 mm to 100 mm deep at 300 mm centres on either side of the crack in a staggered arrangement;
c. the holes are drilled at approximately 30° to 45° so as to intercept the crack;
d. the drilling depth may be adjusted to suit the actual crack condition and the accepted remedial measure;
e. the crack surface and drilled holes are thoroughly cleaned using compressed air to remove dust and loose particles;
f. injection packers are securely installed in the drilled holes;
g. the crack surface is sealed using a quick-setting mortar or epoxy bedding compound and allowed to cure in accordance with the Manufacturer’s requirements; and
h. the crack is injected using a manual or mechanical injection pump appropriate to the crack and accepted repair system.
8 Manual injection pumps may be used for wider cracks where the anticipated injection pressure is less than 2 MPa, subject to the accepted remedial measure.
9 Where movement is expected, the crack is routed or otherwise prepared and repaired using a flexible sealant system suitable for the assessed movement and service exposure.
10 Crack-repair resins, mortars and sealants are applied and cured in accordance with the Manufacturer’s requirements and the accepted remedial measure.
11 The completed crack repair restores the required watertightness, durability and, where applicable, structural integrity of the affected concrete.
6.3.4 [bookmark: _Toc240874516]Concrete and reinforcement repairs
1 Spalled, delaminated or otherwise defective concrete is removed to sound concrete.
2 Before removal of defective concrete, the Contractor saw-cuts the perimeter of the affected repair area to a depth of approximately 10 mm, generally forming a rectangular repair boundary.
3 Concrete within the saw-cut boundary is removed to sound concrete using light-weight pneumatic equipment or another suitable method which does not unnecessarily damage:
a. sound surrounding concrete;
b. reinforcement;
c. embedded waterstops;
d. joints; or
e. other existing structures or embedded items.
4 The repair edges are prepared to provide adequate mechanical anchorage and are dovetailed where required so that the completed repair is not feather-edged and has adequate resistance to pull-off.
5 Reinforcement exposed during concrete removal is sufficiently uncovered to permit proper inspection, cleaning and treatment.
6 Exposed reinforcement is:
a. wire-brushed or otherwise mechanically cleaned to remove corrosion products, loose scale and contaminants; and
b. treated using the applicable accepted reinforcement-protection system where treatment is required.
7 Where reinforcement has significant section loss or another material defect, the Contractor:
a. records the condition;
b. notifies the Project Manager; and
c. implements the accepted remedial measure before the repair is closed.
8 Replacement or supplementary reinforcement is installed where required by the accepted remedial measure.
9 After concrete removal and reinforcement preparation, the repair substrate is cleaned so that all dust, laitance, loose particles and other material which may affect bond are removed.
10 Where required by the Manufacturer of the proposed repair material, the repair substrate is saturated with clean water and excess surface water is removed before application of the repair material.
11 Structural repair mortar is:
a. non-shrink;
b. suitable for structural concrete repair;
c. compatible with the existing concrete;
d. of a strength not less than that required by the applicable repair detail or existing structural concrete; and
e. mixed, placed, compacted, finished and cured in accordance with the Manufacturer’s requirements.
12 Water is not added to a repair material after the permitted mixing or pot-life period in order to restore workability.
13 Where the repair depth exceeds approximately 100 mm, or where repair mortar is otherwise unsuitable, the Contractor uses suitable micro-concrete or replacement concrete in accordance with the accepted remedial measure.
14 Replacement concrete is 30 MPa where required by the applicable repair detail or accepted remedial measure.
15 Where specified by the Manufacturer, the completed repair is cured for a period of seven (7) days, or for such other period stated by the Manufacturer for the accepted repair system.
16 Completed repairs are protected from premature drying, contamination, loading, vibration, immersion or other conditions which may adversely affect the repair during curing.
17 Completed concrete and reinforcement repairs restore the required structural integrity, durability and containment performance of the affected structure.
6.3.5 [bookmark: _Toc240874517]Fuel-tank bund joint repairs
1 The Contractor repairs defective joint sealants in the fuel-containment areas associated with:
a. Gas 1 Tanks C and D
b. OCGT Tank A; and
c. OCGT Tank B.
2 Existing defective sealant and backing material are removed.
3 Joint substrates are prepared in accordance with Section 6.3.2.
4 The Contractor installs, as applicable:
a. closed-cell backing rod;
b. bond-breaker tape;
c. primer;
d. fuel-resistant elastomeric sealant; and
e. replacement waterstop or joint tape where required.
5 The completed sealing system is compatible with the hydrocarbon exposure, movement and substrate conditions and provides a continuous bonded seal.
6.3.6 [bookmark: _Toc240874518]Tank-to-foundation interface sealing
1 The Contractor removes and replaces defective sealant at the interface between the tank-base annular plate and concrete foundation for:
a. Gas 1 Tanks C and D;
b. OCGT Tank A; and
c. OCGT Tank B.
2 The existing interface is inspected for:
a. cracking;
b. debonding;
c. hardening;
d. discontinuity; and
e. other deterioration affecting the integrity of the seal.
3 Existing sealant, debris and contaminants are removed without damaging the tank annular plate or concrete foundation.
4 Steel and concrete substrates are prepared in accordance with the proposed sealant Manufacturer’s requirements.
5 Bond breaker or backing material is provided where required by the selected system.
6 The replacement sealant
a. is resistant to fuel and hydrocarbon exposure;
b. is compatible with steel and concrete;
c. is suitable for outdoor exposure; and
d. remains sufficiently flexible to accommodate movement at the interface.
7 The completed seal is finished to shed surface water away from the tank-foundation interface.
6.3.7 [bookmark: _Toc240874519]Cleaning and degreasing of Clean Water Dam and Dirty Water Dam
1 The Contractor cleans and degreases the internal surfaces of the Gourikwa Clean Water Dam and Dirty Water Dam to remove oil, grease, hydrocarbon contamination, algae, biofilm and other contaminants which may adversely affect inspection or subsequent repair work.
2 The cleaning and degreasing system is biodegradable, non-toxic and compatible with the existing concrete, joints and subsequent repair materials.
3 Cleaning may include scrubbing, low-pressure washing, spraying or another suitable method appropriate to the condition of the affected surface.
4 The Contractor allows the cleaning agent the required dwell time and agitates the affected surface where necessary before controlled rinsing.
5 Cleaning methods and products do not adversely affect:
a. the existing concrete substrate;
b. joints, waterstops or sealants;
c. subsequent condition assessment; or
d. the bond or performance of subsequent repair materials.
6 Wash water, emulsified oil, sludge and residues arising from the cleaning process are collected and controlled and are directed to the existing oil-water separation system or another containment arrangement accepted for the works.
7 Contaminated wash water, oil, sludge and residues are not discharged to the clean stormwater system, soil or environment.
8 Residues requiring off-Site disposal are managed and disposed of lawfully in accordance with Section 2.5.
6.3.8 [bookmark: _Toc240874520]Underground stormwater drainage inspection and flushing
1 The Contractor carries out pre-cleaning inspection of the underground clean and dirty stormwater drainage systems using:
a. a cage-protected drone;
b. a camera inspection system; or
c. another suitable inspection technique accepted in accordance with this Works Information.
2 The SOW expressly allows a different inspection technique to be proposed instead of drone inspection.
3 The pre-cleaning inspection records, as applicable:
a. the drainage route;
b. blockages or restrictions;
c. structural defects;
d. sediment and sludge accumulation;
e. oil-contaminated residue;
f. debris and foreign objects; and
g. photographic or video evidence.
4 The Contractor flushes and cleans affected drainage sections using:
a. high-pressure water jetting;
b. vacuum-assisted flushing; or
c. another suitable method.
5 Flushing and cleaning remove, as applicable:
a. sediment;
b. sludge;
c. organic material;
d. hydrocarbon-contaminated residue; and
e. debris or foreign objects.
6 Flushed material and wastewater are controlled, collected and managed so that contaminated material is not discharged to the environment or clean stormwater system.
7 After cleaning, the Contractor re-inspects the drainage section to verify:
a. removal of obstructions;
b. restoration of free-flowing conditions; and
c. that the cleaning activity has not damaged the drainage system.
8 The Contractor submits the required pre-cleaning and post-cleaning reports, route records, photographs and video records.
6.3.9 [bookmark: _Toc240874521]Subsoil drainage sump
1 Where the detailed condition assessment identifies a blocked subsoil drainage sump or associated drainage blockage, the Contractor unblocks and cleans the affected drainage path.
2 Material removed from the sump or drainage system is handled in accordance with the environmental and waste-management requirements of this Works Information.
3 Where inspection identifies structural damage or another defect requiring permanent repair, the Contractor records the condition and submits the proposed remedial measure before carrying out the repair.
6.3.10 [bookmark: _Toc240874522]Berm extension and erosion repairs
1 The Contractor extends the existing berm north of the Gourikwa Clean Water Dam for a minimum length of 10 m in accordance with Drawing 0.85-4260 and this Works Information. 
2 The berm extension is keyed and benched into the existing berm to reduce differential settlement and erosion and matches the dimensions of the existing berm.. 
3 The berm is constructed on prepared level ground and comprises:
a. a 0.5 m high stable base of G5 material;
b. a clay layer compacted to a minimum of 93% Mod AASHTO; and
c. a final lightly compacted topsoil layer suitable for vegetation establishment.
4 The completed berm is profiled to provide stable slopes and allow stormwater to drain without causing erosion. 
5 Eroded areas are backfilled with suitable material and protected with temporary erosion-control measures until vegetation is established. 
6 Vegetation is established using local indigenous vegetation by hand seeding or another accepted method. 
7 Seed type and vegetation proposed by the Contractor are submitted to the Supervisor for acceptance before use
6.3.11 [bookmark: _Toc240874523]Hazardous-waste skip containment area
1 The Contractor constructs a permanent impermeable hazardous-waste skip containment area in accordance with this Works Information and Drawing 18.85/6134.
2 The containment area is designed to accommodate two 6 m³ hazardous-waste skips.
3 The principal dimensions are:
· outside bund dimensions: 6.3 m × 4.3 m;
· internal bund dimensions: 6.02 m × 4.02 m;
· minimum outside wall height: 0.4 m;
· minimum internal wall height: 0.2 m; and
· approximate internal containment volume: 4.8 m³.
4 The slab is:
a. 200 mm reinforced concrete;
b. 30 MPa concrete;
c. reinforced with Ref 617 mesh at top and bottom; and
d. provided with a minimum 40 mm concrete cover, supported on approved spacers and reinforcement stools.
5 Foundation preparation includes, as applicable:
a. clearing and grubbing and removal of minimum 150 mm topsoil;
b. excavation to approximately 200 mm below natural ground level;
c. ripping and recompaction of 150 mm of the founding layer;
d. replacement of unsuitable founding material with G7 where required;
e. G7 backfill in 150 mm layers where required;
f. compaction to 95% Mod AASHTO; and
g. a 50 mm, 10 MPa blinding layer beneath the slab where required.
6 The bund walls are brick masonry tied or dowelled to the reinforced concrete slab.
7 Internal bund-wall surfaces are finished with 15–20 mm cement-sand plaster.
8 The internal floor and wall surfaces receive the specified chemical-resistant epoxy coating system with a minimum 500 μm dry film thickness, suitable for hydrocarbons, oils and contaminated runoff.
9 The slab is graded towards a low-point sump to permit controlled collection and removal of accumulated liquid by pumping.
10 The completed containment area is impermeable and capable of retaining contaminated stormwater and incidental hydrocarbon spillages without leakage.
11 Testing includes:
a. minimum 24-hour water-retention test;
b. concrete cube strength testing;
c. coating dry-film-thickness measurements; and
d. Manufacturer compliance certificates
12 The hazardous-waste skips accommodated within the containment area are intended for the storage of solid hazardous waste only and are not intended or operated as liquid-storage containers. The skips are fitted with lids to reduce stormwater ingress and contaminated stormwater generation.
13 The containment area is not required to provide 110% secondary containment capacity for the nominal volume of the hazardous-waste skips.
14 The containment area provides sufficient space and access for the safe placement and removal of the two 6 m³ hazardous-waste skips using the existing Site handling Equipment and for routine waste-management activities to be carried out safely and efficiently.
15 The containment area is based on accommodating stormwater associated with a 1:50-year storm event. For the approved design basis, a rainfall depth of approximately 150 mm corresponds to approximately 3.6 m³ of stormwater within the bunded area, which is less than the approximate available containment volume of 4.8 m³.
16 The low-point sump permits accumulated contaminated stormwater or incidental liquids to be collected and removed in a controlled manner by pumping.
17 The completed containment area remains impermeable and functional under the anticipated environmental and operating conditions.
18 Before commencing construction of the hazardous-waste skip containment area, the Contractor submits detailed Method Statements for the applicable construction activities in accordance with the submission and quality requirements of this Works Information.
6.4 [bookmark: _Toc137798119][bookmark: _Toc229128322][bookmark: _Toc240874524][bookmark: _Toc137798120][bookmark: _Toc229128323]Electrical & mechanical engineering works
1 No separate permanent electrical engineering works are required under this contract.
2 No separate permanent mechanical engineering works are required under this contract, except where expressly stated elsewhere in this Works Information.
3 Pumps, hoses, temporary tanks, inspection equipment, drainage-cleaning equipment, lifting equipment and other temporary mechanical or electrical equipment used to Provide the Works remain Contractor’s Equipment and are subject to Sections 3.6 and 4.6.
4 Where temporary electrical or mechanical connections are required to Provide the Works, the Contractor complies with the applicable Site permit, isolation, safety and operational requirements before making or using the connection.
5 Any temporary connection is removed and the affected interface reinstated when no longer required.
6 Any permanent alteration to existing electrical or mechanical Plant is carried out only where expressly required by this Works Information or instructed by the Project Manager
6.5 [bookmark: _Toc240874525]Process control and IT works
1 No process control, instrumentation or IT works are required under this contract unless expressly stated elsewhere in this Works Information.
2 Temporary cameras, drones, data-capture devices, computers, communications equipment and other electronic equipment used by the Contractor for inspection, recording, testing, reporting or contract administration remain Contractor’s Equipment.
3 The Contractor does not connect to, modify, reconfigure or interfere with the Employer’s process-control, instrumentation, telecommunications, network or IT systems unless expressly instructed by the Project Manager and authorised in accordance with the applicable Site requirements.
4 Any temporary electronic or communications connection required for the Contractor’s activities is subject to the Employer’s applicable security, access and IT requirements.
5 Inspection video, photographs and electronic records generated as part of the works are managed in accordance with Sections 2.2, 5.1.8 and 3.8.
6.6 [bookmark: _Toc240874526][bookmark: _Toc137798122][bookmark: _Toc229128325]Applicable standards
1 The Contractor Provides the Works in accordance with the applicable requirements of this Works Information, the drawings listed in Section 7, applicable legislation, the accepted Contractor design where applicable, and the standards and Employer requirements listed below. 
2 Unless a specific revision is stated in the contract, the applicable current version of the relevant standard, procedure or Employer requirement is used. 
3 Employer requirements and reference documents
	Reference
	Description

	36-681
	Generation Plant Safety Regulations

	240-62196227
	Life-Saving Rules

	240-53665024
	Engineering Quality Manual

	240-53114002
	Engineering Change Management Procedure

	240-99527377
	Inspection Manual for Civil Works at Eskom’s Power Stations


4 Applicable national and international standards
	Standard
	Description

	ISO 9001
	Quality Management Systems

	SANS 2001-CC1
	Construction works Part CC1: Concrete works (structural)

	SANS 2001-CC2
	Construction works Part CC2: Concrete works (minor works)

	SANS 2001-EM1
	Construction works Part EM1: Cement plaster

	SANS 1200 – All Parts
	Standardized specification for civil engineering construction

	SANS 10100-2
	The structural use of concrete – Part 2: Materials and execution of work

	SANS 5863
	Non-destructive testing of concrete

	ASTM C920
	Elastomeric joint sealants

	SANS 10400
	The application of the National Building Regulations


5 [bookmark: _Toc240874527]The requirements of 240-99527377 apply, where relevant, to the inspection and assessment of the existing civil structures forming part of the works. 
6 Engineering changes affecting the Employer’s design, permanent works requirements or approved design basis are managed in accordance with 240-53114002 – Engineering Change Management Procedure. 
7 Compliance with the Engineering Change Management Procedure does not by itself change the Works Information. A change to the Works Information is implemented only in accordance with the conditions of contract and an instruction of the Project Manager where required. 
8 Where requirements conflict, the Contractor notifies the Project Manager before proceeding with the affected work
7 List of drawings
7.1 [bookmark: _Toc137798123][bookmark: _Toc229128326][bookmark: _Toc240874528]Drawings issued by the Employer
1 The drawings listed in this section are issued by the Employer and form part of the Works Information to the extent applicable to the Gourikwa works.
2 The Contractor uses the drawings together with this Works Information.
3 The Contractor verifies accessible Site dimensions, levels and interfaces before carrying out the affected work. Verification does not transfer responsibility for the Employer’s design to the Contractor.
4 Where the Contractor identifies an ambiguity, inconsistency or material difference between a drawing, this Works Information or the actual Site condition, it notifies the Project Manager before proceeding with the affected work.
5 A drawing or revised drawing issued after the Contract Date does not by itself change the Works Information. A change to the Works Information is instructed by the Project Manager in accordance with the conditions of contract.
	Drawing  number
	Revision
	Title

	0.86-1338
	0
	Dirty Stormwater Polluted Water Dam

	0.866-1344
	0
	Dirty Stormwater Polluted Water Dam

	0.86-5281
	0
	Dirty Stormwater Polluted Dam General Arrangement Plan

	0.86/872
	1
	Storage fuel tanks foundation section

	0.88-842-1
	Z
	Dirty Stormwater Polluted Dam Layout Plan Setting Out Details

	0.88-843
	Z
	Dirty Stormwater Polluted Dam Sump Detail

	0.88-844
	Z
	Dirty Stormwater Polluted Dam Subsoil Drainage Sump

	0.88-1944-1
	Z
	Dirty Stormwater Polluted Dam General Arrangement Plan

	0.85/2201
	0
	Testing dam stairs & pump structures details

	0.85-4195
	0
	Polluted water dam reinforcement details panel type 1

	0.85-4258
	0
	Dirty stormwater polluted dam setting out

	0.85-4260
	0
	Testing dam & berm layout and details

	0.85/870
	1
	Storage fuel tanks retaining wall sections and details


[bookmark: _Toc137798124][bookmark: _Toc229128327]




[bookmark: _Toc240874529]C3.2	Contractor’s Works Information

	This section of the Works Information will always be contract specific depending on the nature of the works.
It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1.

Typical sub headings could be

a) 	Contractor’s design
b)	Plant and Materials specifications and schedules
c)	Other





This section could also be compiled as a separate file.
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Part 4: Site Information
The information in this Part C4 describes the Site and its surroundings as known to the Employer at the time of tender. Requirements governing how the Contractor Provides the Works are stated in Part C3: Works Information. Weather information used for compensation-event assessment is stated separately in the Contract Data.
1. General description
1. Gourikwa Power Station is situated near Mossel Bay along the N2 in the Western Cape Province, adjacent to PetroSA. The station forms part of Eskom’s peaking generation fleet and comprises five (5) diesel-fired open-cycle gas turbine units. Fuel is supplied to the Power Station through a dedicated pipeline from PetroSA.
2. Gourikwa Power Station is an operational power station. The parts of the Site relevant to this contract are the work areas identified in the Contract Data and Works Information, comprising:
· the Gourikwa Clean Water Dam;
· the Gourikwa Dirty Water Dam;
· the fuel-containment areas associated with Gas 1 Tanks C and D and OCGT Tanks A and B;
· the associated underground clean and dirty stormwater drainage infrastructure;
· the existing berm and erosion-affected areas north of the Clean Water Dam; and
· the hazardous-waste skip containment work area.
3. Clean stormwater at Gourikwa is conveyed through the underground stormwater drainage system and is ultimately discharged to the Blinde River. Dirty stormwater originating mainly from fuel and oil handling areas is collected through dedicated drainage networks and conveyed through oil-water separator systems to the Dirty Water Dam. Treated water is transferred to the Clean Water Dam for testing prior to controlled discharge to the environment.
4. The work areas are located within an operating station and interface with existing Plant, roads, drainage systems, security-controlled areas and ongoing Power Station operations. Operational release of individual work areas may be staged.
2. Existing buildings, structures, and plant & machinery on the Site
1. The principal existing assets and facilities relevant to the works are summarised below.
	Existing asset / facility
	Site information available at tender stage

	Gourikwa Clean Water Dam
	Existing concrete pollution-control dam with an approximate surface area of 3 520 m². Existing joints, waterstops, associated concrete structures and drainage features form part of the asset.

	Gourikwa Dirty Water Dam
	Existing concrete pollution-control dam with an approximate surface area of 5 000 m². Existing joints, waterstops, associated concrete structures, sumps and drainage features form part of the asset.

	Gas 1 Tanks C and D
	Existing diesel fuel-storage tanks, each approximately 15 050 mm diameter, supported on reinforced-concrete ring-beam foundations and located within reinforced-concrete bunds approximately 31 300 mm x 52 300 mm.

	OCGT Tanks A and B
	Existing diesel fuel-storage tanks, each approximately 15 050 mm diameter, supported on reinforced-concrete ring-beam foundations and located within reinforced-concrete bunds approximately 31 300 mm x 52 300 mm.

	Clean and dirty stormwater systems
	Existing underground drainage networks including pipes/drains, manholes and access chambers, oil-water separator interfaces, sumps and associated drainage infrastructure.

	Berm and erosion-affected area
	Existing berm situated north of the Clean Water Dam, with adjacent erosion-affected areas forming the tie-in area for the berm extension and reinstatement works.

	Hazardous-waste skip containment work area
	An area within Gourikwa Power Station identified for construction of the new impermeable hazardous-waste skip containment facility. The permanent containment facility does not exist at the Contract Date.


2. A routine annual visual inspection was carried out before preparation of the Engineering scope. The dams were operational and were not emptied during that inspection, and the inspection was therefore limited to accessible areas. The full condition of the dam basins and sidewalls was not confirmed at that time.
3. The visible defects and conditions recorded during the inspection included concrete spalling and delamination, deterioration or failure of joint sealants, joint movement including displaced or exposed expansion-joint boards, cracks at subsoil-drainage manholes and defective joint sealants within fuel-oil tank bunds. The actual extent of concealed or inaccessible defects is not established by this Site Information.
4. The following Employer drawings provide existing-asset and interface information relevant to the Site. These drawings are also referenced in the Works Information where applicable:
	Drawing number
	Revision
	Title

	0.86-1338
	0
	Dirty Stormwater Polluted Water Dam

	0.866-1344
	0
	Dirty Stormwater Polluted Water Dam

	0.86-5281
	0
	Dirty Stormwater Polluted Dam General Arrangement Plan

	0.86/872
	1
	Storage fuel tanks foundation section

	0.88-842-1
	Z
	Dirty Stormwater Polluted Dam Layout Plan Setting Out Details

	0.88-843
	Z
	Dirty Stormwater Polluted Dam Sump Detail

	0.88-844
	Z
	Dirty Stormwater Polluted Dam Subsoil Drainage Sump

	0.88-1944-1
	Z
	Dirty Stormwater Polluted Dam General Arrangement Plan

	0.85/2201
	0
	Testing dam stairs & pump structures details

	0.85-4195
	0
	Polluted water dam reinforcement details panel type 1

	0.85-4258
	0
	Dirty stormwater polluted dam setting out

	0.85-4260
	0
	Testing dam & berm layout and details

	0.85/870
	1
	Storage fuel tanks retaining wall sections and details

	18.85/6134
	0a
	Gourikwa hazardous-waste skip containment area - plan, sections and construction details


3. Subsoil information
1. No geotechnical investigation report, borehole records or laboratory ground-test results are provided by the Employer as Site Information for the work areas covered by this contract.
2. The surface condition of the berm/erosion work area and the proposed hazardous-waste skip containment work area is visible at Site. The subsurface founding condition beneath the proposed containment area has not been confirmed at tender stage and will only be exposed during excavation.
3. No groundwater-monitoring or groundwater-level information is provided as Site Information for these work areas.
4. The Works Information states the permanent construction and founding requirements applicable to the hazardous-waste skip containment area, including the treatment of unsuitable founding material where encountered. Those requirements do not constitute additional Site Information about the actual subsurface condition.
4. Hidden services
1. No complete verified composite survey showing the exact position, depth and level of all underground or concealed services within the work areas is provided as Site Information.
2. Known existing infrastructure within Gourikwa Power Station includes underground clean and dirty stormwater drainage systems, manholes and access chambers, oil-water separator interfaces, sumps, the subsoil drainage system and other operational pipes, cables, ducts and services associated with the Power Station. Such services may occur within or adjacent to the work areas.
3. The issued drawings and visible service features provide information on certain existing assets and drainage infrastructure. The exact location, depth and level of services are not warranted by the Employer under this Part C4. The absence of a service from the information listed in this Part C4 is not confirmation that no service is present in a particular work area.
4. For tender purposes, existing operational services are to be regarded as remaining in service unless the Works Information or an operational release specifically identifies an isolation or interruption. Requirements for locating, protecting and working near existing services are stated in Part C3: Works Information.
5. Other reports and publicly available information
1. The following Employer Engineering documents contain information relevant to the existing condition, assets and work areas at Gourikwa Power Station and are incorporated or referenced in Part C3: Works Information:
2. Scope of Works for Remedial Repair of Pollution Control Dams and Fuel Tank Bunds at Ankerlig & Gourikwa Power Stations, Unique Identifier 167A-19438, Revision 1; and
3. Scope of work for Gourikwa Power Station Construction of a Hazardous Waste Skips Containment Area, Unique Identifier 194/107301, Revision 1.
4. The Engineering scope identifies the Gourikwa General Authorisation as an informative reference. Where it is required for interpretation of environmental or water-management arrangements, the controlled Employer copy applies.
5. Weather information is not included in this Part C4. The weather measurements and historical weather-data source used for assessment under clause 60.1(13) are stated in the Contract Data and are based on official South African Weather Service data for the weather station nearest to Gourikwa Power Station that provides the stated measurements and sufficient historical records.
6. No additional geotechnical, geological, hydrographic or hydrological reports are provided by the Employer as Site Information under this Part C4.
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