*8

#### THE NATIONAL ECONOMIC DEVELOPMENT & LABOUR COUNCIL

14A Jellicoe Avenue, NEDLAC House, Rosebank PO Box 1775, Saxonwold, 2132

REQUEST FOR PROPOSAL

YOU ARE HEREBY INVITED TO SUBMIT PROPOSALS FOR THE PROVISION OF DEVELOPING AN IMPLEMENTATION PLAN FOR JUST TRANSITION FRAMEWORK IN SOUTH AFRICA

| BID NUMBER: | Nedlac 22/23/04 |
| --- | --- |
| BID ISSUE DATE: | 14 November 2022 |
| CLOSING DATE AND TIME: | 12 December 2022 at 11pm |
| BID VALIDITY PERIOD | 90 days (COMMENCING FROM THE BID CLOSING DATE) |
| COMPULSORY CLARIFICATION MEETING | 21 November 2022 10h00-12h00 Online Zoom Platform: https://climatecommission-org-za.zoom.us/meeting/register/tZModO6rrzwpEtDEaNw5g65FVH8R8hoplgx9 |
| DESCRIPTION OF SERVICE/GOODS | DEVELOPING AN IMPLEMENTATION PLAN FOR JUST TRANSITION FRAMEWORK IN SOUTH AFRICA |
| SUBMISSION OF BID | DEPOSITED IN THE TENDER BOX SITUATED AT: Nedlac offices (Reception Area) 14A Jellicoe Avenue, Rosebank |
| PROCUREMENT ENQUIRY | Name : Ms Patricia Phogole Tel no : 011 328 4200 / 060 771 0870 Email : patricia@nedlac.org.za |
| TECHNICAL ENQUIRY | Name : Mr Dumisani Nxumalo Tel no : 011 328 4200 / 082 342 8565 Email : dumisani@climatecommission.org.za |

TABLE OF CONTENTS

Page

1	SCM BID DOCUMENT SBD 1.……………………………………………….………………………….3

2.	FIXED    PRICING    SCHEDULE…………………………………………………………………………….5

- SCM BID DOCUMENTS SBD.4	7

- SCM BID DOCUMENTS SBD.6.1	09

- CERTIFICATE OF ATTENDANCE AT SITE VISIT AND CLARIFICATION MEETING	14

- CERTIFICATE FOR JOINT VENTURES	15

7.	ANNEXURE A – TERMS OF REFERENCE	16

PART A INVITATION TO BID

| YOU ARE HEREBY INVITED TO BID FOR REQUIREMENTS OF THE NEDLAC |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BID NUMBER: | NEDLAC 22/23/04 |  | CLOSING DATE: |  | 12 December 2022 |  |  |  | CLOSING TIME: |  | 11:00 PM |
| DESCRIPTION | APPOINTMENT OF SERVICE PROVIDER TO DEVELOP AN IMPLEMENTATION PLAN FOR JUST TRANSITION FRAMEWORK IN SOUTH AFRICA |  |  |  |  |  |  |  |  |  |  |
| BID RESPONSE DOCUMENTS MAY BE DEPOSITED IN THE BID BOX SITUATED AT (STREET ADDRESS) |  |  |  |  |  |  |  |  |  |  |  |
| NEDLAC HOUSE |  |  |  |  |  |  |  |  |  |  |  |
| 14A JELLICOE AVENUE |  |  |  |  |  |  |  |  |  |  |  |
| ROSEBANK |  |  |  |  |  |  |  |  |  |  |  |
| RECEPTION AREA – TENDER BOX |  |  |  |  |  |  |  |  |  |  |  |
| BIDDING PROCEDURE ENQUIRIES MAY BE DIRECTED TO |  |  |  | TECHNICAL ENQUIRIES MAY BE DIRECTED TO: |  |  |  |  |  |  |  |
| CONTACT PERSON |  | PATRICIA PHOGOLE |  | CONTACT PERSON |  |  | DUMISANI NXUMALO |  |  |  |  |
| TELEPHONE NUMBER |  | 011 328 4200 |  | TELEPHONE NUMBER |  |  | 011 328 4200 |  |  |  |  |
| FACSIMILE NUMBER |  |  |  | FACSIMILE NUMBER |  |  |  |  |  |  |  |
| E-MAIL ADDRESS |  | patricia@nedlac.org.za |  | E-MAIL ADDRESS |  |  | dumisani@climatecommission.org.za |  |  |  |  |
| SUPPLIER INFORMATION |  |  |  |  |  |  |  |  |  |  |  |
| NAME OF BIDDER |  |  |  |  |  |  |  |  |  |  |  |
| POSTAL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| STREET ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| TELEPHONE NUMBER |  | CODE |  |  | NUMBER |  |  |  |  |  |  |
| CELLPHONE NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| FACSIMILE NUMBER |  | CODE |  |  | NUMBER |  |  |  |  |  |  |
| E-MAIL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| VAT REGISTRATION NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| SUPPLIER COMPLIANCE STATUS |  | TAX COMPLIANCE SYSTEM PIN: |  | OR |  | CENTRAL SUPPLIER DATABASE No: |  | MAAA |  |  |  |
| B-BBEE STATUS LEVEL VERIFICATION CERTIFICATE |  | TICK APPLICABLE BOX] Yes No |  | B-BBEE STATUS LEVEL SWORN AFFIDAVIT |  |  |  |  |  | [TICK APPLICABLE BOX] Yes No |  |
| [A B-BBEE STATUS LEVEL VERIFICATION CERTIFICATE/ SWORN AFFIDAVIT (FOR EMES & QSEs) MUST BE SUBMITTED IN ORDER TO QUALIFY FOR PREFERENCE POINTS FOR B-BBEE] |  |  |  |  |  |  |  |  |  |  |  |
| ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS /SERVICES /WORKS OFFERED? |  | Yes No [IF YES ENCLOSE PROOF] |  | ARE YOU A FOREIGN BASED SUPPLIER FOR THE GOODS /SERVICES /WORKS OFFERED? |  |  |  |  |  | Yes No [IF YES, ANSWER PART B:3 ] |  |
| QUESTIONNAIRE TO BIDDING FOREIGN SUPPLIERS |  |  |  |  |  |  |  |  |  |  |  |
| IS THE ENTITY A RESIDENT OF THE REPUBLIC OF SOUTH AFRICA (RSA)? YES/ NO DOES THE ENTITY HAVE A BRANCH IN THE RSA? YES/NO |  |  |  |  |  |  |  |  |  |  |  |

#### SBD 1

DOES THE ENTITY HAVE A PERMANENT ESTABLISHMENT IN THE RSA?

DOES THE ENTITY HAVE ANY SOURCE OF INCOME IN THE RSA? IS THE ENTITY LIABLE IN THE RSA FOR ANY FORM OF TAXATION?

YES	NO

YES		NO YES	NO

IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN IT IS NOT A REQUIREMENT TO REGISTER FOR A TAX COMPLIANCE STATUS SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 BELOW.

DOES THE ENTITY HAVE A PERMANENT ESTABLISHMENT IN THE RSA?

DOES THE ENTITY HAVE ANY SOURCE OF INCOME IN THE RSA? IS THE ENTITY LIABLE IN THE RSA FOR ANY FORM OF TAXATION?

YES	NO

YES		NO YES	NO

IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN IT IS NOT A REQUIREMENT TO REGISTER FOR A TAX COMPLIANCE STATUS SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 BELOW.

PART B

TERMS AND CONDITIONS FOR BIDDING

1. BID SUBMISSION:

- BIDS MUST BE DELIVERED BY THE STIPULATED TIME TO THE CORRECT ADDRESS. LATE BIDS WILL NOT BE ACCEPTED FOR CONSIDERATION. #### ALL BIDS MUST BE SUBMITTED ON THE OFFICIAL FORMS PROVIDED–(NOT TO BE RE-TYPED) OR IN THE MANNER PRESCRIBED IN THE BID DOCUMENT. - THIS BID IS SUBJECT TO THE PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000 AND THE PREFERENTIAL PROCUREMENT REGULATIONS, 2017, THE GENERAL CONDITIONS OF CONTRACT (GCC) AND, IF APPLICABLE, ANY OTHER SPECIAL CONDITIONS OF CONTRACT. #### THE SUCCESSFUL BIDDER WILL BE REQUIRED TO FILL IN AND SIGN A WRITTEN CONTRACT FORM (SBD7).

2. TAX COMPLIANCE REQUIREMENTS

- BIDDERS MUST ENSURE COMPLIANCE WITH THEIR TAX OBLIGATIONS. - BIDDERS ARE REQUIRED TO SUBMIT THEIR UNIQUE PERSONAL IDENTIFICATION NUMBER (PIN) ISSUED BY SARS TO ENABLE THE ORGAN OF STATE TO VERIFY THE TAXPAYER’S PROFILE AND TAX STATUS. - APPLICATION FOR TAX COMPLIANCE STATUS (TCS) PIN MAY BE MADE VIA E-FILING THROUGH THE SARS WEBSITE WWW.SARS.GOV.ZA. - BIDDERS MAY ALSO SUBMIT A PRINTED TCS CERTIFICATE TOGETHER WITH THE BID. - IN BIDS WHERE CONSORTIA / JOINT VENTURES / SUB-CONTRACTORS ARE INVOLVED, EACH PARTY MUST SUBMIT A SEPARATE TCS CERTIFICATE / PIN / CSD NUMBER. - WHERE NO TCS IS AVAILABLE BUT THE BIDDER IS REGISTERED ON THE CENTRAL SUPPLIER DATABASE (CSD), A CSD NUMBER MUST BE PROVIDED. - NO BIDS WILL BE CONSIDERED FROM PERSONS IN THE SERVICE OF THE STATE, COMPANIES WITH DIRECTORS WHO ARE PERSONS IN THE SERVICE OF THE STATE, OR CLOSE CORPORATIONS WITH MEMBERS PERSONS IN THE SERVICE OF THE STATE.”

#### NB: FAILURE TO PROVIDE / OR COMPLY WITH ANY OF THE ABOVE PARTICULARS MAY RENDER THE BID INVALID.

SIGNATURE OF BIDDER:	……………………………………………

CAPACITY UNDER WHICH THIS BID IS SIGNED:	…………………………………… (Proof of authority must be submitted e.g. company resolution)

DATE:…………………………………………...

#### PRICING SCHEDULE

(Professional Services)

SBD 3.3

NAME OF BIDDER: ………………………………………………………………………………………………BID NO.: ……………………………………

CLOSING TIME 11:00

CLOSING       DATE…………………………......................................................................................

NAME OF BIDDER: ………………………………………………………………………………………………BID NO.: ……………………………………

CLOSING TIME 11:00

CLOSING       DATE…………………………......................................................................................

OFFER TO BE VALID FOR 90 DAYS FROM THE CLOSING DATE OF BID.

| ITEM | DESCRIPTION | BID PRICE IN RSA CURRENCY |
| --- | --- | --- |
| NO |  | **(ALL APPLICABLE TAXES INCLUDED) |

# The accompanying information must be used for the formulation of proposals.

a.	The accompanying information must be used for the formulation of proposals.

  - Bidders are required to indicate a ceiling price based on the total estimated time for completion of all phases and including all expenses inclusive of all applicable taxes for the project.

R………..…………………………………………………...

  - PERSONS  WHO  WILL  BE  INVOLVED  IN  THE  PROJECT  AND  RATES  APPLICABLE  (CERTIFIED  INVOICES  MUST  BE RENDERED IN TERMS HEREOF)

| 4. | PERSON AND POSITION -------------------------------------------------------------------------------------- | HOURLY RATE R------------------------------ | DAILY RATE ---------------- |
| --- | --- | --- | --- |
|  | -------------------------------------------------------------------------------------- | R------------------------------ | ---------------- |
|  | ---------------------------------------------------------------------------- ------------------------------------------------------------------------------------ | R--------------------------- R------------------------------ | --------------- ---------------- |
|  | -------------------------------------------------------------------------------------- | R------------------------------ | ---------------- |

- PHASES ACCORDING TO WHICH THE PROJECT WILL BECOMPLETED, COST PER PHASE AND MAN-DAYS TO BE SPENT

| -------------------------------------------------------------------------- ------------------------------------------------------------------------------- | R--------------------------- R------------------------------ | -------------------------- days -------------------------- days |
| --- | --- | --- |
| -------------------------------------------------------------------------- ------------------------------------------------------------------------------- | R--------------------------- R------------------------------ | -------------------------- days -------------------------- days |

  - Travel expenses (specify, for example rate/km and total km, class of air travel, etc). Only actual costs are recoverable. Proof of the expenses incurred must accompany certified invoices.

| DESCRIPTION OF EXPENSE TO BE INCURRED | RATE | QUANTITY | AMOUNT |
| --- | --- | --- | --- |
| ------------------------------------------------------------------------- | ………………. | …………….. | R……………….. |

| -------------------------------------------------------------------------------- | ………………. | …………….. | R……………….. |
| --- | --- | --- | --- |
| -------------------------------------------------------------------------------- | ………………. | …………….. | R……………….. |
| -------------------------------------------------------------------------------- | ………………. | …………….. | R……………….. |

TOTAL: R………………………………………………….

#### ** ”all applicable taxes” includes value- added tax, pay as you earn, income tax, unemployment insurance fund contributions and skills development levies.

  - Other expenses, for example accommodation (specify, eg. Three star hotel, bed and breakfast, telephone cost, reproduction cost, etc.).  On basis of these particulars, certified invoices will be checked for correctness.  Proof of the expenses must accompany invoices.

| DESCRIPTION OF EXPENSE TO BE INCURRED | RATE | QUANTITY | AMOUNT |
| --- | --- | --- | --- |
| --------------------------------------------------------------------------- ---------------------------------------------------------------------------------- | ……………… ………………. | …………….. …………….. | R……………R……………….. |
| --------------------------------------------------------------------------- ---------------------------------------------------------------------------------- | ……………… ………………. | …………….. …………….. | R……………R……………….. |

|  |  | TOTAL…………………………………………………. |
| --- | --- | --- |
| 6. | Period required for commencement with project after acceptance of bid | …………………………………….……………. |
| 7. | Estimated man-days for completion of project | ………………………………………………………………. |
| 8. | Are the rates quoted firm for the full period of contract? | *YES/NO |

- If not firm for the full period, provide details of the basis on which adjustments will be applied for, for example consumer price index.

……………………………………………………………….

……………………………………………………………….

*[DELETE IF NOT APPLICABLE]

SBD 4

BIDDER’S DISCLOSURE

- PURPOSE OF THE FORM

Any person (natural or juristic) may make an offer or offers in terms of this invitation to bid. In line with the principles of transparency, accountability, impartiality, and ethics as enshrined in the Constitution of the Republic of South Africa and further expressed in various pieces of legislation, it is required for the bidder to make this declaration in respect of the details required hereunder.

Where a person/s are listed in the Register for Tender Defaulters and / or the List of Restricted Suppliers, that person will automatically be disqualified from the bid process.

- Bidder’s declaration

2.1 	Is the bidder, or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise,

employed by the state?						YES/NO

2.1.1	If so, furnish particulars of the names, individual identity numbers, and, if applicable, state employee numbers of sole proprietor/ directors / trustees / shareholders / members/ partners or any person having a controlling interest in the enterprise, in table below.

| Full Name | Identity Number | Name of State institution |
| --- | --- | --- |

2.2	Do you, or any person connected with the bidder, have a relationship with any person who is employed by the procuring institution? YES/NO

2.2.1     If so, furnish particulars:

……………………………………………………………………………………

……………………………………………………………………………………

2.3 	Does the bidder or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise have any interest in any other related enterprise whether or not they are bidding for this contract?				YES/NO

    - If so, furnish particulars:

…………………………………………………………………………….

…………………………………………………………………………….

- DECLARATION

I, the undersigned, (name)……………………………………………………………………. in submitting the accompanying bid, do hereby make the following statements that I certify to be true and complete in every respect:

3.1 	I have read and I understand the contents of this disclosure;

3.2	I understand that the accompanying bid will be disqualified if this disclosure is found not to be true and complete in every respect;

3.3 	The bidder has arrived at the accompanying bid independently from, and without consultation, communication, agreement or arrangement with any competitor. However, communication between partners in a joint venture or consortium will not be construed as collusive bidding.

3.4 	In addition, there have been no consultations, communications, agreements or arrangements with any competitor regarding the quality, quantity, specifications, prices, including methods, factors or formulas used to calculate prices, market allocation, the intention or decision to submit or not to submit the bid, bidding with the intention not to win the bid and conditions or delivery particulars of the products or services to which this bid invitation relates.

3.4	The terms of the accompanying bid have not been, and will not be, disclosed by the bidder, directly or indirectly, to any competitor, prior to the date and time of the official bid opening or of the awarding of the contract.

3.5 	There have been no consultations, communications, agreements or arrangements made by the bidder with any official of the procuring institution in relation to this procurement process prior to and during the bidding process except to provide clarification on the bid submitted where so required by the institution; and the bidder was not involved in the drafting of the specifications or terms of reference for this bid.

  - I am aware that, in addition and without prejudice to any other remedy provided to combat any restrictive practices related to bids and contracts, bids that are suspicious will be reported to the Competition Commission for investigation and possible imposition of administrative penalties in terms of section 59 of the Competition Act No 89 of 1998 and or may be reported to the National Prosecuting Authority (NPA) for criminal investigation and or may be restricted from conducting business with the public sector for a period not exceeding ten (10) years in terms of the Prevention and Combating of Corrupt Activities Act No 12 of 2004 or any other applicable legislation.

I CERTIFY THAT THE INFORMATION FURNISHED IN PARAGRAPHS 1, 2 and 3 ABOVE IS CORRECT.

I ACCEPT THAT THE STATE MAY REJECT THE BID OR ACT AGAINST ME IN TERMS OF PARAGRAPH 6 OF PFMA SCM INSTRUCTION 03 OF 2021/22 ON PREVENTING AND COMBATING ABUSE IN THE SUPPLY CHAIN MANAGEMENT SYSTEM SHOULD THIS DECLARATION PROVE TO BE FALSE.

………………………………	 ..……………………………………………

Signature	                          Date

………………………………	………………………………………………

Position 	Name of bidder

SBD 6.1

PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017

This preference form must form part of all bids invited. It contains general information and serves as a claim form for preference points for Broad-Based Black Economic Empowerment (B-BBEE) Status Level of Contribution

NB: BEFORE COMPLETING THIS FORM, BIDDERS MUST STUDY THE GENERAL CONDITIONS, DEFINITIONS AND DIRECTIVES APPLICABLE IN RESPECT OF B-BBEE, AS PRESCRIBED IN THE PREFERENTIAL PROCUREMENT REGULATIONS, 2017.

- GENERAL CONDITIONS

  - The following preference point systems are applicable to all bids:

    - the 80/20 system for requirements with a Rand value of up to R50 000 000 (all applicable taxes included); and

    - the 90/10 system for requirements with a Rand value above R50 000 000 (all applicable taxes included).

1.2

- The value of this bid is estimated to not exceed R50 000 000 (all applicable taxes included) and therefore the 80/20 preference point system shall be applicable; or

  - Points for this bid shall be awarded for:

    - Price; and

    - B-BBEE Status Level of Contributor.

  - The maximum points for this bid are allocated as follows: I

|  | POINTS |
| --- | --- |
| PRICE | 80 |
| 8B-BBEE STATUS LEVEL OF CONTRIBUTOR | 20 |
| Total points for Price and B-BBEE must not exceed | 100 |

  - Failure on the part of a bidder to submit proof of B-BBEE Status level of contributor together with the bid, will be interpreted to mean that preference points for B-BBEE status level of contribution are not claimed.

  - The purchaser reserves the right to require of a bidder, either before a bid is adjudicated or at any time subsequently, to substantiate any claim in regard to preferences, in any manner required by the purchaser.

- DEFINITIONS

- “B-BBEE” means broad-based black economic empowerment as defined in section 1 of the Broad-Based Black Economic Empowerment Act;

- “B-BBEE status level of contributor” means the B-BBEE status of an entity in terms of a code of good practice on black economic empowerment, issued in terms of section 9(1) of the Broad-

Based Black Economic Empowerment Act;

- “bid” means a written offer in a prescribed or stipulated form in response to an invitation by an organ of state for the provision of goods or services, through price quotations, advertised competitive bidding processes or proposals;

- “Broad-Based Black Economic Empowerment Act” means the Broad-Based Black Economic Empowerment Act, 2003 (Act No. 53 of 2003);

### (e) “EME” means an Exempted Micro Enterprise in terms of a code of good practice on black economic empowerment issued in terms of section 9 (1) of the Broad-Based Black Economic Empowerment Act;

- “functionality” means the ability of a tenderer to provide goods or services in accordance with specifications as set out in the tender documents.

- “prices” includes all applicable taxes less all unconditional discounts;

- “proof of B-BBEE status level of contributor” means:

  - B-BBEE Status level certificate issued by an authorized body or person;

  - A sworn affidavit as prescribed by the B-BBEE Codes of Good Practice;

  - Any other requirement prescribed in terms of the B-BBEE Act;

- “QSE” means a qualifying small business enterprise in terms of a code of good practice on black economic empowerment issued in terms of section 9 (1) of the Broad-Based Black Economic Empowerment Act;

(j) “rand value” means the total estimated value of a contract in Rand, calculated at the time of bid invitation, and includes all applicable taxes;

- POINTS AWARDED FOR PRICE

  - THE 80/20 OR 90/10 PREFERENCE POINT SYSTEMS

A maximum of 80 or 90 points is allocated for price on the following basis:

90

90

80/20	or	90/10

80

80

Ps 	1 

Pt P min 

	or

Ps 	1 

Pt P min 

# 



### Where

P min	

	P min	

| Ps | = | Points scored for price of bid under consideration |
| --- | --- | --- |
| Pt | = | Price of bid under consideration |
| Pmin | = | Price of lowest acceptable bid |

- POINTS AWARDED FOR B-BBEE STATUS LEVEL OF CONTRIBUTOR

### In terms of Regulation 6 (2) and 7 (2) of the Preferential Procurement Regulations, preference points must be awarded to a bidder for attaining the B-BBEE status level of contribution in accordance with the table below:

| B-BBEE Status Level of Contributor | Number of points (90/10 system) | Number of points (80/20 system) |
| --- | --- | --- |

| 1 | 10 | 20 |
| --- | --- | --- |
| 2 | 9 | 18 |
| 3 | 6 | 14 |
| 4 | 5 | 12 |
| 5 | 4 | 8 |
| 6 | 3 | 6 |
| 7 | 2 | 4 |
| 8 | 1 | 2 |
| Non-compliant contributor | 0 | 0 |

- BID DECLARATION

  - Bidders who claim points in respect of B-BBEE Status Level of Contribution must complete the following:

- B-BBEE STATUS LEVEL OF CONTRIBUTOR CLAIMED IN TERMS OF PARAGRAPHS 1.4 AND 4.1

  - B-BBEE Status Level of Contributor:	.	=	………(maximum of 10 or 20 points)

(Points claimed in respect of paragraph 7.1 must be in accordance with the table reflected in paragraph 4.1 and must be substantiated by relevant proof of B-BBEE status level of contributor.

- SUB-CONTRACTING

  - Will any portion of the contract be sub-contracted? (Tick applicable box)

| YES |  | NO |  |
| --- | --- | --- | --- |

### If yes, indicate:

      - What percentage of the contract will be subcontracted............…………….………%

      - The name of the sub-contractor…………………………………………………………. iii)  The B-BBEE status level of the sub-contractor......................................…………….

iv)  Whether the sub-contractor is an EME or QSE

(Tick applicable box)

| YES |  | NO |  |
| --- | --- | --- | --- |

### v) Specify, by ticking the appropriate box, if subcontracting with an enterprise in terms of Preferential Procurement Regulations,2017:

| Designated Group: An EME or QSE which is at last 51% owned by: | EME √ | QSE √ |
| --- | --- | --- |
| Black people |  |  |
| Black people who are youth |  |  |
| Black people who are women |  |  |
| Black people with disabilities |  |  |
| Black people living in rural or underdeveloped areas or townships |  |  |
| Cooperative owned by black people |  |  |
| Black people who are military veterans |  |  |
| OR |  |  |

| Any EME |  |  |
| --- | --- | --- |
| Any QSE |  |  |

8.        DECLARATION WITH REGARD TO COMPANY/FIRM

### 8.1	Name of company/firm:……………………………………………………………………………. 8.2	VAT registration number:……………………………………….………………………………… 8.3	Company registration number:…………….……………………….…………………………….

  - TYPE OF COMPANY/ FIRM

    - Partnership/Joint Venture / Consortium

    - One person business/sole propriety

    - Close corporation

    - Company

    - (Pty) Limited [TICK APPLICABLE BOX]

### DESCRIBE PRINCIPAL BUSINESS ACTIVITIES

……………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………

…………………………………………………………..

  - COMPANY CLASSIFICATION

    - Manufacturer

    - Supplier

    - Professional service provider

    - Other service providers, e.g. transporter, etc. [TICK APPLICABLE BOX]

### Total number of years the company/firm has been in business:……………………………

  - I/we, the undersigned, who is / are duly authorised to do so on behalf of the company/firm, certify that the points claimed, based on the B-BBE status level of contributor indicated in paragraphs 1.4 and 6.1 of the foregoing certificate, qualifies the company/ firm for the preference(s) shown and I / we acknowledge that:

- The information furnished is true and correct;

- The preference points claimed are in accordance with the General Conditions as indicated in paragraph 1 of this form;

- In the event of a contract being awarded as a result of points claimed as shown in paragraphs

1.4 and 6.1, the contractor may be required to furnish documentary proof to the satisfaction of the purchaser that the claims are correct;

- If the B-BBEE status level of contributor has been claimed or obtained on a fraudulent basis or any of the conditions of contract have not been fulfilled, the purchaser may, in addition to any other remedy it may have –

  - disqualify the person from the bidding process;

  - recover costs, losses or damages it has incurred or suffered as a result of that person’s conduct;

  - cancel the contract and claim any damages which it has suffered as a result of having to make less favourable arrangements due to such cancellation;

  - recommend that the bidder or contractor, its shareholders and directors, or only the shareholders and directors who acted on a fraudulent basis, be restricted by the National Treasury from obtaining business from any organ of state for a period not exceeding 10 years, after the audi alteram partem (hear the other side) rule has been applied; and

  - forward the matter for criminal prosecution.

WITNESSES

1.	……………………………………..

2.	…………………………………….

WITNESSES

1.	……………………………………..

2.	…………………………………….

……………………………………….

SIGNATURE(S) OF BIDDERS(S)

DATE:

ADDRESS

…………………………………..

…………………………………..

…………………………………..

…………………………………..

……………………………………….

SIGNATURE(S) OF BIDDERS(S)

DATE:

ADDRESS

…………………………………..

…………………………………..

…………………………………..

…………………………………..

#### PROOF OF ATTENDANCE AT THE COMPULSORY CLARIFICATION SESSION / SITE MEETING

CERTIFICATE OF ATTENDANCE AT SITE VISIT AND CLARIFICATION MEETING

This is to certify that (tenderer) ..............................................................................................................

of (address) ............................................................................................................................................

........................................................................................................... was represented by the person(s) named below at

the compulsory meeting held for all tenderers at (location)

...........................................................................................................

................................................  on (date).................................... starting at (time) ...............................

I / We acknowledge that the purpose of the meeting was to acquaint myself / ourselves with the site of the works and / or matters incidental to doing the work specified in the tender documents in order for me / us to take account of everything necessary when compiling our rates and prices included in the tender.

#### Particulars of person(s) attending the meeting:

Name:	. .....................................................	Signature: ..................................................................

Capacity: ......................................................

Name: .... .......................................................	Signature: ..................................................................

Capacity: ......................................................

#### Attendance of the above person(s) at the meeting is confirmed by the Employer's representative, namely:

Name: .. ......................................................	Signature: ..................................................................

Capacity: ......................................................	Date and Time: ..........................................................

#### CERTIFICATE FOR JOINT VENTURES

This Returnable Schedule is to be completed by EACH member of a joint venture submitting a proposal.

We, the undersigned, are submitting this proposal offer in Joint Venture and hereby authorize

Mr    /    Ms…………………………………………………………………………………………………………………….,

Authorized signatory of the Company…………………………………………………………………………………..

Acting in the capacity of lead JV partner, to sign all documents in connection with the proposal offer and any contract resulting from it on our behalf as a joint venture.

NAME OF JV ORGANISATION……………………………………………………………………………………….

ADDRESS:………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………………..

DULY AUTHORISED SIGNATORY NAME ........………………………………………………………………….

DESIGNATION:……………………………………………………………………………………………………….

SIGNATURE…………………………………………………………………………………………………………..

DATE:…………………………………………………………….

#### ANNEXURE A – TERMS OF REFERENCE

NATIONAL ECONOMIC DEVELOPMENT AND LABOUR COUNCIL

P.O.BOX 1775, SAXONWOLD, 2132 – 14A JELLICOE AVENUE, ROSEBANK 2196 TELEPHONE +27(0) 11 328 4200 WEBSITE: WWW.NEDLAC.ORG.ZA

APPOINTMENT OF A SUITABLY QUALIFIED, EXPERIENCED SERVICE PROVIDER TO DEVELOP AN IMPLEMENTATION PLAN FOR JUST TRANSITION FRAMEWORK IN SOUTH AFRICA

PLAN COMMITMENTS

APPOINTMENT OF A SUITABLY QUALIFIED, EXPERIENCED SERVICE PROVIDER TO DEVELOP AN IMPLEMENTATION PLAN FOR JUST TRANSITION FRAMEWORK IN SOUTH AFRICA

PLAN COMMITMENTS

- INTRODUCTION

The Presidential Climate Commission (PCC) is a multi-stakeholder body established in 2020 by the President of South Africa to advise on the country’s climate change response and support a just transition to a low-carbon climate-resilient economy and society. The commission comprises of government ministers and 22 commissioners that represent diverse perspectives of social partners, including academia, business, civil society, labour and youth. The Commission emanates from the Presidential Summit held in October 2018, when social partners agreed that a statutory entity should be formed to coordinate and oversee the just transition towards a low-carbon, inclusive, climate-resilient economy, and society.

One of the first tasks of the Presidential Climate Commission has been to develop a just transition framework, setting out a shared vision for the just transition in South Africa, the principles to guide the transition, and the policies and governance arrangements to give effect to the transition. The just transition framework builds on research, policies, and consultations on the just transition in South Africa, as well as international best practice guidelines. The framework stands on the shoulders of years of research, done by government, business, civil society, academia, and labour unions. The framework incorporates learnings from prior consultation processes, including those facilitated by the National Planning Commission.

The PCC is currently hosted at the National Economic Development and Labour Council (NEDLAC), owing to its legal establishment processes currently underway.

- BACKGROUND

The PCC, through a multi-stakeholder process successfully delivered the first Just Transition Framework for South Africa, adopted by the Commission in May 2022 and recently approved by Cabinet in July 2022. In their approval, Cabinet approved that the framework should be integrated into the central planning system of government, specifically in the national development plan, the medium-term strategic framework, annual performance plans, and annual budgeting processes to give effect to its implementation. Government departments and other social partners have been encouraged to define their roles in relation to the objectives set out in the just transition framework.

The Just Transition Framework includes:

- A common definition of a Just Transition for South Africa

- Principles to guide the transition, including distributive, restorative and procedural   justice.

- The identification of four priority at-risk sectors and value chains

- Key policy areas to give effect to the transition

- Governance arrangements and broad implementation responsibilities.

- Measures for financing a Just Transition

- PURPOSE

The purpose of the project is to develop an implementation plan for the Just Transition Framework. The implementation plan must set out the key actions, responsibilities across social partners, timeframes and resources required to give effect to the Just Transition Framework.

- SCOPE OF WORK

  - Inception Phase

    - Inception Meeting

The appointed service provider will meet with the PCC project team to further clarify the ToR, understand expectations and revise project timelines in line with the Service Level Agreement (SLA) signed with NEDLAC.

    - Stakeholder analysis

The work plan must be informed by a thorough stakeholder analysis, which aims to identify the key sectors, social partners and implementing agencies that will be integral to the success of the just transition implementation plan, and the key constituencies and actors that need to be consulted in the process of drawing up the plan. The stakeholder analysis must inform the consultation process set out in the work plan, and in particular identify which stakeholders can be consulted as groups or sectors, versus those that need to be consulted individually. The plan should also indicate what mechanisms will be used to consult stakeholders, which may include a combination of online surveys, interviews, virtual and physical meetings.

    - Inception Report

Following the engagement with the PCC project team, and the stakeholder analysis, the service provider will prepare and submit an inception report for consideration by the PCC Secretariat. The inception report will set out the applicable scope of work, research and consultation plans, associated timelines and delivery mechanisms, in line with the discussions and signed SLA.

4.2. Developing the Implementation Plan

It is envisaged that the development of the Implementation Plan will follow a two-pronged approached of policy analysis combined with targeted stakeholder engagement. These activities may be carried out in parallel and iteratively, and the service provider is welcome to propose alternative and innovative methodologies for development of the plan.

    - Policy analysis

The appointed service provider will need to undertake a desktop policy review in order identify the strategies, programmes, regulations and interventions necessary to achieve a just transition, including initiatives within the following policy areas:

- Economic diversification, job creation and industrial policy.

- Active labour market measures and skills development.

- Social and income support, and community resilience mechanisms.

- Regulations, governance, partnerships and implementation capacity.

- Regional development mechanisms and agencies.

- Mobilising resources for a just transition.

The policy review should include the various relevant planning initiatives that are currently underway or have recently been completed, including but not limited to the following:

- High-level Implementation plan currently mapped on the Just Transition Framework

- The various Just Transition Plans developed by government agencies, social partners and social movements

- The JETP Investment Plan.

- The PCC’s work on Climate Resilient Development Pathways.

- The development of a Just Transition Implementation Model by the PCC.

- The World Bank Country Climate and Development Report.

- The conceptual outline for a Just Transition Financing Mechanism.

- The sector Masterplans led by the Department of Trade, Industry and Competition.

- The detailed infrastructure planning being undertaken with respect to energy transition and water resilience and transport, among others (DBSA/NT/NPC/PCC processes) and to take into account that Cabinet recently approved the National Infrastructure Plan 2050 (NIP2050)

The above policy analysis should include a review of existing policies, plans and programmes of the various implementing agencies identified in the stakeholder analysis, as set out in their existing policy documents, development plans, strategic plans or annual performance plans. This will form the basis for a critical engagement with implementing agencies about how to incorporate just transition implementation into their work programmes.

Given the comprehensive nature of the just transition, which cuts across social, economic and environmental functions, tiers of government and work by a multiplicity of stakeholders, the implementation plan needs to be informed by a prioritisation approach which focuses attention on the key catalytic interventions that are required to drive systemic change towards a just transition. The plan must be rooted in an understanding of what makes an “effective and implementable” plan in SA, drawing from literature and previous experience.

    - Stakeholder Consultation

The just transition is based on the principle of procedural justice, which means that the views of those most affected by the transition need to be taken into account in planning processes. Accordingly, the Just Transition Implementation Plan needs to be developed in a consultative manner. The appointed service provider must:

- Review the various reports and recordings of stakeholder engagement processes conducted by the PCC and other organisations, including various thematic and provincial Presidential imbizo sessions, in order to assimilate the views already expressed.

- Undertake a process of gathering further community and social partner views regarding the priorities to be included in the implementation plan, building on the existing programme of community engagements being conducted by the PCC. The project may include an online survey of stakeholder groups to solicit their views on a few key questions related to implementing the just transition.

- Meaningfully engage with each of the social partners and implementing agencies to define what strategies, programmes and interventions they will undertake to give effect to the just transition. This should include one-on-one engagements with each of the relevant national departments and principal economic actors, as well as collective engagements with provinces, local government, economic sectors, organised labour and other social partners.

- The plan needs to be based on a realistic assessment of the existing and required capacity of the different agencies to deliver on their responsibilities, with complementary roles assigned to reinforce where capacity falls short. While a full capacity assessment is beyond the scope of this brief, the consultations should aim elicit an understanding of the capacities and capabilities stakeholders can bring to the implementation of the just transition, in order to inform a realistic assignment of responsibilities.

4.4. Finalising the Implementation Plan

The appointed service provider will draw on the policy analysis and consultations to put together a draft implementation plan. The draft implementation plan must include:

- A prioritisation matrix for determining the critical interventions that require focus, while not excluding the broad diversity of initiatives that stakeholders can pursue around the just transition.

- The policy framework and implementation model that informs the implementation plan.

- The key interventions that comprise the plan and the role of social partners and implementing agencies in implementing them.

- Assignment of specific responsibilities for implementation, broken down according to the main national departments, provinces and local government, the various economic sectors, business and labour organisations, and civil society.

- A phasing and project plan with timeframes, deadlines and deliverables.

- Indicators to monitor whether actions have been completed, and a monitoring and oversight section, with a process of regular stocktaking and reporting to government and the public.

The PCC will publish the implementation for a period of 30 days to enable stakeholders to submit written comments. Parallel to the public commenting process, the PCC will also engage in bilateral consultations with social partners, including government, business, civil society, youth, the religious community, labour and traditional leaders. The service provider is expected to participate in these bilateral sessions, documenting inputs from the various stakeholders.

On the basis of written stakeholder inputs and the above consultations, the appointed service provider will be expected to record all inputs in a stakeholder comments database, which documents the comments received, source (person and Institution), the sections in the document to which they relate, and the response proposed to address the issues raised.

On the basis of the stakeholder inputs and guidance from the Commission, the appointed service provider will be expected to produce a final draft implementation plan that considers all views and inputs from stakeholders. The draft implementation plan will be presented to the Commission and one or more of its working groups before it is approved for handover to government. The service provider will be required to prepare draft presentations on the implementation plan and may be required to attend working group and Commission meetings, following which one further round of amendments to the plan may be required.

- OUTPUTS

The outputs that will be required as part of this project are as follows:

  - Following the signing of Contract with NEDLAC, the appointed service provider must participate in an inception meeting within two (2) weeks of contract signing.

  - An inception report which spells out the understanding of the brief, the methodology to be followed, the consultation process and the project plan to deliver. The inception report should contain a schedule of all stakeholder’s groups and implementing agencies to be consulted. This should be delivered three (3) weeks after the inception meeting.

  - A policy report arising out of the literature review report which sets out the policy framework, implementation model and prioritisation matrix that that informs the implementation plan (if effect the first few chapters of the implementation plan). This should be delivered four (4) weeks after the inception report.

  - A draft implementation plan of not more than fifty (50) pages which is a sufficient basis for soliciting stakeholder views. This should be delivered twelve (12) weeks after the literature review report – in consultation with the PCC.

  - A stakeholder consultation report which indicates what consultations have taken place, when and further includes the name, designation and contact details of all stakeholders consulted as part of the process.

  - A final implementation plan which takes on board all comments and suggestions made by stakeholders, and which sets out the strategies, programmes and interventions to be addressed by each implementing agency, together with timeframes and must be compiled and delivered as the final output of this project.

It is envisaged that the final deliverables should be completed within 16 weeks of project inception, and not longer than 24 weeks from project inception.

- PROJECT TEAM

The project team will require the following expertise and skill-set to successfully deliver on this work:

- A detailed understanding of public policy, development economics and policy     relating to a just transition and the interface between climate and development.

- Extensive experience in strategic planning and programme management.

- Excellent analytical abilities and report writing.

- Stakeholder engagement, communications and facilitation.

- Demonstrable presentation and communication skills, i.e. through publications, conference reports, etc.

- Good track record of governmental and non-governmental stakeholder consultation.

- Experience in working with government planning processes.

- Very good knowledge and understanding of the South African stakeholder landscape.

- At least 10 years' experience working in key economic sectors of South Africa, in particular energy, transport, mining, water, agriculture and community development.

- Very good project management and client relation skills, including conflict management skills.

- Facilitation skills and qualifications will be an asset.

- Project team technical back stopping.

The team members should amongst others comprise of the team leader, project management, industrial development, labour market, social development, climate / environment and facilitation / communications experts.

- PROJECT GOVERNANCE

The PCC, through its Secretariat will be represented in the Project Team comprised of the appointment service provider, representatives from the PCC secretariat and NEDLAC. During the inception meeting, the PCC together will further propose representation for the Project Steering Committee (PSC), which will meet monthly, to consider the progress of the project and reports from the appointed service provider.  The PCC Secretariat will lead all stakeholder discussions and engagements with various stakeholder with strong technical backstopping from the service provider. The service provider may be required to attend quarterly PCC Working Group and Commission meetings when the draft implementation plan is being considered.

- PROJECT TIMELINES

The project must be completed by within a period of six months (24 Weeks) after the signing of the service level agreement.

- REQUIREMENTS OF THE SERVICE PROVIDER

The successful service provider must provide the following to demonstrate experience:

- A company profile indicating the number of years offering similar expertise and facilitation services

- Detailed C.V of the project manager and team members

- A short description of previously completed similar projects, including:

  - Assignment name

  - Signed reference letters from contactable references linked to these assignments, and

  - Scale of the assignment, i.e. national, provincial, municipal.

  - Methodology and approach for the delivery of the full programme, including strategy for stakeholder consultation.

  - Risk management and mitigation strategy for COVID-19 pandemic-related inconveniences.

- SUBMISSION OF DOCUMENTS

In addition to the requirements of 5.1. to 5.4. above, service providers must submit the following documents:

- BBBEE certificate / Sworn affidavit

- Completed SBD forms

- Proof of CSD

- Tax Pin

- SELECTION AND EVALUATION CRITERIA

  - Evaluation criteria

The following evaluation criteria will be utilised:

5= Excellent, 4 = Good, 3 = Satisfactory, 2 = Poor, 1= Unacceptable

The below matrix will be used in scoring the submissions:

| What is required | Application of evaluation criteria | % Allocation |
| --- | --- | --- |
| - Competence and expertise of bidder measured in years of experience |  |  |
| What is required | Application of evaluation criteria | % Allocation |
| Detailed CVs of key personnel indicating the number of years and requisite experience as well as a detailed company profile. The number of years must be for the company and key personnel. | 5= 10 or more years of experience 4= 6-9 years of experience 3= 5 years of experience 2= 3-4 years of experience 1= 1-2 years of experience | 30% |
| B. Similar projects completed |  |  |
| What is required | Application of evaluation criteria | % Allocation |
| Client reference letters for services rendered for a period of 3 years or more for successfully completed projects in line with the required services as set out above. Service provider must submit reference letters bearing a letterhead of the organisation who were the recipient of your services, contacts details and signed by that organisation’s representative. Reference letters that do not meet the listed requirements will not be considered. | 5= 5 or more reference letters 4= 4 reference letters 3= 3 reference letters 2= 2 reference letters 1= 1 reference letter | 20% |
| - Methodology and approach |  |  |
| Provide a detailed methodology and approach for the delivery of the full program. | 5 – excellent understanding, elements of innovation 4 – good understanding, good quality proposal 3 – adequate understanding of the assignment, competent proposal 2 – inadequate understanding 0 – no proposal | 50% |

  - To note

- The minimum functionality points of seventy (70%) is required to qualify to be evaluated for pricing and BEE in phase two.

- The final decision and successful appointment will be made by NEDLAC and no correspondence will be entered into thereafter.

- NEDLAC reserves the right to cancel this bid or ultimately decide not to appoint any service provider in terms of this call for quotations.

- SUBMISSION AND ENQUIRIES

Service providers should submit their proposal and accompanying relevant documentations at Nedlac offices by 12 December 2022 not later than 11am.

Address: Nedlac

14A Jellicoe Ave, Rosebank

For Technical enquiries regarding this RFP should be emailed to dumisani@climatecommission.org.za

Procurement enquiries regarding this RFP should be emailed to Patricia@nedlac.org.za and copy procurement@nedlac.org.za

- PAYMENT TERMS

Payments will be made within 30 days from receipt of invoice and against presentation of satisfactory deliverables as will be agreed upon payment schedule upon appointment of the successful bidder/service provider.

The purpose of this document is to:

  - Draw special attention to certain general conditions applicable to government Bids, contracts and orders; and

  - To ensure that clients be familiar with regard to the rights and obligations of all parties involved in doing business with government.

In this document words in the singular also mean in the plural and vice versa and words in the masculine also mean in the feminine and neuter.

 The GCC will form pa rt of a ll bid docume nts a nd ma y not be a me nde d.

 S pe cia l Conditions of Contra ct (S CC)relevant to a specific bid, should be compiled separately for every bid (if (applicable) and will supplement the GCC. Whenever there is a conflict, the provisions in the SCC shall prevail.

#### TABLE OF CLAUSES

- Definitions

- Application

- General

- Standards

- Use of contract documents and information; inspection

- Patent rights

- Performance security

- Inspections, tests and analysis

- Packing

- Delivery and documents

- Insurance

- Transportation

- Incidental services

- Spare parts

- Warranty

- Payment

- Prices

- Contract amendments

- Assignment

- Subcontracts

- Delays in the supplier’s performance

- Penalties

- Termination for default

- Dumping and countervailing duties

- Force Majeure

- Termination for insolvency

- Settlement of disputes

- Limitation of liability

- Governing language

- Applicable law

- Notices

- Taxes and duties

- National Industrial Participation Programme (NIPP)

- Prohibition of restrictive practices

#### General conditions of contract

- Definitions

The following terms shall be interpreted as indicated:

  - “Closing time” means the date and hour specified in the bidding documents for the receipt of Bids.

  - “Contract” means the written agreement entered into between the purchaser and the supplier, as recorded in the contract form signed by the parties, including all attachments and appendices thereto and all documents incorporated by reference therein.

  - “Contract price” means the price payable to the supplier under the contract for the full and proper performance of his contractual obligations.

  - “Corrupt practice” means the offering, giving, receiving, or soliciting of anything of value to influence the action of a public official in the procurement process or in contract execution.

  - "Countervailing  duties"  are  imposed  in  cases  where  an  enterprise  abroad  is  subsidized  by  its government and encouraged to market its products internationally.

  - “Country of origin” means the place where the goods were mined, grown or produced or from which the services are supplied. Goods are produced when, through manufacturing, processing or substantial and major assembly of components, a commercially recognized new product results that is substantially different in basic characteristics or in purpose or utility from its components.

  - “Day” means calendar day.

  - “Delivery” means delivery in compliance of the conditions of the contract or order.

  - “Delivery ex stock” means immediate delivery directly from stock actually on hand.

  - “Delivery into consignees store or to his site” means delivered and unloaded ithe specified store or depot or on the specified site in compliance with the conditions of the contract or order, the supplier bearing all risks and charges involved until the supplies are so delivered and a valid receipt is obtained.

  - "Dumping" occurs when a private enterprise abroad market its goods on own initiative in the RSA at lower prices than that of the country of origin and which have the potential to harm the local industries in the RSA.

  - “Force majeure” means an event beyond the control of the supplier and not involving the supplier’s fault or negligence and not foreseeable. Such events may include, but is not restricted to, acts of the purchaser in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions and freight embargoes.

  - “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of any bidder, and includes collusive practice among bidders (prior to or after bid submission) designed to establish bid prices at artificial non-competitive levels and to deprive the bidder of the benefits of free and open competition.

  - “GCC” means the General Conditions of Contract.

  - “Goods” means all of the equipment, machinery, and/or other materials that the supplier is required to supply to the purchaser under the contract.

  - “Imported content” means that portion of the bidding price represented by the cost of components, parts or materials which have been or are still to be imported (whether by the supplier or his subcontractors) and which costs are inclusive of the costs abroad, plus freight and other direct importation costs such as landing costs, dock dues, import duty, sales duty or other similar tax or duty at the South African place of entry as well as transportation and handling charges to the factory in the Republic where the supplies covered by the bid will be manufactured.

  - “Local content” means that portion of the bidding price which is not included in the imported content provided that local manufacture does take place.

  - “Manufacture” means the production of products in a factory using labour, materials, components and machinery and includes other related value-adding activities.

  - “Order” means an official written order issued for the supply of goods or works or the rendering of a service.

  - “Project site,” where applicable, means the place indicated in bidding documents.

  - “Purchaser” means the organisation purchasing the goods.

  - “Republic” means the RSA.

  - “SCC” means the Special Conditions of Contract.

  - “Services” means those functional services ancillary to the supply of the goods, such as transportation and any other incidental services, such as installation, commissioning, provision of technical assistance, training, catering, gardening, security, maintenance and other such obligations of the supplier covered under the contract.

  - “Written” or “in writing” means handwritten in ink or any form of electronic or mechanical writing.

#### Application

  - These general conditions are applicable to all Bids, contracts and orders including Bids for functional and professional services, sales, hiring, letting and the granting or acquiring of rights, but excluding immovable

property, unless otherwise indicated in the bidding documents.

  - Where applicable, SCC are also laid down to cover specific supplies, services or works.

2.3 Where such SCC are in conflict with these general conditions, the special conditions shall apply.

#### General

  - Unless otherwise indicated in the bidding documents, the purchaser shall not be liable for any expense incurred in the preparation and submission of a bid. Where applicable a non-refundable fee for documents may be charged.

  - With certain exceptions, invitations to bid are only published in the Government Tender Bulletin. The Government Tender Bulletin may be obtained directly from the Government Printer, Private Bag X85, Pretoria 0001, or accessed electronically from www.treasury.gov.za

#### Standards

  - The goods supplied shall conform to the standards mentioned in the bidding documents and specifications.

#### Use of contract documents and information; inspection

  - The supplier shall not, without the purchaser’s prior written consent, disclose the contract, or any provision thereof, or any specification, plan, drawing, pattern, sample, or information furnished by or on behalf of the purchaser in connection therewith, to any person other than a person employed by the supplier in the performance of the contract. Disclosure to any such employed person shall be made in confidence and shall extend only so far as may be necessary for purposes of such performance.

  - The supplier shall not, without the purchaser’s prior written consent, make use of any document or information mentioned in GCC clause 5.1 except for purposes of performing the contract.

  - Any document, other than the contract itself mentioned in GCC clause 5.1 shall remain the property of the purchaser and shall be returned (all copies) to the purchaser on completion of the supplier’s performance under the contract if so required by the purchaser.

  - The supplier shall permit the purchaser to inspect the supplier’s records relating to the performance of the supplier and to have them audited by auditors appointed by the purchaser, if so required by the purchaser.

#### Patent rights

  - The supplier shall indemnify the purchaser against all third-party claims of infringement of patent, trademark, or industrial design rights arising from use of the goods or any part thereof by the purchaser.

#### Performance security

  - Within thirty (30) days of receipt of the notification of contract award, the successful bidder shall furnish to the purchaser the performance security of the amount specified in SCC.

  - The proceeds of the performance security shall be payable to the purchaser as compensation for any loss resulting from the supplier’s failure to complete his obligations under the contract.

  - The performance security shall be denominated in the currency of the contract, or in a freely convertible currency acceptable to the purchaser and shall be in one of the following forms:a bank guarantee or an irrevocable letter of credit issued by a reputable bank located in the purchaser’s country or abroad, acceptable to the purchaser, in the form provided in the bidding documents or another form acceptable to the purchaser; or

  - a cashier’s or certified cheque

7.5 The performance security will be discharged by the purchaser and returned to the supplier not later than thirty (30) days following the date of completion of the supplier’s performance obligations  under the contract, including any warranty obligations, unless otherwise specified in SCC.

#### Inspections, tests and analyses

  - All pre-bidding testing will be for the account of the bidder.

  - If it is a bid condition that supplies to be produced or services to be rendered should at any stage during production or execution or on completion be subject to inspection, the premises of the bidder or contractor shall be open, at all reasonable hours, for inspection by a representative of the Department or an organisation acting on behalf of the Department.

  - If there are no inspection requirements indicated in the bidding documents and no mention is made in the contract, but during the contract period it is decided that inspections shall be carried out, the purchaser shall itself make the necessary arrangements, including payment arrangements with the testing authority concerned.

  - If the inspections, tests and analyses referred to in clauses 8.2 and 8.3 show the supplies to be in accordance with the contract requirements, the cost of the inspections, tests and analyses shall be defrayed by the purchaser.

  - Where the supplies or  services referred to in clauses 8.2 and 8.3 do not comply with the contract requirements, irrespective of whether such supplies or services are accepted or not, the cost in connection with these inspections, tests or analyses shall be defrayed by the supplier.

  - Supplies and services which are referred to in clauses 8.2 and 8.3 and which do not comply with the contract requirements may be rejected.

  - Any contract supplies may on or after delivery be inspected, tested or analyzed and may be rejected if found not to comply with the requirements of the contract. Such rejected supplies shall be held at the cost and risk of the supplier who shall, when called upon, remove them immediately at his own cost and forthwith substitute them with supplies which do comply with the requirements of the contract. Failing such removal the rejected supplies shall be returned at the suppliers cost and risk. Should the supplier fail to provide the substitute supplies forthwith, the purchaser may, without giving the supplier further opportunity to substitute the rejected supplies, purchase such supplies as may be necessary at the expense of the supplier.

  - The provisions of clauses 8.4 to 8.7 shall not prejudice the right of the purchaser to cancel the contract on account of a breach of the conditions thereof, or to act in terms of Clause 23 of GCC.

#### Packing

  - The supplier shall provide such packing of the goods as is required to prevent their damage or deterioration during transit to their final destination, as indicated in the contract. The packing shall be sufficient to withstand, without limitation, rough handling during transit and exposure to extreme temperatures, salt and precipitation during transit, and open storage. Packing, case size and weights shall take into consideration,

where appropriate, the remoteness of the goods’ final destination and the absence of heavy handling facilities at all points in transit.

  - The packing, marking, and documentation within and outside the packages shall comply strictly with such special requirements as shall be expressly provided for in the contract, including additional requirements, if any, specified in SCC, and in any subsequent instructions ordered by the purchaser.

#### Delivery and documents

  - Delivery of the goods shall be made by the supplier in accordance with the terms specified in the contract. The details of shipping and/or other documents to be furnished by the supplier are specified in SCC.

  - Documents to be submitted by the supplier are specified in SCC.

#### Insurance

  - The goods supplied under the contract shall be fully insured in a freely convertible currency against loss or damage incidental to manufacture or acquisition, transportation, storage and delivery in the manner specified in the SCC.

#### Transportation

  - Should a price other than an all-inclusive delivered price be required, this shall be specified in the SCC.

#### Incidental services

  - The supplier may be required to provide any or all of the following services, including additional services, if any, specified in SCC:

    - performance or supervision of on-site assembly and/or commissioning of the supplied goods;

    - furnishing of tools required for assembly and/or maintenance of the supplied goods;

    - furnishing of a detailed operations and maintenance manual for each appropriate unit of the supplied goods;

    - performance or supervision or maintenance and/or repair of the supplied goods, for a period of time agreed by the parties, provided that this service shall not relieve the supplier of any warranty obligations under this contract; and

    - training of the purchaser’s personnel, at the supplier’s plant and/or on-site, in assembly, start-up, operation, maintenance, and/or repair of the supplied goods.

  - Prices charged by the supplier for incidental services, if not included in the contract price for the goods, shall be agreed upon in advance by the parties and shall not exceed the prevailing rates charged to other parties by the supplier for similar services.

#### Spare parts

  - As specified in SCC, the supplier may be required to provide any or all of the following materials, notifications, and information pertaining to spare parts manufactured or distributed by the supplier:

    - such spare parts as the purchaser may elect to purchase from the supplier, provided that this election shall not relieve the supplier of any warranty obligations under the contract; and

    - in the event of termination of production of the spare parts:

      - Advance notification to the purchaser of the pending termination, in sufficient time to permit the purchaser to procure needed requirements; and

      - following such termination, furnishing at no cost to the purchaser, the blueprints, drawings, and specifications of the spare parts, if requested.

#### Warranty

  - The supplier warrants that the goods supplied under the contract are new, unused, of the most recent or current models, and that they incorporate all recent improvements in design and materials unless provided otherwise in the contract. The supplier further warrants that all goods supplied under this contract shall have no defect, arising from design, materials, or workmanship (except when the design and/or material is required by the purchaser’s specifications) or from any act or omission of the supplier, that may develop under normal use of the supplied goods in the conditions prevailing in the country of final destination.

  - This warranty shall remain valid for twelve (12) months after the goods, or any portion thereof as the case may be, have been delivered to and accepted at the final destination indicated in the contract, or for eighteen (18) months after the date of shipment from the port or place of loading in the source country, whichever period concludes earlier, unless specified otherwise in SCC.

  - The purchaser shall promptly notify the supplier in writing of any claims arising under this warranty.

  - Upon receipt of such notice, the supplier shall, within the period specified in SCC and with all reasonable speed, repair or replace the defective goods or parts thereof, without costs to the purchaser.

  - If the supplier, having been notified, fails to remedy the defect(s) within the period specified in SCC, the purchaser may proceed to take such remedial action as may be necessary, at the supplier’s risk and expense and without prejudice to any other rights which the purchaser may have against the supplier under the contract.

#### Payment

  - The method and conditions of payment to be made to the supplier under this contract shall be specified in SCC.

  - The supplier shall furnish the purchaser with an invoice accompanied by a copy of the delivery note and upon fulfilment of other obligations stipulated in the contract.

  - Payments shall be made promptly by the purchaser, but in no case later than thirty (30) days after submission of an invoice or claim by the supplier.

  - Payment will be made in rand unless otherwise stipulated in SCC.

#### Prices

  - Prices charged by the supplier for goods delivered and services performed under the contract shall not vary from the prices quoted by the supplier in his bid, with the exception of any price adjustments authorised in SCC or in the purchaser’s request for bid validity extension, as the case may be.

#### Contract amendments

  - No variation in or modification of the terms of the contract shall be made except by written amendment signed by the parties concerned.

#### Assignment

  - The supplier shall not assign, in whole or in part, its obligations to perform under the contract, except with the purchaser’s prior written consent.

#### Subcontracts

  - The supplier shall notify the purchaser in writing of all subcontracts awarded under this contract if not already specified in the bid. Such notification, in the original bid or later, shall not relieve the supplier from any liability or obligation under the contract.

#### Delays in the supplier’s performance

  - Delivery of the goods and performance of services shall be made by the supplier in accordance with the time schedule prescribed by the purchaser in the contract.

  - If at any time during performance of the contract, the supplier or its subcontractor(s) should encounter conditions impeding timely delivery of the goods and performance of services, the supplier shall promptly notify the purchaser in writing of the fact of the delay, its likely duration and its cause(s). As soon as practicable after receipt of the supplier’s notice, the purchaser shall evaluate the situation and may at his discretion extend the supplier’s time for performance, with or without the imposition of penalties, in which case the extension shall be ratified by the parties by amendment of contract.

  - No provision in a contract shall be deemed to prohibit the obtaining of supplies or services from a national department, provincial department, or a local authority.

  - The right is reserved to procure outside of the contract small quantities or to have minor essential services executed if an emergency arises, the supplier’s point of supply is not situated at or near the place where the supplies are required, or the supplier’s services are not readily available.

  - Except as provided under GCC Clause 25, a delay by the supplier in the performance of its delivery obligations shall render the supplier liable to the imposition of penalties, pursuant to GCC Clause 22, unless an extension of time is agreed upon pursuant to GCC Clause 21.2 without the application of penalties.

  - Upon any delay beyond the delivery period in the case of a supplies contract, the purchaser shall, without cancelling the contract, be entitled to purchase supplies of a similar quality and up to the same quantity in substitution of the goods not supplied in conformity with the contract and to return any goods delivered later at the supplier’s expense and risk, or to cancel the contract and buy such goods as may be required to complete the contract and without prejudice to his other rights, be entitled to claim damages from the supplier.

#### Penalties

  - Subject to GCC Clause 25, if the supplier fails to deliver any or all of the goods or to perform the services within the period(s) specified in the contract, the purchaser shall, without prejudice to its other remedies

under the contract, deduct from the contract price, as a penalty, a sum calculated on the delivered price of the delayed goods or unperformed services using the current prime interest rate calculated for each day of the delay until actual delivery or performance. The purchaser may also consider termination of the contract pursuant to GCC Clause 23.

#### Termination for default

  - The purchaser, without prejudice to any other remedy for breach of contract, by written notice of default sent to the supplier, may terminate this contract in whole or in part:

    - if the supplier fails to deliver any or all of the goods within  the period(s) specified in the contract, or within any extension thereof granted by the purchaser pursuant to GCC Clause 21.2;

    - if the Supplier fails to perform any other obligation(s) under the contract; or

    - if the supplier, in the judgment of the purchaser, has engaged in corrupt or fraudulent practices in competing for or in executing the contract.

  - In the event the purchaser terminates the contract in whole or in part, the purchaser may procure, upon such terms and in such manner as it deems appropriate, goods, works or services similar to those undelivered, and the supplier shall be liable to the purchaser for any excess costs for such similar goods, works or services. However, the supplier shall continue performance of the contract to the extent not terminated.

  - Where the purchaser terminates the contract in whole or in part, the purchaser may decide to impose a restriction penalty on the supplier by prohibiting such supplier from doing business with the public sector for a period not exceeding 10 years.

  - If a purchaser intends imposing a restriction on a supplier or any person associated with the supplier, the supplier will be allowed a time period of not more than fourteen (14) days to provide reasons why the envisaged restriction should not be imposed. Should the supplier fail to respond within the stipulated fourteen (14) days the purchaser may regard the intended penalty as not objected against and may impose it on the supplier.

  - Any restriction imposed on any person by the Accounting Officer / Authority will, at the discretion of the Accounting Officer / Authority, also be applicable to any other enterprise or any partner, manager, director or other person who wholly or partly exercises or exercised or may exercise control over the enterprise of the first-mentioned person, and with which enterprise or person the first-mentioned person, is or was in the opinion of the Accounting Officer / Authority actively associated.

  - If a restriction is imposed, the purchaser must, within five (5) working days of such imposition, furnish the National Treasury, with the following information:

    - the name and address of the supplier and / or person restricted by the purchaser;

    - the date of commencement of the restriction

    - the period of restriction; and

    - the reasons for the restriction.

  - These details will be loaded in the National Treasury’s central database of suppliers or persons prohibited from doing business with the public sector.

  - If a court of law convicts a person of an offence as contemplated in sections 12 or 13 of the Prevention and Combating of Corrupt Activities Act, No. 12 of 2004, the court may also rule that such person’s name be endorsed on the Register for Tender Defaulters. When a person’s name has been endorsed on the Register, the person will be prohibited from doing business with the public sector for a period not less than five years and not more than 10 years. The National Treasury is empowered to determine the period of restriction and each case will be dealt with on its own merits. According to section 32 of the Act the Register must be open to the public. The Register can be perused on the National Treasury website.

#### Anti-dumping and countervailing duties and rights

  - When, after the date of bid, provisional payments are required, or anti-dumping or countervailing duties are imposed, or the amount of a provisional payment or anti-dumping or countervailing right is increased in respect of any dumped or subsidized import, the State is not liable for any amount so required or imposed, or for the amount of any such increase. When, after the said date, such a provisional payment is no longer required or any such anti-dumping or countervailing right is abolished, or where the amount of such provisional payment or any such right is reduced, any such favourable difference shall on demand be paid forthwith by the contractor to the State or the State may deduct such amounts from moneys (if any) which may otherwise be due to the contractor in regard to supplies or services which he delivered or rendered, or is to deliver or render in terms of the contract or any other contract or any other amount which may be due to him.

- Force majeure

  - Notwithstanding the provisions of GCC Clauses 22 and 23, the supplier shall not be liable for forfeiture of its performance security, damages, or termination for default if and to the extent that his delay in performance or other failure to perform his obligations under the contract is the result of an event of force majeure.

  - If a force majeure situation arises, the supplier shall promptly notify the purchaser in writing of such condition and the cause thereof. Unless otherwise directed by the purchaser in writing, the supplier shall continue to perform its obligations under the contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the force majeure event.

#### Termination for insolvency

  - The purchaser may at any time terminate the contract by giving written notice to the supplier if the supplier becomes bankrupt or otherwise insolvent. In this event, termination will be without compensation to the supplier, provided that such termination will not prejudice or affect any right of action or remedy which has accrued or will accrue thereafter to the purchaser.

#### Settlement of disputes

  - If any dispute or difference of any kind whatsoever arises between the purchaser and the supplier in connection with or arising out of the contract, the parties shall make every effort to resolve amicably such dispute or difference by mutual consultation.

  - If, after thirty (30) days, the parties have failed to resolve their dispute or difference by such mutual consultation, then either the purchaser or the supplier may give notice to the other party of his intention to commence with mediation. No mediation in respect of this matter may be commenced unless such notice is given to the other party.

  - Should it not be possible to settle a dispute by means of mediation, it may be settled in a South African court of law.

  - Mediation proceedings shall be conducted in accordance with the rules of procedure specified in the SCC.

  - Notwithstanding any reference to mediation and/or court proceedings herein,

    - the  parties  shall  continue  to  perform  their  respective  obligations  under  the  contract  unless  they otherwise agree; and

    - the purchaser shall pay the supplier any monies due the supplier.

#### Limitation of liability

  - Except in cases of criminal negligence or wilful misconduct, and in the case of infringement pursuant to Clause 6;

    - the supplier shall not be liable to the purchaser, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the supplier to pay penalties and/or damages to the purchaser; and

    - the aggregate liability of the supplier to the purchaser, whether under the contract, in tort or otherwise, shall not exceed the total contract price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment.

#### Governing language

  - The contract shall be written in English. All correspondence and other documents pertaining to the contract that is exchanged by the parties shall also be written in English.

#### Applicable law

  - The contract shall be interpreted in accordance with South African laws, unless otherwise specified in SCC.

#### Notices

  - Every written acceptance of a bid shall be posted to the supplier concerned by registered or certified mail and any other notice to him shall be posted by ordinary mail to the address furnished in his bid or to the address notified later by him in writing and such posting shall be deemed to be proper service of such notice

  - The time mentioned in the contract documents for performing any act after such aforesaid notice has been given, shall be reckoned from the date of posting of such notice.

#### Taxes and duties

  - A foreign supplier shall be entirely responsible for all taxes, stamp duties, license fees, and other such levies imposed outside the purchaser’s country.

  - A local supplier shall be entirely responsible for all taxes, duties, license fees, etc., incurred until delivery of the contracted goods to the purchaser.

  - No contract shall be concluded with any bidder whose tax matters are not in order.  Prior to the award of a bid the Department must be in possession of a tax clearance certificate, submitted by the bidder. This certificate must be an original issued by the SARSs.

#### National Industrial Participation (NIP) Programme

  - The NIP Programme administered by the DTI shall be applicable to all contracts that are subject to the NIP obligation.

#### Prohibition of restrictive practices

  - In terms of section 4 (1) (b) (iii) of the Competition Act No. 89 of 1998, as amended, an agreement between, or concerted practice by, firms, or a decision by an association of firms, is prohibited if it is between parties in a horizontal relationship and if a bidder (s) is / are or a contractor(s) was / were involved in collusive bidding (or bid rigging).

  - If a bidder(s) or contractor(s), based on reasonable grounds or evidence obtained by the purchaser, has / have engaged in the restrictive practice referred to above, the purchaser may refer the matter to the Competition Commission for investigation and possible imposition of administrative penalties as contemplated in the Competition Act No. 89 of 1998.

  - If a bidder(s) or contractor(s), has / have been found guilty by the Competition Commission of the restrictive practice referred to above, the purchaser may, in addition and without prejudice to any other remedy provided for, invalidate the bid(s) for such item(s) offered, and / or terminate the contract in whole or part, and / or restrict the bidder(s) or contractor(s) from conducting business with the public sector for a period not exceeding ten (10) years and / or claim damages from the bidder(s) or contractor(s) concerned.

#### The above General Conditions of Contract (GCC) are accepted by:

| Name: |  |
| --- | --- |
| Designation: |  |
| Bidder: |  |
| Signature: |  |
| Date: |  |

the power, by one person or a group of persons holding the majority of the equity of an enterprise, alternatively, the person/s having the deciding vote or power to influence or to direct the course and decisions of the enterprise.

Joint venture or Consortium means an association of persons for the purpose of combining their expertise, property, capital, efforts, skill and knowledge in an activity for the execution of a contract.