{"text_format":"3","workbook":"xls","n_sheets":9,"sheets":["Front Page","Company Info","Contents","P&G","Monthly maintenance ","Annual Maintenance ","Schedule E3","Material List","PS717"],"not_rendered":{"images":1,"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Front Page","index":0,"n_rows":26,"n_cols":1,"rows_kept":26,"merged":[[25,0,25,8]],"flags":["formulas_cached_only"]}
{"$rows_empty":25}
["SECTION F                                                                              "]

{"sheet":"Company Info","index":1,"n_rows":22,"n_cols":1,"rows_kept":22,"merged":[[0,0,0,2],[2,0,2,2],[4,0,4,2],[6,0,6,2],[7,0,7,2],[8,0,8,2],[9,0,9,2],[10,0,10,2],[11,0,11,2],[13,0,13,2],[14,0,14,2],[15,0,15,2],[17,0,17,2],[19,0,19,2],[21,0,21,2]],"flags":["formulas_cached_only"]}
["SECTION E:  MAINTENANCE SCHEDULES:  COSTING FIGURES"]
[]
["Company Information"]
[]
["Name of Company Tendering:"]
[]
["Address:"]
[]
[]
[]
[]
[]
[]
["Contact Numbers:"]
["Office Number:"]
["Cell Number:"]
[]
["Name:"]
[]
["Signature:"]
[]
["Date:"]

{"sheet":"Contents","index":2,"n_rows":23,"n_cols":3,"rows_kept":23,"merged":[[0,0,0,2],[2,0,2,1]],"flags":["formulas_cached_only"]}
["SECTION F:  Pricing Schedule "]
[]
["Contents",null,"Page No"]
["F1","Preliminaties and Generals "]
[null,"Building Works - Electrical Services "]
[]
["E1","Preventative Maintenance Monthly Service Costs",6]
["E1.1","Monthly Maintenance work (Musanda) Schedule:  Distribution Board Installations",6]
["E1.1","Monthly Maintenance work (Musanda) Schedule:  Electrical Reticulation and Sub-stations",7]
[]
[]
["E1.2","Monthly Inspection (Musanda) Schedule):  Power and Lighting Installation",8]
["E3","Rates for Call Outs and Emergency Works",10]
[]
["E4","Fixed Rates for Labour",11]
["E4.1","Normal Time",11]
["E4.2","Overtime (After hours and Saturdays)",12]
["E4.3","Overtime (Sundays and Public Holidays)",13]
["E4.4","Traveling Time (Normal Time)",14]
["E4.5","Traveling Time (After hours and Saturdays)",15]
["E4.6","Traveling Time (Sundays and Public Holidays)",16]
[]
["E5","Provisional Sums ",17]

{"sheet":"P&G","index":3,"n_rows":982,"n_cols":8,"rows_kept":982,"merged":[[5,1,5,2],[7,1,7,2],[9,1,9,2],[11,1,11,2],[13,1,13,2],[15,1,15,2],[16,1,16,2],[19,1,19,2],[21,1,21,2],[23,1,23,2],[48,1,48,2],[52,1,52,2],[54,1,54,2],[60,1,60,2],[64,1,64,2],[66,1,66,2],[70,1,70,2],[72,1,72,2],[74,1,74,2],[78,1,78,2],[82,1,82,2],[85,1,85,2],[87,1,87,2],[89,1,89,2],[91,1,91,2],[111,1,111,2],[113,1,113,2],[115,1,115,2],[117,1,117,2],[121,1,121,2],[125,1,125,2],[129,1,129,2],[133,1,133,2],[137,1,137,2],[141,1,141,2],[145,1,145,2],[166,1,166,2],[168,1,168,2],[172,1,172,2],[176,1,176,2],[180,1,180,2],[184,1,184,2],[188,1,188,2],[192,1,192,2],[196,1,196,2],[200,1,200,2],[202,1,202,2],[204,1,204,2],[210,1,210,2],[214,1,214,2],[218,1,218,2],[222,1,222,2],[242,1,242,2],[244,1,244,2],[246,1,246,2],[248,1,248,2],[250,1,250,2],[252,1,252,2],[256,1,256,2],[258,1,258,2],[262,1,262,2],[264,1,264,2],[266,1,266,2],[268,1,268,2],[270,1,270,2],[272,1,272,2],[274,1,274,2],[276,1,276,2],[278,1,278,2],[282,1,282,2],[299,1,299,2],[301,1,301,2],[303,1,303,2],[305,1,305,2],[307,1,307,2],[309,1,309,2],[311,1,311,2],[313,1,313,2],[317,1,317,2],[319,1,319,2],[327,1,327,2],[339,1,339,2],[341,1,341,2],[343,1,343,2],[347,1,347,2],[367,1,367,2],[369,1,369,2],[371,1,371,2],[376,1,376,2],[378,1,378,2],[380,1,380,2],[384,1,384,2],[386,1,386,2],[388,1,388,2],[390,1,390,2],[392,1,392,2],[394,1,394,2],[396,1,396,2],[398,1,398,2],[404,1,404,2],[406,1,406,2],[408,1,408,2],[425,1,425,2],[427,1,427,2],[429,1,429,2],[431,1,431,2],[433,1,433,2],[441,1,441,2],[447,1,447,2],[451,1,451,2],[453,1,453,2],[455,1,455,2],[457,1,457,2],[459,1,459,2],[461,1,461,2],[463,1,463,2],[465,1,465,2],[469,1,469,2],[471,1,471,2],[473,1,473,2],[491,1,491,2],[495,1,495,2],[499,1,499,2],[503,1,503,2],[505,1,505,2],[507,1,507,2],[513,1,513,2],[519,1,519,2],[523,1,523,2],[527,1,527,2],[531,1,531,2],[535,1,535,2],[537,1,537,2],[565,1,565,2],[569,1,569,2],[575,1,575,2],[577,1,577,2],[579,1,579,2],[583,1,583,2],[587,1,587,2],[591,1,591,2],[595,1,595,2],[599,1,599,2],[603,1,603,2],[607,1,607,2],[611,1,611,2],[613,1,613,2],[615,1,615,2],[619,1,619,2],[623,1,623,2],[642,1,642,2],[644,1,644,2],[646,1,646,2],[648,1,648,2],[650,1,650,2],[652,1,652,2],[678,1,678,2],[708,1,708,2],[710,1,710,2],[712,1,712,2],[714,1,714,2],[716,1,716,2],[722,1,722,2],[724,1,724,2],[728,1,728,2],[730,1,730,2],[734,1,734,2],[736,1,736,2],[740,1,740,2],[742,1,742,2],[759,1,759,2],[761,1,761,2],[763,1,763,2],[767,1,767,2],[769,1,769,2],[773,1,773,2],[775,1,775,2],[779,1,779,2],[781,1,781,2],[785,1,785,2],[787,1,787,2],[807,1,807,2],[809,1,809,2],[811,1,811,2],[815,1,815,2],[817,1,817,2],[821,1,821,2],[823,1,823,2],[827,1,827,2],[829,1,829,2],[850,1,850,2],[852,1,852,2],[859,1,859,2],[862,1,862,2],[911,4,911,5],[916,1,916,2]],"flags":["formulas_cached_only"]}
["Item",null,null,"Unit","Qty","Rate ",null,"Amount"]
[null,"SECTION  1 "]
[]
[null,"BILL  NO. 1 "]
[]
[null,"BUILDING AGREEMENT AND PRELIMINARIES "]
[]
[null,"The JBCC Series 2000 Minor Works Agreement (March 2014  edition 5.1) prepared by the Joint Building Contract Committee  shall be the applicable building agreement, amended as  hereinafter described "]
[]
[null,"The ASAQS Preliminaries (November 2007 edition) published  by the Association of South African Quantity Surveyors for use  with the said JBCC Principal Building Agreement shall be deemed to be incorporated in these bills of quantities  "]
[]
[null,"Contractors are referred to the abovementioned documents for  the full intent and meaning of each clause thereof"]
[]
[null,"These clauses are hereinafter referred to by clause number  and heading only. Where standard clauses or alternatives are  not entirely applicable to this contract such modifications,  corrections or supplements as will apply are given under each  relevant clause heading and such modifications, corrections or  supplements shall take precedence notwithstanding anything  contrary contained in the abovementioned documents "]
[]
[null,"Where any item is not relevant to this specific contract such item is marked N/A, signifying not applicable "]
[]
[null,"PREAMBLES FOR TRADES  "]
[]
[null,"The Model Preambles for Trades (2008 edition) as published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of  items fully described in the said Model Preambles will be entertained"]
[]
[null,"Supplementary preambles are incorporated in these bills of quantities to satisfy the requirements of this project. Such supplementary preambles shall take precedence over the provisions of the said Model preambles"]
[]
[null,"The contractor's prices for all items throughout these bills of quantities must take account of and include for all of the  obligations, requirements and specifications given in the said Model Preambles and in any supplementary preambles  "]
{"$rows_empty":10}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[]
[null,"PRICING OF PRELIMINARIES  "]
[]
[null,"Should the contractor select Option A in terms of sub clause 3.2.1 in the Contract Data - Contractor to Employer (CE) for the purpose of adjustment of these preliminaries, the amount entered into the amount column in these preliminaries is to be divided into one or more of the three categories provided namely Fixed (F), Value Related (V) and Time Related (T) "]
[]
[null,"GENERAL "]
[]
[null,"The contractor's prices for all items thought-out these bills of quantities must take into account SANS 10400-F: 2010 Edition 3 part F site operations available of SABS."]
[]
[null,"SECTION A - PRINCIPAL BUILDING  AGREEMENT "]
[]
[null,"Definitions "]
[]
[1,"Clause 1.0 - Definitions and interpretation "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Objective and preparations   "]
[]
[2,"Clause 2.0 - Offer acceptance and performance obligations  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[3,"Clause 3.0 - Documents  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Clause 3 is deemed to be amended by the following: "]
[]
[null,"3.2.1 The construction guarantee shall be in the JBCC  Variable Construction Guarantee Format"]
[]
[4,"Clause 4.0 - Design responsibility  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[5,"Clause 5.0 - Employer's agents "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},null,null,0]
[]
[]
[6,"Clause 6.0 - Contractor's site representative  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[7,"Clause 7.0 - Compliance with laws and regulations  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":11}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",null,null,"Unit","Qty","Rate ",null,"Amount"]
[null,"Clause 7 is deemed to be amended by the addition of the following clause:"]
[]
[7.1,"Without limiting the generality of the provisions of  clause 7.0 of the agreement, the contractor's  attention is drawn to the provisions of the Construction  Regulations, 2003 issued in terms of the Occupational  Health and Safety Act, 1993 in which it is specifically  stated that the employer shall prepare a documented  health and safety specification for the works and that  the employer shall ensure that the contractor has  made provision for the cost of health and safety  measures during the execution of the works.  The  contractor shall price opposite this item for compliance  with the act and the regulations and the provisions of  the aforementioned health and safety specification"]
[]
[7.2,"Without limiting the generality of the provisions of Clause 7.0 of the agreement the Contractors attention is drawn to the provisions of the SSA Emergency Plan and Risk Management requirements, e.g. Risk Assessments, Environmental Awareness Plan and on- and off-site Emergency Evacuation Plans may be required. The Contractor shall price opposite this item for compliance with requirements."]
[]
[7.3,"Without limiting the generality of the provisions of Clause 7.0 of the agreement the Contractors attention is drawn to the provisions of the Rehabilitation Plan requirements. The Contractor shall   price opposite this item for compliance with requirements."]
[]
[8,"Clause 8.0 - Works risk "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[9,"Clause 9.0 - Indemnities  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[10,"Clause 10.0 - General insurances "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[11,"Clause 11.0 - Special insurances  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[12,"Clause 12.0 - Effecting insurances  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[13,"Clause 13.0 - Assignment "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14,"Clause 14.0 - Security "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":7}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[null,"Execution  "]
[]
[15,"Clause 15.0 - Preparation for and execution of the works "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[16,"Clause 16.0 - Site and access"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[17,"Clause 17.0 - Contract instructions "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[18,"Clause 18.0 - Setting out of the works "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[19,"Clause 19.0 - Temporary works and plant"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[20,"Clause 19.2 - Notice boards"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[21,"Clause 20.0 - Nominated subcontractors  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[22,"Clause 21.0 - Selected subcontractors  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[23,"Clause 22.0 - Employer's direct contractors"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[24,"Clause 23.0 - Contractor's domestic subcontractors "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Completion  "]
[]
[25,"Clause 24.0 - Practical completion"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[26,"Clause 25.0 - Works completion  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[27,"Clause 26.0 - Final completion  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[28,"Clause 27.0 - Latent defects liability period  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[]
[]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[29,"Clause 28.0 - Sectional completion  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[30,"Clause 29.0 - Revision of date for practical completion  "]
[]
[null,"The removal and replacement of materials and/or workmanship which do not conform to specification or drawing shall not constitute grounds for the extension of the construction period nor for the adjustment of the contract value (Clause 29.3) "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[31,"Clause 30.0 - Penalty for late or non-completion  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Payment   "]
[]
[32,"Clause 31.0 is deemed to be amended to read as follows:"]
[]
[" ","The employer shall pay the contractor the amount certified in an interim payment certificate within Thirty (30) calendar days following the date of the interim payment certificate. Payment shall be subject to the contractor giving the Project Manager a  valid tax invoice for the amount due "]
[]
[33,"Clause 31.0 - Interim payment ",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"The inclusion of materials and goods stored off site in the amount authorised for payment shall be at the sole discretion of the managers and such inclusion shall only be considered upon the provision, by the contractor, of an approved bank. "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[34,"Clause 32.0 - Adjustment to the contract value "]
[]
[null,"All fluctuations in costs, with the exception of fluctuations in the rate of Value Added Tax, shall be for the account of the contractor Where prices are submitted by the contractor or n/s subcontractor during the progress of the works in respect of contract instructions or in regard to a  claim under the terms of the contract and notwithstanding the fact that such prices may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the project manager wish to accept any such prices prior to the certificate, it shall be in writing issue of the final payment"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[35,"Clause 33.0 - Recovery of expense and loss  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[36,"Clause 34.0 - Final account and final payment "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[37,"Clause 35.0 - Payment to other parties "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[]
[null,"Termination "]
[]
[38,"Clause 36.0 - Termination by employer - contractor's default  ",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[39,"Clause 37.0 - Termination by employer - loss and damage  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[40,"Clause 38.0 - Termination by contractor - employer's default  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[41,"Clause 39.0 - Termination - cessation of the works  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Dispute   "]
[]
[42,"Clause 40.0 - Settlement of disputes "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"Contract agreement "]
[]
[43,"Clause 41.0 - Post tender provisions  ",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[44,"Clause 42.0 - Contractual agreement ",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[null,"The required information of the contracting parties and the amount of the accepted contract sum shall be inserted in the contractual agreement for signature of the agreement by the contracting parties  "]
[]
[1,"CONTRACTING AND OTHER PARTIES"]
[]
[1.1,"Employer: SSA"]
[]
[null,"Physical address:"]
[null,"Building No.8"]
[null,"Montridge Office Park"]
[null,"c/n Memorial & Kekewitch Drive"]
[null,"KIMBERLEY"]
[]
[null,"Interest of project team in the project "]
[]
[null,"The team have no interest in this project apart from their professional interest."]
[]
[2,"CONTRACT DATA - CONTRACT AND SITE INFORMATION "]
[]
[2.1,"Works Description"]
[]
[null,"The scope of work shall include (but is not limited to) the following: Repairs and Renovations of buildings, Internal and External works, Security Installations and Fit out."]
{"$rows_empty":7}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[2.2,"Site Description"]
[]
[null,"Norther Cape Office Block "]
[null,"Unit 8 Mondridge Office Park, Kimberley"]
[2.3,"Date on which possession of the site is intended to  be given: on 60 days from submission of tender"]
[]
[2.4,"Period for the commencement of the works after the contractor takes possession of the site: 1 Day "]
[]
[2.5,"Completion in sections is required"]
[]
[]
[2.6,"Waiver of the contractor's lien or right of continuing  possession is required but SSA does not provide a Payment Guarantee. YES"]
[]
[2.7,"Defined restrictions to the site area - Public toilets may be used as long as premises are left clean, no washing or changing allowed. No sleeping on site"]
[]
[2.8,"Geotechnical investigation of the site has been undertaken N/A"]
[]
[2.9,"Existing premises occupied. NO"]
[]
[3,"CONTRACT DATE - INSURANCES AND SECURITIES"]
[]
[3.1,"Contract works insurance to be effected by the Contractor: For the amount of: Contract Sum + 25 % With deductibles payable by the Contractor to the amount N/A"]
[]
[null,"SASRIA insurance required:                 By Contractor"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[3.2,"Supplementary/ special insurance to be effected by Contractor"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[3.3,"Public liability insurance to be effected by - Contractor (As per signed Service Level Agreement)"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[3.4,"Support insurance to be effected N/A"]
[]
[3.5,"Special insurance to be effected N/A"]
[]
[4,"CONTRACT DATA - PRACTICAL COMPLETION DATES AND PENALTIES "]
[]
[4.1,"Intended date of practical completion is: 60 days from issue of order."]
[]
[4.2,"Intended date of practical completion where sectional completion is required and the penalty per calendar day for the works in sections: N/A and the penalty per calendar day for the works as a whole is: N/A"]
[]
[]
[]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[5,"CONTRACT DATA - DOCUMENTS AND GENERAL "]
[]
[5.1,"Construction document copies to be supplied to the  contractor free of charge"]
[]
[5.2,"The priced document may be used as a specification of materials and goods"]
[]
[5.3,"The contractor shall provide a schedule of rates where applicable "]
[]
[5.4,"On acceptance of the tender the priced document  is to be submitted within 1 Working days",null,"No"]
[]
[null,"SECTION B -  PRELIMINARIES  "]
[]
[6,"DEFINITIONS AND INTERPRETATION "]
[]
[6.1,"Clause 1.0 - Definitions and interpretation  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[7,"DOCUMENTS"]
[]
[7.1,"Clause 2.1 - Checking of documents  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[7.2,"Clause 2.2* - Provisional bills of quantities"]
[]
[null,"These bills of quantities are re-measurable in its totality. no claim or adjustment of rates will be considered to increase or  decrease in quantities"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[7.3,"Clause 2.3 - Availability of construction documentation "]
[]
[null,"The budgetary allowances and selected/nominated subcontract amounts allocated for subsequent trades included in this document will be separately procured, based on multiple procurement of selected/nominated subcontractors during the construction period"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[8,"PREVIOUS WORK AND ADJOINING PROPERTIES"]
[]
[8.1,"Clause 3.1 - Previous work - dimensional accuracy  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[8.2,"Clause 3.2 - Previous work - defects  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[8.3,"Clause 3.3 - Inspection of adjoining properties "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":8}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[9,"SAMPLES, SHOP DRAWINGS AND MANUFACTURER'S INSTRUCTIONS"]
[]
[9.1,"Clause 4.1 - Samples of materials  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[9.2,"Clause 4.2 - Workmanship samples  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[9.3,"Clause 4.3 - Shop drawings "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[9.4,"Clause 4.4 - Compliance with manufacturer's instructions "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[10,"DEPOSIT AND FEES"]
[]
[10.1,"Clause 5.1 - Deposits and fees  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item"]
[{"$nulls":4},{"v":1,"d":"1.00"},0,null,0]
[11,"TEMPORARY SERVICES"]
[]
[11.1,"Clause 6.1 - Water "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[11.2,"Clause 6.2 - Electricity "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[11.3,"Clause 6.3 - Telecommunication facilities"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[11.4,"Clause 6.4 - Ablution facilities"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[12,"PRIME COST AMOUNTS"]
[]
[12.1,"Clause 7.1 - Responsibility for prime cost amounts "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":14}
[null,"Total Carried to Collection",{"$nulls":5},0]
{"$rows_empty":7}
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[13,"SPECIAL ATTENDANCE ON N/S SUBCONTRACTORS"]
[]
[13.1,"Clause 8.1 - Special attendance "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14,"GENERAL"]
[]
[14.1,"Clause 9.1 - Protection of the works"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.2,"Clause 9.2 - Protection/isolation of existing/section ally occupied works "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.3,"Clause 9.3 - Security of the works"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.4,"Clause 9.4 - Notice before covering work  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.5,"Clause 9.5 - Disturbance  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.6,"Clause 9.6 - Environmental disturbance "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.7,"Clause 9.7 - Works cleaning and clearing"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},null,null,0]
[]
[14.8,"Clause 9.8 - Vermin "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.9,"Clause 9.9 - Rubbish removals "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},null,null,0]
[]
["14.10","Clause 9.9 - Overhand work "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.11,"Clause 9.10 - Instruction manuals and guarantees"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.12,"Clause 9.11 - As built information"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[14.13,"Clause 9.12 - Tenant installations"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[]
[]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[15,"SCHEDULE OF VARIABLES "]
[]
[null,"Information necessary for elections and completion of those clauses contained in the schedule which are necessary for tender purposes is given hereunder Where no information is given it shall mean that no specific requirements are expected or that the clause is not relevant to this specific contract  "]
[]
[15.1,"Provisional bills of quantities [clause 2.2] The quantities are provisional YES"]
[]
[15.2,"Availability of construction documentation [clause 2.3] Construction documentation is complete"]
[]
[15.3,"Previous work - dimensional [clause 3.1] accuracy N/A "]
[]
[15.4,"Previous work - defects [clause 3.2] N/A "]
[]
[15.5,"Inspection of adjoining properties [clause 3.3] N/A"]
[]
[15.6,"Water [clause 7.2]"]
[null,"Option A (by contractor)                                        ","No"]
[null,"Option B (by employer - free of charge)    ","Yes"]
[null,"Option C (by employer - metered)    ","No"]
[]
[15.7,"Electricity [clause 7.3]"]
[null,"Option A (by contractor)     ","Yes"]
[null,"Option B (by employer - free of charge)    ","No"]
[null,"Option C (by employer - metered)    ","No"]
[]
[15.8,"Telecommunications [clause 7.4]"]
[null,"Telephone "]
[null,"Contractor"]
[null,"Facsimile"]
[null,"Contractor"]
[null,"E-mail"]
[null,"Contractor"]
[]
[15.9,"Ablution facilities [clause 7.5]"]
[null,"Option A (by contractor)  ","No"]
[null,"Option B (by employer)    ","Yes"]
[]
["15.10","Protection of the works [clause 9.1]"]
[]
[15.11,"Protection/isolation of existing/section ally  occupied works  [clause 9.2] Protection/isolation is  required YES "]
[]
[15.12,"Disturbance [clause 9.5]"]
{"$rows_empty":14}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[]
[null,"The following paragraphs shall be added to this sub-clause:"]
[]
[null,"The contractor shall take all necessary measures to minimise noise. Such measures shall include inter alia, the use of 'silent' compressors and the like."]
[]
[null,"All work shall be executed without unacceptable and unreasonable dust, noise, vibrations, nuisance, inconvenience, annoyance and the like to the public, others other property. Any delays, stoppages and the like arising from or in order to comply with the above will not constitute grounds for an adjustment to the construction period or contract value 'whatsoever'"]
[]
[null,"The contractor indemnifies the employer against and accepts entire responsibilities for any claims, costs, damages and all other loss of whatsoever nature or delays which may arise on the above grounds."]
[]
[null,"The contractor shall take every precaution to protect buildings, etc. on adjoining sites against damage and shall be held solely responsible for any damage to persons or property caused by inadequate precautions."]
[]
[null,"SECTION  C - SPECIFIC PRELIMINARIES "]
[]
[16,"SITE INSTRUCTIONS"]
[]
[null,"Instructions issued on site are to be recorded in triplicate in a site instruction book which is to be maintained on site by the contractor"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[17,"PROPRIETARY BRANDED PRODUCTS"]
[]
[null,"The contractor shall take delivery of, handle, store, use apply and/or fix all proprietary branded products in  strict accordance with the manufacturers instruction after consultation with the manufacturers authorised representative."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[18,"OVERTIME"]
[]
[null,"Should overtime be required to be worked for any reason whatsoever, the costs of such overtime are to be borne by the contractor unless the project manager has specifically authorised in writing, prior to the execution thereof, that costs for such overtime are to be borne by the employer."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[19,"AS BUILT DRAWINGS"]
[]
[null,"The position of construction breaks and the extent of individual concrete pours are to be recorded by the contractor on the structural engineer's drawings and are to be submitted to the project manager and the structural engineer for their records"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[20,"SITE INSTRUCTIONS"]
[]
[null,"Site instructions issued on site are to be recorded in a Site Instruction Book which is to be maintained on site by the contractor. This shall be a carbon triplicate book numbered consecutively which may be used only for the issue of site instructions"]
[]
[null,"Site instructions directed at the contractor and various sub-contractors may be issued only by the project manager or any of the professional consultants so authorised by the project manager and must be addressed firstly for the attention of the contractor, for further distribution. Copies of all site instructions issued are to be submitted to the project manager and the quantity surveyor at the following site meeting or not later than 21days after issue."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[21,"LABOUR RECORD"]
[]
[null,"At the end of each week the contractor shall provide the project manager with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all sub-contractors on the works each day."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[22,"PLANT RECORD"]
[]
[null,"At the end of each week the contractor shall provide the project manager with a written record, in schedule form, reflecting the number, type and capacity of all plant, excluding hand tools, currently used on the works."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[23,"NON CESSION OF MONIES"]
[]
[null,"The contractor shall not cede nor assign his rights or claims to any monies due or to become due under this contract"]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[24,"CONTRACTOR TO BE RESPONSIBLE"]
[]
[null,"The contractor acknowledges that the principal objective of his appointment is his expert knowledge in the execution of the scope of work of this Contract. The Contractor shall therefore be solely responsible for all aspects of the construction of the Works including but not limited to management, resourcing, programming, co-ordination, etc. all as required for the type of project described within the time limits and quality standards specified."]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":8}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[25,"INSTALLATION OF FURNITURE, EQUIPMENT, ETC"]
[]
[null,"During the progress of the contract the employer reserves the right to send onto, install, commission and test in the works any furniture, furnishings, fitments, machinery, equipment and installation, etc., not allowed for in this contract. The contractor shall permit the employer and his representatives and contractors entry to the works for this purpose. No financial allowance shall be made to the contractor (except as specifically allowed for in these bills of quantities) on account of the presence of any of the abovementioned workmen and their materials other than reasonable costs actually incurred and approved by the Project Manager "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[26,"PRICING OF BILLS"]
[]
[null,"Tenderers are to allow opposite each item for all costs associated therewith. All prices are to include, unless otherwise stated, for all materials, fabrication, conveyance and delivery, unloading, storing, unpacking, hoisting, labour, setting, fitting and fixing in position, cutting and waste (except where measured in accordance with the Standard System Of Measurement), patterns, models and templates, plant, temporary works, returning of packings, duties, taxes, imports, establishment charges, overheads, profit and all other obligation arising out of the contract. "]
[]
[null,"Items left unpriced will be deemed to be covered in prices against other items throughout these bills of quantities and no claim for any extras arising out of the tenderer's omission to price any item will be entertained."]
[]
[27,"UNAUTHORISED PERSONS ON SITE"]
[]
[null,"The contractor shall at all times strictly exclude all unauthorised persons from the site. No workmen are to be allowed to sleep on the premises. "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
[]
[28,"DAYWORKS"]
[]
[null,"Where in the opinion of the quantity surveyor any extra work cannot  properly be measured or valued at contract rates, the contractor will be allowed day work prices calculated at the rates and principles stated elsewhere in these bills of quantities. Failure by the contractor to properly complete the day work schedule will be deemed to be  acceptance of the quantity surveyor's discretion as to what applicable day work rates to be used.  "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},0,null,0]
{"$rows_empty":10}
[null,"Total Carried to Collection",{"$nulls":5},0]
[]
[]
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Quantity","Rate",null,"Amounts"]
[29,"OCCUPATIONAL HEALTH AND SAFETY"]
[]
[null,"It is a requirement of this contract that the works are to be executed in strict accordance with the requirements of the Occupation Health And Safety Act. The successful contractor will therefor have to comply with all aspect related thereto and all costs associated therewith are deemed to be included in the contract price. No claims of any kind whatsoever will be entertained due to the contractor's non-compliance with the requirements of the act, the same being enforced onto the contractor. The successful contractor will be issued with a safety specification from the employer in terms of the act. "]
[]
[null,"F:………......... V:............................T:...........................",null,"Item",{"v":1,"d":"1.00"},null,null,0]
[]
[]
[]
[]
[null,"SUMMARY OF CATEGORIES "]
[]
[null,"Category : Fixed   R.........................................................",{"$nulls":5},0]
[]
[]
[null,"Category : Value   R.........................................................",{"$nulls":5},0]
[]
[]
[]
[null,"Category : Time    R........................................................."]
{"$rows_empty":31}
[null,"Total Carried to Collection",{"$nulls":5},0]
{"$rows_empty":8}
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]
["Item",{"$nulls":3},"Page No.",null,null,"Amounts"]
[null,"SECTION  1 "]
[]
[null,"BILL  NO. 1 "]
[]
[null,"BUILDING AGREEMENT AND PRELIMINARIES "]
[]
[]
[]
[null,"COLLECTION"]
[]
[null,"Total Brought forward from page no.",null,null,1,null,null,0]
[{"$nulls":4},2,null,null,0]
[{"$nulls":4},3,null,null,0]
[{"$nulls":4},4,null,null,0]
[{"$nulls":4},5,null,null,0]
[{"$nulls":4},6,null,null,0]
[{"$nulls":4},7,null,null,0]
[{"$nulls":4},8,null,null,0]
[{"$nulls":4},9,null,null,0]
[{"$nulls":4},10,null,null,0]
[{"$nulls":4},11,null,null,0]
[{"$nulls":4},12,null,null,0]
[{"$nulls":4},13,null,null,0]
[{"$nulls":4},14,null,null,0]
[{"$nulls":4},15,null,null,0]
{"$rows_empty":33}
[null,"Total Carried to Summary ",{"$nulls":5},0]
{"$rows_empty":7}
[null,"Section 1 "]
[null,"Bill No. 1"]
[null,"Building Agreement and Preliminaries "]
[null,"Refurbishment of NK Provincial Office"]

{"sheet":"Monthly maintenance ","index":4,"n_rows":40,"n_cols":7,"rows_kept":40,"merged":[[0,0,0,6],[2,0,2,6],[4,0,4,6],[5,0,5,6],[7,0,7,6],[9,0,9,6],[14,0,14,6],[15,0,21,0],[15,3,21,3],[15,4,21,4],[15,5,21,5],[15,6,21,6]],"flags":["formulas_cached_only"]}
["SECTION F:  MAINTENANCE SCHEDULES"]
[]
["Section F1:  Preventative Maintenance Monthly Service Costs"]
[]
["Schedule F.1.1: Monthly Maintenance work (Musanda) Schedule"]
["Complete Monthly Service of the LV Installations, all Musanda sites."]
[]
["Refer to total cost in applicable schedule(s) of Section C1.1.1, C1.1.2, C1.1.3 and C1.2 combined with section F for three year period"]
[]
["Note: All rates must be inclusive of labour and travel."]
[]
[]
["Item","Description",null,"Unit","Qty","Rate Including VAT","Amount Including VAT"]
[1,"Servicing of Distribution Board "]
["Complete monthly inspection of the following:"]
[null,"Check DB's for any visible damage to installation (panels, legends, fixtures)",null,"No",350]
[null,"Check operation of protective and monitoring devices"]
[null,"Check operation of switching elements and meters"]
[null,"Measure phase voltages and currents in DB's and record values in record book"]
[null,"Check operation of earth leakage units"]
[null,"Check operation of surge arrestors"]
[null,"Check wiring and cable terminations for loose connections and fasten all loose connections"]
[null,"Site distribution kiosks"]
[2,"Complete service of the kiosks",null,"No",100]
[null,"Sub-stations"]
[3,"Sub-station building clean up LV section",null,"No",10]
[null,"Miniature Sub-stations"]
[4,"Miniature Sub-station clean up",null,"No",10]
[null,"Complete service and testing of the Earthing and Bonding installations for the sub stations and miniature substations and upgrade/replace if required:"]
[5,"Testing of the Earthing and bonding installation by a specialist contractor",null,"No",20]
[]
[null,"Power and Lighting Installation"]
[6,"Service indoor lighting systems",null,"No",3000]
[null,"Service light switches",null,"No",{"v":1000,"d":"1,000"}]
[null,"Service outdoor lighting systems, floodlights and bulkheads",null,"No",500]
[null,"Service power outlets and fixed appliances",null,"No",{"v":5000,"d":"5,000"}]
[null,"Service earthing, bonding and lightning protection",null,"No",100]
[null,"Check wiring and cable terminations for loose connections and fasten all loose connections",null,"No",{"v":1000,"d":"1,000"}]
[null,"Tidy up power skirting and replace covers",null,"No",500]
[null,"commissioning and testing of the electrical installation after repairs/maintenance work is completed",null,"No",500]

{"sheet":"Annual Maintenance ","index":5,"n_rows":18,"n_cols":7,"rows_kept":18,"merged":[[0,0,0,6],[2,0,2,6],[3,0,3,6],[4,0,4,6],[7,0,7,6],[8,0,17,0],[8,3,17,3],[8,4,17,4],[8,5,17,5],[8,6,17,6]],"flags":["formulas_cached_only"]}
["SECTION F:  MAINTENANCE SCHEDULES"]
[]
["Schedule F1.2: Annual Maintenance work (Musanda) Schedule "]
["Complete Annual Service of theDistribution Boards"]
[]
[]
["Item","Description",null,"Unit","Qty","Rate Including VAT","Amount Including VAT"]
["Electrical Reticulation and Sub-stations"]
[null,"Annual maintenance work of DB",null,"No",350,0,0]
[null,"Inpect DB's for any visible damage to installation (panels, legends, fixtures) and maintain according to OEP specifications "]
[null,"Check all primary and secondary CB's on all DB's for any indication of equipment failure"]
[null,"Check overload current settings on adjustable primary and secondary CB's and align adjustment to ensure protection of downstream equipment"]
[null,"Perform infrared scan of all DB’s and distribution kiosks and major points of consumption"]
[null,"Perform infrared scan of all points of consumption , in particular in critical areas and areas of above average consumption, typically kitchens and equipment rooms"]
[null,"Check condition of Normal power, Emergency power and UPS power distribution points and ensure all are in a reliable condition"]
[null,"Confirm that all installations are compliant to most recently published SANS codes and wiring regulations"]
[null,"Evaluate condition of installation in total"]
[null,"Check condition of all installations in all work areas and storage areas (power channels, cable routes, cable trays, switches, isolators)"]

{"sheet":"Schedule E3","index":6,"n_rows":27,"n_cols":5,"rows_kept":27,"merged":[[0,0,0,2],[2,0,2,4],[4,0,4,4],[5,0,5,4],[6,0,6,4],[7,0,7,4],[23,1,23,4],[24,0,25,0],[24,1,25,1],[24,2,25,2]],"flags":["formulas_cached_only"]}
["SECTION E:  MAINTENANCE SCHEDULES"]
[]
["Section E1:  Preventative Maintenance Monthly Service Costs"]
[]
["Schedule E3:  Rates for Call Outs and Emergency Works"]
["Note: "]
["Call outs are for unquoted emergency works either during normal or after hours not applicable to planned services. Fees will be calculated in line with Board Notice 138 of 2015, guideline for Services and Processes for Estimating fees for fees for persons registered in terms of the Engineering Professional Act (ECSA)"]
["Schedule E4.1:  Fixed Rates - Artisans and Labours"]
["Item","Description","Unit","Rate ","Amounts "]
[1,"Normal Hours"]
[null,"Labour + Accredited Artisan","p/h"]
[null,"Labour + Artisan assistant","p/h"]
[null,"Labour","p/h"]
[]
[2,"Sundays and Public Holidays"]
[null,"Labour + Accredited Artisan","p/h"]
[null,"Labour + Artisan assistant","p/h"]
[null,"Labour","p/h"]
[]
[3,"After Hours and Saturdays"]
[null,"Labour + Accredited Artisan","p/h"]
[null,"Labour + Artisan assistant","p/h"]
[null,"Labour","p/h"]
[8,"Material"]
[8.1,"Mark up on PC Items",{"v":0.12,"d":"12%"},null,"Not exceeding 12%"]
[{"$nulls":4},"(Less than 12% Indicate) "]
[8.2,"Annual Escalation","%",null,"Annual Escalation is determined by CPI rate per annum as determined by SSA"]

{"sheet":"Material List","index":7,"n_rows":798,"n_cols":6,"rows_kept":798,"merged":[[0,0,0,5],[788,0,788,3],[791,0,791,3],[792,0,792,3],[793,0,793,3],[794,0,794,3],[795,0,795,3],[797,0,797,3]],"flags":["formulas_cached_only"]}
["SECTION I:  MATERIAL LIST AND UNIT RATES"]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[1,"MATERIAL AND SERVICES:"]
[1.1,"SABS Approved circuit breakers:"]
[null,"5A, 3 kA single pole - CBI","No."]
[null,"10A, 6 kA single pole - CBI","No."]
[null,"15A, 6 kA single pole - CBI","No."]
[null,"20A, 6 kA single pole - CBI","No."]
[null,"30A, 6 kA single pole - CBI","No."]
[null,"40A, 6 kA single pole - CBI","No."]
[null,"63A, 6 kA single pole - CBI","No."]
[null,"20A, 6 kA double pole - CBI","No."]
[null,"30A, 6 kA double pole - CBI","No."]
[null,"40A, 6 kA double pole - CBI","No."]
[null,"63A, 6 kA double pole - CBI","No."]
[null,"10A, 6 kA three pole - CBI","No."]
[null,"15A, 6 kA three pole - CBI","No."]
[null,"20A, 6 kA three pole - CBI","No."]
[null,"25A, 6 kA three pole - CBI","No."]
[null,"30A, 6 kA three pole - CBI","No."]
[null,"40A, 6 kA three pole - CBI","No."]
[null,"50A, 6 kA three pole - CBI","No."]
[null,"63A, 6 kA three pole - CBI","No."]
[null,"80A, 6 kA three pole - CBI","No."]
[null,"100A, 6 kA three pole - CBI","No."]
[null,"15A, 6 kA single pole slow tripping curve - CBI","No."]
[null,"20A, 6 kA single pole slow tripping curve - CBI","No."]
[null,"30A, 6 kA single pole slow tripping curve - CBI","No."]
[null,"40A, 6 kA single pole slow tripping curve - CBI","No."]
[null,"15A, 6 kA three pole slow tripping curve - CBI","No."]
[null,"20A, 6 kA three pole slow tripping curve - CBI","No."]
[null,"25A, 6 kA three pole slow tripping curve - CBI","No."]
[null,"30A, 6 kA three pole slow tripping curve - CBI","No."]
[null,"40A, 6 kA three pole slow tripping curve - CBI","No."]
[null,"5A, 5 kA single pole - Schneider","No."]
[null,"10A, 5 kA single pole - Schneider","No."]
[null,"15A, 5 kA single pole - Schneider","No."]
[null,"20A, 5 kA single pole - Schneider","No."]
[null,"32A, 5 kA single pole - Schneider","No."]
[null,"40A, 5 kA single pole - Schneider","No."]
[null,"60A, 5 kA single pole - Schneider","No."]
[null,"20A, 5 kA double pole - Schneider","No."]
[null,"32A, 5 kA double pole - Schneider","No."]
[]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[null,"40A, 5 kA double pole - Schneider","No."]
[null,"60A, 5 kA double pole - Schneider","No."]
[null,"10A, 5 kA three pole - Schneider","No."]
[null,"15A, 5 kA three pole - Schneider","No."]
[null,"20A, 5 kA three pole - Schneider","No."]
[null,"25A, 5 kA three pole - Schneider","No."]
[null,"32A, 5 kA three pole - Schneider","No."]
[null,"40A, 5 kA three pole - Schneider","No."]
[null,"50A, 5 kA three pole - Schneider","No."]
[null,"60A, 5 kA three pole - Schneider","No."]
[null,"80A, 5 kA three pole - Schneider","No."]
[null,"100A, 5 kA three pole - Schneider","No."]
[1.2,"SABS approved isolators:"]
[null,"60A 6KA Three pole - CBI","No."]
[null,"100A 6KA Three pole - CBI","No."]
[null,"60A 5KA Three pole - Schneider","No."]
[null,"100A 5KA Three pole - Schneider","No."]
[1.3,"SABS approved contactors:"]
[null,"25A Three pole contractor - CBI DB mount","No."]
[null,"20A Three pole contactor.","No."]
[null,"25A Three pole contactor.","No."]
[null,"30A Three pole contactor.","No."]
[null,"40A Three pole contactor.","No."]
[null,"50A Three pole contactor.","No."]
[null,"60A Three pole contactor.","No."]
[null,"100A Three pole contactor.","No."]
[1.4,"SABS approved earth leakages:"]
[null,"20A 5kA 30mA Two pole earth leakage - CBI","No."]
[null,"63A 5kA 30mA Two pole earth leakage - CBI","No."]
[null,"63A 5kA 30mA four pole earth leakage - CBI","No."]
[null,"80A 10kA 30mA Four pole earth leakage - CBI","No."]
[null,"63A 6kA 30mA Two pole earth leakage - Schneider","No."]
[1.5,"SABS approved surge arrestors:"]
[null,"10KA Two pole surge arrestor","No."]
[null,"40KA Two pole surge arrestor","No."]
[null,"10KA Four pole surge arrestor","No."]
[null,"40KA Four pole surge arrestor","No."]
{"$rows_empty":11}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.6," SABS approved low voltage cables:"]
[null,"1.5mm² 3 core PVC SWA cable","m"]
[null,"2.5mm² 3 core PVC SWA cable","m"]
[null,"4mm² 3 core PVC SWA cable","m"]
[null,"6mm² 3 core PVC SWA cable","m"]
[null,"10mm² 3 core PVC SWA cable","m"]
[null,"16mm² 3 core PVC SWA cable","m"]
[null,"1.5mm² 4 core PVC SWA cable","m"]
[null,"2.5mm² 4 core PVC SWA cable","m"]
[null,"4mm² 4 core PVC SWA cable","m"]
[null,"6mm² 4 core PVC SWA cable","m"]
[null,"10mm² 4 core PVC SWA cable","m"]
[null,"16mm² 4 core PVC SWA cable","m"]
[null,"25mm² 4 core PVC SWA cable","m"]
[null,"35mm² 4 core PVC SWA cable","m"]
[null,"50mm² 4 core PVC SWA cable","m"]
[null,"70mm² 4 core PVC SWA cable","m"]
[null,"95mm² 4 core PVC SWA cable","m"]
[null,"120mm² 4 core PVC SWA cable","m"]
[null,"150mm² 4 core PVC SWA cable","m"]
[null,"185mm² 4 core PVC SWA cable","m"]
[1.7,"Cable Terminations:"]
[null,"1.5mm² 3 core PVC SWA cable","No."]
[null,"2.5mm² 3 core PVC SWA cable","No."]
[null,"4mm² 3 core PVC SWA cable","No."]
[null,"6mm² 3 core PVC SWA cable","No."]
[null,"10mm² 3 core PVC SWA cable","No."]
[null,"16mm² 3 core PVC SWA cable","No."]
[null,"1.5mm² 4 core PVC SWA cable","No."]
[null,"2.5mm² 4 core PVC SWA cable","No."]
[null,"4mm² 4 core PVC SWA cable","No."]
[null,"6mm² 4 core PVC SWA cable","No."]
[null,"10mm² 4 core PVC SWA cable","No."]
[null,"16mm² 4 core PVC SWA cable","No."]
[null,"25mm² 4 core PVC SWA cable","No."]
[null,"35mm² 4 core PVC SWA cable","No."]
[null,"50mm² 4 core PVC SWA cable","No."]
[null,"70mm² 4 core PVC SWA cable","No."]
[null,"95mm² 4 core PVC SWA cable","No."]
[null,"120mm² 4 core PVC SWA cable","No."]
[null,"150mm² 4 core PVC SWA cable","No."]
[null,"185mm² 4 core PVC SWA cable","No."]
[]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.8,"SABS approved Cable Joints:"]
[null,"1.5mm² 3 core PVC SWA cable","No."]
[null,"2.5mm² 3 core PVC SWA cable","No."]
[null,"4mm² 3 core PVC SWA cable","No."]
[null,"6mm² 3 core PVC SWA cable","No."]
[null,"10mm² 3 core PVC SWA cable","No."]
[null,"16mm² 3 core PVC SWA cable","No."]
[null,"1.5mm² 4 core PVC SWA cable","No."]
[null,"1.5mm² 4 core PVC SWA cable","No."]
[null,"4mm² 4 core PVC SWA cable","No."]
[null,"6mm² 4 core PVC SWA cable","No."]
[null,"10mm² 4 core PVC SWA cable","No."]
[null,"16mm² 4 core PVC SWA cable","No."]
[null,"25mm² 4 core PVC SWA cable","No."]
[null,"35mm² 4 core PVC SWA cable","No."]
[null,"50mm² 4 core PVC SWA cable","No."]
[null,"70mm² 4 core PVC SWA cable","No."]
[null,"95mm² 4 core PVC SWA cable","No."]
[null,"120mm² 4 core PVC SWA cable","No."]
[null,"150mm² 4 core PVC SWA cable","No."]
[null,"185mm² 4 core PVC SWA cable","No."]
[1.9," PVC SABS approved Conductors (GP Wire):"]
[null,"1.5mm² PVC Wire","m"]
[null,"2.5mm² PVC Wire","m"]
[null,"4mm² PVC Wire","m"]
[null,"6mm² PVC Wire","m"]
[null,"10mm² PVC Wire","m"]
[null,"16mm² PVC Wire","m"]
[null,"25mm² PVC Wire","m"]
[null,"35mm² PVC Wire","m"]
[{"v":1.1,"d":"1.10"},"SABS approved Silicon Wire:"]
[null,"1.5mm² single Wire","m"]
[null,"2.5mm² single Wire","m"]
[null,"4mm² single Wire","m"]
[null,"6mm² single Wire","m"]
[null,"1.5mm² 3 core wire","m"]
[null,"2.5mm² 3 core wire","m"]
{"$rows_empty":11}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.11," SABS approved Cabtyre:"]
[null,"1.5mm² 3 core wire","m"]
[null,"1.5mm² 4 core wire","m"]
[null,"1.5mm² 5 core wire","m"]
[null,"1.5mm² 7 core wire","m"]
[null,"2.5mm² 3 core wire","m"]
[null,"2.5mm² 4 core wire","m"]
[null,"2.5mm² 5 core wire","m"]
[null,"4mm² 3 core wire","m"]
[1.12," SABS approved Surfix:"]
[null,"1.5mm² 2+E ","m"]
[null,"1.5mm² 3+E ","m"]
[null,"1.5mm² 4+E ","m"]
[null,"2.5mm² 2+E ","m"]
[null,"2.5mm² 3+E ","m"]
[null,"2.5mm² 4+E ","m"]
[null,"4mm² 2+E ","m"]
[null,"4mm² 3+E ","m"]
[null,"4mm² 4+E ","m"]
[null,"6mm² 2+E ","m"]
[null,"6mm² 3+E ","m"]
[null,"6mm² 4+E ","m"]
[1.13," SABS approved Bare Copper Conductors:"]
[null,"1.5mm² Bare Copper Conductor (BCEW)","m"]
[null,"2.5mm² Bare Copper Conductor (BCEW)","m"]
[null,"4mm² Bare Copper Conductor (BCEW)","m"]
[null,"6mm² Bare Copper Conductor (BCEW)","m"]
[null,"10mm² Bare Copper Conductor (BCEW)","m"]
[null,"16mm² Bare Copper Conductor (BCEW)","m"]
[null,"25mm² Bare Copper Conductor (BCEW)","m"]
[null,"35mm² Bare Copper Conductor (BCEW)","m"]
[null,"50mm² Bare Copper Conductor (BCEW)","m"]
[null,"70mm² Bare Copper Conductor (BCEW)","m"]
[null,"95mm² Bare Copper Conductor (BCEW)","m"]
[1.14,"SABS approved Cable Ladders:"]
[null,"150mm Wide Power way Cable Ladder","m"]
[null,"200mm Wide Power way Cable Ladder","m"]
[null,"300mm Wide Power way Cable Ladder","m"]
[null,"400mm Wide Power way Cable Ladder","m"]
[null,"500mm Wide Power way Cable Ladder","m"]
[null,"600mm Wide Power way Cable Ladder","m"]
[null,"800mm Wide Power way Cable Ladder","m"]
[null,"1000mm Wide Power way Cable Ladder","m"]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.15,"SABS approved Cable Ladder Brackets:"]
[null,"150mm Wide Cantilever Arm","ea"]
[null,"200mm Wide Cantilever Arm","ea"]
[null,"250mm Wide Cantilever Arm","ea"]
[null,"350mm Wide Cantilever Arm","ea"]
[null,"450mm Wide Cantilever Arm","ea"]
[null,"550mm Wide Cantilever Arm","ea"]
[null,"650mm Wide Cantilever Arm","ea"]
[null,"850mm Wide Cantilever Arm","ea"]
[null,"1050mm Wide Cantilever Arm","ea"]
[1.16," SABS approved Power Skirting:"]
[null,"Single Compartment With Cover","m"]
[null,"External Elbow","ea"]
[null,"Internal Elbow","ea"]
[null,"Flat Elbow","ea"]
[null,"Flat Tee","ea"]
[null,"End Cap","ea"]
[null,"Two Compartment With Covers","m"]
[null,"External Elbow","ea"]
[null,"Internal Elbow","ea"]
[null,"Flat Elbow","ea"]
[null,"Flat Tee","ea"]
[null,"End Cap","ea"]
[null,"Three Compartment With Covers:","m"]
[null,"External Elbow","ea"]
[null,"Internal Elbow","ea"]
[null,"Flat Elbow","ea"]
[null,"Flat Tee","ea"]
[null,"End Cap","ea"]
[1.17,"SABS approved Steel Power Skirting Accessories:"]
[null,"Normal plug Including Cradle And Cover","ea"]
[null,"Dedicated plug Including Cradle And Cover","ea"]
[null,"Euro Socket Including Cradle And Cover","ea"]
[null,"Double Data plug Including Cradle And Cover","ea"]
[null,"Telkom plug Including Cradle And Cover","ea"]
[null,"USB Point Including Cradle And Cover","ea"]
[null,"Power Pole With Covers","m"]
{"$rows_empty":11}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.18,"SABS approved Lamps:"]
[null,"G4 1W Lamp LED","ea"]
[null,"G4 2W Lamp LED","ea"]
[null,"G9 3W Lamp LED","ea"]
[null,"G9 3.5W Lamp Dimmable LED","ea"]
[null,"R7S 6W LED Lamp 78mm","ea"]
[null,"R7S 75W Halogen Lamp 78mm","ea"]
[null,"R7S 10W LED Lamp 118mm","ea"]
[null,"R7S 150W Halogen Lamp 118mm","ea"]
[null,"50W 12V Down Light MR16","ea"]
[null,"20W 12V Down Light MR14","ea"]
[null,"3W 12V LED MR16","ea"]
[null,"5.5W 12V LED MR16","ea"]
[null,"7W 12V LED MR16","ea"]
[null,"7W 12V LED MR16 Dimmable","ea"]
[null,"3W 220V LED GU10","ea"]
[null,"5.5W 220V LED GU10","ea"]
[null,"7W 220V LED GU10","ea"]
[null,"7W 220V LED GU10 Dimmable","ea"]
[null,"Circular Tube 22W","ea"]
[null,"Circular tube 32W","ea"]
[null,"Circular tube 40W","ea"]
[null,"40W Incadesent Lamp BC/ES","ea"]
[null,"5W Filament Lamp BC/ES LED","ea"]
[null,"7W Filament Lamp BC/ES LED","ea"]
[null,"40W Incadesent Lamp  Mini BC/ES (E14)","ea"]
[null,"4W A60 Lamp Mini BC/ES LED E14","ea"]
[null,"40W Candle Lamp BC/ES","ea"]
[null,"4W Candle Lamp BC/ES LED","ea"]
[null,"40W Candle Lamp Mini BC/ES (E14)","ea"]
[null,"4W Candle Lamp E14  Mini BC/ES LED (E14)","ea"]
[null,"40W Golfball ES Lamp BC/ES","ea"]
[null,"5W Golfball ES A60 Lamp BC/ES LED","ea"]
[null,"40W Golfball ES Lamp Mini BC/ES E14","ea"]
[null,"4W Golfball ES Lamp Mini BC/ES LED (E14)","ea"]
[null,"7W A60 LED Lamp Day /Night Sensor","ea"]
[null,"7W A60 LED Lamp Movement Sensor","ea"]
[null,"2D Compact Fluorescent Lamp","ea"]
[null,"2D Replacement LED Element 2 Pin 12w","ea"]
[null,"9W Compact Fluorescent Lamp","ea"]
{"$rows_empty":8}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[null,"11W Compact Fluorescent Lamp","ea"]
[null,"CFL LED Replacement 2.5W","ea"]
[null,"13W Compact Fluorescent Lamp","ea"]
[null,"CFL LED Replacement 4.5W","ea"]
[null,"14W Compact Fluorescent Lamp","ea"]
[null,"CFL LED Replacement 5.5W","ea"]
[null,"15W Compact Fluorescent Lamp","ea"]
[null,"CFL LED Replacement 9W","ea"]
[null,"18W Compact Fluorescent Lamp","ea"]
[null,"26W Compact Fluorescent Lamp","ea"]
[null,"85W Compact Fluorescent Lamp (ES40)","ea"]
[null,"PL5 Lamp","ea"]
[null,"PL7 Lamp","ea"]
[null,"PL9 Lamp","ea"]
[null,"PL11 Lamp","ea"]
[null,"PL13 Lamp","ea"]
[null,"PL18 Lamp","ea"]
[null,"PL26 Lamp","ea"]
[null,"8W 12V DC Linear Fluorescent Lamp","ea"]
[null,"18W Linear Fluorescent Lamp","ea"]
[null,"9W LED Tube T8","ea"]
[null,"36W Linear Fluorescent Lamp","ea"]
[null,"18W LED Tube T8","ea"]
[null,"58W Linear Fluorescent Lamp","ea"]
[null,"24W LED Tube T8","ea"]
[null,"75W Linear Fluorescent Lamp","ea"]
[null,"28W Linear Fluorescent Lamp T5","ea"]
[null,"14W Linear Fluorescent Lamp T5","ea"]
[null,"R63 60W Incadesecnt lamp","ea"]
[null,"R63 60W LED lamp","ea"]
[null,"80W Mercury Vapour Lamp","ea"]
[null,"125W Mercury Vapour Lamp","ea"]
[null,"250W Mercury Vapour Lamp","ea"]
[null,"400W Mercury Vapour Lamp","ea"]
[null,"70W High Pressure Sodium Lamp","ea"]
[null,"100W High Pressure Sodium Lamp","ea"]
[null,"125W High Pressure Sodium Lamp","ea"]
[null,"250W High Pressure Sodium Lamp","ea"]
[null,"400W High Pressure Sodium Lamp","ea"]
[null,"1000W High Pressure Sodium Lamp","ea"]
[null,"70W  Metal Halide","ea"]
{"$rows_empty":7}
["Item","Description","Unit","QTY","Rate ","Amount "]
[null,"100W  Metal Halide","ea"]
[null,"125W  Metal Halide","ea"]
[null,"250W  Metal Halide","ea"]
[null,"400W  Metal Halide","ea"]
[null,"1000W  Metal Halide","ea"]
[null,"LED Highbay Light Lamp","ea"]
[1.19,"SABS approved Lamp Holders:"]
[null,"Rotolock Lamp Holder","ea"]
[null,"Telescopic Lamp Holder","ea"]
[null,"12V Down Light Lamp holder MR16","ea"]
[null,"220V Down Light Lamp holder GU10","ea"]
[null,"Down Light Fitting Springs","ea"]
[null,"E40 ES Ceramic Lamp Holder","ea"]
[{"v":1.2,"d":"1.20"}," SABS approved Starters:"]
[null,"18W Linear Fluorescent","ea"]
[null,"36W Linear Fluorescent","ea"]
[null,"58W Linear Fluorescent","ea"]
[null,"Ignitor For 250W/400W Lights","ea"]
[null,"10 micro Farad Capacitor","ea"]
[null,"45 micro Farad Capacitor","ea"]
[1.21,"SABC approved Electronic Transformer"]
[null,"12V Electronic Transformer For Low Voltage Lamps\nFrom 20W to 50W","ea"]
[1.22,"Supply SABS approved Ballasts:"]
[null,"9W Electronic Ballast For Compact Fluorescent Lamps","ea"]
[null,"13W Electronic Ballast For Compact Fluorescent Lamps","ea"]
[null,"18W Electronic Ballast For Compact Fluorescent Lamps","ea"]
[null,"26W Electronic Ballast For Compact Fluorescent Lamps","ea"]
[null,"18W Ballast For Linear Fluorescent Lamps","ea"]
[null,"36W Ballast For Linear Fluorescent Lamps","ea"]
[null,"58W Ballast For Linear Fluorescent Lamps","ea"]
[null,"75W Ballast For Linear Fluorescent Lamps","ea"]
[null,"400W Ballast For Floodlights","ea"]
[null,"250W Ballast For Floodlights","ea"]
[null,"125W Ballast For Floodlights","ea"]
[null,"2x18W 4 Output Electronic Ballast","ea"]
[null,"3x18W 4 Output Electronic Ballast","ea"]
[null,"3x18W 6 Output Electronic Ballast","ea"]
[null,"2x36W 6 Output Electronic Ballast","ea"]
[null,"2x36W 7 Output Electronic Ballast","ea"]
[null,"3x36W 8 Output Electronic Ballast","ea"]
[null,"2x58W 6 Output Electronic Ballast","ea"]
[null,"3x58W 7 Output Electronic Ballast","ea"]
[null,"3x58W 8 Output Electronic Ballast","ea"]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.23," SABS approved Complete Control Gear:"]
[null,"80W Mercury Vapor Lamp","ea"]
[null,"125W Mercury Vapor Lamp","ea"]
[null,"250W Mercury Vapor Lamp","ea"]
[null,"400W Mercury Vapor Lamp","ea"]
[1.24," SABS approved Complete Control Gear:"]
[null,"70W High Pressure Sodium Lamp","ea"]
[null,"100W High Pressure Sodium Lamp","ea"]
[null,"125W High Pressure Sodium Lamp","ea"]
[null,"250W High Pressure Sodium Lamp","ea"]
[null,"400W High Pressure Sodium Lamp","ea"]
[null,"1000W High Pressure Sodium Lamp","ea"]
[1.25," SABS approved Complete Control Gear:"]
[null,"70W Metal Halide Lamp","ea"]
[null,"100W Metal Halide Lamp","ea"]
[null,"125W Metal Halide Lamp","ea"]
[null,"250W Metal Halide Lamp","ea"]
[null,"400W Metal Halide Lamp","ea"]
[null,"1000W Metal Halide Lamp","ea"]
[1.26," SABS approved Complete Control Gear:"]
[null,"30W LED Flood Light","ea"]
[null,"50W LED Flood Light","ea"]
[null,"100W LED Flood Light","ea"]
[null,"120W LED Flood Light","ea"]
[null,"150W LED Flood Light","ea"]
[null,"LED Street Light","ea"]
[null,"LED Highbay Light","ea"]
[1.27," SABS approved Luminaries:"]
[null,"50W Low Voltage Pressed Steel Downlight complete with 12V Electronic Transformer","ea"]
[null,"Compact Fluorescent Down Lighter complete with electronic control gear suitable for 9W, 13W & 18W lamps - Lascon Futura Down Lighter","ea"]
[null,"LED Downlight 3W Cut Out 68mm","ea"]
[null,"LED Downlight 6W Cut Out 108mm","ea"]
[null,"LED Downlight 9W Cut Out 132mm","ea"]
[null,"LED Downlight 12W Cut Out 156mm","ea"]
[null,"LED Downlight 15W Cut Out 172mm","ea"]
[null,"Metal Halide Down Lighter complete wtih control gear suitable for 70W & 150W Lascon Metal Halide Down Lighter","ea"]
[]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[null,"LED 12W Surface Mount Round","ea"]
[null,"LED 18W Surface Mount Round","ea"]
[null,"LED 24W Surface Mount Round","ea"]
[null,"LED 12W Surface Mount Square","ea"]
[null,"LED 18W Surface Mount Square","ea"]
[null,"LED 24W Surface Mount Square","ea"]
[null,"3X36W AR27 Recessed Fluorescent Luminaire complete with electronic control gear, diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"3X36W AR27 Recessed LED Luminaire complete with diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"3X36W LLB Recessed Fluorescent Luminaire complete with electronic control gear, diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"3X36W LLB Recessed LED Luminaire complete with diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"3X18W AR27 Recessed Fluorescent Luminaire complete with electronic control gear, diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"3X18W LLB Recessed Fluorescent Luminaire complete with electronic control gear, diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"2X36W AR27 Surface Mounted Fluorescent Luminaire complete with electronic control gear, diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"2X36W AR27 Surface Mounted LED Luminaire complete with diffuser, cabtyre with 5Amp plug, lamps etc","ea"]
[null,"2X58W  Open Channel Fluorescent Luminaire complete with telescopic lamp holders, electronic control gear, lamps, etc","ea"]
[null,"2X58W  Open Channel LED Luminaire complete  \n with telescopic lamp holders, lamps, etc","ea"]
[null,"LED Emergency Exit Light - emergency maintained exit box complete with lamp, internal wiring, NiCad batteries for 2.6 hours backup and pictogram","ea"]
[null,"2X18W Round Dome Type Bulk Head Luminaire\ncomplete with electronic control gear, lamp holders","ea"]
{"$rows_empty":9}
["Item","Description","Unit","QTY","Rate ","Amount "]
[null,"LED Bulk Head Round 20W IP65","ea"]
[null,"High Bay Luminaire suitable for 250W or 400W mercury vapour, high pressure sodium or metal halide lamps complete with control gear, wiring and lamp ","ea"]
[null,"Bulk Head Luminaire suitable for mercury vapour, high pressure sodium or metal halide lamps complete with control gear, wiring and lamp","ea"]
[null,"2X36W LED IP65 Vapour Proof Luminaire complete with lamps, electronic control gear, lamp holders etc ","ea"]
[null,"2X58W IP65 Vapour Proof Luminaire complete with\nlamps, electronic control gear, lamp holders etc ","ea"]
[null,"Flood light Luminaire suitable for 250W & 400W  metal halide or high pressure sodium lamps complete with lamp, control gear, fixing bracket ","ea"]
[null,"2x26W Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket (Reef light)","ea"]
[null,"10W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"20W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"30W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"50W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"70W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"80W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket (Beka LED nova-midi)","ea"]
[null,"100W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"120W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
{"$rows_empty":11}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[null,"150W LED Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"279W LED Flood Luminaire complete with lamp, control gear ,fixing bracket  (Beka LED flood)","ea"]
[null,"463W LED Flood Luminaire complete with lamp, control gear ,fixing bracket (Beka OMNI star - maxi)","ea"]
[null,"10W LED Sensor Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"20W LED Sensor Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"30W LED Sensor Spot/Flood Luminaire complete with lamp, control gear ,fixing bracket ","ea"]
[null,"LED Street Luminaire complete with lamp, control gear ,fixing bracket (Beka- LED lumi mini 55W)","ea"]
[null,"LED Highbay Luminaire complete with lamp, control gear ,fixing bracket (BEKA - LED bay 216W)","ea"]
[null,"LED Highbay Luminaire complete with lamp, control gear ,fixing bracket (BEKA - OMNI star 463W)","ea"]
[1.28,"SABS approved Light switches: (Crabtree + Clipsal)"]
[null,"16A, single lever, one way","ea"]
[null,"16A, two lever, one way","ea"]
[null,"16A, three lever, one way","ea"]
[null,"16A,four lever, one way","ea"]
[null,"16A, single lever, two way","ea"]
[null,"16A, illuminated single lever, one way","ea"]
[null,"16A, single lever, one way surface mounted","ea"]
[null,"16A, single lever, dimmable, one way","ea"]
[null,"16A, two lever, dimmable, one way","ea"]
[null,"Ceiling Mounted Motion Detector PIR With Ultrasonic Detection Also (Schneider SAE-UE-MS-CSAWE)","ea"]
[1.29," SABS approved Photo Day Light Switches:"]
[null,"10A Photo Electrical Switch","ea"]
[null,"15A Photo Electrical Switch","ea"]
[null,"20A Photo Electrical Switch","ea"]
{"$rows_empty":8}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[{"v":1.3,"d":"1.30"}," SABS approved Switched Socket Outlets: (Crabtree + Clipsal)"]
[null,"16A, single SSO c/w cover (4x4)","ea"]
[null,"16A, single SSO Slim line (Euro) in draw box ","ea"]
[null,"16A, double SSOc/w (4x4)","ea"]
[null,"16A, single dedicated SSO c/w (4x4)","ea"]
[null,"16A, double dedicated SSO c/w (4x4)","ea"]
[null,"16A, single SSO c/w (2x4)","ea"]
[null,"16A, single dedicated SSO c/w (2x4)","ea"]
[null,"16A, double  SSO surface mounted with surface box (4x4)","ea"]
[null,"16A, single  SSO surface mounted with surface box (4x4)","ea"]
[null,"16A, single  SSO (Industrial Plug)","ea"]
[null,"16A, double  SSO (Industrial Plug)","ea"]
[null,"16A, single dedicated SSO (Industrial Plug)","ea"]
[null,"16A, double dedicated SSO (Industrial Plug)","ea"]
[null,"16A, 3pin f/male switchable caravan plug","ea"]
[null,"32A, 3pin f/male switchable caravan plug","ea"]
[null,"63A, 3pin f/male switchable caravan plug","ea"]
[null,"16A, 3pin male caravan plug top","ea"]
[null,"32A, 3pin male caravan plug top","ea"]
[null,"63A, 3pin male caravan plug top","ea"]
[null,"32A, 5pin f/male switchable caravan plug","ea"]
[null,"32A, 5pin male caravan plug top","ea"]
[null,"5A, single SSO for round box","ea"]
[null,"5A, single SSO for 2x4 box","ea"]
[null,"5A plug tops","ea"]
[null,"16A Plug top Normal","ea"]
[null,"16A Plug top Dedicate Red/Blue/Black","ea"]
[null,"16A Slim line Plug top (Euro)","ea"]
[null,"2x4 Steel/PVC extension box","ea"]
[null,"4x4 Steel/PVC extension box","ea"]
[null,"2x4 Blank plate","ea"]
[null,"4x4 Blank plate","ea"]
[null,"Round blank plates","ea"]
[null,"4x4 Weather proof plug box","ea"]
[]
[]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[]
[1.31,"SABS approved Isolators: (Crabtree + Clipsal)"]
[null,"30A double pole flush mounted","ea"]
[null,"30A four pole flush mounted","ea"]
[null,"60A double pole flush mounted","ea"]
[null,"60A four pole flush mounted","ea"]
[null,"30A double pole surface mounted with box","ea"]
[null,"30A four pole surface mounted with box","ea"]
[null,"60A double pole surface mounted with box","ea"]
[null,"60A four pole surface mounted with box","ea"]
[null,"20A double pole with cord outlet","ea"]
[null,"20A double pole with cord outlet surface mounted","ea"]
[null,"30A double pole (Industrial)","ea"]
[1.32," SABS approved DB's And Enclosures: "]
[null,"3CR12 Stubbie/Kiosk","ea"]
[null,"10 Way Surface Mount","ea"]
[null,"18 Way Surface Mount","ea"]
[null,"20 Way Surface Mount","ea"]
[null,"3x12 Way Surface Mount","ea"]
[null,"3x28 Way Surface Mount","ea"]
[null,"Clip In Neutral Bar","ea"]
[null,"DB Conversion Clips (Adaptor Plates)","ea"]
[null,"DB Blanks","ea"]
[null,"Single Phase Bus bar For Breakers","ea"]
[null,"Tree Phase Bus bar For Breakers","ea"]
[null,"DB Lable Booklet","ea"]
[1.33," Lamp Poles With Brackets: "]
[null,"Beca 7m Fibreglass","ea"]
[null,"Beca 12m Fibreglass","ea"]
[null,"Galvanised Steel 5.5m","ea"]
[null,"Garden Light Pole 3m","ea"]
{"$rows_empty":7}
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.34," SABS approved Timers:"]
[null,"24Hour Timer with Battery Backup - CBI","ea"]
[null,"24Hour 7 Day Timer With Battery Backup - Schneider","ea"]
[null,"24Hour 7 Day Timer With Battery Backup For Geyser Purposes With Din to Samite Rail Conversion Plate","ea"]
[null,"24Hour 7 Day Timer With Battery Backup - Top Tronic","ea"]
[1.35," SABS approved Conduit And Accessories:"]
[null,"20mm PVC Conduit Pipe","m"]
[null,"25mm PVC Conduit Pipe","m"]
[null,"20mm PVC Couplings","ea"]
[null,"25mm PVC Couplings","ea"]
[null,"20mm PVC Adaptors","ea"]
[null,"25mm PVC Adaptors","ea"]
[null,"20mm PVC 90 Deg Bend","ea"]
[null,"25mm PVC 90 Deg Bend","ea"]
[null,"20mm PVC Saddles","ea"]
[null,"25mm PVC Saddles","ea"]
[null,"PVC Round Looping Box With Cover Plate","ea"]
[null,"20mm Galvanised Conduit Pipe","m"]
[null,"25mm Galvanised Conduit Pipe","m"]
[null,"32mm Galvanised Conduit Pipe","m"]
[null,"20mm Galvanised Couplings","ea"]
[null,"25mm Galvanised Couplings","ea"]
[null,"32mm Galvanised Couplings","ea"]
[null,"20mm Galvanised Adaptors","ea"]
[null,"25mm Galvanised Adaptors","ea"]
[null,"32mm Galvanised Adaptors","ea"]
[null,"20mm Galvanised 90 Deg Bend","ea"]
[null,"25mm Galvanised 90 Deg Bend","ea"]
[null,"32mm Galvanised 90 Deg Bend","ea"]
[null,"20mm Galvanised Hospital Saddles","ea"]
[null,"25mm Galvanised Hospital Saddles","ea"]
[null,"32mm Galvanised Hospital Saddles","ea"]
[null,"50mm Galvanised Conduit Pipe","m"]
[null,"50mm Galvanised Couplings","ea"]
[null,"50mm Galvanised Adaptors","ea"]
[null,"50mm Galvanised 90 Deg Bend","ea"]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[]
[null,"50mm Galvanised Hospital Saddles","ea"]
[null,"20mm Steel Sprague Tube","m"]
[null,"25mm Steel Sprague Tube","m"]
[null,"20mm Steel Sprague Tube Male Adaptor","ea"]
[null,"25mm Steel Sprague Tube Male Adaptor","ea"]
[1.36," SABS Approved Trunking And Accessories:"]
[null,"16x16 PVC Trunking","m"]
[null,"16x25 PVC Trunking","m"]
[null,"25x25 PVC Trunking","m"]
[null,"16x40 PVC Trunking","m"]
[null,"25x40 PVC Trunking","m"]
[null,"40x40 PVC Trunking","m"]
[null,"50x50 PVC Trunking","m"]
[null,"40x100 PVC Trunking","m"]
[null,"100x100 PVC Trunking","m"]
[null,"Half Round Tree Compartment Trunking 75mm","m"]
[null,"P1000 Galv Trunking","m"]
[null,"P2000 Galv Trunking","m"]
[null,"P4000 Galv Trunking","m"]
[null,"P1184 Galv Cover","m"]
[null,"P8000 Galv Trunking","m"]
[null,"P8100 Galv Trunking","m"]
[null,"P8200 Galv Trunking","m"]
[null,"P8300 Galv Trunking","m"]
[null,"P8300 Galv Trunking 5A Plug Knock Out","m"]
[null,"P8184 Galv Cover","m"]
[null,"P9800 Galv Trunking","m"]
[null,"P9810 Galv Trunking","m"]
[null,"P9000 Galv Trunking","m"]
[null,"P9184 Galv Cover","m"]
[null,"P9000 Galv Splices","ea"]
[null,"P9000 Galv End Caps","ea"]
[null,"P9000 Galv Hor Elbows","ea"]
[null,"P9000 Galv Int Elbows","ea"]
[null,"P9000 Galv Ext Elbows","ea"]
[]
[]
[]
[]
["Item","Description","Unit","QTY","Rate ","Amount "]
[]
[1.37,"Civil Works:"]
[null,"Concrete/Tar Cutting","m"]
[null,"Re-instate Concrete/Tar","m"]
[null,"Remove Paving","m"]
[null,"Re-instate Paving","m"]
[null,"Concrete Work ","cube"]
[null,"Install Cable Sleeves 110mm (Material Included)","m"]
[1.38,"Trenching Work:"]
[null,"Soft Soil","m"]
[null,"Hard Soil","m"]
[null,"Hard Rock","m"]
[null,"Backfill And Compacting","m"]
[null,"River sand","cube"]
[null,"Cable Marking Tape","m"]
[1.39,"Equipment Renting:"]
[null,"Scaffolding 10m High","p/d"]
[null,"Cherry Picker Diesel Driven 15m ","p/d"]
[{"v":1.4,"d":"1.40"},"Labour Costs, Special services"]
[null,"Cable Fault Testing - test tariff only excluding travel","p/fault"]
[null,"Disposal of fluorescent bulbs according to the Hazards chemicals substances regulations","p/kg"]
[1.41,"Electric Gate Motors with battery back-up"]
[null,"D5 Centurion sliding gate motor only, with battery","ea"]
[null,"D5 Centurion sliding gate motor complete with rack & baseplate","ea"]
[null,"D10 Centurion sliding gate motor only, with battery","ea"]
[null,"D10 Centurion sliding gate motor complete with rack  & baseplate","ea"]
[null,"Battery for D5 Centurion sliding gate motor","ea"]
[null,"Battery set for D10 Centurion sliding gate motor","ea"]
[null,"Controller circuit board for D5 Centurion Gate","ea"]
[null,"Controller circuit board for D10 Centurion Gate","ea"]
[null,"Remote control transmitter 2 button for Centurion gate motor","ea"]
[null,"Remote control transmitter 4 button for Centurion gate motor","ea"]
[]
[]
[]
[]
[]
["Name of Company Tendering:"]
[]
[]
["Address:"]
[]
[]
[]
[]
[]
[]
["Signature:"]

{"sheet":"PS717","index":8,"n_rows":121,"n_cols":8,"rows_kept":121,"merged":[[8,1,8,2],[10,1,10,2],[12,1,12,2],[14,1,14,2],[20,1,20,2],[26,1,26,2],[32,1,32,2],[38,1,38,2],[55,4,55,5]],"flags":["formulas_cached_only"]}
[null,"SECTION F"]
[]
[null,"BILL NO. 1"]
[]
[null,"ELECTRICAL WORKS"]
[]
[null,"PREAMBLES"]
[]
[null,"For preambles see \"Model Preambles for Trades (2008 Edition)\" and applicable supplementary preambles as specified in the Trades. The said Model and Supplementary Preambles apply to all work described in this document. Tenderers are therefor referred to these documents for the full meaning and intention of all descriptions as no claims of any kind whatsoever will be entertained in this regard."]
[]
[null,"All costs must be inclusive of supply, delivery, installation and insurance."]
[]
[null,"All items on Electrical works are re-measurable. Allowances are for budgetary purposes"]
[]
[null,"Note: All rates must include material, labour, transport, attendance and profit "]
[]
[null,"Electrical Works "]
[]
[null,"Provisional Amounts"]
[]
[null,"Allow Provisional Sums for Energy Saving Light fittings and sensors ",null,"Prov Sum",1,{"v":70000,"d":"70,000.00"},null,{"v":70000,"d":"R70,000.00"}]
[]
[null,"Attendance ",null,null,{"v":0.15,"d":"15%"},{"v":10500,"d":"10,500.00"},null,{"v":10500,"d":"R10,500.00"}]
[]
[null,"Profit ",null,null,{"v":0.2,"d":"20%"},{"v":14000,"d":"14,000.00"},null,{"v":14000,"d":"R14,000.00"}]
[]
[null,"Allow Provisional Sums for DB's",null,"Prov Sum",1,{"v":50000,"d":"50,000.00"},null,{"v":50000,"d":"R50,000.00"}]
[]
[null,"Attendance ",null,null,{"v":0.15,"d":"15%"},{"v":7500,"d":"7,500.00"},null,{"v":7500,"d":"R7,500.00"}]
[]
[null,"Profit ",null,null,{"v":0.2,"d":"20%"},{"v":10000,"d":"10,000.00"},null,{"v":10000,"d":"R10,000.00"}]
[]
[null,"Allow Provisional Sums for Power Point ",null,"Prov Sum",1,{"v":50000,"d":"50,000.00"},null,{"v":50000,"d":"R50,000.00"}]
[]
[null,"Attendance ",null,null,{"v":0.15,"d":"15%"},{"v":7500,"d":"7,500.00"},null,{"v":7500,"d":"R7,500.00"}]
[]
[null,"Profit ",null,null,{"v":0.2,"d":"20%"},{"v":10000,"d":"10,000.00"},null,{"v":10000,"d":"R10,000.00"}]
[]
[null,"Allow Provisional Sums for Cable work ",{"$nulls":3},{"v":70000,"d":"70,000.00"},null,{"v":70000,"d":"R70,000.00"}]
[]
[null,"Attendance ",null,null,{"v":0.15,"d":"15%"},{"v":10500,"d":"10,500.00"},null,{"v":10500,"d":"R10,500.00"}]
[]
[null,"Profit ",null,null,{"v":0.2,"d":"20%"},{"v":14000,"d":"14,000.00"},null,{"v":14000,"d":"R14,000.00"}]
[]
[]
[]
[]
[null,"Total Carried to Collection",{"$nulls":5},{"v":324000,"d":"R324,000.00"}]
[]
[]
[]
[null,"Section 2"]
[null,"Bill No. 8"]
[null,"Electrical Works"]
[]
["Item",{"$nulls":3},"Page No.",null,null,"Amounts"]
[null,"SECTION 2"]
[]
[null,"BILL NO. 1"]
[]
[null,"ELECTRICAL WORKS"]
[]
[]
[null,"COLLECTION"]
[]
[]
[null,"Total Brought forward from page no.",null,null,34]
[]
[{"$nulls":4},35]
[]
[{"$nulls":4},36]
[]
[{"$nulls":4},37]
{"$rows_empty":37}
[null,"Total Carried to Summary ",{"$nulls":5},0]
{"$rows_empty":7}
[null,"Section 2"]
[null,"Bill No. 1"]
[null,"Electrical Works"]