NEC3 Term Service Contract

| A Contract between | Eskom Holdings SOC Ltd. (Reg No. 2002/015527/30; VAT No. 4740101508) |  |
| --- | --- | --- |
| and |  |  |
| for | The provision of ‘as and when’ maintenance and repair services for approximately 370 online dissolved gas analysers installed in Eskom Transmission, that is about 300 Kelman TRANSFIX and 70 TM8 Multi Gas Severon gas analysers. The contractor is required to make sure that the gas analyser are repaired and serviced as and when requested by Transmission Grid’s personnel. |  |
| Contents: |  | Doc Ref |
| Part 1 | Agreements & Contract Data | C1.1 & C1.2 |
| Part 2 | Pricing Data | C2.1 & C2.2 |
| Part 3 | Scope of Work : Service Information | C3.1 |

# PART 1:	 AGREEMENTS & CONTRACT DATA

| ## Document reference | ## Title | ## No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer & Acceptance | 2 |
| C1.2 | Contract Data |  |
|  | Data provided by the Employer | 16 |
|  | Data provided by the Contractor | 1 |

Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance page signature block on the next page, has solicited offers to enter into a contract for the procurement of:

The provision of ‘as and when’ maintenance and repair services for approximately 370 online dissolved gas analysers installed in Eskom Transmission, that is about 300 Kelman TRANSFIX and 70 TM8 Multi Gas Severon gas analysers. The contractor is required to make sure that the gas analyser are repaired and serviced as and when requested by Transmission Grid’s personnel.

The tenderer, identified in the signature block below, has examined the draft contract as listed in the Acceptance page and agreed to provide this Offer.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the Contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

|  | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Purchaser by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Supplier in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an Agreement between the Employer and the tenderer upon the terms and conditions contained in this Agreement and in the Contract that is the subject of this Agreement.

The terms of the Contract, are contained in:

Part 1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part 2	Pricing Data

Part 3	Scope of Work: (Service Information)

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule, which must be signed by the duly authorised representative(s) for both parties.

The tenderer shall within one week of receiving a completed copy of this Agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this Agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this Agreement.

Notwithstanding anything contained herein, this Agreement comes into effect on the date when the tenderer receives one fully completed copy of this document, including the Schedule of Deviations (if any).  Unless the tenderer (now Contractor) within five days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this Form of Offer and Acceptance, this Agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |
| --- | --- | --- | --- |
| Name(s) | S Scheppers |  |  |
| Capacity | Group Executive: Transmission |  |  |
| for the Employer | Eskom Holdings SOC Ltd Megawatt Park, Maxwell Drive, Sandton, Johannesburg, 2199 |  |
| Name & signature of witness | M Kibido General Manager Transmission Grids ………………………………… …………………………………… |  |  |  |

Contract Data

# Part one - Data provided by the Employer

| Clause number | ## Statement | ## Data |  |  |
| --- | --- | --- | --- | --- |
| 1 | ## General |  |  |  |
| 10.1 | The Employer is (name): | Eskom Holdings SOC Ltd. (reg no: 2002/015527/30), a juristic person incorporated in terms of the company laws of the Republic of South Africa |  |  |
|  | Address | Megawatt Park, Maxwell Drive, Sandton, 2199. |  |  |
|  | Tel No. | 011 800 2105 |  |  |
|  | Fax No. | 086 538 2581 |  |  |
| 10.1 | The Service Manager is (name): | Thapelo Ndlovu |  |  |
|  | Address | 235 Beyers Naude, Rustenburg, North West |  |  |
|  | Tel | 014 565 1333 or 072 425 1880 |  |  |
|  | Fax | N/A |  |  |
|  | e-mail | NdlovuTS@eskom.co.za |  |  |
| 11.1 | The conditions of contract are the core clauses and the clauses for main Option: |  |  |  |
|  |  | A: Priced contract with price list |  |  |
|  | dispute resolution Option | W1 Dispute resolution |  |  |
|  | and secondary Options | X2: Changes in the law |  |  |
|  |  | X18: Limitation of liability |  |  |
|  |  | X19: Task Order |  |  |
|  |  | X20: Key performance indicators |  |  |
|  |  | Z Additional conditions of contract |  |  |
|  | of the NEC3 Term Service Contract (April 2013) |  |  |  |
| 11.2(2) | The Affected Property is | power transmission facilities operated by the Transmission Division of Eskom Holdings SOC Ltd. |  |  |
| 11.2(13) | The service is | The provision of ‘as and when’ maintenance and repair services for approximately 370 online dissolved gas analysers installed in Eskom Transmission, that is about 300 Kelman TRANSFIX and 70 TM8 Multi Gas Severon gas analysers. The contractor is required to make sure that the gas analyser are repaired and serviced as and when requested by Transmission Grid’s personnel. |  |  |
| 11.2(14) | The following matters will be included in the Risk Register | as identified by the parties from time to time, and recorded in the Site specific Risk Registers |
| 11.2(15) | The Service Information is in | Part 3 Scope of Work. |  |
| 12.2 | The law of the contract is the law of | the Republic of South Africa subject to the jurisdiction of the Courts of South Africa. |  |
| 13.1 | The language of this contract is | English. |  |
| 13.3 | The period for reply to a communication is | within eight hours unless otherwise stated in a Task Order. |  |
| ## 2 | ## The Contractor’s main responsibilities |  |  |
| 21.1 | The Contractor is to submit a first plan for acceptance within | the Employers official outage plan is used as the accepted plan, and for all work done in Task Orders, as specified in the task order |  |
| ## 3 | ## Time |  |  |
| 30.1 | The starting date is. | 1 December 2021 |  |
| 30.1 | The service period is | from the starting date until 31 November 2023 |  |
| ## 4 | ## Quality |  |  |
| ## 42.1 | ## Testing and Defects | The Defect correction period for a particular defect, is to be agreed by the party’s at the first meeting when that defect is formally discussed. Due to the complexity of this Service, it is not beneficial to have a specific time period stipulated in the Contract Data, as it is often not in the Employers interest to take Affected property out of service to correct a defect, but to rather decide when the optimal time is to correct the defect. |  |
| ## 42.2 | ## Contract Quality Plan (CQP) and Quality Control Plan (QCP)/ Inspection and Test Plan (ITP) | The Quality Plans must be reviewed and approved by the contractor and employer within four (4) weeks after contract award. |  |
| ## 42.3 | ## Quality Management System (QMS) | The Contractor shall maintain a QMS ISO 9001 certificate as per 240-105658000 (QM 58) specification for Supplier Quality Management. The contractor’s QMS must drive management system processes to ensure that employer’s requirements are fully met on a consistent basis. |  |

| ## 5 | ## Payment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 50.1 | The assessment process is |  | On each Task Order the assessment schedule is agreed and recorded on the Task Order under the heading (Assessment schedule). The alternatives for assessments are: - The assessments will be based upon the assessment date and intervals agreed upon and recorded in the Task Order. - Percentage completion assessments may be agreed to and recorded on the Task Order, which stipulates assessment percentages against a project milestone and not a date. Default is alternative 1 in case of disagreement. The parties may agree to an assessment at the start of the work but the assessment will be based on pre outage work completed or costs incurred to date. |  |  |  |  |
| 50.1 | The assessment date is |  | to be specified in the task order |  |  |  |  |
| 50.1 | The assessment interval is |  | to be specified in the task order |  |  |  |  |
| 51.1 | The currency of this contract is the |  | South African Rand. |  |  |  |  |
| 51.2 | The period within which payments are made is |  | 30 days from receipt of a valid Contractor’s invoice to the Employer. |  |  |  |  |
| 51.4 | The interest rate is |  | the publicly quoted prime rate of interest (calculated on a 365 day year) charged by from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands. |  |  |  |  |
| ## 6 | ## Compensation events |  |  |  |  |  |  |
| ## 61.8 |  |  | The Contractor will submit a compensation event 3 days after the early warning and Technical notification meeting (site work). ## Compensation Events are to be approved by the Employer within 48 hours of receipt from the Contractor. ## Should the Employer not agree with the terms of the compensation event, he shall declare a dispute within 24 hours |  |  |  |  |
| ## 7 | ## Use of Equipment Plant and Materials |  | ## No data is required for this section |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks |  |  |  | 1. Not Applicable |  |  |
| 83.1 |  | The Employer provides the insurances stated in the Insurance Table below. INSURANCE TABLE Insurance against; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; As per the insurance policy document.. Project insurance; As per the insurance policy document.. General and Public Liability; As per the insurance policy document.. Environmental Liability; As per the insurance policy document.. Transport (Marine); As per the insurance policy document.. Motor Fleet and Mobile Plant; As per the insurance policy document.. Terrorism; As per the insurance policy document.. Cyber Liability; As per the insurance policy document.. |
| 83.1 |  | The Contractor provides the insurances stated in the Insurance Table. The insurances provide cover for events which are at the Contractor’s risk from the starting date until the end of the service period or a termination certificate has been issued INSURANCE TABLE Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage caused by the Contractor to the Employer’s property; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance.. Loss of or damage to Plant and Materials; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance.. Loss of or damage to Equipment; The replacement cost where not covered by the Employer’s insurance. The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance.. The Contractor’s liability for loss of or damage to property (except the Employer’s property, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Service; Loss of or damage to property The replacement cost Bodily injury to or death of a person The amount required by the applicable law.. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| ## 9 | ## Termination |  |  | No data required for this section |  |  |
| ## 10 | ## Data for main, W1 and secondary Option clauses |  |  |  |  |  |
| A: | Priced contract with Price List |  |  |  |  |  |
| 20.5 | The Contractor prepares forecasts of the final total of the Prices for the whole of the service at intervals no longer than |  |  | Not applicable: See additional condition Z15. |  |  |
| W | W1 Dispute resolution |  |  |  |  |  |
| W1.1 | The Adjudicator is (name): |  |  | the strategic team comprising the Employer’s General Manager and the Contractor’s Product Group Manager to whom the Parties delegate their respective responsibility for this contract. |  |  |
|  |  |  |  | Note: The strategic team is part of the steering committee which performs the functions described in the Service Information. |  |  |
| W1.2(3) | The adjudicator nominating body is |  |  | N/A |  |  |

| W1.4(2) |  | The tribunal is: |  |  |  | arbitration |
| --- | --- | --- | --- | --- | --- | --- |
| W1.4(5) |  | The arbitration procedure is |  |  |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |
|  |  | The place where arbitration is to be held is |  |  |  | Johannesburg – South Africa |
|  |  | The person or organisation which will choose an arbitrator if the Parties cannot agree a choice or if the arbitration procedure does not state who selects a replacement arbitrator is: |  |  |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |
| W1. |  | Dispute resolution Option W1 |  |  |  | “Any dispute arising under or in connection with this contract is decided by the CTOM and the ETOM at the location where the dispute arose. That part of the dispute which has not been settled is then referred to and decided by, in the order listed - 2. Outage or Project Dispute - Level 1: - Employers Outage / Project Manager and Contractors Project Manager - Level 2: - Employers Senior Manager and Contractors Service Manager - Level 3: - Employers Senior Representative and Contractors Senior Representative - Dispute must be completed within 7 days on each of the above levels |
| W2.1 |  |  |  |  |  | Only disputes notified by formal dispute resolution form (Appendix 9) will be recorded on the dispute log. Any dispute resolved before it is recorded in a dispute resolution form, will be taken to be resolved, and not recorded on the dispute log |
| W2.2 |  |  |  |  |  | Delete the words “Between two and four weeks” at the beginning of each entry in the right hand column of the Adjudication Table in clause W1.3(1) and replace by “By the date decided by the steering committee.” |
| X1 |  | Price adjustment for inflation |  |  | N/A |  |
| X1.1 |  | The base date for indices is |  |  | for CPI: April of that year (SIEFSA D2) for Labour: As per Eskom Bargaining and Non Bargaining |  |
|  |  |  |  |  | The escalation is determined through using the table below (The values populating this table are examples only). The proportion split and weights will be calculated in the rates calculation process and will be fixed and firm for the service period. Other cost based on CPI as at December of the preceding year published by Stats SA |  |
| X.1.1 |  | Price adjustment |  |  |  |  |  |
| X.1.1.1 |  |  |  | The agreed calculated Prices in the Price List are fixed and firm for the first year and thereafter adjusted annually on 1st July. The annual rates increases in the Price List are calculated before 30 June each year, based on clause X1. |  |  |  |
| X.1.12 |  |  |  | For quotations in progress or Task Orders already in execution, but overlapping into the next annual contract cycle, the Prices applicable after 1st July will only be used if the proportion of work after 1st July is more than 50% of the period between the starting date and the Completion Date. |  |  |  |  |
| X2 | Changes in the law |  |  |  | No data is required for this Option |  |
| X18 | Limitation of liability |  |  |  |  |  |
| X18.1 | The Contractor’s liability for indirect or consequential loss is limited to |  |  |  | R0.0 (Zero Rand) |  |
| X18.2 | For any one event the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to |  |  |  | the deductible due under the Employer’s Assets All Risks Policy, as specified in 83.1. The amount of the deductibles relevant to the event described in the “Format TSC3” insurance policy available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx |  |
| X18.3 | The Contractor’s liability for Defects due to his design of an item of Equipment is limited to |  |  |  | The greater of the total of the Prices at the Contract Date and the amounts excluded and unrecoverable from the Employer’s insurance (other than the resulting physical damage to the Employer’s property which is not excluded) plus the applicable deductibles in the Employer’s assets and works / maintenance policies available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx the amount of the Task Order from which the Defect arose. . |  |
| X18.4 | The Contractor’s total liability to the Employer, for all matters arising under or in connection with this contract, other than the excluded matters, is limited to |  |  |  | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for Defects due to his design, plan and specification, Defects due to manufacture and fabrication outside the Affected Property, loss of or damage to property (other than the Employer’s property, Plant and Materials), death of or injury to a person and infringement of an intellectual property right. . |  |
| X18.5 | The end of liability date is |  |  |  | as per time periods stated in clause 4.4 in the Service Information and not later than five years for liability under clause X18.3 above after Completion of the Task Order from which the liability arose. |  |
| X19 | Task Order |  |  |  |  |  |
| X19.2 | Delay damages |  |  |  | 0.25% per day to a maximum of 1.5% per affected task order for site work 0.25% per week to a maximum of 1.5% per affected task order for workshop work. |  |
| X19.5 | The Contractor submits a Task Order programme for acceptance within |  |  |  | the time requirements stated in clause 3.2 and 3.3 of Service Information. |  |
| X20 | Key Performance Indictors |  |  |  |  |  |
| X20.1 | The incentive schedule for Key Performance Indicators is in |  |  |  | Clause 3.5 and Appendix 2 of the Service Information. |  |
| X20.2 | A report of performance against each Key Performance Indicator is provided at intervals of |  |  |  | Quarterly. |  |
| Z | The additional conditions of contract are: |  |  |  | Z1 to Z 18 will always apply |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry and the Electricity Distribution Industry. |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Service Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |
| Z2.3 | The Contractor does not substantially alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |
| Z3 | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |
| Z3.1 | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |
| Z3.2 | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Service Manager within thirty days of the notification or as otherwise instructed by the Service Manager. |  |  |  |  |  |
| Z3.3 | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |
| Z3.4 | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P4 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Service Manager. |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the Affected Property or any portion thereof, in the course of Providing the Service and after the end of the service period, requires the prior written consent of the Service Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Service Manager or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing |  |  |  |  |  |
| Z6 | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |
| Z6.1 | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the service. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Occupational Health & Safety Act 85 of 1993 and its regulations for the Affected Property; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Occupational Health & Safety Act 85 of 1993 and its regulations, safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of the service; and - undertakes, in and about the execution of the service, to comply with the applicable Occupational Health & Safety Act 85 of 1993 and its regulations, rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. For maintenance related work refer to attached signed document Non construction work agreement. |  |  |  |  |  |
| Z6.2 | The Contractor, in and about the execution of the service, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Service Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |
| Z8 | Notifying compensation events |  |  |  |  |  |
| Z8.1 | Delete from the last sentence in core clause 61.3, “unless the Service Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 82.1 is provided for in 60.1(12) and the Employer’s liability under the indemnity is limited to compensation as provided for under the compensation events stated in this contract. |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |
| Z10.1 | or had a judicial management order granted against it. |  |  |  |  |  |
| Z11 | Z11; Ethics. For the purposes of this Z-clause, the following definitions apply: Affected Party means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, Coercive Action means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, Collusive Action means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, Committing Party means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees, Corrupt Action means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, Fraudulent Action means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, Obstructive Action means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action and Prohibited Action means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. Z 11.1 A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. Z 11.2 The Employer may terminate the Contractor’s obligation to Provide the Service if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Service for this reason. Z 11.3 If the Employer terminates the Contractor’s obligation to Provide the Service for this reason, the procedures and amounts due on termination are respectively P1, P2, P3 and P4, and A1 and A3. Z 11.4 A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |
| Z13 | Defined Cost |  | Delete clause 11.2(5) and replace by: (5) “Defined Cost is the amount for people who are employed by the Contractor or for the Contractor’s work centres at the rates stated in the Price List, paid by the Contractor for Plant and Materials, paid by the Contractor for work that he has subcontracted, and paid to people and others by the Contractor in relation to people and work centres for expenses incurred for Providing the Service, less Disallowed Cost.” |  |  |  |
|  |  |  | The amount for Equipment is treated as being included in people or work centre rates stated in the Price List, except when Equipment is expressly identified in the Price List, or is in amounts paid to subcontractors. |  |  |  |
| Z14 | The Fee and the fee percentages |  | Delete clause 11.2(8) and replace by: (8)The Fee is the sum of the amounts calculated by applying the subcontracted fee percentage to the Defined Cost of Plant and Materials, subcontracted work, and expenses as described in clause Z13 above, (Contractor’s non capacity costs) and the direct fee percentage to the Defined Cost of other work (Contractor’s capacity costs). The subcontracted fee percentage and the direct fee percentage are calculated at the beginning of the service period, and will be applicable for the duration of the contract. |  |  |  |
| Z15 | Forecasts of the final total of the Prices |  | Delete clause 20.5 in Option A and replace by: The steering committee makes forecasts of the final total of the Prices for the whole of the service. Forecasts are made at the starting date and at each anniversary of the Contract Date until the end of the service period. An explanation of the changes made since the previous forecast is contained in each forecast. |  |  |  |
| Z16 | Limitation of liability for Defects in Plant and Materials manufactured, repaired or refurbished by the Contractor |  | Further to the requirements of clause 42: The Contractor is not liable for Defects arising from workmanship in Plant and Materials which he has manufactured, repaired or refurbished which are notified to him later than 12 months after Completion of the Task Order under which the work was carried out. If the Plant and Materials manufactured, repaired or refurbished by the Contractor are not put to their intended use when they are supplied, but placed instead into the Employer’s storage, the 12 month period starts and ends as stated in Clause 4.4 of the Service Information and in terms of the conditions stated in the Service Information. |  |  |  |
| Z17 | Incentive payments in secondary Option X20 |  | Add to clause X20.4: The Contractor pays to the Employer the amount calculated as stated in the Service Information if the target stated for a Key Performance Indicator is not achieved. Delete second sentence of clause X20.4 and replace by: Payment of the amount due by either Party to the other is done at the times stated in the Service Information. |  |  |  |
| Z18 | Searching for Defects |  |  |  |  |  |
| Z18.1 |  |  | Until the end of the service period, the Service Manager may instruct the Contractor to search for a Defect. He gives his reasons for the search with his instruction. Searching may include uncovering, dismantling, re-covering and re-erecting work, providing facilities, materials and samples for tests and inspections done by the Service Manager and doing tests and inspections which the Service Information does not require. |  |  |  |
| Z18.2 |  |  | If the Service Manager instructs the Contractor to search for a Defect and no Defect is found, or the Contractor’s liability for correcting Defects has expired, the instruction is a compensation event unless the search is needed only because the Contractor gave insufficient notice of doing work obstructing a required test or inspection. |  |  |  |
| Z18.3 |  |  | Before the contractors starts work under an instruction to search for a Defect, the pricing process described in Part 3 of this contract is to be followed, and the ETOM and CTOM shall both sign the Task order for the Search for Defect work, with reference to Clause Z8. However, this signed task order will not be accompanied by a 45 SAP order number, as it is only issued to ensure that the correct processes, durations, quality procedures are in place to protect the plant. This will also assist both the Employer and Contractor to know what the possible financial liability would be to whichever party is finally responsible for the outcome of the search for Defect work. Should a defect be found, then the Task order, and any associated compensation events will be closed at the Contractors cost, and should no defect be found, a 45 SAP order will be issued to the Task Order, and any associated compensation events value. |  |  |  |

Contract Data

# Part two - Data provided by the Contractor

Please read the relevant clauses in the NEC3 Term Service Contract (June 2005) in order to understand the implications of this Data.

| ## Clause number | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 52.1 | The direct fee percentage is | Zero. (Note: This is because the direct fee percentage has already been included into the Prices in the Price List of people and work centres.) |
|  | The subcontracted fee percentage for | Zero. |
| 24.1 | The key persons are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | Address |  |
|  | Telephone |  |
|  | Fax |  |
|  | E-mail |  |
| 21.1 | The plan identified in the Contract Data is | The Employers official outage plan is used as the accepted plan, and for all work done in Task Orders, as specified in the task order |
| A | Priced contract with price list |  |
| 11.2(12) | The price list is | Part 2 Pricing Data |
| 11.2(19) | The tendered total of the Prices is | [Not Applicable.] |

# Part 2: Pricing Data

TSC3 Option C

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option C | 2 |
| C2.2 | The price list | [●] |

C2.1 Pricing assumptions: Option C

# How work is priced and assessed for payment

Clause 11 in the core clauses and Option C clauses of the NEC3 Term Service Contract (TSC3) state:

| Identified and defined terms | 11 11.2 | (12) The Price List is the price list unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (18) The Price for Services Provided to Date is the Defined Cost which the Contractor has paid plus the Fee. |
|  |  | (20) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate. |

Payments are made at Defined Cost plus Fee (See core clauses 11.2(5), 11.2(6) and 11.2(8)).  At the dates stated in the Contract Data, the Service Manager calculates the Contractor’s share in terms of clause 53.  If the Contractor has been paid more than the equivalent Prices in the Price List for the same work he pays the Employer a portion of the over-run (the pain) but if he has been paid less than the equivalent Prices in the Price List he is paid a portion of the under-run (the gain).  The Prices in the Price List are derived from a list of items of service which can be priced as lump sums or as expected quantities of service multiplied by a rate or a mix of both.

# Function of the Price List

In this Option the Price List is used as a means of arriving at a target price.  Clause 54.1 in Option C states: “Information in the Price List is not Service Information”.  This confirms that instructions to do work or how it is to be done are not included in the Price List but in the Service Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Service in accordance with the Service Information”. Hence the Contractor does not Provide the Service in accordance with the Price List.

# Link to the Contractor’s plan

Clause 21.4 states “The Contractor provides information which shows how each item description on the Price List relates to the operations on each plan which he submits for acceptance”.  Hence when compiling the price list, the tendering contractor needs to develop his first clause 21.2 plan in such a way that operations shown on it can be related to items of service priced in the price list.

# Preparing the price list

Before preparing the price list, both the Employer and tendering contractors should read the TSC3 Guidance Notes pages 14 and 15.  In an Option C contract, either Party may have entered items into the price list either as a process of offer and acceptance (tendering) or by negotiation depending on the nature of the service to be provided.  Alternatively the Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in the price list to be prepared and priced by him.

It is assumed that in preparing or finalising the price list the Contractor:

- Has taken account of the guidance given in the TSC3 Guidance Notes relevant to Option C;

- Understands the Price List is only used as a means of arriving at a target and that work done is paid for at Defined Cost and the resulting Fee;

- Is aware of the need to link operations shown in his plan to items shown in the Price List;

- Has listed and priced items in the price list which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Service Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate item within the Prices or rates of other listed items in order to fulfil the obligation to complete the service for the tendered total of the Prices.

- Understands there is no adjustment to items priced as lump sums if the amount, or quantity, of work within that item later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the (lump sum) Prices is as a result of a compensation event.

## Format of the price list

Entries in the first four columns in the price list in section C2.2 are made either by the Employer or the tendering contractor.

If the price list includes an amount for the item which is not adjusted if the quantity of work in the item changes, the tendering contractor enters the amount in the Price column only, the Unit, Expected Quantity and Rate columns being left blank.

If the price list includes an amount for an item of work which is the rate for the work multiplied by the quantity completed, the tendering contractor enters the rate which is then multiplied by the Expected Quantity to produce the Price, which is also entered.

If the price list includes an item proportional to the length of time for which a service is provided, a unit of time is stated in the Unit column and the expected length of time (as a quantity of the stated units of time) is stated in the Expected Quantity column.

C2.2 the price list

| Item nr | Description | Unit | Expected Quantity | Rate | Price |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices |  |
| --- | --- |

# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page and contents | 3 |
| C3.1 | Employer’s Service Information | 23 |
|  | Appendix 1: Classification of services | 1 |
|  | Appendix 2: Key Performance Indicators | 2 |
|  | Appendix 3: Pro Forma Task Order | 3 |
|  | Appendix 4: Confidentiality Agreement | 2 |
|  | Appendix 5: Task costing schedules | 2 |
|  | Appendix 6: Dispute Resolution Form | 2 |
|  | Appendix 7: NCR Form | 1 |
|  | Appendix 8: Planning time frames Appendix 9: Transparency in costing of Task Orders Appendix 10: SD & L | 1 2 5 |
|  | Total number of pages | 45 |

# Employer’s Service Information

Contents

Part 3: Scope of Work	1

Employer’s Service Information	2

Definitions	4

Definitions of the Employers’ contract administrators	4

Service Manager (SM) - The SM shall be responsible for the overall management of the contract on behalf of the Employer	4

Definitions of the Contractors contract administrators	4

1.	Description of the service	4

1.1	Interpretation and terminology	4

1.2	Executive overview	5

1.3	Contract  objectives	5

2.	Management strategy	6

2.1	Role players	6

2.2	Allocation of work	7

3.	Description	10

3.2	Planning	12

3.3	Providing the Service by Task Order	13

3.4	Developing and pricing Task Orders	14

3.5	Performance incentives	16

3.6	Other management matters	16

4.	Health & safety, the environment and quality assurance	19

4.1	Health & safety and the environment	19

4.2	Quality assurance	19

4.3	Standards of performance	21

4.4	Liability for Defects in Plant and Materials	21

5.	Procurement	22

5.1	Subcontracting	22

6.	Working on the Employer’s property and on Affected Property	22

6.1	Access to the Employer’s SAP operational systems	22

6.2	Access and other people controls at substation sites	22

6.3	Use of Employer’s equipment	23

6.4	Working on Affected Property	23

6.5	Adverse weather	23

Appendix 1:  Classification of Services	24

1.	Preferred or strategic supplier assets and services	24

Services suitable for open tender	24

Appendix 2:  Key Performance Indicators (KPI’s):	25

1.	Principles behind KPI’s developed for this contract	25

2.	Essential elements of KPI’s	25

3.	Calculating KPI bonus and penalty payments	26

4.	Transmission Grid operational areas and their KPI’s	26

Appendix 3:  Pro Forma Task Order	27

Appendix 4:  Confidentiality Agreement	30

Appendix 5:  Task Costing Schedules	32

Appendix 7:  NCR FORM	36

Appendix 8:  PLANNING TIME FRAMES	37

APPENDIX 9: TRANSPARENCY IN COSTING OF TASK ORDERS	38

Appendix 10: SDL	40

1. Philosophy	40

# Definitions

## Definitions of the Employers’ contract administrators

# Service Manager (SM) - The SM shall be responsible for the overall management of the contract on behalf of the Employer

Site Service Manager (SSM) - The SSM shall be responsible to the Service Manager for all Task Orders issued by the Grid he represents. He shall also be the authorised Grid services manager for that Grid.

Employer’s Task Order Manager (ETOM) - A third tier responsibility is adopted for the Contract, which allows all the actions required to manage a Task Order to be carried out by the Employers representative who is responsible for the execution of the proposed work, subject to that representative carrying out the Task Order action within the delegation of his line appointment, and subject to him carrying out that action within the parameters laid down by the SSM of that Site. These representatives of the Employer, will be referred to as the Employers Task Order Manager (ETOM)

## Definitions of the Contractors contract administrators

Contractors Contract Administrator (CCA) - The Contractor shall identify to the Service Manager one of his key persons as the overall contract administrator to be known as the Contractor’s Contract Administrator (CCA).

Contractors Project Manager (CPM) - The CCA shall submit to a Grid SSM the name of a representative he proposes be appointed to carry out the actions of the Contractor stated in this contract, at that site.  Once the Grid SSM has accepted a person proposed by the CCA, that person shall be identified as the Contractor’s Project Manager (CPM).

Contractors Task Order Manager (CTOM) - Will manage Task Orders on behalf of the Contractor. This will allow all the actions required to manage a Task Order to be carried out by the Contractors representative who is responsible for the execution of the proposed work, subject to that representative carrying out the Task Order action within the delegation of his line appointment, and subject to him carrying out that action within the parameters laid down by the CPM of that Site, and the CCA. These representatives of the Contractor will be referred to as the Contractors Task Order Manager (CTOM).

# Description of the service

## Interpretation and terminology

For the purpose of interpreting this Service Information the following terminology shall apply:

Activities to be undertaken by the Contractor in performing the service are generally referred to as ‘items of work’.

For this contract, secondary Option X19 of the NEC3 Term Service Contract (April 2013) has been selected which allows for work to be instructed by Task Order.   A Task is defined as work within the service which the Service Manager may instruct the Contractor to carry out within a stated period of time.  Tasks are identified at each Grid for example, within outages, regular site maintenance, and other ad hoc work or project.  Each Task Order will contain a priced list of items of work within the Task.

Where the word ‘service’ is not italicised, it shall be given its common meaning.

The terms ‘site’ used in this Service Information means the area used by the Employer for the purpose of owning and operating the sub stations.   It must not be confused with the term Site used in other NEC contracts.  The Affected Property identified in the Contract Data for this contract is an area or facility within these sites but it is not the whole of the site.

The terms SHEQ and T&SS used in this Service Information are the capital initials for departments within the Contractor’s organisation known as Divisional SHEQ Department and Transformer and Switchgear Services respectively.

## Executive overview

The work in this contract unless stated otherwise relates to the ‘as and when’ maintenance and repair services for approximately 370 online dissolved gas analysers installed in Eskom Transmission, that is about 300 Kelman TRANSFIX and 70 TM8 Multi Gas Severon gas analysers. The contractor is required to make sure that the gas analyser are repaired and serviced as and when requested by Transmission Grid’s personnel. The details are contained in the “GA works information” in Appendix 1.

All of the service shall be instructed by means of Task Orders issued by the Employer at any time during the term of the contract (the service period) for identified work procedures and resources within each Task.  The Price for each item of work in the Task shall be taken from the Price List; however it is a requirement of this contract that Prices not included in the Price List at contract formation stage are to be assessed during the course of this contract before the Task is carried out.  The method of assessment is described elsewhere in this Service Information.

Technical, quality, and workmanship requirements for the service are described in quality control procedures (QCPs) provided by the Contractor and accepted by the Service Manager before work is carried out.

Key Performance Indicators (KPI’s) have been included in this Service Information to motivate best practice and steady innovation for improved service outputs by the Contractor.

## Contract objectives

The contract objectives for this contract include:

Maintaining and repairing of the online gas analysers on Transmission transformers and reactors.

Replace defective and obsolete equipment.

Ensure all units are functional at all times.

Transfer skills by providing training that will ensure that the Grids staff can maintain and repair the equipment after contract expiry.

The Contractor shall provide adequate resources and engineering capability to support the contract objectives.

  - Location where the service is required

The services listed in Appendix 1 may be carried by the Contractor at any of these Employer’s Transmission stations in the various Grids within the borders of South Africa as follows and any other sites owned by the employer:

Transmission Grids

North

East

North East				Apollo DC

Central					Western

Free State

Including:

Asset Management Execution

# Management strategy

## Role players

The nature of the service, the range and location of Affected Property, and the manner in which the electricity power supply industry operates make it necessary to identify several role players for this contract.

### Employer’s representatives

The Service Manager may delegate the actions of him stated in this contract that are necessary for the setting up and administration of a Task Order.

The Employer shall in conjunction with the Service Manager appoint a Site Service Manager (SSM) at each Grid where work in this contract is to be undertaken.  The SSM shall be responsible to the Service Manager for all Task Orders issued by the Grid he represents. He shall also be the authorised Grid services manager for that Grid.

A third tier responsibility is adopted for the Contract, which allows all the actions required to manage a Task Order to be carried out by the Employers representative who is responsible for the execution of the proposed work, subject to that representative carrying out the Task Order action within the delegation of his line appointment, and subject to him carrying out that action within the parameters laid down by the SSM of that Site. These representatives of the Employer, will be referred to as the Employers Task Order Manager (ETOM), The Task Orders are to be signed by the ETOM, except for the page of the Task Order which contains the Price of the Task Order, which page shall be signed by the correct delegate in terms of the Employers delegation of authority, unless this delegate is the relevant ETOM, in which case he may also sign the page of the Task Order which contains the Price of the Task Order. The ETOM may only be appointed with the consent of the relevant Grid Manager, or the relevant Production Unit Senior Manager. The SSM will however remain responsible for the overall running of the contract on that site. The contract authorization will remain as issued and the Employers Task Order Manager’s appointment is a local matter.

Duties of a general nature relating to the overall performance and administration of this contract will generally not be delegated by the Service Manager and the SSM.

### Contractor’s representatives

The Contractor shall identify to the Service Manager one of his key persons as the overall contract administrator to be known as the Contractor’s Contract Administrator (CCA).

The CCA shall submit to a Grid SSM the name of a representative he proposes be appointed to carry out the actions of the Contractor stated in this contract, at that site. Once the Grid SSM has accepted a person proposed by the CCA, that person shall be identified as the Contractor’s Project Manager (CPM).

The CCA shall also submit to the relevant SSM the names of the Contractors Representatives who will manage Task Orders on behalf of the Contractor. This will allow all the actions required to manage a Task Order to be carried out by the Contractors representative who is responsible for the execution of the proposed work, subject to that representative carrying out the Task Order action within the delegation of his line appointment, and subject to him carrying out that action within the parameters laid down by the CPM of that Site, and the CCA. These representatives of the Contractor will be referred to as the Contractors Task Order Manager (CTOM). The Task Orders are to be signed by the CTOM, except for the page of the Task Order which contains the Price of the Task Order, which page shall be signed by the correct delegate of the Contractors delegation of authority, unless this delegate is the relevant CTOM, in which case he may also sign the page of the Task Order which contains the Price of the Task Order. The CPM will however remain responsible for the overall running of the contract on that site. The Contractors task order Manager will ensure that the correctly delegated person in terms of Contractor’s Delegation of Authority T-65 standard countersigns that page of the Task Order which contains the Price of the Task Order.

### Steering committee

The Parties shall appoint representatives to act on a steering committee for this contract.  The function of the steering committee shall be to

- review the overall performance of this contract,

- perform the functions of the steering committee described elsewhere in this Service Information, and

- provide assistance and back up to persons designated by the Parties’ to perform actions on their behalf in terms of this contract.

The steering committee shall comprise the following members:

| Steering Committee membership | Role undertaken by: |
| --- | --- |
| 2 senior representatives, one from each Party | One of the Employer’s Senior General Managers and the Contractor’s Product Group Manager |
| 2 contract administrators, one from each Party | The Service Manager and the CCA |
| 2 financial representatives, one from each Party | Appointed by the senior representatives |
| 2 contract negotiators, one from each Party | Appointed by the senior representatives |

At the start date of the Contract, the Steercom appointees are as follows:

- Employers Senior Representative

- Contractors Senior Representative

- Employers Financial Representative

- Contractors Financial Representative Employers Negotiator

- Contractors Negotiator

- Employers Service Manager

- Contractors Administrator

Should either party decide to change the individuals appointed to these positions during the duration of the Contract, such changes will be presented to the Steering Committee, and once agreed at the Steering Committee meeting, such changes will be recorded in the relevant decision log.

Each senior representative may second others to the committee for a specific need with the acceptance of the other senior representative.

One of the senior representatives shall act as chairman of the steering committee for 12 months, passing the function to the other senior representative if required. The secretarial function shall be carried out by the contract administrator from the same Party as the Chairman and will change in phase with the change of Chairman.

Each Party shall bear its own costs arising from the role and functions of the steering committee.

### The Strategic Team

The two senior representatives on the steering committee shall jointly perform the function of the strategic team described elsewhere in this contract.

### Manufacturer

For the purpose of this contract Manufacturer shall mean an organisation

that supplied the original or presently installed power distribution facility (the Affected Property), or

- which is capable of providing the relevant services or equipment similar to and capable of equal or better performance than that provided by the original supplier or as presently installed.

## Allocation of work

### Using the Contractor as a strategic or preferred supplier

The Contractor shall have the obligation or right to carry out all work listed in Appendix 1.

In this case a Manufacturer may be a Subcontractor and in terms of the subcontract which the Contractor has with the Manufacturer, the Manufacturer shall report directly to the Contractor with recommendations and reporting done via the Contractor’s Engineering Department.

The Contractor shall implement the necessary subcontract with the Manufacturer, which shall include provisions for skills and technology transfer to the Contractor and the Employer.

However the Employer may still contract directly with a Manufacturer of his choice for engineering support and quality assurance services associated with such work.

Notwithstanding the services listed in Appendix 1, this obligation and right which the Contractor has does not extend to services carried out in terms of a contract between the Employer and others existing at the Contract Date.  In this case, the services may continue to be provided by others until the end of the current contract with them, after which time such services shall be provided by the Contractor in terms of this contract.  If the service is to continue to be provided by others, the Employer shall justify this in terms of Clause 2.2.2 below.

### Employer’s right to contract with others

The Employer may, due to special circumstances including but not limited to when the Employer considers that the Contractor does not have the capability to adequately perform the work

contract directly with a Manufacturer stipulating that the Manufacturer employs the Contractor as a domestic subcontractor,

require that the Contractor employs a Manufacturer as a Subcontractor for work in this contract, or

contract directly with a Manufacturer

for some of the services listed in Appendix 1.

The ETOM shall prepare a detailed justification of such special circumstances and why it is in the Employer’s best interests to undertake the recommended actions, and after approval of his line authority, this justification will be forwarded to the Employer’s relevant Senior General Manager for consideration. If the Employer’ Senior General Manager accepts the justification, he will engage the Contractor’s Chief Executive Officer, and after consideration and agreement at this level, a decision will be given to the ETOM and CTOM in writing. This decision will be implemented by the ETOM and CTOM. Until this decision is given, no action shall be taken to breach any clause within this contract.

## Meetings and reporting

### Steering committee

The current chairman of the steering committee shall arrange meetings of the steering committee to take place in January and June of each year, or more frequently as either of the senior representatives may decide.  The chairman provides an agenda with his notification of the meeting and also arranges a suitable venue, other facilities and refreshments.

A quorum for the meeting shall be the two senior representatives, the two contract administrators and the two financial representatives or their delegates.  Failure to reach a quorum will require that the meeting be cancelled and re arranged for a new date.

At each meeting those who attend co-operate in reviewing as a minimum:

Date:		Insert Date of Meeting

Division:	Insert Division here

Serial No.:	XX/YYYY (Meeting Number/Year)

Chairperson:	Insert Name of Chairperson

Time:		Insert Starting Time of Meeting 00H00

Venue:	 	Insert Venue of Meeting

Purpose:	Review this contract between Transmission and the Contractor

NOTE: Please change blue text into black and remove the text where explanation is no longer required.

| # Description | Time Allocated (Indicate allocated time for each item e.g. 09h00 – 09h10) | Responsibility (Indicate the person responsible for leading the discussion or presenting the item) |
| --- | --- | --- |
| - Welcome, Opening and Apologies |  | Chairperson |
| - Safety and Emergency Evacuation Procedure |  | Chairperson |
| - Adoption of Agenda & Declaration of Interest |  | Chairperson |
| - Address by Senior Representatives |  | Senior Representatives |
| - Acceptance of previous minutes and review of action items |  | Chairperson |
| - Issues with the interpretation and resolution of NEC3 Term Service Contracts terms and conditions |  | Service Mgr / CCA |
| - KPI’s, Performance and Bonus/Penalty levels of the Contractor |  | CCA |
| - Overview KPI’s, establish any changes required for next year and sign off new KPI targets. |  | CCA |
| - Report on re-valued and adjusted income statements and balance sheets |  | Contractors Financial Rep |
| - Employer’s year end projection |  | Employers Financial Rep |
| - Year-end view of incentives to comply with AC 130 |  | Contractors Financial Rep |
| - Overview of Employer’s forward planning and Contractor’s capacity planning & scheduling |  | CCA |
| - Progress on review of skills development |  | CCA |
| - Review of Dispute log |  | CCA |
| - Review of NCR log |  | CCA |
| - Non adherence to this contract. |  | Service Mgr / CCA |
| - Determine audit programme and review audit results |  | Service Manager |
| - Review of contract training needs |  | Service Mgr / CCA |
| - Confirmation of pricing policy |  | Contractors Financial Rep |
| - Decision Log |  | Senior Reps |
| - General |  | Chairperson |
| Closure |  |  |

The contract administrator (Service Manager or CCA) whose turn it is to act as committee secretary shall issue minutes of the steering committee within 14 working days of the meeting after circulation to each member for comment and after the chairman has approved them.

Any decisions taken at a steering committee meeting shall also be recorded in a log for recording purposes.  The minutes and the log shall also record the committee member delegated with the responsibility for ensuring that the decision is implemented, and by what date.

The Service Manager shall note which decisions have a connection with actions required by the contract and who, in accordance with this contract, will take them.  He shall give a copy of his record to the Contractor.  Each such decision shall be implemented separately in accordance with the contract and its associated due date.

The senior representatives shall report on the results of the steering committee meetings to their respective executive managers.

The current chairperson may, himself or upon acceptance of a request from a member

- require other employees of either Party to attend all or part of any meeting, and

- consult with and seek information which the committee may require from any employee of either Party.

The committee shall conduct a self-assessment of its performance and the effectiveness of the contract at least before end of contract.

### Annual presentation for feedback of results and clarification of contract

A presentation shall be made by the steering committee’s senior representatives in June of each year during the service period.

The presentation shall

review the Grids performance results including contractors performance against KPI’s;

recognise the work team demonstrating the best performance in terms of this contract;

provide clarification where needed through a question and answer session, and

generally strive to maintain mutual trust and cooperation between all who attend towards achieving the Employer’s objectives stated in this Service Information.

The Service Manager and the CCA shall jointly

manage the provision of a venue and all function arrangements;

notify persons required to attend using a reasonable period of notice, and of the arrangements for the function;

compile and circulate an agenda determined by the steering committee which shall also contain sufficient time for an open question and answer session;

circulate an attendance register, ensuring that all those who attend duly record their attendance;

prepare a budget for the event on the basis of all costs being shared equally by the Parties and paid separately from this contract, and

submit their respective Party’s costs to that Party’s senior representative for allocation and payment as necessary.

Attendees at the presentation shall include

members of the steering committee,

the Employer’s production unit senior managers, Grid managers, project integration managers, maintenance managers, SSM’s and their delegates, and electrical engineering representatives,

the Contractor’s service managers, project managers / leaders, site representatives, and

other key stakeholders.

### Grid site meetings

Each SSM shall arrange a monthly meeting at his Grid at a time to suit attendance by both himself and the CPM and for every quarterly per year throughout the service period

Either the SSM or the CPM may invite others to attend the meeting as necessary, but may not delegate their attendance to others.   If the SSM fails to arrange the meeting by the 15th of any month, the CPM may arrange the meeting and both the SSM and the CPM shall attend the meeting so arranged.

In the meeting the SSM and the CPM shall

- review the previous month’s actions and responsibilities in terms of the contract, decide what corrective actions are to be taken (if any), and by whom the contract requires them to be taken and by what time;

- review, agree and sign a summary listing of work carried out during the month under review which shall contain as a minimum

a schedule of any major incidents or unplanned work,

the amount due to the Contractor,

any substantial disagreements between the SSM and  CPM and any disputes notified in terms of the contract,

the CPM’s general comments on the work done during the month under review,

the SSM’s general comments on the work done during the month under review,

any notable achievements,

any contractual or commercial issues,

KPI results for plant, cost, quality, safety, and reporting correctly recorded and signed as such by the applicable Employer’s maintenance manager, Contractor’s service manager, the SSM and CPM;

- review future work and add items to the Accepted Plan for any future non routine work;

- check and ensure that amounts recorded in SAP at the Grids are sufficient for future needs;

- review relationships between representatives of both Parties and attempt to address any adverse issues through the action plan; and

- review any opportunities that can be explored to capitalise on value arising from this contract.

The SSM shall prepare a monthly report in the form of minutes of the above referenced meeting with the KPI schedule attached, ensure that both he and the CPM have agreed and signed the minutes before submitting copies to the Grid manager, the senior representatives on the steering committee, the Service Manager and the CCA.

The Grid site meeting held in March of each year during the service period shall review effectiveness of the station’s existing KPI’s and whether they are appropriate for the following year.  Following this review, under mandate by the steering committee, changes to KPI’s may be negotiated based on new targets and new requirements within the overall set of KPI’s in this contract.

### Employer’s Technical plan meetings

The Contractor’s Representatives will attend the Employer’s Technical Plan meetings at Grid level. The Service Manager will forward the date of any Technical Plan meetings to the CCA, as soon as such schedules are issued, and the CCA will forward the names of the Contractor’s representatives who will attend the meetings, to the Service Manager

## Planning

### Planning process

The planning process shall:

- Be structured to enable the Parties to operate efficiently within the requirements of the Employer’s production plan;

- Include a full scope of work development and spare part needs identification / verification process;

- Include a risk management process to ensure scope integrity is in line with the age and condition of the Affected Property;

- Be carried out jointly by the Parties under the overall co-ordination of the Service Manager, who shall make the final decision.

An Employer’s outage plan optimisation workshop shall be held jointly with the Contractor on at least a twice yearly basis as notified to the Contractor by the Service Manager.  The workshop shall review and optimise future outage plans.  Before each workshop the Contractor shall provide to the Service Manager detailed resource schedules showing how the Contractor’s resources are forecast to be applied to work he is contracted to undertake and specifically resources applied to all major work being undertaken for the Employer.  The Service Manager shall make the final decision on the scheduling of outages.

The Employer’s outage plan shall be optimized and agreed in the workshop and revised resource schedules (if any) shall be submitted by the Contractor to the Service Manager within one week of the end of the workshop.

### Planning time frames

The Service Manager shall issue to the Contractor on a yearly basis the Employer’s 5 year outage and\or maintenance planning schedule duly updated by the Employer and showing for each proposed outage a high level scope of work with estimated outage duration.

The time schedules for planning for outages is included in Appendix 8

It is recorded that the Parties have agreed to be flexible in amending work schedules when the need arises (at no cost to the Employer) in a manner such that a compensation event is not notified by either the Service Manager or the Contractor.

### Workshop Planning

The Contractor shall implement an efficient workshop scheduling system to meet the Employer’s requirements.

## Providing the Service by Task Order

### Requirements for each Task Order

Secondary Option X19 is part of the conditions of contract and states the procedure for developing and managing a Task Order.  Persons involved in the administration of this contract shall read Option X19 before preparing any Task Order.  A Task Order format suitable for this contract is provided in Appendix 3.

A Task Order is required for all work carried out under or in connection with this contract.

### Contractor unable to supply resources

If the Contractor becomes unable to supply the resources required to complete a Task Order by the Task Completion Date, he shall immediately notify the matter to the SSM as an early warning.  The notification shall include recommendations as to how the work can be completed by the Task Completion Date.

### Emergency work

The Service Manager may at any time instruct the Contractor orally, followed up in writing, to carry out work which is of an emergency nature, including work which the Contractor may require a subcontractor to undertake.   The Contractor puts the work into effect.

The Service Manager shall issue a Task Order and Emergency Declaration for this work making reference to this emergency procedure and the Eskom Supply and Procurement Management Procedure 32-1034 before the end of the next business day.

Where there is emergency work, whether it is a task order or compensation event driven emergency, the following process to be managed by the ETOM and CTOM within 24 hours

- An identified team is to agree to a timetable for finalising the final SOW, PQP, Programme

- This team is also to be immediately tasked to ensure a preliminary SOW, PQP, Programme and Task Order are put in place to allow work to start immediately, and to continue for long enough to get the final SOW, PQP, Programme and Task Order in place.

In the case of a sudden equipment failure, the Contractor shall immediately conduct a preliminary investigation including a damage report with recommendations for repair and submit it to the Service Manager. Ensure compliance to the procurement procedure 32-1034.

### Task Order technical report

Within 42 days of Task Completion, the Contractor shall unless advised otherwise by the SSM submit to the SSM in accordance with his requirements, a detailed technical report for every completed Task Order.  This report shall include all technical information and data produced for the Task Order and a technical evaluation of findings from the work done with recommendations for future action by the Parties and other information as the ETOM may require.

## Developing and pricing Task Orders

### Assessment of additional Prices for service items not included in the Price List

The Prices for each item of work within the service shall be those on the Price List.  Clause X19.3 requires that items of work within the service which are not on the Price List are assessed as for compensation events.

Most of the items of work within the service required by this contract will not have been priced before the starting date. As a result, additional Prices shall be developed as an express requirement of this contract in such a manner that they can be included in the Price List once agreed by the Parties.

### Principles behind pricing strategy

These principles are provided to give clarity and consistency, but shall not detract from any Grid or Grid’s flexibility, historical approach, and application of initiative or management discretion.

The Service Manager shall ensure that the Task ‘Work Breakdown Structure, Resource and Time’ schedules are in place and signed off for all outages. Templates for these schedules are contained in Appendix 5.  Priorities for the development of these Task schedules shall be based on the Employer’s outage programme.

- The SSM and the CPM shall co-ordinate the appointment of a team to develop the Task schedules for each outage.  (Specialists could also be considered).

- All non-outage related Tasks and compensation events for outage or non-outage Tasks will be developed independently by the Contractor on the same principles, and then transparency will take place at the SSM level by disclosure of the items of work, the hours and the rates used to develop that Task schedule.

- Outage related Tasks will be set at the level of modules / major components or systems, and will have a lower level of activities, broken into a work breakdown structure of the lowest possible level of resource input, which will have the allocated hours attached to each resource per activity.

For the Contractors Projects Department

  - Develop the specific Scope of Work for each system / module on the outage;

  - Create a Work Breakdown Structure from the Scope of Work which is at least one level more detailed than modules

  - Create each activity/operation from the WBS;

  - Create a MS Projects Bar Chart showing at least each activity/operation and applicable resource and duration

  - Negotiate the hours and resources required, for each activity/operation as per the Bar chart

  - Carry out resource levelling per module, to determine the amount of resources required per module

  - Populate Task Schedules as per Appendix 5 with resources and hours at 1 level lower than a module, ie Strip, Refurbish, Reassemble

  - The ETOM signs off the Task schedules as per Appendix 5, but they will not be considered to be approved schedules at this stage;

  - The ETOM issues the Task Order Request to the Contractor, with all specific requirements stipulated, and with the signed Task schedule attached;

  - The Contractor now applies the approved rates to the Task Schedule as per Appendix 5;

  - The Contractor then prepares the Task Order Quotation based on the Task Order Request and relevant Task schedules, now adding the Plant & Material, Subcontractors, and other non-capacity items into the Task Order Quotation.

  - The Contractor submits the Task Order Quotation to the ETOM, signed by the CTOM;

  - The Task Order Quotation is to be reviewed by the ETOM, and queries resolved with the Contractor’s CTOM;

  - The Task Order Quotation is signed by the ETOM indicating acceptance, and is issued, with a SAP 45 Order, to the CTOM as an approved, fixed price, Task Order

  - With the Task Order thus approved, the priced Task Order can then be added to the TSC Part 2 Task item library as an approved Task, and released by the Contractor for the execution of the work.

For the Contractors Works Department

  - The Contractor will develop the specific Scope of Work for each system / module / Compensation event

  - The Contractor will create a Work Breakdown Structure from the SOW which is at the lowest level of activity at which the rates can be applied

  - The Contractor will populate Task Schedules as per Appendix 8 with all activities in the WBS

  - The Contractor will allocate the hours and resources required for each activity/operation in the Task Schedule

  - The Contractor will sign off the Task schedules as per Appendix 8, but they will not be considered to be approved schedules at this stage;

  - The Contractor now applies the approved rates to the Task Schedule as per App 8 at WBS level;

  - The Contractor then prepares the Task Order Quotation / compensation event based on the Task Order Request and relevant  Task schedules, now adding the Plant & Material, Subcontractors, and other non-capacity items into the Task Order Quotation

  - The Contractor submits the Task Order Quotation / compensation event to the ETOM, signed by the CTOM;

  - The Task Order Quotation /compensation event is to be reviewed by the ETOM, and queries resolved with the Contractor’s CTOM and if required by the ETOM, then transparency will take place with the SSM by disclosure of the activities, the hours and the rates used to develop that priced Task;

  - The Task Order Quotation / compensation event is signed by the SSM indicating acceptance, and is issued, with a SAP 45 Order / SAP 45 Order modification, to the CTOM as an approved, fixed price, Task Order / compensation event

With the Task Order thus approved, the priced Task Order can then be added to the TSC Part 2 Task item library as approved an Task, and released by the Contractor for the execution of the work.

### Development of the Price List

The Price List shall be developed in two sections

Section 1:	Rates developed for use in the Task schedules.

The rates used in the Task Orders are reflected in the price list.

Section 2:-	Categories of work and associated resources

These are:

- Outage related Tasks, and refurbishment of major components outside outages related Tasks, based on PQP’s,

- Prices for independent Tasks, non-outage Tasks on minor components, and compensation events for outage or non-outage Tasks.

A library of the Task Orders, showing the final fixed Price for the Task Orders, as well as the rates and resources used to arrive at the Price, shall be made available in the offices of the Contractor, and a copy of the final fixed Price Task Orders, shall be made available by the Contractor in the Employers offices, at the relevant Grid ETOM’s office.

A summary of the Price List, which will be updated monthly, will be developed by the Contractor and retained in the Contractor’s library for access as stated above.

## Performance incentives

### Performance measurement

The Contractor’s performance shall be measured against the Key Performance Indicators (KPI’s and gate keepers) listed in Appendix 2 at each Grid.  The KPI’s may be adjusted at each anniversary of this contract in accordance with directives from the steering committee.

As required in clause 3.1.2 the SSM and CPM shall record and sign off the KPI’s and gate keepers achieved at each Grid each month.  As required by clause 2.2.4 the steering committee reviews every six months the year to date results of the performance of the Affected Property and of the Contractor.

In July of each year the Contractor shall prepare his statements based on the incentive scheme and the annual KPI’s achieved using the KPI’s achieved and recorded each month at the Grids.  The Contractor shall determine the proportion of the incentive fee applicable, according to the performance criteria stated in Appendix 2 and in accordance with the process below.

The Contractor KPI targets listed in Appendix 2 shall be set for duration of contract by the steering committee.  Each Grid shall compile their compact from the KPI’s and Gatekeepers as per Annexure 2 before the 31 July of each year.

At each Grid, at the end of each financial year the weighted composite average of the KPI results is calculated on a 5 point scale.  The Annual Score is obtained by calculating a weighted average of the monthly score.  The monthly weight distribution is indicated in table B. This score is applied to that Grid’s annual capacity turnover of the Contractor to obtain a bonus or penalty payable to or by the Contractor.  The Contractor’s capacity turnover includes capacity applied to others where the Employer is the end user.  The Percentage Bonus or Penalty is calculated as per Table A

The KPI’s form the Basis for calculating the Performance score on a 5 point scale and have a total weight adding to 100%.  The gatekeepers will only have an effect of reducing the overall score by a maximum of 20% in total, if the gatekeeper performance is unacceptable

| Floor | Kick-in | Target | Stretch | Ceiling |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| - 4% | - 1.5% | 0% | 1.5% | 4.0% |

Table A

## Other management matters

### The Parties use of Intellectual Property

Ownership of design work undertaken by the Contractor of a proprietary nature and paid for by the Employer shall vest in both Parties.  In order to comply with this requirement the Contractor obtains approval from others where necessary.

The Employer shall have the right to use such material drawings and data as he sees fit.

### Records and information generally

Either Party may request the other to provide free of charge non third party technical information and drawings, such as operational and maintenance histories, operating advisory information, quality assurance and control records, copies of job reports, drawings and sketches of modifications or repair procedures, technical procedures or any other matter of like kind for work being done under this contract.

Both Parties shall allow access to their facilities as requested by the other Party within the control procedures of both organisations.

All records and information shall be retained for the duration of this contract.

At the end of the service period or earlier termination of this contract the Contractor shall make available to the Employer all records and information relating to the work carried out under this contract at no extra cost to the Employer.  The Contractor may not retain copies of any third party records and drawings of a proprietary nature.  However, if the service period is extended, or a new contract between the Parties comes into existence at the end of the service period which effectively ensures continuity of the Contractor Providing the Service, the records and information shall be retained by the Contractor and dealt with in terms of the new contract.

No records and information exchanged shall be divulged to others without the prior consent in writing of both Parties during this contract.

### Confidentiality

The Parties shall keep confidential for a period of 5 years from the end of the service period or earlier termination of this contract, any confidential or proprietary information made available by either of them to the other in terms of a requirement of this contract, except when a Party may be required by law to disclose it or if the Party providing the information has given its prior consent to the other Party.

The Contractor’s Confidentiality Agreement included in Appendix 4 shall be completed and signed by all persons not directly employed by the Contractor and who are required to be involved in setting new Prices using information made available by the Contractor from his internal records.  :

At the start of each meeting where such information is to be disclosed, the chairman (whether employed by the Employer or the Contractor) shall:

- emphasise the importance of confidentiality to both Parties including creating an awareness of how unintended breaches of the Confidentiality Agreement can arise,

- ask those attending if they have a conflict of interest regarding the subject matter of the meeting and if so to please leave the meeting,

- enquire if all those present have signed the Confidentiality Agreement, and request those who have not to sign it before the meeting continues, and

- ensure that his comments and actions regarding such confidentiality are recorded in the minutes of the meeting.

### Non Conformance Reports

To ensure that there is constant improvement in providing the Service, the Employer shall issue Non Conformance reports to the Contractor when the service is provided at a level which is lower than the Employer’s expectation. The following process must be adhered to when Employer NCR’s are issued

#### All NCR must be captured on SAP Quality Issue Management (QIM)

#### The ETOM shall forward a NCR (Appendix 7) for any non-conformance to the relevant CTOM.  The CTOM shall also forward an electronic copy to the CPM and to the Contractor’s Divisional Quality Manager

#### The unique NCR number and other required information must be noted on the Service Agreement NCR log by the Contractor’s Divisional Quality Manager

#### The CTOM is responsible to raise an Internal NCR in the Contractors NCR system, referencing the Employer’s NCR number and other required information on the Contractors NCR, and to issue this NCR, with a copy of the Employer’s NCR attached, to the responsible Contractor’s SHEQ /T&SS department/ section/ individual for Correction and Corrective action.

#### The CTOM is required to discuss and ensure agreement with the relevant department/ section/ individual that Immediate Corrective action will be implemented within seven days of issue of the NCR, or sooner if the issue requires urgent attention.  An agreed closeout date for Corrective action implementation must be negotiated between the CPM and NCR receiver ensuring the agreed date is documented on the NCR prior to signing receipt of the NCR

#### The CTOM shall inform the ETOM of the closeout dates of the Employer’s NCR, based on the close out negotiated with the Contractor’s NCR receiver

#### The original Contractor’s NCR must be kept by the receiver to record Corrective and Preventative actions and the CPM is to keep a copy inside the Site Office in an applicable file for this purpose, ensuring the blue copy is forwarded to the SHEQ department for capture onto the NCR dBase

#### The CPM shall track the response date against the agreed close out date, recording all progressive information during this process on the Service Agreement NCR log.

#### The CPM shall keep copies of communications with the ETOM, as well as communications with the relevant department/ section/ individual responsible for closing out the Contractor’s NCR.

#### The Contractor’s NCR is to be closed out by the relevant department/ section/ individual, and as soon as it is closed out, but not later than the agreed closeout date, a copy of the formally closed out NCR is to be forwarded to the CPM from where it originated.

#### Any discussions, communications, minutes of meetings etc., during the close out process, must be copied to the CPM immediately, and not at the time of NCR closeout, so that he may be aware of the close out processes.

#### The CPM will discuss the closed out NCR with the ETOM, and if necessary, this will be done with the attendance of the person who was responsible for the close out of the NCR.  If the NCR close out is not acceptable to the ETOM who raised the NCR, then the Contractor’s NCR must be re-opened, a new agreed close out date negotiated, and the further actions required by the Employer’s representative should be actioned accordingly.

#### When the Employer accepts the close out of the Contractor’s NCR, the CPM must then complete all required areas in the original Employer’s NCR, and submit it via document transmittal to the Employer’s representative not later than the agreed date.

### Audits

The Service Manager may in accordance with a predetermined programme decided by the steering committee carry out audits on the Contractor’s processes supporting any work done or to be done in terms of this contract, as well as on the work actually carried out.  The Service Manager shall give the Contractor notice of his intention to perform an audit in order that the Contractor may provide a representative observer.

Depending on the findings of such an audit, the Service Manager may notify the Contractor of an NCR.  The Contractor shall notify the Service Manager of the actions he intends to take to clear the NCR, and by when he will have taken them.  The Contractor maintains a database system to record and track all NCR’s raised and reports these to the SSM monthly.

### Standing time claims of actual cost incurred by the contractor relating to moving outages, where less than two weeks’ notice is given

- Contractor to compile standing time claim with actual supporting documents.

- This will be presented to the respective Senior Manager - Projects, who will review and sign off the file within 3 working days

- Once completed, the file is to be returned to RE for presentation

- Will then be presented to the Senior Representative Transmission by Senior the Representative Rotek.

- All standing time claims will be paid by Transmission at contract rates

- For non-Capacity this will be at the actual cost

- For Capacity, it will be at the cost less the agreed Mark-up %

# Health & safety, the environment and quality assurance

## Health & safety and the environment

Each location where the service is carried out (see paragraph 1.4) has a health and safety specification or procedure and safety risk management requirements relevant to that location (the Employer’s site Health and Safety Plan). The CPM shall ensure that he is a registered recipient of such documentation at each location where work is carried out, and is always in possession of the current version of such documentation before any work in this contract is undertaken at that location.  The SSM shall inform the CCA and CPM of new revisions when they are published.

The Contractor shall comply with the requirements imposed on a contractor / supplier stated in the current version of such documentation at each location where work in this contract is carried out and shall identify to the relevant SSM the name of the Contractor’s person responsible for monitoring such compliance.

The Contractor shall ensure that he is in possession of documentation relevant to protection of the environment at each location where work in this contract is carried out and shall comply with the requirements imposed on a contractor / supplier stated therein.

The Contractor shall keep records which demonstrate compliance with all health, safety and environmental requirements whether statutory or otherwise and shall allow the SM or relevant SSM to inspect them at any time within working hours.

## Quality assurance

### Assuring availability of persons with the necessary skills

The Contractor shall

- be accredited as ISO 9001 compliant for both quality and environmental management and shall maintain this accreditation throughout the service period.  The Contractor shall report immediately any change in this status to the Service Manager, such report containing details of steps to be taken and by when they will be taken to restore the accreditation status.

- provide the service in accordance with the latest revision of the Employer’s document, “240-105658000 (QM 58) Supplier Quality Management Specification.

- implement a skills quality management system designed to ensure the provision of adequately skilled, experienced and qualified persons, whether employed on a permanent or temporary basis, to carry out work in this contract.

The skills quality management system shall be designed to provide at any time at least the following particulars:

- Detailed skills, experience and qualification documentation for each staff member employed or to be employed for work in this contract.

- Details about on-going training attended and accreditation procedures complied with for existing as well as new employees.

- Listings of specialist staff by category of skill, for example turbine artisans with specific skills, experience and qualification requirements.

The Contractor allows the Service Manager to inspect at any time within working hours the details and records within the skills quality management system.

### Skills allocated to each Task

Before starting work on a Task the Contractor shall provide to the Service Manager for their acceptance outline details of persons to be employed for work in the Task, to the extent that the Service Manager has requested in the Task Order.

The Contractor shall not commence work in a Task Order until such persons to be employed have been accepted by the Service Manager.   The Service Manager may not accept persons who are in their opinion not adequately qualified or experienced to undertake the work in the Task.

The Contractor shall provide for the Service Manager’s acceptance similar details for new or replacement persons employed after work in the Task Order has commenced.

Notwithstanding this requirement, the Service Manager or SSM may at any time instruct the Contractor to provide the full CV of a person to be employed if they consider the outline details to be insufficient.

For the purpose of this contract, persons employed for work in the Task Order shall include any person, whether under contract of employment to the Contractor, a Subcontractor or others.

### Specifications for Plant and Materials & workmanship

The Contractor’s business management systems shall include a corporate Quality Plan designed to ensure quality assurance and control of the work carried out for this contract, including work carried out by subcontractors.   The Contractor shall submit the Quality Plan to the Service Manager for his acceptance.

Any further quality assurance requirements and associated control documentation (the Process Quality Plan) specific to a Task Order shall be provided by the Contractor to the SSM for his acceptance before work commences on the Task Order.

Plant and Materials and workmanship specifications referred to in the Contractor’s PQP’s are also part of the Contractor’s Service Information.

The Process Quality Plan (PQP) for each Task Order shall demonstrate that the Contractor has or will make as a minimum provision for:

- Adequate engineering support.

- Technical and quality input from the Contractor in sufficient detail specific to the Affected Property and Equipment used.

- Reference to all applicable procedures which procedures shall be available at the site of the work,

- Hold and witness points and provision for other appropriate sign off.

The PQP shall be completed and updated during the course of the work to demonstrate that all hold and witness points have been respected.

For work not described in PQP’s, the Contractor develops and submits a PQP to the SSM for acceptance before work related to the PQP commences.

### Educational presentations and workshops about this contract

In order to

- establish and maintain the necessary contract administration skills, by creating an awareness of the existence and contents of the contract and its intentions,

- foster and sustain the obligation to act in a spirit of mutual trust and cooperation required by this contract, and

- identify and deal with non-adherence to the contract by either party and their representatives,

overall contract presentations shall be implemented jointly by the Parties throughout the service period as agreed jointly by the Parties, and failing agreement, as determined by the Service Manager

## Standards of performance

All work carried out by the Contractor under or in connection with this contract shall make use of competent and professional knowledge that conforms to internationally accepted standards and practices prevailing in the power industry at the time of completion.

Plant and Materials supplied by the Contractor shall be new, free of defects of any kind, and fit for the purpose to which they are intended to be used in the Affected Property.

After the service has been performed the Affected Property shall operate in accordance with Manufacturer’s specifications and operating requirements to the Employer’s satisfaction, having regard for the age of the Affected Property.

## Liability for Defects in Plant and Materials

The Contractor’s 12 month liability period for Defects that may arise with regard to workmanship in Plant and Materials manufactured repaired or refurbished by the Contractor and not put to their intended use at the time they are supplied, but placed into the Employer’s storage shall be applied as follows:

A 36 month “application window” including a 12 month “active window” shall apply subject to the following conditions, as depicted in the sketch below

Total “application” window, Task Order Completion plus 36 months

End of “application” window

Scenario 1; No storage

Scenario 2; 6 months storage

Scenario 3: 24 months storage

Active window

Active window

Active window

6

12

18

24

30

36

- The period starts at Completion of the Task Order under which the work was carried out on the Plant and Materials.

- The maximum “application window” is 36 months from Completion of the Task Order.

- The maximum storage period by the Employer is 24 months.

- The maximum “active window” period (liability for correction of Defects) is 12 months.

- Storage is subject to storage management procedures agreed beforehand by the Employer and the Contractor being applied throughout the storage period.

- The Contractor shall be contracted to ensure correct storage conditions.

- The Employer shall state the storage period within his Task Order, and the Contractor will specify the storage conditions and cost in quotation for the Task.

- Incidents compromising the integrity of the Plant & Materials whilst it is in the Employer’s care may nullify the Contractor’s liability.

- The Contractor’s liability will lapse should the correct storage process and procedures not be followed by the Employer or his agents (except the Contractor).

Should the situation change, and it is required to extend or shorten the storage period, this situation shall be notified as a compensation event, following an early warning notification from the Service Manager.

If the Employer requires a storage period, greater than 24 months, pre conditions for the long term storage and management of the Plant and Materials shall be prepared jointly by the Service Manager and the Contractor.  The detailed description of the work which is included in the relevant Task Order shall also include a description of the work required on the Plant and Materials to meet these conditions.  The 12 month “active window” period for correction of Defects shall commence at the end of the extended storage period, on commissioning of the component. Employer to ensure compliance to storage procedure #240-91180732.

# Procurement

## Subcontracting

Where in the opinion of the Service Manager the Contractor does not have the capacity or capability to supply any part of the service using the Contractor’s own resources, the Employer shall not be under an obligation to use the Contractor for that part of the service and may enter into a separate contract with others for that part of the service. Otherwise if the Service Manager is prepared to permit the Contractor to subcontract such part of the service, after the Service Manager has accepted the proposed Subcontractor, the amount due to the Contractor for the subcontracted work is the amount which the Subcontractor invoices to the Contractor (subject to the requirements of core clause 52.1) plus the subcontracted fee percentage specified in Part 1 of this contract.

Before commencing any work under a subcontract, the Contractor shall ensure that the Subcontractor is adequately qualified to complete the work and has in place the necessary quality assurance and control procedures which this contract requires.

# Working on the Employer’s property and on Affected Property

## Access to the Employer’s SAP operational systems

The Service Manager shall on request from the Contractor arrange for the Employer to provide such access to the Employer’s SAP system as necessary for the recording of reports and other matter which the Employer requires to be communicated and recorded in SAP.

The Employer may provide the Contractor limited access to the Employer’s maintenance management systems such as those recorded in SAP.

In order to have access to the Employer’s SAP system the Contractor shall comply with the Employer’s standards titled:

“Logon and Authentication”

“Third Party Security”

## Access and other people controls at substation sites

The Contractor complies with the access and controls procedures issued by each Grid site where work in this contract is carried out.  The Contractor shall obtain copies of such requirements from the SSM at each Grid site.  The contents of such documents applicable at the Contract Date are deemed to be part of this Service Information.

The Service Manager, SSM’s and any other employee or agent of the Employer shall comply with the Contractor’s access and control procedures at places under the Contractor’s ownership or control.

## Use of Employer’s equipment

The use of the Employer’s equipment is subject to the terms and conditions applicable at each Transmission site, and also subject to statutory requirements. The contents of such Employer’s terms and conditions shall be treated as though they are part of this Service Information subject to this Service Information taking precedence where there is ambiguity or inconsistency between the Employer’s terms and conditions and this Service Information.

## Working on Affected Property

All items of Affected Property shall be inspected, repaired and rebuilt in accordance with the specific Task Order requirements.

## Adverse weather

During the maintenance and repair of transformers the Contractor shall take particular care regarding the ingress of moisture by ensuring that it does not exceed norms stated by the Manufacturer or recommended by good engineering practice.   The Contractor shall show on each Task Order programme submitted to the Service Manager for acceptance time risk allowances he has made for possible delays to such maintenance and repair work appropriate to the timing of the work and the environment within which the transformer is located.

If delays are caused to the Contractor in excess of the time risk allowances shown on the Contractor’s accepted Task Order programme, the effect of the additional time to the extent that it may affect planned Completion shown on the Contractor’s accepted Task Order programme shall be treated as a compensation event.

# Appendix 1: woRK INFORMATION

# Appendix 1:

Works Information

As and When Required Maintenance Scope of Work for Online Dissolved Gas Analysers

| 1 | Description of the Works |
| --- | --- |
| 2 | Scope of Work to be performed by the Contractor for the Works |

INDEX

- DESCRIPTION OF THE WORKS

- SCOPE OF WORK TO BE PERFORMED BY THE CONTRACTOR FOR THE WORKS

  - GE Energy Kelman TRANFIX

  - Siemens/Qualitrol TM8 Multi Gas Serveron

- QUALITY ASSURANCE AND QUALITY CONTROL

  - Quality Assurance

  - Quality Control

- ACCOMODATION AND TRAVEL

- LABOUR

- LETTER OF AUTHORIZATION

- DESCRIPTION OF THE WORKS

The works includes ‘as and when’ maintenance and repair services for approximately 370 online dissolved gas analysers installed in Eskom Transmission, that is about 300 Kelman TRANSFIX and 70 TM8 Multi Gas Severon gas analysers. The contractor is required to make sure that the gas analyser are repaired and serviced as and when requested by Transmission Grid’s personnel.

- SCOPE OF WORK TO BE PERFORMED BY THE CONTRACTOR FOR THE WORKS

The contractor is required to perform the following scope of work per gas analysers but not limited to.

  - GE Energy Kelman TRANFIX

Firstly, the Contractor shall bring the gas analyser into a working condition from its current state and provide guarantees for the work done. Secondly, as per request from Eskom in a given time perform one or a combination of the following items, which will be deemed necessary for the correct operation of the gas analyser.

- Onsite monitor calibration,

- Gas analyser firmware and software upgrades,

- Replacement or refurbishment of PGA module,

- Replacement or refurbishment of the power supply unit,

- Replacement or refurbishment the cooler unit,

- Visual inspection,

- Perform vacuum test, oil flow test, noise test and functional test,

- Verification of the analyser measurements,

- Air filter cleaning,

- Replacement or refurbishment of equipment responsible for communication using IP protocols over fixed fibre-optic or wireless telecoms links,

- Test remote communication (GPRS Modem),

- Replacement of defective parts.

  - Siemens/Qualitrol TM8 Multi Gas Serveron

Firstly, the Contractor shall bring the gas analyser into a working condition from its current state and provide guarantees for the work done. Secondly, as per request from Eskom in a given time perform one or a combination of the following items, which will be deemed necessary for the correct operation of the gas analyser.

- Replacement or refurbishment Gas Separation Columns (Hot Zone) hot zone,

- Replacement or refurbishment sub assemble,

- Replacement verification gas cylinder,

- Helium cylinder replacement,

- Helium pressure adjustment,

- Oil filter inspection/cleaning,

- Fuse replacement,

- Verification gas regulator adjustment,

- Onsite monitor calibration,

- Monitor firmware and software upgrades

- Replacement or refurbishment of equipment responsible for communication using IP protocols over fixed fibre-optic or wireless telecoms links,

- Test remote communication (GPRS Modem),

- Replacement or refurbishment of the power supply unit,

- Replacement of defective parts.

- QUALITY ASSURANCE AND QUALITY CONTROL

  - Quality Assurance

The Contractor to adhere and comply with the ISO 9001 quality assurance program in all processes and activities.

  - Quality Control

The Contractor to compile Process Quality Plan (PQP) that includes and provides the following:

- Details of the process and reference to the project.

- Acceptance by the Employer.

- A list of signatures (and reference to the owner) which will be used to complete all the steps for the process. This is necessary for identification of the relevant Authority for signing off certain steps or tasks in the process.

- Hold Points and Witness Points as required by various steps in the processes.

- Reference to certificates or any important documentation e.g. acceptance criteria for inspection points or tests.

- The main process broken down into individual tasks or steps, to a point as to reflect logical building blocks necessary to complete the main process.

- For each step/task there must be place for signature (with date of signature) of a relevant Authority (Supervisor, Inspector etc.).

4.	ACCOMODATION AND TRAVEL

All travel and accommodation of the Contractor’s staff whether permanent, non-permanent, part-time, sub-contracted is the Contractor’s responsibility. It must be included in their quotation.

5.	LABOUR

All staff whether permanent, non-permanent, part-time, sub-contracted, and labour only supply, is the Contractor’s responsibility in terms of supervision and control.

The Contractor’s supervisor shall be on site at all times seeing to it that all the workers under his supervision work properly and safely.

The Contractor shall indicate the man-hours required to execute each activity and this shall be used to gauge the efficiency of the bidder.

6.	LETTER OF AUTHORIZATION

Contractor to have an accreditation certificate indicating that they have been trained and certified to repair/do maintenance on the equipment. This certificate can be on individuals or for a company, however there must traceable evidence that the skills are still within the service provider.

# APPENDIX 2: Key Performance Indicators (KPI’s):

# Principles behind KPI’s developed for this contract

These principles have been taken into consideration for the establishment, selection and management of KPI’s for this contract over the period of this contract:

- Alignment with regards to philosophy and objectives of this contract.

- The Employer’s Transmission Division management will focus on the strategic relationship between the Contractor and the Employer.

- Measurement will occur in SMT’s, Projects, Works and CCC areas.

- Grid KPI measurement will focus on overall Transmission Grid plant & project performance, cost, safety health and environment (SHE), quality and communication areas.

- KPI’s will remain a pillar of this contract.

- .The incentive is for the Employer to benefit from exceptional performance by the Contractor on each Grid & for the Contractor to earn related returns for his efforts.

- Grid incentives should be standardized at all sites and should be levied proportionally to each Grid’s capacity turnover.

- Grid’s will have a choice of KPI’s from the basket of KPI’s listed below, they will also have the prerogative to  make up their own KPIs as long as it conforms to point 2 below.

- The CPM and SSM will manage and control the KPI process.

- The CCA and Service Manager will monitor and audit the KPI results.

- A high standard of professional and ethical behaviour is expected from both Parties in the use and administration of this contract.

- KPI’s will be reviewed at the steering committee meetings.

# Essential elements of KPI’s

The set for this contract shall have these features:

  - They must be simple to understand.

  - The results or measurement of KPI's and gate keepers must be easy to obtain, compute & record (preferably from existing systems).

  - They must be auditable as they are used for payment.

  - They must reflect as nearly as possible the efforts of the Contractor.

  - They must be few in numbers (otherwise each measure is diluted).

- They must be accepted by both Parties.

- They must as far as possible be centrally defined.

- They must be objective.

- They must take the local Site situation into consideration.

# Transmission Grid operational areas and their KPI’s

The Grid operational areas within which aspects of the Contractor’s performance shall be measured, according to the following KPI’s. KPI’s weights and target settings for the KPI’s will be set at the various Transmission Grids.

Definitions:

- On-Site Plant Failure within guarantee period:

Number of failures within the guarantee period due to Contractor’s performance, calculated as a % of total work, to be determined by formal investigation.

Guarantee period starts after forma l site hand over or formal hand over from works in the case of transformers and reactors going in to storage

- On-time Completion (Site Work – all units):

Total number of projects that were completed on time at site as agreed in task orders.

- Number of NCR customer complaints

The number of formal customer complaints (escalated NCR’s) to management level

- Invoice Timing

To be counted as from the GRN being received from Eskom - percentage invoices to be supplied within 30 days

- Quotation timing

To be counted from the time the request is submitted to the contractor. Quotations to be submitted within 7 days.

NOTE: A MAXIMIUM OF 5 KPI’S TO BE SELECTED AND MINIMUM OF 4

# Appendix 3:  Pro Forma Task Order

|  |  |  |  | Task Order for use with NEC3 Term Service Contract |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Grid |  |  |  | Department: |  |  |  |  |  |
| Contract No: | 46______ |  |  | Task Order No: |  |  | 45___________ |  |  |
| Part One: Data provided by the Employer |  |  |  |  |  |  |  |  |  |
| Grid name: |  |  | Employer’s postal address: |  |  | Employers Task Order Manager (ETOM) |  |  |  |
|  |  |  |  |  |  | Name |  |  |  |
|  |  |  |  |  |  | Tel |  |  |  |
|  |  |  |  |  |  | Fax |  |  |  |
|  |  |  |  |  |  | Cell |  |  |  |
|  |  |  |  |  |  | E-mail |  |  |  |
| Detailed description of the work in the Task |  |  |  |  |  |  |  |  |  |
| Services and other things provided by the Employer |  |  |  |  |  |  |  |  |  |
| Starting date: |  | dd/mm/yyyy |  |  | Task Completion Date: |  |  | dd/mm/yyyy |  |
| Delay damages: |  | N/A |  |  |  |  |  |  |  |
| The period of reply to a communication for this Task Order is: |  | ……..Days (Default 8 Hours) |  |  | The Contractor submits a revised programme for this Task Order every |  |  | ……..Days |  |
| Contractor’s Task Order Manager (CTOM): Signature:________________________________ |  |  |  |  | Employer’s Task Order Manager (ETOM): Signature:________________________________ |  |  |  |  |

| Part Two: Data provided by the Contractor |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Contractor’s postal address: |  | Contractor’s Task Order Manager (CTOM) |  |
|  |  |  | Name |  |
|  |  |  | Tel |  |
|  |  |  | Fax |  |
|  |  |  | Cell |  |
|  |  |  | E-mail |  |
| Additional compensation events |  |  |  |  |
| - Additional data |  |  |  |  |
| Assessment schedule (Part 1. 50.1) |  |  |  |  |
| Contractor’s Task Order Manager (CTOM) : Signature:________________________________ |  | Employer’s Task Order Manager (ETOM) : Signature:________________________________ |  |  |

| Capacity Prices: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task nr | Description |  |  |  |  |  |  |  | Price |
|  |  |  |  |  |  |  | See attached Task |  |  |
| Total of the Capacity Prices for this Task Order |  |  |  |  |  |  |  |  | R |
| Non-Capacity Prices: |  |  |  |  |  |  |  |  |  |
| Item nr. | Description | Unit | Quantity | Unit price |  | Subtotal |  | Add subcontracted fee percentage | Total Price |
| Total of the Non Capacity Prices for this Task Order |  |  |  |  |  |  |  |  | R |
| Total of the Prices for this Task Order |  |  |  |  |  |  |  |  | R |
| Total of the Prices for this Task Order (in words): |  |  |  |  |  |  |  |  |  |
| All Prices in this Task Order exclude VAT |  |  |  |  |  |  |  |  |  |
| The above prices are valid for _________ days from the date of the Contractors signature below |  |  |  |  |  |  |  |  |  |
| Contractor’s Delegated Authority: Signature:________________________________ Name: (Print) _____________________________ Date: |  |  |  |  | Employer’s Delegated Authority: Signature:________________________________ Name: (Print) _____________________________ Date: |  |  |  |  |

# Appendix 4:  Confidentiality Agreement

WHEREAS, the Parties wish to exchange certain information;

###### And

WHEREAS, in view of the nature of the information to be exchanged, such exchange can only be carried out in confidence

NOW, THEREFORE, in consideration of the premises and of the mutual covenants herein contained, the parties hereto agree as follows:

- As used in this agreement, the terms “Confidential Information” shall mean any financial, scientific, technical or commercial information relating to, including, without limitation, data, designs, specifications, drawings, test work results, maintenance data, procedures, operating conditions, specifications, patents and/or costs relating thereto, disclosed in written form or orally or acquired by observation. All such information shall be considered confidential unless stated specifically in writing otherwise.

- To assure protection of both parties’ Confidential Information, the parties agree that the information received hereunder shall:

  - Be maintained in confidence;

  - Not be disclosed directly or indirectly to any other party without in each instance having first prior written consent of the other party;

  - Not be used except for the purpose for which it was disclosed; and

  - Protect against unauthorized disclosure by any of the employees, sub-contractors, consultants, to or agents of the receiving party by the taking of reasonable precautions, including the limiting of access to the information received hereunder to employees, sub-contractors, consultants and agents who have signed secrecy agreements with the receiving party, binding them to obligations of confidentiality, non-use and non-disclosure at least as stringent as those set forth in this agreement.

- The obligations of confidentiality, non-use and non-disclosure accepted by each party pursuant to the preceding paragraph shall not prevent either party from disclosing to others or from using in any manner whatsoever:

  - Information which has been or is hereafter published or otherwise becomes public without breach of any obligations hereunder;

  - Information which the receiving party can demonstrate was in its possession in written and/or graphic form prior to receipt thereof from the disclosing party; in this event the receiving party shall notify the party from which the information was received within seven (7) days of receipt of the information;

  - Information which the Receiving Party acquires from any party which has the legal right to disclose same; and

  - Information which is required to be disclosed by law.

However, information received by each party hereunder and designated as confidential shall prima facie be deemed to be confidential and the burden of establishing that such information comes within the foregoing exceptions shall rest upon the receiving party.

- The disclosure by one of the parties to the other of any Confidential Information hereunder shall not be construed as granting to such other party a license or any other rights under such patents of the disclosing party which have been or may hereunder be issued to say disclosing party in any country.

- The obligations assumed by each party with regard to any Confidential Information received from the other pursuant to this agreement, shall terminate ten (10) years from the date of this agreement.

- This agreement shall be governed by and construed in accordance with the civil laws of the Republic of South Africa.  All disputes shall be managed as per the Additional Condition of Contract, Dispute resolution, W1, of the current Service Agreement.

- Any breach of this agreement by the receiving party is immediate grounds for termination (of a Consultant) or disciplinary action (of an Employee).

IN WITNESS WHEREOF, this agreement is executed as of the date below

| FROM |  |  | FROM ESKOM TRANSMISSION |  |
| --- | --- | --- | --- | --- |
| By |  |  | By |  |
| Title |  |  | Title |  |
| As Witness |  |  | As Witness |  |
| Date |  |  | Date |  |
|  |  |  | ESKOM HOLDINGS SOC LTD Reg. No.: 2002/015527/30 ESKOM TRANSMISSION Megawatt Park Maxwell Drive SANDTON 2199 |  |

# Appendix 5:  NCR FORM

| NCR Ref Number |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  | Reference Documents |  |  |  |  |  |  |  | 1: 2: 3: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ORIGINATOR | Required Condition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deviating Condition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name |  |  |  |  | Tel No. |  |  |  |  |  |  | Designation |  |  |  |  | Signature |  |  |  |  | Date |  |  |  |  |
| ACCEPTANCE | Immediate Action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name |  |  |  |  |  | Designation |  |  |  |  |  |  |  |  | Signature |  |  |  |  |  | Date |  |  |  |  |  |
|  | SDR No. |  |  |  |  |  | Raised By |  |  |  |  |  |  |  |  | Signature |  |  |  |  |  | Date |  |  |  |  |  |
| CORRECTIVE ACTION | - Cause |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Corrective Action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Action taken to prevent recurrence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Effective Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name |  |  |  |  | Tel No. |  |  |  |  |  |  | Designation |  |  |  |  | Signature |  |  |  |  | Date |  |  |  |  |
| ACCEPTANCE | Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Names |  |  |  |  | Tel No. |  |  |  |  |  |  | Designation |  |  |  |  | Signature |  |  |  |  | Date |  |  |  |  |
| VERIFICATION | Action(s) Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Names |  |  |  |  | Tel No. |  |  |  |  |  |  | Designation |  |  |  |  | Signature |  |  |  |  | Date |  |  |  |  |

# APPENDIX 5: TRANSPARENCY IN COSTING OF TASK ORDERS

# Transparency in costing of Task orders

This appendix addresses the Employer’s objective to become an informed buyer and will be applicable to the capacity and non-capacity costs for T&SS.

This means;

- Assurance and an understanding of the methodology that has been used to determine a fair price

- The concept of fixed pricing shall still apply

- Site actual hours and resources captured at activity level

- Works actual hours captured at machine centre level

- Transparency information to be made available at the level off the Employers PMM

- Insight and influence over the actual versus planned hours and resources used to determine a fair price

- Standards applicable to working hours and resources will be reviewed and agreed jointly between the Employer and the Contractor after each outage or project on the request of either Party

- Contract users to be fully informed of this process

The process is applicable to task orders issued for refurbishment of major components.

Major components include the following equipment: Power Transformers from 1.25 and above.

# Standard Programs

Standard programs are in place that have been developed based on historical data. These standards are being used as a basis for compiling baseline programs for the pricing of task orders.

The current practice is for the standards to be reviewed by the Contractor and updated based on the formal change request process where necessary.

As per the following processes the Employer will now be part of the review and change process.

# Post Task Order Review

Formal reviews will be conducted at the end of each outage/project on the request of either Party within 3 months of completion. In the event that a review was not required, then the current standard will remain applicable.

The Contractor’s Senior Project Manager and the Employer’s OU Senior Manager Operations & Maintenance are responsible for conducting the review.

The following information will be available at the post task order review;

- The Works program with planned and actual durations, updated Work Breakdown Structures and Work to Lists

- The Site program with planned and actual durations, primary resources and Work to Lists

- The Standard which was originally applied for activity durations and resources where applicable

Note: The Site and Works Work to lists will only be available for review at the Contractors offices. (This means that the information on the lists will be available for reviews but copies of these lists will not be distributed by the Contractor)

# Updating of Standards

Any proposed change to a standard shall be agreed to, and motivated by the Contractors Senior Project Manager and Employers OU Senior Manager Operations & Maintenance for consideration.

The proposed change to a standard shall be presented to the Contractor’s Senior Management for consideration and approval before being implemented.

If the proposed change to a standard is not approved by the Contractor’s Senior Management the Employers OU Senior Manager Operations & Maintenance must be informed of this including the reasons for rejecting the proposed changes

An auditable data base must be maintained by the Contractor per station off all standards and records must be kept of any changes made to the standards.

# Transparency for Non Capacity

The following information on non-capacity will be provided as per Appendix 3, revision 1 of the task order form.

| Non-Capacity Prices: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item nr. | Description | Quantity | Unit | Duration |  | Unit price | Subtotal | Add Sub fee % | Total Price |
| 1 | Accommodation. |  | Person |  | Days |  |  |  |  |
| 2 | Living Out Allowance |  | Person |  | Days |  |  |  |  |
| 3 | Vehicle Hire |  | Vehicle |  | Days |  |  |  |  |
| 4 | Consumables |  | Lot |  | Lot |  |  |  |  |
| 7 | Subcontract 1 |  | Lot |  | Lot |  |  |  |  |
| 8 | Subcontract 2 |  | Lot |  | Lot |  |  |  |  |
| 9 | Subcontract 3 |  | Lot |  | Lot |  |  |  |  |
| 10 | Subcontract 4 |  | Lot |  | Lot |  |  |  |  |
| Total of the Non Capacity Prices for this Task Order |  |  |  |  |  |  |  |  |  |

# Appendix 6: SDL

# 1. Philosophy

Eskom, as a state owned enterprise, is tasked with achieving government socio-economic transformation and development initiatives through its procurement spend. Therefore, Supplier Development, Localisation and Industrialisation (SDL) team sets targets on B-BBEE, Localisation, Industrialisation, Skills Development, Job Creation and Supplier Development to which suppliers submit their proposals.

2. OBLIGATIONS

Section 1: Pre-qualification Criteria for Preferential Procurement

SDL&I will apply the following pre-qualification criteria as envisaged in PPPFA 2017 regulation 4

YES; NO. - Minimum BBBEE status level of contributor?; ☐. If Yes, what is the BBBEE status and/or level required. YES; NO. - Is there BBBEE category targeted for this enquiry?; ☐. If Yes, BBBEE category. YES; NO. - Minimum subcontracting requirement for this?; ☐. If Yes, what is the minimum percentage?. YES; NO. - Is this commodity or part of it a Designated Sector?; ☐. If Yes, it is mandatory to complete Section 2. YES; NO. - Is there CIDB compulsory training?; ☐. If Yes, what is the% of the Construction Skills Development Goal % (CSDG); Not applicable. If Yes, it is mandatory to complete Section 3. NOTE 1: If subcontracting is part of the pre-qualification criteria (c), Sub-contracting agreement/s must be submitted as a tender returnable.

Section 2: Designated Sectors (Continuation of Pre-qualification)

When applicate the following stipulated minimum threshold for Local Production and Content must be achieved in full by the tenderer

Commodity; Components; Local Content Threshold. Steel; Fasteners, wire products, joining / connecting components and various components; 100%. Cable; Power wire and various components; 90%. Transformer; Transformer oil and various components; Class 0 is 90%; Classes 1,2,3 80% and 20% for class 4. Switchgear; Various components; 50%. NOTE 2: SBD 6.2 Declaration Form, Annex C, Annex D and Annex E are therefore mandatory and must be a tender returnable.

Section 3: CIDB Skills Development

Continuation of Pre-qualification

Criteria; Eskom Target; Tenderer Commitment. CSDG Percentage; N/A. Description; N/A. Note 3: Failure by the Contractor/Service Provider/Supplier to meet the CIDB CSDG mandatory % will render their tender non-responsive.

Section 4: Validity of Affidavit

The following must be considered when it comes to validity of Affidavits;

- Affidavit must be completed in full (i.e. dates, ownership percentages and contribution level).; ☐. - Deponent and Commissioners date must be same.; ☐. - Affidavits on Accountants/Auditors letterheads will not be accepted.; ☐. - Affidavits signed by Accountants/Auditors will not be accepted.; ☐. - Only BBBEE certificates for EMEs coming from DTI will be accepted.; ☐. Specify others requirements. - …………………………………………………………………………………………..; ☐. - …………………………………………………………………………………………..; ☐.

Section 5: SDL&I Undertaking

Tenderers who complete and submit the undertaking as required, but who do not meet Eskom’s targets, will not be disqualified. SDL&I undertakings do not form part of scoring but commitments will form part of contractual obligations

- BBBEE Contractor has successfully migrated from the non-compliant status to a B-BBEE recognition status of level 5 – refer attached Contractor’s latest B-BBEE certificate that expires on 29 September 2021 and the verification report. Contractor is required to make improvements on the BBBEE status over the contract period. - Local content: The costs for designated materials and all activities that take place within the borders of South Africa. Eskom Target; Obligation. 95%; 95%. - Subcontracting: Contractor is required to procure from enterprises that are 51% owned by black persons. Activities include tap changer service at sites, accommodation, workshop consumables, manufacturing of winding, supply of transformer oil and the hiring of cranes and trucks. Eskom Target; Obligation. Procurement from enterprises 51% owned by Black Persons; 20% of local content; 20% 0f the Total Procurement Expenditure. Based on historical trends Contractor subcontracts less than 15% of the overall contract, the bulk of the contract is executed by Contractor utilising its own resources, e.g. for the recent interim contract valued at approximately R500 million, Contractor spent around R53 million on procurement – 20% of which to Black Owned businesses. It is on this basis that I request that we base the targets on procurement expenditure to ensure that targets are achievable and Contractor SDL&I will share progress reports monthly on procurement trends. - Job Opportunities Contractor has committed to creating no new jobs and retaining 396 jobs as a direct result of this contract. - Penalty for SDL&I Commitments Eskom will apply a penalty of 2.5% of every invoice amount for failure to submit SDL&I performance reports every quarter; or failure to meet the SDL&I obligations in a contract. Once Eskom has verified that Contractor has fulfilled its SDL&I obligations, the 2.5% retained shall be approved for reimbursement by Eskom to Contractor within 90 (ninety) days of verification by Eskom. - Monitoring and Reporting of SDL&I Commitments - Contractor shall on a quarterly basis submit a report to Eskom in accordance with Data Collection Template on its compliance with the SDL&I obligations described above. - Eskom shall review the quarterly reports submitted by within 60 (sixty) days of receipt of the reports and notify Contractor in writing if its SDL&I obligations have not been met. - Upon notification by Eskom that Contractor has not met its SDL&I obligations, Contractor shall be required to implement corrective measures to meet those SDL&I obligations before the commencement of the following quarter, failing which Retention clauses shall be invoked. This contract shall be accompanied by the SDL&I implementation schedule which must be completed by Contractor and returned to SDL&I representative for acceptance before contract award. This will be used as a reference document for monitoring, measuring and reporting on the supplier’s progress in delivering on their stated SDL&I commitments.

This total is required by the Purchaser for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.