## TERMS OF REFERENCE

DSAC 17/22-23

THE APPOINTMENT OF A SCULPTOR FOR THE PRODUCTION AND INSTALLATION OF STATUE AND PLAQUE OF ARCHIBALD (ARCHIE) GUMEDE IN ETHEKWINI (DURBAN), KWAZULU-NATAL

CLOSING DATE AND TIME OF BID: 10 MARCH 2023 AT 11:00AM

COMPULSORY BRIEFING SESSION:

VENUE: KwaMuhle Museum, 130 Bram Fischer Road, Durban (KZN)

DATE: 23 FEBRUARY 2023

TIME: 11:00AM

BID VALIDITY PERIOD: 120 DAYS

THE APPOINTMENT OF A SCULPTOR FOR THE PRODUCTION AND INSTALLATION OF STATUE AND PLAQUE OF ARCHIBALD (ARCHIE) GUMEDE IN DURBAN, KWAZULU-NATAL

- InTRODUCTION

The National Department of Sport, Arts and Culture (DSAC) is seeking to appoint a sculptor for the production and installation of a bronze statue that will be a realistic visual representation of Archibald (Archie) Gumede and plaque to be installed at the Frances Farewell Square (Church Walk), next to City Hall, eThekwini (Durban), KwaZulu-Natal.  The Department will implement the project as a legacy project and working closely with key project stakeholders and the sculptor.

The purpose of this document is to outline project scope, deliverables and what is expected from the service provider in the project.

2. 	Background

2.1	Mr. Archie Gumede was one of the founder members and leaders who was actively engaged in the struggle against oppression as most leaders were either in exile or imprisoned. Archie Gumede was elected one of the three Presidents of the new political movement called the United Democratic Front (UDF) in 1983.

2.2 	The UDF filled a political leadership vacuum within the borders of the 1980s Apartheid South Africa while other political organisations were still banned. Under the leadership of Mr. Archie Gumede, UDF was instrumental as a political movement inside South Africa in bringing apartheid to its knees thus bringing democratic dispensation.

  - The objectives of the project:

    - to transform the heritage landscape.

    - to promote and preserve the legacy of Archie Gumede.

  - The implementing of the development and installation of the Archie Gumede bronze statue and plaque project scheduled for 2023/24 and 2024/25 financial years.

  - The nine metre (9m) tall bronze statue including concrete plinth from the surface, will be installed at the Frances Farewell Square, eThekwini, Church Walk, next to City Hall, which area is considered popular for hosting passers-by, pedestrians, and tourists who frequently use the space to rest and take pictures.

- SCOPE AND EXTENT OF THE TENDER / TASK DIRECTIVE

  - The Department requires the services of a duly experienced and knowledgeable sculptor in undertaking the table below. Bidders should confirm that, they have read and understood the task description, they should indicate as such in the third column.

| No | TASK/SCOPE AND DELIVERABLES | YES/NO/NOTES |
| --- | --- | --- |
|  | The sculptor will be expected to produce and install a bronze statue that will be a realistic representation that honours the life and work of Mr. Archibald (Archie) Gumede with accompanying plaque. |  |
|  | The expected deliverable is an installed bronze statue of Archie Gumede on a concrete plinth with a plaque containing a summarised inscription of Mr. Archie Gumede’s contribution towards liberation and freedom. |  |
|  | Archie Gumede statue will be larger than life with the size of six metres (6m) tall plus three metres (3m) tall concrete plinth from surface. The total size of the statue together with concrete plinth will be nine (9m) high, excluding foundation of the plinth. The exact size of the underground depth of the concrete plinth foundation will be determined by structural engineer and service provider. The total height of the artwork must perfectly correspond with the weight of the subject. |  |
|  | The concrete plinth/pedestal must reflect designs of an African aesthetic symbolism against colonial narrative. |  |
|  | The statue should capture both the actual likeness and personality of Archie Gumede. The sculptor/service provider must demonstrate skills in applying relevant portrait-making techniques to achieve this requirement. Elements such as gesture, pose, and general mannerisms of the portrayed subject must contribute towards the final likeness/appearance and personality of Archie Gumede. His high social standing as a struggle hero and statesman must also be astutely expressed in the final piece. |  |
|  | Realist and romanticist elements must be successfully combined in the statue to add something that can enigmatically capture the viewer’s imagination. Essential personality traits and mannerisms can be discovered through thorough preliminary research by the service provider. People who never had a privilege of personally interacting with Archie Gumede should be enabled to construct nostalgic feelings or ‘memories’ about his heroism, grace, steadfastness, etc. The personality of the subject must, by all possible means, be endowed with a strong ‘presence’. |  |
|  | The final piece must be visually convincing and aesthetically pleasing, complying strictly with all principles of scale and proportion. This can be achieved if the service provider accurately studies the basic personal characteristics of Archie Gumede including the distribution of his height and weight. Every part of the body should perfectly harmonize with the overall appearance of the whole statue. |  |
|  | Elements of posture and gesture must be combined to construct a sense of compelling dignity and power marking Archie Gumede’s personality. The statue must be in a standing pose. |  |
|  | The statue must be highly finished in bronze, allowing the prestige of the material and the personality of the subject to enhance its visual impact. |  |
|  | The main, final piece should be preceded by a maquette to be submitted and presented to the Project Steering Committee (PSC), strictly complying with all the above requirements. Its height must be 300mm. A two-dimensional drawing must include a north point and sight-lines from various vantage points will be required. NB: This maquette is separate from the maquette submitted with bidding documentation. |  |
|  | The service provider is required to construct corresponding landscape features around the artwork/piece, with clear ideas of the environmental context in a two-dimensional sketch. |  |
|  | The plaque, also in bronze, must have a summarized descriptive narration of 100 words of who Mr. Archie Gumede was, including his key role in the formation of the UDF and his contribution as a politician after the demise of Apartheid. However, the bold, visible, and easy-to-read text must concisely capture the main description of the hero. |  |
|  | The inscription on the above-mentioned plaque must be in two official languages predominantly spoken in KwaZulu-Natal in this order, isiZulu and English. The service provider must mount the plaque with descriptive inscription on the plinth after final approval by DSAC. |  |
|  | The production phases/stages/process must be clearly stated and include, but not be limited to, sculpture designs/sketches development (informed by extensive research), moulding, casting, bronze making, transportation and installation. |  |
|  | The service provider will be required to present work in progress and obtain a go ahead from the PSC members before commencement of the next stage. |  |
|  | The Department, in collaboration with the PSC and Gumede family, will approve a statue mould and plaque inscription before final product in bronze is completed. |  |
|  | All bid documents should be accompanied by the following: - Graphic rendition of a maquette and site model: Bidders will be required to submit a fully sketched presentation and graphic interpretation and a site model (plinth or base) of the proposed Archie Gumede sculpture that should be hand-drawn sketches or computerized two-dimensional (2D) versions showing front, back, side and aerial elevations with a synopsis explaining the concept. A two-dimensional drawing must include a north point and sight-lines from various vantage points. - Maquette: - Bidders are required to produce a maquette of 300mm based on the detailed drawings that each bidder is required to submit as explained above. The maquette will consist of the Archie Gumede sculpture and the site model (site model should be proportional to the sculpture). - Failure to submit maquette will result in your bid being disqualified. - Site Landscaping Design - Bidders are required to design a cultural heritage landscape displaying liberation and transformation theme/symbolism. - Enhance harmony with natural environment and sculptural artistry exhibiting people’s liberation route and historical significance. - Inscription: - Bidders are required to submit a draft inscription/summarized inscription of one hundred (100) words that will go onto the metal plaque. |  |
|  | The statue project implementation plan document must accommodate all transportation logistics of the mould from the studio to and from the foundry and to the site of installation including transportation costs. |  |
|  | The service provider has an obligation to appoint a registered professional civil structural engineer to oversee the statue structural works based on their design, construction monitoring, and certification of all the statue structural works undertaken by the appointed service provider/artist/sculptor. NB: The estimated costs for the civil structural engineer will be the responsibility of the service provider and not the client. Therefore, service provider must clearly indicate cost estimates for the civil structural engineer in the total cost breakdown for the project. |  |
|  | The civil structural engineer, appointed and paid by the service provider has the responsibility to undertake but not limited to the following activities, (as their final scope of works will be agreed between engineer and service provider): - geotechnical site investigation. - rationally design and specify suitable base/foundation. - provide technical and detailed construction drawings. NB: All relevant drawings should be, where applicable, submitted to and approved by either the KwaZulu-Natal Amafa and Research Institute or the South African Heritage Resources Agency (SAHRA) and/or EThekwini Metropolitan Municipality ensuring that the proposed statue and plinth are in compliance with all municipal by-laws. NB: The above listed activities are crucial in ensuring the structural stability of the statue against mass, environmental factors, wind resistance and warranting the safety of the public. |  |
|  | The appointed Civil Structural Engineer must be a holder of a Civil Engineering Degree/BTech qualification, specializing in structural engineering design work and be professional registered with ECSA. The service provider must make allowance for conducting Geotechnical Investigations by a professional/registered soil laboratory. |  |
|  | The service provider must provide the Department with approvals and proof of engagements (with regards to above) with Municipality, either SAHRA, or the relevant Provincial Heritage Resources Agency (PHRA), which will be the KwaZulu-Natal Amafa and Research Institute in this case. |  |
|  | Service provider must provide the Department with all certifications including the structural engineering compliance certificate and project completion certificate of the installed statue, plinth and plaque. |  |
|  | Service provider must submit invoices accompanied by periodic reports of work completed, incorporating photos, job opportunities created with details of people employed by the project. Details of employed people must include names, ID numbers, gender, age and area of work (skills transferred or developed), physical addresses and contacts. The reports must include the number of persons with disabilities who have been employed on the project should there be any. |  |
|  | The service provider will be required to make budget provision and prepare for: - PSC meetings scheduled to be held at least twice per quarter. - Cleaning the site before and after installation of the statue, plinth and plaque. - Limiting/enclosing statue site from public viewing and accessibility during installation process in liaising with Municipality. |  |
|  | The service provider should budget for all necessary services required during the production and installation of the statue and plaque. This include but not limited to: - foundry visits with PSC/DSAC Senior Officials/Executive Authority for monitoring and approval purposes. - compliance certificates, services to be procured by the service provider (e.g. structural engineer costs). - insurance for transportation of the mould/statue from one place to another. - and any material that may be required during the process such as construction materials to limit but public viewing during installation. - quality and resistant material to tight wrap the installed statue and plinth immediately after being installed. - a nine metre (09) quality cloth tailored to cover the statue and plinth on the day of official unveiling ceremony. |  |
|  | The service provider will be working with the following key stakeholders: - Project Steering Committee. - The Archie Gumede Family. - The Archie Gumede Foundation. - KZN AMAFA and Research Institute. - KZN Dept of Sport, Arts and Culture. - EThekwini Municipality. - Other key stakeholders as identified by PSC. |  |

5.	EVALUATION STAGES

5.1	The bid evaluation process consists of several stages that are applicable as defined in the table below:

| Stage | Description | Applicable for this bid |
| --- | --- | --- |
| Stage 1 | Initial screening process to check compliance with bid requirements. | Yes |
| Stage 2 | Functionality requirement evaluation. | Yes |
| Stage 3 | Price and BBBEE evaluation and Specific goals. | Yes |

5.1.1	Stage 1:

Verification of service provider (s) compliance with bid requirements and initial screening process.

5.1.2	Stage 2:

The Technical proposal will be evaluated out of 100 points with a threshold of 70 points.  Bidders that score less than minimum of 70 points will be disqualified.  Bidders must score a minimum of 70 or more points to qualify for further evaluation on price and preference points.

5.1.3	Stage 3:

Bids will then be evaluated in accordance with the prescripts of the Preferential Procurement Policy Framework Act (PPPFA) and the associated Preferential Procurement Regulations of 2022, which stipulate an 80/20 preference point system is applicable up to a rand value of R50 million (all applicable taxes included).

- The following criteria will be used in particular as the criteria for appointment, apart from those laid down in the Preferential Procurement Regulations, 2022, pertaining to the Preferential Procurement Policy Framework Act 5 of 2000.

- Tenderers are required to submit proof of B-BEEE status level of contributor. Proof includes valid B-BEEE Status Level Verification certificate together with their tenders, to substantiate their B-BEEE rating claims. Failure to submit a valid B-BBEE certificate will result in zero preference points being awarded for B-BBEE. B-BBEE certificates or sworn affidavits must be valid at the time of the closing of the tender.

- Tenderers are required to submit B-BEEE status level verification certificate issued by the following agencies;

Tenderers other than EMEs – Verification agencies accredited by SANAS;

Tenderers who qualify as EME’s – Sworn affidavit signed by the EME representative and attested by Commissioner of oaths and/or B-BBEE certificate issued by the companies and Intellectual Property Commission.

- Where specific goals points are claimed, bidders to attach certified copies of ID’s, company registration documents and most recent CSD report.

The points for this bid are allocated as follows:

| No | Components | Points |
| --- | --- | --- |
| 1. | Price | 80 |
| 2. | Preferential points: BBBEE | 10 |
| 3. | Specific goals as per SBD 6.1 | 10 |
|  | Total | 100 |

6.	EVALUATION PROCESS

6.1	The 80/20 preference point system in terms of the Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000) shall apply. The lowest acceptable bid will score 80 points for price and remaining 20 points for B-BBEE status level of contribution and specific goals as per attached SBD 6.1

6.2	Prospective bidders will have to score at least 70 out of 100 points allocated for

functionality before the company’s proposal will be considered for pricing.

7.	BID REQUIREMENTS

General requirements

The following is required of bidders and should be submitted to the department as part of the bid submission:

7.1	Company profile.

7.2	All Bidders must be registered on the National Treasury Central Supplier Database (CSD) and must attach a copy of the most recent report to the tender document.

7.3	The tax status on CSD must be compliant, as Department is unable to award a contract to a company whose tax affairs are not in order as determined by SARS. Bidders whose tax matters have expired, or compliance status is invalid will be disqualified. Note that it is no longer a requirement for bidders to submit hard copies of tax clearance certificates as compliance to tax matters can be assessed and verified on the CSD report.

7.4	Tenderers are required to submit proof of B-BEEE status level of contributor. Proof includes valid B-BEEE Status Level Verification certificate together with their tenders, to substantiate their B-BEEE rating claims. Failure to submit a valid B-BBEE certificate will result in zero preference points being awarded for B-BBEE. B-BBEE certificates or sworn affidavits must be valid at the time of the closing of the tender.

7.5	Original Company Resolution or Letter of authority or Letter of appointment authorizing the signatory of the Entity to sign the contract with the Department.

7.6	Valid contact details including e-mail address.

7.7	Certified ID copies of all Directors.

7.8	Bidders are requested to provide one original, one copy of the original document and one electronic copy (in a form of USB) of original document.

7.9	Companies, who registered for VAT, should include VAT on their costing.

7.10	Any other details that may be relevant in respect of the tender evaluation criteria 	described above.

7.11	All bidders are required to submit details of Shareholder status as follows:

- Shareholder certificates with the names of Directors and percentage of ownership.

- Identity Documents of all Shareholders.

Technical Requirements

- A detailed proposal including:

- Project Implementation plan.

- Detailed Cost breakdown

- Capacity and experience.

- Number and level/ranks of team member/s to be involved in sculpturing.

- CVs/Resumes of all involved in sculpturing project (including, but not limited to, qualifications, knowledge, experience and level of expertise and/or current designation).

8.	EVALUATION CRITERIA

All bids dully lodged will be evaluated by a panel first on functionality then price.  For purposes of comparison and to ensure meaningful evaluation, bidders are requested to furnish detailed information in substantiation of compliance to each of the evaluation criteria mentioned below. The following evaluation criteria will be used to evaluate all bidders.

| 8.1. | EXPERIENCE IN RENDERING SCULPTURING WORKS. - Brief summary of experience in rendering sculpturing works of similar scale. 10 points. - To substantiate the above, service provider must provide evidence in the form of: - profile of similar works, scopes/scale and costs with quality images/pictures of sculptures/statues completed in the past in line with reference letters above: - 3 profiles of different works = 5 – 7 points - 4 profiles and above = 8 – 10 points - verifiable reference letters confirming previous and/or existing clients. Letters must make reference to the size of the sculptures/statues, material used, location where artwork/piece was installed, costs and comments whether services were rendered successfully or not. - 3 reference letters = 5 - 7 points - 4 and above letters = 8 - 10 points | 30 |
| --- | --- | --- |
| 8.2. | CAPACITY AND RESOURCES - attach resumes of human resource displaying teamwork skills and expertise in crafting/sculpturing, capacity and ability to produce/render required service. 5 points. - confirmation of financial resources availability to start the project as the client will not make an upfront payment. 5 points. - Confirm availability of material resources, such facility/studio or renting space at studio and adequate equipment where the work will be done. 5 points. - Submission of the maquette/miniature clay scale model with actual likeness and proportionality to the base/plinth with African aesthetic symbolism as described in the scope of task directives/deliverables under section 3 of the terms of reference. 5 points. | 20 |
| 8.3. | PROJECT PLAN AND IMPLEMENTATION PLAN - Submission of the project plan with implementation plan illustrating the sculpturing phases/stages with realistic timelines indicating how much time for each milestone/phase/stage. Phases/stages must include amongst others: - 20 points - sculpture designs/sketches development. - Clay sculpturing. - Mould/Mold-making. - Transportation of the clay sculpture from the studio to the foundry. - Waxing and Casting. - Bronze making. - Transportation/Delivery of the complete sculpture from the foundry to the site of installation. - Site preparation, Installation and landscaping logistics including hiring/renting of equipment for putting up the art piece. - Completion phase with close-out report accoupled with final invoices and compliance certifications. - Clear and realistic costs breakdown. 10 points | 30 |
| 8.4. | LAYOUT OF ENVIRONMENTAL INTEGRATION PLAN - Illustration of cultural heritage transformation theme/symbolism/representation in landscaping designs incorporating existing memorials/monuments in the precinct. 10 points - Enhancing harmony with natural environment and sculptural artistry. 10 points | 20 |
|  | TOTAL | 100 |

9. 	CONFIDENTIALITY

9.1 	No information or documentation may be used for any other purpose other than providing for a tender proposal to the Department, and no copies of any document may be made, except with prior written approval from the Department.

9.2	The successful bidders and staff will be required to sign a non-disclosure agreement.

10.	INTELLECTUAL PROPERTY AND OWNERSHIP

10.1	Ownership and copyright of all documentation developed during the period of the contract will be vested in the Department of Sport, Arts and Culture.

10.2	All intellectual property rights relating to any work produced by the service provider in relation to the performance of this contract shall belong to the Department and may not be used for any other purpose by the service provider.  The service provider shall give the Department all assistance in protecting such intellectual property rights. All material, in paper, electronic or any recorded format produced by the service provider in the performance of this contract shall remain the property of the Department of Sport, Arts and Culture and must be handed over to the Department on termination of the contract.

10.3	All service providers undertake not to infringe the intellectual property of third parties. Should any action or claim be instituted against the Department emanating from an infringement of intellectual property or an alleged infringement of intellectual property, the service providers hereby indemnify the Department against such claims or actions as well as all costs (including legal costs on an attorney and client scale).

11.	CONTRACTUAL ARRANGEMENT

The service provider is required to enter into a Service Level Agreement with the Department of Sport, Arts and Culture to perform all functions as set out in the project Specification or Terms of Reference and National Treasury General Conditions of Contract of 2010.

The contract duration will be crossing over from 2023/24 to 2024/25 from the date of appointment. The service provider should attend a meeting at the DSAC within a week of his/her appointment and should avail himself/herself for progress meetings as per the Department’s request.

12.	FINANCIAL IMPLICATIONS

12.1	The project budget has been allocated for and part of procurement plan in respect of advertised competitive bids for 2022/23 financial year. The budget allocation is crossing over to 2023/24 and 2024/25 financial years.

12.2 	No service will be provided to the Department before an official order has been issued to

the supplier or service provider.

12.3 	The Department will not make an upfront payment to the service provider.

12.4 	Tranche payments schedule will be discussed and agreed upon during the process of signing SLA based on agreed milestones completed and signed off.

12.4	Payments will be done according to the schedule and requirements as per the provision of the signed Service Level Agreement (SLA).

13.	CLIENT BASE

The Department of Sport Arts and Culture reserves the right to contact references during the evaluation and adjudication process to obtain information.

14.	COMMUNICATION

The Department of Sport Arts and Culture may communicate with bidders for, among others, where bid clarity is sought, to obtain information or to extend the validity period.

15.	PRESENTATION

The Department of Sport, Arts and Culture may request presentations and or interviews from short-listed bidders as part of the bid process.

16.	SUPPLIER DUE DILIGENCE

The State reserves the right to conduct supplier due diligence prior to final award or at any time during the contract period. Bidders must note that, the Department may conduct verification on the information submitted and any misrepresentation will result in an automatic disqualification.

17.	CONFLICT OF INTEREST

The bidder or bidders’ group must submit a document (you may include it in your covering letter), stating whether any of its employees have any interest in the Department or whether any of Department’s personnel have any interest in the bidders or affiliated business.

18.	PACKAGING OF SBDs

Bidders to arrange the Standard Bidding Documents (SBDs) in your submission numerically and orderly.

19.	BRIEFING SESSION

The Department will have a compulsory physical briefing session at KwaMuhle Museum, 130 Bram Fischer Road, Durban, KwaZulu-Natal Province on the 23 February 2023 at 11:00am.

20.	SUBMISSION OF BID DOCUMENTS

20.1	Bidders are advised to ensure that bids are submitted allowing sufficient time for any

unforeseen events that may delay the delivery of the bid and time to access the premises

because of security arrangements when entering the department main entrance.

20.2     Bidders are requested to provide one original, one copy of the original document and one electronic copy (in a form of USB) of original document.

20.3	All bidders are required to complete a bid register fully, when submitting bid documents.

The Bid register is available at the below-mentioned address.

20.4	Bidders should deposit their documents into the tender box available on the Ground Floor reception area by 11H00 at the address below:

Department of Sport, Arts and Culture

Sechaba House

202 Madiba Street, Cnr Madiba and Paul Kruger Streets

Pretoria

21.	COST OF BIDDING

The bidder shall bear all costs associated with the preparation and submission of its bid and the Department, will no case be held responsible or liable for these costs, regardless of the conduct or outcome of the tender process. The bidder will not be entitled to claim for travel and subsistence expenses. If such expenses are applicable, these charges must be included in the bid price.

22.	PRICE OR FEES NEGOTIATION

The Department may negotiate the price or fees with the preferred bidder/s during a competitive bidding process.

23.	LATE BIDS

Bids are received at the address indicated above. Bids received after the closing date and time will not be accepted for consideration and will be returned unopened to the bidder. Bids documents should be submitted before 11:00 on the closing date of the tender.

24.	BID AND TECHNICAL ENQUIRIES / CLARIFICATION OF TENDER DOCUMENTS

The Department will respond in email to any request for clarification of the tender documents which it receives no later than one (1) week prior to the deadline for submission of bids prescribed by the Department.  All enquiries related to the technical content of the Terms of Reference as well as the bid enquires may be directed in writing to the officials listed below:

For Technical Enquiries:

Name: Msawenkosi Khumalo

Tel: 012 441 3676 / 082 909 1326

E-Mail: msawenkosik@dsac.gov.za

Name: Thembi Malao

Tel: 012 441 3542 / 082 680 6688

E-Mail: thembim@dsac.gov.za

For Supply Chain Management Enquiries:

Name: Tuelo Thubisi

Tel: 012 441 3504

E-Mail: tuelot@dsac.gov.za

Name: Ms Tshepiso Ramatapa

Tel: 012 4413173 / 072 751

E-Mail: tshepisor@dsac.gov.za