eskom holdings soc ltd

	[image: image1.jpg]R Eskom






NEC3 Engineering & Construction Contract
	Between


	ESKOM HOLDINGS SOC Ltd 

(Reg No. 2002/015527/30) 

	and


	[Insert at award stage]
(Reg No. ___________ )

	for


	Eskom Academy of Learning Electrical Reticulation System Replacement Project

	
	

	Contents:


	
	No of pages

	Part C1
	Agreements & Contract Data
	[●]

	Part C2
	Pricing Data
	[●]

	Part C3
	Scope of Work
	[●]

	Part C4
	Site Information
	[●]

	
	
	

	CONTRACT No.
	[Insert at award stage]

	
	

	
	

	
	


Part C1: Agreements & Contract Data
	Contents:


	
	No of pages

	C1.1
	Form of Offer and Acceptance 

[to be inserted from Returnable Documents at award stage]
	[●]

	C1.2a
	Contract Data provided by the Employer
	[●]

	C1.2b
	Contract Data provided by the Contractor
[to be inserted from Returnable Documents at award stage]
	[●]

	C1.3
	Proforma Guarantees
	[●]


C1.1 Form of Offer & Acceptance

Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Eskom Academy of Learning (EAL) Electrical Reticulation System Replacement Project
The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.
By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data. 

Delete the Options which do not apply

	Options A B, C or D
	The offered total of the Prices exclusive of VAT is 
	R [●]

	Option E or F
	The first forecast of the total Defined Cost plus the Fee exclusive of VAT is
	R [●]

	
	Sub total
	R [●]

	
	Value Added Tax @ 15% is
	R [●]

	
	The offered total of the amount due inclusive of VAT is

	R [●]

	
	(in words) [●]



This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

	Signature(s)


	
	
	

	Name(s)


	
	
	

	Capacity


	
	
	

	For the tenderer:

	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	

	Tenderer’s CIDB registration number (if applicable) 
	


Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in: 

Part C1

Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2

Pricing Data

Part C3

Scope of Work: Works Information
Part C4

Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.
The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).  
Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

	Signature(s)


	
	
	

	Name(s)
	
	
	

	Capacity


	
	
	

	for the Employer


	

	Name & signature of witness
	(Insert name and address of organisation)
	
	Date
	


Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.
Schedule of Deviations to be completed by the Employer prior to contract award
Note:

1.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.
2. The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

3. A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

	No.
	Subject
	Details

	1
	[●]
	[●]

	2
	[●]
	[●]

	3
	[●]
	[●]

	4
	[●]
	[●]

	5
	[●]
	[●]

	6
	[●]
	[●]

	7
	[●]
	[●]

	
	
	


By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.  

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement. 

	
	For the tenderer:


	
	For the Employer



	Signature


	
	
	

	Name
	
	
	

	Capacity


	
	
	

	On behalf of
	(Insert name and address of organisation)


	
	(Insert name and address of organisation)



	Name & signature of witness
	
	
	

	Date
	
	
	


C1.2 ECC3 Contract Data
Part one - Data provided by the Employer
[Instructions to the contract compiler:  (delete these two notes in the final draft of a contract)
1. Please read the relevant clauses in the conditions of contract before you enter data.  The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.  

2. Some ECC3 options are always selected by Eskom Holdings SOC Ltd.   The remaining ECC3 options are identified by shading in the left hand column.  In the event that the option is not required select and delete the whole row.  Where the following symbol is used “[●]” - data is required to be inserted relevant to the specific option selected.]

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

	Clause
	Statement
	Data

	1
	General
	

	
	The conditions of contract are the core clauses and the clauses for main Option 
	

	
	
	A:

Priced contract with activity schedule

	
	
	

	
	dispute resolution Option
	W1:
Dispute resolution procedure

	
	and secondary Options 
	

	
	
	X2

Changes in the law

	
	
	X5:

Sectional Completion

	
	
	X7:

Delay damages

	
	
	X16:
Retention

	
	
	X17:
Low performance damages

	
	
	X18:
Limitation of liability 

	
	
	Z:

Additional conditions of contract

	
	of the NEC3 Engineering and Construction Contract, April 2013 (ECC3)
	If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data

	10.1
	The Employer is (Name):
	Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa

	
	Address
	Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg

	10.1
	The Project Manager is: (Name)
	To be advised at contract award stage

	
	Address
	Eskom Academy of Learning, Dale Road, Midrand

	
	Tel
	[●]

	
	Fax
	[●]

	
	e-mail
	[●]

	10.1
	The Supervisor is: (Name)
	To be advised at contract award stage

	
	Address
	[●]

	
	Tel No.
	[●]

	
	Fax No.
	[●]

	
	e-mail
	[●]

	11.2(13)
	The works are 
	Replacement of Electrical Reticulation System at Eskom Academy of Learning

	11.2(14)
	The following matters will be included in the Risk Register
	1.
Adverse weather conditions, such as heavy rainfall, snowfall, and strong winds, necessitate the contractor to exercise caution when organizing the schedule and resources for the project.

2.
Any harm to existing equipment and foundations is the responsibility of the Contractor to replace or reconstruct. All delays in construction and procurement of such equipment will be borne by the Contractor and will not be charged back to Eskom.

3.
Theft. The site and working areas are to be guarded to ensure that no theft can take place that will affect construction.

4.
Material suppliers. Suppliers to meet all Eskom requirements. The Employer will not handle any disputes between the Suppliers and the Contract.

5.
Time. This contract has to be completed within the contract period. The Employer shall not be liable for any delays caused by the Contractor.

6.
The contractor will need to be aware that the site will be operational during construction and should provide the necessary security measures to ensure that security is not compromised.

7.
Reputable OEM used with accredited installers, where required.

8.
Limited as-built, operation and maintenance information.

9.
The contractor will need to be aware of the Eskom security requirements and standard that must be adhered to and comply with.

10.
Additional risks will be identified during the initial project meeting and continuously assessed throughout the project duration.


	11.2(15)
	The boundaries of the site are 
	Eskom Academy of Learning

	11.2(16)
	The Site Information is in 
	Part 4: Site Information

	11.2(19)
	The Works Information is in  
	Part 3: Scope of Work and all documents and drawings to which it makes reference.

	12.2
	The law of the contract is the law of 
	the Republic of South Africa

	13.1
	The language of this contract is 
	English

	13.3
	The period for reply is
	Five (5) working days

	2
	The Contractor's main responsibilities
	Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. 

	3
	Time
	

	11.2(3)
	The completion date for the whole of the works is
	Eight (8) months – post Contractor’s appointment

	11.2(9)
	The key dates and the conditions to be met are:
	Condition to be met
	key date

	
	
	1
2

3

4

5

6

7

8


	Project Schedule
Notice of construction be

given to Department of

Labour
Security clearance of

personnel and induction

Safety File Submission

and induction
Design Approval
Construction Phase
Commissioning and
 training
Handover
	2 weeks After Contractor appointment

Before

Execution of

works.
Before

Execution of

Works
Before

Execution of

works.
After Contractor appointment
As per 
approved schedule

As per approved schedule

As per approved schedule



	
	
	
	
	

	
	
	
	
	

	30.1
	The access dates are:
	Part of the Site
	Date

	
	
	1
	Eskom Academy of Learning Complex
	Before Execution of works.



	
	
	
	
	

	
	
	
	
	

	31.1
	The Contractor is to submit a first programme for acceptance within 
	Two (2) weeks of the Contract Date

	31.2
	The starting date is
	The date for the site handover will be provided after the contract has been awarded and the SHE audit has been done and passed by the Contractor.



	32.2
	The Contractor submits revised programmes at intervals no longer than 
	Two (2) weeks.

	35.1
	The Employer is not willing to take over the works before the Completion Date.
	All works shall be completed before the Employer can take over the works

	4
	Testing and Defects
	

	42.2
	The defects date is 
	52 weeks after Completion of the whole of the

works.

	43.2
	The defect correction period is 
	Two (2) weeks

	
	 
	

	
	 
	

	5
	Payment
	

	50.1
	The assessment interval is 
	On completion of each activity as per the accepted payment schedule.

	51.1
	The currency of this contract is the 
	South African Rand.

	51.2
	The period within which payments are made is 
	Four (4) weeks.

	51.4
	The interest rate is 
	the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and 

(ii) the LIBOR rate applicable at the time for amounts due in other currencies.  LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove.

	6
	Compensation events
	

	60.1(13)
	The place where weather is to be recorded is:
	Eskom Academy of Learning, Midrand

	
	The weather measurements to be recorded for each calendar month are, 
	the cumulative rainfall (mm)

	
	
	the number of days with rainfall more than 10 mm

	
	
	the number of days with minimum air temperature less than 0 degrees Celsius

	
	
	the number of days with snow lying at 09:00 hours South African Time

	
	
	and these measurements:

	
	The weather measurements are supplied by
	The South African Weather Bureau at the nearest station next to the site.

	
	The weather data are the records of past weather measurements for each calendar month which were recorded at: 
	

	
	and which are available from: 

Addition to the Scope of Works by Eskom for which proof is:
	the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer
Written instruction issued by the Eskom Representative stipulated in this Contract document

	60.1(13)


	Assumed values for the ten year return weather data for each weather measurement for each calendar month are:
	As stated in Annexure A to this Contract Data provided by the Employer.
Note:  If this arrangement is used, delete the rows above for 60.1(13) and delete this note.

	7
	Title
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	8
	Risks and insurance
	

	80.1
	These are additional Employer's risks  
	1. Risks to be discussed during the execution of the projects

	84.1
	The Employer provides these additional insurances
	as stated for “Format A” available on http://www.eskom.co.za/Tenders/InsurancePolicies Procedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx (See Annexure B for basic guidance)

	84.2
	The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Employer for an amount of
	

	84.3
	The minimum limit of indemnity for

insurance in respect of loss of or damage to property (except the works, Plant,
Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract for any one event is
	whatever the Contractor deems necessary in addition to that provided by the Employer.

	84.4
	The minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is
	As prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of Indemnity of not less than R500 000 (Five hundred thousand Rands).

	
	
	

	
	
	

	9
	Termination
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	10
	Data for main Option clause
	

	A
	Priced contract with activity schedule
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.

	60.6
	The method of measurement is 
	Option A published by NEC 3 Engineering and Construction Contract of June 2005 and amended as stated in Part C2.1, Pricing Assumptions

	11
	Data for Option W1
	

	W1.1
	The Adjudicator is 
	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him.  (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA).

	
	Address
	[●]

	
	Tel No.
	[●]

	
	Fax No.
	[●]

	
	e-mail
	[●]

	W1.2(3)
	The Adjudicator nominating body is:
	the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body.

	W1.4(2)
	The tribunal is: 
	arbitration.

	W1.4(5)
	The arbitration procedure is 
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	
	The place where arbitration is to be held is
	[●] South Africa

	
	The person or organisation who will choose an arbitrator 

· if the Parties cannot agree a choice or
· if the arbitration procedure does not state who selects an arbitrator, is
	the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.

	12
	Data for secondary Option clauses
	

	X2
	Changes in the law
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.

	X5
	Sectional Completion
	

	X5.1
	The completion date for each section of the works is:
	Section
	Description
	Completion date

	
	
	1
	Section/phase to be agreed with the Employer
	As per approved schedule

	
	
	2
	Section/phase to be agreed with the Employer
	As per approved schedule

	
	
	3
4

5


	Section/phase to be agreed with the Employer 
Section/phase to be agreed with the Employer 
Section/phase to be agreed with the Employer
	As per approved schedule 
As per approved schedule 
As per approved schedule

	X5 & X7

X5.1  X7.1
	Sectional completion and delay damages used together

Delay damages for late Completion of the sections of the works are: 
	
	
	

	
	
	section
1
	Description
Section/phase to be agreed with the Employer
	Amount per day
R5000.00

	
	
	2
	Section/phase to be agreed with the Employer
	R5000.00

	
	
	3
4

5
	Section/phase to be agreed with the Employer
Section/phase to be agreed with the Employer
Section/phase to be agreed with the Employer
	R5000.00
R5000.00

R5000.00

	
	
	
	
	

	
	The total delay damages payable by the Contractor does not exceed:
	Maximum of 10% of Contract Value

	X16
	Retention (not used with Option F)
	

	X16.1
	The retention free amount is 
	

	
	The retention percentage is
	10% of the Contract value

	X17
	Low performance damages
	

	X17.1
	The amounts for low performance damages are:
	Amount of
	Performance level

	
	
	R 200,000.00 or cost of low performance damages stated
R 200,000.00 or cost of low performance damages stated

R 200,000.00 or cost of low performance damages stated

R 200,000.00 or cost of low performance damages stated

R 200,000.00 or cost of low performance damages stated


	For section 1
For section 2

For section 3

For section 4

For section 5

	X18
	Limitation of liability
	

	X18.1
	The Contractor’s liability to the Employer for indirect or consequential loss is limited to:
	R0.0 (zero Rand)

	X18.2
	For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to:
	the amount of the deductibles relevant to the event 

	X18.3
	The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to
	The greater of 

· the total of the Prices at the Contract Date 

and 

· the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date.

	X18.4
	The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to:
	the total of the Prices other than for the additional excluded matters.

The Contractor’s total liability for the additional excluded matters is not limited. 

The additional excluded matters are amounts for which the Contractor is liable under this contract for

· Defects due to his design which arise before the Defects Certificate is issued,

· Defects due to manufacture and fabrication outside the Site,

· loss of or damage to property (other than the works, Plant and Materials),

· death of or injury to a person and 

· infringement of an intellectual property right.

	X18.5
	The end of liability date is 
	(i) Seven (7) years after the defects date for latent Defects and 
(ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter.

A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. 

If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect.

	Z
	The Additional conditions of contract are
	Z1 to Z15 always apply.

	
	

	Z1
	Cession delegation and assignment

	Z1.1
	The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer.

	Z1.2
	Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. 

	
	

	Z2
	Joint ventures

	Z2.1
	If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract.

	Z2.2
	Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf.

	Z2.3
	The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing.

	
	

	Z3
	Change of Broad Based Black Economic Empowerment (B-BBEE) status

	Z3.1
	Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change.

	Z3.2
	The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager.

	Z3.3
	Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works.

	Z3.4
	Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93.

	
	

	Z4
	Confidentiality

	Z4.1
	The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time).  Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient.

	Z4.2
	If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager.

	Z4.3
	In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure.  In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed.

	Z4.4
	The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager.  All rights in and to all such images vests exclusively in the Employer.  

	Z4.5
	The Contractor ensures that all his subcontractors abide by the undertakings in this clause.

	
	

	Z5
	Waiver and estoppel: Add to core clause 12.3:

	Z5.1
	Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing.

	
	

	Z6
	Health, safety and the environment:  Add to core clause 27.4

	Z6.1
	The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor:

· accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site;

· warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and

· undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	Z6.2
	The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	
	

	Z7
	Provision of a Tax Invoice and interest.  Add to core clause 51

	Z7.1
	Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate.

	Z7.2
	If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice.  Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made.

	Z7.3
	The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment.

	
	

	Z8
	Notifying compensation events

	Z8.1
	Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”.

	
	

	Z9
	Employer’s limitation of liability

	Z9.1
	The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand)

	Z9.2
	The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited.

	
	

	Z10
	Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it":  

	Z10.1
	   or had a business rescue order granted against it.

	
	

	Z11
	Addition to secondary Option X7 Delay damages (if applicable in this contract)

	Z11.1
	If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table.

	
	


	Z12
	Ethics

	For the purposes of this Z-clause, the following definitions apply:

	Affected Party
	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

	Coercive Action
	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

	Collusive Action
	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

	Committing Party
	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees,

	Corrupt Action
	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

	Fraudulent Action
	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

	Obstructive Action
	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and

	Prohibited Action
	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

	Z12.1
	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

	Z12.2
	The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason.

	Z12.3
	If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

	Z12.4
	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

	
	

	Z13
	Insurance

	Z 13.1
	Replace core clause 84 with the following:


	Insurance cover
	84
	

	
	
	

	
	84.1
	When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force.

	
	
	

	
	84.2
	The Contractor provides the insurances stated in the Insurance Table A.

	
	
	

	
	84.3
	The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate.

	
	
	

	
	
	INSURANCE TABLE A
Insurance against
Minimum amount of cover or minimum limit of indemnity
Loss of or damage to the works, Plant and Materials
The replacement cost where not covered by the Employer’s insurance
The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance
Loss of or damage to Equipment
The replacement cost
Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract
Loss of or damage to property

Employer’s property

The replacement cost where not covered by the Employer’s insurance
The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance
Other property

The replacement cost

Bodily injury to or death of a person 

The amount required by applicable law
Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract
The amount required by the applicable law


	
	
	

	Z 13.2
	
	Replace core clause 87 with the following:
The Employer provides the insurances stated in the Insurance Table B.

	
	
	

	
	
	

	
	
	

	
	
	INSURANCE TABLE B
Insurance against or name of policy
Minimum amount of cover or minimum limit of indemnity

Assets All Risk

Per the insurance policy document

Contract Works insurance

Per the insurance policy document

Environmental Liability

Per the insurance policy document
General and Public Liability

Per the insurance policy document
Transportation (Marine)

Per the insurance policy document
Motor Fleet and Mobile Plant

Per the insurance policy document
Terrorism

Per the insurance policy document
Cyber Liability

Per the insurance policy document

Nuclear Material Damage and Business Interruption
Per the insurance policy document
Nuclear Material Damage Terrorism
Per the insurance policy document



	Z14
	Nuclear Liability

	Z14.1
	The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS.

	Z14.2
	The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z14.3
	Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z14.4
	The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter.

	Z14.5
	The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned.

	
	

	Z15
	Asbestos

	For the purposes of this Z-clause, the following definitions apply:

	AAIA
	means approved asbestos inspection authority.

	ACM
	means asbestos containing materials.

	AL
	means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL.

	Ambient Air
	means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet.

	Compliance Monitoring
	means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	OEL
	means occupational exposure limit.

	Parallel Measurements
	means measurements performed in parallel, yet separately, to existing measurements to verify validity of results.

	Safe Levels
	means  airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	Standard
	means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles.

	SANAS
	means the South African National Accreditation System.

	TWA
	means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA.

	Z15.1
	The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM.

	Z15.2
	Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan.

	Z15.3
	The Employer manages asbestos and ACM according to the Standard.

	Z15.4
	In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe.

	Z15.5
	The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable.

	Z15.6
	The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001.

	Z15.7
	Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation.


Annexure A:
 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]
If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

	
	Weather measurement

	Month
	Cumulative rainfall (mm)
	Number of days with rain more than 10mm
	Number of days with min air temp < 0 deg.C
	Number of days with snow lying at 08:00 CAT
	[Other measurements if applicable]

	January
	[●]
	[●]
	[●]
	[●]
	

	February
	[●]
	[●]
	[●]
	[●]
	

	March
	[●]
	[●]
	[●]
	[●]
	

	April
	[●]
	[●]
	[●]
	[●]
	

	May
	[●]
	[●]
	[●]
	[●]
	

	June
	[●]
	[●]
	[●]
	[●]
	

	July
	[●]
	[●]
	[●]
	[●]
	

	August
	[●]
	[●]
	[●]
	[●]
	

	September
	[●]
	[●]
	[●]
	[●]
	

	October
	[●]
	[●]
	[●]
	[●]
	

	November
	[●]
	[●]
	[●]
	[●]
	

	December
	[●]
	[●]
	[●]
	[●]
	


Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

C1.2 Contract Data

Part two - Data provided by the Contractor
[Instructions to the contract compiler:  (delete this notes before issue to tenderers with an enquiry)
Whenever a cell is shaded in the left hand column it denotes this data is optional.  If not required select and delete the whole row, otherwise insert the required Data.]

Notes to a tendering contractor:

1. Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN)
 in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

2. The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data

3. Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.
Completion of the data in full, according to Options chosen, is essential to create a complete contract.
	Clause
	Statement
	Data

	10.1
	The Contractor is (Name):
	     

	
	Address
	     

	
	Tel No.
	     

	
	Fax No.
	     

	11.2(8)
	The direct fee percentage is
	     %

	
	The subcontracted fee percentage is
	     %

	11.2(18)
	The working areas are the Site and
	     

	24.1
	The Contractor's key persons are:
	

	
	1
Name:
	     

	
	
Job:
	     

	
	
Responsibilities:
	     

	
	
Qualifications:
	     

	
	
Experience:
	     

	
	2
Name:
	     

	
	
Job
	     

	
	
Responsibilities:
	     

	
	
Qualifications:
	     

	
	
Experience:
	     

	
	
	CV's (and further key persons data including CVs) are appended to Tender Schedule entitled     .

	11.2(3)
	The completion date for the whole of the works is
	     

	11.2(14)
	The following matters will be included in the Risk Register
	     

	11.2(19)
	The Works Information for the Contractor’s design is in:
	     

	31.1
	The programme identified in the Contract Data is
	     

	A
	Priced contract with activity schedule
	

	11.2(20) 
	The activity schedule is in
	     

	11.2(30)
	The tendered total of the Prices is 
	      (in figures) 

      (in words), excluding VAT 

	
	Data for Schedules of Cost Components
	Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013).

	A
	Priced contract with activity schedule
	Data for the Shorter Schedule of Cost Components

	41 in SSCC
	The percentage for people overheads is:
	     %

	21 in SSCC
	The published list of Equipment is the last edition of the list published by
	     

	
	The percentage for adjustment for Equipment in the published list is
	Minus      %

	22 in SSCC
	The rates of other Equipment are:
	Equipment
	Size or capacity
	Rate

	
	
	     
	     
	     

	
	
	     
	     
	     

	
	
	     
	     
	     

	
	
	     
	     
	     

	
	
	     
	     
	     

	61 in SSCC
	The hourly rates for Defined Cost of design outside the Working Areas are
	Category of employee
	Hourly rate

	
	Note:  Hourly rates are estimated ‘cost to company of the employee’ and not selling rates.  
	     
	     

	
	Please insert another schedule if foreign resources may also be used
	     
	     

	
	
	     
	     

	
	
	     
	     

	62 in SSCC
	The percentage for design overheads is
	     %

	63 in SSCC
	The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are:
	     

	
	
	     
	     
	     

	
	
	     
	     
	     

	
	
	     
	     
	     


C1.3 Forms of Securities 

Pro formas for Bonds & Guarantees

For use with the NEC3 Engineering & Construction Contract 

The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:

Option X16:
Retention (not used with Option F)
The Contractor may provide a Retention Money Guarantee in the form stated here.  When the Employer receives and accepts a Retention Money Guarantee exactly in the form stated he will instruct the Project Manager not to assess any amount be retained in terms of secondary Option X16.
The Contractor shall guarantee his ASGI-SA Obligations by providing the Employer with an ASGI-SA Guarantee in the form provided here.
[Note to contract compiler:  If there are no ASGI-SA Obligations in this contract, delete the above statement]

The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.  

Pro forma Retention Money Guarantee (may be used when Option X16 applies)

(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)
	Eskom Holdings SOC Limited

Megawatt Park

Maxwell Drive

Sandton

Johannesburg 
	Date:
	


Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]
Retention Money Guarantee: [Drafting Note: Name of Contractor to be inserted]
Project [  ] : Contract Reference:  [Drafting Note: Contractor contract reference number to be inserted]
1. In this Guarantee the following words and expressions shall have the following meanings:-

1.1 “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

1.2 “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

1.3 “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. ………. as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

1.4 “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

1.5 “Eskom” - means Eskom Holdings SOC Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30
1.6 “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

1.7 “Guaranteed Sum” - means the sum of R [●] ([●] Rand); [Drafting Note: Insert amount of Retention Money Guarantee.].

1.8 “Project” - means the…………………………………..

2. At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

3. A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

3.1 be signed on behalf of Eskom by a director of Eskom or his authorised delegate.
3.2 state the amount claimed (“the Demand Amount’);

3.3 state that the Contractor has failed to carry out his obligation(s) to rectify certain defect(s) for which he is responsible under the Contract (and the nature of such defect(s)) alternatively that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

4. Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

4.1 is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

4.2 is not, and shall not be construed to be, accessory or collateral on any basis whatsoever. 

5. The Bank’s obligations in terms of this Guarantee:

5.1 shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

5.2 shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed by the fact that a dispute may exist between Eskom and the Contractor.

6. Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract. 

7. Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

8. This Guarantee:

8.1 shall expire on the Expiry Date until which time it is irrevocable;

8.2 is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

8.3 shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

8.4 shall be regarded as a liquid document for the purpose of obtaining a court order; and

8.5 shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

8.6 Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

9. The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________

Date ____________  Bank’s seal or stamp
For and behalf of the Bank

Bank Signatory: ___________________

Bank Signatory: ___________________

Witness: ________________________

Witness: _________________________

Pro forma ASGI-SA Guarantee
(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)
	Eskom Holdings Limited

Megawatt Park

Maxwell Drive

Sandton

Johannesburg
	Date:
	


Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]
Pro-Forma ASGI-SA  Guarantee: [Drafting Note: Name of Contractor to be inserted]
Project [  ] Contract Reference: [●] [Drafting Note: Contractor contract reference number to be inserted]
1. In this Guarantee the following words and expressions shall have the following meanings:-

1.1 “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

1.2 “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

1.3 “Contract” – means the written agreement relating to the Project, entered into between the Employer and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. [●] as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

1.4 “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

1.5 “Contractor’s ASGI-SA Obligations” – means the Contractor’s ASGI-SA Obligations under and as defined in the Contract.

1.6 “Employer” - means Eskom Holdings Limited, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/06.

1.7 “Expiry Date” - means the [●] day of [●] 200[●]; [Drafting Note: anticipated date of issue of ASGI-SA Performance Certificate to be inserted.]

1.8 “Guaranteed Sum” - means the sum of R [●] ([●] Rand); 

1.9 “Project” – means the …………………………

2. At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of the Employer, as security for the proper performance by the Contractor of the Contractor’s ASGI-SA Obligations and hereby undertake to pay to the Employer, on written demand from the Employer received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

3. A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

3.1 state the amount claimed (“the Demand Amount’);

3.2 state that the Demand Amount is payable to the Employer in the circumstances contemplated in the Contract.

4. Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

4.1 is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

4.2 is not, and shall not be construed to be, accessory or collateral on any basis whatsoever. 

5. The Bank’s obligations in terms of this Guarantee:

5.1 shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

5.2 shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between the Employer and the Contractor.

6. The Employer shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract. 

7. Should the Employer cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then the Employer shall be entitled to cede to such third party the rights of the Employer under this Guarantee on written notification to the Bank of such cession.

8. This Guarantee:

8.1 shall expire on the Expiry Date until which time it is irrevocable;

8.2 is, save as provided for in 7 above, personal to the Employer and is neither negotiable nor transferable;

8.3 shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

8.4 shall be regarded as a liquid document for the purpose of obtaining a court order; and

8.5 shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the courts of the Republic of South Africa.

8.6 Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.
9. The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________

Date ____________________________

For and behalf of the Bank

Bank Signatory: ___________________

Bank Signatory: ___________________

Witness: ________________________

Witness: _________________________

Bank’s seal or stamp

Part 2: Pricing Data

ECC3 Option A
	Document reference
	Title
	No of pages

	C2.1
	Pricing assumptions: Option A
	     

	C2.2
	The activity schedule  
	     


C2.1 Pricing assumptions: Option A
1. How work is priced and assessed for payment
Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

	Identified and defined terms
	11

11.2
	(20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract.



	
	
	(27) The Price for Work Done to Date is the total of the Prices for 
· each group of completed activities and

· each completed activity which is not in a group.
A completed activity is one which is without Defects which would either delay or be covered by immediately following work.


	
	
	(30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract.



This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date. 
2. Function of the Activity Schedule
Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.  
3. Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.  

4. Preparing the activity schedule
Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly. 

It is assumed that in preparing his activity schedule the Contractor:
· Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

· Understands the function of the Activity Schedule and how work is priced and paid for;
· Is aware of the need to link the Activity Schedule to activities shown on his programme;
· Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;
· Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices. 
· Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event. 
An activity schedule could have the following format: 

	Item

No.
	Programme Reference
	Activity description
	Price

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	


C2.2 the activity schedule
	ESKOM REAL ESTATE PROJECT DELIVERY

	ESKOM ACADEMY OF LEARNING

	ELECTRICAL RETICULATION UPGRADE

	HIGH LEVEL SUMMARY

	 
	 
	 
	 
	 
	 

	ITEM
	DESCRIPTION
	UNIT
	QUANTITY
	RATE
	AMOUNT

	 
	 
	 
	 
	 
	 

	1
	ACTIVITY SCHEDULE 1:  PRELIMINARIES AND GENERAL
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 

	2
	ACTIVITY SCHEDULE 2: REPLACEMENT OF DB BOARDS
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 

	3
	ACTIVITY SCHEDULE 3: REPLACEMENT OF KIOSKS
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	TOTAL COST OF PROJECT (EXCL. VAT)
	 


	ITEM NO.
	 
	DESCRIPTION
	UNIT
	QUANTITY
	RATE
	AMOUNT

	ACTIVITY SCHEDULE 1:  Preliminaries and General

	 
	 
	The sums stated for items under this heading shall cover the cost of providing, establishing and commissioning on the site the facilities adequately equipped to enable all the work to commence and to proceed to completion as required in terms of the contract.
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Industry rates shall be obtained from suitable suppliers prior to pricing these P&Gs and only items to be required by the contractor for completion of the works shall be priced .
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	1
	 
	FIXED RELATED CHARGES
	 
	 
	 
	 

	 
	 
	These shall be the set up costs for the project and shall be aligned to size of project
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Establishment of facilities on site
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	1.1
	Fixed Charges
	Office and storage sheds
	Sum
	1
	 
	 

	1.2
	Fixed Charges
	Ablutions and latrine services
	Sum
	1
	 
	 

	1.3
	Fixed Charges
	Tools and Equipment
	Sum
	1
	 
	 

	1.4
	Fixed Charges
	Health & Safety File
	Sum
	1
	 
	 

	1.5
	Fixed Charges
	Medical tests / Induction training and clearances
	Sum
	1
	 
	 

	1.6
	Fixed Charges
	SHE Equipment (first aid box/fire equipment)
	Sum
	1
	 
	 

	1.7
	Fixed Charges
	Personal Protective Clothing
	Sum
	1
	 
	 

	1.8
	Fixed Charges
	Signs and barricading for laydown areas and workers eating area
	Sum
	1
	 
	 

	1.9
	Fixed Charges
	Quality Management Plan
	Sum
	1
	 
	 

	1.10
	Fixed Charges
	Site De-establishment
	Sum
	1
	 
	 

	1.11
	Fixed Charges
	Provide the scanning to identify the underground power cables and underground services
	Sum
	1
	 
	 

	1.12
	Fixed Charges
	Other fixed charge obligations (Specify items below)
	Sum
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	Sub Total carried to summary
	 

	 
	 
	 

	 
	 
	 
	 

	ITEM NO.
	 
	DESCRIPTION
	UNIT
	QUANTITY
	RATE
	AMOUNT

	
	
	TIME RELATED CHARGES
	
	
	
	

	 
	 
	Time related items shall be for the duration of the project
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	2.1
	Time Related Charges
	Operation and maintenance of facilities on site (offices and ablutions)
	Months
	8
	 
	 

	2.2
	Time Related Charges
	Supervision and management for duration of construction
	Months
	8
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	HEALTH AND SAFETY COST
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	All safety costs within the pricing schedule shall be aligned to the safety costs within the SHEQ costing submission
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	2.3
	Time Related Charges
	Full time registered health and safety officer for duration of contract
	Months
	8
	 
	 

	2.4
	Time Related Charges
	Maintenance of safety plans and audits
	Months
	8
	 
	 

	2.5
	Time Related Charges
	Maintenance of PPE and SHE Equipment
	Months
	8
	 
	 

	 
	 
	 
	 
	 
	 
	 

	2.6
	Time Related Charges
	Company and Head Office overhead costs 
	Months
	8
	 
	 

	2.7
	Time Related Charges
	Tools and Equipment
	Months
	8
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ENVIRONMENTAL COSTS
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	2.9
	Time Related Charges
	Waste Management for duration of project
	Months
	8
	 
	 

	2.10
	Time Related Charges
	Other time related obligations (Specify items below)
	Months
	8
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	DESIGNS
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	All hours shall be verified for the design works. Submission of hours shall be required.
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	Time Related Charges
	General arrangement drawings
	Hrs
	40
	 
	 

	 
	Time Related Charges
	Develop the layout drawings
	Hrs
	60
	 
	 

	 
	Time Related Charges
	Electrical single line diagrams
	Hrs
	40
	 
	 

	 
	Time Related Charges
	EAL reticulation network diagram 
	Hrs
	40
	 
	 

	 
	Time Related Charges
	Full detailed design work report
	Hrs
	40
	 
	 

	 
	Time Related Charges
	Assess and produce detailed design report (where applicable)
	Hrs
	40
	 
	 

	 
	Time Related Charges
	Assess and produce detailed report of the re-positioning of Kiosks (where applicable)
	Hrs
	80
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	PROFESSIONAL FEES
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Professional Fees shall be provided for the duration of the project
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	2.11
	Time Related Charges
	Electrical Engineer
	Months
	8
	 
	 

	2.13
	Time Related Charges
	Master Electrician
	Months
	8
	 
	 

	2.15
	Time Related Charges
	Project and Contracts Management
	Months
	8
	 
	 

	2.16
	Time Related Charges
	Other (please provide list below)
	Months
	8
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	Sub Total carried to summary
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	TOTAL COST OF PRICES (Excl Vat)
	 
	 
	 


	ITEM
	SANS 10142-1
	DESCRIPTION
	UNIT
	QTY
	RATE
	AMOUNT

	
	
	
	
	
	
	

	 
	 
	
	 
	 
	
	 

	 
	 
	ACTIVITY SCHEDULE 2: REPLACEMENT OF DB BOARDS
	 
	 
	
	 

	 
	 
	
	 
	 
	
	 

	 
	 
	ELECTRICAL WORK
	 
	 
	
	 

	 
	 
	
	 
	 
	
	 

	 
	 
	NOTES: All works shall comply with SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations) and Electrical Installation Regulation of the OHS Act, (Occupational Health and Safety Act, 1993 (Act 85 of 1993).
	 
	 
	
	 

	 
	 
	
	 
	 
	
	 

	 
	 
	This activity shall be filled in line with the Technical Specification of the project. The Activity Schedule shall not be used as an independent document. 
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	DISTRIBUTION BOARDS
	 
	 
	
	 

	 
	 
	All electrical equipment in the installation must be approved, South African Bureau of Standards (SABS). All electrical equipment must be installed in an approved manner, must be securely attached in place and suitably protected from little fingers gaining access. Pricing of DB Boards shall include associated wiring cost where applicable.
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	HI BAY

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ALTERATIONS
	 
	 
	 
	 

	2,1
	 
	Removal of all existing DB Boards and cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	REPLACEMENT OF DISTRIBUTION BOARDS
	 
	 
	 
	 

	2,2
	 
	DB BOARD 1
	No
	1
	 
	 

	2,3
	 
	DB BOARD 2
	No
	1
	 
	 

	2,4
	 
	DB BOARD 3
	No
	1
	 
	 

	2,5
	 
	DB BOARD 4
	No
	1
	 
	 

	2,6
	 
	DB BOARD 5
	No
	1
	 
	 

	2,7
	 
	DB BOARD 6
	No
	1
	 
	 

	2,8
	 
	DB BOARD 7
	No
	1
	 
	 

	2,9
	 
	DB BOARD 8.1
	No
	1
	 
	 

	2,10
	 
	DB BOARD 10
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ELECTRICAL CABLES
	 
	 
	 
	 

	2,11
	 
	Replacement of all Electrical cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	
	
	
	
	
	
	

	ITEM
	SANS 10142-1
	DESCRIPTION
	UNIT
	QTY
	RATE
	AMOUNT

	 
	 
	TESTING AND CERTIFICATION
	 
	 
	 
	 

	2,12
	 
	Commissioning, Testing and COC
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Sub Total Carried to Total
	 

	 
	 
	 
	 
	 
	 
	 

	MAIN BUILDING AREA

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ALTERATIONS
	 
	 
	 
	 

	3,1
	 
	Removal of all existing DB Boards and cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	REPLACEMENT OF DISTRIBUTION BOARDS
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	3,2
	 
	DB BOARD 6 - OPPOSITE S1
	No
	1
	 
	 

	3,3
	 
	DB Board 4A/C
	No
	1
	 
	 

	3,4
	 
	DB Board 42
	No
	1
	 
	 

	3,5
	 
	LOCAL MAIN
	No
	1
	 
	 

	3,6
	 
	DB Board 3A/C
	No
	1
	 
	 

	3,7
	 
	DB Board 21
	No
	1
	 
	 

	3,8
	 
	DB BOARD 23 - RECEPTION
	No
	1
	 
	 

	3,9
	 
	DB Board 25 
	No
	1
	 
	 

	3,10
	 
	DB BOARD 27 - CONGELLA
	No
	1
	 
	 

	3,11
	 
	DB Board 30
	No
	1
	 
	 

	3,12
	 
	DB Board 32
	No
	1
	 
	 

	3,13
	 
	DB Board 35 
	No
	1
	 
	 

	3,14
	 
	DB BOARD 37 - EDISSON B ROOM
	No
	1
	 
	 

	3,15
	 
	DB BOARD 39 - STAIRS
	No
	1
	 
	 

	3,16
	 
	DB BOARD 29 - DRAKENSBURG
	No
	1
	 
	 

	3,17
	 
	DB Board 5A/C
	No
	1
	 
	 

	3,18
	 
	DB BOARD 36 - VB & ASSOC
	No
	1
	 
	 

	3,19
	 
	DB BOARD 13 - S10 MAIN BUILDING 
	No
	1
	 
	 

	3,20
	 
	DB BOARD 4 - S76
	No
	1
	 
	 

	3,21
	 
	DB BOARD 8 - S45
	No
	1
	 
	 

	3,22
	 
	DB BOARD 9 - S11
	No
	1
	 
	 

	3,23
	 
	DB BOARD - FLOWER
	No
	1
	 
	 

	3,24
	 
	DB BOARD 01 - KITCHEN AND ADMIN
	No
	1
	 
	 

	3,25
	 
	DB BOARD 1 - EXHIBITION AREA
	No
	1
	 
	 

	3,26
	 
	DB BOARD 2 - EXHIBITION AREA
	No
	1
	 
	 

	3,27
	 
	DB BOARD 20 - AUDITORIUM
	No
	1
	 
	 

	3,28
	 
	DB BOARD 23A - RECEPTION AREA
	No
	1
	 
	 

	3,29
	 
	DB BOARD 23C - R30A
	No
	1
	 
	 

	3,30
	 
	DB BOARD 25 - J MAREE REGISTRATION
	No
	1
	 
	 

	3,31
	 
	DB BOARD 28 - CLEANING OFFICE
	No
	1
	 
	 

	3,32
	 
	DB BOARD 29A - DRAKENSBURG KITCHEN
	No
	1
	 
	 

	3,33
	 
	DB BOARD 3 - EXHIBITION AREA
	No
	1
	 
	 

	3,34
	 
	DB BOARD 3 - MAIN KITCHEN
	No
	1
	 
	 

	3,35
	 
	DB BOARD 30 - G-LEVEL
	No
	1
	 
	 

	3,36
	 
	DB BOARD 31 - O-LEVEL
	No
	1
	 
	 

	3,37
	 
	DB BOARD 33 - O-LEVEL
	No
	1
	 
	 

	3,38
	 
	DB BOARD 34 - B-LEVEL
	No
	1
	 
	 

	3,39
	 
	DB BOARD 4 - KITCHEN
	No
	1
	 
	 

	3,40
	 
	DB BOARD 42 - CONGELLA
	No
	1
	 
	 

	3,41
	 
	DB BOARD 4A - UMGENI
	No
	1
	 
	 

	3,42
	 
	DB BOARD 5 - KITCHEN
	No
	1
	 
	 

	3,43
	 
	DB BOARD 6 - KITCHEN
	No
	1
	 
	 

	3,44
	 
	DB BOARD 7 - UMGENI
	No
	1
	 
	 

	3,45
	 
	DB BOARD 7A - UMGENI LV ROOM
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ELECTRICAL CABLES
	 
	 
	 
	 

	3,46
	 
	Replacement of all Electrical cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	TESTING AND CERTIFICATION
	 
	 
	 
	 

	3,47
	 
	Commissioning, Testing and COC
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Sub Total carried to Total
	 

	 
	 
	 
	 
	 
	 
	 

	SIMULATOR BUILDING

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ALTERATIONS
	 
	 
	 
	 

	4
	 
	Removal of all existing DB Boards and cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	REPLACEMENT OF DISTRIBUTION BOARDS
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	4,1
	100A
	DB BOARD 11 - IT CONTROL ROOM - SIMULATOR 
	No
	1
	 
	 

	4,2
	100A
	DB BOARD 14 - V40 -  SIMULATOR 
	No
	1
	 
	 

	4,3
	63A
	DB BOARD 15 - OPPOSITE V35  - SIMULATOR 
	No
	1
	 
	 

	4,4
	100A
	DB BOARD 16 - OPPOSITE V44  - SIMULATOR  
	No
	1
	 
	 

	4,5
	100A
	DB BOARD 17 - OPPOSITE E17A - SIMULATOR 
	No
	1
	 
	 

	4,6
	100A
	DB BOARD 18 - MAIN PASSAGE - SIMULATOR 
	No
	1
	 
	 

	4,7
	150A
	DB BOARD 19 - E14B - SIMULATOR 
	No
	1
	 
	 

	4,8
	60A
	DB BOARD 20 - HORTICULTURE - SIMULATOR 
	No
	1
	 
	 

	4,9
	100A
	DB BOARD 13 - SIMULATOR 
	No
	1
	 
	 

	4,10
	100A
	DB BOARD 12- SIMULATOR 
	No
	1
	 
	 

	4,11
	63A
	DB BOARD X- SIMULATOR 
	No
	1
	 
	 

	4,12
	63A
	DB BOARD HALL C - SIMULATOR 
	No
	1
	 
	 

	 
	 
	 

	 
	 
	 
	 

	 
	 
	ELECTRICAL CABLES
	 
	 
	 
	 

	4,13
	 
	Replacement of all Electrical cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	4,14
	 
	TESTING AND CERTIFICATION
	 
	 
	 
	 

	4,15
	 
	Commissioning, Testing and COC
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	
	 
	 
	 
	 

	 
	 
	Sub Total carried to Total
	 

	 
	 
	 
	 
	 
	 
	 

	PODS/WORKSHOPS

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ALTERATIONS
	 
	 
	 
	 

	5
	 
	Removal of all existing DB Boards and cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	REPLACEMENT OF DISTRIBUTION BOARDS
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	POD 1
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	5,1
	 
	DB BOARD NO. 41
	No
	1
	 
	 

	5,2
	 
	DB BOARD NO. 43
	No
	1
	 
	 

	5,3
	 
	DB BOARD NO. 44
	No
	1
	 
	 

	5,4
	 
	DB BOARD NO. 45
	No
	1
	 
	 

	5,5
	 
	DB BOARD NO. 46
	No
	1
	 
	 

	5,6
	 
	DB BOARD NO. 47
	No
	1
	 
	 

	5,7
	 
	DB BOARD NO. 48
	No
	1
	 
	 

	5,8
	 
	DB BOARD NO. 49
	No
	1
	 
	 

	5,9
	 
	DB BOARD NO. 50
	No
	1
	 
	 

	5,10
	 
	DB BOARD NO. 51
	No
	1
	 
	 

	5,11
	 
	DB BOARD NO. 52
	No
	1
	 
	 

	5,12
	 
	DB BOARD NO. 53
	No
	1
	 
	 

	5,13
	 
	DB BOARD NO. 54
	No
	1
	 
	 

	5,14
	 
	DB BOARD NO. 55
	No
	1
	 
	 

	5,15
	 
	DB BOARD NO. 56
	No
	1
	 
	 

	5,16
	 
	DB BOARD NO. 57
	No
	1
	 
	 

	5,17
	 
	DB BOARD NO. 59
	No
	1
	 
	 

	5,18
	 
	DB BOARD NO. 60
	No
	1
	 
	 

	5,19
	 
	DB BOARD NO. 61
	No
	1
	 
	 

	5,20
	 
	DB BOARD NO. 62
	No
	1
	 
	 

	5,21
	 
	DB BOARD NO. 63
	No
	1
	 
	 

	5,22
	 
	DB BOARD NO. 66
	No
	1
	 
	 

	5,23
	 
	DB BOARD NO. 67
	No
	1
	 
	 

	5,24
	 
	DB BOARD NO. 68
	No
	1
	 
	 

	5,25
	 
	DB BOARD NO. 69
	No
	1
	 
	 

	5,26
	 
	DB BOARD NO. 70
	No
	1
	 
	 

	5,27
	 
	DB BOARD NO. 71
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	POD 2
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	5,28
	 
	COMPRESSOR 
	No
	1
	 
	 

	5,29
	 
	DB BOARD NO. 11
	No
	1
	 
	 

	5,30
	 
	DB BOARD NO. 12
	No
	1
	 
	 

	5,31
	 
	DB BOARD NO. 13
	No
	1
	 
	 

	5,32
	 
	DB BOARD NO. 14
	No
	1
	 
	 

	5,33
	 
	DB BOARD NO. 15
	No
	1
	 
	 

	5,34
	 
	DB BOARD NO. 18
	No
	1
	 
	 

	5,35
	 
	DB BOARD NO. 19
	No
	1
	 
	 

	5,36
	 
	DB BOARD NO. 20
	No
	1
	 
	 

	5,37
	 
	DB BOARD NO. 21
	No
	1
	 
	 

	5,38
	 
	DB BOARD NO. 22
	No
	1
	 
	 

	5,39
	 
	DB BOARD NO. 23
	No
	1
	 
	 

	5,40
	 
	DB BOARD NO. 26
	No
	1
	 
	 

	5,41
	 
	DB BOARD NO. 27
	No
	1
	 
	 

	5,42
	 
	DB BOARD NO. 28
	No
	1
	 
	 

	5,43
	 
	DB BOARD NO. 29
	No
	1
	 
	 

	5,44
	 
	DB BOARD NO. 30
	No
	1
	 
	 

	5,45
	 
	DB BOARD NO. 31
	No
	1
	 
	 

	5,46
	 
	DB BOARD NO. 32
	No
	1
	 
	 

	5,47
	 
	DB BOARD NO. 33
	No
	1
	 
	 

	5,48
	 
	DB BOARD NO. 36
	No
	1
	 
	 

	5,49
	 
	DB BOARD NO. 37
	No
	1
	 
	 

	5,50
	 
	DB BOARD NO. 38
	No
	1
	 
	 

	5,51
	 
	DB BOARD NO. 39
	No
	1
	 
	 

	5,52
	 
	DB BOARD NO. 40
	No
	1
	 
	 

	5,53
	 
	DB BOARD NO. 41
	No
	1
	 
	 

	5,54
	 
	DB BOARD NO. 42
	No
	1
	 
	 

	5,55
	 
	DB BOARD NO. 43
	No
	1
	 
	 

	5,56
	 
	DB BOARD NO. 44
	No
	1
	 
	 

	5,57
	 
	DB BOARD NO. 45
	No
	1
	 
	 

	5,58
	 
	DB BOARD NO. 46
	No
	1
	 
	 

	5,59
	 
	DB BOARD NO. 47
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	POD 3
	 
	 
	 
	 

	5,60
	 
	DB BOADRD NO 3  (A/C)
	No
	1
	 
	 

	5,61
	 
	DB BOARD NO. 12
	No
	1
	 
	 

	5,62
	 
	DB BOARD NO. 13
	No
	1
	 
	 

	5,63
	 
	DB BOARD NO. 14
	No
	1
	 
	 

	5,64
	 
	DB BOARD NO. 15
	No
	1
	 
	 

	5,65
	 
	DB BOARD NO. 16
	No
	1
	 
	 

	5,66
	 
	DB BOARD NO. 17
	No
	1
	 
	 

	5,67
	 
	DB BOARD NO. 18
	No
	1
	 
	 

	5,68
	 
	DB BOARD NO. 20
	No
	1
	 
	 

	5,69
	 
	DB BOARD NO. 21
	No
	1
	 
	 

	5,70
	 
	DB BOARD NO. 22
	No
	1
	 
	 

	5,71
	 
	DB BOARD NO. 23
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	POD 4
	 
	 
	 
	 

	 
	 
	
	 
	 
	 
	 

	5,72
	 
	COMPRESSOR
	No
	1
	 
	 

	5,73
	 
	DB 1
	No
	1
	 
	 

	5,74
	 
	DB 2
	No
	1
	 
	 

	5,75
	 
	DB 3
	No
	1
	 
	 

	5,76
	 
	DB 5
	No
	1
	 
	 

	5,77
	 
	DB 6
	No
	1
	 
	 

	5,78
	 
	DB 7
	No
	1
	 
	 

	5,79
	 
	DB 8
	No
	1
	 
	 

	5,80
	 
	DB 9
	No
	1
	 
	 

	5,81
	 
	DB 10
	No
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ELECTRICAL CABLES
	 
	 
	 
	 

	5,82
	 
	Replacement of all Electrical cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	TESTING AND CERTIFICATION
	 
	 
	 
	 

	5,83
	 
	Commissioning, Testing and COC
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Sub Total carried to Total Summary
	 

	 
	 
	 
	 
	 
	 
	 

	MISCELLANEOUS AREAS

	 
	 
	 
	 
	 
	 
	 

	 
	 
	ALTERATIONS
	 
	 
	 
	 

	6
	 
	Removal of all existing DB Boards and cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	REPLACEMENT OF DISTRIBUTION BOARDS
	 
	 
	 
	 

	 
	 
	
	 
	 
	 
	 

	6,10
	 
	SECURITY MAIN GATE 
	No
	1
	 
	 

	6,11
	 
	HV YARD 
	No
	1
	 
	 

	6,12
	 
	11KV MAIN SUBSTATION 
	No
	1
	 
	 

	6,13
	 
	SEWER PLANT 
	No
	1
	 
	 

	6,14
	 
	SEWER PLANT 
	No
	1
	 
	 

	6,15
	 
	TRADE TEST CENTER 
	No
	1
	 
	 

	6,16
	 
	VODACOM TOWER 
	No
	1
	 
	 

	6,17
	 
	WATER TOWER 
	No
	1
	 
	 

	6,18
	 
	SMALL GATE 
	No
	1
	 
	 

	 
	 
	
	 
	 
	 
	 

	 
	 
	ELECTRICAL CABLES
	 
	 
	 
	 

	6,19
	 
	Replacement of all Electrical cabling
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	TESTING AND CERTIFICATION
	 
	 
	 
	 

	6,20
	 
	Commissioning, Testing and COC
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Sub Total carried to Total Summary
	 

	EARTHING AND LIGHTNING PROTECTION

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	7
	 
	LEGENDS
	 
	 
	 
	 

	7,1
	 
	Re-generate and reproduce the Legends for each individual DB’s, Sub DB’s and Kiosks
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	LIGHTNING PROTECTION
	 
	 
	 
	 

	7,2
	 
	Existing earthing and lightning protection system for the buildings shall be inspected, repaired, tested, and certified
	Item
	1
	 
	 

	 
	 
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 
	 

	 
	 
	
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 
	Sub Total carried to Total Summary
	 

	
	
	
	
	
	
	

	 
	TOTAL FOR DB BOARDS (EXCL. VAT)
	 

	
	
	 

	
	
	 


	ITEM
	SANS 10142-1
	DESCRIPTION
	UNIT
	QTY
	RATE
	AMOUNT

	 
	 
	ACTIVITY SCHEDULE 3: REPLACEMENT OF KIOSKS
	 
	 
	
	 

	 
	 
	
	 
	 
	
	 

	 
	 
	All materials that will be removed shall be disposed off by the contractor.
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	ALTERATIONS
	 
	 
	
	 

	 
	 
	
	 
	 
	
	 

	1,0
	 
	Removal of existing Kiosks
	Item
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	KIOSK REPLACEMENT
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	1,1
	 
	Finesse Building
	 
	 
	
	 

	1.1.1
	 
	Kiosk 1
	No.
	1
	
	 

	1.1.2
	 
	Kiosk 2
	No.
	1
	
	 

	1.1.3
	 
	Kiosk 3
	No.
	1
	
	 

	1.1.4
	 
	Kiosk 4
	No.
	1
	
	 

	1.1.5
	 
	Finesse  kitchen 
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,2
	 
	Lethabo kiosk 
	 
	 
	
	 

	1.2.1
	 
	Lethabo kiosk 
	No.
	5
	
	 

	 
	 
	 
	 
	 
	
	 

	1,3
	 
	House  Keeping
	 
	 
	
	 

	1.3.1
	 
	House  Keeping
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,4
	 
	Grootvlei
	 
	 
	
	 

	1.4.1
	 
	Grootvlei
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,5
	 
	Lapa
	 
	 
	
	 

	1.5.1
	 
	Kiosk 1
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,6
	 
	Sewage plant 
	 
	 
	
	 

	1.6.1
	 
	Kiosk C
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,7
	 
	Matimba Accommodation
	 
	 
	
	 

	1.7.1
	 
	Kiosk 9
	No.
	1
	
	 

	1.7.2
	 
	Kiosk 10
	No.
	1
	
	 

	1.7.3
	 
	Kiosk 11
	No.
	1
	
	 

	1.7.4
	 
	Kiosk 12
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,8
	 
	Majuba Accommodation
	 
	 
	
	 

	1.8.1
	 
	Kiosk 13
	No.
	1
	
	 

	1.8.2
	 
	Kiosk 14
	No.
	1
	
	 

	1.8.3
	 
	Kiosk 15
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	1,9
	 
	Hendrina
	 
	 
	
	 

	1.9.1
	 
	Hendrina
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,0
	 
	Koeberg Building
	 
	 
	
	 

	2,01
	 
	Kiosk No.16
	No.
	1
	
	 

	2,02
	 
	Kiosk No.17
	No.
	1
	
	 

	2,03
	 
	Kiosk No.18
	No.
	1
	
	 

	2,04
	 
	Kiosk No.19
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,1
	 
	Kendal Accommodation
	 
	 
	
	 

	2.1.1
	 
	Kiosk 1
	No.
	1
	
	 

	2.1.2
	 
	Kiosk 1A
	No.
	1
	
	 

	2.1.3
	 
	Kiosk No 3
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,2
	 
	Isithupha Houses
	 
	 
	
	 

	2.1.2
	 
	Kiosk No 1
	No.
	1
	
	 

	2.1.2
	 
	Kiosk No D
	No.
	1
	
	 

	2.1.3
	 
	Kiosk No 2
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,2
	 
	Parameter Fencing
	 
	 
	
	 

	2.2.1
	 
	Kiosk 1
	No.
	1
	
	 

	2.2.2
	 
	Kiosk 2
	No.
	1
	
	 

	2.2.3
	 
	Kiosk 3
	No.
	1
	
	 

	2.2.4
	 
	Kiosk 4
	No.
	1
	
	 

	2.2.5
	 
	Kiosk 5
	No.
	1
	
	 

	2.2.6
	 
	Kiosk 6
	No.
	1
	
	 

	2.2.7
	 
	Kiosk 7
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,3
	 
	Main Substation
	 
	 
	
	 

	2.3.1
	 
	Kiosk 1
	No.
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	2,4
	 
	CONSUMPTION METERS
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	2.4.1
	 
	Supply and installation of complete electrical consumption meters on new electrical Kiosks
	No.
	42
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	Sub Total for Kiosks Replacement
	 

	 
	 
	 
	 
	 
	
	 

	3
	SANS 1200
	CIVILWORKS
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	3,1
	 
	Breaking and removal of existing plinths 
	Item
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	3,2
	 
	Remove paving where applicable for reuse
	Item
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	3,3
	 
	Strip off top soil and compact
	m²
	360
	
	 

	 
	 
	 
	 
	 
	
	 

	3,4
	 
	Backfilling under plinth and above
	m³
	72
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	PRECAST CONCRETE
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	3,5
	 
	Precast concrete plinths
	No.
	42
	
	 

	 
	 
	 
	 
	 
	
	 

	 
	 
	PAVING
	 
	 
	
	 

	3,6
	 
	Replacement of paving put aside for reuse
	Item
	1
	
	 

	 
	 
	 
	 
	 
	
	 

	3,7
	 
	Allow provisional sum of R75,000.00 (Seventy five thousand) for new paving
	Item
	1
	R 75 000,00
	R 75 000,00

	 
	 
	 
	 
	 
	
	 

	 
	 
	STEEL
	 
	 
	
	 

	3,8
	 
	Allow provisional sum of R100,000.00 (hundred thousand) for steel plinths where applicable.
	Item
	1
	R 100 000,00
	R 100 000,00

	 
	 
	 
	 
	 
	
	 

	 
	 
	RELOCATION WORKS
	 
	 
	
	 

	 
	 
	 
	 
	 
	
	 

	3,9
	 
	Allow provisional sum of R1,500 000.00 (one million rand) for possible relocation of Kiosks
	Item
	1
	R 1 500 000,00
	R 1 500 000,00

	 
	 
	 
	 
	 
	
	 

	 
	SUBTOTAL CARRIED TO SUMMARY
	 

	
	
	
	
	
	
	

	 
	TOTAL COST CARRIED TO SUMMARY
	 


Part 3: Scope of Work

	Document reference
	Title
	No of pages

	
	This cover page
	

	C3.1
	Employer’s Works Information
	38


	C3.2
	Contractor’s Works Information

(insert at award stage or delete if not applicable)
	1

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	Total number of pages
	39


C3.1: Employer’s works Information

Contents

1Part 3: Scope of Work

C3.1: Employer’s works Information
2
1
Description of the works
5
1.1
Executive overview
5
1.2
Employer’s objectives and purpose of the works
5
1.3
Interpretation and terminology
5
2
Management and start up.
5
2.1
Management meetings
5
2.2
Documentation control
6
2.3
Health and safety risk management
6
2.4
Environmental constraints and management
7
2.5
Quality assurance requirements
7
2.6
Programming constraints
7
2.7
Contractor’s management, supervision and key people
7
2.8
Invoicing and payment
7
2.9
Insurance provided by the Employer
8
2.10
Contract change management
8
2.11
Provision of bonds and guarantees
8
2.12
Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor
8
2.13
Training workshops and technology transfer
8
3
Engineering and the Contractor’s design
9
3.1
Employer’s design
9
3.2
Parts of the works which the Contractor is to design
9
3.3
Procedure for submission and acceptance of Contractor’s design
9
3.4
Other requirements of the Contractor’s design
9
3.5
Use of Contractor’s design
9
3.6
Design of Equipment
9
3.7
Equipment required to be included in the works
10
3.8
As-built drawings, operating manuals and maintenance schedules
10
4
Procurement
11
4.1
People
11
4.1.1
Minimum requirements of people employed on the Site
11
4.1.2
BBBEE and preferencing scheme
11
4.1.3
Accelerated Shared Growth Initiative – South Africa (ASGI-SA)
11
4.2
Subcontracting
11
4.2.1
Preferred subcontractors
11
4.2.2
Subcontract documentation, and assessment of subcontract tenders
11
4.2.3
Limitations on subcontracting
12
4.2.4
Attendance on subcontractors
12
4.3
Plant and Materials
12
4.3.1
Quality
12
4.3.2
Plant & Materials provided “free issue” by the Employer
12
4.3.3
Contractor’s procurement of Plant and Materials
12
4.3.4
Spares and consumables
12
4.4
Tests and inspections before delivery
13
4.5
Marking Plant and Materials outside the Working Areas
13
4.6
Contractor’s Equipment (including temporary works).
13
4.7
Cataloguing requirements
13
5
Construction
14
5.1
Temporary works, Site services & construction constraints
14
5.1.1
Employer’s Site entry and security control, permits, and Site regulations
14
5.1.2
Restrictions to access on Site, roads, walkways and barricades
14
5.1.3
People restrictions on Site; hours of work, conduct and records
14
5.1.4
Health and safety facilities on Site
14
5.1.5
Environmental controls, fauna & flora, dealing with objects of historical interest
14
5.1.6
Title to materials from demolition and excavation
14
5.1.7
Cooperating with and obtaining acceptance of Others
15
5.1.8
Publicity and progress photographs
15
5.1.9
Contractor’s Equipment
15
5.1.10
Equipment provided by the Employer
15
5.1.11
Site services and facilities
15
5.1.12
Facilities provided by the Contractor
15
5.1.13
Existing premises, inspection of adjoining properties and checking work of Others
15
5.1.14
Survey control and setting out of the works
16
5.1.15
Excavations and associated water control
16
5.1.16
Underground services, other existing services, cable and pipe trenches and covers
16
5.1.17
Control of noise, dust, water and waste
16
5.1.18
Sequences of construction or installation
16
5.1.19
Giving notice of work to be covered up
16
5.1.20
Hook ups to existing works
16
5.2
Completion, testing, commissioning and correction of Defects
17
5.2.1
Work to be done by the Completion Date
17
5.2.2
Use of the works before Completion has been certified
17
5.2.3
Materials facilities and samples for tests and inspections
17
5.2.4
Commissioning
17
5.2.5
Start-up procedures required to put the works into operation
17
5.2.6
Take over procedures
18
5.2.7
Access given by the Employer for correction of Defects
18
5.2.8
Performance tests after Completion
18
5.2.9
Training and technology transfer
18
5.2.10
Operational maintenance after Completion
18
6
Plant and Materials standards and workmanship
19
6.1
Investigation, survey and Site clearance
19
6.2
Building works
19
6.3
Civil engineering and structural works
19
6.4
Electrical & mechanical engineering works
20
6.5
Process control and IT works
20
6.6
Other [as required]
20
7
List of drawings
21
7.1
Drawings issued by the Employer
21
C3.2
Contractor’s Works Information
22


1 Description of the works
1.1 Executive overview 
The requirements include replacement all EAL Distribution Boards, Sub-Distribution Boards, Kiosks and ensuring work performed safely complies to SANS 10142-1 (The Wiring of Premises - Part 1: Low- voltage Installations) and the Electrical Installation Regulation of the OHS Act, (Occupational Health and Safety Act, 1993 (Act 85 of 1993).

The Eskom Academy of Learning (EAL) site comprises of 39 buildings, which require safe and efficient electrical supplies. EAL Main building, Finesse building, Workshops, Simulator Building, Administrative center buildings, Accommodation buildings, Fire Protection Pump Station, and Water Treatment Plant. The Electrical Installation regulations have changed considerably since the time that the EAL site was constructed. As a result, the site does not comply with the SANS and OHS act. The vast majority of the EAL Kiosks require full replacement this is due to their hazardous conditions. The EAL Electrical installation has many outdated, defective, and irregular-sized components that pose a risk of failure to protect human life in case of emergency and/or to respond slowly to prevent damage to property/Equipment in case of malfunctions/overcurrent.
The scope of work is as follows:
•
Replacement all distribution boards, sub-distribution boards and kiosks at EAL to comply with the SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations). The installation shall be tested, and a certificate of compliance shall be issued per distribution, sub board and kiosk.

•
Production of full detailed design work report.

•
Provision of the electricity metering. Currently there are no meters installed in the distribution boards (DBs). Sub energy metering shall be allowed for on the main incomers DB/Kiosk per building. The kWh sub metering will monitor the electrical consumption per building. Install separate meters for lighting, general power and equipment be installed to facilitate and record better energy usage. Separate meters to be included on single line diagrams. Provide board load metering per phase for on the single line diagrams to aid energy management. Every meter is supplied with a Building Management System (BMS) interface module capable of communication on a BACNet TCP-IP protocol.

•
Provide General arrangement drawings (GA) for each Kiosks, Distribution boards and Sub- Distribution boards connections.

•
Conduct the tests and issue electrical Certificate of Compliance (CoC) by a qualified, registered electrician. The purpose of this certificate is to prove that all the electrical work and installations are in safe, good working order, and up to standard. The SANS10142-1 electrical installation regulations comprise of an entire book of regulations and the Occupational Health and Safety Regulations.

•
Develop the layout drawings indicating the positioning of the Lights, Isolators, plugs. The positions of the distribution, sub boards and kiosks shall be indicated on the layout drawings.

•
Production of Electrical single line diagrams (from each mini-substation, kiosk up to distribution, and sub-distribution boards level).

•
Conduct the full design base verification of the entire EAL reticulation network diagram and produce a single line network reticulation diagram.

•
Provide the accurate ratings of all the DB’s and Kiosks including their components. The technical data must include all “As Is” electrical drawings and on completion of the works, produce the “As built” electrical circuit wiring diagrams with detailed component, circuit breaker types, ratings, and sizes.

•
Work should always be subject to full time supervision by a qualified and experienced site Eskom electrical technician.

•
Re-generate and reproduce the Legends for each individual DB’s, Sub DB’s and Kiosks for the entire EAL site.  Comprehensive, neatly legends card identifying all circuits.

•
Compile the data sheet for all LV cables feeding from mini-substation, kiosks to distribution boards and sub-distribution boards.

•
Produce a detailed design report for EAL DB’s, Sub-DB’s and Kiosks indicating the “As Is” and “As built” accurate components list.

•
Distribution boards and Kiosks requirements, such as kA ratings, space limitations and colour requirements, to be made available on the “As Built” single line and wiring diagrams.

•
Produce list and cost of all components that require urgent replacement to prevent business operations disruptions.

•
Build new concrete and metal plinths of the Kiosks to meet the relevant standards and regulations.

•
Assess and produce detailed report of the re-positioning of all the Kiosks located where there is soil erosion or non-compliant in accordance with SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations) and give recommendations with cost for repositioning.

•
Label all EAL DB’s, Sub-DB’s and Kiosks. Clearly engraved labels are to be provided below the relevant isolators, sockets, and circuit breakers. An engraved label is to be provided on the outside of the doors indicating the name of the distribution board and Kiosk. Distribution board signage such as danger signs shall be included in accordance with relevant regulations.

•
The existing earthing and lightning protection system for the buildings shall be inspected, repaired, tested, and certified. Earthing for the electrical system shall be provided in accordance with SANS 10292.

•
Earthing, bonding, and lightning protection. The Contractor shall ensure that all earth continuity conductors and earth busbars on all distribution, sub-distribution boards and kiosks are connected to the main earth system via the earthing of each supply cable. The building shall be properly earthed according to SANS 10313 and SANS 62305.

•
The front face of the distribution boards, sub-distribution boards and kiosks shall be secured by means of appropriate slot or square key catches.

•
Provide the scan to identify the underground power cables and underground services

•
Provide a list of strategic spares with costs.

The Purpose of Works include the following:
The purpose of this document is to describe the functional requirements that must be met by the Contractor to replace, test and issue CoC’s and detailed Electrical network diagrams of the EAL Kiosks, Distribution Boards and Sub-Distribution Boards including associated cables. The test report shall be in the format approved by the chief inspector, in respect of every electrical installation. The test results report and “As built” technical data, including the layout and wiring diagrams will be reviewed by the Employer for acceptance. The detailed designs will be used on a day-to-day basis for plant operation and maintenance purposes. The scope of this document applies to Electrical distribution boards, Sub-Distribution boards and kiosks EAL site environment.

•
Fulfil the legal obligation to ensure that all electrical Installation is of a good quality standard.

•
Safe for use by humans and it may not cause a negative environmental impact.

•
Conduct design base verification and provide detailed design report per distribution, sub distribution boards and kiosks.

•
All works shall comply with SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations) and Electrical Installation Regulation of the OHS Act, (Occupational Health and Safety Act, 1993 (Act 85 of 1993).

•
Production of “As is” and “As built” drawings

•
The design data is identified and is based on the following criteria:

· What is the equipment?

· What is the equipment connected to?

· How is the equipment identified?

· What is the respective size of the Kiosks, Distribution Boards and Sub-Distribution Boards.

The electrical certificate shall cover:

•
Everything in the main kiosks, distribution boards, and any sub distribution boards, circuit breakers, earth leakage etc.

•
The earthing system and connectivity throughout the installation.

•
Bonding of all metal components.

•
The socket outlets and light switches.

•
All isolators for fixed appliances.

•
All the cables from the mains incoming points, Switchgear, Kiosks to the main distribution board, sub boards and kiosks.

•
All the cabling from the distribution boards to switches and plugs (including the wall plugs and light switches, through to the connection at the lights).

•
All circuits and wiring to any fixed appliances, even if they are plugged into a wall socket (excluding the actual appliance itself).

•
Positioning of electrical equipment (e.g., light switches and plugs that may not be within a certain distance of taps, shower, baths etc.).

•
Mains switch and their accessibility within a certain height from the floor in case of emergencies.

•
Ensuring that all electrical equipment in the installation is approved by SABS or other relevant approvals and be of the correct type and rating for the application.

•
Ensuring that all electrical equipment must be installed in an approved manner.

•
Ensuring that all electrical equipment is securely attached in place and suitably protected from little fingers gaining access.

•
Ensuring that all parts of the permanent electrical installation is in good working order (including safety features); and lastly,

•
An electrician will also take various readings to ensure that voltages, insulation, earthing, and other values adhere to regulatory requirements.

•
Calibration certificates for energy meters supplied and installed.

The scope of works includes the design base verification, detail design replacement report, production of layout drawings, single line diagrams, of the EAL Electrical Switchgear, Kiosks and Distribution boards (DB’s), including sub-distribution boards, at Eskom Academy of Learning complex.

The purpose of the project is to provide an assurance that the electrical wiring and installations of the site are safe and in order. The Electrical Installation Regulations (“the Regulations”), promulgated under section 43 of the Occupational Health and Safety Act 85 of 1993, obliges every user or lessor of an electrical installation to have a valid certificate of compliance under regulation 7(1):

“Subject to the provisions of sub regulation (3), every user or lessor of an electrical installation, as the case may be, shall have a valid certificate of compliance for that installation in the form of Annexure 1, which shall be accompanied by a test report in the format approved by the chief inspector, in respect of every such electrical installation.”

Under section 1 of the Regulations a “certificate of compliance” means:

“(a) a certificate with a unique number obtainable from the chief inspector, or a person appointed by the chief inspector, in the form of Annexure 1, and issued by a registered person in respect of an electrical installation or part of an electrical installation; or

(b) a certificate of compliance issued under the Electrical Installation Regulations, 1992”

•
All work shall be executed and supervised by suitably qualified staff. Only “ACCREDITED PERSONS” shall be permitted to carry out and supervise work.

•
The Contractor shall always have an adequate number of employees available during the works period to ensure that the work does not delay the construction programme.

•
The works shall be supervised by a full time registered “MASTER ELECTRICIAN”. A valid electrical certificate of compliance (CoC) issued by a registered person as prescribed by Clause 9 of the Electrical Installation Regulations of 2009 is proof that your electrical installation complies with the minimum safety standard.

1.2 Employer’s objectives and purpose of the works
The objectives and purpose of the Works is to do replacement, test, and issue CoC’s at EAL site Distribution, Sub-Distribution Boards and Kiosks system, produce detailed replacement reports per building and produce the “As built” electrical layout, and wiring diagrams, Compliance with electrical wiring code (SANS 10142-1) for protection of people, animals, and property when it comes to electrical installations. Ensure installation as well as materials to be repaired/replaced to comply with Electrical Installation Safety Standards as outlined in Electrical Installation Regulation GNR.242 of 6 March 2009 and as stipulated in SANS10142-1.

· Fulfil the legal obligation to ensure that all electrical Installation is of a good quality standard.

· Safe for use by humans and it may not cause a negative environmental impact.

1.3 Interpretation and terminology
The following abbreviations are used in this Works Information:

	Abbreviation
	Description

	AC
	Alternating Current

	DC
	Direct current

	BMS
	Building Management System

	CAPEX
	Capital Expenditure

	C&I
	Control and Instrumentation

	EMaP
	Engineering Management Plan

	LPS
	Low Pressure Services

	OEM
	Original Equipment Manufacturer


The following definitions are used in this Works Information:
	Definition
	Description

	Acceptance
	The Employer accept the condition or design but does not take responsibility from the Contractor

	Architect Engineer
	Architect Engineer - When Eskom acts as the Architect Engineer on a project/package/plant/system/asset, the reviewer(s) shall review the design documentation issued by the Design Authority to ensure that: the design satisfies the stakeholder requirements (i.e. validation of design deliverables against stakeholder requirements); the design is integrated by identifying all interfaces with other packages/plant systems/assets and ensuring that these interfaces are catered for; foreseen technical risks are identified and addressed/challenged with the Design Authority; general technical oversight is

provided over the design.

	Approval
	Written agreement or authorization by Employer. All requests for approval must

be submitted in writing and any proposed deviation from specified requirements must be fully justified and agreed by Employer.

	Client
	The end user will be Eskom who will be represented by Eskom Real Estate throughout the duration of the Project.

	Contractor
	Refers to the corporation appointed to perform the detailed design, plant and material selection, shop/construction drawings, procurement, and construction works required for Eskom Academy of Learning Refurbishment Project.

	Design Authority
	Design Authority - When Eskom acts as the Design Authority on a project/package/plant/system/asset, the reviewer(s) shall review the design documentation to ensure that: the design satisfies the design requirements; all relevant Eskom design standards, procedures and guidelines have been adhered to; the design is suitable and correct (calculations, philosophy, functionality, etc.); best Engineering practices were applied; the design is integrated by identifying all interfaces with other packages/plant

systems/assets and ensuring that these interfaces are catered for.


	Design freeze
	Is a binding decision that defines the whole product, its parts or parameters and allows the continuation of the design based on that decision (no further changes can be made to the design, it is cut-off for the engineers)

	Design Base
	The Design Base is defined as the set of information that the engineering function deems material to describe the system design and the evolving design of an asset to ensure that the asset fulfils its intended purpose.

	Employer
	Refers to Eskom Holdings State Owned Company

	Eskom Plant Engineering
	Refers to the Eskom Engineering team who will perform the reviews and provide technical assistance for the work performed by the appointed Contractor/

	Interface
	Interface in these document means either to hard wired or software interaction between the Contractor and/or other Works

	Owners Engineer
	Owners Engineer - When Eskom acts as the Owners Engineer on a project/package/plant/system/asset, the reviewer(s) shall review the design documentation issued by the Design Authority to ensure that: the design satisfies the stakeholder requirements (i.e. validation of design deliverables against stakeholder requirements). General technical oversight is provided over the design.

	Plant Equipment
	An item performing a particular purpose as part of a system (Site Infrastructure).

	Site Infrastructure
	Refers to Eskom Academy of Learning All Electrical Kiosks, Distribution Boards, and Sub-Distribution Boards installed in all EAL buildings, sewage plant, Fire Protection pump station, and other pump stations around the EAL site. This includes the Civil and Structural, Electronics, Electrical System

required to support the works.

	Specification
	The document/s forming part of the contract in which the methods of executing the various items of work to be done is described, as well as the nature and quality of the materials to be supplied and it includes technical schedules and

drawings attached thereto as well as all samples and patterns

	System
	An integrated set of constituent pieces that are combined in an operational or support environment to accomplish a defined objective. These pieces include people, hardware, software, firmware, information, procedures, facilities,

services and other support facets.


2 Management and start up.

2.1 Management meetings

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

	Title and purpose
	Approximate time & interval
	Location
	Attendance by:

	Risk register 
	Weekly 
	Eskom Academy of Learning
	Employer, Contractor, Supervisor, and Designing team

	Overall contract progress and feedback
	Weekly  
	Eskom Academy of Learning
	Employer, Contractor, Supervisor, and Designing team

	Compensation events
	When required
	Eskom Academy of Learning
	Employer, Contractor, Supervisor, and Designing team

	Look ahead schedule etc
	Fortnightly 
	Eskom Academy of Learning
	Employer, Contractor, Supervisor, and Designing team


Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.  
All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.  

2.2 Documentation control
All contractual communications will be in the form of properly compiled letters or forms attached to e-mails and not as a message in the e mail itself. All of which will be copied to the Principal Agent/ Project Manager.

The Contractor will submit the following documents to the Employer for review, the Employer will review the documents for acceptance and inform the Contractor if the documents have been accepted or if it is not accepted and stating the reasons of not the accepting the documentation. The Employer will give the Contractor reasonable time which will be agreed to between the Contractor and the Employer to respond or re-submit the documents.

The documents are as follows:
	Title and purpose
	Frequency

	Weekly plan
	Every Monday of the week

	Weekly progress report, reporting on actual work completed.
	Every Friday of the week, reporting on the previous week’s progress

	Three weeks look ahead plan – detailing planned activity during the period
	Monthly

	Risk Register
	Monthly

	Power application permit
	When required

	Permit to perform work related to civil
	When required


All documents shall be drawn as specified by the Eskom Engineering Drawing Standard – Common Requirements, the document number is 240-8697350. In addition, a document list shall be delivered in Microsoft Excel format that contains the following fields: “document name”, “document type”, “version number”, “date created” and “created by”.
2.3 Health and safety risk management
The Contractor/tenderer is expected to comply to the following documents when working at/rendering a service to Eskom but not limited to the following:

a. Occupational Health and Safety Act 85 of 1993 and its Regulations (OHS Act)

b. Disaster Management Act, no 57 of 2002.

c. Safety, Health and Environmental requirements contained in the SHE Specification for Contractors.

d. Eskom SHEQ Policy, Standards, Procedures, Guidelines, Specifications and Regulations as listed below:


i. Eskom Safety, Health, Environmental and Quality Policy: 32-727 


ii. Eskom Lifesaving Rules, Directive: 32-421 


iii. Eskom Procedure on Smoking: 32-36 


iv. Eskom Incident Management Procedure 32-95 (latest revision) 


v. Implementation of Occupational Hygiene management programme, Standard 240-42262670 


vi. Eskom Life Saving Rules, Directive: 240- 62196227 


vii. Eskom vehicle and driver safety management 32-93 


viii. Eskom vehicle specification 32-345 


ix. Eskom Contractor Health and Safety requirements standards 32-136 


x. Employees’ right of refusal to work in an unsafe situation 240-43848327 


xi. Eskom Waste Management Standard 32-245 


xii. Annexure B: Acknowledgement Form for Eskom SHE Rules and other Requirements 
Appendix A The Contractor requests all applicable Eskom procedures & requirements. The Contractor ensures safety awareness at all times through continuous training. The Contractor, at all times is responsible for the supervision of his employees, agents, Subcontractors and takes full responsibility and accountability for ensuring they are competent, compliant and aware of the legal requirements and other requirements and execute the works accordingly. 
The Contractor ensures that all statutory appointments and appointments required by any Eskom Regulations are made in writing and that all appointees fully understand their responsibilities and are trained and competent to execute their duties.
The Divisional Safety Risk Managers who will be responsible for the allocation of resources to assist P&SCM with the above processes are as follows:

·         Generation: Roley McIntyre

·         Transmission: Tony Patterson

·         Distribution: Alex Stramrood

·         Enterprises: Jace Naidoo

·         Corporate: Kerseri Pather
The Contractor shall comply with the health and safety requirements contained in Annexure ___________ to this Works Information.
2.4 Environmental constraints and management
Describe or cross refer to environmental constraints applicable to the Contractor’s design and his activities on Site and how they should be managed.  Include here or cross refer to an Annexure to the Works Information. 

In terms of the Minimum Requirements for Environmental Management System, ISO 14001: 2015, which certification is not required but the Supplier or Contractor must comply with the following requirement:
1. The contractor must develop an environmental policy that adheres to the following specifications.
Integration: The policy can either be integrated with safety or remain a stand-alone document

Commitments: The policy must comply all relevant environmental legislation and laws, the contractor must ensure strict adherence to all national, local and international environmental regulations and laws throughout the project.

Approval: The environmental policy must be signed off by a Senior company Member, such as Managing Director or the CEO, to ensure top level commitment.

2. Appointment and Responsibilities:  
The contractor must appoint the dedicated environmental representative. This individual will be responsible for overseeing all environmental activities and ensuring that project construction activities are managed in accordance with the outlined environmental standards and regulations.

3. Environmental Management Plan:
The contractor must develop a comprehensive Environmental Management Plan (EMP) or an Aspects and Impacts Register. This plan should detail the strategies and measures for managing environmental activities throughout the project lifecycle.

The plan must address the management and disposal of both general and hazardous waste, including but not limited to asbestos, in compliance with the National Environment Waste Act.

4. Waste Management:

General and Hazardous Waste:
The contractor must ensure that the waste generated during the project is managed and disposed of in accordance with the applicable legislation.

Disposal Requirements:
All waste, including hazardous materials must be disposed od at registered landfill site.

The contractor must provide the disposal certificates for all the waste disposed of

The contractor must have all the necessary permits including the transportation permits for hazardous materials as per the applicable legislation.

The contractor must maintain detailed records of waste management activities including disposal certificates and permits.

5. Environmental Emergency Preparedness Plan:

The contractor must Develop and implement and Environmental Emergency Preparedness Plan which will outline the identification of potential environmental Incidents, outlining the protocols to be followed in the event of environmental incidents, Contingency measures which will be taken to minimise the impacts of any environmental incident, Communication plan to inform all relevant stakeholders, including emergency services, and statutory authorities in the event of an incident.

All environmental incidents are reported to the Employer within 24 hours of such occurrence. All environmental incidents occurring on the Project Site (or on any other places, if any, as may be specified under the Contract as forming part of the Site) are recorded, detailing how each incident was dealt with in an Environmental Incident register. 

The Contractor shall construct and/or implement all the necessary environmental protection measures in each area before any production work will be allowed to proceed. The Employer may suspend the Works at any time in terms the Conditions of Contract should the Contractor, in the Employer’s opinion, fail to implement, operate or maintain any of the environmental protection measures adequately.

The Contractor shall comply with the environmental criteria and constraints stated in Annexure ________

2.5 Quality assurance requirements

The Contractor complies to the following documents when working at/rendering a service to Eskom but not limited to the following: 

i.  240-12248652 - List of Tender Returnable/Quality Requirement Document

ii. 240-68099512 - FORM A: Tender & Contract Quality Requirements For QM 58 and Quality Requirements For ISO 9001 Standard
iii. 240-105658000 (QM 58)- Supplier Quality Management: Specification

iv. 240-109253698- Contract Quality Plan (CQP)

v. 240-109253302- Quality Control Plan (QCP)/ Inspection and Test Plan (ITP)

After the acceptance of the construction drawings the contractor submits the associated construction Method Statements and relevant QCP/ITP for acceptance and determination of intervention points prior to construction. 

Failure to comply with an accepted Method Statement/QCP or ITP may result the issuing of a NCR, rejection of the works as well as the withholding of payment until the appropriate remedial actions have occurred.

1.
The Contractor demonstrates, provide and maintains a Quality Management System that is ISO 9001:2008 certified or compliant thereto. Compliance with the provisions of this clause in no way relieves the Contractor of the final responsibility to furnish an acceptable product and/or services. 

2.
The Contractor agrees to control and professionally preserve and store appropriate documents, records, and recordings for a period of at least 3 years after termination of the agreement to guarantee the traceability of the services rendered and inspection thereof.

3.
The Contractor agrees to regularly update and implement all the latest technology available as well as the necessary improvements for the installation, production and organisation deemed necessary to meet the requirements of the agreement and in order to enhance all system capabilities and effectiveness to deliver high quality, cost-effective services.

4.  The delivered product and / or services shall be uniform in Quality and condition, sound and free from defects or external copyright or intellectual property rights, consistent with good industry practices and adhere to requested Eskom requirements, without deviation.

5.
Eskom shall have the right to conduct surveys and perform surveillance of the Contractor’s and/or Sub-Contractor facilities to evaluate their capability to comply with the requirements necessary to conform to contractual requirements.

6.
Eskom reserves the right to inspect, at reasonable times, any or all of the work included in the Works Information at the Contractor’s or Sub-Contractor’s premises or elsewhere. Verification by Eskom shall not absolve the Contractor of the responsibility to provide acceptable product and / or services, nor shall it preclude subsequent rejection by Eskom.

7.
The services must comply with the agreed specifications and the applicable directives and technical standards set out in the contract and annexures. Defects notified by Eskom shall be remedied by the Contractor upon demand by Eskom without undue delay and at no extra cost. The Contractor shall continuously monitor and identify non-conformances, both internal and external, as signals of opportunities for improvement making process and other relevant changes to prevent recurrence.

8.
The Contractor shall further identify potential problems before they occur by identifying deviations in patterns or trends in product, service or process performance.

9.
Nothing contained in the contract and/or scope of work and /or works information shall relieve in any way the Contractor from the obligation of quality control thereof. 

10.
The Contractor guarantees that the quantity, quality and outward appearance of the delivered Product / services comply with the requirements of the contract and/or relevant specifications.

11.
The Contractor shall, on request, prove its ability to relate to the proposed scope of work which establishes the manner in which the Contractor intends to perform the Contract.

12.
The Contractor shall, on request, prove its organisational, logistics and support resources to ensure the requirements of the contract can and will be achieved.

13.
Eskom reserves the right to assess and measure, during the existence of the agreement, the qualifications, capability and competence of the key staff (assigned personnel) in relation to the scope of work and to interview any / all Contractors to confirm the Quality evaluation.

14.
The professional personnel who will be conducting the service will be available on a continuous basis until the conclusion of the project.

15.
The Contractor shall demonstrate experience in comparable projects or specific aspects of the project and / or performance in similar projects, on request.

16.
The Quality of the service / product and the contents thereof will always be in accordance with professional standards.

17.
For the duration of the Contract, the professional staff rendering the service / product, must be and remain a member of his/her Professional Society (where available/applicable)

18.
The Contractor must, at all relevant times, scrutinise and be aware of Eskom’s requirements with specific focus on, inter alia, its philosophy , principles , strategies , practises , mission , vision , models, policies and practises.

19.
It is the Contractor’s obligation to ensure that their operations and the products and services it provides to Eskom comply with any applicable statutes and or regulations. Any non-compliance by the Contractor and the resultant corrective actions shall be the responsibility of the Contractor.

20.
The Contractor shall ensure that he complies with the works information and that appropriate quality requirements (as in the main contract) are included in subcontracts placed by Contractors to ensure subcontractor’s compliance with the works Information.

21.
The Contractor shall execute the Works in accordance with Eskom’s Quality requirements set out in QM 58 document: Supplier Contract Quality Requirements Specification
2.6 Programming constraints 

The Contractor submits a single integrated programme that incorporates all the work to be performed including that of his Subcontractors. The interfaces between Subcontractors as well as the interfaces between Subcontractors and the Contractor are clearly identified. Project key dates are incorporated into the programme.
A programme showing the key activities is to be submitted with the tender documents or once appointed within two weeks. The Contractor submits a single integrated programme that incorporates all the work to be performed including that of his Subcontractors. 

The interfaces between Subcontractors as well as the interfaces between Subcontractors and the Contractor are clearly identified. 

Project key dates are incorporated into the programme. 

All critical path items are indicated and outlined on the programme.

The order and timing of operations which the Contractor plans in order to provide the works. Strict adherence to the programme will be monitored and updated on fortnightly basis to achieve the completion dates and submitted to Eskom Project Co-ordinator. Non-conformance to the stated programme will be liable for delay damages. Any deviations on time and cost are subject to Eskom approval.

The Contractor provides the Project Programme in Microsoft Projects Format to the level 3 detail. The programme is to be updated weekly and submitted to the Project Manager for review.
2.7 Contractor’s management, supervision and key people

The Contractor provides the Employer with a detailed organogram of all staff and management on the contract, showing their lines of authority / communication, within two weeks of contract award. This is revised monthly and reflects any changes to the staff and management structure. The Employer reserves the right to audit and verify the structure. The Contractor has a full-time Safety and Health Officers onsite.
2.8 Invoicing and payment
Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.  
The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd and include on each invoice the following information:

· Name and address of the Contractor and the Project Manager; 

· The contract number and title;

· Contractor’s VAT registration number;

· The Employer’s VAT registration number 4740101508;

· Description of service provided for each item invoiced based on the Price List;

· Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

· (add other as required)

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

2.9 Insurance provided by the Employer
Contractor familiarises themselves with the Eskom Insurance Format A as provided in the Contract Data and make provision for all items that they are liable for.
2.10 Contract change management 
The Employer instructs changes to the scope at any time, each instruction sets out the change and the date on which it becomes effective; and is issued to the Contractor in writing to be valid.
2.11 Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.  
The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract. 
2.12 Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor
N/A
2.13 Training workshops and technology transfer

After Completion of the contract, the Contractor is required to provide training and transfer system knowledge to the building owner/manager by submitting documented Design Intent, As-built drawings, Operational and Maintenance Manual, Commissioning Records, Commissioning Report and by providing training on all the systems to the building management staff to ensure that they have all the information and understanding needed to operate and maintain the features and systems in the building.

The Contractor is to provide on-site training and training material to the Engineers, Operators and Maintenance personnel prior to taking-over of the works. The training will preferable be offered during the commissioning and testing. The Contractor will, prior to handing over of the works, satisfy the Employer or authorized representative that maintenance and operational personnel are competent and adequately trained to maintain and operate the Plant and Materials supplied.

The training is to cover the following, however not limited to:

a.
Information provided in the design intent report (including energy/environmental features) 

b.
Review of controls set up, programming, alarms and troubleshooting 

c.
Review of O&M manuals 

d.
Building operation (start up, normal operation, unoccupied operation, seasonal changeover, shutdown) 

e.
Measures that can be taken to optimise energy efficiency 

f.
Occupational health and safety (OH&S) issues 

g.
Maintenance requirements and sourcing replacements 

h.
Obtaining and addressing occupant satisfaction feedback 

Steps for Conducting On-site Training are to include, but not limited to:

a.
Preparation

b.
Introduction

c.
Explanation

d.
Demonstration

e.
Practice Under Supervision

f.
Conclusion

The operating and maintenance manual must be available during the training of site staff. Site staff must also be made familiar with the contents of that manual.

Operational maintenance after Completion

The Contractor conducts maintenance for 52 weeks post completion of the works.

3 Engineering and the Contractor’s design
3.1 Employer’s design
The Contractor provides preliminary designs by registered engineers to the Project Manager for acceptance. These would have to be reviewed with possible amendments having to be made to comply with Eskom requirements. Adequate time is allowed for this. After acceptance of preliminary designs, the Contractor provides detailed designs.
The scope of works include the detail design, drawings, procurement, manufacture, fabrication, quality control, supply, delivery, installation, commissioning, testing, handing over, training and maintenance during the guarantee period of all materials and equipment necessary for the complete refurbishment of the EAL Electrical Kiosks and Distribution boards (DB’s), including sub-distribution boards, at Eskom Academy of Learning complex.
3.2 Parts of the works which the Contractor is to design
The Contractor is responsible for the detailed replacement of the complete Works based on the Employer’s

functional specification.

The Contractors’ works is to comprise of detailed reports packages which will be reviewed and approved by Eskom.

The Contractor is required to carry out detailed site investigation and take the actual measurements onsite. All survey data must be submitted to Eskom for record purposes and to assist as input during the review process. 
The Contractor shall be responsible for accurate and complete works, i.e., safety, effectiveness, and adequacy of the EAL electrical system, propose the new areas which require alterations. The Contractor shall assume that the electrical services to site are operational. Finishing and tidying shall therefore not be left to the end of the contract but shall be a continuous operation.

a)
The Contractor is responsible for obtaining information regarding services for the existing works which may be affected by the new works. Before the Contractor commences operations, he must discuss with and have the acceptance of the engineer concerned regarding the method he/she proposes to use for the safeguarding of any services and existing works he may encounter during construction. The cost of all precautionary measures, which may be necessary to ensure the safety of such services and existing works, as well as the protection of all persons, shall be borne by the Contractor. Any alteration to services, which may be required, shall be carried out by the Authority concerned at the expense of the Contractor. The Contractor shall be held responsible for any damage, injury or accident caused because of his failure to take the necessary precautionary measures.

b)
The Contractor shall ensure that all safety regulations and measures are applied and enforced during the works.

c)
The Contractor shall take all the necessary precautions to protect existing services, finishes and structures during the execution of the contract, and shall be fully responsible for all repairs and damages thereto. The costs for any repairs of damages shall be recovered from the Contractor.

3.2.1 Electrical System Design

The Contractor is to design for a complete integrated Electrical Installation to comply with the relevant SANS Standards and codes specified in this functional specification document. The electrical wiring installation system which will comply and be issued with the valid CoC’s to vastly improve its reliability-based design and operation features, and further take into consideration that the plant is to be easily accessible to the operating and maintenance personnel.

The complete Electrical wiring installation and Kiosks system is to be designed to accommodate 10% future growth under Eskom Academy of Learning site conditions. 

The complete Electrical wiring installation and Kiosks system is to be designed and constructed from new generation energy efficient type component in order to reduce the energy consumption.

The complete Electrical wiring installation and Kiosks performance figures obtained during testing and commissioning must be within a range of ±5% of the specified figures given during Contractors design, plant and material selection phase.

3.2.2 Outdoor Design Conditions

The outdoor design conditions for the Kiosks and Distribution Boards, including Sub-Distribution Boards are based on the Weather Bureau data. The mean maximum temperature (DB) for summer and mean minimum temperature for winter is taken as a design condition. The Weather Bureau does not list temperature and associated relative humidity (RH) as one set of data. The designer has to interpret data, study hourly temperatures and hourly humidity to establish the outdoor condition. The Eskom Academy of learning climate conditions are as follows:

• 
Summer: Ambient Temperature = 31.7oC DB 19.9oC WB (to be confirmed)

• 
Winter: Ambient Temperature = 1.1oC DB -2.2oC WB (to be confirmed)

• 
Elevation = 1633 m (to be confirmed)

3.2.3 Indoor Design Conditions

The Electrical Wiring Installation system is to maintain indoor conditions to prolong the equipment lifespan and provide occupational hygienic requirements.  

3.2.4 Objectives and purpose of the works
The objectives and purpose of the Works is to upgrade, test, and issue CoC’s at EAL site Distribution, Sub-Distribution Boards and Kiosks system, produce detailed upgrade report and produce the “As built” electrical layout, and wiring diagrams, Compliance with electrical wiring code (SANS 10142-1) for protection of people, animals, and property when it comes to electrical installations. Ensure installation as well as materials to be repaired/replaced to comply with Electrical Installation Safety Standards as outlined in Electrical Installation Regulation GNR.242 of 6 March 2009 and as stipulated in SANS10142-1.

•
Fulfil the legal obligation to ensure that all electrical Installation is of a good quality standard.

•
Safe for use by humans and it may not cause a negative environmental impact.

The objectives and purpose of the Works includes the following:

a. To ensure that Eskom infrastructure function correctly and safely to comply with current statutory requirements/standards.

b. Provide adequate and safe electrical supply to ensure comfort of humans and long term integrity of all process control electronic component is maintained to the required levels as detailed in the works.

c. To provide & maintain safe electrical power supply

d. To provide a safe environment for occupants 

e. To allow safe operation of the breakers and maintain continuous and uninterruptible power supply

f. To maintain safe protection during fault conditions

3.2.5 Electrical Services

The Contractor provides a detailed report of the Distribution Boards (DB’s) and Kiosks including the reticulation diagrams and the layout arrangements. This includes:

•
Replace each Distribution Boards (DB’s), sub-distribution boards & Kiosks and provides the detailed design.

•
Contractor verifies the Eskom condition assessment reports referenced in this document, evaluates, and provides design commendations of the required alterations to comply with the SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations). The employer to review the designs before work starts.

•
All works to comply with relevant electrical standards. Electrical Installation Regulation GNR.242 of 6 March 2009 and as stipulated in SANS10142-1.

•
Provide electrical system “As is” and “As built” layout drawings.

•
The works shall also comply with the requirements as laid down by the latest editions of:

· Applicable SANS-codes

· OHS Act

· ESKOM regulations for building installations

•
The Contractor adheres to National Building regulations and uses 240-54937450 – Fire Protection and Life Safety Design Standard and 240-54937448 Fire Detection and Life Safety Design Standard a guidance for Eskom specific requirements.

•
The Contractor must supply the following documentation as a minimum for Employer Acceptance:

i.
Scaled site electrical layout drawings indicating the following:

•
Accurate Legends in each Kiosk and Distribution Boards, including Sub- Distribution boards.

ii.
System fault monitoring capabilities

iii.
Detailed description of each interface including protocol used for interface

iv.
Power Supply methodology

v.
Method statements of the work prior to proceeding with the work

3.2.6 Component Requirements and Compliance
a. All materials supplied or utilised under this shall be new and unused. Only materials of first class quality and finish shall be utilised. All materials and equipment shall be subject to acceptance by the Engineer before procurement. Specifications for each item priced shall be supplied by the tenderer to the Eskom.

b. During the design phases the Contractor chooses all components to be used and consult with the Employer regarding choices of component.

c. The Contractor shall be responsible for the onsite co-ordination with the principal contractor and other sub-contractors. Due allowance shall be made for this liaison and on-site co-ordination in the tender price.
3.2.7 Installation Requirements
a. All cables shall comply with the relevant SANS specifications as provided in by the relevant STANDARD SPECIFICATIONS, REGULATIONS AND CODES. 

b. All LV power cables shall have stranded copper conductors, shall be of the 600/1 000V PVC/SWA/PVC type. Specifications for each item priced shall be supplied by the tenderer to the Eskom. 

c. The Contractor shall submit samples and data sheets for acceptance of all types of cables to be installed to the Engineer prior to the procurement thereof. 

d. Any hazardous zones should be identified during the design phase of the project. 
3.2.8 Interface Requirements
a) Interfaces between the other systems must be identified and managed by the Contractor Project Manager and the Eskom Project Manager.

3.2.8.1 Civil and Structural Services

•
Upgrade all the plinths and steel supports (where required) for all the Kiosks as per relevant SANS standards

The civil and structural design provides the support infrastructure for all the technical services required above. The high level infrastructure to be designed, but not limited to, is as follows:

a. Full geotechnical investigation is required for all areas identified to cater for the support structures. The ground condition is taken into account for the design. Geotechnical report and findings to be submitted for review. This is specific to all Kiosks and Distribution Boards that are installed outdoors.

b. Support structure for the Kiosks. The design of the structure must take into account the imposed loading from all components and assess the dynamic and static forces. 

c. All architectural requirements to match the current existing design philosophy at EAL and as specified in Eskom’s corporate identity standard.

3.2.8.2 Interfaces

The following interfaces are part of the project:

•
Earthing surge, and lightning protection

•
Civils and Structural requirements (Kiosks plinths and stands)

3.3 Procedure for submission and acceptance of Contractor’s design

The following process will be followed during submission of documents:

a)
The Contractor submits the documents/drawings to the Employer

b)
The Employer’s Document Controller registers the documents.

c)   The Employer’s Document Controller will supply the documents/drawings to all relevant parties within the Employer’s project team.

d)
The Employer’s project team reviews the documents/drawings and will submit all comments or inputs to the Contractor for consideration.

e)
If the Employer finds major deficiencies in the submitted documents/drawings, the Contractor

revises the documents/drawings and resubmits to the Employer.

f)
The Employer reviews the documents/drawings and if no major deficiencies are found, the

Contractor organises a Review session.

g)
The Employer and the Contractor conduct a Review.

h)
If any fundamental errors were found in the works or further actions are required, the

Contractor record all concerns raised and revises the designs.

i)
The Contractor organises a Review session once all works were revised according to the concerns raised by the Employer.

j)
If no fundamental errors were found in the designs during the Design Review session, the

Contractor compiles the Review minutes or report and submits it to the Employer

k)
The Employer’s Document Controller registers the report.

l)
The Employer’s project team reviews the Contractor report/minutes. If the report/minutes are not acceptable, the Contractor revises the report/minutes and resubmits to the Employer’s Agent.

m)  The Employer’s Agent will accept the Contractor works once the report/minutes are accepted by the Employer’s project team.

n)
Work shall always be subject to full time supervision by a qualified and experienced site agent. This representative must be authorised and competent to receive instructions on behalf of the Contractor.

The following documents are supplied to the Employer by the Contractor as a minimum:

Detail Design

· Detail design report

· Detail calculations

· Coordination between services

· Design including components data sheets and specification for selected components, distribution and Kiosks panels, electrical cabling and other associated component

· Dimensioned detailed drawings showing the general arrangement of all plant and component including isometrics and/or P&ID’s where required. Sufficient views must be given to ensure clarity and the drawing shall have at least a plan and two different elevations or sections giving overall dimensions.

· Detail design drawings. Dimensioned detail drawings showing proposed method of fixing of all the plant and component

· Steel structures required for access to component

· Detailed electrical wiring diagrams including schematic and control circuits.

· Detailed sequencing manner for installation procedure of works

· Detailed programme for the works in sufficient detail as to represent the units of work to enable the representative to assess the progress of the works

· Technical Specifications. Technical literature for all items of component that forms part of the complete installation

· Proposed corrosion protection systems, including data sheets for coating proposed of component

· List of recommended spares and technical specifications for the spares

· Detailed structural & civil works for complete works

· Detailed maintenance, reliability, control and operating philosophies

· Testing, balancing and commissioning procedures

· Plant and material acceptance testing

· Plant Codification Lists for each Section of the Works

· Detailed Works Information

· Small power and lighting layouts
Process Design

· Component lists/schedules
· 3D model
· Plant Layout Drawings 
· FMECA (Failure Modes Effects Analysis) study
· HAZOP (hazard and operability)study
· RAM (Reliability, Availability and Maintainability) Report/Analyses
Arrangement Drawings

•
Plant Layout Drawings

•
Arrangement drawings

· 3D model

Civil Detail Design

· Supports (Steel or Concrete)

· Pipe racks

· Plinths Components, racks, supports and 

· Component specifications

· Corrosion protection
Technical Specification

•
Technical Specification document (Works Information/Tender document) 
•
Technical tender evaluation strategy

Construction administration and Quality Assurance and Close out

•
Construction Completion Review

•
Acceptance Testing Review

•
Quality assurance report

•
Close out reports

3.4 Other requirements of the Contractor’s design
All the design solutions are developed by the relevant Professional Engineers at all design stages, the associated Professional Engineer will form part of the Contractor’s supervision team and inspect and sign off the various quality documents.
The Contractor is to comply with all legislated safety requirements as well as Eskom’s health and safety standards.
3.5 Use of Contractor’s design
The Contractor grants to the Employer, with effect from the starting date, an irrevocable royalty-free non-exclusive licence to use all of the documents provided to provide the Works (including, but not limited to calculations, drawings, manuals, models and other documents of a technical nature), for any purpose whatsoever, including for the purpose of operating, repairing, maintaining, dismantling, re-assembling and making adjustments to all parts of the Works.
Design of Equipment
a.
The components are to be designed to facilitate efficient manufacture, inspection, transportation, installation, maintenance, cleaning and repairs.

b.
The components are to be designed to ensure safe and satisfactory operation for a life expectancy of at least 30 years under the conditions prevailing at Eskom Academy of Learning.

c.
The components are to be designed to prevent undue stresses being produced by expansion and contraction due to temperature change and other local natural and manmade conditions.

d.
The components are to be designed to keep maintenance costs to a minimum.

e.
The components are to be designed to comply with all the legal requirements in respect of safety and the prevention of environmental pollution.

f.
The components are to be designed to satisfy any specific requirements contained in the relevant statutory codes and standards.

g.
The components are to be designed for operation of 365 day per annum, 24hrs per day.

h.
The components are to be designed such that all material from which the components are manufactured from is compatible with the intended duty and service conditions. All components are suitable treated and protected from corrosion.

3.6 Equipment required to be included in the works
Geotechnical and utility detection equipment to be used by the Contractor to perform the works.
The minimum general components design criterion that is to be met is as follows:

3.7 As-built drawings, operating manuals and maintenance schedules

3.7.1 As-built drawings
At Take-over, the Contractor provides two full sets of as-built documentation as hard copies and electronic PDF and native CAD formats (. DGN or .DWG which must be compatible with Bentley MicroStation) to the Employer.

The Operating and Maintenance Manual must describe how the plant is to be operated and by whom, as well as the desired level of training and orientation required for the building occupants. The operation and maintenance manuals are to consist of the following as a minimum:

a.
List of Contents (Index)

b.
Introduction

c.
General description of the functions of each of the systems including detailed description of each element of each system, how it functions, how it operates and how to maintain it and what attic stock or tools to carry. 

d.
Full as-built drawings and detailed drawings, brochures and catalogues for each system and each element of each system. 

e.
The format of the O & M documentations is to be A4 and be a specially bound document with hard cover and with metal ring binding. (All drawings and details are to be reduced to A3 format and folded into A4 format.)

f.
The names, addresses and telephone/fax numbers/email addresses of all responsible persons and manufacturers/suppliers are to be listed in the O& M manual.

g.
A full list with reference numbers is to be included to enable the O&M staff to order materials and spares.

h.
Colour diagrams are be provided to illustrate the operation and function of each system with reference to the relevant as-built drawings or brochures of Plant and Materials. These diagrammatic drawings must also indicate the locations of valves with their numbers.

i.
outlines all the required maintenance activities for the complete works as well as the frequency of such activities and by whom.
3.7.2 Shop Drawings

Shop drawings are to indicate all Plant and Materials, distribution systems, testing/inspection/instrumentation positions, access requirements and builder's work requirements. 

The Contractor is to review, stamp all shop drawings to confirm that co-ordination with building and services drawings have taken place before submitting to the Employer for Acceptance.

The Contractor’s drawings are to be prepared in accordance with SANS 10111 (Engineering drawing practice) and 240-86973501 (Eskom Engineering Drawing Standard Common Requirements). General arrangement and detailed drawings are to be cross referenced using codification system

3.7.3 Operating Manuals and Maintenance schedules

The Operating and Maintenance Manual must describe how the plant is to be operated and by whom, as well as the desired level of training and orientation required for the building occupants
The operation and maintenance manuals are to consist of the following as a minimum:
a. List of Contents (Index)
b. Introduction
c. General description of the functions of each of the systems including detailed description of each element of each system, how it functions, how it operates and how to maintain it and what attic stock or tools to carry. 
d. Full as-built drawings and detailed drawings, brochures and catalogues for each system and each element of each system. 
e. The format of the O & M documentations is to be A4 and be a specially bound document with hard cover and with metal ring binding. (All drawings and details are to be reduced to A3 format and folded into A4 format.)
f. The names, addresses and telephone/fax numbers/email addresses of all responsible persons and manufacturers/suppliers are to be listed in the O& M manual.
g. A full list with reference numbers are to be included to enable the O&M staff to order materials and spares.
h. Colour diagrams are be provided to illustrate the operation and function of each system with reference to the relevant as-built drawings or brochures of Plant and Materials. These diagrammatic drawings must also indicate the locations of valves with their numbers
3.8 Codes and Standards

The complete detailed designs report is to comply with the following codes and standards:

GENERAL

•
240-54179170, Classification and Designation of Technical Documentation Standard.

•
240-71432150, Plant Labelling Standard.

•
GIT general labelling standard for communication and power cables.

•
240-86973501, Engineering Drawing Standard Common Requirements.

•
SANS 10400, The Application of the National Building Regulations

The latest edition, including all amendments up to date of tender of the following specifications, publications and codes of practice shall be read in conjunction with this specification and shall be deemed to form part thereof:

•
Occupational Health and Safety Act 85 of 1993 and regulations as amended Compulsory standards:
•
Compulsory specification for circuit-breakers, as published by Government Notice No. R. 967 (Government Gazette 29265) of 6 October 2006. (VC 8036)

•
Compulsory specification for earth leakage protection units, as published by Government Notice No. 2286 (Government Gazette 10987) of 16 October 1987. (VC 8035)

•
Compulsory specification for manually operated switches for fixed installations, as published by Government Notice No. R. 438 (Government Gazette 18779) of 3 April 1998. (VC 8003)

•
Compulsory specification for plugs, socket-outlets and socket-outlet adaptors, as published by Government Notice No. R. 1075 (Government Gazette 33763) of 19 November 2010. (VC 8008)

•
Compulsory specification for the safety of electric cables with extruded solid dielectric insulation for fixed installations (300/500 V to 1 900/3 300 V), as published by Government Notice No. R. 1165 (Government Gazette 25306) of 15 August 2003. (VC 8075)

•
Compulsory specification for safety of flexible cords for electrical appliances, as published by Government Notice No. R. 1079 (Government Gazette 33763) of 19 November 2010. (VC 8006)

Applicable SANS standards:

•
SANS 10142-1 (The Wiring of Premises - Part 1: Low-voltage Installations)

•
SANS 152 (SABS 152), Low-voltage air-break switches, air-break disconnectors, air-break switch-disconnectors, and fuse-combination units. (Superseded by SANS 60947-3.)

•
SANS 156: Moulded-case circuit breakers
•
SANS 164-0, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 0: General and safety requirements

•
SANS 164-1, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 1: Conventional system, 16 A 250 V a.c.

•
SANS 164-2, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 2: IEC system, 16 A 250 V a.c.

•
SANS 164-3, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 3: Conventional system, 6 A 250 V a.c.

•
SANS 164-4, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 4: Dedicated system, 16 A 250 V a.c.

•
SANS 164-6, Plug and socket-outlet systems for household and similar purposes for use in South Africa – Part 6: Two-pole systems, 16 A 250 V a.c., for connection of class II equipment.

•
SANS 337, Stove couplers

•
SANS 529, Heat-resisting wiring cables

•
SANS 556-1, Low-voltage switchgear – Part 1: Circuit breakers
•
SANS 556-2-1, Low-voltage switchgear Part 2-1: Earth leakage circuit breakers
•
SANS 556-2-2, Low-voltage switchgear Part 2-2: Earth leakage switches

•
SANS 767-1, Earth leakage protection units – Part 1: Fixed earth leakage protection circuit- breakers

•
SANS 950, unplasticized polyvinyl chloride rigid conduit and fittings for use in electrical installations.

•
SANS 1012, Electric light dimmers

•
SANS 1063, Earth rods, couplers and connections

•
SANS 1065-1 (SABS 1065-1), Metal conduits and fittings (screwed-end and plain-end) for electrical wiring – Part 1: Metal conduits. (Superseded by SANS 61386-1 and SANS 61386- 21.)

•
SANS 1065-2 (SABS 1065-2), Metal conduits and fittings (screwed-end and plain-end) for electrical wiring – Part 2: Metal fittings. (Superseded by SANS 61386-1 and SANS 61386-21.)

•
SANS 1085, Wall outlet boxes for the enclosure of electrical accessories

•
SANS 1195, Busbars

•
SANS 1213, Mechanical cable glands

•
SANS 1239, Plugs, socket-outlets and couplers for industrial purposes

•
SANS 1411-1, Materials of insulated electric cables and flexible cords – Part 1: Conductors

•
SANS 1433-1, Electrical terminals and connectors – Part 1: Terminal blocks having screw and screw less terminals

•
SANS 1973-1, Low-voltage switchgear and control gear ASSEMBLIES Part 1: Type-tested ASSEMBLIES with stated deviations and a rated short-circuit withstand strength above 10 kA

•
SANS 1973-3, Low-voltage switchgear and controlgear ASSEMBLIES Part 3: Safety of ASSEMBLIES with a rated prospective short-circuit current of up to and including 10 kA

•
SANS 1973-8, Low-voltage switchgear and controlgear ASSEMBLIES Part 8: Safety of minimally tested ASSEMBLIES (MTA) with a rated short-circuit current above 10 kA and a rated busbar current of up to and including 1 600 A a.c. and d.c.

•
SANS 1507-1, Electric cables with extruded solid dielectric insulation for fixed installations (300/500 V to 1 900/3 300 V) – Part 1: General.

•
SANS 1507-2, Electric cables with extruded solid dielectric insulation for fixed installations (300/500 V to 1 900/3 300 V) – Part 2: Wiring cables

•
SANS 1507-3, Electric cables with extruded solid dielectric insulation for fixed installations (300/500 V to 1 900/3 300 V) – Part 3: PVC distribution cables

•
SANS 1574-3, Electric flexible cores, cords and cables with solid extruded dielectric insulation

–
Part 3: PVC-insulated cores and cables

•
SANS 1574-5, Electric flexible cores, cords and cables with solid extruded dielectric insulation

–
Part 5: Rubber-insulated cores and cables

•
SANS 1765, Low-voltage switchgear and controlgear assemblies (distribution boards) with a rated short-circuit withstand strength up to and including 10 kA

•
SANS 1777, Photoelectric control units for lighting (PECUs)

•
SANS 10199, The design and installation of earth electrodes

•
SANS 10313, Protection against lightning – Physical damage to structures and life hazard

•
SANS 60309-1/IEC 60309-1, Plugs, socket-outlets and couplers for industrial purposes – Part 1: General requirements

•
SANS 60439-1/IEC 60439-1, Low-voltage switchgear and controlgear assemblies – Part 1: Type-tested and partially type-tested assemblies

•
SANS 60529/IEC 60529, Degrees of protection provided by enclosures (IP Code)

•
SANS 60669-1/IEC 60669-1, Switches for household and similar fixed electrical installations -
       Part 1: General requirements.

•
SANS 60934, Circuit-breakers for equipment (CBE)

•
SANS 60947-2/IEC 60947-2, Low-voltage switchgear and controlgear – Part 2: Circuit- breakers

•
SANS 60947-3/IEC 60947-3, Low-voltage switchgear and controlgear – Part 3: Switches, disconnectors, switch-disconnectors and fuse combination units

•
SANS 60947-4-1/IEC 60947-4-1, Low-voltage switchgear and controlgear – Part 4-1: Contactors and motor-starters – Electromechanical contactors and motor-starters

•
SANS 60947-4-2/IEC 60947-4-2, Low-voltage switchgear and controlgear – Part 4-2: Contactors and motor-starters – AC semiconductor motor controllers and starters

•
SANS 60947-4-3/IEC 60947-4-3, Low-voltage switchgear and controlgear – Part 4-3: Contactors and motor-starters – AC semiconductor controllers and contactors for non-motor loads

•
SANS 60947-5-2/IEC 60947-5-2, Low-voltage switchgear and controlgear – Part 5-2: Control circuit devices and switching elements – Proximity switches

•
SANS 61084-1/IEC 61084-1, Cable trunking and ducting systems for electrical installations – Part 1: General requirements

•
SANS 61312-3/IEC/TS 61312-3, Protection against lightning electromagnetic impulse – Part 3: Requirements of surge protective devices (SPDs)

•    SANS 61386-1/IEC 61386-1, Conduit systems for cable management – Part 1: General requirements

•
SANS 61386-21/IEC 61386-21, Conduit systems for cable management – Part 21: Particular requirements – Rigid conduit systems

•
SANS 61386-22/IEC 61386-22, Conduit systems for cable management – Part 22: Particular requirements – Pliable conduit systems

•
SANS 61386-23/IEC 61386-23, Conduit systems for cable management – Part 23: Particular requirements – Flexible conduit systems

•
SANS 61439-1, Low-voltage switchgear and controlgear assemblies Part 1: General rules

•
SANS 61643-1/IEC 61643-1, Low-voltage surge protective devices – Part 1: Surge protective devices connected to low-voltage power distribution systems – Requirements and tests

•
SANS 61643-12/IEC 61643-12, Low-voltage surge protective devices – Part 12: Surge protective devices connected to low-voltage power distribution systems – Selection and application principles

•
SANS 62208, Empty enclosures for low-voltage switchgear and controlgear assemblies- General requirements

•
SANS 62305-1/IEC 62305-1, Protection against lightning – Part 1: General principles

•
SANS 62305-2/IEC 62305-2, Protection against lightning – Part 2: Risk management

•
SANS 62305-3/IEC 62305-3, Protection against lightning – Part 3: Physical damage to structures and life hazard

•
SANS 62305-4/IEC 62305-4, Protection against lightning – Part 4: Electrical and electronic systems within structures

•
SATS 17576, Light emitting diode products for lighting: Performance requirements

•
SANS 890-1, Ballasts for fluorescent lamps Part 1: Ballasts for lamps for operation with starters (class A lamps)

•
SANS 890-2, Ballasts for fluorescent lamps Part 2: Ballasts for lamps for operation without starters (class B lamps)

•
SANS 1041, Tubular fluorescent lamps for general service

•
SANS 1464-22, Safety of luminaires Part 22: Luminaires for emergency lighting

•
SANS 1662, Self-ballasted LED tubular lamps for general lighting services > 50 V - Safety requirements

•
SANS 60598-2-2, Luminaires Part 2-2: Particular requirements - Recessed luminaires

•
SANS 62560, Self-ballasted LED-lamps for general lighting services by voltage > 50 V - Safety specification

•
SANS 62504, General lighting - Light emitting diode (LED) products and related equipment - Terms and definitions

•
SANS 10313: The protection of structures against lightning.

•
SANS 10198-3: The selection, handling and installation of electric power cables of rating not exceeding 33kV Part 3: Earthing systems - general provisions, South African National Standards, Pretoria.

•
SANS 10198-12: The selection, handling and installation of electric power cables of rating not exceeding 33kV Part 12: Installation of earthing system, South African National Standards, Pretoria.

•
IEC 61439-1: General Rules

•
IEC 61439-2: Power Switchgear and Controlgear Assemblies

•
IEEE 81: IEEE Guide for Measuring Earth Resistivity, Ground Impedance, and Earth Surface Potentials of a Grounding System

•
SANS 204: Energy Efficiency in Buildings

•
SANS 475: Luminaires for interior lighting, street lighting and floodlighting - Performance requirements

•
SANS 10098: Public lighting

•
SANS 10108: The classification of hazardous locations and the selection of apparatus for use in such locations

•    SANS 10114-1: Interior lighting Part 1: Artificial lighting of interiors

•    SANS 10114-2: Interior lighting Part 2: Emergency lighting

•
Electrical Installation Regulations, 2009 as amended (Promulgated in terms of the Occupational Health and Safety Act by GNR 242 of 6 March 2009).

•
Equipment used shall originate from Suppliers which have been certified in accordance with SABS ISO 9001 (ISO 9001) or SABS ISO 9002 (ISO 9002) for quality assurance.

•
Manufacturer's specifications and installation instructions

•
Local by-laws

ELECTRICAL

•    240-56356396 Earthing and Lighting Protection

•
240-103059202, Capacity of Essential Power Supplies for Telecommunication, Protection and Tele control Equipment of the Transmission System.

•
240-53114248, Specification for Thyristor and switch mode chargers, AC/DC to DC/AC converters and inverter/uninterruptible power supplies.

•
240-56356510 Definitions of Terms Applicable to DC Emergency Supplies Standard

•
240-56535959 Management of Emergency AC and DC Supplies at Non-Nuclear Sites Standard

•
240-56357424 MV and LV Switchgear Protection Standard

•
240-56357421 Measurements and Metering Standard

•
240-62581162 Generation Energy Management and Data Acquisition System (EMDAS) Standard

•
240-56359083 Metering and Measurement Systems for Power Stations in Generation Standard

•

240-56227516 LV Switchgear Control Gear Assembly Associated Component for Voltage 1000V AC and 1500V Standard

•
240-56227443 Requirements for Control and Power Cables for Power stations Standard

•
240-55714363 Coal Fired Power Stations Lighting and Small Power Installation Standard

•
240-56227426 Management of Power Station MV and LV Protection and Settings Standard

CIVIL

· 240-56364535, Architectural Design and Green Building Compliance Manual.

· 240-107981296, Constructability Assessment Guideline

· 240-56364545, Structural Design and Engineering Standard.

· SANS 10100-1,The Structural Use Of Concrete Part 1 – Design

· SANS 10100-2,The Structural Use Of Concrete Part 2 – Materials and execution of work 

· SANS 10160, Basis of structural design and actions for buildings and industrial structures

· SANS 10162-1, The structural use of steel Part 1: Limit-states design of hot- rolled steelwork 

· SANS 10162-2, The structural use of steel Part 2: Cold-formed steel structures

· SANS 10400, The application of the National Building Regulations

· Applicable SANS standards listed in the documents above based on the final scope requirements.

· National Building Regulations

4 Procurement
The Contractor provides the following procurement services in performing the works:

 •
Preparation of Employer approved supplier and Sub-Contractor’s lists for equipment and contracts to be submitted to the Employer for review and approval.

•
Follows the most cost and time saving procurement strategies.

•
Contract management services for the selection, appointment, and management of Sub-Contractors, where required to execute the scope. 

•
Obtains delivery dates from Sub-Contractors and suppliers in order to realize the Completion Date;

•
Receiving of invoices, verification thereof in terms of purchase orders and contract provisions, certification of invoices as being correct and payable and supply of correct invoices to the Employer  

•
Management of and negotiating of all suppliers and Sub-Contractors compensation events and recommendations to the Employer as to the validity, amount and payment of such events.

•
Determination of penalties payable by suppliers and Sub-Contractors and recommendation to the Employer as to the enforcement of such penalties prior to any communication to suppliers and Contractors.

•
Ensuring that all suppliers and Sub-Contractors, from whom the Contractor procures equipment and materials do not retain, encumber or reserve title to such items.
4.1 People
4.1.1 Minimum requirements of people employed on the Site
•
All Contractors personnel are subjected to access control conditions as per Eskom requirements. 

•
All workers employed on site comply with Eskom’s health and safety standards. Workers are not allowed to be transported on the back of vans or bakkies. 

•
Workers are restricted to the area of activity in close proximity to the construction.

•
The Contractor recruits within the immediate District Municipality for general labour/ skills to execute the project.
4.1.2 BBBEE and preferencing scheme

The Contractor is required to achieve or maintain BBBEE Level 4 rating in accordance to SD&L requirements.
4.1.3 Accelerated Shared Growth Initiative – South Africa (ASGI-SA) 

Not applicable for the contract.
4.2 Subcontracting
4.2.1 Preferred subcontractors

The Contractor notifies the Project Manager in the event of using any Sub-contractor and provides the Project Manager with a list of all sub-contractors on the project. Subcontractors cannot subcontract work to another subcontractor. The choice of the proposed sub-contractor is subject to the Project Manager’s approval before using the services of such subcontractor. The Subcontractor must be familiar with the required work and should submit CV’s of past experience and have the necessary statutory accreditations.

The Contractor provides the Project Manager with the Health and Safety plans of all the sub-contractors on the project, before commencing the project.
4.2.2 Subcontract documentation, and assessment of subcontract tenders

The Contractor uses the NEC subcontractor agreements. All subcontractor quotations for which provisional sums or budgets have been allowed, is first approved by the Employer or his representative with documentary proof. This is done well in advance of the planned scheduling of the work.
4.2.3 Limitations on subcontracting

As per Eskom requirements, subcontracting will be limited to 30% as far as possible. The Employer is notified where subcontracting exceeds the 30% threshold prior to commencement of the specific subcontracting works.
4.2.4 Attendance on subcontractors

The contractor attends to the activities of all subcontractors including direct subcontractors
4.3 Plant and Materials
4.3.1 Quality

The Contractor will not use Plant or Materials which are generally recognised as being unsuitable or otherwise to be avoided for the purpose for which they are intended.

Only components of high reliability will be utilised, with a proven operating history, to enable the Plant to achieve required reliability and availability. Plant and Material design, engineering and manufacture will accord with the best modern practice applicable to high-grade products of the type to be furnished, so as to ensure the efficiency and reliability of the Works and the strength and suitability of the various parts for the Works. 

Plant and Materials withstands ambient conditions and the variations of temperature arising under working conditions without distortion, deterioration or undue strains in any part.

All parts are made accurately, and where practicable, to standard gauges so as to facilitate replacement and repairs. Like parts are interchangeable.

No repair of defective Plant and/or Materials will be permitted without the Project Manager’s Acceptance and any such repair, if accepted, will be carried out to the satisfaction of the Employer.

The Project Manager is free to specify hold and witness points during the installation and on-site testing stages of the project. The Contractor issues preliminary notification of such hold and witness points by fifteen working days advance notice to the Project Manager and confirms such hold and witness points at least seven working days prior to the activity. 

Typical hold points are listed below:

a.
Design Review

b.
Factory Acceptance Test

c.
Delivery to Site

d.
Erection

e.
Site Acceptance Test

f.
All manuals and drawings (in the specified format)

g.
Commissioning

In addition to maintaining appropriate inspection and test records to substantiate conformance to requirements, the following records are safely stored for a minimum period of seven years following the final Completion of the Works:

a.
Construction, layout and component Acceptances

b.
Type and routine test certificates

c.
Construction drawings and Acceptances

After this period, the Contractor offers these records to the Employer (in writing) and obtains a disposal instruction.

Documentation regarding quality procedures is submitted within thirty days of Contract Award. The Employer will review and comment on the acceptability of these documents in a time frame as per the requirements of the contract for contractual correspondence. If controlled copies of these documents have been submitted to the Employer, then the controlled copy numbers may be quoted in the submission.

The Contractor adheres to:

Vendor Document Submittal Schedule (the schedule to be issued to the Contractor by the Employer)
4.3.2 Plant & Materials provided “free issue” by the Employer
None, all Plant and Materials are to be provided by the Contractor.
4.3.3 Contractor’s procurement of Plant and Materials

The Contractor is responsible for ensuring that all products are preserved in their appropriate manner as described in their specifications or in Eskom preservation, shipping and transportation procedures as applicable. The Contractor shall submit the preservation, shipping and transportation procedures to the Employer for review and acceptance. The Employer may choose to witness the packaging, loading and offloading of the products depending on their criticality, this will be indicated in the intervention points on the QCP / ITP document. The Contractor shall ensure that all storage requirements for products are properly implemented to preserve the products against adverse conditions, deterioration, damages, etc. Storage and preservation procedures for the different products must be submitted to the Employer for review and 

acceptance. The Employer may request to inspect the stored products at any given point during the storage period of the product. Requirements for preservation, shipping and transportation are addressed in 240-105658000
4.3.4 Spares and consumables
The Contractor provides as part of the tender proposal, a recommended parts list as well as a proposal for the execution there of:

a.
The Employer is responsible for purchasing of recommended spares.

b.
The Contractor is responsible for ensuring that consignment spares are available in time of need.

Each recommended spare part is to be uniquely identified with a part number, which can be cross referenced to a part list and associated drawing. The Employer prefers that support from the OEM is available locally in South Africa.
4.4 Tests and inspections before delivery

The Employer carries out quality inspections at his own discretion. The Employer will inspect and approve stages of manufacture of all Plant and Materials necessary to ensure the correct quality of Plant and Materials as prescribed in the accepted project quality plan.

All inspections and testing are to be performed in accordance with the Quality Control Procedure (QCP) developed by the Contractor after Acceptance by the Employer.

The Contractor must provide facilities for inspection of all items of Plant and Materials at the place of the manufacture and this requirement must extend to all sub-contractors and suppliers if applicable. All material labour or assistance, tools, gauges, articles or apparatus that the Employer may require for the purpose of testing, gauging and inspection, must be provided by the Contractor. The Contractor must provide all such facilities for testing and the contract price must include for this.

The Employer reserves the right to reject items that do not conform to the Employer’s requirements. When the plant has passed the prerequisite tests the Employer will furnish to the Contractor a certificate or endorse the Contractor’s test certificate to that effect. Examination by the Employer does not relieve the Contractor from the responsibility of carrying out all tests which may be necessary to ensure the required standard of manufacture or from any obligations in terms of the contract. 

The achievement of adequate standards during the tests at the place of manufacture, if performed, is only the first requirement. The final criterion will be performance onsite, and any of the requirement which proves defective due to bad workmanship or material must be replaced forthwith by the Contractor at his own cost on the instruction of the Employer.

The following tests are conducted by the Contractor and are to be witnessed by the Employer at the manufacturer’s works or Contractor’s premises as a minimum requirement:

a.
Visual inspection of the Plant and Materials

b.
Review of the certification requirements

c.
Inspection of paint work and corrosion protection.

d.
Verification that all components are delivered to the Contractor’s premises.

e.
Verification that all power plugs is correct.

f.
Verification that components installed is correct.

g.
Verification that all labels are correct.

h.
Phase rotation
4.5 Marking Plant and Materials outside the Working Areas

All Material paid for by the Employer is clearly labelled as being the Employer’s property
4.6 Contractor’s Equipment (including temporary works).

The Contractor provides the following in order to complete the works:

a.
All scaffolding required

b.
Any Equipment necessary to complete the works

c.
Lifting facilities

The Contractor supplies, installs, maintains and removes all temporary construction facilities and utilities necessary to Provide the Works.
4.7 Cataloguing requirements by the Contractor
Unique Identifier 240-1289988974 to be provided on request
5 Construction
The Contractor is required to:

a)
Submit a comprehensive method statement of the entire works to the Project Manager for acceptance prior to the start of the works

b)
Submit a project specific safety file to the Employer for comments / acceptance.

c)
Prepare earthworks for craneage access and working rigging areas if required. 

d)
Manage his activities on Site to ensure that no interference takes place between his work and that of others.

e)
Complete "Contract Activities Daily Reports".

f)
Liaise with the Project Manager regarding utilities and telephone facilities required for his Site establishment.

g)
Liaise with the Project Manager regarding the location of waste disposal sites and rubbish dumps,

h)
Maintain and promotes labour harmony on the Site and in the working environment.

i)
Immediately report any potential labour disharmony to the Project Manager.

j)
Not recruit or employ any personnel from the Employer and Others, without prior acceptance of the Project Manager.

k)
The Contractor submits a fully detailed Quality Control Plan (QCP) for acceptance within one week of the Contract Date.

l)
The Contractor submits a schedule of unpriced orders to be placed and this is updated regularly.

m)
The Contractor is responsible for defining the level of QA/QC (intervention Points) or inspection to be imposed on his Subcontractors and suppliers of material in the Quality Control Plans (QCPs). This level is based on the criticality of plant and materials, and is submitted to the Employer for acceptance.

n)
Product data sheets and product samples are submitted for review and acceptance by the Project Manager after contract award and prior to the commencement of work.

o)
All quality control documentation is submitted to the Project Manager within 7 days of Contract Date.

CONSTRUCTION AND ERECTION
a)
The Contractor is responsible for the design, erection, maintenance, and removal of all temporary or false work required for the execution of the works.

b)
The Contractor takes all necessary precautions to ensure that none of the existing structures and services that are not in the scope of works is damaged during any demolition required. If structures and services which are not in the scope of work is damaged, the Contractor is liable to repair or replace the damaged items at their own cost.

c)
All construction works complies with SANS 1200 standardised specification for civil engineering construction.

HANDOVER
The Contractor is responsible for the provision of a final data book.  The document contains all the relevant documentation, designs, drawings including as-built drawings, materials certificates, and product specifications on all products used, tests and results etc. which were applicable during the contract. The Contractor ensures that all relevant documentation is traceable and cross referenced where applicable.

Data Book

a)
Apart from any statutory data packages required, the Contractor also compiles a data package of the relevant drawings, test certificates etc. which he submits to the Project Manager for acceptance. These include, but are not limited to:

­
Document List 

­
Instruction for Work/Purchase Order

­
Approved ITP’s, QCP’s

­
Method statements and specification adhered to

­
Rigging studies (if applicable)

­
Risk assessments

­
Approved Drawings

­
Fabrication Drawings 

­
Material Certificates

­
Approved NDT procedure

­
NDT Reports / Results

­
Certificate of Manufacture

­
Inspection Reports

­
Corrosion Protection Consumables Certificates 

­
Calibration Certificates

­
Notifications

­
Modifications

­
Concessions

­
TQ’s, ER’s and communication with Employer

­
Non-conformance reports

­
Internal Release Notes

­
Transport notifications 

­
Additional

­
Calculations for any temporary works that may be required for the safe execution of the works.

­
Concrete cube test results and reports

­
Welding procedure specifications

­
Welder qualifications

­
Non-destructive weld test results

­
Weld test certificates

­
Steel grade certificates

­
Concrete test results

­
As-built data and drawings of the completed works upon handover. As-built drawings are submitted in PDF and native CAD formats (.DGN)

­
Structural Certificate signed by the Professional Civil Engineer confirming that works have been constructed in accordance with the design.

The contents are presented in a hard cover file or files.

The data packages are prepared on a daily basis for all completed work.

Two hard copies and one soft copy of the Data Book are handed to the Employer for acceptance. 

Data Books are submitted for review and acceptance before completion of the works to the Employer.

5.1 Temporary works, Site services & construction constraints

5.1.1 Employer’s Site entry and security control, permits, and Site regulations
The site is located in a part of an existing campus, with existing buildings all around, most buildings are currently occupied. 

1.
The Contractor attends the Compulsory site clarification meeting prearranged by the Employer prior to submitting tender. 

2.
The Contractor ensures that he familiarizes himself with site conditions. 

3.
Contractors access is limited to the areas as indicated in the scope and Contractor’s staff is prohibited from roaming in the rest of the facility.

4.
Eskom Holdings indemnifies themselves from any negligent events by the Contractor relating to the scope of the works within the contract period

5.  The Contractor, his staff and the Sub-contractors maintain identification at all times e.g. Uniforms etc.

6.
The Contractor is deemed to execute Safety Procedures to ensure the safety of his staff, Sub-contractors, Eskom staff during the Contract Period.

7.
Use of power and loud tools to be controlled and/or managed with Eskom office management team.

8.
The safety of the Contractors Employees, Subcontractors and building’s tenants takes preference over the scope of the works of this project.

9.
All site instructions to be approved and authorised in writing by the Project Manager. If this directive is not adhered to it could result in non-payment.
5.1.2 Restrictions to access on Site, roads, walkways and barricades

Access to the site

1.
The Employer provides the Contractor with an Access Certificate to formally provide access to the site.

2.
The Contractor ensures that he is familiar with conditions of access to the buildings, which includes constraints to limited parking and no goods lift is available in some of the blocks.

3.
The Contractor adheres to all the requirements which include, but not restricted to:

a.
Identity cards with photographs

 b.
 Cooperation in order to help Eskom provide the customer with a project schedule reflecting the period during which the construction and commissioning activities will take place. 

4.
The Contractor will be responsible for external disputes which may occur regarding the works.

5.
The Contractor is when necessary or needed, required to make all the necessary arrangements with the Local Authorities via the Building Manager and or Eskom Representative.
5.1.3 People restrictions on Site; hours of work, conduct and records

Working after normal working hours and on weekends requires special permission. The Contractor shall give the Employer adequate notice if this is planned.
5.1.4 Health and safety facilities on Site 
Refer to SHE specifications issued.
5.1.5 Environmental controls, fauna & flora, dealing with objects of historical interest 

The Contractor shall ensure that all fauna and flora is preserved and protected during his activity on site. All such fauna and flora will be reinstated after completion of the work
5.1.6 Title to materials from demolition and excavation

N/A
5.1.7 Cooperating with and obtaining acceptance of Others

Two weeks look-ahead schedule to be developed and submitted to Project Manager on a fortnight basis in order to make timeous arrangements for access into occupied buildings with the occupants concerned.
5.1.8 Publicity and progress photographs 

The Contractor requests approval from Project Manager for any photography and progress photographs prior to undertaking.
5.1.9 Contractor’s Equipment

The Contractor keeps an inventory of equipment brought to site. This is verified and acknowledged by Eskom security to allow removal of such equipment when required by the contractor.

Security of materials on sites:

•
The Contractor provides own security on site and is held liable for excess of insurance in case of theft or loss.

Material and Bill of Quantities
· Storage and security of material is the responsibility of the Contractor until the Final Completion Certificate is certified. The Contractor is responsible for all costs involved to expedite lost, damaged or stolen material.
5.1.10 Equipment provided by the Employer
The Contractor provides all equipment and tools required to complete the works.
5.1.11 Site services and facilities
The Employer will provide power and water, 

The Contractor shall make provision of waste disposal, and submit proof in a form of Waste Disposal Certificates to the Employer for approval

The Contractor shall provide everything else necessary for providing the Works
5.1.12 Facilities provided by the Contractor
A clearly demarcated site establishment area will be provided by the Contractor for the following:

·
Suitable facilities for Contractor to store all material and equipment

·
Suitable facilities for his employees for changing

·
Facilities for the consumption of food

·
Site offices

·
Toilet/Ablution facilities

·
Other temporary facilities required by the Contractor
5.1.13 Existing premises, inspection of adjoining properties and checking work of Others

Contractor is to investigate existence of any services before commencement of work. Care is to be taken when Contractor is doing demolitions so as not to damage the work of others.

5.1.14 Survey control and setting out of the works
It is the Contractors responsibility to ensure accuracy when performing setting out of the works, 

The Contractor shall provide adequate fastening to existing connection points.
5.1.15 Excavations and associated water control

Where excavation is required, the Contractor takes the necessary precautions not to damage any existing services.
5.1.16 Underground services, other existing services, cable and pipe trenches and covers

There is limited information regarding existing underground services.

Should the need arise for the contractor to work on underground services, the Contractor is required to conduct Scanning to determine the existing/underground services and provides this information as As-Build drawings to the Employer.
5.1.17 Control of noise, dust, water and waste 

The Contractor takes all precautions necessary to prevent any noise and dust whilst carrying out the work.
5.1.18 Sequences of construction or installation

The Contractor sequences execution in order of priority as per the sectional completion schedule and ensures all interfaces are coordinated and carried out without causing any disruptions
5.1.19 Giving notice of work to be covered up
Contractor to advise at least 4 weeks prior to starting work at that particular section so that proper notification is provided, including relevant authorisation to proceed
5.1.20 Hook ups to existing works

Contractor stipulates methodology for hooking-up when working in heights and provides notification to the SHE Officer in advance and obtain permission to proceed. The Contractor cannot not hook up for lifting, supporting or for any other reason to any position or existing works in the plant without a written approval by the Project Manager.
5.2 Completion, testing, commissioning and correction of Defects

5.2.1 Work to be done by the Completion Date

The following is mandatory.  

The contract is deemed to be complete when the following have been completed in accordance with the scope of work:

a.
The Plant is erected, and commissioned 

b.
Signed erection and safety clearance certificates have been submitted.

c.
The final drawings have been submitted.

d.
All documentation has been submitted including testing reports and the associated certificates received. All Quality Control Plan (QCP) documentation received. Final Draft of the Technical, Operating, Maintenance manuals have been delivered

e.
The Plant and all documentation I drawings are coded and labelled.

f.
All special tools / spares have been supplied.
5.2.2 Use of the works before Completion has been certified

On completion, commissioning and testing of plant, the Contractor may hand over completed section of the works for certification and operation.

5.2.3 Materials facilities and samples for tests and inspections 
The Contractor provides all Materials, facilities and/or samples required for tests and inspections.  

The Employer reserves the right to call for samples of the Equipment offered to inspect the workmanship as the work proceeds and to either accept or reject the Equipment or workmanship. 

The Employer’s Acceptance of the workmanship or Equipment must in no way reduce the Contractor's liability to provide complete buildings.

The purpose of these inspections is to reduce the risk of non-compliant Equipment and Materials being transported to site. The presence of the Employer at the inspections does not reduce the Contractor’s responsibility to comply with the contract.

The Contractor is to make arrangements that these inspections are carried out within the boundaries of South Africa. Should any tests or inspections be required outside of the Gauteng Area, the Contractor is to allow in his Tender price for all costs (travel, accommodation, subsistence, etc) for two persons to attend such tests or inspections. Accommodation and subsistence arrangements are to be submitted to the Employer for Acceptance in writing
5.2.4 Commissioning
•
When the electrical reticulation system is ready for service; commissioning shall take place to check whether the correct quantities of equipment have been delivered and the installation is in accordance with the specifications. Commissioning shall be performed in co-operation with the Contractor and representatives of the Employer and Supervisor.

•
Practical Completion certificates will only be issued once the whole of the electrical reticulation system installation satisfies the operational performance requirements of the contract and the Supervisor is satisfied that all electrical reticulation system is capable of operating effectively.

•
Performance and acceptance testing to determine whether the electrical reticulation system achieves the required level of performance will only be undertaken after all routine testing, adjusting, commissioning, approvals and building work associated with the contract are complete and the work have been fully tested and commissioned by the Contractor.

•
Details of the testing required for each system and equipment shall be included in the Contractor’s quality plan.

•
The Contractor shall supply all labour, materials and equipment required to fully commission and test the installation.

•
All costs associated in demonstrating that the electrical reticulation system performs as required by the contract, shall be borne by the Contractor. Equipment which fails to operate correctly or is found to be installed incorrectly shall be repaired or replaced by the Contractor. Where any test is unsuccessful the defective equipment shall be repaired appropriately and subjected to retesting.

•
The Contractor shall do his own complete commissioning tests before the actual first take-over tests are done. This is to satisfy himself that everything is working and is in accordance with the specification.
5.2.5 Start-up procedures required to put the works into operation
No alterations or adjustments will be made to the Works after functional checks are done without the Employer’s written permission.

At this stage, the following must have been achieved:

a.
Installation and pre-commissioning completed.

b.
Testing report and the associated certificates received.

c.
Signed erection and safety clearance certificates received.

d.
Final Draft of the Technical, Operating, Maintenance manuals delivered.

e.
All Quality Control Plan (QCP) documentation received.
5.2.6 Take over procedures

The Employer takes over completion of the Works on Completion Dates of the Accepted Program.
5.2.7 Access given by the Employer for correction of Defects

The Project Manager arranges the date and access to site for the Contractor to correct defects. The Contractor updates the site safety file and the records contained inside as per construction regulations. The Contractor will be responsible for ensuring that the area is barricaded before correcting any defects.
5.2.8 Performance tests after Completion

In accordance with clause X17, performance test will be conducted on completion.
5.2.9 Training and technology transfer

After Completion of the contract, the Contractor is required to provide training and transfer system knowledge to the building owner/manager by submitting documented Design Intent, As-built drawings, Operational and Maintenance Manual, Commissioning Records, Commissioning Report and by providing training on all the systems to the building management staff to ensure that they have all the information and understanding needed to operate and maintain the features and systems in the building.

The Contractor is to provide on-site training and training material to the Engineers, Operators and Maintenance personnel prior to taking-over of the works. The training will preferable be offered during the commissioning and testing. The Contractor will, prior to handing over of the works, satisfy the Employer or authorized representative that maintenance and operational personnel are competent and adequately trained to maintain and operate the Plant and Materials supplied.

Steps for Conducting On-site Training are to include, but not limited to:
a. Preparation
b. Introduction
c. Explanation
d. Demonstration
e. Practice Under Supervision
f. Conclusion
The Contractor shall accordingly take into the works an agreed number of members of the Employer’s staff for an agreed period. The Contractor shall give the staff workshop hands-on training as fitter-erectors on the plant and shall give instruction in the assembly, adjustment and works testing of main items of plant.

Subsequently the Contractor will have the assistance of Employer’s staff in commissioning of the plant and shall give appropriate instruction during these periods. Whilst the personnel allocated by the Employer can be expected to contribute in some measure to the erection work, the Contractor shall, in the Tender and when determining the programme, take into account that these personnel are involved only for training purposes.

The Contractor shall include attendance of the Employer’s staff during testing and witnessing and for key works inspections.

The Contractor shall provide detailed proposals setting out the key aspects of training which will be provided for the Employer’s personnel, both in the manufacturers’ works and on the Site, including the proposed training programmes.
5.2.10 Operational maintenance after Completion

The Contractor will be liable for maintenance of the equipment for 52 weeks after the completion date.
6 Plant and Materials standards and workmanship

The drawings include final general arrangements. Drawings include sections and details to fully identify design concepts, design loadings and any other special features.

Drawings are fully dimensioned and the dimension figures on the drawing are deemed to be correct, even if the drawings are not to scale. No dimensions are obtained from a drawing by scaling.

All drawings show full endorsement by a Professional Civil Engineer (including Pr. Eng Number and signature evident on all civil and structural drawings).
6.1 Investigation, survey and Site clearance

The Employer shall instruct the Contractor to conduct additional investigations of existing facilities within the building, such as fire safety systems and plumbing conditions
6.2 Building works
All building works to be compliant with SANS building standards.
6.3 Civil engineering and structural works
All Civil works are to be in compliance with the relevant SANS standards
6.4 Electrical & mechanical engineering works

All electrical and mechanical works are to be in compliance with the relevant SANS standards
6.5 Process control and IT works
N/A
6.6 Other [as required]

7 List of drawings

7.1 Drawings issued by the Employer
No drawings issued by the Employer.
	Drawing  number
	Revision
	Title

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


C3.2
Contractor’s Works Information

	This section of the Works Information will always be contract specific depending on the nature of the works.

It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1.
Typical sub headings could be

a) 
Contractor’s design

b)
Plant and Materials specifications and schedules

c)
Other



This section could also be compiled as a separate file.


Part 4: Site Information
	Document reference
	Title
	No of pages

	
	This cover page
	1

	C4
	Site Information
	1

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	Total number of pages
	2


Part 4: Site Information
5. General description

The Eskom Academy of Learning (EAL) is built on 105 hectares of land and surrounded by a 3.9km radius High Security Mesh Fence perimeter. There are 39 buildings on site, which cater for diverse business operations specializing in among others, training and development, conferencing, hospitality, Information and Communication Technology, accommodation, and business office environment. All this business operations are supplied by a network of the Electrical Reticulation which comprises of the (11/0.4 kV) substations, 400V mini- substations, Kiosks, Distribution Boards and Sub-Distribution Boards.

6. Existing buildings, structures, and plant & machinery on the Site
The actual construction area can only be accessed from the main gate. It is imperative to protect the property, belongings, and vehicles. All areas containing kiosks and distribution boards scheduled for replacement should be considered operational, necessitating sectional or phased construction. Every effort must be made to ensure the safety and health of Eskom staff and the surrounding environment, while minimizing disruption to Eskom staff activities during the construction process.
7. Subsoil information
Not available.
8. Hidden services 

The Contractor will verify and confirm all hidden services before any on-site work begins, with this process being discussed with the project team in advance.
9. Other reports and publicly available information

N/A
� This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.


� Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see � HYPERLINK "http://www.ecs.co.za" ��www.ecs.co.za� 







Contract
2
ecc3 Cover pages


