THE SOUTH AFRICAN NATIONAL

ROADS AGENCY SOC LIMITED

CONTRACT SANRAL N.001-249-2019/1R NSC

CONTRACT TITLE:

NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND

MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

PROJECT DOCUMENT

| BASE DATE: MARCH 2024 | TENDER DOCUMENT VOLUME 3 BOOK…1…OF…1… |
| --- | --- |

CHIEF EXECUTIVE OFFICER

SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

48 TAMBOTIE AVENUE

VAL DE GRACE

PRETORIA, 0184

NAME OF TENDERER: ……………………………………………………

Set sequential number

THE SOUTH AFRICAN NATIONAL

ROADS AGENCY SOC LIMITED

## CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND

MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

THIS DOCUMENT IS ISSUED BY SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

UNDER THE DIRECTION OF THE REGIONAL MANAGER NORTHERN REGION

The South African National Roads Agency SOC Ltd

38 Ida Street

Menlo Park

0081

Tel: (012) 426 6200

LIST OF CONTRACT DOCUMENTS

The following documents form part of this Agreement:

VOLUME 1: 	CONDITIONS OF CONTRACT

Volume 1, Book 1	Conditions of Contract for Design, Build and Operate Projects (2008), issued by the Fédération Internationale des Ingénieurs – Conseils (FIDIC) which the Tenderer shall purchase himself

Volume 1, Book 2	Particular Conditions of Contract (October 2010)

VOLUME 2:  	EMPLOYER’S REQUIREMENTS

Volume 2, Book 1a	Standard Specifications for Operations and Maintenance of CTROM Projects:  Part A:  Glossary of Terms (October 2010) and Part B:  Generic Scope of Works (October 2010)

Volume 2, Book 2a	Standard Specifications for Operations and Maintenance of CTROM Projects:  General (October 2010)

Volume 2, Book 3	Standard Specifications for Operations and Maintenance of CTROM Projects: Electrical and Mechanical Equipment (October 2010)

Volume 2, Book 4a	Standard Specifications for Operations and Maintenance of CTROM Projects:  Toll Systems (October 2010)

Volume 2, Book 5	Standard Specifications for Operations and Maintenance: Electronic Toll Collection (ETC) (September 2010)

Volume 2, Book 6a	Standard Specifications for Operations and Maintenance of CTROM Projects:   Performance Measurement (October 2010)

Volume 2, Book 7a	Standard Specifications for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (October 2010)

Volume 2, Book 8a	Standard Specifications for Operations & Maintenance of CTROM Projects:  ETC Interoperability – Business Rules (October 2010)

VOLUME 3:  	PROJECT DOCUMENT

Volume 3		The Project Document, containing the tender notice, Conditions of Tender, Tender Data, Returnable Schedules, general and particular conditions of contract, project specifications, Pricing Schedule, Form of offer and Site Information is issued by the Employer (see note 3 below). The Employer’s Form of Acceptance and any correspondence from the selected tenderer, performance security-demand guarantee, and all addenda issued during the period of tender will also form part of this volume once a successful tenderer has been appointed.

The conditions of tender are the standard conditions of tender as contained in Annexure C of the STANDARD FOR UNIFORMITY IN ENGINEERING AND CONSTRUCTION WORKS CONTRACTS, AUGUST 2019: Standard conditions of tender, document, which the tenderer may download himself from the CIDB website

https://www.cidb.org.za/download/100/procurement-documents-templates-and-guidelines/6157/standard-for-uniformity-august-2019.pdf

Volume 4:	PROJECT INFORMATION DOCUMENT

Volume 4	Project Information Document

Notes to tenderer:

- 1.	Volume 1 is obtainable from CESA, PO Box 68482, Bryanston, 2021. Tel: (011) 463 2022 Fax: (011) 463 7383, email: general@cesa.co.za

- 2.	Volume 2 is issued in electronic format (PDF) on the SANRAL’s website:

https://www.nra.co.za/service-provider-zone/tenders/open-tenders/.

- 3.	Volume 3 is issued at tender stage in electronic format on SANRAL website (link below) and contains the following files:

https://www.nra.co.za/service-provider-zone/tenders/open-tenders/.

- The full Project Document in PDF format (excluding the standard conditions of tender)

- The returnable forms in Ms Word format

- The pricing data in Ms Excel format

The standard conditions may be downloaded from the CIDB website on the following link:

https://www.cidb.org.za/download/100/procurement-documents-templates-and-guidelines/6157/standard-for-uniformity-august-2019.pdf

At contract stage Volume 3 will be a bound signed paper copy containing the following documents:

- Returnable schedules relevant to the project

- Agreements and Contract Data

- Pricing Data

- Scope of Work

- Site Information

a)	Technical Proposal (USB Flash Drive and printed and bound hard copy enclosed in one Envelope):

-	All Returnable schedules listed in T2.1 List for Returnable Schedule for inclusion in the Technical Proposal.

-	The Returnable Schedules shall be completed in the electronic format stipulated in T2.1 List for Returnable Schedule and stored in a USB Flash Drive and printed and bound hard copy.

-	Where T2.1 List for Returnable Schedule specify submission in a format other than PDF, the specific Returnable Schedule shall be included in both PDF and the stipulated format and stored on the USB Flash Drive.

b)	Financial (USB Flash Drive/CD enclosed in one Envelope)

-	All Returnable schedules listed in T2.1 List for Returnable Schedule for inclusion in the Financial Proposal.

-	The Returnable Schedules shall be completed in the electronic format stipulated in T2.1 List for Returnable Schedule and stored in a USB Flash Drive

-	Where T2.1 List for Returnable Schedule specify submission in a format other than PDF, the specific Returnable Schedule shall be included in both PDF and the stipulated format and stored on the USB Flash Drive.

Both envelopes shall be sealed in one envelope and submitted in accordance with instructions as stated in the Tender Data.

Information provided by a tenderer over and above the above elements of volume 3 shall be treated as information only and will only be bound into the document if the tenderer notes on Form A4: Schedule of Variations or deviations that the information has a bearing on the tender price.

5.	For alternative offers the tenderer shall comply with instructions of item 4.

6.	Volume 3 of the Operations and Maintenance of the Toll Plazas will also be issued at tender stage in electronic format.

Table of Contents	PAGE

PART T1:	TENDERING PROCEDURES	T1

PART T2:	RETURNABLE SCHEDULES	T25

PART C1:	AGREEMENTS AND CONTRACT DATA	C1

PART C2:	PRICING DATA	C69

PART C2	PRICING DATA	C70

PART C3: 	SCOPE OF WORKS	C74

PART C4:	SITE INFORMATION	C350

PART C5: ANNEXURES TO CONTRACT DOCUMENT	C354

PART T1:	TENDERING PROCEDURES

Part T1: Tendering Procedures

TABLE OF CONTENTS	PAGE

T1.1	TENDER NOTICE AND INVITATION TO TENDER (Incorporating SBD1)	T3

T.1.2	TENDER DATA	T5

SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

T1.1	TENDER NOTICE AND INVITATION TO TENDER (Incorporating SBD1)

CLOSING DATE (at 11:00): FRIDAY, 5 April 2024

The South African National Roads Agency SOC Limited (SANRAL) invites tenders for the Nominated Sub-contract for the Design Build Operations and Maintenance of the Toll System for the Operations and Maintenance of Toll Plazas on the N1 North Toll Road. This project is in the province of Limpopo and in the District Municipalities of Waterberg, Capricorn and Vhembe.

The minimum duration of this contract shall be 37.5 months and the maximum duration is 73.5 months, including the 6 weeks for the Establishment Period.

Only Tenderers who are registered on the National Treasury Central Supplier Database (CSD) and meet the minimum requirements for Tenderer’s relevant experience as stipulated in clause C.2.1 at the tender closing date, are eligible to tender.

TENDER DOCUMENTS

Tender documents are available at no cost, in electronic format downloadable from the SANRAL website by the following link https://www.nra.co.za/service-provider-zone/tenders/open-tender/.

Tenderers must have access to Microsoft © Office 2013 and Adobe Acrobat © 9.0 or similar compatible software.

Tenderers must submit, via email, the duly completed Form A1.1 Certificate of Intention to Submit a Tender prior to 23 February 2024. Failure to submit this certificate would result in the tenderer not receiving addenda or additional issued information and may result in the tenderer being non-responsive, if “any material amendment/s” contained in the addenda or additional information is not included in the tender offer/submission.

TENDERER’S CLARIFICATION MEETING

A tender clarification briefing presentation is available to be downloaded from the SANRAL website by the following link: https://www.nra.co.za/sanral-tenders/status?region_id=national A non-compulsory clarification briefing meeting will be held via a virtual platform on 27 February 2024, at 14:00 where the project will be presented. A link to the clarification briefing meeting will be sent to tenderers who complete and submit a Certificate of Intention to Submit a Tender (Form A1.1).A tenderer’s representative cannot represent more than one tenderer at the tender briefing meeting.

COMPLETION AND DELIVERY OF TENDERS

The closing time for receipt of tenders is 11:00 on 5 April 2024.

Telegraphic, telephonic, telex, e-mail, facsimile and late tenders will not be accepted.

Tenders may only be submitted in the format as stated in the Tender Data.

Requirements for sealing, addressing, delivery, opening and assessment of tenders are stated in the Tender Data.

Queries relating to issues arising from these documents may be addressed to:

Bidding procedure and technical enquiries

Contact person: The Procurement Office

E-mail: ProcurementNR4@sanral.co.za

T.1.2	TENDER DATA

The conditions of tender are the standard conditions of tender as contained Annexure C of the CIDB STANDARD FOR UNIFORMITY IN ENGINEERING AND CONSTRUCTION WORKS CONTRACTS as per Government Notice No. 423 published in Government Gazette No. 42622 of 08 AUGUST 2019 and as amended from time to time.

https://www.cidb.org.za/wp-content/uploads/2021/07/Standard-for-Uniformity-August-2019.pdf

The standard conditions of tender make several references to the tender data for details that apply specifically to this tender. The tender data shall have precedence in the interpretation of any ambiguity or inconsistency between the tender data and the standard conditions of tender

Definitions

Add the following to Definitions:

Wherever reference is made in the documentation to bill of quantities it shall also mean pricing schedule.

Wherever reference is made in the documentation to Contractor it shall also mean Service Provider or Operator.

Each item of data given below is cross-referenced to the clause in the standard conditions of tender to which it mainly applies.

| Clause Number | Data |
| --- | --- |
| C.1 | GENERAL |
| C1.1 | Actions The Employer is The South African National Road Agency SOC Limited (SANRAL). The Employer’s domicilium citandi et executandi (permanent physical business address) is: 48 Tambotie Avenue Val De Grace, Pretoria, 0184 The Employer’s address for communication relating to this project is: The Regional Manager (Northern Region) The South African National Roads Agency SOC Ltd 38 Ida Street Menlo Park Pretoria, 0081 |
| C.1.2 | Tender Documents The tender documents issued by the Employer comprise: VOLUME 1; CONDITIONS OF CONTRACT. Book 1; Contract for Design, Built and Operate Projects (2008) published by Fédération Internationale des Ingénieurs-Conseils (FIDIC). Book 2; Particular Conditions of Contract (October 2010). VOLUME 2; EMPLOYERS REQUIREMENTS: STANDARD SPECIFICATIONS. Book 1a; Standard Specifications for Operations and Maintenance of CTROM Projects: Part A: Glossary of Terms and Part B: Generic Scope of Works (October 2010). Book 2a; Standard Specifications for Operations and Maintenance of CTROM Projects: General (October 2010). Book 3; Standard Specifications for Operations and Maintenance of CTROM Projects: Electrical and Mechanical Equipment (October 2010). Book 4a; Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (October 2010). Book 5; Standard Specifications for Operations and Maintenance of CTROM Projects: Electronic Toll Collection (ETC) (September 2010). Book 6a; Standard Specifications for Operations and Maintenance of CTROM Projects: Performance Measurement (October 2010). Book 7a; Standard Specifications for Operations and Maintenance of CTROM Projects: Payment Methodology and Description of Payment Items (October 2010). Book 8a; Standard Specifications for Operations and Maintenance of CTROM Projects: ETC Interoperability - Business Rules (October 2010). VOLUME 3; PROJECT DOCUMENT. Part T1; TenderING Procedures. T1.1; Tender Notice and Invitation to Tender. T1.2; Tender Data. Part T2; Returnable Schedules. T2.1; List of Returnable Schedules. T2.2; Returnable Schedules. Part C1; Agreement and Contract DATA. C1.1; Form of Offer and Acceptance. C1.2; Contract Data. C1.3; Particular Conditions - Part B: Special Provisions. C1.4; Other Standard Forms. Part C2; Pricing Data. C2.1; Pricing Instructions. C2.2; Schedule of Payments/Cost Matrix. Part C3; SCOPE OF WORK. C3.1; Project Description. C3.2; Particular Specifications for Operations and Maintenance. C3.3; Environmental Management Plan. C3.4; Occupation Health and Safety. C3.5; Risk Assessment Plan. Part C4 pART D; Site Information Stakeholder and Community Liaison and Targeted Labour and Targeted Enterprises Utilisation and Development. PART E; ANNEXURES. VOLUME 4; PROJECT INFORMATION DOCUMENT. |
| C.1.4 | Communication and employer’s agent The Employer’s Agent is SANRAL Procurement Office They can be contacted at: ProcurementNR4@sanral.co.za |
| C.1.5 | Cancellation and Re-Invitation of Tenders |
| C.1.5.3 | Clause C.1.5.3 is not applicable. |
| C.1.6.2 | Competitive negotiation procedure Clause C.1.6.2 is not applicable. |
| C.2 | Tenderer’s Obligations |
| C.2.1 | Eligibility Only those tenderers who satisfy the following eligibility criteria are eligible to submit tenders: - National Treasury Central Supplier Database (Form A3.4) Tenderers, or in the event of a Joint Venture, each member of the Joint Venture, shall be registered on the National Treasury Central Supplier Database at the closing date for tender submissions. Tenders received from such tenderers who do not comply with this requirement, will be declared non-responsive. - Tenderer’s Relevant Experience The tenderer must be able to show that he has relevant experience by providing information of at least: 3 (three) similar or relevant project(s), of which one should be to the value of at least R 10 million per project, while the other two (2) should be at least to the value of R5 million each, which has either started or been completed within the last 15 years, or which is still ongoing (subject to the provisions of Form D5.1 and Form D5.2). The relevant experience for all 3 projects must be in at least 2 of the following key areas of which at least 1 project’s 1 key area is required to be in ii) Development and/ or maintenance of a toll system (or sub-systems) (Form D5.1 & Form 5.2): - Operations and maintenance of a toll project; - Development and/ or maintenance of a toll system (or sub-systems); - Multi-disciplinary project management; - Development and maintenance of IT systems (not necessarily Toll related). |
| C.2.2 | Cost of tendering Tender documents are available from SANRAL website at no cost. |
| C.2.6 | Acknowledge addenda Failure to apply instructions contained in addenda issued by the Employer will render a Tenderer’s offer non-responsive in terms of Condition of Tender C.3.8. Test for Responsiveness. |
| C.2.7 | Clarification meeting A tender clarification briefing presentation is available to be downloaded from the SANRAL website by the following link: https://www.nra.co.za/sanral-tenders/status?region_id=national. A non-compulsory clarification briefing meeting will be held via a virtual platform on 27 February 2024 at 14:00 where the project will be presented. A link to the clarification briefing meeting will be sent to tenderers who complete and submit a Certificate of Intention to Submit a Tender (Form A1.1) within the specified time. A link to the clarification briefing meeting will be sent to tenderers who complete and submit a Certificate of Intention to Submit a Tender (Form A1.1). A tenderer’s representative cannot represent more than one tenderer at the tender clarification briefing meeting. The onus rests with the tenderer to ensure that the representative attending/reading the clarification briefing presentation is appropriately qualified to understand all directives and clarifications given in the presentation. The signature on the duly completed and signed Form A1 shall be considered proof that the tenderer read the whole clarification briefing presentation and clearly understood all directives and clarifications given in the presentation. |
| C.2.8 | Seek clarification Request clarifications at least 12 (twelve) working days before the closing date. |
| C.2.9 | Insurance The Principal Employer has insurance for Employers Facilities, Permanent Design-Build Assets and Equipment provided by the Principal Employer. Refer to C1.2.5 APPENDIX 3 TO CONTRACT DATA: INSURANCE DATA. |
| C.2.10 | Pricing the tender offer |
| C.2.10.3 | The rates and prices shall be adjusted as specified in the conditions of contract clause 13.8 Adjustments for Changes in Costs |
| C.2.10.4 | Tenderers are required to state the rates and currencies in Rand |
| C.2.12 | Alternative tender offers |
| C.2.12.1 | An alternative tender offer shall only be considered from a tenderer whose postulated tender offer is the preferred tender. A tenderer wishing to submit an alternative offer (excluding alternative offers of different contract duration, retention guarantees, discounted offers or different compliant material sources) shall first apply to the Employer’s agent for confirmation that the Employer’s standards and requirements envisaged in the design are not compromised or reduced. Such confirmation must have been provided by the Employer’s agent in writing within 10 working days after receipt of the application but not later than 5 working days before the date and time of tender closing given in Tender Data clause 4.15, or as extended by an addendum sent to all tenderers. Also, not acceptable as alternative offers are alterations to contingency pay items provided in the bill of quantities (pricing schedule), fixed prices for individual items or a fixed price contract. If an alternative proposal is confirmed to be acceptable, calculations, drawings and all other pertinent technical information and characteristics as well as proposed modification of, or alternative to, the Pricing Data must be submitted with the alternative tender offer to enable the Employer to evaluate the efficacy of the alternative and its principal elements, to take a view on the degree to which the alternative complies with the Employer’s standards and requirements and to evaluate the acceptability of the pricing proposals. Calculations must be set in clear and logical sequence and must clearly reflect all design assumptions. Pricing Data must reflect all assumptions in the development of the pricing proposal. Acceptance of an alternative offer will mean acceptance in principle of the offer. It will be an obligation of the contract with the tenderer, in the event that the alternative is accepted, to accept full responsibility and liability that the alternative offer complies in all respects with the Employer’s standards and requirements. |
| C.2.13 | Submitting a tender offer |
| C.2.13.2 | The returnable documents shall be electronically completed in their entirety, submitted on the issued software format or fully compatible format, unless otherwise specified. Submission in the tender box - Submit the tender offer electronically on a flash drive and printed hard copy of Form of Offer and summary of pricing schedule. - (In the relevant MS Word 2013 and MS Excel 2013 format as issued, and not in .pdf format, except where so specified.) |
| C.2.13.3 | Submission in the tender box The tenderer is required to upload all certificates as listed in the List of Returnable Schedules as scanned copies, in .pdf format, on the flash drive |
| C.2.13.4 | The tenderer is required to submit all certificates as listed in the Schedule of Tender Compliance (Form F1) in the stipulated format. |
| C.2.13.6 | A two-envelope procedure will apply as follows: Submission in the tender box - A folder is provided marked “TECHNICAL PROPOSAL” - Ensure that all returnable schedules listed in T2.1 List of Returnable Schedules for inclusion in the Technical Proposal and listed in the Technical Proposal folder are electronically completed on a USB Flash Drive Wherever it is a requirement to attach certificates or letters to the returnable schedules, these should be scanned in, on the Flash Drive in .pdf format. Contents of USB Flash Drive shall be printed and bound in hard copy. The completed Flash Drive, the printed and bound hard copy should be marked with the tenderer’s company name, the project number and description and marked “TECHNICAL PROPOSAL”. - Scan and insert a valid B-BBEE certificate. - Electronically sign the declaration in the folder. - Insert the electronically completed Flash Drive, the printed and bound hard copy in an envelope marked “TECHNICAL PROPOSAL”. - A folder is provided marked “FINANCIAL PROPOSAL” - Ensure that all returnable schedules listed in T2.1 List of Returnable Schedules for inclusion in the Financial Proposal and listed in the Financial Proposal folder are electronically completed on a Flash Drive (Contract Data and Pricing Schedule). Wherever it is a requirement to attach letters or certificates to the returnable schedules, these should be scanned in, on the USB Flash drive in .pdf format. Contents of Flash Drive shall be printed and bound in hard copy. The completed Flash Drive, the printed and bound hard copy should be marked with the tenderer’s company name, the project number and description and marked “FINANCIAL PROPOSAL”. - Electronically sign the declaration in the folder. - Complete and electronically sign the Form of Offer and scan into the folder. A draft copy of this form is provided. - Scan and insert a copy of the Summary of Pricing Schedule into the folder. - Insert the electronically completed Flash Drive and the printed and bound hard copy in an envelope marked “FINANCIAL PROPOSAL – DO NOT OPEN WITH TECHNICAL PROPOSAL”. 3. Each envelope shall state on the outside the Employer’s address, contract number and title as well as the Tenderer’s name, authorised representative’s name, postal address and contact telephone numbers. 4. Seal both envelopes in an outer envelope with the words “TENDER” clearly marked and bearing the Employer’s name, contract number and description as well as the Tenderer’s authorised representative’s name, postal address and contact details. If a tenderer submits: - One envelope with one document or one Flash Drive and printed hard copy (financial and technical); or - Incorrectly labelled envelopes where the Financial Offer is labelled Technical, and the Technical Offer is labelled financial. The tender will be declared non-responsive. |
| C.2.14 | Information and data to be completed in all respects Provided that the omission is not a material omission, the Employer reserves the right to condone the omission and may waive any nonconformities in the tender. Provided that the omission is not a material omission, the Employer reserves the right to condone the omission and may request the tenderer to submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the tender related to documentation requirements. |
| C.2.15 | Closing time |
| C.2.15.1 | Submission in tender box The Employer’s address for delivery of tender offers and identification details to be shown on each tender offer package are: Location of tender box: Reception Area Physical address: The South African National Roads Agency SOC Ltd The Regional Manager Northern Region 38 Ida street Menlo Park Pretoria 0081 Identification details: Place the signed original tender offer in a package marked with the tenderer’s company name, the project number and description: CONTRACT SANRAL N.001-249-2019/1R NSC FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD Tenderer’s company name: project number: description Location of tender box: Physical address: Tenders must be submitted during hours (09:00 to 16:00) Monday to Friday at the Employer’s address. It is in the tenderer’s interest to ensure that the delivery of the tender offer is recorded in the Employer’s tenders received register and deposited in the tender box. |
| C.2.16 | Tender offer validity |
| C.2.16.1 | The tender offer validity period is 24 weeks. |
| C.2.16.2 | Should the tenderer not accept the validity extension or if the tenderer does not withdraw a condition attached to a conditional acceptance, this shall result in a non-responsive tender or the tender is considered to have made an election to exclude itself from the tender process. |
| C.2.16.3 | Where a tenderer, at any time after the opening of his tender offer, but prior to entering into a contract based on his tender offer: - Withdraws his tender; - Gives notice of his inability to execute the contract in terms of his tender; or - Fails to comply with a request made in terms of C.2.17, C.2.18 or C.3.9, such tenderer shall be barred from tendering on any of the Employer’s tenders for a period to be determined by the Employer, but not less than six (6) months from a date determined by the Employer. This sanction also applies to tenders under evaluation and not yet awarded. This sanction does not apply to tenders under evaluation where a request for extension of the validity period was not accepted by the tenderer. The Employer may fully or partly exempt a tenderer from the provisions of this condition if he is of the opinion that the circumstances justify the exemption. |
| C2.17 | Clarification of tender offer after submission Any clarification requested under this clause must be provided within 1 (one) working day of date of request. |
| C.2.18 | Provide other material |
| C.2.18.1 | Any additional information requested under this clause must be provided within five (5) working days of date of request. |
| C.2.19 | Inspections, tests and analysis Access shall be provided for the following inspection of the Works: The documents indicating all the requirements and procedures as specified are available in Volume 4 of this Tender document. Contact the Employer's Agent’s at ProcurementNR4@sanral.co.za to arrange for a site visit to visit the toll plaza(s). |
| C.3 | The Employer’s undertakings |
| C.3.1 | Responding to requests from the tenderer |
| C.3.1.1 | The employer shall respond to clarifications received up to 12 (twelve) working days before tender closing date. The Employer shall respond to any clarifications from the tenderers emanating from the addenda until 3 working days before tender closing date. |
| C.3.2 | Issue Addenda The employer shall issue addenda until 10 (ten) working days before tender closing time. |
| C.3.4 | Opening of tender submissions |
| C.3.4.1 | Two Envelope: The time for opening of the tender offer (TECHNICAL PROPOSALS) via live streaming or at Northern Region offices are: Time: 11h00 on 5 April 2024 Location: A live streaming link will be provided to all tenderers who submitted their Form A1.1. |
| C.3.5 | Two-envelope system The time for opening of the Financial offers via live streaming shall be communicated to all tenderers having achieved the minimum number of points for quality as prescribed. The financial offer of all tenderers who failed to achieve the minimum number of points for quality shall be returned unopened. Reasons for non-responsive/not achieving the threshold will only be communicated when the tender process is concluded, in terms of Clause C.3.16 of the Tender Data. The scores obtained for the non-financial proposals will not be announced at the opening of the financial offers /proposals.” |
| C.3.7 | Grounds for rejection and disqualification Prior to disqualification, the Employer shall inform the tenderer and give the tenderer an opportunity to make representations within 14 (fourteen) days as to why the tender submitted should not be disqualified and as to why the tenderer should not be restricted by the National Treasury from conducting any business with any organ of state for a period not exceeding 10 years. In the event of disqualification, the Employer may, at its sole discretion, claim damages from the tenderer and impose a specified period during which tender offers will not be accepted from the offending tenderer and the Employer shall inform the National Treasury. |
| C.3.8 | Test for responsiveness |
| C.3.8.2 | A Substantially responsive tender is a tender in which all of the material information and documentation submitted at close of tender contains non-material and non-conformities to the bid specifications but are not related to price. The correction of any such documentation or information, or the condonement for the non-inclusion of any such document or information may not be prejudicial towards the offer and claimed preference of any responsive tender or be construed to be giving an unfair advantage to any tender. A responsive tender is also one that conforms to all the terms, conditions, and scope of work of the tender documents, without material omissions. The test for a material omission is the same as the test for a material deviation or qualification. Amongst reasons for tender cancellation, SANRAL will cancel the tender should all tenders be non-responsive in terms of Clause C.3.8 and no negotiations will be conducted. |
| C.3.9. | Arithmetical errors, omissions, discrepancies and imbalanced unit rates |
| C.3.9.1 | Check responsive tenders for discrepancies between amounts in words and amounts in figures. Where there is a discrepancy between the amounts in figures and the amount in words, the amount appearing in the Summary of Schedule of Payments/Cost Matrix shall govern. |
| C.3.9.3 | Check the highest ranked tender or tenderer with the highest number of tender evaluation points after the evaluation of tender offers for: - The gross misplacement of the decimal point in any unit rate; - Omissions made in completing the pricing schedule or Schedule of Payments/Cost Matrix; or - Arithmetic errors in: i) line item totals resulting from the product of a unit rate and a quantity in bills of quantities or schedules of prices; or ii) the summation of the prices. - imbalanced unit rates. Notify shortlisted tenderers of all errors, omissions or imbalanced rates that are identified in their tender offers and either confirm the tender offers as tendered or accept the corrected total prices. |
| C.3.9.4 | Where the tenderer elects to confirm the errors, omissions or re-balancing of imbalanced rates the tender offer shall be corrected as follows: - If bills of quantities or Schedule of Payments/Cost Matrix apply and there is an error in the line item total resulting from the product of the unit rate and the quantity, the unit rate shall govern, and the line item total shall be corrected. Where there is an obviously gross misplacement of the decimal point in the unit rate, the line item total as quoted, and the unit rate shall be corrected. - Where there is an error in the total of the prices either as a result of other corrections required by this checking process or in the tenderer’s addition of prices, the total of the prices shall be corrected. - Where the unit rates are imbalanced, the tenderer shall adjust such rates by increasing or decreasing them and selected others while retaining the total of the prices derived after any other corrections made under (a) and (b) above. Where there is an omission of a line item, no correction is possible, and the offer may be declared non-responsive. Should the original price not be retained after balancing, the tenderer will be rendered non responsive Declare as non-responsive and reject any offer from a tenderer who elects not to accept the proposed correction of the; errors, omissions or imbalanced rates. During testing of tender responsiveness, clause C.3.8 of CIDB tender conditions will be applicable. The tenderer is required to submit balanced unit rates for rate only items in the pricing schedule. The rates submitted for these items will be taken into account in the evaluation of tenders. If the Form of Offer is submitted but the Pricing Schedule is omitted, where rate only items are applicable; or If a signed Form of Offer is submitted with an incomplete pricing schedule (no summary to tender) that does not balance back to the Form of Offer and the Pricing schedule is incomplete; or If a signed Form of Offer is submitted with an incomplete pricing schedule that does not balance back to the Form of Offer and only summary of Pricing Schedule submitted; then the rates cannot be evaluated and the tender shall be declared non-responsive |
| C.3.11 | Evaluation of tender offers Evaluating price and preference - 80/20 preference point system for acquisition of goods and services for Rand value equal to or above R2 000 and up to R50 million The following formula will be used to calculate thee points out of 80 for price: Ps =80(1-(Pt-Pm)/Pm) Where: Ps is the points scored for price of tender under consideration. Pt is the price of the tender under consideration; and Pm is the price of the lowest acceptable tender. - 90/10 preference point system for acquisition of goods and services for Rand value above R50 million The following formula will be used to calculate thee points out of 90 for price: Ps =90(1-(Pt-Pm)/Pm) Where: Ps is the points scored for price of tender under consideration. Pt is the price of the tender under consideration; and Pm is the price of the lowest acceptable tender. In the event that the calculated value is negative, the allocated score shall be 0 (zero). Scoring preference (Specific Goals): Points for specific goals will be awarded according to the table below: Specific goals; Criteria; 10 points; 20 points. Point allocation; Maximum points; Point allocation; Maximum points. B-BBEE Level; Level 1; 10.00; 10.00; 20.00; 20.00. Level 2; 9.00; 18.00. Level 3; 6.00; 14.00. Level 4; 5.00; 12.00. Level 5; 4.00; 8.00. Level 6; 3.00; 6.00. Level 7; 2.00; 4.00. Level 8; 1.00; 2.00. Non-compliant contributor; 0.00; 0.00. A valid B-BBEE verification certificate must be submitted. - The tenderer’s scorecard shall be a B-BBEE Certificate issued in accordance with: - the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry; or - in the event that the Measured Entity operates in more than one sector or a sub-sector, the scorecard for the sector or sub-sector in which the majority of its core activities (measured in terms of annual revenue) are located will be acceptable. The tenderer must comply with the annual revenue thresholds for EME or QSE or Generic in accordance with the amended Construction Sector Codes; or - the amended Codes of Good Practice published in Notice 303 of 2019 of Government Gazette No. 42496 on 31 May 2019 by the Department of Trade and Industry or; - the Information and Communication Technology (ICT) Sector Codes (Published in Notice 1387 of Government Gazette No. 40407 of 7 November 2016); or - ;the Financial Sector (Published in Notice 1325 of Government Gazette No. 41287 of 1 December 2017); or - The Integrated Transport Sector Codes (Published in Notice 1162 of Government Gazette No. 32511 of 21 August 2019). - The scorecard shall be submitted as a certificate attached to Returnable Schedule Form D1; and - The certificate shall: - be valid at the tender closing date; and - have been issued by a verification agency accredited by the South African National Accreditation System (SANAS); or - be in the form of a sworn affidavit or a certificate issued by the Companies and Intellectual Property Commission in the case of an Exempted Micro Enterprise (EME) with a total annual revenue of less than R3 million if issued in accordance with the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry; and - have a date of issue less than 12 (twelve) months prior to the original advertised tender closing date (see Tender Data C.2.15); and - A valid BBBEE Certificates shall contain: - Name of enterprise as per enterprise registration documents issued by CIPC, and enterprise business address. - Value-Added Tax number, where applicable. - The B-BBEE Scorecard against which the certificate is issued, indicating all elements and scores achieved for each element. The actual score achieved must be linked to the total points as per the relevant Codes. - B-BBEE status with corresponding procurement recognition level. - The relevant Codes used to issue the B-BBEE verification certificate. - Date of issue and expiry (e.g. 9 June 2018 to 8 June 2019). Where a measured entity was subjected to a re-verification process, due to material change, the B-BBEE Verification Certificate must reflect the initial date of issue, date of re-issue and the initial date of expiry. Re-verification does not extend the lifespan of the B-BBEE Verification Certificate. - Financial period which was used to issue the B-BBEE Verification Certificate. - A valid Sworn Affidavit shall contain: - Name/s of deponent as they appear in the identity document and the identity number. - Designation of the deponent as either the director, owner or member must be indicated in order to know that person is duly authorised to depose of an affidavit. - Name of enterprise as per enterprise registration documents issued by the CIPC, where applicable, and enterprise business address. - Percentage black ownership, black female ownership and whether they fall within a designated group. - Indicate total revenue for the year under review and whether it is based on audited financial statements or management accounts. - Financial year-end as per the enterprise’s registration documents, which was used to determine the total revenue. The valid format of the Financial Year-End is Day/Month/Year - B-BBEE status level. An enterprise can only have one status level. - Date deponent signed and date of Commissioner of Oath must be the same. - Commissioner of Oath cannot be an employee or ex officio of the enterprise because, a person cannot by law, commission a sworn affidavit in which they have an interest, and - Compliance with any other information requested to be attached to Returnable Schedule Form C1; and - In the event of a Joint Venture (JV), a project-specific consolidated (SANRAL project number indicated) valid B-BBEE verification certificate in the name of the JV, issued by a verification agency accredited by the South African National Accreditation System (SANAS) shall be submitted. Criteria for breaking deadlock If two or more tenders score the same number of points and these tenders are also the highest ranked tenders, the tender with the highest preference points will be recommended for award. If functionality is part of the evaluation process and two or more tenders score equal total points and equal preference points, the tender that scored the highest points for functionality will be recommended for award. If two or more tenders score the same number of financial points and preference points and these tenders are also the highest ranked tenders, the tenderer to be recommended for award will be decided by the drawing of lots. The quality criteria maximum score and scoring mechanism in respect of each of the criteria are as follows: A quality scoring is as follows: Item; Functional Scoring; Form; Max Score. 1; Relevant Experience of the Tendering Entity; D5.1 & D5.2; 50. 2; Tendering Entity's QMS Credentials; D14; 10. 3; Participation of Key Previously Disadvantaged Individuals (PDI) Staff; D14; 10. 4; Key Resources (CV's to be provided); D4 & D14; 68. 5; Tendering Entity's Proposed Design, Build, Software Development and Operations and Maintenance Plan; D14; 62. 6; Technical and System Information; D10; 72. Total Score; 272. Score (Minimum = 75%); 204. The detailed scoring is explained in APPENDIX 1: BREAKDOWN OF QUALITY CRITERIA. |
| C.3.13 | Acceptance of a tender offer The conditions stated in clauses C.3.13(a) to (f) of the Conditions of Tender as well as the following additional clauses C.3.13(g) to (l) shall be applied as objective criteria in terms of section 2(1)(f) of the Preferential Procurement Policy Framework Act, 2000 and as compelling and justifiable reasons in terms of Conditions of Tender clause C.3.11: - The tenderer or any of its directors is not listed on the Register of Tender Defaulters in terms of the Prevention and Combating of Corrupt Activities Act of 2004 as a person prohibited from doing business with the public sector; - The tenderer has not abused the Employer’s supply chain management system; - The tenderer has not failed to perform on any previous contract and has not been given a written notice to this effect; and - The tenderer is tax compliant. The recommended tenderer who becomes non-compliant, prior to award, shall be notified and must become compliant within seven (7) working days of the date of being notified. A recommended tenderer who remains non-compliant after the seven (7) working days of being notified, shall be declared non-responsive. - the tenderer is registered and in good standing with the compensation fund or with a licensed compensation insurer. The licensed compensation insurer shall be approved by Department of Labour in terms of Section 80 of the Compensation for Injury and Disease Act, 1993 (Act No. 130 of 1993). - Price negotiations. - If the price offered by a tenderer scoring the highest points is not market related, the Organ of state may not award the tender to that tenderer. - The Organs of state may – - Negotiate a market related price with the tender scoring the highest points or cancel the tender; - If the tenderer does not agree to a market related price, negotiate a market related price with the tenderer scoring the second highest points or cancel the tender; - If the tenderer scoring the second highest points does not agree to a market related price, negotiate a market related price with the tenderer scoring the third highest points or cancel the tender; - If a market related price is not agreed as envisaged in paragraph 2(iii), the organ of state must cancel the tender. In addition to the requirements under paragraph (b) of the Conditions of Tender, in the event that a due diligence is performed as part of the tender evaluation, the due diligence report will be used to evaluate the tenderer’s ability to perform the contract as stated in paragraph (b) The due diligence will evaluate the overall risk associated with the tender. The due diligence will take into consideration the following: - Assessment of financial statements to assess the financial position of the tenderer and its ability to obtain the necessary guarantees or insurances, - Evaluation of managerial and technical ability and available resources in relation to the proposed tender, - Integrity Risk Evaluation, - Operations, Activities, Locations and Key Customers, - Reference checks from previous clients, and - Risk rating (i.e. High Risk, Medium to High risk, Medium risk or Low risk) of the tenderer. |
| C.3.16 | Registration of the award SANRAL will notify unsuccessful tenderers when the tender process has been concluded. Any unsuccessful tenderer may request a debriefing in writing as specified in Clause C.3.19. |
| C3.17 | Provide copies of the contracts The number of paper copies of the signed contract to be provided by the Employer is one (1). |
| C.3.18 | Provide written reasons for actions taken All requests shall be in writing. |
| ADDITIONAL CONDITIONS OF TENDER CLAUSES |  |
| SC.3.19 | Jurisdiction Unless stated otherwise in the tender data, each tenderer and the Employer undertake to accept the jurisdiction of the law courts of the Republic of South Africa. |

TENDER DATA: APPENDIX 1: BREAKDOWN OF QUALITY CRITERIA (CLAUSE c.3.11)

| C.3.11 | Functionality Criteria Only tenderers who meet the minimum 75% threshold for Functionality will be considered responsive. The functional criteria listed will be combined to determine a functional score with a maximum of 257 points. A minimum threshold of 75% 204 points out of a potential 272 points score) is required. The functional score will be calculated as follows: Item; Functional Scoring; Form; Max Score. 1; Relevant Experience of the Tendering Entity; D5.1 & D5.2; 50. 2; Tendering Entity's QMS Credentials; D14; 10. 3; Participation of Key Previously Disadvantaged Individuals (PDI) Staff; D14; 10. 4; Key Resources (CV's to be provided); D4 & D14; 68. 5; Tendering Entity's Proposed Design, Build, Software Development and Operations and Maintenance Plan; D14; 62. 6; Technical and System Information; D10; 72. Total Score; 272. % Score (Minimum = 75%); 204. The detailed scoring will be as follows: - Relevant Experience of the Tendering Entity; 50. The Tenderer must list similar projects matching the subject project’s scope of work that have been satisfactorily and substantially completed, and only in the past 15 years. (at least completed as a prime contractor, joint venture member, management contractor or sub-contractor). The relevant experience must be in at least 2 of the following key areas of which one is required to be ii) Development and/ or maintenance of a toll system (or sub-systems): Only the following type of projects will be considered for functional scoring purposes: - Operations and maintenance of a toll project; - Development and/ or maintenance of a toll system (or sub-systems); - Multi-disciplinary project management; - Development and maintenance of IT systems (not necessarily Toll related). The projects listed shall only be considered if the value of the project meets the following criteria: - Major Projects refer to projects with a value in excess of R 5 million; - Large Projects refer to projects with a value in excess of R 15 million, and - Mega Projects refer to projects with a value in excess of R 45 million. Completed contracts must be listed under Form D 5.1 and Contracts in progress under Form D 5.2. and will be evaluated as indicated below.. Experience on similar projects; Max Points. a; No evidence of a similar project.; 0. b; Indicate evidence of a similar project(s), where project was a Major project, and the experience gained was in at least two (2) of the areas listed above.; 20. c; Evidence of a similar project(s), where projects presented were either a Large project, or three (3) Major projects, and the experience gained was in at least two (2) of the areas listed above.; 30. d; Evidence of a similar project(s), where projects presented were either a Mega project, or three (3) Major projects, and the experience gained was in at least three (3) of the areas listed above.; 40. e; Evidence of a similar project(s), where projects presented were at least one (1) Mega project, and one (1) Large project, and the experience gained was in all of the areas listed above.; 50.. - Tendering Entity's Quality Management System QMS Credentials- Form D14; # 10. 2.1 Scoring:. - No evidence of QMS; # 0. - Evidence of QMS based on ISO-9001; # 5. - Evidence of ISO-9001 certified QMS; # 10. - Participation of Previous Disadvantaged Individual (PDI) Staff -Form D14; # 10. 3.1 Scoring:. - Contracts Engineer (Nominated Sub-contractor’s (NSC) Representative); # 2.5. - Quality Control Officer; # 2.5. - Maintenance Manager; # 2.5. - System/ software support specialist; 2.5. - Key Resources (Forms D4.1-D4.4); 68. Key Persons; Max Points. 4.1 Contracts Engineer (Nominated Sub-contractor’s (NSC) Representative) (Form D4.1); 12. - Qualification. - A relevant Business, Commerce, Law or Engineering degree or diploma (3 or more years full time study) or higher qualification; 4. - Relevant Experience. - Ten (10) years relevant experience; 2. - Contract Management experience;; 2. - The resource should also have experience in:. - Business/Operations Management;; 1. - Systems Integration Management;; 0.5. - Maintenance (Systems and Facilities) Management;; 0.5. - FIDIC Experience/Dispute Resolution;; 1. - Performance Management.; 1. 4.2 Quality Control Officer (Form D4.2); 12. - Qualification; MAX 4. - National Diploma OR; 2. - BTech or relevant degree (e.g. BSC/BEng) or higher.; 4. - Relevant Experience. - At least ten (10) years relevant experience;; 4. - The resource should have experience in:. - Testing and assessing of software products; 1. - Identifying defects or potential issues and determining ways to resolve; 1. - Recording and reporting issues; 1. - Supporting process improvements throughout the testing and quality assurance processes.; 1. 4.3 Maintenance Manager (Form D4.3); 12. - Qualification; MAX 4. - National Diploma OR; 2. - B-Tech or relevant degree (e.g. BSC/BEng) or higher.; 4. - Relevant Experience. - Ten (10) years’ relevant experience; 4. - The resource should have experience in:. - Project Management;; 0.5. - Performance Management;; 1. - Documentation Development (procurement) and procurement process;; 1. - Hardware Maintenance Programmes;; 0.5. - Maintenance Audit Reviews;; 0.5. - Maintenance Trend Analysis.; 0.5. 4.4 System/ Software Support Specialist (Form D4.4); 12. - Qualification; MAX 4. - National Diploma OR; 2. - BTech or computer science, information systems or relevant degree (e.g. BSC/BEng) or higher.; 4. - Relevant Experience. - Ten (10) years’ relevant experience; 4. - The resource should have experience in:. - Support to end-users via email, phone, web or in-person; 1. - Monitoring and owning all support related metrics including ticket backlog, average time to close, etc.; 1. - Working with development teams to modify and engineer software solutions and configurations; 1. - Team management; resource planning and scheduling.; 1. Organisational Structure / organogram. 4.5 Network and security specialist (Form D4.5); 12. - Qualification; MAX 4. - National Diploma OR; 2. - BTech or computer science, information systems or relevant degree (e.g. BSC/BEng) or higher.; 4. - Relevant Experience. - Ten (10) years’ relevant experience; 4. - The resource should have experience in:. - Local Area and Wide Area network design; 1. - Network architecture; 1. - Network performance monitoring, maintenance, and support; 1. - Network/cyber security; 1. Organisational Structure / organogram. 4.6 Organisational Structure (Form D14); 8. - Organogram indicating the actual numbers of staff proposed for the maintenance and support for each Toll Plaza (Control Centre and remote Plazas); 2. - Proposed maintenance and support team(s) including a breakdown of staff categories reflected in the Costs Matrix; 2. - Organogram indicating the actual numbers of staff proposed for the Design-Build Sections for each Toll Plaza (Control Centre and remote Plazas); 2. - Proposed design and installation team(s) including a breakdown of staff categories reflected in the Costs Matrix; 2. - Tendering Entity's Proposed Development, Operations and Maintenance Plan (Technical Proposal Form D14); 62. The tenderer shall submit a signed copy of his Technical Proposal in Form D14, providing a clear statement of his / her understanding and approach to execute the work. The statement shall use the headings and sub-headings listed on Form D14 and the tenderer’s statement and the contents of his plan will be evaluated as indicated below.. Tenderer’s Technical Proposal; Max Points. Note: Aspects not specifically listed here are evaluated elsewhere and could also be using information on other Forms.. - Proposed Development, Operations and Maintenance Plan; 26. - Financial Statements; 4. - Financial Statements; 4. - Risk Management; 5. - Role players; 1. - Transaction risk; 1. - Interfaces; 1. - Performance Management; 1. - Reporting; 1. - Interoperability of and with various systems and interfaces; 7. - The role of the national TCH; 1. - Dealing with Road Queries (point of presence, Call Centre, etc.); 1. - TCH interface management; 1. - Electronic transaction file transfer; 1. - Account settlement; 1. - Road User mobility account registration; 1. - Tag Management (procurement, distribution and stock control); 1. - Establishment; 10. - Staff procurement; 3. - Training; 1. - Sub-Contractor procurement; 1. - On-site establishment; 1. - Maintenance and support of legacy Toll System (system taken over); 2. - Envisaged timelines and program; 2. - Toll System Development and Maintenance; 36. - Financial Management (Including Revenue Streams); 4. - Understanding of the processes, revenue streams and system requirements; 2. - Provision of a secure Tolling System with a high availability; 2. - System Maintenance (All Lines of Support); 11. - Understanding the System Maintenance Scope of Works; 2. - Hardware and software support (in the context of the Contractor's scope); 2. - Fault reporting and responses; # 2. - The proposed Resource Management plan (including all resource categories and numbers); # 2. - Managing toll system and spares availability risk (including Business Continuity solutions); # 2. - Asset replacement and hand back; # 1. - Performance Management; 8. - Performance monitoring/reporting/improvement; # 8. - Quality Assurance; 2. - QA Plan; # 2. - Environmental Management; 2. - Environmental Management plan; # 2. - Health and Safety; 2. - Health and Safety plan; # 2. - Toll system roll out programme; 5. - Assessment of feasibility of programme, all sections, components, and milestones reflected.; 5. - System Security; 2. - System Security plan; # 2. 6. Technical and System Information (Form D10); 72. Note: Aspects not specific listed here are evaluated elsewhere and using information on other Forms.. The tenderer shall complete and submit a signed copy of this Technical and System Information on Form D10, providing the specification’s and/or functionality, using the headings and sub-headings listed on Form D10.. The Tenderer shall demonstrate his capability to design, develop, build, integrate, operate, and maintain each item listed below, as part of the Technical and System Information provided on Form D10. The Tenderer’s statement shall cover requirements listed for each specific item on Form D10, and provide relevant information such as layout drawings, hardware/equipment, software, and or other applicable components of each item.. 56. 6.1 VGS, VGS audit WS, QLS and QL1 (D10 - Item 2.2); 8. 6.2 AVC including DCS – Hardware, Software (D10 - Items 2.3 & 2.4); 8. 6.3 AVC accuracy (Count and classification) (D10 - Item 2.5); 8. 6.4 Toll Collection Lane Equipment (D10 - Item 2.6); 8. 6.5 BOS/Back Office System (D10 - Item 2.8); 8. 6.6 Automatic Number Plate Recognition System (D10 - Item 2.11); 8. 6.7 TA/TCH Interface (D10 - Item 2.12); 8. The tenderer’s statement for these items will be evaluated as indicated below. Scoring. - The tenderer’s statement adequately covers 100% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 8. - The tenderer’s statement adequately covers more than 75% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 6. - The tenderer’s statement adequately covers more than 50% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 4. - The tenderer’s statement adequately covers more than 50% of the items listed, but the information provided does not demonstrate the relevance of the proposal to the toll environment.; 2. - The contractor’s statement covers less than 50% of the listed items.; 0. 16. 6.8 Data Communications Network (D10 - Item 2.1); 4. 6.9 ETC (D10 - Item 2.7); 4. 6.10 Customer Service Centres/Point of Sales (D10 - Item 2.9); 4. 6.11 Over height detection system (D10 - Item 2.10); 4. The tenderer’s statement for these items will be evaluated as indicated below. Scoring. - The tenderer’s statement adequately covers 100% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 4. - The tenderer’s statement adequately covers more than 75% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 3. - The tenderer’s statement adequately covers more than 50% of the items listed, and the information provided demonstrates the relevance of the proposal to the toll environment.; 2. - The tenderer’s statement adequately covers more than 50% of the items listed, but the information provided does not demonstrate the relevance of the proposal to the toll environment.; 1. - The contractor’s statement covers less than 50% of the listed items.; 0. |
| --- | --- |

PART T2:	RETURNABLE SCHEDULES

SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

PART T2.1: RETURNABLE SCHEDULES

The tenderer must complete the following returnable schedules:

Notes to tenderer:

- Returnable schedules have been based on the CIDB Standard for Uniformity in Construction Procurement and incorporate National Treasury requirements within them. Returnable schedules are separated into the following categories:

(i)	Forms, certificates, and schedules for completion by the tenderer for use in the quantitative and qualitative evaluation of the tender (Forms A to E)

(ii)	A list of all returnable documents for completion by the tenderer (Form F1)

- Failure to submit fully completed relevant returnable documents may render such a tender offer non-responsive.

- Tenderers shall note that their signature appended to each returnable form represents a declaration that they vouch for the accuracy and correctness of the information provided.

- Notwithstanding any check or audit conducted by or on behalf of the Employer, the information provided in the returnable documents is accepted in good faith and as justification for entering into a contract with a tenderer. If subsequently any information is found to be incorrect such discovery shall be taken as wilful misrepresentation by that tenderer to induce the contract. In such event:

- a.	The Employer shall inform the tenderer and give the tenderer an opportunity to make representations within 14 days as to why the tender submitted should not be disqualified and as to why the tenderer should not be restricted by the National Treasury from conducting any business with any organ of state for a period not exceeding ten (10) years;

- b.	If the Employer has already entered into a contract with the tenderer, the Employer has the discretionary right under FIDIC Particular Condition 15.2(g) to terminate the contract.

- These forms must be completed in non-erasable ink and any alterations made prior to tender closure countersigned by an authorised signatory.

PART T2.1		LIST OF RETURNABLE DOCUMENTS

- This form has been created as an aid to ensure a tenderer’s compliance with the completion of the returnable forms and schedules and subsequent placement in the correct envelope.

- The electronic format for the submissions of the relevant forms is indicated in the schedule below.

| FORM No/SBD NO | electronic format | FORM DESCRIPTION |  | INITIAL if cOMPLETED | eNVELOPE |
| --- | --- | --- | --- | --- | --- |
| A1 | pdf | certificate of CONFIRMATION THAT THE TENDERER READ THE PRESENTATION OR ATTENDED THE COMPULSORY CLARRIFICATION MEETING |  | *1 | TECHNICAL PROPOSAL (1St Envelope) |
| A1.1 | PDF | CERTIFICATE OF INTENTION TO SUBMIT A TENDER |  | *1 |  |
| a2.1 | pdf | certificate of authority for signatory |  | *1 |  |
| a2.2 | pdf | declaration of tenderer’s current status of any debt outstanding to sanral |  | *1 & *2 |  |
| A2.3 | PDF | CERTIFICATE OF SINGLE TENDER SUBMISSION |  | *1 & *2 |  |
| A2.4 | PDF | CERTIFICATE OF FRONTING PRACTICES |  | *1 & *2 |  |
| A2.5 | PDF | DECLARATION OF DOMESTIC PROMINETN INFLUENTIAL PERSONS, FOREIGN PROMINENT PUBLIC OFFICIALS AND FOREIGN INFLUENTIAL NATIONALS (DPIPS, FPPOS & FINS) |  | *1 & *2 |  |
| A2.6 | PDF | CERTIFICATE OF PERMISSION TO CONDUCT DUE DILIGENCE INVESTIGATION |  | *1 & *2 |  |
| a3.1/SBD4 | pdf | BIDDER’S DISCLOSURE |  | *1 & *2 |  |
| A3.2/SBD9 | PDF | CERTIFICATE OF INDEPENDENT TENDER |  | N/A |  |
| A3.3 | PDF | DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES |  | N/a |  |
| A3.4 | PDF | REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE |  | *1 & *2 |  |
| a3.5 | pdf | DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS (SBD 6.2) |  | *1 & *2 |  |
| a3.6 | pdf | LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE (ANNEXURE C) |  | *1 & *2 |  |
| a4 | pdf | SCHEDULE OF DEVIATIONS or qualifications BY TENDERER |  | *1 & *2 |  |
| a5 | pdf | SCHEDULE OF ADDENDA TO TENDER DOCUMENTS |  | *1 |  |
| A6/SBD2 | pdf | CERTIFICATES OF TAX COMPLIANCE |  | *1 |  |
| A7 | pdf | CERTIFICATE OF INSURANCE COVER |  | *1 |  |
| A8 | pdf | TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS |  | *1 |  |
| A9.1 | pdf | SCHEDULE OF TENDERER’S LITIGATION HISTORY |  | *1 |  |
| A9.2 | pdf | ENVIRONMENTAL, SOCIAL, HEALTH, AND SAFETY PERFORMANCE DECLARATION |  | *1 |  |
| A10 | pdf | SCHEDULE OF CURRENT COMMITMENTS |  | *1 |  |
| A11 | pdf | CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993 (ACT NO. 130 OF 1993) |  | *1 |  |
| A12 | PDF | JOINT VENTURE AGREEMENT |  | *1 & *2 |  |
| A13/SBD1 | pdf | INVITATION TO BID AND TERMS AND CONDITIONS FOR BIDDING |  | *1 & *2 |  |
| C1.1 | pdf | TENDERER’S B-BBEE VERIFICATION CERTIFICATION |  | *1 & *2 |  |
| c1.2/sbd6.1 | pdf | PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017 (INCORPORATING SBD6.1) |  | *1 & *2 |  |
| D1 | pdf | SCHEDULE OF TENDERER’S PLANT AND EQUIPMENT |  | *1 |  |
| D.2 | pdf | TENDERER’S METHOD STATEMENT |  | *1 |  |
| D3 | pdf | TENDERER’S ORGANISATION AND STAFFING |  | *1 |  |
| D4.1 | pdf | PERSONNEL RESOURCE DETAIL (NSC representative) |  | *1 |  |
| D4.2 | pdf | PERSONNEL RESOURCE DETAIL (QUALITY CONTROL OFFICER) |  | *1 & *2 |  |
| D4.3 | pdf | PERSONNEL RESOURCE DETAIL (ROUTE maintenance manager) |  | 1 & *2 |  |
| D4.4 | pdf | PERSONNEL RESOURCE DETAIL (SYSTEM SOFTWARE SPECIALIST) |  | 1 & *2 |  |
| D4.5 | pdf | PERSONNEL RESOURCE DETAIL (NETWORK AND SECURITY SPECIALIST) |  | 1 & *2 |  |
| D4.6.1 | pdf | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 1) |  | 1 & *2 |  |
| D4.6.2 | pdf | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 2) |  | 1 & *2 |  |
| D4.6.3 | pdf | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 3) |  | 1 & *2 |  |
| D4.6.4 | pdf | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 4) |  | 1 & *2 |  |
| D4.7 | pdf | PERSONNEL RESOURCE DETAIL (H&S MANAGER/OFFICER) |  | 1 & *2 |  |
| D5.1 | pdf | TENDERER’S EXPERIENCE BASED ON COMPLETED PROJECTS |  | 1 & *2 |  |
| D5.2 | pdf | TENDERER’S EXPERIENCE BASED ON PROJECTS IN PROGRESS |  | 1 & *2 |  |
| D7.1 | pdf | TENDERER’S INDICATIVE PROGRAM |  | 1 & *2 |  |
| D7.2 | pdf | PROPOSED ESTABLISHMENT PROGRAMME |  | 1 & *2 |  |
| D9 | pdf | NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE |  | 1 & *2 |  |
| D10 | pdf | TECHNICAL AND SYSTEM INFORMATION |  | 1 & *2 |  |
| D11 | pdf | TOLL PLAZA UPGRADING SCHEDULES |  | 1 & *2 |  |
| D12 | pdf | ADDITIONAL INFORMATION |  | 1 & *2 |  |
| D13 | pdf | DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS |  | 1 & *2 |  |
| D14 | pdf | TECHNICAL PROPOSAL |  | 1 & *2 |  |
| D15 | pdf | CORPORATE SOCIAL INVESTMENT |  | 1 & *2 |  |
| E1 | pdf | ELECTRICAL SCHEDULE OF MATERIALS |  | 1 & *2 |  |
| F1 | pdf | SCHEDULE OF TENDER COMPLIANCE |  | 1 & *2 |  |
| c1.1.1/SBD7 | pdf | FORM OF OFFER | *2 |  | FINANCIAL PROPOSAL (2nd Envelope) |
| C1.2.3 | pdf | CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER | *2 |  |  |
| C2.2/SBD3 | MS Excel | PRICING SCHEDULE | *1 & *2 |  |  |
| C2.3 | MS Excel | SUMMARY OF PRICING SCHEDULE | *1 & *2 |  |  |
| A3.5/SBD6.2 | pdf | DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS | *1 & *2 |  |  |
| A3.6 | pdf | LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE |  |  |  |
| B1 | pdf | CURRENCY EXCHANGE RATE FLUCTUATIONS | *1 & *2 |  |  |
| D8 | pdf | SCHEDULE OF ESTIMATED MONTHLY EXPENDITURE | 1 & *2 |  |  |

NOTES:

*1- SCHEDULES/documents required for tender evaluation purposes

*2- Schedules/documents that will be INCORPORATED into the contract

PART T2	RETURNABLE SCHEDULES

TABLE OF CONTENTS

FORM A1:	CERTIFICATE OF CONFIRMATION THAT THE TENDERER READ THE PRESENTATION OR ATTENDED THE COMPULSORY CLARIFICATION MEETING	T31

FORM A1.1: 	CERTIFICATE OF INTENTION TO SUBMIT A TENDER	T32

FORM A2.1:	CERTIFICATE OF AUTHORITY FOR SIGNATORY	T34

FORM A2.2: 	DECLARATION OF TENDERER’S CURRENT STATUS OF ANY DEBT OUTSTANDING TO SANRAL	T35

FORM A2.3:	CERTIFICATE OF SINGLE TENDER SUBMISSION	T36

FORM A2.4:	CERTIFICATE OF FRONTING PRACTICES	T37

FORM A2.5:	DECLARATION OF DOMESTIC PROMINENT INFLUENTIAL PERSONS, FOREIGN PROMINENT PUBLIC OFFICIALS AND FOREIGN INFLUENTIAL NATIONALS (DPIPs, FPPOs & FINs)	T39

FORM A2.6:	CERTIFICATE OF PERMISSION TO CONDUCT DUE DILIGENCE INVESTIGATION	T42

FORM A3.1:	BIDDER’S DISCLOSURE (SBD4)	T43

FORM A3.2:	CERTIFICATE OF INDEPENDENT TENDER (INCORPORATING SBD9)	T46

FORM A3.3:	DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES (INCORPORATING SBD8)	T47

FORM A3.4:	REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE	T49

FORM A3.5:	DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS (SBD 6.2)	T50

FORM A3.6:	LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE (ANNEXURE C)	T54

FORM A4:	SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER	T59

FORM A5:	SCHEDULE OF ADDENDA TO TENDER DOCUMENTS	T60

FORM A6: 	CERTIFICATE OF TAX COMPLIANCE (INCORPORATING SBD2)	T61

FORM A7:	CERTIFICATE OF INSURANCE COVER	T62

FORM A8:	TENDERERS REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS	T63

FORM A9.1:	SCHEDULE OF TENDERER'S LITIGATION HISTORY	T65

FORM A9.2:	ENVIRONMENTAL, SOCIAL, HEALTH, AND SAFETY PERFORMANCE DECLARATION	T66

FORM A10:	SCHEDULE OF CURRENT COMMITMENTS	T67

FORM A11:	CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993 (ACT NO. 130 OF 1993)	T68

FORM A12:	JOINT VENTURE AGREEMENT	T69

FORM A13:	FORM SBD1 – INVITATION TO BID AND TERMS AND CONDITIONS FOR BIDDING	T70

FORM B1:	CURRENCY EXCHANGE RATE FLUCTUATIONS	T72

FORM C1.1:	TENDERER’S B-BBEE VERIFICATION CERTIFICATION	T73

FORM C1.2:	PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017 (INCORPORATING SBD6.1)	T76

FORM D1:	SCHEDULE OF TENDERER’S PLANT AND EQUIPMENT	T80

FORM D2:	TENDERER’S METHOD STATEMENT	T81

FORM D3:	TENDERER’S ORGANISATION AND STAFFING	T82

FORM D4.1:	PERSONNEL RESOURCE DETAIL (NSC representative)	T83

FORM D4.2:	PERSONNEL RESOURCE DETAIL (QUALITY CONTROL OFFICER)	T85

FORM D4.3:	PERSONNEL RESOURCE DETAIL (maintenance manager)	T87

FORM D4.4:	PERSONNEL RESOURCE DETAIL (SYSTEM/ SOFTWARE SPECIALIST)	T89

FORM D4.5:	PERSONNEL RESOURCE DETAIL (NETWORK AND SECURITY SPECIALIST)	T91

FORM D4.6.1:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 1)	T93

FORM D4.6.2:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 2)	T95

FORM D4.6.3:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 3)	T97

FORM D4.6.4:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 4)	T99

FORM D4-7:	PERSONNEL RESOURCE DETAIL (H&S manager/officer)	T101

FORM D5.1:	TENDERER’S EXPERIENCE based on completed projects	T103

FORM D5.2:	TENDERER’S EXPERIENCE based on projects IN PROGRESS	T105

FORM D7.1: TENDERER’S INDICATIVE PROGRAM	T107

FORM D7.2: 	PROPOSED ESTABLISHMENT PROGRAMME	T108

FORM D8:	SCHEDULE OF ESTIMATED MONTHLY EXPENDITURE	T109

FORM D9:	NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE	T111

FORM D9:	NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE (CONTINUED)	T113

FORM D10:	TECHNICAL AND SYSTEM INFORMATION	T115

FORM D11:	TOLL PLAZA UPGRADING SCHEDULES	T120

FORM D12:	ADDITIONAL INFORMATION	T120

FORM D13:	DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS	T122

FORM D13: DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS	T141

FORM D14:	TECHNICAL PROPOSAL	T142

FORM D15:	CORPORATE SOCIAL INVESTMENT	T147

FORM E1:	ELECTRICAL SCHEDULE OF MATERIALS	T148

FORM F1:	SCHEDULE OF TENDER COMPLIANCE	T149

FORM A1:	CERTIFICATE OF CONFIRMATION THAT THE TENDERER READ THE PRESENTATION OR ATTENDED THE COMPULSORY CLARIFICATION MEETING

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

This is to certify that I,

representative of (tenderer)

of (address)

telephone number

fax number

e-mail

read the clarification presentation presented by the Employer online and/or

attended the clarification meeting on (date) .............................................................................................

conducted by ............................................................................................................................................

in the presence of (Employer’s representative) ........................................................................................

EMPLOYER’S REPRESENTATIVE

(Signature)...........................................................................................Date..............................................

TENDERER’S REPRESENTATIVE (Signature)

FORM A1.1: 	CERTIFICATE OF INTENTION TO SUBMIT A TENDER

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to Tenderer:

- The duly completed certificate of intention to submit a tender must be submitted by whoever intends to tender for this particular tender prior to 23 February 2024. Failure to submit the certificate of intention to tender within the required period may render the tenderer non-responsive and SANRAL does not accept responsibility for any communication not received by the tenderer timeously.

- Failure to submit this certificate would result in the tenderer not receiving addenda or additional issued information and may result in the tenderer being non-responsive if “any material amendment/s” contained in the addenda or additional information is not included in the tender offer/submission.

- Late notification of intention to tender by a prospective tenderer will not necessarily result in the tender closing date being extended.

- Should you intend to submit a tender for this particular tender please sign the certificate, scan and email the completed document to the email address indicated in T1.1 of this tender document.

- The Employer shall send all correspondence, including Addenda, only to the Tenderer’s email address as provided herein; in addition, the Employer shall upload all correspondences on SANRAL website and National Treasury eTender Portal.

This is to certify that I,

representative of (insert name of tenderer)

of (address)

telephone number

fax number

e-mail

intends to submit a tender in response to the tender notice and invitation for tender this contract.

TENDERER'S REPRESENTATIVE			Date   …………………..

(Signature)

FORM A2.1:	CERTIFICATE OF AUTHORITY FOR SIGNATORY

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The signatory for the tenderer shall confirm his/her authority thereto by attaching on the tendering company’s letterhead a duly signed and dated copy of the relevant resolution of the board of directors/partners.  Scan a copy of the resolution on Flash drive.

- In the event that the tenderer is a joint venture, a certificate is required from each member of the joint venture clearly setting out:

  - (i)	Authority for signatory,

  - (ii)	Undertaking to formally enter into a joint venture contract should an award be made to the joint venture,

  - (iii) Name of designated lead member of the intended joint venture, as required by tender condition C.2.13.4.

Proforma

The resolution below is given as an example of an acceptable format for authorisation, but submission of this page with the example completed shall not be accepted as authorisation of the tenderer’s signatory.

By resolution of the board of directors passed at a meeting held on

Mr/Ms. 	,

whose signature appears below, has been duly authorized to sign all documents in connection with the tender for

CONTRACT SANRAL N.001-249-2019/1R NSC FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

and any contract which may arise therefrom on behalf of enter name of tenderer in block capitals

SIGNED ON BEHALF OF THE COMPANY:

IN HIS/HER CAPACITY AS:

DATE:

SIGNATURE OF SIGNATORY:

WITNESS 1:

SIGNATURE:	 NAME (IN CAPITALS)

WITNESS 2:

SIGNATURE:	 NAME (IN CAPITALS):

FORM A2.2: 	DECLARATION OF TENDERER’S CURRENT STATUS OF ANY DEBT OUTSTANDING TO SANRAL

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The signatory for the tenderer shall complete and sign this form declaring the current status of any debt outstanding to SANRAL.

- In the event that the tenderer is a Joint Venture, a declaration is required from each member of the Joint Venture.

I, the undersigned ………………………………….…………………………………………...…………. declare that:

- the tenderer or any of its Directors/Members do not have any debt outstanding to SANRAL, other than what is listed below:

- the tenderer and/or any of its Directors/Members freely, voluntarily and without undue duress unconditionally authorizes the SANRAL to set off any debts agreed to which is due and payable by the tenderer or any of its Directors/Members in terms of this declaration against any moneys due to the tenderer or any of its Directors/Members; and

- to the best of my knowledge the above information is true and accurate.

SIGNATURE:

Signed and sworn before me at ……………………………….… on the ……… day of 	20

The deponent having:

- acknowledged that he/she knows and understands the contents hereof;

- confirmed that he/she has no objection to the taking of the prescribed oath;

- confirmed that he/she considered the prescribed oath as binding upon his/her conscience; and

- confirmed that the Regulations contained in the Government Gazette Notice R1258 of July 1972 and R1648 of August 1977 have been complied with.

COMMISSIONER OF OATHS

FORM A2.3:	CERTIFICATE OF SINGLE TENDER SUBMISSION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- This certificate serves as a declaration by the tenderer that a single tender was submitted.

- In the case of a Joint Venture (JV) or a Targeted Enterprise, a separate certificate is to be completed and submitted by each JV member or Targeted Enterprise.

DECLARATION

I, the undersigned, …………………………...……………………………………………………. in submitting the accompanying tender on behalf of the tenderer do hereby make the following statements that I certify to be true and complete in every respect:

1.	I have read and understand the notes to, and the contents of, this certificate.

2.	I understand that the accompanying tender and any other tender shall be disqualified in the event that    I, including a Joint Venture partner or a Targeted Enterprise, participate in more than 1 (one) tender.

SIGNATURE:

DATE:

NAME:

POSITION:

FORM A2.4:	CERTIFICATE OF FRONTING PRACTICES

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Fronting Practices

Window-dressing: This includes cases in which black people are appointed or introduced to an enterprise on the basis of tokenism and may be:

- Discouraged or inhibited from substantially participating in the core activities of an enterprise; and

- Discouraged or inhibited from substantially participating in the stated areas and/or levels of their participation;

Benefit Diversion: This includes initiatives implemented where the economic benefits received as a result of the B-BBEE Status of an enterprise do not flow to black people in the ratio as specified in the relevant legal documentation.

Opportunistic Intermediaries: This includes enterprises that have concluded agreements with other enterprises with a view to leveraging the opportunistic intermediary's favourable B-BBEE status in circumstances where the agreement involves:

- Significant limitations or restrictions upon the identity of the opportunistic intermediary's suppliers, service providers, clients or customers;

- The maintenance of their business operations in a context reasonably considered improbable having regard to resources; and

- Terms and conditions that are not negotiated at arms-length on a fair and reasonable basis.

Responsibility to Report Fronting

In order to effectively deal with the scourge of Fronting, verification agencies, and/or procurement officers and relevant decision makers are encouraged to obtain a signed declaration from the clients or entities that they verify or provide business opportunities to, which states that the client or entity understands and accepts that the verification agency, procurement officer or relevant decision maker may report fronting practices to the Department of Trade and Industry. Intentional misrepresentation by measured entities may constitute fraudulent practices, public officials and verification agencies are to report such cases to the Department of Trade and Industry.

SANRAL or its appointed agent has every right to embark on an investigation of fronting with regards to any potential service provider. In this regard, SANRAL is entitled to request any further information, interview and any documentation from the respective potential service provider prior to any award. (This statement is for internal use)

Fronting Indicators

- The black people identified by an enterprise as its shareholders, executives or management are unaware or uncertain of their role within an enterprise;

- The black people identified by an enterprise as its shareholders, executives or management have roles of responsibility that differ significantly from those of their non-black peers;

- The black people who serve in executive or management positions in an enterprise are paid significantly lower than the market norm, unless all executives or management of an enterprise are paid at a similar level;

- There is no significant indication of active participation by black people identified as top management at strategic decision making level;

- An enterprise only conducts peripheral functions and does not perform the core functions reasonably expected of other, similar, enterprises;

- An enterprise relies on a third-party to conduct most core functions normally conducted by enterprises similar to it;

- An enterprise cannot operate independently without a third-party, because of contractual obligations or the lack of technical or operational competence;

- The enterprise displays evidence of circumvention or attempted circumvention;

- An enterprise buys goods or services at a significantly different rate than the market from a related person or shareholder;

- An enterprise obtains loans, not linked to the good faith share purchases or enterprise development initiatives, from a related person at an excessive rate; and

- An enterprise shares all premises and infrastructure with a related person, or with a shareholder with no B-BBEE status or a third-party operating in the same industry where the cost of such premises and infrastructure is disproportionate to market-related costs.

DECLARATION

I,………………………………………………………………………………………………… the undersigned, in submitting the accompanying tender on behalf of the tenderer do hereby make the following statements that I certify to be true and complete in every respect:

- I have read and understand the contents of this certificate.

- I accept that the Employer may report fronting practices to the Department of Trade and Industry and the BBBEE commissioner.

- I accept that intentional misrepresentation by measured entities may constitute fraudulent practices that shall be reported to the Department of Trade and Industryand the BBBEE commissioner.

SIGNATURE:

DATE:

NAME:

POSITION:

FORM A2.5:	DECLARATION OF DOMESTIC PROMINENT INFLUENTIAL PERSONS, FOREIGN PROMINENT PUBLIC OFFICIALS AND FOREIGN INFLUENTIAL NATIONALS (DPIPs, FPPOs & FINs)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- In line with a policy on Domestic Prominent Influential Persons (DPIP’s), Foreign Prominent Public Officials (FPPO’s) & Foreign Influential Nationals (FIN’s), the purpose of this declaration form is to ensure maintenance and monitoring of the business relationships with prominent, influential stakeholders who have domestic and/or foreign influence as far as the procurement under the management of SANRAL is concerned. This is done to mitigate SANRAL’s perceived association, reputational, operational or legal risk, as it strives to foster and maintain fair and transparent business relations. (The policy is available on SANRAL website: www.nra.co.za)

- It is compulsory that all prospective and existing bidders conducting business with SANRAL, who potentially meet the definition of DPIPs, FPPOs or FINs, complete this form by supplying credible information as required and submit together with their bid document.

- Bidders are required at the tender stage to declare any DPIPs, FPPOs or FINs involved in their bids, as part of their submission.

- Further, that bidders shall at the tender stage furnish SANRAL of all information relating to namely, shareholders names, ID numbers and share certificates of the individual and/or transaction concerned using, the form below, for verification purposes, including where applicable, confirmation as it relates to:

    - Knowledge of any offence within the meaning of Chapter 2 section 12 & 13 of Prevention and Combating of Corrupt Practices Act no 4 of 2006; and or

    - Knowledge of any offence within the meaning of chapter 3 of Prevention of Organised Crime Act no. 121 of 1998 as it relates to any of the shareholders, Directors, Owners and/or individual link to the bidder.

- Bidders undertake that should it be discovered that the information provided in the form below, is fraudulently or negligently misrepresented then Chapter 9 sec 214 & 216 of Companies Act no 17 of 2008 shall apply to shareholders, Directors, Owners and/or individual link to the bidder.

- Should the bidder fail to declare or supply SANRAL with credible information in the prescribed form, the bid may be rendered invalid.

- Should the SANRAL, in the process of conducting verification and investigation of information supplied by the bidder find out that the information poses a reputational risk, the bid shall be rendered invalid.

- The following definitions shall apply:

  - “Board” means the Board of Directors or the Accounting Authority of SANRAL

  - “Business relationship” means the connection formed between SANRAL and external stakeholders for commercial purposes.

  - “DD” means Due Diligence which is defined for this form as:

- the verification of disclosures in the disclosure form, including if the disclosure is “none”; and

- further investigation if any areas of risk are identified from publicly available information.

  - “Domestic Prominent Influential Person” means an individual who holds an influential position, including in an acting position for a period exceeding six months, or has held at any time in the preceding twelve months, in the Republic, as defined in the Financial Intelligence Centre Amendment Act (No.1 of 2017).

  - “DPIP” means a Domestic Prominent Influential Person.

  - “Family members and known close associates” means immediate family members and known close associates of a person in a foreign or domestic prominent position, as the case may be, as defined in the Financial Intelligence Amendment Act, No.1 of 2017).

  - “Foreign Influential National” means an individual who is not a South African citizen or does not have a permanent residence permit issued in terms of the Immigration Act (No.13 of 2002), who possesses personal power that induces another person to give consideration or to act on any basis other than the merits of the matter.

  - “Foreign Prominent Public Official” means (as defined in the Financial Intelligence Centre Amendment Act (No.1 of 2017) an individual who holds, or has held at any time in the preceding twelve months, in any foreign country a prominent public function

  - “FPPO” means a Foreign Prominent Public Official.

  - “Improper influence” means personal power that induces another person to give consideration or to act on any basis other than the merits of the matter.

  - “PIP” means Prominent Influential Person and includes DPIP, FPPO and FIN

  - “SANRAL” means the South African National Roads Agency SOC Limited, with registration number 1998/009584/30.

  - “Senior Management” means the Executive Committee or its individual members.

- A separate declaration is required from each PIP. In the event that the tenderer is a Joint Venture, a separate declaration from each PIP from each of the Joint Venture members, is required

Prominent Influential Persons (PIP’) Reporting Form.

| IDENTIFICATION PARTICULARS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Primary Particulars |  | First Name | Surname |  | Middle Name |  | ID/Passport Number |  |
| Country Details |  | Country of Origin |  | Citizenship | Current Country of Residence |  |  |  |
| CURRENT STATUS AND BACKGROUND |  |  |  |  |  |  |  |  |
| Current Occupation |  | Occupational Title |  |  | Status |  |  |  |
|  |  |  |  |  | Active |  | Non-active |  |
| Is the potential/business partner (mark with an “X” whichever is applicable): |  |  |  |  |  |  |  |  |
| a DPIP |  | a FPPO | a FIN | Family member or Close Associate of a DPIP/FPPO/FIN? |  |  |  |  |
| KNOWN BUSINESS INTERESTS |  |  |  |  |  |  |  |  |
| No | Name of Entity |  |  | Role in Entity |  | Status |  |  |
| 1 |  |  |  |  |  | Active |  | Non-active |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |

MEDIA REPORTS / OTHER SOURCES OF INFORMATION

(Please reference all known negative or damaging media reports associated with the DPIP/FPPO/FIN)

Reporting Person/s:

| Full names: |  |  |
| --- | --- | --- |
| Designation: |  |  |
| Department: |  |  |
| Head of Department: |  |  |
| Head of Department’s signature: | Date: |  |
| Reporting Person’s signature: | Date: |  |

I, the undersigned,………………………………………………………………………………. declare that:

- the information furnished on this declaration form is true and correct, and

- I accept that any action may be taken against me should this declaration prove to be false.

SIGNATURE:

NAME:

POSITION:

DATE:

NAME OF TENDERER:

FORM A2.6:	CERTIFICATE OF PERMISSION TO CONDUCT DUE DILIGENCE INVESTIGATION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer shall complete the declaration below

- In the case of a Joint Venture (JV), each member of the JV shall comply with the above requirements.

DECLARATION

I, 	 (name)

the undersigned in my capacity as 	 (position)

on behalf of 	 (name of company),

herewith grant consent that SANRAL or any of their appointed Service Providers may conduct a due diligence investigation on 	 (name of company)

to evaluate our ability to perform the contract as stipulated in the Standard Conditions of Tender, C.3.13(b).

In addition, any information in this regard requested by SANRAL or any of their appointed Service Providers, shall be submitted within the timelines of the request.

SIGNATURE: 	…………………………………………………………………

DATE: 	…………………………………………………………………

NAME: 	…………………………………………………………………

POSITION: 	…………………………………………………………………

FORM A3.1:	BIDDER’S DISCLOSURE (SBD4)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- Definitions:

  - “State” means:

- any National or Provincial Department, National or Provincial Public Entity or Constitutional Institution within the meaning of the Public Finance Management Act, 1999 (Act No 1 of 1999);

- any Municipality of Municipal Entity;

- Provincial Legislature;

- National Assembly or the National Council of Provinces;  or

- Parliament.

- “Shareholder” means a person who owns shares in the company and is actively involved in the management of the enterprise or business and exercises control over the enterprise.

  - “Shareholder” means a person who owns shares in the company and is actively involved in the management of the enterprise or business and exercises control over the enterprise.

- In the case of a joint venture (JV), a separate declaration form is to be completed and submitted by each JV member.

- If the Form is omitted or blank; or if the tenderer found to have failed to declare conflict or declare false information, The tender will be declared non-responsive and should it be discovered after the award of a contract, contract maybe terminated and tenderer will be ultimately blacklisted.

______________________________________________________________________________

PURPOSE OF THE FORM

Any person (natural or juristic) may make an offer or offers in terms of this invitation to bid. In line with the principles of transparency, accountability, impartiality, and ethics as enshrined in the Constitution of the Republic of South Africa and further expressed in various pieces of legislation, it is required for the bidder to make this declaration in respect of the details required hereunder.

Where a person/s are listed in the Register for Tender Defaulters and / or the List of Restricted Suppliers, that person will automatically be disqualified from the bid process.

BIDDER’S DECLARATION

Is the bidder, or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise, employed by the state?						                YES/NO

If so, furnish particulars of the names, individual identity numbers, and, if applicable, state employee numbers of sole proprietor/ directors / trustees / shareholders / members/ partners or any person having a controlling interest in the enterprise, in table below.

| Full Name | Identity Number | Name of State institution |
| --- | --- | --- |

Do you, or any person connected with the bidder, have a relationship with any person who is employed by the procuring institution?

YES/NO

If so, furnish particulars:

……………………………………………………………………………………

……………………………………………………………………………………

Does the bidder or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise have any interest in any other related enterprise whether or not they are bidding for this contract?

YES/NO

If so, furnish particulars:

…………………………………………………………………………….

…………………………………………………………………………….

DECLARATION

I, the undersigned, (name)……………………………………………………………………. in submitting the accompanying bid, do hereby make the following statements that I certify to be true and complete in every respect:

I have read and I understand the contents of this disclosure;

I understand that the accompanying bid will be disqualified if this disclosure is found not to be true and complete in every respect;

The bidder has arrived at the accompanying bid independently from, and without consultation, communication, agreement or arrangement with any competitor. However, communication between partners in a joint venture or consortium will not be construed as collusive bidding.

In addition, there have been no consultations, communications, agreements or arrangements with any competitor regarding the quality, quantity, specifications, prices, including methods, factors or formulas used to calculate prices, market allocation, the intention or decision to submit or not to submit the bid, bidding with the intention not to win the bid and conditions or delivery particulars of the products or services to which this bid invitation relates.

The terms of the accompanying bid have not been, and will not be, disclosed by the bidder, directly or indirectly, to any competitor, prior to the date and time of the official bid opening or of the awarding of the contract.

There have been no consultations, communications, agreements or arrangements made by the bidder with any official of the procuring institution in relation to this procurement process prior to and during the bidding process except to provide clarification on the bid submitted where so required by the institution; and the bidder was not involved in the drafting of the specifications or terms of reference for this bid.

I am aware that, in addition and without prejudice to any other remedy provided to combat any restrictive practices related to bids and contracts, bids that are suspicious will be reported to the Competition Commission for investigation and possible imposition of administrative penalties in terms of section 59 of the Competition Act No 89 of 1998 and or may be reported to the National Prosecuting Authority (NPA) for criminal investigation and or may be restricted from conducting business with the public sector for a period not exceeding ten (10) years in terms of the Prevention and Combating of Corrupt Activities Act No 12 of 2004 or any other applicable legislation.

I CERTIFY THAT THE INFORMATION FURNISHED IN PARAGRAPHS 1, 2 and 3 ABOVE IS CORRECT.

I ACCEPT THAT THE STATE MAY REJECT THE BID OR ACT AGAINST ME IN TERMS OF PARAGRAPH 6 OF PFMA SCM INSTRUCTION 03 OF 2021/22 ON PREVENTING AND COMBATING ABUSE IN THE SUPPLY CHAIN MANAGEMENT SYSTEM SHOULD THIS DECLARATION PROVE TO BE FALSE.

………………………………	 	..……………………………………………

Signature	                          	Date

………………………………		………………………………………………

Position 				Name of bidder

.

FORM A3.2:	CERTIFICATE OF INDEPENDENT TENDER (INCORPORATING SBD9)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Form REPEALED

FORM A3.3:	DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES (INCORPORATING SBD8)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- This declaration:

- must form part of all tenders submitted.

- in the case of a joint venture (JV), must be completed and submitted by each member of the JV

- This form serves as a declaration to be used by institutions in ensuring that when goods and services are being procured, all reasonable steps are taken to combat the abuse and/or misused the State’s procurement of the supply chain management system.

- The tender of any tenderer may be disregarded if that tenderer or any of its directors have –

- abused the institution’s supply chain management system;

- committed fraud or any other improper conduct in relation to such State system;

- has been charged with fraud, corruption or any other improper conduct whether of a criminal or civil nature during the course and scope of rendering services to the state or any other party and/or entity; or

- failed to perform on any previous contract with the State.

- In order to give effect to the above, the following questionnaire must be completed and submitted with this tender.

| 4.1 | Is the tenderer or any of its directors listed on the National Treasury’s Database of Restricted Suppliers as companies or persons prohibited from doing business with the public sector? Companies or persons who are listed on this Database were informed in writin g of this restriction by the Accounting Officer/ Authority of the institution that imposed the restriction after the audi alteram partem rule was applied. The Database of Restricted Suppliers now resides on the National Treasury website (www.treasury.gov.za) and can be accessed by clicking on its link at the bottom of the home page. | Yes  | No  |
| --- | --- | --- | --- |
| 4.1.1 | If Yes, furnish particulars: |  |  |
| 4.2 | Is the tenderer or any of its directors listed on the Register for Tender Defaulters in terms of Section 29 of the Prevention and Combatting of Corrupt Activities Act (No. 12 of 2004)? The Register for Tender Defaulters can be accessed on the National Treasury website ((www.treasury.gov.za) by clicking on its link at the bottom of the home page. | Yes  | No  |
| 4.2.1 | If Yes, furnish particulars: |  |  |
| 4.3 | Was the tenderer or any of its directors convicted by a court of law (including a court outside the Republic of South Africa) for fraud or corruption during the past five years? | Yes  | No  |
| 4.3.1 | If Yes, furnish particulars: |  |  |
| 4.4 | Was any contract between the tenderer and any organ of State terminated during the past five years on account of failure to perform on or comply with the contract? | Yes  | No  |
| 4.4.1 | If Yes, furnish particulars: |  |  |

CERTIFICATION

I, the undersigned, .........................................................................................................................

certify that the information furnished on this declaration form is true and correct.

I accept that, in addition to cancellation of a contract, action may be taken against me should this declaration prove to be false.

Signature: ..................................................................................................................................

Name: ........................................................................................................................................

Position: .....................................................................................................................................

Date: ..........................................................................................................................................

Name of tenderer: ......................................................................................................................

FORM A3.4:	REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

The tenderer shall provide a pdf. copy of the supplier registration form from National Treasury Central Supplier Database (www.treasury.gov.za). Tenderers who are not registered on the Central Supplier Database at tender closure will be declared non-responsive (refer to Tender Data, Clause C.2.1.1). In the case of a Joint Venture or a Targeted Enterprise, a pdf. supplier registration form must be provided for each member of the Joint Venture or Targeted Enterprise.

NAME OF CONTRACTOR:

CENTRAL SUPPLIER DATABASE SUPPLIER NUMBER:

SUPPLIER COMMODITY:

DELIVERY LOCATION:

SIGNED BY TENDERER:

FORM A3.5:	DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS (SBD 6.2)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

This Standard Bidding Document (SBD) must form part of all bids invited. It contains general information and serves as a declaration form for local content (local production and local content are used interchangeably).

Before completing this declaration, bidders must study the General Conditions, Definitions,the South African Bureau of Standards (SABS) approved technical specification number SANS 1286:2017 and the Guidance on the Calculation of Local Content together with the Local Content Declaration Templates [Annex C (Local Content Declaration: Summary Schedule), D (Imported Content Declaration: Supporting Schedule to Annex C) and E (Local Content Declaration: Supporting Schedule to Annex C).

- General Conditions

  - The local content (LC) expressed as a percentage of the bid price must be calculated in accordance with the SABS approved technical specification number SANS 1286:2017 as follows:

LC = [1 - x / y] * 100

Where:

x		is the imported content in Rand

y 	is the bid price in Rand excluding value added tax (VAT)

Prices referred to in the determination of x must be converted to Rand (ZAR) by using the exchange rate published by South African Reserve Bank (SARB) on the date of advertisement of the bid as indicated in paragraph 3.1 below.

The SABS approved technical specification number SANS 1286:2017 is accessible on http://www.thedtic.gov.za/wp-content/uploads/SANS-1286-2017.pdf at no cost.

  - A bid may be disqualified if this Declaration Certificate and the Annex C (Local Content Declaration: Summary Schedule – Form A3.6) are not submitted as part of the bid documentation.

1.3	Only locally produced or locally manufactured Textiles, Clothing, Leather and Footwear from local raw material or input, with a minimum threshold for local production and content of 100% will be considered.

- The stipulated minimum threshold(s) for local production and content (refer to Annex A of SANS 1286:2017) for this bid is/are as follows:

| Description of services, works or goods | Stipulated minimum threshold |
| --- | --- |
| Electrical cable material products |  |
| Low Voltage | 90% |
| Low Cost Reticulation | 90% |
| Medium & High Voltage | 90% |
| ACR | 90% |
| Telecom cable material products |  |
| Optical Fibre Cables | 90% |
| Copper Telecom Cables | 90% |
| Plastic Pipes |  |
| Polyvinyl chloride (PVC) pipes | 100% |
| High density Polyethylene (HDPE) pipes | 100% |
| Polypropylene (PP) pipes | 100% |
| Glass Reinforced Plastic (GRP) pipes | 100% |
| Textiles, Clothing, Leather and Footwear | 100% |
| Only locally produced or locally manufactured textiles, clothing, leather and footwear from local raw material or input | 100% |

- Does any portion of the services or goods offered have any imported content?

| YES |  | NO |  | Tick applicable box |
| --- | --- | --- | --- | --- |

3.1	If yes, the rate(s) of exchange to be used in this bid to calculate the local content as prescribed in paragraph 1.1 of the general conditions must be the rate(s) published by SARB for the specific currency on the date of advertisement of the bid: 16 February 2024

The relevant rates of exchange information are accessible on https://www.resbank.co.za.

Indicate the rate(s) of exchange against the appropriate currency in the table below (refer to

Annex A of SANS 1286:2017):

| Currency | Rates of exchange |
| --- | --- |
| US Dollar |  |
| Pound Sterling |  |
| Euro |  |
| Yen |  |
| Other |  |

NB: Bidders must submit proof of the SARB rate(s) of exchange used.

4.	Where, after the award of a bid, challenges are experienced in meeting the stipulated minimum threshold for local content the DTI must be informed accordingly in order for the DTI to verify and in consultation with the AO/AA provide directives in this regard.

LOCAL CONTENT DECLARATION

(REFER TO ANNEX B OF SANS 1286:2017)

LOCAL CONTENT DECLARATION BY CHIEF FINANCIAL OFFICER OR OTHER LEGALLY RESPONSIBLE PERSON NOMINATED IN WRITING BY THE CHIEF EXECUTIVE OR SENIOR MEMBER/PERSON WITH MANAGEMENT RESPONSIBILITY (CLOSE CORPORATION, PARTNERSHIP OR INDIVIDUAL) IN RESPECT OF BID NO.: CONTRACT SANRAL N.001-249-2019/1R NSC FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD ISSUED BY: THE SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED (the Procurement Authority / Institution): N.B.: - The obligation to complete, duly sign and submit this declaration cannot be transferred to an external authorized representative, auditor or any other third party acting on behalf of the bidder. - Guidance on the Calculation of Local Content together with Local Content Declaration Templates (Annex C, D and E) is accessible on http://www.thedtic.gov.za/sectors-and-services-2/industrial-development/industrial procurement/?hilite=%27local%27%2C%27content%27%2C%27declaration%27. Bidders should first complete Declaration D. After completing Declaration D, bidders should complete Declaration E and then consolidate the information on Declaration C. Declaration C should be submitted with the bid documentation at the closing date and time of the bid in order to substantiate the declaration made in paragraph (c) below. Declarations D and E should be kept by the bidders for verification purposes for a period of at least 5 years. The successful bidder is required to continuously update Declarations C, D and E with the actual values for the duration of the contract. - Examples of Annex D and E as well as the Process for application for exemption and guidelines for the calculation of the local content is provided in Part C4: Appendix 8. Examples of Annex D and E is also provided in Excel format on the Tender document link. I, the undersigned (full names), do hereby declare, in my capacity as of (name of bidder entity) the following: - (a) The facts contained herein are within my own personal knowledge. - (b) I have satisfied myself that the goods/services/works to be delivered in terms of the above-specified bid comply with the minimum local content requirements as specified in the bid, and as measured in terms of SANS 1286:2017; and - (c) The local content percentage (%) indicated below has been calculated using the formula given in clause 3 of SANS 1286:2017, the rates of exchange indicated in paragraph 3.1 above and the information contained in Declarations D and E which has been consolidated in Declaration C: Bid price, excluding VAT (y); R. Imported content (x), as calculated in terms of SANS 1286:2017; R. Stipulated minimum threshold for local content (paragraph 2 above); ………….%. Local content %, as calculated in terms of SANS 1286:2017; ………….%. If the bid is for more than one product, the local content percentages for each product contained in Declaration C shall be used instead of the table above. The local content percentage for each product has been calculated using the formula given in clause 3 of SANS 1286:2017, the rates of exchange indicated in paragraph 3.1 above and the information contained in Declarations D and E. - (d) I accept that the Procurement Authority / Institution has the right to request that the local content be verified in terms of the requirements of SANS 1286:2017. SIGNATURE: DATE: WITNESS 1: SIGNATURE: ……………………………………... NAME (IN CAPITALS): WITNESS 2: SIGNATURE: ……………………………………... NAME (IN CAPITALS):

FORM A3.6:	LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE (ANNEXURE C)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

| C1 | Tender No.: |  |  |  |  |  |  | Note: VAT to be excluded from all calculations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C2 | Tender Description: |  |  |  |  |  |  |  |
| C3 | Designated Product(s): |  |  |  |  |  |  |  |
| C4 | Tender Authority: |  |  |  |  |  |  |  |
| C5 | Tendering Entity Name: |  |  |  |  |  |  |  |
| C6 | Tender Exchange Rate: | Pula | P | EU | € | GBP | £ |  |

|  |  | Calculation of Local Content |  |  |  |  |  |  |  |  |  | Tender Summary |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender Item No.’s | List of Items | Tender Price Each (Excl. VAT) | Exempted Imported Value | Tender Value Net of Exempted Imported Content |  | Imported Value |  | Local Value | Local Content % (Per Item) |  |  | Tender Qty | Total Tender Value | Total Exempted Imported Content | Total Imported Content |
| (C8) | (C9) | (C10) | (C11) | (C12) |  | (C13) |  | (C14) | (C15) |  |  | (C16) | (C17) | (C18) | (C19) |
|  |  |  |  |  |  |  |  |  | (C20) Total Tender Value |  |  |  | R |  |  |
|  |  |  |  |  |  |  |  |  | (C21) Total Exempt Imported Content |  |  |  |  | R |  |
|  |  |  |  |  |  |  | (C22) Total Tender value net of exempt imported content |  |  |  |  |  |  | R |  |
|  |  |  |  |  |  |  |  |  |  |  |  | (C23) Total Imported Content |  |  | R |
|  |  |  |  |  |  |  |  |  |  |  |  | (C24) Total Local Content |  |  | R |
|  |  |  |  |  |  |  |  |  |  |  | (C25) Average Local Content % of tender |  |  |  | …% |
| Signature of tenderer from Annex B (SANS 1286.2017): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ANNEXURE D:  IMPORTED CONTENT DECLARATION - SUPPORTING SCHEDULE TO ANNEXURE C

| (D1) | Tender No.: |  |  |  |  |  |  | Note: VAT to be excluded from all calculations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (D2) | Tender Description: |  |  |  |  |  |  |  |
| (D3) | Designated Product(s): |  |  |  |  |  |  |  |
| (D4) | Tender Authority: |  |  |  |  |  |  |  |
| (D5) | Tendering Entity Name: |  |  |  |  |  |  |  |
| (D6) | Tender Exchange Rate: | Pula | P | EU | € | GBP | £ |  |

| A. Exempted imported content |  |  |  | Calculation of imported content |  |  |  |  |  | Summary |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender item’no's | Description of imported content | Local supplier | Overseas Supplier | Foreign currency value as per Commercial Invoice | Tender Exchange Rate | Local value of imports | Freight costs to port of entry | All locally incurred landing costs & duties | Total landed cost excl VAT | Tender Qty | Exempted imported value |
| (D7) | (D8) | (D9) | (D10) | (D11) | (D12) | (D13) | (D14) | (D15) | (D16) | (D17) | (D18) |
|  |  |  |  |  |  |  |  | (D19) Total exempt imported value |  |  | R0 |
|  |  |  |  |  |  |  |  | This total must correspond with Annex C - C 21 |  |  |  |

| B. Imported directly by the Tenderer |  |  |  | Calculation of imported content |  |  |  |  |  | Summary |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tender item’no's | Description of imported content | Local supplier | Overseas Supplier | Foreign currency value as per Commercial Invoice | Tender Exchange Rate | Local value of imports | Freight costs to port of entry | All locally incurred landing costs & duties | Total landed cost excl VAT | Tender Qty | Exempted imported value |
| (D33) | (D34) | (D35) | (D36) | (D37) | (D38) | (D39) | (D40) | (D41) | (D42) | (D43) | (D44) |
|  |  |  |  |  |  |  |  | (D45) Total imported value by 3rd party |  |  | R0 |

| Signature of tenderer from Annex B (SANS 1286.2017): |  |  |
| --- | --- | --- |
| Date: |  |  |

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

| C. Imported by a 3rd party and supplied to the Tenderer |  |  |  |  |  |  |  |  |  | Calculation of imported content |  |  |  |  |  |  |  |  |  |  |  | Summary |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description of imported content |  | Unit of measure |  |  |  | Local supplier |  | Overseas Supplier |  | Foreign currency value as per Commercial Invoice |  | Tender Rate of Exchange |  | Local value of imports |  | Freight costs to port of entry | All locally incurred landing costs & duties |  | Total landed cost excl VAT |  |  | Quantity imported |  | Total imported value |
| (D33) |  | (D34) |  |  |  | (D35) |  | (D36) |  | (D37) |  | (D38) |  | (D39) |  | (D40) | (D41) |  | (D42) |  |  | (D43) |  | (D44) |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | (D45) Total imported value by 3rd party |  |  |  |  |  |  |  |  |  | R 0 |
| D. Other foreign currency payments |  |  |  |  |  |  |  | Calculation of foreign currency payments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Summary of payments |
| Type of payment |  | Local supplier making the payment |  |  |  | Overseas beneficiary |  | Foreign currency value paid |  | Tender Rate of Exchange |  |  |  |  |  |  |  |  |  |  |  |  |  | Local value of payments |
| (D46) |  | (D47) |  |  |  | (D48) |  | (D49) |  | (D50) |  |  |  |  |  |  |  |  |  |  |  |  |  | (D51) |
|  |  |  |  |  |  |  |  |  |  | (D52) Total of foreign currency payments declared by tenderer and/or 3rd party |  |  |  |  |  |  |  |  |  |  |  |  |  | R 0 |
| Signature of tenderer from Annexure B: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (SANS 1286.2017) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | (D53) Total of imported content & foreign currency paymen–s - (D32), (D45) & (D52) above |  |  |  |  |  |  |  |  |  |  | R 0 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | This total must correspond with Annex C - C 23 |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ANNEXURE E:  IMPORTED CONTENT DECLARATION - SUPPORTING SCHEDULE TO ANNEXURE C

| (E1) | Tender No.: |  | Note: VAT to be excluded from all calculations |
| --- | --- | --- | --- |
| (E2) | Tender Description: |  |  |
| (E3) | Designated Product(s): |  |  |
| (E4) | Tender Authority: |  |  |
| (E5) | Tendering Entity Name: |  |  |

| Local Products (Goods, Services and Works) |  |  | Description of items purchased |  |  | Local suppliers | Value |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (E6) |  |  | (E7) | (E8) |
|  |  |  | (E9) Total local products (Goods, Services and Works) |  |  |  | R 0 |
| (E10) | Manpower costs |  | (Tende’er's manpower cost) |  |  |  | R 0 |
| (E11) | Factory overheads |  | (Rental, depreciation & amortisation, utility costs, consumables etc.) |  |  |  | R 0 |
| (E12) | Administration overheads and mark-up |  |  | (Marketing, insurance, financing, interest etc.) |  |  | R 0 |
|  |  |  |  | (E13) Total local content |  |  | R 0 |
|  |  |  | This total must correspond with Annex C - C24 |  |  |  |  |

| Signature of tenderer from Annexure B: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| (SANS 1286.2017) |  |  |  |  |  |
| Date: |  |  |  |  |  |

FORM A4:	SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The postulated tender MUST be priced.

- When submitting any alternative tender, condition of clause C.2.12 of Tender Data, shall be followed.

| Page | Description |
| --- | --- |

SIGNED BY TENDERER:

FORM A5:	SCHEDULE OF ADDENDA TO TENDER DOCUMENTS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- If an addendum containing material amendments is not incorporated by the tenderer in his tender offer, the tender will be declared non-responsive.

| We confirm that the following communications received from the Employer before the submission of this tender offer, amending the tender documents, have been taken into account in this tender offer: |  |  |
| --- | --- | --- |
|  | Date | Title or Details |

SIGNED BY TENDERER:

FORM A6: 	CERTIFICATE OF TAX COMPLIANCE (INCORPORATING SBD2)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

The tenderer shall complete the declaration below.

I, 	 (name)

the undersigned in my capacity as 	 (position)

on behalf of 	 (name of company)

herewith grant consent that SARS may disclose to the South African National Roads Agency SOC Limited (SANRAL) our tax compliance status. For this purpose, our unique security personal identification number (PIN) is …………………our tax reference number is

and our tax clearance certificate number is 	.

In the event of a joint venture, each member shall comply with the above requirement.

SIGNED BY TENDERER:

FORM A7:	CERTIFICATE OF INSURANCE COVER

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

In the event of the tenderer being a joint venture/consortium, the details of the individual members must also be provided.

The tenderer shall provide the following details of this insurance cover:

- Name of Tenderer:

- Period of Validity:

- Value of Insurance:

- Insurance for Works and Contractor’s Equipment

Company:

Value:

- Insurance for Contractor’s Personnel

Company:

Value:

- General public liability

Company:

Value:

- SASRIA

Company:

Value:

SIGNED BY TENDERER:

FORM A8:	TENDERERS REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer shall attach to this form a letter (dated less than 3 months prior to the tender closing date) from a Registered Financial Service Provider (registered with the FSB) confirming his account and confirms the Tenderer’s available capital and that the Tenderer has the financial means net of current commitments (independent of any contractual advance payment) available to meet the construction cash flow requirements estimated for the subject contract or a written confirmation from any registered financial institution or the tenderer’s independent registered accountant should be requested to submit confirmation of the available working capital to meet the construction workflow requirements estimated for the subject contract. The confirmation by an independent registered accountant must indicate that the review, to be conducted in terms of ISRS4400, was done in terms of the Section 30 and Regulation 29 of the Companies Act No. 71 of 2008.

- Failure to provide the required letter with the tender submission may render the tenderer’s offer non-responsive in terms of tender condition C.3.8. Failure to provide the required letter with the tender submission may render the tenderer’s offer non-responsive in terms of tender condition C.3.8.

- In the event that the tenderer is a joint venture enterprise, details of all the members of the joint venture shall be similarly provided and attached to this form.

- In the event that the Employer at its sole discretion is not satisfied with the financial capability of the tenderer as a result of whatsoever nature and reason, the Employer reserves the right to invoke the provisions under tender data C.3.13. In addition, the Employer reserve the right to perform a full risk assessment as per tender data C.3.13. Furthermore, if the aforementioned occur, any and all report/s will be used to evaluate the Tenderer’s ability to perform the contract as stated in sub-clause C3.13.(b) of the CIDB  Standard for Uniformity.

- The letter shall contain the information as indicated below.

- The successful Tenderer may be requested to demonstrate its financial capability to execute the contract prior to award at SANRAL’s discretion.

- If the tenderer does not have financial resources, the tender will be declared non-responsive.

DATE

Bank Name

FSB Number

Bank Address

RE:	ACCOUNT CONDUCT AND CASHFLOW CONFIRMATION

To Whom It May Concern:

We hereby confirm that Tenderer Name has been banking with xxxx bank for a period of xxx years and the account has been conducted in a satisfactory manner. Tenderer Name has the financial means, net of current commitments available to meet the construction cash flow requirements to the value of xxxxx for contract (insert contract number).

- Name of Account Holder:

- Account Number:

- Bank name:

- Branch Number:

- Bank and branch contact details

Yours Sincerely,

BANK STAMP

Name______________________		Signature ________________________

FORM A9.1:	SCHEDULE OF TENDERER'S LITIGATION HISTORY

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

- The tenderer shall list below details of any litigation with which the tenderer (including its directors, shareholders or other senior members in previous companies) has been involved with any organ of state or state department within the last ten years. The details must include the year, the litigating parties, the subject matter of the dispute, the value of any award or estimated award if the litigation is current and in whose favour the award, if any, was made.

| Employer | Other litigating party | Dispute | Award value | Date resolved |
| --- | --- | --- | --- | --- |

SIGNED BY TENDERER:

FORM A9.2:	ENVIRONMENTAL, SOCIAL, HEALTH, AND SAFETY PERFORMANCE DECLARATION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer (and in the case of a Joint Venture, each member of the Joint Venture) shall indicate below by marking with an “X” if suspension or termination of a contract occurred or not, and/or if the performance security has been called or not, related to Environmental, Social, Health or Safety (ESHS) performance, in the past five (5) years prior to the tender submission date.

- In the event that suspension or termination occurred and/or the performance security has been called, the tenderer shall complete the details of all the suspensions and terminations as well as the details of all performance securities called since the date indicated.

The Employer may use this information to seek further information or clarifications in carrying out its due diligence.

| Environmental, Social, Health, and Safety Performance Declaration in accordance with clause 4.1.1 of the Tender Data. |  |  |  |
| --- | --- | --- | --- |
| ¨ No suspension or termination of contract: An employer has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental, Social, Health, or Safety (ESHS) performance in the past five (5) years prior to the tender submission date. ¨ Declaration of suspension or termination of contract: The following contract(s) has/have been suspended or terminated and/or Performance Security called by an employer(s) for reasons related to Environmental, Social, Health, or Safety (ESHS) performance in the past five (5) years prior to the tender submission date. Details are described below: |  |  |  |
| Year | Suspended or terminated portion of contract | Contract Identification | Total Contract Amount |
| [insert year] | [insert amount and percentage] | [insert complete contract name, contract number, Name of Employer, Address of Employer, Reason(s) for suspension or termination] | [insert amount] |
| Performance Security called by an employer(s) for reasons related to ESHS performance |  |  |  |
| Year | Contract Identification |  | Total Contract Amount |
| [insert year] | [insert complete contract name, contract number, Name of Employer, Address of Employer, Reason(s) for calling of performance security] |  | [insert amount] |

SIGNED BY TENDERER:

FORM A10:	SCHEDULE OF CURRENT COMMITMENTS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer shall list below all contracts currently in progress or awarded and about to commence and tenders for which offers have been submitted but awards not yet made.

- In the event of a joint venture enterprise, details of all the members of the joint venture shall similarly be attached to this form.

- The lists must be restricted to not more than 20 contracts and 20 tenders. If a tenderer’s actual commitments or potential commitments are greater than 20 each, those listed should be in descending order of expected final contract value or sum tendered.

| Table 1: CONTRACTS AWARDED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer | Project | Expected total value of contract (incl. VAT) | Duration (Months) | Expected completion date |

| Table 2: TENDERS NOT YET AWARDED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Employer | Project | Sum Tendered (incl. VAT) | Tendered Duration (Months) | Expected commence-ment |

SIGNED BY TENDERER:

FORM A11:	CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993 (ACT NO. 130 OF 1993)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- Discovery that the tenderer has failed to make proper disclosure may result in SANRAL terminating a contract that flows from this tender on the ground that it has been rendered invalid by the tenderer’s misrepresentation.

- The tenderer shall attach to this Form evidence that he is registered and in good standing with the compensation fund or with a licensed compensation insurer who is approved by Department of Labour in terms of section 80 of the Compensation for Injury and Disease Act, 1993 (Act No. 130 of 1993).

- The tenderer is required to disclose, by also attaching documentary evidence to this form, all inspections, investigations and their outcomes conducted by the Department of Labour into the conduct of the tenderer at any time during the 36 months preceding the date of this tender.

- In the event of a Joint Venture each member of JV must comply with the above.

SIGNED BY TENDERER:

FORM A12:	JOINT VENTURE AGREEMENT

CONTRACT SANRAL N.004-112-2019/1

FOR THE OPERATIONS AND MAINTENANCE OF QUAGGA AND PELINDABA TOLL PLAZAS ON THE N4 MAGALIES TOLL ROAD

Note to Tenderer:

- In the event of a Joint Venture, attach to this form a signed and properly completed Joint     Venture Agreement.

SIGNED BY TENDERER:

FORM A13:	FORM SBD1 – INVITATION TO BID AND TERMS AND CONDITIONS FOR BIDDING

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

PART A:  INVITATION TO BID

| YOU ARE HEREBY INVITED TO BID FOR REQUIREMENTS OF THE (NAME OF DEPARTMENT/ PUBLIC ENTITY) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BID NUMBER: | N.001-249-2019/1R NSC |  |  | CLOSING DATE: |  | 5 April 2024 |  |  | CLOSING TIME: |  | 11h00 |
| DESCRIPTION | FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD |  |  |  |  |  |  |  |  |  |  |
| BID RESPONSE DOCUMENTS MAY BE DEPOSITED IN THE BID BOX SITUATED AT (STREET ADDRESS) |  |  |  |  |  |  |  |  |  |  |  |
| The South African National Roads Agency SOC Ltd |  |  |  |  |  |  |  |  |  |  |  |
| 38 Ida Street |  |  |  |  |  |  |  |  |  |  |  |
| Menlo Park |  |  |  |  |  |  |  |  |  |  |  |
| Pretoria, 0081 |  |  |  |  |  |  |  |  |  |  |  |
| BIDDING PROCEDURE ENQUIRIES MAY BE DIRECTED TO |  |  |  |  | TECHNICAL ENQUIRIES MAY BE DIRECTED TO: |  |  |  |  |  |  |
| CONTACT PERSON |  |  | Procurement Office |  | CONTACT PERSON |  |  |  |  | Procurement Office |  |
| TELEPHONE NUMBER |  |  | N/A |  | TELEPHONE NUMBER |  |  |  |  | N/A |  |
| FACSIMILE NUMBER |  |  | N/A |  | FACSIMILE NUMBER |  |  |  |  | NO CHANGE REQUIRED |  |
| E-MAIL ADDRESS |  |  | procurementNR4@sanral.co.za |  | E-MAIL ADDRESS |  |  |  |  | procurementNR4@sanral.co.za |  |
| SUPPLIER INFORMATION |  |  |  |  |  |  |  |  |  |  |  |
| NAME OF BIDDER |  |  |  |  |  |  |  |  |  |  |  |
| POSTAL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| STREET ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| TELEPHONE NUMBER |  | CODE |  |  |  |  | NUMBER |  |  |  |  |
| CELLPHONE NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| FACSIMILE NUMBER |  | CODE |  |  |  |  | NUMBER |  |  |  |  |
| E-MAIL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |
| VAT REGISTRATION NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| SUPPLIER COMPLIANCE STATUS |  | TAX COMPLIANCE SYSTEM PIN: |  |  | OR |  |  | CENTRAL SUPPLIER DATABASE No: | MAAA |  |  |
| #### ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS /SERVICES OFFERED? |  | Yes No [IF YES ENCLOSE PROOF] |  |  | #### ARE YOU A FOREIGN BASED SUPPLIER FOR THE GOODS /SERVICES OFFERED? |  |  |  |  | Yes No [IF YES, ANSWER THE QUESTIONNAIRE BELOW] |  |
| QUESTIONNAIRE TO BIDDING FOREIGN SUPPLIERS |  |  |  |  |  |  |  |  |  |  |  |
| IS THE ENTITY A RESIDENT OF THE REPUBLIC OF SOUTH AFRICA (RSA)? YES NO DOES THE ENTITY HAVE A BRANCH IN THE RSA? YES NO DOES THE ENTITY HAVE A PERMANENT ESTABLISHMENT IN THE RSA? YES NO DOES THE ENTITY HAVE ANY SOURCE OF INCOME IN THE RSA? YES NO IS THE ENTITY LIABLE IN THE RSA FOR ANY FORM OF TAXATION? YES NO IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN IT IS NOT A REQUIREMENT TO REGISTER FOR A TAX COMPLIANCE STATUS SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 BELOW. |  |  |  |  |  |  |  |  |  |  |  |

# PART B: TERMS AND CONDITIONS FOR BIDDING

- BID SUBMISSION:

- BIDS MUST BE DELIVERED BY THE STIPULATED TIME TO THE CORRECT ADDRESS. LATE BIDS WILL NOT BE ACCEPTED FOR CONSIDERATION. - ALL BIDS MUST BE SUBMITTED ON THE OFFICIAL FORMS PROVIDED (NOT TO BE RE-TYPED) OR IN THE MANNER PRESCRIBED IN THE BID DOCUMENT. - THIS BID IS SUBJECT TO THE PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000 AND THE PREFERENTIAL PROCUREMENT REGULATIONS, THE GENERAL CONDITIONS OF CONTRACT (GCC) AND, IF APPLICABLE, ANY OTHER SPECIAL CONDITIONS OF CONTRACT. - THE SUCCESSFUL BIDDER WILL BE REQUIRED TO FILL IN AND SIGN A WRITTEN CONTRACT FORM (SBD7).

- TAX COMPLIANCE REQUIREMENTS

- BIDDERS MUST ENSURE COMPLIANCE WITH THEIR TAX OBLIGATIONS. - BIDDERS ARE REQUIRED TO SUBMIT THEIR UNIQUE PERSONAL IDENTIFICATION NUMBER (PIN) ISSUED BY SARS TO ENABLE THE ORGAN OF STATE TO VERIFY THE TAXPAYER’S PROFILE AND TAX STATUS. - APPLICATION FOR TAX COMPLIANCE STATUS (TCS) PIN MAY BE MADE VIA E-FILING THROUGH THE SARS WEBSITE WWW.SARS.GOV.ZA. - BIDDERS MAY ALSO SUBMIT A PRINTED TCS CERTIFICATE TOGETHER WITH THE BID. - IN BIDS WHERE CONSORTIA / JOINT VENTURES / SUB-CONTRACTORS ARE INVOLVED; EACH PARTY MUST SUBMIT A SEPARATE TCS CERTIFICATE / PIN / CSD NUMBER. - WHERE NO TCS PIN IS AVAILABLE BUT THE BIDDER IS REGISTERED ON THE CENTRAL SUPPLIER DATABASE (CSD), A CSD NUMBER MUST BE PROVIDED. - NO BIDS WILL BE CONSIDERED FROM PERSONS IN THE SERVICE OF THE STATE, COMPANIES WITH DIRECTORS WHO ARE PERSONS IN THE SERVICE OF THE STATE, OR CLOSE CORPORATIONS WITH MEMBERS PERSONS IN THE SERVICE OF THE STATE.”

NB:   FAILURE TO PROVIDE ANY OF THE ABOVE PARTICULARS will render the tenderer’s offer non-responsive and it will not be considered

SIGNATURE OF BIDDER:		…………………………….…

CAPACITY UNDER WHICH THIS BID IS SIGNED:	……………………………….

(Proof of authority must be submitted, e.g. Company Resolution)

DATE:	……………………………….

FORM B1:	CURRENCY EXCHANGE RATE FLUCTUATIONS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to Tenderer:

- Tenderers should note that the Contract and the Contract Price are ZAR (Rand) denominated. The Employer shall however allow the tenderer, should it so elect, to indicate which parts of Plant and specialist foreign labour the tenderer wishes to price in foreign currency.  Only Euro or USD will be allowed as foreign currencies.  All the remaining items and all the other associated costs shall remain in ZAR and the tenderer shall complete the Schedule of Payments as such. All amounts paid pursuant to the Contract, will however be paid by the Employer to the Contractor in ZAR, with the foreign currency components being converted into ZAR by the Employer (at the rate quoted by the Employer's primary bankers at 10:00 seven (7) days prior to the last day for payment as contemplated in the FIDIC Conditions of Contract (Volume 1) as amended by the FIDIC Particular Conditions of Contract and the Special Provisions (Part C1)). For these purposes, the tenderer shall list below those items of Plant and Specialist Foreign Labour which it intends to price in Euro or USD. Under no circumstances may items which do not constitute Plant or Specialist Foreign Labour, be priced in Euro or USD and included in the items to be listed below.

For tender evaluation purposes only, the tenderer shall include those items of Plant (which are priced in Euro or USD) and which are listed below, in the Schedule of Payments/Cost Matrix in ZAR, by converting those items into ZAR at the applicable exchange rate, taken at 28 days prior to the closing date of the tender.  The tenderer shall state the exchange rate used for each item in the table below.

The balance of the tendered amount (i.e. the non-Euro or non-USD based amount) in the Schedule of Payments/Cost Matrix shall be subject to Contract Price Adjustment as contemplated in Part C2: Pricing Data.

| No | Payment Item reference in SoP | Item Description (Plant of Specialist Foreign labour only) | Direct Foreign Price | Tendered Amount in ZAR to be transferred to SoP | Exchange rate used (USD:ZAR) |
| --- | --- | --- | --- | --- | --- |
|  | Tenderer to add Rows to table as needed |  |  |  |  |

This aforementioned is however subject to the requirements of sub-clause 14.17 of the Particular Conditions of Contract (Part C1).

SIGNED BY TENDERER:

FORM C1.1:	TENDERER’S B-BBEE VERIFICATION CERTIFICATION

Notes to tenderer:

1. The tenderer shall attach to this form a valid B-BBEE verification certificate issued in accordance with:

(a)	the revised Notice of Clarification published in Notice 444 of 2015 of Government Gazette No.38799 on 15 May 2015 by the Department of Trade, Industry and Competition, or

(b)	if the scorecard is issued after 1 December 2020, the amended Codes of Good Practice published in Notice 303 of 2019 of Government Gazette No. 42496 on 31 May 2019 by the Department of Trade, Industry and Competition or;

(c)	the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade, Industry and Competition.

If Measured Entity operates in more than one sector or sub-sector, the scorecard for the sector or sub-sector in which the majority of its core activities (measured in terms of Annual Revenue) are located will be acceptable.

(d)	the Information and Communication Technology (ICT) Sector Codes (Published in Notice 1387 of Government Gazette No. 40407 of 7 November 2016); or

(e)	;the Financial Sector Sector (Published in Notice 1325 of Government Gazette No. 41287 of 1 December 2017); or

(f)	The Integrated Transport Sector Codes (Published in Notice 1162 of Government Gazette No. 32511 of 21 August 20192009).

2.	The certificate shall:

a)	have been issued by a verification agency accredited by the South African National Accreditation System (SANAS); or

b)	be in the form of a sworn affidavit or a certificate issued by the Companies and Intellectual Property Commission in the case of an Exempted Micro Enterprise (EME) with a total annual revenue of less than R3 million if issued in accordance with the amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade, Industry and Competition; and

c)	be valid at the original advertised tender closing date; and

d)	have a date of issue less than 12 (twelve) months prior to the tender closing date (see Tender Data C.2.15).

3.	A valid BBBEE Certificates shall contain:

a)	Name of enterprise as per enterprise registration documents issued by CIPC, and enterprise business address.

b)	Value-Added Tax number, where applicable.

c)	The B-BBEE Scorecard against which the certificate is issued, indicating all elements and scores achieved for each element. The actual score achieved must be linked to the total points as per the relevant Codes.

d)	B-BBEE status with corresponding procurement recognition level.

e)	The relevant Codes used to issue the B-BBEE verification certificate.

f)	Date of issue and expiry (e.g. 9 June 2018 to 8 June 2019). Where    a measured entity was subjected to a re-verification process, due to material change, the B-BBEE Verification Certificate must reflect the initial date of issue, date of re-issue and the initial date of expiry. Re-verification does not extend the lifespan of the B-BBEE Verification Certificate.

g)	Financial period which was used to issue the B-BBEE Verification Certificate

4.	A valid Sworn Affidavit shall contain:

a)	Name/s of deponent as they appear in the identity document and the identity number.

b)	Designation of the deponent as either the director, owner or member must be indicated in order to know that person is duly authorised to depose of an affidavit.

c)	Name of enterprise as per enterprise registration documents issued by the CIPC, where applicable, and enterprise business address.

d)	Percentage black ownership, black female ownership and whether they fall within a designated group.

e)	Indicate total revenue for the year under review and whether it is based on audited financial statements or management accounts.

f)	Financial year-end as per the enterprise’s registration documents, which was used to determine the total revenue. The valid format of the Financial Year-End is Day/Month/Year

g)	B-BBEE status level. An enterprise can only have one status level.

h)	Date deponent signed and date of Commissioner of Oath must be the same.

i)	Commissioner of Oath cannot be an employee or ex officio of the enterprise because, a person cannot by law, commission a sworn affidavit in which they have an interest, and

5.	In the event of a Joint Venture (JV), a project specific (SANRAL project number indicated) consolidated B-BBEE verification certificate in the name of the JV, shall be attached.

6.	The attached verification certificate and the associated assessment report shall comply with the requirements of Tender Data clause C.3.11.8 and shall identify:

(a)	The name and domicilium citandi et executandi of the tenderer.

(b)	The registration and VAT number of the tenderer.

(c)	The dates of granting of the B-BBEE score and the period of validity.

(d)	The expiry date of the verification certificate.

(e)	A unique identification number.

(f)	The standard and/or normative document, including the issue and/or revision used to evaluate the tenderer.

(g)	The name and/or mark/logo of the B-BBEE verification agency.

(h)	The category (Generic, QSE, EME) in which the tenderer has been measured.

(i)	The B-BBEE status level.

(j)	The South African National Accreditation System (SANAS) logo on the verification certificate once verification agencies have been accredited.

(k)	The B-BBEE procurement recognition level.

(l)	The score achieved per B-BBEE element.

(m)	The % black shareholding.

(n)	The % black women shareholding.

(o)	The % black persons with disabilities shareholding

(p)	The % black youth shareholding

(q)	The % black people living in rural or underdeveloped areas or townships shareholding

(r)	The % black military veterans shareholding

(s)	The value-added status of the tenderer.

7.	The Employer will not be responsible to acquire data that it needs for its own reporting systems and which may not form part of a verification agency’s standard certificate format. The tenderer, at its own cost, must acquire any missing specified data listed in 4 above from its selected verification agency and have it recorded on the certificate. Alternatively, such missing data must be supplied separately, but certified as correct by the same verification agency and also attached to this form.

FORM C1.2:	PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017 (INCORPORATING SBD6.1)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

This preference form must form part of all tenders invited.  It contains general information and serves as a claim form for preference points for specific goals.

NB:	BEFORE COMPLETING THIS FORM, TENDERERS MUST STUDY THE GENERAL CONDITIONS, DEFINITIONS AND DIRECTIVES APPLICABLE IN RESPECT OF THE TENDER AND PREFERENTIAL PROCUREMENT REGULATIONS, 2022

- GENERAL CONDITIONS

  - The following preference point systems are applicable to invitations to tender:

- the 80/20 system for requirements with a Rand value of up to R50 000 000 (all applicable taxes included); and

- the 90/10 system for requirements with a Rand value above R50 000 000 (all applicable taxes included).

  - To be completed by the organ of state

- The applicable preference point system for this tender is the 90/10 preference point system.

- Either the 90/10 or 80/20 preference point system will be applicable in this tender. The lowest/ highest acceptable tender will be used to determine the accurate system once tenders are received.

  - Points for this tender (even in the case of a tender for income-generating contracts) shall be awarded for:

- Price; and

- Specific Goals.

  - To be completed by the organ of state:

The maximum points for this tender are allocated as follows:

|  | POINTS |
| --- | --- |
| PRICE | 90 |
| SPECIFIC GOALS | 10 |
| Total points for Price and Specific Goals | 100 |

  - Failure on the part of a tenderer to submit proof or documentation required in terms of this tender to claim points for specific goals with the tender, will be interpreted to mean that preference points for specific goals are not claimed.

  - The organ of state reserves the right to require of a tenderer, either before a tender is adjudicated or at any time subsequently, to substantiate any claim in regard to preferences, in any manner required by the organ of state.

- DEFINITIONS

- “tender” means a written offer in the form determined by an organ of state in response to an invitation to provide goods or services through price quotations, competitive tendering process or any other method envisaged in legislation;

- “price” means an amount of money tendered for goods or services, and includes all applicable taxes less all unconditional discounts;

- “rand value” means the total estimated value of a contract in Rand, calculated at the time of bid invitation, and includes all applicable taxes;

- “tender for income-generating contracts” means a written offer in the form determined by an organ of state in response to an invitation for the origination of income-generating contracts through any method envisaged in legislation that will result in a legal agreement between the organ of state and a third party that produces revenue for the organ of state, and includes, but is not limited to, leasing and disposal of assets and concession contracts, excluding direct sales and disposal of assets through public auctions; and

- “the Act” means the Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000).

- FORMULAE FOR PROCUREMENT OF GOODS AND SERVICES

  - POINTS AWARDED FOR PRICE

3.1.1   THE 80/20 OR 90/10 PREFERENCE POINT SYSTEMS

A maximum of 80 or 90 points is allocated for price on the following basis:

80/20	or						90/10

Ps=801-Pt-PminPmin	or	Ps=901-Pt-PminPmin

Where

Ps	=	Points scored for price of tender under consideration

Pt	=	Price of tender under consideration

Pmin	=	Price of lowest acceptable tender

- POINTS AWARDED FOR SPECIFIC GOALS

  - In terms of Regulation 4(2); 5(2); 6(2) and 7(2) of the Preferential Procurement Regulations, preference points must be awarded for specific goals stated in the tender. For the purposes of this tender the tenderer will be allocated points based on the goals stated in table 1 below as may be supported by proof/ documentation stated in the conditions of this tender:

  - In cases where organs of state intend to use Regulation 3(2) of the Regulations, which states that, if it is unclear whether the 80/20 or 90/10 preference point system applies, an organ of state must, in the tender documents, stipulate in the case of—

- an invitation for tender for income-generating contracts, that either the 80/20 or 90/10 preference point system will apply and that the highest acceptable tender will be used to determine the applicable preference point system; or

- any other invitation for tender, that either the 80/20 or 90/10 preference point system will apply and that the lowest acceptable tender will be used to determine the applicable preference point system,  then the organ of state must indicate the points allocated for specific goals for both the 90/10 and 80/20 preference point system.

Table 1: Specific goals for the tender and points claimed are indicated per the table below.

| The specific goals allocated points in terms of this tender | Criteria | Number of points allocated (90/10 system) | Number of points allocated (80/20 system) | Number of points claimed (90/10 system) (To be completed by the tenderer) | Number of points claimed (80/20 system) (To be completed by the tenderer) |
| --- | --- | --- | --- | --- | --- |
| B-BBEE level scorecard of the tendering entity. | B-BBEE Level 1 | 1,00 | 2.00 |  |  |
|  | B-BBEE Level 2 | 0,90 | 1.80 |  |  |
|  | B-BBEE Level 3 | 0,60 | 1.20 |  |  |
|  | B-BBEE Level 4 | 0,50 | 1.0 |  |  |
|  | B-BBEE Level 5 | 0,40 | 0.80 |  |  |
|  | B-BBEE Level 6 | 0,30 | 0.60 |  |  |
|  | B-BBEE Level 7 | 0,20 | 0.40 |  |  |
|  | B-BBEE Level 8 | 0,10 | 0.20 |  |  |
|  | Non-compliant contributor | 0 | 0 |  |  |
| Percentage black ownership of the tendering entity. | < 51 % black ownership | 0 | 0 |  |  |
|  | ≥ 51 to < 70 % black ownership. | 1 | 2 |  |  |
|  | ≥ 70 to < 100 % black ownership. | 2 | 4 |  |  |
|  | 100 % black ownership | 5 | 10 |  |  |
| Percentage Subcontracting to Targeted Enterprises | Min 50 % subcontracting | 0 | 4 | 0 | 8 |
|  | > 50 to < 55 % subcontracting | 1 |  | 2 |  |
|  | ≥ 55 to < 60 % subcontracting | 2 |  | 4 |  |
|  | ≥ 60 % subcontracting | 4 |  | 8 |  |

Note to tenderers: The tenderer must indicate how they claim points for each preference point system.

- DECLARATION WITH REGARD TO COMPANY/FIRM

  - Name of company/firm…………………………………………………………………….

  - Company registration number: …………………………………………………………...

  - TYPE OF COMPANY/ FIRM

Partnership/Joint Venture / Consortium

One-person business/sole propriety

Close corporation

Public Company

Personal Liability Company

(Pty) Limited

Non-Profit Company

State Owned Company

[Tick applicable box]

  - I, the undersigned, who is duly authorised to do so on behalf of the company/firm, certify that the points claimed, based on the specific goals as advised in the tender, qualifies the company/ firm for the preference(s) shown and I acknowledge that:

- The information furnished is true and correct;

- The preference points claimed are in accordance with the General Conditions as indicated in paragraph 1 of this form;

- In the event of a contract being awarded as a result of points claimed as shown in paragraphs 1.4 and 4.2, the contractor may be required to furnish documentary proof to the satisfaction of the organ of state that the claims are correct;

- If the specific goals have been claimed or obtained on a fraudulent basis or any of the conditions of contract have not been fulfilled, the organ of state may, in addition to any other remedy it may have –

  - disqualify the person from the tendering process;

  - recover costs, losses or damages it has incurred or suffered as a result of that person’s conduct;

  - cancel the contract and claim any damages which it has suffered as a result of having to make less favourable arrangements due to such cancellation;

  - recommend that the tenderer or contractor, its shareholders and directors, or only the shareholders and directors who acted on a fraudulent basis, be restricted from obtaining business from any organ of state for a period not exceeding 10 years, after the audi alteram partem (hear the other side) rule has been applied; and

  - forward the matter for criminal prosecution, if deemed necessary.

……………………………………….

SIGNATURE(S) OF TENDERER(S)

SURNAME AND NAME:	 ……………………………………………………….

DATE:			………………………………………………………

ADDRESS:		………………………………………………………

………………………………………………………

………………………………………………………

………………………………………………………

FORM D1:	SCHEDULE OF TENDERER’S PLANT AND EQUIPMENT

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

The tenderer shall provide full details in the table below what equipment that will be immediately available for this contract, equipment that will become available by virtue of outstanding orders, and further what equipment that will be acquired or hired for the works should the tenderer be awarded the contract.

D1.1:  MIS/BACK OFFICE SYSTEM AND TOLL COLLECTION LANE EQUIPMENT (MIS, TCCs, TCTs, AVCs, OHLS, etc., and testing/measuring equipment, including servers, workstations, laptop computers, mimic test panel, oscilloscope, AVC simulator, ETC Equipment, spare equipment, etc.) (All equipment listed should be in good working condition)

- Equipment immediately available (I)

- Equipment in order (O) (State details of arrangements made, with delivery dates)

- Equipment that will be acquired or hired (H) (State details of delivery arrangements)

| DESCRIPTION, SIZE, CAPACITY | NUMBER | AVAILABILITY |
| --- | --- | --- |

SIGNED BY TENDERER:

FORM D2:	TENDERER’S METHOD STATEMENT

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

The tenderer shall provide a method statement with the details as indicated on this form.

The method statement must respond to the Scope of Work and Site Information under Part C4 and outline the proposed approach/methodology. The method statement should articulate what value the Tenderer will add by in achieving the stated objectives for the project.

The Tenderer must as such explain the following:

- Its understanding of the objectives of the assignment and the Employer’s stated and implied requirements,

- Highlight the issues of importance and explain the technical approach they would adopt to address them, and

- Explain the methodologies which are to be adopted, demonstrate the compatibility of those methodologies with the proposed approach. The approach should also include a quality plan which outlines processes, procedures and associated resources, applied by whom and when, to meet the requirements and indicate how risks will be managed and what contribution can be made regarding value management.

The tenderer must attach his/her approach paper to this page. The approach paper should not be longer than 5 pages.

SIGNED BY TENDERER:

FORM D3:	TENDERER’S ORGANISATION AND STAFFING

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The intention of this form is to demonstrate the tenderer’s project structure, as well as the lines of responsibility between members of the project team and between the project team and the overall company structure. Attach own organogram to this form; do not populate the example diagram below.

- Tenderers which are large companies may simplify the organogram by ‘rolling up’ portfolios e.g. combining directors/associates into one box of the organogram. However, the individual positions of the key persons within the structure must still be shown. The same person could fill multiple positions.

- Joint Venture tenders require each element of the venture to submit separate organograms that show the individual structure of each member company and the lines of responsibility of the proposed personnel involved in the project. In addition, there must also be a combined organogram that indicates how the joint venture itself will function and the proposed share of the work will become a contractual obligation between the members of the joint venture.

- State the city or town where the company’s head office is located. The locality of regional or satellite offices, regardless of degree of autonomy or size is not required. Only submit the number of offices other than the head office. Do not count offices outside RSA.

- In the lower table list those who will be involved in priority order of most to least responsibility for the service. Provide details of the key staff. Except for the MD, all of others must submit Forms D4. The same person may perform multiple roles.

- Failure to comply with all requirements on Form D3 may render the Tender offer as non-responsive.

- The Contractor shall complete Form D4.x for all the key personnel required in C3.11 of Part T1. The Contractor shall also complete D4.x for non-key personnel as indicated.

| Head Office: | State City/Town. See note 4. |
| --- | --- |
| Other Offices: | Only list number, See note 4 |
| Total Employees : |  |
| % share in JV agreement: | State 100% if no JV |

| Name of employee | Position in team | Estimated monthly hours | Relevant specialist areas of knowledge demonstrating suitability for position |
| --- | --- | --- | --- |
|  | Construction manager (Contractor’s Representative) |  |  |
|  | Example Operations Manager |  |  |
|  | Maintenance Manager |  |  |
|  | Plaza Manager |  |  |

SIGNED BY TENDERER:

FORM D4.1:	PERSONNEL RESOURCE DETAIL (NSC representative)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Business/Operations Management • Systems Integration Management • Maintenance (Systems and Facilities) Management; • FIDIC Experience/Dispute Resolution • Performance Management.. Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.2:	PERSONNEL RESOURCE DETAIL (QUALITY CONTROL OFFICER)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Testing and assessing of software products • Identifying defects or potential issues and determining ways to resolve • Recording and reporting issues; • Supporting process improvements throughout the testing and quality assurance processes.. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.3:	PERSONNEL RESOURCE DETAIL (maintenance manager)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Project Management; • Performance Management; • Documentation Development (procurement) and procurement process;; • Hardware Maintenance Programmes; • Maintenance Audit Reviews; • Maintenance Trend Analysis.. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.4:	PERSONNEL RESOURCE DETAIL (SYSTEM/ SOFTWARE SPECIALIST)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Support to end-users via email, phone, web or in-person • Monitoring and owning all support related metrics including ticket backlog, average time to close, etc.; • Working with development teams to modify and engineer software solutions and configurations • Team management; resource planning and scheduling.. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.5:	PERSONNEL RESOURCE DETAIL (NETWORK AND SECURITY SPECIALIST)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Local Area and Wide Area network design • Network architecture • Network performance monitoring, maintenance, and support; • Network/cyber security. Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.6.1:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 1)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Preventative, corrective and routine toll collection equipment maintenance • AVC installation and calibration • Toll lane and AVC software installation and calibration; • 1st Line software support • Stock control and management of spares. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.6.2:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 2)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Preventative, corrective and routine toll collection equipment maintenance • AVC installation and calibration • Toll lane and AVC software installation and calibration; • 1st Line software support • Stock control and management of spares. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.6.3:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 3)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Preventative, corrective and routine toll collection equipment maintenance • AVC installation and calibration • Toll lane and AVC software installation and calibration; • 1st Line software support • Stock control and management of spares. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4.6.4:	PERSONNEL RESOURCE DETAIL (plaza TECHNICIAN 4)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. • Preventative, corrective and routine toll collection equipment maintenance • AVC installation and calibration • Toll lane and AVC software installation and calibration; • 1st Line software support • Stock control and management of spares. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |

SIGNED BY TENDERER:

FORM D4-7:	PERSONNEL RESOURCE DETAIL (H&S manager/officer)

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

1.	GENERAL

The tenderer must have in its permanent employment key personnel/key resources as listed in tender data Clause C.3.11 who meet the minimum requirements as stipulated.  Alternatively, the tenderer shall provide a signed undertaking from the organisation having the required personnel, stating that they will undertake the necessary work on behalf of the tenderer in terms of a subconsultant agreement.  Such undertaking must be attached to Form D4 of the Returnable Schedules.

A key person/resource may only be proposed in more than one tender submission if that person is a sub-consultant in each of the tenderers in which the key person/resource is proposed and is not in a permanent employment of any of the tenderers.  In the event that the same key person/resource is proposed in more than one tender and the key person/key resource is the permanent employment of one of the tenderers, then all tenders proposing the key person will be declared non-responsive.

Where a key person(s)/resource(s) is no longer available to undertake then necessary work after the tender award, the Contractor shall within a period of fourteen (14) working days replace the key person(s)/resource(s) as listed in forms D4 with the person(s)/resource(s) with equivalent competencies and subject to approval by the Employer.  Such approval shall not be unreasonably withheld.

| 2. KEY PERSONNEL DETAILS The tenderer shall complete this form in full and provide all the required information for the subject position’s proposed candidate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company, member of joint venture, subcontractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discipline: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Present position: |  |  |  |  |  |
| Proposed position in project: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Speciality: …………………………… |  |  |  |  |  |  | Qualification: |  |  |  |  |  |  |
| Years Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In field of speciality: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| With organisation: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. KEY PERSONNEL RESUMÉ AND CV A Curriculum Vitae (CV) of the key personnel indicated in this form shall be appended to this form and signed by the candidate. The CV (max 4 Pages) shall provide the following information: - Professional summary. - Relevant experience, indicating Position/Role, Period, and area of specialization. - Project experience: Project, role, project duration, project phase, project status and project value. - Formal education: Qualifications, Institution and year of completion. Copies of Qualifications/Certificates shall be attached to the CV. |  |  |  |  |  |  |  |  |  |  |  |  |  |

SIGNED BY TENDERER:

FORM D5.1:	TENDERER’S EXPERIENCE based on completed projects

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

- The tenderer shall provide details of previous experience required for this project and attach contract performance evaluation certificates in the form of CIDB Contractor Performance Reports or an official reference letter from previous employer(s).

- The Tenderer must have satisfactorily completed (at least completed as a prime contractor, joint venture member, management contractor or sub-contractor) a minimum number of 1 (one) similar or relevant project(s), to the value of at least R 5 million, or 3 (three) similar or relevant project(s), to the value of at least R 1.5 million per project matching the subject project’s scope of work, between 1st January 2008 and tender submission deadline.  The completed contract must have a minimum value that exceeds R 5 million or 1.5 million, have a Performance Rating not less than zero (0) Adequate, as rated in terms of the CIDB Performance Rating system or official reference letters from previous employer(s).

- The Tenderer shall have completed each of the listed projects as either a prime contractor or joint venture member or management contractor or sub-contractor. The listed project’s scope of work be shall substantially match that of the subject project’s scope of work.

- Each listed project shall have a Performance Rating not less than zero (0) Adequate, as rated in terms of the CIDB Performance Rating system r official reference letters from previous employer(s).

- For listed projects where the Tenderer participated as a joint venture member or sub-contractor, the Tenderer shall state value (V) limited to his/her share of certified work.

- If the Tenderer is a joint venture, the value of contracts completed by the individual joint venture members can be combined and shall be treated as one contract to determine whether the requirement of the minimum value of a single contract has been met. In the case of combined contracts, each contract performed by each member shall exceed fifty percent (50%) of the minimum value of a single contract as required for single entity. In determining whether the joint venture meets the requirement of total number of contracts, the number of contracts completed by all JV members each of value equal or more than the minimum value required shall be aggregated. For the afore-mentioned purpose, contracts which are combined to meet the minimum value shall be treated as one contract.

- If one or more of the listed projects does not meet minimum requirements as stipulated above, the tender shall be declared non-responsive in terms of clause C.3.13 (b) of the Tender Data.

(List only the most recent 3 (or 1) project(s) of the firm that the tenderer considers relevant to the specified scope of works

| Client | Description of project | Project start date | Project end date | Value of Work (i.e. the service provided) inclusive of VAT (Rand) | Contact Person and Firm | Contact Number | CIDB EQUIVALENT PERFORMANCE RATING (NOT REQUIRED WHERE AN OFFICIAL REFERENCE LETTERS FROM PREVIOUS EMPLOYER(S) IS ATTACHED) |
| --- | --- | --- | --- | --- | --- | --- | --- |

Comments:

I confirm that the information provided herein is true, that the projects reported, and the corresponding responsibilities are truly the experiences of the firm or consortium of firms tendering for this project.

SIGNED BY TENDERER:

FORM D5.2:	TENDERER’S EXPERIENCE based on projects IN PROGRESS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

- Submission of this form is optional. This form must be submitted if the tenderer does not comply with the requirements of Form D5.1, and elects to list project(s) that are in progress to comply with afore- mentioned requirements.

- The Tenderer shall list project(s) in progress as stipulated under Table 1 below which commenced after 1st January 2008.

- The Tenderer shall list 1 (one) similar or relevant project(s), to the value of at least R 5 million, or 3 (three) similar or relevant project(s), to the value of at least R 1.5 million per project which commenced after 1st January 2008.  Each listed project shall have a certified value of work that exceeds 40% of the awarded value.

- The Tenderer shall be employed on each listed project as either a prime contractor or joint venture member or management contractor or sub- contractor. The listed project’s scope of work shall substantially match that of the subject project’s scope of work..

- Each listed project shall have a Performance Rating not less than zero (0) Adequate, as rated in terms of the CIDB Performance Rating system or official reference letters from previous employer(s). The Performance Rating and certified value of work at closing date must be confirmed by the Project Employer or Project Engineer in writing.

- For listed projects where the Tenderer participated as a joint venture member or sub-contractor, the Tenderer shall state value (V) limited to his/her share of certified work.

- If the Tenderer is a joint venture, the value of contracts completed by the individual joint venture members can be combined and shall be treated as one contract to determine whether the requirement of the minimum value of a single contract has been met. In the case of combined contracts, each contract performed by each member shall exceed fifty percent (50%) of the minimum value of a single contract as required for single entity. In determining whether the joint venture meets the requirement of total number of contracts, the number of contracts completed by all JV members each of value equal or more than the minimum value required shall be aggregated. For the afore-mentioned purpose, contracts which are combined to meet the minimum value shall be treated as one contract.

- If one or more of the listed projects does not meet minimum requirements as stipulated above, the tender shall be declared non-responsive in terms of clause C.3.13 (b) of the Tender Data..

(List only the most recent 3 projects of the firm that the tenderer considers relevant to the specified scope of works

| Client | Description of project | Project start date | Project end date | Award Value of Work (i.e. the service provided) inclusive of VAT (Rand) | Value of works certified by the Engineer | Contact Person and Firm | Contact Number | CIDB EQUIVALENT PERFORMANCE RATING (NOT REQUIRED WHERE AN OFFICIAL REFERENCE LETTERS FROM PREVIOUS EMPLOYER(S) IS ATTACHED) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Comments:

I confirm that the information provided herein is true, that the projects reported, and the corresponding responsibilities are truly the experiences of the firm or consortium of firms tendering for this project.

SIGNED BY TENDERER:

FORM D7.1: TENDERER’S INDICATIVE PROGRAM

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer shall attach an indicative programme, reflecting the proposed sequence, resources anticipated and tempo of execution of the various activities comprising the work for this contract. The programme shall be in accordance with the information provided in Form D1: Schedule of Contractor’s Equipment and with all other aspects of the tender.  The programme shall indicate the resources anticipated to be used.

- The programme shall be in accordance with the information provided in Form D1: Schedule of Contractor’s Equipment, Form D14: and with all other aspects of the tender.

- If a tenderer wishes to submit an alternative tender then this form, appropriately completed, shall also be attached to the Pricing Schedule for the alternative proposal.

Refer to EXCEL file

SIGNED BY TENDERER:

FORM D7.2: 	PROPOSED ESTABLISHMENT PROGRAMME

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

The tenderer shall indicate the proposed establishment programme. The Establishment Period shall be complete fourteen (14) days before the Commencement Date of Operation Service Period, except for activities indicated below.

| ACTIVITY | WEEKS FOR THE ESTABLISHMENT PERIOD |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | -6 | -5 | -4 | -3 | -2 | -1 | 0 |
| 1 Receipt of NSC’s unconditional letter of acceptance |  |  |  |  |  |  | Start of Operations Services Period |
| 2 Finalise/formalise JVs/consortia and contractual documentation |  |  |  |  |  |  |  |
| 3 Supply copies of letter of intent to subcontractors to the Employer. |  |  |  |  |  |  |  |
| 4 Appointment of personnel |  |  |  |  |  |  |  |
| 5 Training of personnel |  |  |  |  |  |  |  |
| 6 Evaluation of personnel |  |  |  |  |  |  |  |
| 7 Personnel transport arrangements |  |  |  |  |  |  |  |
| 8 Appointment of subcontractors (if applicable) |  |  |  |  |  |  |  |
| 9 Submission of operations and maintenance procedure manuals (toll system related) |  |  |  |  |  |  |  |
| 10 Supply of office equipment, consumables (toll system related) |  |  |  |  |  |  |  |
| 11 Supply of electronic/ electrical test measurement equipment (toll system related) |  |  |  |  |  |  |  |
| 12 Supply of other LE/E&M/MIS equipment |  |  |  |  |  |  |  |
| 13 Provision of insurance certificates and performance security |  |  |  |  |  |  |  |
| 14 Start of Operation Service Period |  |  |  |  |  |  |  |
| 15 Other |  |  |  |  |  |  |  |

Note: Tick the appropriate boxes indicating during which week the activity will take place.

SIGNED BY TENDERER:

FORM D8:	SCHEDULE OF ESTIMATED MONTHLY EXPENDITURE

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

If a tenderer wishes to submit an alternative tender then this form, appropriately completed, shall also be attached to the Pricing Schedule for the alternative proposal.

The tenderer shall state his estimated value of the work to be completed every month, based on his preliminary programme and his tendered unit rates, in the table below.

| CERTIFICATE / MONTH | VALUE | CERTIFICATE / MONTH | VALUE |
| --- | --- | --- | --- |
| Establishment M1 Establishment M2 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 32 33 34 35 36 TOTAL c/f | R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R | TOTAL b/f 37 38 39 40 41 42 43 44 45 46 47 48 49 50 51 52 53 54 55 56 57 58 59 60 61 62 63 64 65 66 67 68 69 70 71 72 (FINAL)* | R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R R |
|  |  | TOTAL: R |  |

* Final payment at end of Defects Notification Period is for balance of retention and any other payments due.

SIGNED BY TENDERER:

FORM D9:	NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

| 1. Nomination of company, member, subcontractor, etc. for each discipline |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The tenderer shall indicate which company, subcontractor, member of a joint venture, etc. will execute EACH of the disciplines listed below. Where the tenderer has not yet identified or selected a company, subcontractor or member of a joint venture to execute a specific discipline, this shall be stated by entering "not assigned" in the appropriate row of the table. All companies, members of a joint venture and subcontractors that the tenderer intends to include in its organisation must be listed in the table. When one of the listed disciplines is not assigned to a specific party, this party must be listed under "other parties", and the intended role/function of the party must be given. |  |  |  |  |  |  |  |  |
| DISCIPLINE |  | NAME OF ORGANISATION | TYPE OF ORGANISATION [e.g. (Pty) Ltd] | CATEGORY OF ORGANISATION (e.g. BE(SMME)] | STATUS IN PROJECT: LEADING MEMBER OF JV, COMPANY, SUBCONTRACTOR, ETC | NATIONALITY | YEARS EXPERIENCE IN DISCIPLINE |  |
|  |  |  |  |  |  |  | OWN COUNTRY | INTERNATIONAL |
| 1.1 Project management |  |  |  |  |  |  |  |  |
| 1.2 Toll plaza operations |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |
| 1.3 Toll Collection Lane Equipment |  |  |  |  |  |  |  |  |
| AVC | Supply |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |
| ETC | Supply |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |
| TCC | Supply |  |  |  |  |  |  |  |
|  | Software support |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |
| VGS | Supply |  |  |  |  |  |  |  |
|  | Software and support |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |
| QLS | Supply |  |  |  |  |  |  |  |
|  | Software and support |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |

FORM D9:	NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE (CONTINUED)

| 1. Nomination of company, member, subcontractor, etc. for each discipline |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DISCIPLINE |  |  | NAME OF ORGANISATION | TYPE OF ORGANISATION [e.g. (Pty) Ltd] | CATEGORY OF ORGANISATION [e.g. BE(SMME)] | STATUS IN PROJECT: LEADING MEMBER OF JV, COMPANY, SUBCONTRACTOR, ETC | NATIONALITY | YEARS EXPERIENCE IN DISCIPLINE |  |
| VIDEO/ CCTV | Supply |  |  |  |  |  |  |  |  |
|  | Maintenance |  |  |  |  |  |  |  |  |
| Software support |  |  |  |  |  |  |  |  |  |
| 1.4 Back office system (BOS)/ |  |  |  |  |  |  |  |  |  |
| Supply |  |  |  |  |  |  |  |  |  |
| Support |  |  |  |  |  |  |  |  |  |
| 1.5 Customer call centre |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.6 Incident management system |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.7 Electrical & mechanical equipment |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.8 Financial |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.9 Legal |  |  |  |  |  |  |  |  |  |
| 1.10 Environment |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.11 Points of sale |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.12 Tag management |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.13 Customer service centres (CSC) |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |
| 1.14 Other parties |  |  |  |  |  |  |  |  |  |

SIGNED BY TENDERER:

FORM D10:	TECHNICAL AND SYSTEM INFORMATION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

The tenderer shall complete and submit a signed copy of this Technical and System Information, providing the technical information, speciation’s and/or functionality, using the headings and sub-headings listed in table below. The Employer shall only consider a tender if the information provided is clearly stated in the tender documentation for evaluation purposes. The information given shall also be used inter alia, to determine Equipment performance during the maintenance of the existing systems and the design, testing, commissioning and maintenance stages of the upgraded Toll System and peripherals, during the Contract Period. Any other relevant details that the tenderer intends to submit, must be compiled, and submitted as an Appendix to the Technical Information in order to provide a complete and comprehensive description of the proposed system. The tenderer shall clearly indicate the extent to which the existing assets will be utilized.  It should be noted whether existing equipment will be upgraded or replaced.

Tenderer as a minimum to provide:

1.	STANDARDS

The tenderer shall itemise each and every standard used in the manufacture of the equipment and shall include such information either in the schedule below or in the separate document entitled “TECHNICAL INFORMATION”.

2.	TOLL EQUIPMENT PERFORMANCE

The tenderer shall provide the information required below and shall substantiate all information given.

2.1	Data Communications Network

Provide full details of the proposed various communication network(s), including separation, security, surge protection, power supply (POE) and UPS power supply to the network(s).

- Supplier details

- Supplier

- Other demonstration installations

- Technical support and standby arrangements, including Network monitoring and reporting/notifications.

(ii)	Technical proposal, include physical layout drawings/diagrams.

(iii)	Highlight the following aspects: Network management, redundancy, separation, cabling, lightning & Surge protection.

(iv)	TCH main and fall-back networks.

(v)	Secure Toll System Data repository service, for interfacing with the SANRAL MIS.

(vi)	SANRAL ITIS Interface.

(vii)	SANRAL Commercial Banking Interface

(viii)	SANRAL Fleetbank Interfaces.

(ix)	Interface with the Helpdesk, shared with the Main Contractor.

(x)	Any other Data Interface service and or internet breakouts required or to be provided to the Main Contractor.

(xi) 	Methodology to provide secure SANRAL MIS Interface data repository in order to interface with various Principal Employer data services in the near future.

2.2	VGS, VGS audit WS, QLS and QL1

Provide full details of the proposed VGS, QLS and QL1, including, cameras, security, surge protection, power supply (POE) and UPS power supply.

- Supplier details

- Supplier/s

- Other demonstration installations

- Technical support and standby arrangements.

- Technical proposal

- Include physical layout drawings

- Detail of the transaction framing and video linking process based on TCC, AVC, ANPR and video motion detection

- QLS - includes cameras, DVRs/NVRs, UPS power backup and surge protection

- VGS – includes cameras, DVRs/NVRs, UPS power backup and surge protection

- QLS - includes cameras, DVRs/NVRs, UPS power backup and surge protection

- QL1 - includes cameras, DVRs/NVRs, UPS power backup and surge protection

- VGS workstation and VGS audit clerk functionality

- Time source and time synchronisation with toll system

- Method to meet the strict timeline to commission the VGS, VGS workstation, QLS and Queue Line 1 & 2 Transgression detection and notification obligations.

- Detail on the access, version and configuration control system

2.3	AVC including DCS (Repeat this section for each different type of AVC or Toll Lane Type, being deployed. E.g. Single lane Mixed Manual ETC lane, Single lane Dedicated ETC lane, Tandem lane (where applicable), Reversible lane combinations of all above, Extra-Wide lanes, Ramp/Mainline swapable Lenes, etc.

Provide full details of the AVC, including the following:

- Supplier details

- Supplier

- Other installations and what version of the system has been installed at such site. Include number of units installed

- Indicate to what degree the demonstration systems, noted below, do not meet the requirements described in this Agreement. Define / list any shortcomings and/or alternative methodologies to fulfil the requirements. Indicate when such functionality will be finally compliant and ready for compliance certification by the Employer

- An installation where the equipment can be inspected in an operational environment

- Proven maximum traffic volumes processed through previously installed AVCs

- Processor description

- CPU / micro-processor

- Software used (operating system, database, development language, network operating system, version, etc.)

- Internal power backup

- AVC UPS - method, reserve backup power period provided and what is the battery recovery period after battery low warning.

- AVC UPS Power monitoring – Method and equipment to provide battery power low alarms and battery restore monitoring method and alarm/indicator. Include details of UPS power supplies, chargers, batteries threshold voltages etc

- Communication between TCC and AVC – indicate methodology of correcting flawed communications described in the standard specification

- Other communication

- System security

- System licences

- AVC system power consumption details – dormant and active

- Sensor description and logic

- Sensor types and layout

- Axle counter details

- Heavy and light vehicle identification

- Motorcycle detection

- Loop sensor details or other vehicle presence detection method/s

- Other sensors used

- Sensor redundancy

- Specific vehicle separation in Tandem Toll Lanes – provide details of vehicle separation device/s proposed.

- Specific vehicle separation in Dedicated ETC Toll Lanes – provide details of vehicle separation devices proposed.

- Installation requirements.

- Detail on the access, version and configuration control system

2.4	AVC and DCS Software (Repeat this section for each different type of AVC being deployed. E.g. Single lane single direction, Single lane Mixed Manual ETC lane, Single Dedicated ETC lane, Tandem lane, Reversible lane combinations of all above, etc.

Provide full details of the AVC Software, including the following:

- Supplier details

- Supplier

- Other installations

- An installation where the software can be inspected in an operational environment

- Software used

- Operating system

- Database

- Development language

- Network operating system

- Version

- Software licences

- Other applicable information.

- Software logic

- Self diagnostics

- Self correcting

- Automated data management

- Automated and secure data updating to Back Office / MIS

- Automated data diagnostics on AVC data received – Monitoring and generation of status event messages.

- Data integrity management between AVC and DCS and DCS and it is

- Detail on the access, version and configuration control system

2.5	AVC accuracy (Repeat this section for each different type of AVC being deployed. E.g. Single lane single direction, Single lane Mixed Manual ETC lane, Single Dedicated ETC lane, Tandem lane, Reversible lane combinations of all above, etc..,

Provide full details of the survey procedure used to measure AVC accuracy.

- Proven AVC Count accuracy achieved by previously installed AVCs in terms of the CTROM Initial  and Post AVC count accuracy verification process (V2B4 10.2.1) (or similar process) for the plaza

- Proven AVC Classification accuracy achieved, per class, by previously installed AVCs in terms of the CTROM Initial and Post AVC classification accuracy verification process (V2B4 10.2.1)(or similar process) for the plaza

2.6	Toll Collection Lane Equipment (Repeat this section for each different type of Lane Equipment being deployed. E.g. Single lane single direction, Single lane Mixed Manual ETC lane, Single Dedicated ETC lane, Tandem lane, Reversible lane combinations of all above, etc..,

Provide full details of the Toll Collection Lane Equipment, including:

- Supplier details

- Supplier

- Previous installations

- An installation where the accuracy can be verified in an operational environment

- System description

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- User account management – different user identifiers and account functionality possibilities.

- Handling of registered users paying with cash or Master/Visa cards directly in toll lanes

- Hardware. Include details of Exit booms, User fare displays, OHLSs, etc

- Fraud restrictions

- TCC Surveillance cameras and independent recording devices

- External Swipe card readers – user swipe

- Detail on the access, version and configuration control system

- other

2.7	ETC (Repeat this section for each different type of ETC being deployed. E.g. Single lane single direction, Single lane Mixed Manual ETC lane, Single Dedicated ETC lane, Tandem lane, Reversible lane combinations of all above, etc..,

Provide details on the ETC Tags, readers and other Equipment to be utilized:

- Supplier details

- Supplier

- Previous installations

- An installation where the equipment can be inspected in an operational environment

- System description

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- Hardware

- Redundancy

- User support System in the event of tag read or processing failures

- User communication

2.8	BOS/Back Office System

Provide full details of the BOS, including:

- Supplier details

- Supplier

- Previous installations

- An installation where the system can be inspected in an operational environment

- System description

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- User account management including route-based accounts

- Data communications network – including UPS power backup and surge protection

- Hardware for all above and other components.

- Time source and time synchronisation between all system/components of entire tolling system

- Detail on the access, version and configuration control system

2.9	Customer Service Centres/Point of Sales

- Supplier Details

- Supplier

- Previous installations

- An installation where the system can be inspected in an operational environment

- System Description

- System layout

- Software used (operating system, database, development language, network operating system, etc)

- Hardware

2.10 	Over height detection system

Provide full details of the OHDS, including:

- Supplier

- Previous installations

- An installation where the system can be inspected in an operational environment

- System description

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- Data communications network – including UPS power backup and surge protection

- Hardware for all above and other components.

- Time source and time synchronisation between all system/components of entire tolling system

2.11 	ANPR System

Provide full details of the ANPR system, including:

- Supplier

- Previous installations

- An installation where the system can be inspected in an operational environment

- System description for lane level (on board ANPR cameras) and BOS (ANPR engin)

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- Data communications network – including UPS power backup and surge protection

- Hardware for all above and other components.

- Time source and time synchronisation between all system/components of entire tolling system

- Proven ANPR achieved at an operational site, including; lane level realtime ANPR accuracy, BOS level ANPR accuracy, ANPR confidence level (see V3B1 PS 3.4.8.10 ANPR accuracy and monitoring)

2.12 	TA/TCH INTERFACE

Provide full details of the TA/TCH interface, including:

- Supplier details

- Supplier

- Previous installations

- An installation where the system can be inspected in an operational environment

- System description

- System layout

- Software used (operating system, database, development language, network operating system etc.)

- User account management including route based accounts

- Hardware for all above and other components.

- Time source and time synchronisation between all system/components of entire tolling system

- Detail on the access, version and configuration control system

SIGNED BY TENDERER:

FORM D11:	TOLL PLAZA UPGRADING SCHEDULES

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Not Applicable

FORM D12:	ADDITIONAL INFORMATION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ADDITIONAL INFORMATION

Any further information to be considered with the tender shall be added below. In addition, if other documents are attached, these shall be listed below. If no additional information is submitted, this form shall be marked "N/A" (not applicable).

SIGNED BY TENDERER:

FORM D13:	DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- This form shall be signed by the Contractor (appointed through this tender process and also known as the “Nominated Subcontractor” or NSC) and the Operations and Maintenance Contractor (appointed through another tender process and also referred to as the “Main Contractor” or MC) and is included in both tenders. The form jointly covers the risk related to the collection of Toll or the supply, installation or maintenance of the Toll System.

- If the risk for any of these activities will be shared or carried by any party other than a subcontractor, the agreements with these party(s) shall be submitted in terms of Clause 4.4 of FIDIC General Conditions of Contract (2008) Volume 1 Book 1 for subcontracts.

Risk transfer model:

- The Toll system is a factor in controlling many of the operational risks inherent in the CTROM contract. As such, any underperformance of the Toll System heightens the risk. This section defines the mechanism of transferring the risks equitably and accurately to the entity most capable of detecting issues, managing, and implementing timeous corrective steps.

- The Payment Methodology (V2B7a) transfers income losses (V2B7a clause 4.5) to the Main Contractor, for which the Main Contractor tenders as part of their monthly OPEX rate.  Income losses, under optimal Toll System performance, is therefore covered by Main Contractor.  Mechanisms are in place to address Main Contractor losses due to exceptional events.

- The Payment Methodology also includes the inherent data source variances, which include Toll System detection and classification variances.

- Reducing Toll System related risks and losses is reliant on a properly designed and deployed Toll System, hardware and software support, operational mitigation and effective management of personnel and resources.  The responsibilities therefore are:

  - The monitoring of all the relevant aspects of the operational, technical and KPI conformance at regular intervals, by the MC and/or NSC. This includes inspections and feedback from site staff, monitoring of system incidents, monitoring of statistical trends and electronic payment submission processes.

  - Early detection of possible non-compliances and

  - Implementation of corrective steps, including steps/procedures to limit the impact of the identified non- performance. This includes steps/procedures to limit the impact of known system defects and system limitations.

Toll System support procurement models:

For the Toll System Support and related A5300 range Cost Matrix items, the following roles and responsibilities are defined for the Main Contractor (MC) and the Nominated Sub-Contractor (NSC):

- The MC will perform Toll Operations only and the NSC will perform Toll System Software and Hardware Maintenance.

- The NSC will therefore have full-time on-site technicians and do remote software support and maintenance.

- The MC will be responsible for the supply and maintenance of the Help Desk and Toll Equipment record system and regular Workshop spares stock control.

- The NSC will also be required to do maintenance and update the Help Desk and Toll Equipment record system entries, based on their site activities and regular Workshop spares stock control and replenishment.

Toll System supply and upgrade

The roles of the MC and NSC during the Toll System supply and upgrade are as follow:

- The MC will perform Toll Operations only

- The NSC will perform Toll System Software and Hardware Maintenance, that will include:

  - The design, procurement, testing, commissioning and handover of the Toll System software and hardware supply in terms of the various cost matrix items (B 2000 and B3000 range items).

  - Toll system functional, provisional, and full compliance verification.

  - Supply a full set of critical spares,

  - Maintenance:  Hardware and software maintenance of the system. All system KPIs will apply during the upgrade process

RISK CATEGORY, DESCRIPTION, CAUSES, MITIGATION AND ALLOCATION

|  | CATEGORY | DESCRIPTION | CAUSES |  | MITIGATION |  | ALLOCATION* |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Technical specifications risk: Design | Design that results in individual technical characteristics of the Toll System that fail to meet standards and specifications. | Low quality of works, non-compliance with standard Specifications and the rectification of known or latent defects. Failure to implement accurate KPI reporting and Health Monitoring |  | NSC, MC and ER to perform quality control. Apply Penalties |  | Main CTROM Contractor (MC) or Subcontractor (NSC) MC; NSC. 20%; 80%. |
| 2 | Completion risks: Toll system Upgrade | The possibility that the completion of Toll System works may be delayed | Difficulties/Delay in developing undelivered requirements. Incomplete requirements Supply, deployment and commissioning failures. |  | Apply Penalties. |  | Main CTROM Contractor (MC) or Subcontractor (NSC) MC; NSC. 20%; 80%. |
| 3 | Completion risks: SANRAL MIS and SANRAL Toll System | The possibility that the completion of SAP MIS RSS Mediation layer works may be delayed | Difficulties in developing mediation layer to requirements. Incomplete requirements Failure in understanding technical requirements |  | Follow Contractual process. |  | Covered under other items in this table. |
| 4 | Cost over-run risk | The possibility that during the design build phase of the SANRAL MIS Toll System Interface, the actual costs will exceed projected Project costs (Provisional Sum). | Mistakes in design build cost estimates. Underestimating technical requirements Increased costs through the fault of Subcontractor. Contingencies. |  | Follow Contractual process. |  | Follow Contractual process. |
| 5 | Design risk | The possibility of mistakes in SANRAL MIS Toll System Interface mediation layer project solutions. | Technical solutions mistakes. |  | Follow Contractual process. |  | Follow Contractual process. |
| 6 | Exceptional Event and risks | The possibility of the occurrence of certain unexpected events that are beyond the control of the Parties (natural disasters, civil riots) | Various natural and man-made causes. |  | Follow Contractual process. |  | Follow Contractual process. |
| 7 | Insolvency risk | The possibility of the insolvency of the Main CTROM Contractor or/ and Subcontractor. | Increased debt liabilities under the Project. Low revenue - Main Contractor/ Subcontractor |  | Follow Contractual process. |  | Follow Contractual process. |
| 8 | Insurance risk | The possibility that insurance services become inaccessible or too costly. | Increase theft and Vandalism |  | Follow Contractual process. |  | Follow Contractual process. |
| 10 | Currency Volatility risk | The possibility that volatility in currency will increase the cost of specialized imported TS equipment | Due to inflation levels, interest rates, geopolitical stability, import and export levels, and monetary policy |  | List items subject to exchange rate fluctuations on Form B1, Part T2. |  | Follow Contractual process. |
| 12 | Regulatory risk | The possibility that Consents required from the government will not be obtained or, if obtained, can only be implemented at a greater cost than originally projected. | Relating to planning |  | Follow Contractual process. |  | Follow Contractual process. |
| 13 | The risk that the Project Assets at termination or expiry will not be in the prescribed condition. | Risk of value loss on the transfer of the project or at termination of the Concession Agreement. | Insufficient maintenance of the toll system, civils and E& M. Delayed overhaul and preventive maintenance. Carelessness of contractors. |  | Follow Contractual process. |  | Follow Contractual process. |
| 14 | Resource or input risk | The possibility of a failure or shortage in the supply of the inputs or resources required for the operation of the project. | Main Contractor’s & or Subcontractor cash-flow problems |  | Financial Sustainability checks as part of evaluation stage. |  | Follow Contractual process. |
| 15 | Technology obsolescence risk | The possibility that the technology inputs for the outsourced institutional function may fail to deliver the required output specifications, or technological improvements may render these technology inputs out-of-date. | The use of obsolete materials and equipment. |  | Obligation on Main CTROM Contractor to refresh technology as required from time to time to meet the output specifications. Penalty Deductions for failure to meet output specifications. |  | Main Contractor & NSC MC; NSC. 20%; 80%. |
| 16 | Utilities risk | Shortage of utilities (e.g. water, electricity, etc.), necessary for construction and/or operation of the project. | Failure of the utility companies to provide utility services. |  | Emergency back-up facilities. |  | Main Contractor |
| 17 | Revenue risk | Income lost to fraud or operational negligence in use of Toll System | Due to vehicle discrepancies not assigned correctly for cash transaction. Toll staff collusion Processing in lanes with known defects |  | Close faulty lanes in favor of fully functional lanes. Payment Methodology - decision tree Segregation of duties Internal controls VGS audits and Incident control to ensure quick mitigation of risks |  | Main Contractor, follow Contractual process. |
| 18 | Revenue risk Design defect risk: AVC detection and classification | TEL traffic may be used to determine the income payable to SANRAL | Due to AVC or MIS not been the highest income traffic arising from AVC detection and or classification inabilities. |  | Validation and Verification of vehicles by the supervising toll plaza personnel Audit reports Count accuracy audits Create lost transactions Assig lifted axle status. Apply KPI penalties. |  | Main Contractor and NSC, follow contractual process |
| 19 | Revenue risk Design defect risk: Lost transactions | System defects arising in Loss of income | Due to flaws in the systems mentioned or failures of the systems mentioned Written-off cross-read and overdue ETC transactions. |  | System compliance NSC to correct defects Recover identified errors Use VGS audit to assign responsibility. |  | Main Contractor and NSC, follow Contractual process. |
| 20 | Revenue risk Design defect risk: | Contractor might lose income due to differences between the MIS and TEL traffic or income as per the payment decision tree as applied by the Main Contractor’s ER. | Toll system defects TEL defects |  | Toll System Maintenance Data verification and validation Video footage of traffic entering and exiting lanes Count accuracy audits Create lost transactions Assign lifted axle status. Apply KPI penalties. |  | Main Contractor and NSC, follow contractual process |
| 21 | Revenue risk | Charge - backs | Validations list not implemented on time as per the merchant agreement |  | Monitor processes and ensure validation list are implemented as per the merchant agreement |  | Main Contractor and NSC, follow Contractual process |
| 22 | Design defect risk. | Latent defects taken over from existing Toll System | System not compliant to Employer’s requirements |  | Manual workarounds need to be implemented by MC. Expedite establishment upgrades and system replacement. |  | Main Contractor and NSC, follow Contractual process |
| 23 | Financial risk Operational risk | Data loss | Back-up and data archiving failure HDD failure Loss of data via network |  | Contractual Storage Requirement must be adhered to and verified |  | Main Contractor and NSC, follow Contractual process |
| 24 | Toll System risk | System limitations | Poor System Design |  | Manual workarounds need to be implemented |  | Main Contractor and NSC, follow Contractual process |
| 25 | Risk due to non-compliant AVC accuracy | Non-compliant AVC accuracy – Software related |  |  | Decision tree AVC related KPI’s |  | OPEX: Main Contractor Related KPI: Main Contractor & NSC MC; NSC. 20%; 80%. The following KPI’s will be assigned as indicated by the table above. Ref; Name. CT3a; AVC Availability (Critical Errors). CT3b; AVC Availability (Serious Errors). CT3c; Automatic Vehicle Classification for Class 1 to 4. CT3d; AVC Count. CT8a; Compliance with Employer’s reporting requirements – Critical Reports. AVC Accuracies. System Availability. |
| 26 | Risk of increase cost due to system upgrades | Additional cost due to system upgrades brought on by system obsolescence, lack of support for operating systems, hardware and application software and performance related issues. | Obsolete Equipment, Software etc. |  | Contractual requirements – Upgrade / Replacement of equipment due to obsolescence, lack of support or performance problem |  | Main Contractor & Subcontractor MC; NSC. 20%; 80%. |
| 27 | Risk of Inadequate Insurance | Risk of damage to systems and the consequential losses thereof due to lightning, theft, vandalism and accident damage not covered by insurance. | Inadequate insurance coverage |  | Penalties and KPIs pertaining to non-compliance to repair of damaged assets, equipment functionality, maintenance performance etc. |  | Main Contractor |
| 28 | Asset replacement risk | Cost of equipment replacement, spares and equipment related consumables related to toll systems. |  |  | Asset replacement responsibility specified in contract |  | Main Contractor & Subcontractor MC; NSC. 20%; 80%. |
| 29 | Risk of damages arising | Risk due to any other consequential, incidental or indirect damages |  |  | Follow the Contractual Process |  | Follow the Contractual Process |
| 30 | System defect risk | System Compliance Penalties | Non-Compliance |  | Apply Penalties |  | MC; NSC. 20%; 80%. |
| 31 | Interest risk due to late deposits: Cash | Interest on late deposits to the bank arising from cash | Cash at the plaza not deposited within the prescribed contractual time. |  | Follow the Contractual Process. |  | Main Contractor |
| 32 | Interest risk due to late deposits: Credit cards | Interest on late deposits to the bank arising from credit card transactions | Bank not receiving the credit card transaction information within the prescribe merchant agreement. |  | Follow the Contractual Process |  | Main Contractor (MC) or Subcontractor (NSC) MC; NSC. 50%; 50%. |
| 33 | Loss of Income – Electronic settlement of toll transactions | Charge backs implemented by the Banks due to “Negative files” not downloaded to lanes within the contractual timelines | Hotlisted cards not downloaded into the toll lanes within the prescribed contractual time. |  | Follow the Contractual Process |  | Main Contractor (MC) or Subcontractor (NSC). The Party responsible for the loss of income – 90% the other Party 10%. |
| 34 | Operational and Financial risk- | Late submission of monthly reports | All transaction not validated, Missing data, Contractor’s personnel have not closed all shifts. | Contractual recourse (penalties) + Payment cert not being processed Apply applicable KPIs |  | KPI: Main Contractor (MC) or Subcontractor (NSC) MC; NSC. 50%; 50%. The following KPI’s will be assigned as indicated by the table above. Ref; Name. CT8a; Compliance with Employer’s reporting requirements – Critical Reports. Hourly, Daily & Monthly Traffic Report. Discount / Exempt Report. Account Status. Payment Trends. Day/Month Closures. AVC Accuracies. System Availability. Equipment failures. Response & Repair times. Problem Data. Support Reports. Stock & Spares. Performance Measurement Report. KPI 11. KPI 19. CT8b; Compliance with Employer’s reporting requirements – Non-Critical Reports. Transaction Tariff report. Discount Structure Report. Transaction details report. Class discrepancy acknowledgement. Access Control. Version Control. MTBF. Incident Report. Dashboard Report. Upgrade Reports. |
| 35 | Reputational and safety risk | Queue Length penalties | Not enough lanes opened to process vehicles as per average processing time. | Contractual Requirements governing queues |  | Main Contractor |  |
| 36 | TS enhancement risks- | Regression after system fixes and enhancements implemented | Patched deployed on production site without proper internal quality and control checks | Contractual requirements addressing software changes |  | Main Contractor and NSC, follow Contractual process |  |
| 37 | System defect risk | Software or AVC, TCC or other 3rd party license expiry, failure or termination | Subcontractor has a AVC license expiry date which is not in accordance to the contractual license agreement | Subcontractor provided a 20yr to perpetual license/s |  | Main Contractor and NSC, follow Contractual process |  |
| 38 | Maintenance risk-FR | Unavailability of spares | Poor inventory control and spares management | Contractual requirement governing repair times and availability of spares |  | Main Contractor and NSC, follow Contractual process |  |
| 39 | Support and Maintenance risk- | Toll system supplier poor performance with regards to providing satisfactory service and support in terms of system supply and maintenance | Low quality of maintenance of the works, lack of spares and other site factors that cause non-compliance with standard Specifications. | NSC and MC monitor, detect issues and inform Operational staff ASAP. The MC to manage the use of affected lanes, when possible, to limit the risk. |  | OPEX: Main Contractor (MC) KPI: Main Contractor (MC) or Subcontractor (NSC) MC; NSC. 20%; 80%. The following KPI’s will be assigned as indicated by the table above. Ref; Name. CT1a; Repair Time Compliance – Severity Level 1 - Employer Facilities. CT1b; Repair Time Compliance – Severity Level 2 - Employer Facilities. CT1c; Repair Time Compliance – AVC and TCC. CT2a; SCADA Availability. CT2b; VGS Availability (Critical Errors). CT2c; QLS Availability (Critical Errors). CT2d; QL1 Availability (Critical Errors). CT2e; QL2 Availability (Critical Errors). CT2f; BOS Availability (Critical Errors). CT2g; PGW Availability (Critical Errors). CT4a; Daily AVC Data Transmission – Un-validated. CT4b; Daily AVC Data Transmission – Validated. CT4c; Daily Back-Office Data Transmission. CT4d; Monthly Back-Office Data Transmission. CT4e; Monthly Back-Office Income Data Transmission. CT10; Charging and charge reconciliation processes - accuracy. CT12; ETC lane availability. CT13; ETC Transaction Records submitted to TCH – timeliness.. CT15; QLS –availability. CT16; Maintenance. |

The MC and NSC should note that the table above, which considers the various possible risks, will have an impact on the application of the Performance Measurement Model (PMM), contained in Volume 2 Book 6a. Each KPI, or Penalty Item could be influenced in terms of risk distrubution, depending on the risk at play.  The tables below show how each performance measurement could be influenced by various risk types above, which impacts on the risk distribution between the MC and NSC.

If a case occurs where the situation is not accurately described in the risk table, and/or the risk allocation is not fair, the ER for the Main Contractor shall consult with the MC, NSC and the Principal Employer and issue a Determination in line with the Conditions of Contract (FIDIC) Sub-clause 3.5 [Determinations].

| Volume 2 Book 6a - Section 4 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| KPI # |  | Description | Penalty Application |  |  |  |  |
|  |  |  | MC | NSC |  | Comment |  |
| CT1a |  | Repair Time Compliance – Severity Level 1 - Employer Facilities | 100% | 0% |  | Main Contractor |  |
| CT1b |  | Repair Time Compliance – Severity Level 2 - Employer Facilities | 100% | 0% |  | Main Contractor |  |
| CT1c |  | Repair Time Compliance (AVC & TCC) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 17, 19, 22, 23, 24, 25, 26, 36, 37, 38 |  |
| CT1d |  | Repair Time Compliance – Severity Level 1 Permanent Design Built Assets | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT1e |  | Repair Time Compliance – Severity Level 2 Permanent Design Built Assets | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2a |  | SCADA Availability | 100% | 0% |  | Main Contractor |  |
| CT2b |  | VGS Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2c |  | QLS Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2d |  | QL1 Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2e |  | QL2 Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2f |  | BOS Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT2g |  | PGW Availability (Critical Errors) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT3a |  | AVC Availability - Critical Errors | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 25, 26, 36, 37, 38 |  |
| CT3b |  | AVC Availability - Serious Errors | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 25, 26, 36, 37, 38 |  |
| CT3c |  | AVC Accuracy | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 25, 26, 36, 37, 38 |  |
| CT3d |  | AVC TOTAL Count Accuracy | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 25, 26, 36, 37, 38 |  |
| CT4a |  | DAILY UN-Validated AVC Transmission Data (ITIS) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 26, 36, 37, 38 |  |
| CT4b |  | DAILY Validated AVC Transmission Data (ITIS) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 26, 36, 37, 38 |  |
| CT4c |  | DAILY BOS Transmission Data (ITIS) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 26, 36, 37, 38 |  |
| CT4d |  | MONTHLY BOS Transmission Data (ITIS) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 26, 36, 37, 38 |  |
| CT4e |  | MONTHLY BOS INCOME Transmission Data (ITIS) | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 13, 15, 26, 36, 37, 38 |  |
| CT6a |  | Route Call Centre Service Availability including IVR Services | 20% | 80% |  |  |  |
| CT6c |  | Route Call Centre Queuing Time including IVR Services pending transfers to an Operator | 20% | 80% |  |  |  |
| CT8a |  | Compliance with Employer’s reporting requirements – Critical Reports | 20% | 80% |  |  |  |
| CT8b |  | Compliance with Employer’s reporting requirements – Non-Critical Reports | 20% | 80% |  |  |  |
| CT9 |  | POP Customer Service Facilities - availability | 20% | 80% |  |  |  |
| CT10 |  | Charging and charge reconciliation processes - accuracy | 20% | 80% |  |  |  |
| CT11 |  | Customer Satisfaction | 20% | 80% |  |  |  |
| CT12 |  | ETC Lane Availability | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT13 |  | ETC Transaction Records submitted to TCH – timeliness. Availability | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 17, 19, 22, 23, 24, 26, 36, 37, 38 |  |
| CT14 |  | TCH Account Registration Processing Accuracy | 20% | 80% |  |  |  |
| CT15 |  | QLS Availability | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 1, 13, 15, 26, 36, 37, 38 |  |
| CT16 |  | Maintenance | 20% | 80% |  | For Risk Allocation, see the applicable risk desription and allocation. The following Risk numbers are applicable to this KPI: 38 |  |
| CT18 |  | Tactical marketing programme Level of Service (LOS) | 20% | 80% |  |  |  |
| CT20 |  | Route Patrol Personnel Qualifications | 100% | 0% |  | Main Contractor |  |
| CT21 |  | Fresh Air Management System | 100% | 0% |  | Main Contractor |  |
| Volume 2 Book 6a - Section 6 |  |  |  |  |  |  |  |
| Clause # | Description |  |  |  |  |  | Description |
|  |  |  | MC |  | NSC |  |  |
| 6.2.1 | In the event that the Contractor does not fully comply with its obligations relating to maintenance of documents, drawings and Software in terms of Clauses 2 of the Standard Specifications of the Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) herein, the Contractor shall pay a penalty for the following: |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 38 |
| 6.3.1 | In the event that the Contractor does not provide for and accept all specified Methods of Payment as specified in Clause 7 of the Standard Specifications of Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) from the Commencement Date of the Operations Service Period or such other date as may be stipulated by the Employer Representative, the Employer shall be entitled to terminate this Agreement. Alternatively, the Contractor shall pay a penalty for the initial event of non-compliance and for each month of non-compliance thereafter. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 17, 19, 22, 23, 24, 36, 38 |
| 6.3.2 | In the event that the Contractor does not comply with the VAT business rules contained in the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a) from the Commencement Date of the Operation Service Period or such other date as stipulated by the Employers Representative, the Employer shall be entitled to terminate this Agreement. Alternatively, the Contractor shall pay a penalty for the initial event of non-compliance and for each month of non-compliance thereafter. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 17, 19, 22, 23, 24, 36, 38 |
| 6.4.1 | In the event that the Contractor does not meet the Queue Length Specification in terms of Clause 10.3 of the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) during any 15 (fifteen) minute period of monitoring done by the Contractor or the Employer’s Representative, the Contractor shall pay a penalty for each 15 (fifteen) minute period of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.4.2 | In the event that the Contractor meets the Queue Length Specification in terms of Clause10.3 of the Standard Specifications for Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) during any 15 (fifteen) minute period of monitoring done by the Contractor or Employer Representative for a period, as specified in the Project Document (Volume 3), the Employer shall pay an incentive to the Contractor. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.4.3 | In the event that the Contractor does not meet the Average Service Time Specification in terms of Clause 10.5 of the Standard Specifications of Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) the Contractor shall pay the penalty for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.4.4 | In the event that the Contractor meets the Average Service Time Specification in terms of Clause 10.5 of the Standard Specifications of Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) for a period, as specified in the Project Document (Volume 3), the Employer shall pay an incentive to the Contractor. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.5.1 | In the event of an MIS failure, the Contractor shall pay a penalty for each day that such failure was recorded or for each day or part thereof that data loss occurred. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 17, 19, 22, 23, 24, 36, 37, 38 |
| 6.5.2 | In the event that the Contractor process more than ten (10) vehicles in a lane where the AVC is in Critical Error Mode, the Contractor shall pay a penalty for each event of non-compliance. This penalty shall be applied per event of non-compliance up to a maximum of twenty (20) events per lane per calendar month. (Incident 49) |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 37, 38 |
| 6.5.3 | In the event the Contractor has not submitted the complete results of the initial AVC accuracy certification process (including all requisite corroboratory information) as indicated in the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a) within forty five (45) days after the completion of the initial AVC monitoring period, the Contractor shall pay a penalty per week until such time as these results have been submitted to the Employer Representative. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 25, 38 |
| 6.5.4 | In the event that the Contractor operates the lanes in Manual Mode, the Contractor shall pay the following penalties – |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 17, 19, 22, 23, 24, 36, 37, 38 |
| 6.5.5 | In the event that the Contractor does not comply with the AVC system/the Employer interface requirements of the Standard Specifications for Operations and Maintenance for CTROM Projects: Toll Systems (Volume 2 Book 4a), from the Commencement Date or such other date as stipulated by the Employers Representative, such non-compliance, the Contractor shall pay a penalty per equipment type for each event of non-compliance. This penalty shall be applied once per calendar month, for each calendar month of non- compliance. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 38 |
| 6.5.6 | In the event that the Contractor’s Toll Collection Lane Equipment does not comply with the requirements for User Fare Displays, Receipts and/or Lane Tax Invoices issued in the Lanes, Tariff boards, Lane mode boards, Overhead Lane Signs and Traffic Lights (User interface), as contained in the Standard Specifications for Operations and Maintenance for CTROM Projects: Toll Systems (Volume 2 Book 4a), the Contractor shall pay a penalty per equipment type for each event of non-compliance. This penalty shall only be applied once per month, for each month of non- compliance. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 17, 19, 22, 23, 24, 36, 37, 38 |
| 6.5.7 | In the event that the Contractor does not comply with the interface requirements between all other systems excluding the AVC, and the Employer, as contained in the Standard Specifications for Operations and Maintenance for CTROM Projects: Toll Systems (Volume 2 Book 4a) from the Commencement Date or such other date as stipulated by the Employers Representative, the Contractor shall pay a penalty for each month of non-compliance. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 17, 19, 22, 23, 24, 36, 37, 38 |
| 6.5.8 | In the event that the Contractor does not fully comply with the requirements of the Standard Specifications for Operations and Maintenance for CTROM Projects: Electronic Toll Collection (ETC) (Volume 2 Book 5), the Contractor shall pay a penalty for each month of non-compliance and for each month of non-compliance thereafter. |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 17, 19, 22, 23, 24, 36, 37, 38 |
| 6.5.9 | In the event that the Contractor does not provide a detailed program for the complete Toll System upgrade/replacement activities within a) 5 days for Section 1, b) 21 days for section 2, c) 14 days for any onther notice after the commencement date, the Contractor shall pay a penalty as specified in the Project Document (Volume 3) per day for each day or part thereof, that the program is submitted late. |  | 20% |  | 80% |  |  |
| 6.5.10 | In the event that the Contractor does not meet the dates for the milestone targets (listed below), as indicated on the approved Toll System upgrade/replacement program, the Contractor shall pay a penalty. This penalty shall be applied per event where milestone target dates have not been met by the Contractor: |  | 20% |  | 80% |  |  |
| 6.6.1 | In the event that the Contractor does not comply with its obligations relating to recording and reporting of damage in terms of Clause 14.3.5 of the Standard Specifications of Operations and Maintenance for CTROM Projects: General – (Volume 2 Book 2a), the Contractor shall pay a penalty for each occurrence. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.7.1 | In the event that the Contractor does not comply with its obligations relating to Asset Management System as detailed in Clause 14.4 of the Standard Specifications of the Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a), the Contractor shall pay a penalty for the following: |  |  |  |  |  | See Risk Allocations in the Risk table when this penalty item is triggered because of on of the following risk numbers: 1, 13, 15, 36, 37, 38 |
| 6.8.1 | In the event that more than 10% (ten percent) of the canopy luminaires are not functional at any Toll Plaza, the Contractor shall pay a penalty for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.8.2 | In the event that more than 10% (ten percent) of the lighting mast luminaires are not functional at any Toll Plaza, the Contractor shall pay a penalty for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.8.3 | In the event that the Contractor does not submit a 3 (three) yearly corrosion status reports on all assets, in accordance with the Standard Specifications of the Operations and Maintenance for CTROM Projects: General (Volume 2 book 2a), within 5 (five) Business Days after the last day of each 2 (two) month period commencing from the Commencement Date, the Contractor shall pay a penalty for each event of non-compliance, and every subsequent month thereafter. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.8.4 | In the event that the Contractor does not submit a monthly handyman, HVAC or equipment failure report, in accordance with the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 book 2a), Contractor shall pay a penalty for each event of non-compliance, and every subsequent month thereafter. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.9.1 | In the event if an interruption of electricity supply to any Toll Plaza as a result of the Clause 15.1 of the Standard Specifications of the Operations and Maintenance for CTROM Projects: General (Volume 2 Book 2a) the Contractor shall pay a penalty. Without prejudice to any other remedy which the Employer may have either in terms of this Agreement or in law, the Employer shall be entitled to call on the Performance security. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.9.2 | In the event of non-compliance by the Contractor of its obligations pursuant to Clauses .15.1 of the Standard Specifications for Operations and Maintenance for CTROM Projects: General – Volume 2 Book 2(a), (save in respect of electricity supply), the Contractor shall pay for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.9.3 | In the event of an interruption in the UPS or emergency electricity supply to the Toll Plaza, the Contractor shall pay the following penalty: |  | 20% |  | 80% |  |  |
| 6.10.1 | In the event that the Contractor does not comply with its obligations specified in Clauses 15.4 (Safety and Security) of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), the Contractor shall pay a penalty for the each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.10.2 | In the event that the Contractor achieves any type of safety rating, i.e. NOSA-5star or similar, during the duration of this agreement, an incentive for the safety ratings obtained during a twelve (12) month period will be paid to the Contractor. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.11.1 | In the event that the Contractor does not comply with its obligations specified in Clause 15.5 (Quality Assurance) of the Standard specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), the Contractor shall pay a penalty for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.12.1 | In the event that the Contractor does not comply with its obligations relating to the handover of documents to the Next Contractor pursuant to the provisions of this Agreement, the Employer shall without prejudice to any other remedy which the Employer may have pursuant to this Agreement and in law, be entitled to call on the Performance Security, if any. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.13.1 | In the event the Contractor does not comply with all the requirements related to the participation of Incident Management System specifications as specified in Clause 19.2 of the Standard Specifications of Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), then the Contractor shall pay a penalty for each event of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.14.1 | In the event that the Contractor does not meet the following route service patrol specifications. The following penalties shall apply: |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.14.1.1 | If the Contractor does not comply to the frequency of Route Service Patrols and the number of Patrol Vehicles as specified in the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) then the Contractor pay a penalty for each day of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.14.1.2 | If the Contractor does not comply with activities listed in Clause 19.4 of the Standard Specifications for Operations and Maintenance CTROM Projects: General (Volume 2 Book 2a) then the Contractor pay a penalty for each day of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.14.1.3 | If the Contractor does not comply with the verification of incidents listed in Clause 19.4 of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) then the Contractor pay a penalty for each day of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.14.1.4 | If the Contractor does not comply with the minimum required equipment specified in Clause 19.4 (Route Patrol Service) of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) then the Contractor pay a penalty for each day of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |
| 6.15.1 | In the event that the Contractor does not meet the requirements related to the Customer Call Centre as specified in Clause 19.3 of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a). The Contractor shall pay a penalty for each day of non-compliance. |  | 100% |  | 0% |  | Risk is for the Main Contractor |

FORM D13: DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

SIGNED BY TENDERER:

SIGNED ON BEHALF OF PROSPECTIVE CONTRACTOR:

NAME OF REPRESENTATIVE:

SIGNATURE:

FORM D14:	TECHNICAL PROPOSAL

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Notes to tenderer:

- The tenderer shall take cognisance of the scoring methodology in TENDER DATA: APPENDIX 1: BREAKDOWN OF QUALITY CRITERIA (CLAUSE C.3.11) of PART T1.

- The tenderer shall submit a signed copy of this Technical Proposal, providing a clear statement of his / her understanding and approach to execute the work, using the headings and sub-headings listed below. The Employer shall only consider a tender if the information provided is clearly stated in the tender documentation.  Any other relevant details that the tenderer intends to submit, must be compiled and submitted as an Appendix to the Technical Proposal.

- 1. 	General Operations

  - Key Resources and other important personnel

The tenderer to provide Curriculum Vitae (no longer than A4 page) reflecting the contract management, toll system development and maintenance, human resource management and any other experience on SANRAL type of Contracts and/or similar Contracts for the following persons:

- Contracts Engineer / NSC’s Representative (Key Person)

- Quality Control Officer (Key Person)

- Maintenance Manager (Key Person)

- System/ software support specialist (Key Person)

- Network and Security Specialist (Key Person)

- Database Management Specialist

- H&S Officer (SHEQ Officer)

- Plaza Technicians

- Assistance Technicians (if applicable)

- Project Manager (for the various Design and Built Sections and for the Operations Service Period)

  - Organisation and Staffing

- The tenderer to provide the proposed detailed organogram indicating the proposed names of key resources, operations departments, number of staff for each staff level / category for each Toll Plaza for the Operations Service Period.

- The above to include the load of any individual on any specialist field and shared activity outside this contract, if awarded.

- The tenderer to provide breakdown of various staff categories that is reflected in the appropriate items of the Schedule of Payments/Costs Matrix.

- The tenderer to provide details of the proposed team(s) during the Design-Build Period, including the actual numbers, qualifications, relevant experience and durations utilised on the Employer type of Contracts and any other types of Contracts. This includes an indication as to the period during which individual will be active on this contract, during the Contract Period.

Note:  No cost information shall be provided in this Technical Proposal.

  - Key PDI Staff

- The tenderer to provide a list of key Previous Disadvantaged Individual (PDI) staff proposed for this project.

  - Past performance

- The tenderer to provide all relevant experience and durations on the Employers type Contracts and any other similar types of projects.

- Proposed Development, Operations and Maintenance Plan

  - Financial Statements

- The tenderer to provide a copy of the latest available Audited Financial Statements. Where the tenderer's latest financial period has ended more than 6 (six) months prior to the closing date of the tender, the tenderer's annual financial statements of the most recent reporting period shall be submitted. If this is not possible, the tenderer must provide motivation from the auditors to explain why the statement from the recent period is not available, together with the financial statements of the preceding financial year.

- The tenderer must show that it has an average annual turnover, over the last five (5) years of the tendering end, in excess of R5 million (Excl VAT) per year. If the tendering entity is a Consortium or Joint Venture, the annual turnover will be considered the sum of all shareholders or members and evidence thereof.

  - Risk Management

- The tenderer is to provide a Risk Management Plan (RMP) detailing all the perceived and toll system related risks while execution this type of contract. The risks need to be categorized in terms of risk severity (low to high risk) and how these risks be managed and controlled.  The RMP needs to provide comfort to the Employer that the tenderer understands the risks in this contract. The Tenderer is to indicate how these risks will be managed and controlled, but not limited to the following items:

- Communication risks (WAN and LAN)

- AVC (level of compliance in terms of CTROM requirements)

- Toll lane (level of compliance in terms of CTROM requirements)

- ETC and all other Payment Mechanisms in the Toll Lane (level of compliance in terms of CTROM requirements and downstream obligations).

- VGS/QLS and Booth Camera obligations (to surpass the minimum levels of compliance in terms of CTROM requirements).

- BOS and other peripheral systems and data platforms (level of compliance in terms of CTROM requirements).

- Maintenance and support of the toll system taken over at the start of the contract.

- The typical risks that the tenderer should be aware of and demonstrate in the RMP how it will be managed and mitigated include:

- Role players

- Transaction risk

- Interfaces

- Performance Management

- Reporting

The above is specially aimed at the shared risk in the Tolling Environment where the Main Contractor is dependent on the accurate and continued functioning of the supplied and maintained Tolling System.

- In support of the above, the tenderer is to complete, sign and clearly define/distribute the risk between NSC and the Main Contractor, and any subcontractor(s) in the Returnable Documents “Form D13”.

  - Interoperability of and with various systems and interfaces

The Tenderer needs to provide an operational plan and method to provide the Principal Employer confidence that the tenderer has the capacity, skill and depth to deal with the listed topics below to ensure financial and performance security from the first day of the Operational Service Period. The Tenderer is required to show tangible evidence of the readiness of the suggested skills base from the Establishment Date, preparing for the Operational take-over of an actively operational site.

    - The role of the national TCH

    - Dealing with Road Queries (point of presence, Call Centre, etc.)

    - TCH interface management

    - Electronic transaction file transfer

    - Account settlement

    - Road User account registration

    - Tag Management (procurement, distribution and stock control)

  - Establishment Phase/Period:

The Tenderer needs to provide a substance based operational plan and method to provide the Principal Employer confidence that the tenderer has the capacity, skill and depth to take over an existing legacy system and guarantee the required maintenance of the system components and peripheral interfaces and services required to ensure financial and performance security from the first day of the Operational Service Period. The Tenderer is required to show tangible evidence of the readiness of the suggested skills base from the Establishment Date, preparing for the Operational take-over of an actively operational site, with specific reference to the topics listed below.

    - Staff procurement

    - Training

    - Sub-Contractor procurement

    - On-site establishment

    - Maintenance and support of legacy Toll System (system taken over)

    - Envisaged timelines and program

- Toll System Development and Maintenance

  - Financial Management (Including that of Revenue Streams)

- The Nominated Subcontractor is financially exposed in a similar manner as the Main Contractor. The tenderer to provide his understanding of the processes and systems requirements to support these processes, ensuring the provision of a secure and near-100% uptime, operational Tolling System which protects the Main Contractor and in turn protects the Nominated Subcontractor, within the maximum allowed window period to fulfil various operational tasks and services. The Tenderer is required to address the topics listed below under financial management:

    - Understanding of the financial processes, revenue streams and system requirements

    - Provision of a secure Tolling System with a high availability

  - System Maintenance (All Lines of Support)

- In accordance with the planned and intended Operational Tolling Services which require a near real time response to any system abnormality or degradation, the Tenderer is to indicate how this service would be delivered on a continuous basis, for the duration of the Contract Period.

- The above include the procedures to guarantee support and operational corrective action to ensure operational performance success and avoidance of negative KPI and/or Penalty scenarios, as applicable to the Main Contractor.

- The Tenderer is also to highlight all support services provided to the Main Contractor (including system related Training) to ensure the optimal operational use and participation in maintaining a comprehensive system and databases to the highest levels of integrity and accuracy.

- The Tenderer is required to address the topics listed below:

    - Understanding the System Maintenance Scope of Works

    - Hardware and software support (in the context of the Contractor's scope)

    - Fault reporting and responses

    - The proposed Resource Management plan (including all resource categories and numbers)

    - Managing toll system and spares availability risk (including Business Continuity solutions)

    - Asset replacement and hand back

  - Performance Management

- The tenderer to provide information of how the performance will be monitored and reported as specified in the tender requirements. The tenderer shall also indicate plans on how performance can be improved and how it was manged on other similar projects.

  - Quality Assurance

- The tenderer is to provide a Quality Assurance Plan indicating the processes and controls related to the design, built, operation and maintenance of the toll system at the toll plazas.

- The tenderer to provide copies of any Quality related Certification(s)

  - Environmental Management (as applicable to the technical environment of the Tenderers Scope of works).

- The tenderer to provide an Environmental Management Plan indicating the processes and controls related to the design, built, operation and maintain of the toll system at the Toll Plazas

- The tenderer to provide copies of any Environmental related Certification(s). Specific reference to the discarding of electronic equipment and hazardous materials like batteries etc.

  - Health and Safety

- The tenderer to provide a plan indicating how the latest OHSACT requirements related to the design, built, operate and maintain of the toll system will be maintained during the Design Build phase and during the Operation Service Period from the first day of the Establishment Period.

- The tenderer to provide copies of any OHS related Certification(s)

  - Toll system roll out programme

- The tenderer to provide a realistic and pragmatic program of the toll system roll out reflecting to all the toll system Sections, Components & milestones, payment milestones and contractual performance milestone dates.

  - System Security

- The tenderer to provide a plan of how the tenderer will deal with the system security.

  - Toll system technical analysis

- The tenderer to provide the documents “Form D10”, in association with this FORM D14 and any other relevant information, which will assist the Employer to evaluate the technical aspects of the proposed toll system.

  - Other

- The tenderer to provide any other relevant design, built, operate and maintenance information of the toll system.

SIGNED BY TENDERER:

FORM D15:	CORPORATE SOCIAL INVESTMENT

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

With regard to clause D1012: Community Development, of the Project Specifications:

Notes to tenderer:

- The tenderer shall list below Corporate Social Investment initiatives that will actively be pursued for this project.

- The Corporate Social Investment initiatives will be evaluated and applied as objective criteria in terms of section 2(1)(f) of the Preferential Procurement Policy Framework Act, 2000.

| CSI Initiative | Community Affected | Estimated Rand Value of Initiative | Estimated Time for Implementation |
| --- | --- | --- | --- |

SIGNED BY TENDERER:

FORM E1:	ELECTRICAL SCHEDULE OF MATERIALS

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to Tenderer:

- The schedules must only be completed insofar as the equipment and materials required for this particular contract are concerned.

- If these schedules are not properly completed by the tenderer, his bid document will be regarded as incomplete. All technical data sheets to be attached to this Form E1 to complete the tender submission to ensure the complete evaluation of the tender offer.

- Where types, etc. are filled in below and these do not comply with the Specification, this must be specifically pointed out by the Tenderer. Filling in of types, etc. below does not, if they do not comply, signify that they are acceptable or will be accepted. Any changes to the specification or requirements must be approved in writing by SANRAL before making any changes.

- CABLES, CONDUCTORS AND ACCESSORIES AS PER V2B3

| EQUIPMENT AND MATERIAL | DESCRIPTION AND MAKE |
| --- | --- |
| PVC SWA PVC LV Cable |  |
| PVC SWA PVC LV Cable glands |  |
| PVC SWA PVC LV Cable joints |  |
| PVC SWA PVC LV Cable terminations |  |

FORM F1:	SCHEDULE OF TENDER COMPLIANCE

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note to tenderer:

- This form has been created as an aid to ensure a tenderer’s compliance with the completion of the returnable forms and schedules and subsequent placement in the correct envelope.

| FORM No /SBD NO | FORM DESCRIPTION | TICK IF COMPLETED |
| --- | --- | --- |
| A1 | CERTIFICATE OF CONFIRMATION THAT THE TENDERER READ THE PRESENTATION OR ATTENDED THE COMPULSORY CLARRIFICATION MEETING |  |
| A1.1 | CERTIFICATE OF INTENTION TO SUBMIT A TENDER |  |
| A2.1 | CERTIFICATE OF AUTHORITY FOR SIGNATORY |  |
| A2.2 | DECLARATION OF TENDERER’S CURRENT STATUS OF ANY DEBT OUTSTANDING TO SANRAL |  |
| A2.3 | CERTIFICATE OF SINGLE TENDER SUBMISSION |  |
| A2.4 | CERTIFICATE OF FRONTING PRACTICES |  |
| A2.5 | DECLARATION OF DOMESTIC PROMINETN INFLUENTIAL PERSONS, FOREIGN PROMINENT PUBLIC OFFICIALS AND FOREIGN INFLUENTIAL NATIONALS (DPIPS, FPPOS & FINS) |  |
| A2.6 | CERTIFICATE OF PERMISSION TO CONDUCT DUE DILIGENCE INVESTIGATION |  |
| a3.1/SBD4 | BIDDER’S DISCLOSURE |  |
| A3.2/SBD9 | CERTIFICATE OF INDEPENDENT TENDER | N/A |
| A3.3 | DECLARATION OF TENDERER’S PAST SUPPLY CHAIN MANAGEMENT PRACTICES |  |
| A3.4 | REGISTRATION ON NATIONAL TREASURY CENTRAL SUPPLIER DATABASE |  |
| A3.5/SBD6.2 | DECLARATION CERTIFICATE FOR LOCAL PRODUCTION AND CONTENT FOR DESIGNATED SECTORS |  |
| A3.6 | LOCAL CONTENT DECLARATION: SUMMARY SCHEDULE |  |
| A4 | SCHEDULE OF DEVIATIONS OR QUALIFICATIONS BY TENDERER |  |
| A5 | SCHEDULE OF ADDENDA TO TENDER DOCUMENTS |  |
| A6/SBD2 | CERTIFICATES OF TAX COMPLIANCE |  |
| A7 | CERTIFICATE OF INSURANCE COVER |  |
| A8 | TENDERER’S REGISTERED FINANCIAL SERVICE PROVIDER LETTER AND BANK DETAILS |  |
| A9.1 | SCHEDULE OF TENDERER’S LITIGATION HISTORY |  |
| A9.2 | ENVIRONMENTAL, SOCIAL, HEALTH, AND SAFETY PERFORMANCE DECLARATION |  |
| A10 | SCHEDULE OF CURRENT COMMITMENTS |  |
| A11 | CERTIFICATE OF COMPLIANCE WITH COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT, 1993 (ACT NO. 130 OF 1993) |  |
| A12 | JOINT VENTURE AGREEMENT |  |
| A13/SBD1 | INVITATION TO BID AND TERMS AND CONDITIONS FOR BIDDING |  |
| B1 | CURRENCY EXCHANGE RATE FLUCTUATIONS |  |
| C1.1 | TENDERER’S B-BBEE VERIFICATION CERTIFICATION |  |
| C1.2/SBD6.1 | PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017 (INCORPORATING SBD6.1) |  |
| D1 | SCHEDULE OF TENDERER’S PLANT AND EQUIPMENT |  |
| D.2 | TENDERER’S METHOD STATEMENT |  |
| D3 | TENDERER’S ORGANISATION AND STAFFING |  |
| D4.1 | PERSONNEL RESOURCE DETAIL (NSC REPRESENTATIVE) |  |
| D4.2 | PERSONNEL RESOURCE DETAIL (QUALITY CONTROL OFFICER) |  |
| D4.3 | PERSONNEL RESOURCE DETAIL (MAINTENANCE MANAGER) |  |
| D4.4 | PERSONNEL RESOURCE DETAIL (SYSTEM SOFTWARE SPECIALIST) |  |
| D4.5 | PERSONNEL RESOURCE DETAIL (NETWORK AND SECURITY SPECIALIST) |  |
| D4.6.1 | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 1) |  |
| D4.6.2 | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 2) |  |
| D4.6.3 | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 3) |  |
| D4.6.4 | PERSONNEL RESOURCE DETAIL (PLAZA TECHNICIAL 4) |  |
| D4.7 | PERSONNEL RESOURCE DETAIL (H&S MANAGER/OFFICER) |  |
| D5.1 | TENDERER’S EXPERIENCE BASED ON COMPLETED PROJECTS |  |
| D5.2 | TENDERER’S EXPERIENCE BASED ON PROJECTS IN PROGRESS |  |
| D7.1 | TENDERER’S INDICATIVE PROGRAM |  |
| D7.2 | PROPOSED ESTABLISHMENT PROGRAMME |  |
| D8 | SCHEDULE OF ESTIMATED MONTHLY EXPENDITURE |  |
| D9 | NOMINATION OF COMPANY, MEMBER, SUBCONTRACTOR, ETC. FOR EACH DISCIPLINE |  |
| D10 | TECHNICAL AND SYSTEM INFORMATION |  |
| D11 | TOLL PLAZA UPGRADING SCHEDULES |  |
| D12 | ADDITIONAL INFORMATION |  |
| D13 | DISTRIBUTION OF RISK BETWEEN THE NSC AND THE MAIN CONTRACTOR AND ANY OTHER SUB-CONTRACTORS |  |
| D14 | TECHNICAL PROPOSAL |  |
| D15 | CORPORATE SOCIAL INVESTMENT |  |
| E1 | ELECTRICAL SCHEDULE OF MATERIALS |  |
| F1 | SCHEDULE OF TENDER COMPLIANCE |  |
| C1.1.1/SBD7 | FORM OF OFFER |  |
| C1.5 | CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER |  |
| C2.2/SBD3 | PRICING SCHEDULE |  |
| C2.3 | SUMMARY OF PRICING SCHEDULE (REPEALED) | N/A |

PART C1:	AGREEMENTS AND CONTRACT DATA

C1.1	FORMS OF OFFER AND ACCEPTANCE

C1.1.1	LETTER OF OFFER (INCORPORATING SBD7)

The South African National Roads Agency SOC Limited

PO Box 415

PRETORIA

0001

Sir,

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

  - I/we, by signing this part of the forms of offer and acceptance acknowledge they are the equivalent of the Letters of Tender and Acceptance as defined in clauses 1.1.48 and 1.1.49 in the “Conditions of Contract for Design, Build and Operate Projects” (2008), published by the Fédération Internationale des Ingénieurs-Conseils, (FIDIC).

  - I/we confirm that I/we practise the principles of corporate governance that abhors corruption and fraud, and that I/we have examined the documents listed in the tender data and addenda thereto as listed in the returnable schedules and am/are duly authorised to represent and commit the tenderer to the contractual obligations contained therein.

  - I/we further confirm that by submitting this offer the tenderer accepts the conditions of tender and offers to perform all of the obligations and liabilities of the contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of tender and the conditions of contract identified in the contract data.

  - PRICE OFFERED

THE OFFERED TOTAL OF THE PRICES FOR THE DESIGN-BUILD AND DEVELOPMENT OF WORKS AND THE OPERATION SERVICE PERIOD (INCLUSIVE OF VALUE ADDED TAX) BROUGHT FORWARD FROM SECTION C2.2 SCHEDULE OF PAYMENTS/COST MATRIX IS:

..............................................................................................................................................

................................................................................................................................................................................

..............................................................................................................................(in words)

R .........................................................................................................................(in figures)

I/we confirm that if any difference between the total of the Schedule of Payments/Cost Matrix and the amounts stated above exists, the amount stated in words shall apply.

I/

  - PREFERENCE CLAIMED

I/we claim the following B-BBEE contributor status level ......................... as per Returnable Schedule Form C1: Tenderer’s B-BBEE Verification Certificate subject to Tender Data C.3.11 In the event of any difference between the above stated status level and the Verification Certificate attached to Form C1, the Verification Certificate shall apply.

  - You may accept this offer by signing and returning to the tenderer one copy of the letter of acceptance before the end of the period of validity stated in the tender data, (or at the end of any agreed extension thereof), whereupon the tenderer becomes the party named as the contractor in the conditions of contract identified in the contract data.

  - Notwithstanding anything contained in a covering letter to this tender, I/we declare this offer is submitted entirely without deviations or qualifications other than those stipulated in Form A4: Schedule of Deviations or Qualifications by the tenderer, and that it is made free from any fraud, corruption, and misrepresentation.

Yours faithfully

SIGNATURE: …………………………………………      DATE: ……………………………………………...

NAME (IN CAPITALS):

CAPACITY:

Date and minute reference of Board resolution if different from returnable schedule Form A2.1:

Certificate of Authority for Signature ……………………………………………………………………………

NAME AND ADDRESS OF ORGANISATION:  ……………………………………………………………….

NAME AND SIGNATURE OF WITNESSES:

AS WITNESSES:

1			………………………………………………..

…………………………………………………………..	…………………………………………………

SIGNATURE	NAME (IN CAPITALS)

- ……………………………………………………	…………………………………………………

SIGNATURE 	NAME (IN CAPITALS)

C1.1.2	FORM OF ACCEPTANCE (INCORPORATING SBD7)

Form to be printed on SANRAL letterhead

To (Name of successful tenderer)

Dear Sir,

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ACCEPTANCE OF OFFER

- It is our pleasure to inform you that the South African National Roads Agency SOC Limited (the Employer) accepts your (select if applicable corrected/corrected alternative/alternative) offer in the amount of R…………………….…….. (i.e. including VAT but excluding cost indexation and any contingent sum not in the priced schedule) for the Operation Service Period of six (6) years with the base date of March 2024 (28 days prior to the actual closing date of tender).

- The amount due may not be the Accepted Contract Amount but payment shall be made in accordance with the conditions of contract identified in the contract data.

The Main Contractor for THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD shall be instructed to appoint you as the Nominated Subcontractor for THE DBOM OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD.

Proforma

The Main Contractor shall issue you with a Letter of Acceptance as defined in clause 1.1.48 of the “Conditions of Contract for Design, Build and Operate Projects” (2008), published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC) Gold Bank.

- Acceptance of the Main Contractor’s letter shall form an agreement between you according to the terms and conditions contained in this form and in the Contract that is comprised of:

Part C1: Agreements and Contract Data (including this Letter of Acceptance),

Part C2: Pricing Data,

Part C3: Scope of the Work,

Part C4: Site Information,

Part D: Stakeholder and Community Liaison, and Targeted Labour and Targeted Enterprises utilisation and development; and

Part E: Annexures

together with issued drawings, addenda, Employer Requirements and other documents, or parts thereof, which may be incorporated by reference into Parts listed above.

- Deviations and/or qualifications included in your offer as well as any changes to the terms of the offer agreed between you and the Main Contractor during the process of tender offer and acceptance shall not be valid unless contained in the tendered Returnable Schedule of deviations.  Addenda issued during the tender period are not deemed to be deviations to the tender documents and schedules.

- Notwithstanding the need to agree the mandate required by Section 37 of the Occupational Health and Safety Act, 1993 (Act No 85 of 1993), a proforma of which is attached for your reference, the Main Contractor will appoint you as the Principal Contractor in terms of Regulation 5(1)(k) of the Construction Regulations, GNR. 84 of 2014.

- A SARS compliance check has been done on you and you are found to be ….. (select:  “compliant” or “non-compliant”). “Within 7 calendar days of the date of this Form of Acceptance you shall provide proof that you are SARS compliant. Failure to fulfil this obligation shall constitute a repudiation of this agreement.”)

- Within fourteen (14) calendar days of the date of the Main Contractor’s Letter of Acceptance (including the tendered Returnable Schedule of deviations if any) you shall deliver to him/her:

- Performance Security – Surety Bond (as per clause 4.2 and 13.8 of the Conditional of Contract (FIDIC)) a pro forma is contained in the sample forms of tender and agreement of the FIDIC DBO Conditions of Contract for your reference.  There shall be no deviations from the wording of the pro forma Performance Security – Surety Bond.

- Proof of insurance in terms of the information provided in the Contract Data and clause 19 of the Condition of Contract (FIDIC).  Proof of currency of insured cover shall be provided on a monthly basis until date stated in Contract Completion Certificate.

- Fully completed and signed form together with your Health and Safety plan and proof of the Construction Health and Safety Officer’s Registration with SACPCMP.

- Proof that you are registered and in good standing with the compensation fund or with a licensed compensation insurer.

- A completed Form of banking Details. (Note to compiler: only include this if the successful tenderer has not previously been registered as a vendor with the Employer)

- Proof of registration on the Employer’s Project Information Module (ITIS).

- Alternative nominated DAB member details. Note to compiler: only include this if a standing DAB is specified under Conditions of Contract clause 20.2

Failure to fulfil either of the obligations in (i), (ii) or (iii) above, shall constitute a repudiation of this agreement and we may at our discretion apply any rights of remedy including barring you from tendering on any of our future tenders for a period to be determined by us, but not less than twelve (12) months, from the date of tender closure.

- The tenderer must register an account on SAP Ariba before the hand-over meeting. The link and information to register the Ariba account is provided below.

https://www.nra.co.za/sap-ariba/

Contact : ProcurementSR5@sanral.co.za for queries regarding SAP Ariba registration.

- The effective date of the contract shall be the date of the Letter of Acceptance unless you within four (4) calendar days of the effective date, notify the Main Contractor in writing of any justification why you cannot accept the contents of this agreement.

- The Commencement Date of the Works shall be that on which the commencement meeting is held, which shall not be later than …. ………………..(Note to compiler: the commencement meeting date indicated above is usually within 28 calendar days after the date of this form, as circumstances demand and as agreed between tenderer/Employer. The above can also be amended by fixing the Commencement Date to a given date). Access to the Site shall be on the Commencement Date.

- Notwithstanding that a full, original-signed copy of the Contract document containing all Contract Data and schedules (including that of accepted deviations) will be delivered to you, the Letter of Acceptance constitutes the binding contract between us.

- The Main Contractor shall appoint a Nominated Subcontractors Representative to fulfil the functions and duties of the Employer’s Representative in the administration of this Contract.  Please contact ………………… at ……………………. to make arrangements for the signing of the Contract documents and handover of the Site.

SIGNATURE:		………………………………………….. DATE:	………….…………………...

NAME (IN CAPITALS):

CAPACITY:  Regional Manager Northern Region

EMPLOYER’S NAME AND ADDRESS:

The Regional Manager (Northern Region)

The South African National Roads Agency SOC Ltd

38 Ida Street

Menlo Park

Pretoria,

0081

AUTHORITY TO ACT: SANRAL Delegation of Authority: Item 2.4.1.2.

C1.1.3	APPENDIX TO FORM OF ACCEPTANCE

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Schedule of Deviations

The deviations listed below constitute agreed deviations/amendments to the tender document negotiated between the tenderer and Principal Employer based on information provided in the tendered Returnable Schedule of Deviations or Qualifications by tenderer or imposed conditions of award.

1.	Subject:

Proforma

Details:

2	Subject:

Details:

3	Subject:

Details:

4	Subject:

Details:

By the duly authorised representatives signing this agreement, the Main Contractor and the tenderer agree to and accept the afore-going schedule of deviations as the only deviations from and amendments to the documents listed in the tender data and addenda thereto as listed in the Returnable Schedules, as well as any confirmation, clarification or changes to the terms of the offer agreed by the tenderer and the Principal Employer during this process of offer and acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Contract shall have any meaning or effect in the Contract between the Parties arising from this agreement.

C1.1.4	CONTRACT AGREEMENT

This Agreement made on the ______________________ day of ______________________ , 20_________,

between	(Note to Contract Compiler:  Update to reflect the Main Contractor’s details who will be the Employer in this Agreement)

of 		(Note to Contract Compiler:  Update to reflect the Main Contractor’s address

(herein called "the Employer"), of the one part,

and 	__________________________________________________________ (name of Contractor)

of 	________________________________________________________ (address of Contractor)

(herein called "the Contractor"), of the other part:

Whereas the Employer desires that the “FOR THE NOMINATED SUB-CONTRACT FOR THE DBOM OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD“ (the Works), should be completed, improved, expanded, replaced, designed, executed, commissioned, operated and maintained by the Contractor and has accepted a Tender from the Contractor for the design, execution, completion, commissioning and operation and maintenance of these Works, and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

- In this Agreement, the words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

The following documents shall be deemed to form and be read and construed as a part of this Agreement:

- The Letter of Acceptance dated

- The Letter of Tender dated

- The Addenda Nos.

- The Conditions of Contract

- The Employer's Requirements

- The completed Schedules

- The Operating Licence, and

- The Contractor's Proposal

In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby agrees with the Employer to design, execute, complete and commission the Design-Build works, and to operate and maintain the Works and remedy any defects therein in conformity with the provisions of the Contract and the Operating Licence granted by the Employer.

The Employer hereby agrees to pay the Contractor, in consideration of the design, execution, completion and commissioning of the Design-Build works, and the operation and maintenance of the Works and the remedying of defects therein, the Contract Price at the times and in the manner prescribed by the Contract, and to grant the Contractor a royalty-free licence to enable him to take-over, operate and maintain the Works during the Operation Service Periods.

In witness whereof the Parties hereto have caused this Agreement to be executed on the day and year first above written.

SIGNED BY:		SIGNED BY:

(Signature) 					       	 (Signature)

for and on behalf of the Contractor in the presence of	for and on behalf of the Employer in the presence of

WITNESS:			WITNESS:

(Signature)    						 (Signature)

NAME: 	   	NAME:

ADDRESS:		ADDRESS:

DATE:		DATE:

C1.2	CONTRACT DATA

C1.2.1	INTRODUCTION

This Contract will be let as a Nominated Subcontract to the Main Contract for the Operations and Maintenance of the Toll Plazas on the N1 North Toll Road.

C1.2.1.1	CONDITIONS OF CONTRACT CONCEPTS

The Conditions of Contract comprise the "General Conditions", "Particular Conditions Part A – Contract Data" and "Particular Conditions Part B – Special Provisions", which include amendments and additions to such General Conditions.

For the Main Contract the following shall apply:

- The General Conditions of Contract shall be the “Conditions of Contract for Design, Build and Operate Projects, First Edition 2008” published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC)

- The Contract Data (Particular Conditions, Part A) as set out in the Main Contract Part C1, and which provisions take preference over the General Conditions and Special Provisions; and

- The Special Provisions (Particular Conditions, Part B) as set out in the Main Contract PART C1, and which provisions take preference over the General Conditions.

- A copy of the Main Contractor’s Tender Document will be made available to the NSC for purposes of context and a better understanding of the Works.

For the Nominated Sub-Contract (NSC) (this Contract) the following shall apply:

- The General Conditions of Contract shall be the “Conditions of Contract for Design, Build and Operate Projects, First Edition 2008” published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC)

- The Contract Data (Particular Conditions, Part A) as set out in C.1.2.1 below, and which provisions take preference over the General Conditions and Special Provisions; and

- The Special Provisions (Particular Conditions, Part B) as set out in C.1.2.2 below, and which provisions take preference over the General Conditions.

- A copy of the Nominated Subcontract will be made available to the MC for purposes of context and a better understanding of the Works.

C1.2.1.2	ASSOCIATED Contracts and terminology

The terminology used for the contracts and the various roles versus the FIDIC terminology is tabled and clarified below.

Table 1: ASSOCIATED Contracts and terminology

| Contract Entity | Main Contract (MC) (CTROM Operations and Maintenance Contract) | Toll System Subcontract (NSC) | How these should be interpreted in this contract |
| --- | --- | --- | --- |
| SANRAL | Employer | Principal Employer | Principal Employer |
| Main Contractor (MC) (Operations and Maintenance Contractor) | Contractor | Employer | Main Contractor |
| Toll System Subcontractor (NSC) | Nominated Subcontractor (NSC) | Contractor | Nominated Subcontractor (NSC) |
| Employer’s Representative | Employer’s Representative | Main Contractor’s (MC) Representative | MC Representative |
| SANRAL MIS System Integrator |  |  | 3rd Party - SANRAL MIS System Integrator (SI) |
| SANRAL Toll System Integrator |  |  | 3rd Party - SANRAL Toll System Integrator (SI) |

The Special Provisions (Particular Conditions, Part B) as set out in C.1.2.2 below, include clarifications and special stipulations to make the Nominated Subcontract Conditions of Contract specific to this nominated subcontract.

All references to Contractor or NSC in the General Conditions, the Contract Data and the Special Provisions refer to the Nominated Subcontractor (NSC).

C1.2.2	PART A: “PARTICULAR CONDITIONS:  CONTRACT DATA

| Clause No. | Condition Reference. | Data |
| --- | --- | --- |
| 1.1.24 | Where the Contract allows for Cost Plus Profit, percentage profit to be added to the cost: | 5% |
| 1.1.26 | Cut Off Date (number of days after the Time for Completion of Design-Build): | 180 days |
| 1.1.32 | Employer’s name and address: | Means the Main Contractor, who will be notified once appointment has been finalised. The Employer’s Address is: To be notified once appointment has been finalised. |
| 1.1.35 | Employer’s Representative name and address: | An Employer’s Representative are not applicable under this Nominated Subcontract. The Main Contractor shall, however, during the Establishment Period propose the name and full particulars of his Main Contractor’s Representative (who shall be capable to undertake similar responsibilities and duties as set for an Employer’s Representative pursuant to the Conditions of Contract) for approval by the Principal Employer. |
| 1.1.70 | Parts of the Works that shall be designated a Section for the purposes of the Contract: | Contract Data for Sections is provided in Appendix 1 hereto. |
| 1.1.78 | Time for Completion of Design-Build: | Contract Data for Sections is provided in Appendix 1 hereto. |
| 1.3 | Agreed methods of electronic transmission: | Virus protected E-mail |
| 1.3 | Address of Employer for communications: | To be confirmed after award of the contract |
| 1.3 | Address of Employer’s Representative for communications: | To be confirmed after award of the contract |
| 1.3 | Address of Contractor for communications: | To be confirmed after award of the contract |
| 1.4 | Contract shall be governed by the law of: | South Africa |
| 1.4 | Ruling language: | English |
| 1.4 | Language for communications: | English |
| 2.1 | After receiving the Letter of Acceptance, the Contractor shall be given access to all or part of the site within: | Contract Data on envisaged site access is given in Appendix 1 hereto. |
| 4.2 | Initial Performance Security during the design-built section 2: (that applies to the Design Build part of the works only) | 10% of the Design Build part of the Contract Amount at Base Date value and which shall be adjusted in accordance with Sub-Clauses 4.2 and 13.8. The Design Build Performance Security requirements increase with the addition of each new section of Design Build work. |
| 4.2 | Performance Security during the Operation Service part of the Work: (due from the start of the Contract for the duration of the Operations Service) | 10% of the Operation Service part of the Contract Amount (excluding the Design Build works) at Base Date value and which shall be adjusted in accordance with Sub-Clauses 4.2 and 13.8 |
|  | Currency………………………………… | ZAR (South African Rand) |
| 5.1 | Period of notification of errors, faults and other defects is: | 21 days |
| 5.2 | Contractor’s documents requiring approval: | Contract Data is tabled in Appendix 2 hereto. |
| 6.5 | Normal working hours on the Site: | With the exception of public holidays (including statutory election days) of the Country and necessary shift works pursuant to the Employer’s Requirements and the Operation and Maintenance Plan, the normal working hours are: South African time (7:00 to 18:00) on Mondays to Fridays. For Toll Operations the working hours are 24 hours for 7 days |
| 8.2 | Period of the Operation Service: |  |
|  | Operation Service Period sections 1 and 2 at the Toll Plazas on the N1 North Toll Road commencing on the issuing of Commissioning Certificate for Design-Build: Section 1. | 6 years |
| 8.3 | Software to be used for Contractor’s time programmes: | Unless otherwise stated in the Employer’s Requirements, appropriate Microsoft programming products shall be used. |
| 9.2 | Time for Completion of Design-Build of all Works: | Contract Data for Sections is provided in Appendix 1 hereto. |
| 9.2 | Time for Completion of each Section: | Contract Data for Sections is provided in Appendix 1 hereto. |
| 9.6 | Delay damages relating to Design-Build (amount per day of delay at Base Date value and which shall be adjusted in accordance with Sub-Clause 13.8): | Contract Data for Sections is provided in Appendix 1 hereto. |
|  | Note: If specified in the Employer’s Requirements and in addition to the application of delay damages, programme performance adjustments may be applicable when the Contractor fails to achieve interim milestones on his time programmes. |  |
| 9.6 | Maximum Amount of delay damages: | 10% of Value of Work for particular section |
| 10.6 (a) | Maximum Compensation payable by Contractor (Amount): | 10% of Contract Amount and which shall be adjusted in accordance with Sub-Clause 13.8 |
| 10.6 (b) | Maximum Compensation payable by Employer (Amount): | 10% of Contract Amount and which shall be adjusted in accordance with Sub-Clause 13.8 |
| 10.7 (b) | Rights of Employer if failure continues for more than 84 days: | In addition to the stated Conditions of Contract, the Employer shall also be entitled to: (i) arrange for the performance of the relevant affected part of the Operation Service by another person at the Contractor’s cost, or (iv) terminate the affected, relevant and appropriate part of the Operation Service by giving not less than 56 days’ Notice, in accordance with Sub-Clause 15.2 [Termination for Contractor’s Default] |
| 14.2 | Amount of Advance Payment (percent of Accepted Contract Price): | ZAR 0.00 (0%) |
| 14.2 | Currencies of Advance Payment if different to the currencies quoted in the Contract: | Not applicable |
| 14.2 | Percentage deductions for the repayment of the Advance Payment: | Not applicable |
| 14.3 (c) | Retention deductions from Interim Payments during: |  |
|  | Design – Build Period ……………………….. | 0% |
| 14.3 (c) | Operation Service Period …………………… | 0% |
|  | Limit of Retention Money during: |  |
|  | Design – Build Period ………………………. | ZAR 0.00 |
|  | Operation Service Period …………………… Note: The provisions for retention (deductions, retention money, maintenance retention fund, retention period, retention guarantee / bond and the like) is not applicable to the Contract. | ZAR 0.00 |
| 14.6 | Plant and Materials for payment when shipped and delivered to Site: | 0%, This provision shall not be applicable to the Contract. |
| 14.7 | Minimum Amount of Interim Payment Certificate: | ZAR 0,00 |
| 14.9 | Financing charges for delayed payment (percent points above discount rate): | 2 % above the repo rate of the South African Reserve Bank |
| 14.17 | Currencies for payment of Contract Price: | ZAR (South African Rand) only |
| 14.17 | Proportions of Local and Foreign Currencies are: |  |
|  | Local……………………………..…… | 100 % |
|  | Foreign…………………………….… | 0 % |
| 14.19 | Amount of Maintenance Retention Fund: | ZAR 0.00, This provision shall not be applicable to the Contract. |
| 17.1 (b) | Operation of forces of nature allocated to the Contractor: | The Conditions of Contract shall be applicable. |
| 17.8 | Total liability of Contractor shall not exceed: | 10% of the Accepted Contract Amount |
| 19.2(a)(i) | Permitted deductible limits: | ZAR 100,000 per event at Base Date Value which shall be adjusted in accordance with Sub-Clause 13.8 |
| 19.2(a)(ii) | Additional sum to be insured: | 15% of the value of the assets of the project. |
| 19.2(a)4 | Additional sum to be insured: | Contract Data is given in Appendix 3 hereto |
| 19.2(a)4 | Employer’s Risk to be insured if different to Sub-Clause 17.1(b)(iii): | Contract Data is given in Appendix 3 hereto |
| 19.2(a)5 | Exceptional Risks to be insured if different to Sub-Clause 18.1(4): | Contract Data is given in Appendix 3 hereto |
| 19.2(b) | Insurance of Contractor’s Equipment (amount required): | An amount equal to the full replacement value thereof at Base Date Value and which shall be adjusted in accordance with Sub-Clause 13.8 |
| 19.2(c) | Amount of Professional Liability Insurance required: | Contractor to determine appropriate amount |
| 19.2(c) | Period for which professional liability insurance required: | Up to the issuing of the Contract Completion Certificate |
| 19.2(e) | Amount of insurance required for injury to employees and damage to property | Contractor to determine appropriate amount |
| 19.3(a) | Insurance of the works: | As specified in Table 1 of Appendix 3 hereto and at full replacement value at Base Date and which shall be adjusted in accordance with sub-Clause 13.8 on an annual basis. |
|  | Permitted deductible limits: | Employer’s Equipment: As specified in Table 1 of Appendix 3 hereto |
| 19.3(b) | Injury to any person and damage to property amount: | Contractor to determine appropriate amount |
| 19.3(d) | Other insurances required by law and local practice: | Contract Data is given in Appendix 3 hereto |
| 19.3(e) | Other optional Operational Insurances: | Contract Data is given in Appendix 3 hereto |
| 20.3 | Date for appointment of ad-hoc DAB….. | The date shall be a date within 28 days after the date of a Dispute Notice of either Party to the other Party |
| 20.3 | Selection list of DAB Chairperson: | Not applicable |
| 20.4 | The DAB shall comprise: | One (1) member |
| 20.8 | Appointing entity (official) for DAB members, if not agreed, shall be……………………… | President of the South African Institute for Civil Engineers or a person nominated by him/her |
|  | Language of arbitration: | English |
| C3.3.5(d) | Environmental Management Plan (EMPC) | Not Applicable |
| `C3.4.4(e) | Appointed PLO | No PLO appointed |
| SECTION D | STAKEHOLDER AND COMMUNITY LIAISON AND TARGETED LABOUR AND TARGETED ENTERPRISES UTILISATION AND DEVELOPMENT |  |
| D1002 | DEFINITIONS AND APPLICABLE LEGISLATION |  |
|  | D1002.01 Definitions |  |
|  | (r) Target Area(s) | For Targeted Labour: Tshwane Metropolitan Municipality |
|  | (w) Targeted Labour | Target Group for Targeted Labour: a. black designated groups (As per latest PPPFA Regulations); b. black people; c. women; d. people with disabilities |
| D1003 | TARGET GROUP PARTICIPATION |  |
|  | D1003.04 Contract Participation Goal (CPG) |  |
|  | CPG for Targeted Labour: | Minimum of 10% of the Final Contract Value by the end of the contract to Targeted Labour The Final Contract Value is defined in clause D1003.04 |
|  | Targeted Labour minimum contributions by the following Target Groups: |  |
|  | a. black designated groups; (i) Black people who are youth | 30% of targeted labour value |
|  | (ii) Black people who are persons with disabilities | 0.5% of targeted labour value |
|  | b. Black women; | 30% of targeted labour value |
|  | CPG for Targeted Enterprise | Minimum of 30 (%) of the Final Contract Value by the end of the contract to Targeted Enterprises The Final Contract Value is defined in clause D1003.04. |
|  | Targeted Enterprise minimum contribution by the following Target Groups: i) Youth owned – min. 5% ii) Women owned – min. 5% iii) MV owned – min. 1% iv) Disabled owned – min. 0.5% v) CIDB 1&2 – min. 5% for contract <R50M, min. 2% for contract <R250M, min. 1.5% for contract <R500M, min. 1% for contract >R500M. vi) CIDB 3&4 - min. 5% for contract <R50M, min. 2% for contract <R250M, min. 1.5% for contract <R500M, min. 1% for contract >R500M |  |
|  | Targeted Enterprise with ≥51% ownership by Youth | No subminimum specified. |
|  | Targeted Enterprise with ≥51% ownership by Women | No subminimum specified. |
|  | Targeted Enterprise with ≥51% ownership by Military veterans | No subminimum specified. |
|  | Targeted Enterprise with ≥51% ownership by Disabled persons (Differently abled) | No subminimum specified. |
|  | Targeted Enterprise with CIDB 1 or 2 grading | No subminimum specified. |
|  | Targeted Enterprise with CIDB 3 or 4 grading | No subminimum specified. |
| D1008 | WORK SUITABLE FOR EXECUTION BY TARGETED ENTERPRISES | Toll System Maintenance and Toll Lane related maintenance work, plus any of the other categories of work listed in PART D. |

C1.2.3	APPENDIX 1 TO CONTRACT DATA:  SECTION DATA.

- Design-Build Section data

  - The summarized Design-Build Section data (definitions) in table 2 below shall also be read and construed in accordance with the Employer’s Requirements and Schedule of Payments.

  - It shall be noted that the Design-Build works for the defined Sections shall be executed in a real time operational environment.

  - Sections 4 and 5 are subject to If-Triggered Notices and may or may not be implemented. The Contractor shall not be entitled to claim in case one or more Sections are not triggered by the Principal Employer.

  - More than one Section may have to be executed in parallel, depending on the date of a Trigger Notice. The Contractor shall not be entitled to claim for additional time and cost in case the Sections are to be executed and/or performed simultaneously.

  - Section 1 is for the Contractor to establish and take over existing systems, operations, and maintenance activities.  The Contractor shall be given access to the site on the Commencement Date.

  - Section 2 covers the Establishment Upgrades of the existing system handed over at Commencement Date.

  - Section 3 covers the provision of a new Toll System (hardware and software) during which the Contractor shall participate extensively in the planning, design, testing (including the performance of the trial operations testing by the Contractor), data migration, interfacing, switch-over, commissioning, etc, in order to sign-off and take-over the new Toll System for the purpose of operations. The Contractor shall perform the management, coordination, liaison and interface management during the replacement of existing Toll System.

  - Section 4 covers the provision of a SANRAL MIS interface.  This section can overlap with Sections 3 or 5. This will include inter-alia, interface management, liaison, cooperation, etc between all applicable third-party contracts during the development of the interface.t

  - Section 5 covers the provision and deployment of a national SANRAL Toll System. This Section can overlap with Sections 3 or 4 during the migration period. This will include inter-alia, interface management, liaison, cooperation, etc between all applicable third-party contracts during the development.

  - The Section data tabled below is of a general nature and shall be interpreted in accordance with the corresponding or associated data as detailed in the Employer’s Requirements.  The data also refers to the general provisions for access to and possession of the applicable part of the Site pursuant to Sub-Clause 2.1 (Right of Access to the Site) of the Conditions of Contract.  It further refers to the Principal Employer’s Assets to be taken over by the Contractor prior to the issue of a Section Commissioning Certificate and for the purpose of operations and maintenance thereof, pursuant to Sub-Clause 4.26 (Take-over of Employer’s Assets) of the Conditions of Contract.

  - The Principal Employer is entitled to re-allocate any part (subject that it is not material) of the Works, Design-Build and/or Operation Service of an earlier Section to a subsequent Section by notifying the Contractor at a reasonable period in advance. Notwithstanding any other contrary provision of the Contract, the execution of this entitlement shall not give rise to any Contractor’s claim for delay and additional cost [pursuant to Sub-Clause 20.1 (Contractor’s Claims) of the Conditions of Contract] in relation thereto.

Figure 1:  Graphical representation of Design Build and Operation Service Sections

Table 2:  APPENDIX TO CONTRACT DATA (NOMINATED SUBCONTRACT)

| Section no | Design-Build Section definition | Section Start date | Time for completion (days) | Delay damages (per day) | Section Commissioning Certificate | Cut-off date (days) | Retention |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-Clause references |  | 1.1.6, 8.1, 9.1 | 1.1.78, 8.2; 9.2 | 8.5; 9.6 | 1.1.71, 11.5, 11.7 | 1.1.26, 9.13 | 1.1.66 |
| 1 | Establishment period. | Commencement Date | 42 days | N/A | Yes | 90 days | N/A |
| 2 | Keep existing compliance level: Functional Compliance with the 2010 CTROM requirements plus Establishment Upgrades | Section 1 Commissioning (Contractor can start earlier at Commencement Date) | 360 days | Refer Section 6 of V2B6a | Yes | 90 days | N/A |
| 3 | The supply of a complete Toll System, including additional items detailed in V3B1. (This section runs in parallel with Section 2 and contains the following sub-sections 3.1 to 3.9) | Section 1 Commissioning (Contractor can start earlier at Commencement Date) | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.1 | AVC/DCS: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.2 | Dedicated ETC lane: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.3 | ANPR: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.4 | Bank card processing: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.5 | Cash processing: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.6 | Discount and concessions: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.7 | Incident control: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.8 | VGS system: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 3.9 | QLS and QL system: | Section 1 Commissioning | 1080 days | Refer Section 6 of V2B6a | Yes | 180 days | N/A |
| 4 | The deployment of the SANRAL MIS interface. (If triggered item). | Date stated in trigger Notice | 180 days TBC with trigger | Refer Section 6 of V2B6a | Yes | 90 days | NA |

- Operation Service Period Section Data

  - The Operation Service Period Sections are as defined in Item 2 of this Appendix 1 and as shown in Figure 1.  Each Design Build Section have its own specific Operation Service requirements, and for this purpose separate Operation Service Periods are defined.

Each OSP Section shall only commence after the completion of the Trial Operations and System Compliance verification.  The previous OSP Section shall continue whilst DB for the following Section is not commissioned.

  - Operation Service Period Section 1 (OSP Sec 1) is for the operations and maintenance of Design Build Section 1.

  - The Contractor shall perform the Operation Service for OSP Sec 1 in accordance with Sub-Clause 10 (Operation Service).

The commencement of OSP Sec 1 shall follow on the commissioning date of Design Build Section 1.

The scope of OSP Sec 1 shall be as described in PART C3 and include all the work required to perform the operations and maintenance of the handed over Toll System and any upgrades.

  - There is no Operation Service Period Section 2 (OSP Sec 2).  OSP Sec 1 shall continue until both Design Build Sections 2 and 3 are commissioned.

  - Operation Service Period Section 3 (OSP Sec 3) is for the operations and maintenance of Design Build Sections 2 and 3.

  - The Contractor shall perform the OSP Sec 3 in accordance with Sub-Clause 10 (Operation Service).

The commencement of OSP Sec 3 shall follow on the commissioning date of Design Build Section 3.

The scope of OSP Sec 3 shall be as described in PART C3 and include all the work required to design, build and implement a new Toll System.

  - The Contractor shall perform the OSP Sec 4 in accordance with Sub-Clause 10 (Operation Service).

The commencement of OSP Sec 4 shall follow on the commissioning date of Design Build Section 4.

The scope of OSP Sec 4 shall be as described in PART C3 and include all the work required to design, build and implement a SANRAL MIS.

  - The Contractor shall perform the OSP Sec 5 in accordance with Sub-Clause 10 (Operation Service).

The commencement of OSP Sec 5 shall follow on the commissioning date of Design Build Section 5.

  - The scope of OSP Sec 5 shall be as described in PART C3 and include all the work required to design, build and implement a National SANRAL Toll System.

  - The Section data tabled here and in figure 1 is of a general nature and shall be interpreted in accordance with the corresponding or associated data as detailed in the Employer’s Requirements.

  - The Principal Employer is entitled to re-allocate any part (subject that it is not material) of the Works, Design-Build and/or Operation Service of an earlier Section to a subsequent Section by notifying the Contractor at a reasonable period in advance.  Notwithstanding any other contrary provision of the Contract, the execution of this entitlement shall not give rise to any Contractor’s claim for delay and additional cost [pursuant to Sub-Clause 20.1 (Contractor’s Claims) of the Conditions of Contract] in relation thereto.

C1.2.4 	APPENDIX 2 TO CONTRACT DATA:  APPROVAL DATA

The Contractor’s Documents requiring approval pursuant to Sub-Clause 5.2 and the provisions and requirements of the Contract include:

C1.2.4.1	All Contractor’s documentation related to his quality assurance system, OHS and environmental plans,

C1.2.4.2	The functional specifications, testing procedures, software executable release plans and as-built documentation in relation to the Design-Build,

C1.2.4.3	The Operation and Maintenance Plan,

C1.2.4.4	The Operation and Maintenance Manuals related to the Operation Service,

C1.2.4.5	The Maintenance Manuals related to the Maintenance and Support Services,

C1.2.4.6	Design-Build documents requiring approval in terms of the Employer’s Requirements, and

C1.2.4.7	Operation Service documents requiring approval in terms of the Employer’s Requirements.

C1.2.5	APPENDIX 3 TO CONTRACT DATA:  INSURANCE DATA

The following insurance obligations and data shall apply in relation to the corresponding Sub-Clauses of the Conditions of Contract:

Delete the entire Clause 19 and replace with the following:

19.1 Contractor’s Insurance

Without in any way limiting or derogating from the obligations, liabilities or responsibilities of the Contractor, the Contractor shall effect and maintain for the duration of this Contract such insurances as the Contractor considers sufficient to adequately cover its risks and liabilities and obligations associated with this Contract.

All such insurances shall be effective from the Commencement Date and maintained in force until the Termination Date or Contract Completion Certificate, as applicable.

Within 14 (fourteen) days of the Commencement Date, or as stated in the Contract Data and on the annual anniversary of this Contract and at any other time, during the existence of this Contract, as required by the Employer the Contractor shall submit to the Employer for the Employer’s approval, which shall not be unreasonably withheld, detail of all such insurances, existing or proposed. The approval of the Employer shall not in any way constitute a waiver to any of its rights in terms of the Contract and the Contractor shall at all times comply fully with its obligations under this Contract.

Such detail shall as a minimum, in respect of each separate insurance, include:

a) confirmation and proof that the Employer is named as an additional insured under the policies;

b) the extent to which the Employer is indemnified by the insurance;

c) confirmation that a "cross liability" clause is included;

d) the identity of the insurers and re-insurers;

e) a description of the cover provided, with detail of the principal extensions of cover;

f) where relevant, a description of the insured property;

g) the relevant period of insurance, showing the next renewal date;

h) the sums insured and/or indemnity limits and whether these apply per occurrence of indemnifiable loss or for the period of insurance;

i) the amount and application of deductibles/excesses/first amounts payable;

j) the principal exclusions;

k) an undertaking from the Insurers that any:

i. restriction or limitation of the cover provided;

ii. change to the period of insurance;

iii. reduction in the sums insured and/or limits of indemnity or;

iv. notice of cancellation or non-renewal

will be provided to the Employer at least 60 (sixty) days before the effective date of such event;

l) an undertaking pursuant to Clause 19.1(k) from the Contractor’s insurance brokers.

Whenever so required by the Employer, the Contractor shall provide to the Employer:

a) full copies of such insurances; and

b) evidence or proof of any or all premium payments.

Details of insurance effected by the Employer in respect of the Employer Fixed Assets, Permanent Design-Build Assets provided by the Employer, and the cover that will be available to the Contractor is detailed in Clause 19.5. The Contractor shall be liable for all deductibles latent to these insurances. The Contractor shall determine the amount of the deductibles applicable under this insurance and shall review the scope and extent of cover available under the Employer’s insurance at each renewal date.

The Contractor’s Third Party Liability insurance shall provide protection against all third party claims arising out of or in connection with any activities relating to the Works including, inter alia:

a) loss, destruction or damage to real or personal property;

b) obstruction, loss of amenities, loss of use of land, water, building, property or right of way;

c) liability that may result from latent defects or removal or weakening of support to property;

d) injury to, or disease or death of persons; and

e) legal costs of insured parties in respect of claims.

The principal classes of insurance for consideration by the Contractor should include Public Liability, Professional Indemnity, Assets All Risks, Electronic Equipment, Business Interruption, Money, Fidelity Guarantee and Sasria perils.

The Contractor shall review the scope and extent of cover limits to cater for any relevant change in the exposures to loss damage or liability on either each annual anniversary of the Commencement Date of the Contract or the anniversary of the relevant insurances. Any proposed changes to the insurances arising from such review shall require the approval of the Employer.

The Contractor shall comply and ensure that its sub-contractors of all tiers comply with the terms and conditions of all insurances effected in accordance with this sub-clause 19 and the procedures for claims notification and registration thereunder and shall do nothing or omit to do anything which might prejudice such insurances.

The Contractor shall submit the declaration of insurance.

PCC19.2 The Employer’s Right to Insure

If the Contractor fails or refuses to comply with its obligations under this Clause 19, the Employer shall, without prejudice to any of its rights hereunder or otherwise and subject to giving the Contractor prior notice allowing the Contractor a reasonable period not exceeding 14 (fourteen) days to comply with such obligations, be entitled to affect such insurances itself and recover the premiums and all reasonable administrative and other expenses of doing so by calling on the Performance Security and/or from the Contractor as a debt.

PCC19.3 Notification of Claims

The Contractor shall give the Employer immediate notification (with a copy to the Employer’s Representative) of any claim under any of the insurances effected in accordance with this Clause 19 and provide, at its own cost, to the Employer copies of all exchange of correspondence between the Contractor and the insurers and/or loss adjusters in regard to any ongoing or intended claims under any such circumstances.

PCC19.4 Contractor’s obligation to restore the Site

Subject to the provisions of the Employers Requirements, if any loss or damage to the Site or any part thereof is occasioned by any one or more of the perils insured against by the insurances referred to in this Clause 19, the Contractor shall, notwithstanding that settlement of any insurance claim has not been completed, with due diligence, repair or replace the Site, remove and dispose of any debris and proceed with the execution of the Works in accordance with this Contract.

The Contractor shall indemnify and keep indemnified the Employer against all loss or claims arising out of the default of or failure by the Contractor to comply fully with its obligations under Clause 19. Without prejudice to any right or remedy that the Employer may have in law or in terms of this Contract, the Employer shall be entitled to call on the Performance Security.

PCC 19.5: Employer’s Insurance

Details of insurance effected by the Employer in respect of the Employers Facilities, Permanent Design-Build Assets and Equipment provided by the Employer, shall be provided at the Commencement date of the Contract.

In general, the Employer’s insurance covers all Employer facilities, provided by and/or replaced by the Employer and/or the Contractor, for the duration of the contract.  The deductible for each and every loss, per incident/event shall be payable by the Contractor to the Employer.  There is no premium payable by the Contractor for this cover.

The Assets All Risks Insurance Policy effected by the Employer covers all Permanent Design-Build Assets sub-clause provided and/or replaced by the Employer and/or Contractor for the duration of the contract. The deductible for each and every loss is payable by the Contractor.  The policy may include an increased deductible in respect of accidental damage or through negligence by the Contractor and/or Subcontractor/Agents.  There is no premium payable by the Contractor for this cover.

The Finite and Assets All Risks Insurance Policies which are renewable annually currently provide protection against loss of or damage to the Employer property caused by perils including, but not limited to fire, lightning, explosion, storm, tempest, flood, earthquake, impact, and such risks and perils as are insurable by the South African Special Risks Insurance Association. The deductibles and/or policy coverage may change on an annual basis and it is incumbent on the Contractor to establish whether there have been any changes to the deductibles and/or policy coverage on an annual basis as the Contractor will in the event of an admissible claim be responsible for the payment of the policy deductible.

Table 2: EMPLOYER’S EQUIPMENT

| Asset | Replacement value | Max Deductible |
| --- | --- | --- |
| Hardware, Software and equipment | R 15 million | R100,000 |
| Software | Included in above amount. | R100,000 |

The Contractor shall be included as an additional insured in terms of the Employer Insurance Policies.”

C1.3	PART B: PARTICULAR CONDITIONS SPECIAL PROVISIONS

C1.3.1	PART B:  THE PARTICULAR CONDITIONS OF CONTRACT: SPECIAL PROVISIONS

Notes to tenderer:

The International Federation of Consulting Engineers (“FIDIC”), Conditions of Contract for Design, Build and Operate Projects, First Edition 2008 (“GCC”), shall apply to this Contract.  The amendments and additions as set out below shall constitute the Special Provisions and shall be read in conjunction with the GCC.  In the event of any conflict between the provisions of GCC and these Special Provisions, the Special Provisions shall prevail.

The following additions and amendments shall be made to the GCC.  References to clause numbers are as they appear in the GCC.

SUB-CLAUSE 1.1.2:	“ASSET REPLACEMENT FUND”

Insert a second sentence to the definition:

“In the case of no Contract Data provided under this sub-clause 1.1.2, specifically confirming applicability, the Asset Replacement Fund and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.3:	“ASSET REPLACEMENT SCHEDULE”

Insert a second sentence to the definition:

“In the case of no Contract Data provided under this sub-clause 1.1.3, specifically confirming applicability, the Asset Replacement Schedule and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.8:	“COMMISSIONING CERTIFICATE”

Insert the following at end of the definition:

“… the commencement of the Operations Service Period, if applicable.”

SUB-CLAUSE 1.1.10:	“CONTRACT”

After ‘Letter of Acceptance’ on the last line of the paragraph add the following wording:

“… and any subsequent written supplementary agreement or amendment mutually agreed and legitimately signed by the Parties”

SUB-CLAUSE 1.1.15:	“CONTRACT PERIOD”

Delete this definition and replace with the following wording:

“means the period from the date notified under sub-clause 8.1 [commencement date] to the date stated in the Contract Completion Certificate.”

SUB-CLAUSE 1.1.30:	“DESIGN-BUILD PERIOD”

Delete the definition under this sub-clause and replace with the following wording:

“means the period from the Commencement Date to the date stated in the Contract Completion Certificate at the end of the Contract Period or the date stated in the last section Commissioning Certificate to be issued under the Contract.  Each Design-Build section shall have its own period of Design-Build or “Time for Completion” as defined in the Contract Data and on Completion of a Section Commissioning Certificate shall be issued for each section.  The Section Commissioning Certificate shall state the actual date of completion of the relevant section.  The Section Design-Build periods shall run concurrently with the Operation Service Period.

SUB-CLAUSE 1.1.36:	“EMPLOYERS REQUIREMENTS”

Delete the definition under this sub-clause and replace with the following wording:

“means all the books of Volume 2 (entitled Employers Requirements) of the Contract as may have been amended and/or expanded pursuant to Volume 3 and Volume 4 of the Contract and any additions and modifications made thereto in accordance with the Contract.  Such documents specify the purpose, scope and/or design and/or other technical criteria for the execution of the works and provision of operation services.”

SUB-CLAUSE 1.1.43:	“FINANCIAL MEMORANDUM”

Insert a second sentence to the definition:

“In the case of no Contract Data provided under this sub-clause 1.1.43, specifically confirming applicability, the Financial Memorandum and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.48:	“LETTER OF ACCEPTANCE”

After the heading insert the following words:

“Letter of Acceptance or Form of Acceptance” means the letter.”

SUB-CLAUSE 1.1.49:  	“LETTER OF TENDER”

After the heading insert the following words:

“Letter of Tender or Form of Offer” means the document

SUB-CLAUSE 1.1.51:	“MAINTENANCE RETENTION FUND” AND “MAINTENANCE RETENTION GUARANTEE”

Insert a second sentence to the definition:

“In the case of no Contract Data provided under this sub-clause 1.1.51, specifically confirming applicability, the Maintenance Retention Fund and Maintenance Retention Guarantee and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.58:	“OPERATION SERVICE PERIOD”

Delete this definition and replace with the following:

“means the period commencing on the date contemplated in the Section Commissioning Certificate in respect of Section 1 stipulated in the Contract Data and ending third (3rd) anniversary of the commencement of the Operation Service Period, - Section 1 unless extended by the Employer in accordance with sub-clause 10.8 [Completion of Operation Service Period].“

SUB-CLAUSE 1.1.65:	“RETENTION MONEY”

Insert a second sentence to the definition:

“In the case of no Contract Data provided under this sub-clause 1.1.65, specifically confirming applicability, Retention Money and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.66:	“RETENTION PERIOD”

Insert a second sentence to the definition:

“In the case of no Contract Data under this sub-clause 1.1.66, specifically confirming applicability, the Retention Period and associated contractual provisions shall not apply to the Contract.”

SUB-CLAUSE 1.1.78:	“TIME FOR COMPLETION OF DESIGN-BUILD”

Insert after the words ‘Commencement Date’ the following additional wording:

“or any other date(s) stipulated in the Contract Data”

SUB-CLAUSE 1.1.72:	“SITE”

Add a second sentence to the definition:

“The extent of the site for the Design-Build and for Operation Service Period shall include the toll plazas with associated assets and is indicated in the drawings included in the Employer Requirements.”

SUB-CLAUSE 1.1.82:	“WORKS”

Delete this definition and replace with the following:

“means the Permanent Works [including assets related to plant, materials and Contractor’s documents as appropriate] and Temporary Works [including assets relating to temporary Contractor’s facilities, pursuant to Sub-clause 1.16 [Project Assets] or either of them as appropriate and the facility [including assets relating to Employer’s Facilities and Contractor’s facilities as appropriate, pursuant to sub-clause 1.16 (Project Assets)] to be operated by the Contractor during the Operation Service Period."

After Sub-clause 1.1.83, insert the following new definitions:

“SUB-CLAUSE 1.1.84:  EMPLOYER’S DOCUMENTS:	means the calculations, computer programs and other software, drawings, manuals, models and other documents supplied by the Employer under the Contract; which are also referred to in sub-clause 1.12 [Contractor’s Use of Employer’s Documents] and sub-clause 1.16 [Project Assets] and as detailed in the Employer’s Requirements;”

“SUB-CLAUSE 1.1.85:  EMPLOYER’S FACILITIES:	means those facilities made available by the Employer to the Contractor for purposes of the Works and the Operation Service and includes the Employer’s Fixed Assets, Employer’s Equipment and Employer’s Documents; which facilities are also referred to in sub-clause 1.16 [Project Assets], sub-clause 4.26 [Use of Employer’s Facilities] and as detailed in the Employer’s Requirements;”

“SUB-CLAUSE 1.1.86:  EMPLOYER’S FIXED ASSETS:	means generally but not necessarily, the Employer’s fixed type of infrastructure associated with civil works, structural works, building, electrical and mechanical assets and as detailed in the Employer’s Requirements.”

“SUB-CLAUSE 1.1.87:  NOMINATED SUBCONTRACTOR	means any person named in the Contract as a Nominated Subcontractor, or any person appointed as a Nominated Subcontractor, for a part of works; and the legal successor in title to each of these persons.”

SUB-CLAUSE 1.2:	“INTERPRETATION”

At the end of this sub-clause 1.2, insert the following sentence:

“Reference to a person shall include a natural person, a juristic person and any unincorporated association.”

SUB-CLAUSE 1.3:	“NOTICES AND OTHER COMMUNICATIONS”

At the end of this sub-clause 1.3, insert the following paragraph:

“Any notice, consent, approval, certificate or determination by any person shall not be deemed to have been given or issued by virtue of its appearance in the minutes of any meeting or in the content of an e-mail message.  For the avoidance of doubt, e-mail messages, although permitted for the purposes of informal communications, shall not constitute contractual correspondence or be used to gain benefit under the Contract.”

SUB-CLAUSE 1.5:	“PRIORITY OF DOCUMENTS”

Delete the wording under this sub-clause and replace with the following:

“The documents forming the Contract are to be taken as mutually explanatory of one another. For the purposes of interpretation, the priority of the documents, as may have been amended during tender stage, shall be in accordance with the following sequence:

- The Contract Agreement (if any);

- The Letter of Acceptance; [ Form of Acceptance]

- The Letter of Tender; [Form of Offer]

- The Particular Conditions Part A – Contract Data;

- The Particular Conditions Part B – Special Provisions;

- The General Conditions;

- Any additions or modifications to the Employer’s Requirements pursuant to Volume 3 and Volume 4 of the Contract.

- Volume 2 entitled “Employer’s Requirements”, which for purposes of interpretation shall be in accordance with the following sequence –

i)	Volume 2 Book 1a – Standard Specification for Operations and Maintenance of CTROM Projects:  Part A:  Glossary of Terms and Part B:  Generic Scope of Works

ii)	Volume 2 Book 2a – Standard Specification for Operations and Maintenance of CTROM Projects: General

iii)	Volume 2 Book 7a - Standard Specification for Operations and Maintenance of CTROM Projects: Payment Methodology and Description of Payment Items

iv)	Volume 2 Book 6a - Standard Specification for Operations and Maintenance of CTROM Projects: Performance Measurement

v)	Volume 2 Book 8a - Standard Specification for Operations and Maintenance of CTROM Projects: ETC Interoperability – Business Rules

vi)	Volume 2 Book 4a – Standard Specification for Operations and Maintenance of CTROM Projects: Toll Systems

vii)	Volume 2 Book 5 – Standard Specification for Operations and Maintenance of CTROM Projects: Electronic Toll Collection (ETC)

viii)	Volume 2 Book 3 – Standard Specification for Operations and Maintenance of Toll Projects: Electrical and Mechanical Equipment

- The Schedules of Payment/Cost Matrix; and

- The Contractor’s Proposal.

If an ambiguity or discrepancy is found in the documents, the Employer’s Representative shall issue any necessary clarification or instruction, save that where this relates to the Employer’s Requirements; the following principles shall also apply:

  - If any provision of the Employer’s Requirements imposes a standard or duty that is more onerous than, or additional to that imposed by another provision of the Employer’s Requirements, this will not be considered as an error, inconsistency, discrepancy or ambiguity and the relevant standard or duty will be treated as cumulative, failing which the more onerous standard or duty will apply;

  - If any ambiguity or discrepancy is found between a provision in one book and a provision of another book of the Employer’s Requirements, the provision of the book with the highest priority shall prevail, unless the application of the provision in the other book will, as clarified or instructed by the Employer’s Representative, result in a higher standard and/or will result in Works or Operation Service which are most beneficial to the Employer, then in such circumstances the provision of the other book shall prevail;

  - If any ambiguity or discrepancy is found between the provisions of any single book of the Employer’s Requirements, the provisions which results in a higher standard and/or result in Works or Operation Service which is safer or more conservative and/or will result in works which are most beneficial to the Employer shall prevail;

  - The aforementioned shall not constitute an error in the Employer’s Requirements for purposes of Clause 1.10 and the provisions thereof shall not apply hereto and accordingly such ambiguity or discrepancy shall be resolved solely by the necessary clarification or instruction issued by the Employer’s Representative;

  - The Contractor having had the opportunity to negotiate the Employer’s Requirements (where applicable), the contra preferentum rule shall not be applied in the interpretation of the Employer’s Requirements.

No above-mentioned ambiguity or discrepancy shall vitiate this Contract.”

SUB-CLAUSE 1.9:	“CARE AND SUPPLY OF DOCUMENTS”

At the end of the sub-clause insert new paragraphs which read as follows:

“In case of Contractor’s Documents which are in the form of computer programs and other software, the Contractor shall place and maintain the same in ESCROW, in accordance with the Employer’s Requirements.

In the case of Employer’s Documents and/or in the case of expansions, upgrades, replacements, modifications and the like to Employer’s Documents (as part of the Contractor’s Design-Build and / or Operation Service obligations), which Employer’s Documents are in the form of computer programs and other software, the Contractor shall place and maintain the same in ESCROW, in accordance with the Employer’s Requirements.

In the case of integrated computer program and other software systems, consisting of Employer’s Documents and Contractor’s Documents, such integrated software systems shall be placed and maintained in ESCROW by the Contractor, in accordance with the Employer’s Requirements.”

SUB-CLAUSE 1.11:	“EMPLOYER’S USE OF CONTRACTOR’S DOCUMENTS”

At the end of paragraph 2 of this sub-clause and after sub-paragraph (d) insert the following:

“and;

(e)	enable the Employer to take over the whole or part of the Works and effectively operate and maintain the Works or any part thereof; and

(f)	enable the Employer, at the end of the Operation Service Period, to appoint any other person/s for purposes of effectively operating and maintaining the Works or any part thereof; and

(g)	transfer to the Employer the right to the use and/or licenses in respect of any computer programs, software, design documents, codes and information of which a party, other than the Contractor, holds proprietary rights and/or copy right to enable the Employer to effectively operate and maintain the Works or to appoint another person/s to operate and maintain the Works or any part thereof; and

(h)	enable the Employer to incorporate any other toll roads or associated national systems, in the Republic of South Africa, into the Works.”

(f) 	The Employer may, at agreed fee, purchase the source code so that it includes a perpetual license in favour of SANRAL, which license shall include the entirety of the current and future SANRAL toll routes.

(i) 	License fees in respect of any additions or extensions beyond the scope of the current Contract shall be negotiated at that time.

(ii)	SANRAL shall have the right to use, modify, implement, support and/or maintain the Software as it sees fit for use at any of its entirety of the current and future SANRAL toll routes.

iii) 	The Contractor shall be afforded the first option to quote on future modification, implementation, support and/or maintenance of the Software; however, the appointment of a service provider to perform any works in respect of the Software shall be at SANRAL’s sole discretion.

(iv) 	The Contractor shall have the right of commercial use of the adapted Software (locally and internationally).

(v) 	Intellectual Property shall remain vested in the Contractor.

SUB-CLAUSE 1.12:	“CONTRACTOR’S USE OF EMPLOYER’S DOCUMENTS”

Insert the following new paragraphs at the end of this sub-clause 1.12 that read:

“In the case of Employer’s Documents which are in the form of computer programs and other software, the Contractor shall:

take-over, operate, maintain, resolve defects, modify, expand, replace, dispose, upgrade and hand-back such documents in accordance with the Operating License, and relevant parts of the Conditions of Contract and the Employer’s Requirements; and

in the case of access by the Contractor to such documents be restricted or prevented, in relation to proprietary and intellectual / copy rights of other parties, then the Contractor shall perform and implement all things necessary at his expense to ensure compliance to the Conditions of Contract and the Employer’s Requirements.  For the avoidance of doubt, such case shall not imply any excuse, or right to claim, or relieve for the Contractor being unable to meet the associated risks, liabilities, obligations and Employer’s Requirements under the Contract.”

After Sub-clause 1.15, insert a new Sub-clause 1.16 with the following wording:

“SUB-CLAUSE 1.16:	PROJECT ASSETS”

The complete project assets consist of:

- Employer’s Facilities

The Employer’s Facilities are those on-Site assets, whether of a permanent or temporary nature, made available by the Employer to the Contractor for purposes of the Works and the Operation Service under the Contract.  The Employer’s Facilities are those taken over and used by the Contractor in accordance with sub-clause 4.26 [Use of Employer’s Facilities], are detailed in the Employer’s Requirements and consist of:

Employer’s Fixed Assets (as defined in the Conditions of Contract and generally, but not necessarily, of a fixed asset type),

Employer’s Equipment (as defined in the Conditions of Contract and generally, but not necessarily, of a semi-fixed asset type and/or hardware system nature), and

Employer’s Documents (as defined in the Conditions of Contract and generally, but not specifically, of a documentation and software system asset type); and

- Permanent Design-Build assets

The permanent Design-Build assets are generally on Site assets and are those assets designed, built, operated and handed back (at the end of the Contract Period) by the Contractor for the purposes of the Works and Operation Service under the Contract, as specified and detailed in the Employer’s Requirements and consist of:

  - Plant (as defined in the Conditions of Contract and generally, but not necessarily, of a semi-fixed asset type and/or hardware system nature),

  - Materials (as defined in the Conditions of Contract and including assets such as the levels of spares, as specified in the Employer’s Requirements or provided in accordance with recognized good practice for the purpose of maintaining Employer’s Facilities, Plant and Contractor’s Documents), and

  - Contractor’s Documents (as defined in the Conditions of Contract and generally, but not necessarily, of a documentation and software system asset type); and

- Contractor’s facilities

The Contractor’s facilities include all other facilities / assets, whether of a permanent or temporary nature and whether on or off Site [in addition to those listed under this sub-clause 1.16 (a), (b) and (d)] made available by the Contractor and required to complete the Works and to perform the Operation Service under the Contract.; and

- Contractor’s Equipment (as defined in the Conditions of Contract and generally, but not necessarily, of a movable asset type).”

Add the following new clause after Sub-clause 1.16:

“SUB-CLAUSE 1.17:	THE MAIN CONTRACT

“The Employer (In this case the Main Contractor) shall make the Main Contract (other than the confidential details of the Main Contractor’s prices and the confidential parts of the Main Contract when so identified and agreed) available for inspection to the Nominated Subcontractor.  The Main Contractor shall provide the Nominated Subcontractor with a copy of Part C1 of the Main Contract and details of any other contractual provisions which may apply to the Main Contract and differ from the General Conditions of Contract of the Main Contract.

The Nominated Subcontractor shall be deemed to have full knowledge of the relevant provisions of the Main Contract (save for the confidential details).

The Nominated Subcontractor shall promptly give notice to the Employer (In this case the Main Contractor) of any ambiguity or discrepancy which he discovers when reviewing this Contract (the Nominated Subcontract) and the Main Contract or executing the Works.”

Add the following new clause after Sub-clause 1.17:

“SUB-CLAUSE 1.18	COMPLIANCE WITH THE MAIN CONTRACT

“The Nominated Subcontractor shall, in relation to the Works (as described in the Employer’s Requirements), perform and assume all the obligations and liabilities of the Main Contractor, save that the Nominated Subcontractor shall have no obligations in respect of:

- Main Contract Clause 4.7 [Setting Out]

- Sub paragraphs (d) and (e) of the Main Contract Clause 4.8 [Safety Procedures]

- Main Contract Clause 4.9 [Quality Assurance]

- Main Contract Clause 4.13 [Rights of Way and Facilities]

- Sub-paragraphs (a) and (b) of Main Contract Clause 4.15 [Access Route]

- Main Contract Clause 4.19 [Electricity, Water and Gas]

- Sub-paragraphs (a) of Main Contract Clause 4.22 [Security of the Site]

- Main Contract Clause 7.8 [Royalties]

- Overall co-ordination and project management of the Main Works; and

- Those exclusions (if any) set out elsewhere in the Contract.”

Add the following new clause after Sub-clause 1.18:

“SUB-CLAUSE 1.19	INSTRUCTIONS AND DETERMINATIONS UNDER THE MAIN CONTRACT

“The Nominated Subcontractor shall, in relation to the Works (as described in the Employer’s Requirements), comply with all Notices, instructions and determinations issued under the Main Contract and which are copied to him, irrespective that such Notices, instructions and determinations were not directly issued under the Nominated Subcontract. When the Nominated Subcontractor receives any direct Notice, instruction or determination from the Principal Employer or the Main Contract’s Employer’s Representative:

- He shall immediately inform the Main Contractor’s Subcontract Representative (in this case the “Employer’s Representative” of the Nominated Subcontract) and shall supply him with a copy of such direct correspondence if given in writing; and

- He shall have no obligation to comply with any such direct instruction unless and until it has been confirmed in writing by the Main Contractor’s Subcontract Representative as an instruction under this Contract.

If any Notice, instruction or determination of the Employer’s Representative constitutes a Variation, Clause 13 [Variations and Adjustments] shall apply.

“SUB-CLAUSE 1.8     ASSIGNMENT

Replace the whole clause with the following:

“1.8 Assignment

Neither Party shall assign the whole or any part of the Contract and may not transfer its rights and obligations in or under the Contract.

However, either Party may, Cession its right to payment of any moneys due, or to become due, under the Contract, only in the event that:

    - the Cession is in favour of a registered Financial Services Provider (FSP) or a State Institution established for the express purpose of providing funding to businesses and entities; and

    - the written request for Cession is made by the Party and not a third party; and

    - the written request by the Party is accompanied by a cession agreement; and

    - the other Party agrees to the Cession.”

SUB-CLAUSE 2.1:	“RIGHT OF ACCESS TO THE SITE”

At the end of paragraph 1, insert the following:

“The Contractor shall liaise and fully co-operate with any other contractor appointed by the Employer, in order to gain access to the Site or any part thereof.”

After paragraph 2, insert the following:

“The Contractor shall not, whether directly or indirectly, cause the closure of any public road or any lanes forming part of a public road.  If and when the Contractor requires access to the Works or any part thereof which will necessitate the closure of a public road or lanes forming part of a public road, he shall notify the Employer’s Representative, who shall, as soon as is reasonably possible, arrange for the closure of such road or lanes as is reasonably necessary to allow access to the Site or part thereof.

SUB-CLAUSE 4.2:	“PERFORMANCE SECURITY”

Replace the wording of the second paragraph under this sub-clause 4.2 with:

“The Performance Security includes all guarantees / bonds and the like and the renewals, replacements or extensions thereof as required to meet the Performance Security obligations and requirements.

The Contractor shall renew the Performance Security whenever the amount of it changes due to the contractual requirements.  The amount of the Performance Security shall have been adjusted, not later than its expiry or 90 (ninety) days after each anniversary of the Commencement Date in accordance with sub-clause 13.8 [Adjustments for changes in Costs].

Replace the wording of the fourth paragraph under this sub-clause 4.2 with:

“The Contractor shall ensure that the Performance Security remains valid and enforceable until 120 days after the date of the issue of the Contract Completion Certificate or 90 days after the Date of Termination.

Failure by the Contractor to maintain the validity of the Performance Security shall be grounds for termination in accordance with sub-clause 15.2 [Termination for Contractor’s Default].

Replace the wording in sub-clause 4.2 (a) with:

“ (a) 	in the case of a renewal, extension or replacement of the Performance Security required to meet the Performance Security obligations and requirements and failure by the Contractor to renew, extend or replace such Performance Security prior to a date determined at, 21 days prior to the expiry or invalidity of the Performance Security, in which event the Employer may claim the full or, in case of an earlier reduction, the reduced amount of the Performance Security;”

Below sub-paragraph (d), insert a new sub-paragraph (e) with the following wording:

“or circumstances which entitle the Employer under sub-clause 12.1 (Completion of Outstanding Work and Remedying Defects].”

Replace the wording of the last paragraph in this sub-clause 4.2 with:

“The Employer shall return the Performance Security to the Contractor within 21 days after the valid expiry date(s) thereof.”

SUB-CLAUSE 4.4:	“SUBCONTRACTORS”

At the end of sub-clause 4.4, insert the following:

“Every subcontract entered into between the Contractor and any Subcontractor shall contain the following provisions:

The Subcontract shall be able to be ceded and assigned and to be transferred, including all rights and obligations and in favour of the Employer who shall notify the subcontractor within 21 days of entering into any cession or assignment or transfer; and

The Subcontractor shall be deemed, by signing this subcontract, to give the Main Contractor and the Principal Employer a non-terminable, transferable, non-exclusive royalty free license to copy, use and communicate the Subcontractor’s documents for purposes of the Works and the Operation Service.  This license shall:

- apply throughout the actual or intended working life (whichever is the longer) of the relevant part of the Works; and

- entitle any person, in lawful possession of the relevant part of the Works, to copy, use and modify the Subcontractor’s documents for purposes of completing, operating, maintaining, altering, adjusting, repairing and/or demolishing the Works; and

- in the case of the Subcontractor’s documents, which are in the form of computer programs and other software, permit the use thereof on any computer on the Site, or any other place envisaged in this Contract, including the replacement, upgrading or expansion of any software supplied by the Contractor and/or the Employer; and

- enable the Contractor to transfer all rights to the Employer and enable the Employer to re-let the Contract; and

- enable the Employer to take over the whole or part of the Works and effectively operate and maintain the Works or any part thereof; and

- enable the Employer, at the end of the Operation Service Period, to appoint any other person/s for purposes of effectively operating and maintaining the Works or any part thereof; and

- transfer to the Employer the licenses and/or the right of use in respect of any computer programs, software, design documents, codes and information of which a party, other than the Subcontractor, holds proprietary rights and/or copyright so as to enable the Contractor and/or Employer to effectively operate and maintain the Works or appoint another person/s to operate and maintain the Works or any part thereof; and

- enable the Employer to incorporate any other toll roads or national systems, in the Republic of South Africa, into the Works.

The Subcontractor shall ensure that, where necessary, the consent and/or license for the use of any design, computer program, software and other documents, which may be required for the effective operation and maintenance of the Works, are obtained in favour of the Main Contractor and the Principal Employer.”

SUB-CLAUSE 4.20:	“EMPLOYER’S EQUIPMENT AND FREE-ISSUE MATERIALS”

Delete the wording in this sub-clause 4.20 and insert the following:

“The Employer shall make the Employer’s Equipment available for the use of the Contractor in the execution and operation of the Works in accordance with the details and arrangements stated in the Employer’s Requirements and Contractor’s approved programme pursuant to sub-clause 8.3 [Programme] of the Conditions of Contract.

The Contractor shall be responsible for each item of Employer’s Equipment whilst the Contractor is in possession and control of it.

The Employer shall supply, free of charge, the “free-issue materials” (if any) in accordance with the details stated in the Employer’s Requirements.”

After sub-clause 4.25, insert a new Sub-Clause 4.26, which reads as follows:

“SUB-CLAUSE 4.26	USE OF EMPLOYER’S FACILITIES

The Employer shall transfer to the Contractor the Employer’s Facilities, as described in the Employer’s Requirements, for purposes of the Contractor undertaking the Works and Operation Service.

The Contractor shall, promptly after having received right or shared right of access to the Site where the Employer’s Facilities are located, commence to inspect the facilities and shall within 90 days of the date of inspection of the Employer’s Facilities, notify the Employer’s Representative of any defects, shortages or defaults in these facilities.  Unless otherwise agreed by the Parties, the Employer shall within a reasonable period rectify the notified shortages, defects or defaults.

After the inspection by the Contractor and immediately upon having received right of possession of the Employer’s Facilities, the Contractor shall take custody and control of the facilities and be responsible for the operation, maintenance and care of the Employer’s Facilities in accordance with the Employer’s Requirements for the remainder of the Contract Period.

The risk of any loss or damage to the Employer’s Facilities, save for ‘Employer’s Fixed Assets’ as described in sub-clause 1.16 (Project Assets) and as otherwise stated in the Employer’s Requirements, shall be borne by the Contractor.”

SUB-CLAUSE 6.1:	“ENGAGEMENT OF STAFF AND LABOUR”

At the end of this Sub-Clause add the following:

“The Contractor shall give effect to the Laws of the Country and specifically relating to Broad Based Black Economic Empowerment and Employment Equity.”

SUB-CLAUSE 6.4:	“LABOUR LAWS”

At the end of this sub-clause, insert the following:

“At the end of the Operation Service Period or in the event of early termination of the Contract, the Employer may or re-let the Contract or any part thereof to another/other person/s and should such action constitute a transfer of business, the old and the newly appointed Contractor should adhere to the provisions of Section 197 of the Labour Relations Act 1995 (Act 66 of 1995) or any amendment or replacement thereof and shall take such steps as may be necessary to facilitate the transfer of business. In the event that the early termination or re-let of the Contract doesn’t warrant a Section 197 transfer, the Contractor is obliged to comply to the applicable provisions of the Labour Relations Act including section 189 or any other employment laws

SUB-CLAUSE 6.9:	“CONTRACTOR’S PERSONNEL”

Add the following to this sub-clause:

“The Contractor is to make provision for any costs incurred due to the employment of the following personnel with the required qualifications and training.

| PERSONNEL CATEGORY | REQUIRED QUALIFICATION AND TRAINING |
| --- | --- |
| 1. Assistant Technician (Electronic) | HEQSF* level 5 (Referring to a minimum qualification of a higher certificate or advanced certificate) in electronics or similar Basic electricity safety awareness Six months practical experience |
| 2. Technician (Electronic) | HEQSF* level 6 National Diploma in Information Technology, Computer Engineering, Digital Technology or Instrumentation and Process Control or similar accredited diploma Preferably registered with the Engineering Council of SA (ECSA) or similar accredited institution Minimum one year experience in similar technical field or proof of logbooks from practical period for Diploma Extensive knowledge in electricity safety Access to transport between Plazas with a valid driver’s licence |
| 3. Senior Technician (Electronic) | HEQSF* level 6 National Diploma in Information Technology, Computer Engineering, Digital Technology or Instrumentation and Process Control or similar accredited diploma Preferably registered with the Engineering Council of SA (ECSA) or similar accredited institution Minimum of three years related technical experience Extensive knowledge in electricity safety Access to transport between Plazas a valid driver’s licence Minimum of 2 years experience in managing staff and resources |
| 5. Construction Health and Safety Officer | NQF Level 6 National Diploma in Safety Management (NDS MN) equivalent training course as a minimum qualification. Preferably registered with the South African Council for the Project and Construction Management Professions (SACPMP). Minimum five (5) years of experience with regards to implementing and maintaining a health and safety management system compliant. Access to transport between Toll Plazas with a valid driver’s licence. |

Note:	*Reference to the Engineering Qualifications and the Higher Education Qualifications sub-framework (HEQSF) presentation by ECSA (http://www.sasee.org.za/CMS/WP-content/uploads/2014/07/HEQSF-And-Engineering-Qualifications-B-van-Wyk.PDF

SUB-CLAUSE 7.7:	“OWNERSHIP OF PLANT AND MATERIALS”

At the end of this clause, insert the following:

“To the extent that the Contractor is unable, for any reason whatsoever, to transfer ownership in and to any item of Plant, the Contractor hereby grants the Employer a license, in perpetuity, to use such Plant.  The license of use shall be in accordance with the terms and conditions as in respect of the Employer’s use of the Contractor’s Documents as set out in clause 1.11 [Employer’s use of Contractor’s Documents].”

SUB-CLAUSE 8.1:	“COMMENCEMENT DATE”

Delete Sub-clause 8.1 and replace with the following:

“The Employer shall give notice stating the Commencement Date to the Contractor not less than 7 days prior to the Commencement Date.  Unless otherwise stated in the Particular Conditions, Commencement Date shall be within 28 days after the issue of the Letter of Acceptance.”

SUB-CLAUSE 8.3:	“PROGRAMME”

Replace the first sentence of this sub-clause 8.3 with the following new wording:

The Contractor shall submit detailed time programmes to the Employer’s Representative within:

“5 days” after receiving the Notice under sub-clause 8.1 [Commencement Date] for the purpose of Section 1; and

“21 days” after receiving the Notice under sub-clause 8.1 [Commencement Date] for the purpose of Sections 2, 3 and 4; and

“14 days” after receiving a Notice that triggers the commencement date for any ad-hoc Section or any major activity to be performed by the Contractor during the Operation Service Period.

Each programme shall be compiled using the software as set out in the Contract Data.”

After sub-paragraph (e) (iii), insert (iv) which reads as follows:

(e)	 “and shall clearly identify the critical path”

At the end of paragraph 1, insert the following sub-paragraph: -

“(f)	shall identify key milestone areas and target dates as contained in the Employer’s Requirements and Contractor’s Proposal.”

SUB-CLAUSE 8.6:	“CONTRACT COMPLETION CERTIFICATE”

The third line of the first paragraph to be modified to read as follows:

“…. the Contract Completion Certificate has been signed by the Employer and issued to the Contractor….”

Amend the existing paragraph 2, by deleting the last sentence and replacing the same with the following:

“The Employer may exercise the option referred to in sub-clause 10.8 [Completion of Operation Service] to extend the Operation Service Period.”

Insert a paragraph at the end of this sub-clause 8.6 that reads:

“The Contractor shall render his full co-operation and provide sufficient shared access to the operations, resources and project assets [as described in sub-clause 1.16 (Project Assets)] associated with the Works and do all things necessary to assure that the next contractor / person is in a position to comply with similar Design-Build and establishment obligations and requirements applicable to Section 1 of this Contract.”

SUB-CLAUSE 9.1:	“COMMENCEMENT OF DESIGN-BUILD”

In the first sentence, replace the words “28 days” with “5 days”.

SUB-CLAUSE 10.2:	“COMMENCEMENT OF OPERATION SERVICE PERIOD”

Delete Paragraph 1 of this sub-clause and replace with the following:

“The Operation Service Period shall commence on the date stated in the Section Commissioning Certificate issued in respect of Section 1.”

SUB-CLAUSE 10.3:	“INDEPENDENT COMPLIANCE AUDIT”

Delete this sub-clause 10.3 and replace with the following:

“Either Party may or both Parties may jointly, at any point when circumstances warrant, elect to appoint an Auditing Body to carry out an independent and impartial audit during the performance of the Operation Service.  The terms of the appointment of an Auditing Body shall be in accordance with the terms included in the Employer’s Requirements and the purpose will be to audit performance of either Party or both Parties in compliance with the Operation Management Requirements. In the case of a joint appointment where the Parties cannot agree on the appointment, the matter shall be referred to the / a DAB and the / a DAB shall make the appointment.

All reports issued by an Auditing Body shall be distributed to both Parties and both Parties shall cooperate with the Auditing Body and give due regard to the matters raised in each report issued by the Auditing Body.

In case of a joint appointment, each Party shall carry 50% of the cost of the Auditing Body.

In case of an appointment by either Party, the Party who made the appointment shall carry 100% of the cost of the Auditing Body.

All Auditing Body costs to be carried by the Contractor shall be deemed to be included in his Rates and Prices.”

SUB-CLAUSE 10.6:	“DELAYS AND INTERRUPTIONS DURING THE OPERATION SERVICE”

Replace the second sentence of sub-paragraph (a) with the following wording:

“The amount of the compensation due or performance adjustments to be made shall be calculated in accordance with the relevant Employer’s Requirements or as determined by the Employer’s Representative in accordance with sub-clause 3.5 [Determinations] and the Employer shall be entitled to make a corresponding adjustment to the next payment due to the Contractor.”

At the end of the wording of sub-paragraph (a), insert a new sub-paragraph that reads as follows:

“The amount of compensation that the Employer may recover as aforesaid shall be in addition to any payment adjustments which the Employer may be entitled to make by reason of the failure by the Contractor to reach the production outputs as contemplated in sub-clause 10.7 [Failure to Reach Production Outputs].”

SUB-CLAUSE 10.7:	“FAILURE TO REACH PRODUCTION OUTPUTS”

Delete paragraph 2 of sub-paragraph (b) and replace with the following:

“In these circumstances the Employer shall be entitled to apply a payment reduction in accordance with the performance criteria and measurements set out in the Employer’s Requirements.”

At the end of this sub-clause insert a new sub-paragraph that reads as follows:

“(c)	In the event that the Contractor exceeds the performance criteria set out in the Employer’s Requirements, the Contractor shall be entitled to payment of the performance incentives and/or bonuses (if any) as set out in the Employer’s Requirements.

Payment adjustment, negative or positive, shall be reflected in Payment Certificates as contemplated in sub-clause 14.7 [Issue of Advance and Interim Payment Certificates] and be deducted from or added to the payment to the Contractor

In this regard and for the avoidance of doubt, performance payment reductions shall first be made up to the maximum provided for in the Employer’s Requirements and thereafter the Employer shall be entitled to recover the actual loss suffered or incurred subject to sub-clause 3.5 [Determinations].”

SUB-CLAUSE 10.8:	“COMPLETION OF OPERATION SERVICE”

At the end of this sub-clause add the following:

“The Employer shall have the option to extend the Operation Service Period for a further period of 3, 6, 12 or 24 months.

The Employer’s Representative shall notify the Contractor, in writing, not later than 180 days prior to the end of the Operation Service Period, of the Employer’s intention to exercise such option to extend the Operation Service Period.  The price payable to the Contractor in respect of the extended Operations Service Period shall be calculated in accordance with the Rates and Prices quoted by the Contractor for the appropriate Operation Service and shall be adjusted in accordance with sub-clause 13.8 [Adjustments for Changes in Costs] hereunder.”

After sub-clause 10.9 add the following clause:

“SUB-CLAUSE 10.10:	ADVERTISING AND MARKETING AND ASSOCIATED INCOME

The Contractor shall be entitled to all income generated through direct mandating at the relevant sites such as handing out pamphlets, provided the direct marketing relates to a road safety initiative and subject to the prior approval of the Employer.

The Contractor shall report such income to the Employer on a monthly basis. Any other income generated through advertising on the site shall be for the benefit of and accrue to the Employer.”

SUB-CLAUSE 11.8:	“JOINT INSPECTION PRIOR TO CONTRACT COMPLETION”

In the first sentence in the first line replace the words “two years” with “180 days”.

SUB-CLAUSE 12.1:	“COMPLETION OF OUTSTANDING WORK AND REMEDYING DEFECTS”

Replace the wording of sub-paragraph (b) and the last paragraph of this sub-clause 12.1 with the following:

“(b)	Operation Service Period: Unless otherwise stated in the Employer’s Requirements, the Contractor shall be responsible for repairing and making good any damage or defect occurring during the Operation Service Period, whether such defect or damage is notified by the Employer or his Representative or observed by the Contractor himself.

In the case of all outstanding work, defects and damage, including all such items reported by the next Contractor and identified under sub-clause 11.8 [Joint Inspection Prior to Contract Completion] not completed or resolved by the Contractor at the time of the issue of the Contract Completion Certificate, the Contractor shall remain liable until completion thereof and the Employer shall be entitled to claim under sub-clause 4.2 [Performance Security].”

SUB-CLAUSE 12.2:	“COST OF REMEDYING DEFECTS”

Below sub-paragraph (b), insert a new sub-paragraph (c) with the following wording:

“(c) or where such risk and cost is specifically excluded by virtue of the Employer’s Requirements.”

In the last paragraph, insert after the words ‘or (b)’, the words “or (c)”.

SUB-CLAUSE 13.1	“RIGHT TO VARY”

In the first sentence delete words “at any time prior to issuing of the Commissioning Certificate” and replace with the following “during the Contract Period.”

In the third paragraph the term “proceed with variation” with the word “proceed with variation (save for provisional variation arising from Provisional Sums in the Schedule of Payments/Cost Matrix)”

SUB-CLAUSE 13.3	“VARIATION PROCEDURE”

The first sentence of the 2nd paragraph to be modified to read as follows:

“The Employer’s Representative shall, as soon as practicable after receiving such proposal (under sub-clause 13.2 [value Engineering] or otherwise) make a recommendation to the Employer to approve, disapprove or comment. Upon receipt of the Employer decision, the Employer Representative will notify the Contractor of the approval, disapproval or comments.  The Contractor ….”

SUB-CLAUSE 13.5:	“PROVISIONAL SUM”

The first sentence of the 1st paragraph to be modified to read as follows:

“The Employer will approve the usage of a Provisional Sum, in whole or in part and the contract price ….”

Delete the last sentence of sub-clause 13.5(b) (ii) and replace with the following:

“…. Appropriate schedule.  The maximum percentage allowed for each item is stated in the Contract Data.  If there is no such rate, the percentage shall be zero (0) and shall be applied to all scheduled and provisional sums added during the contract period.”

After sub-clause 13.8 insert the following new Sub-Clause 13.9 to read as follows:

“SUB-CLAUSE 13.9:	“ADJUSTMENTS FOR PERFORMANCE OUTPUTS”

“The amount payable to the Contractor shall be adjusted as contemplated by sub-clause 10.7 [Failure to Reach Production Outputs].”

SUB-CLAUSE 14.5:	“ASSET REPLACEMENT SCHEDULE”

Replace the wording under this sub-clause 14.5 with the following:

“Unless otherwise specified in the Employer’s Requirements, the Contractor shall be responsible for all project assets [as described in sub-clause 1.16 (Project Assets)] replacements and all associated costs in relation thereto, save for the Employer’s Fixed Assets of which replacements (if any) shall be effected by the Employer or as provided for in the Employer’s Requirements.”

SUB-CLAUSE 14.7:	“ISSUE OF ADVANCE AND INTERIM PAYMENT CERTIFICATES”

In the first paragraph of this sub-clause 14.7, replace the words ’28 days’ with the words “21 days”.

SUB-CLAUSE 14.8:	“PAYMENT”

In sub-paragraph (b) of this sub-clause 14.8, replace the words ’56 days’ with the words

“32 days”.

SUB-CLAUSE 14.10:	“PAYMENT OF RETENTION MONEY”

Delete the wording and insert the following:

“Void”

SUB-CLAUSE 14.18:	“ASSET REPLACEMENT FUND”

Delete the wording and insert the following:

“Void”

SUB-CLAUSE 14.19:	“MAINTENANCE RETENTION FUND”

Delete the wording and insert the following:

“Void”

SUB-CLAUSE 15.2:	“TERMINATION FOR CONTRACTOR’S DEFAULT”

In paragraph 1 at the end of sub-paragraph (c), insert the following:

“or;

(iii)	fails to proceed with and bring to completion the Design-Build parts of the Works, within the periods stated in the Contract Data.”

In paragraph 1 at end of sub paragraph (h), insert the following

“(i)	In the case of the Contractor default referred to under Clause 15.1, The Employer may terminate this Contract by notice in writing having immediate effect (with a copy to the Employer Representative).  Then the provision in Clause 15.3 and Clause 15.4 shall apply.

The Employer will also have the right to terminate any other Contract between the Employer and Contractor and not allow to tender on any future project put out to tender by the Employer for a period of five (5) years from the date of Notice, which period may be reduced by application to and at the sole discretion of the Employer.”

SUB-CLAUSE 15.5:	“TERMINATION FOR EMPLOYER’S CONVENIENCE”

Add the following paragraph after the first paragraph:

“Upon termination of the Main Contract, for whatever reason, this Nominated Subcontract may:

- also be terminated upon having received a Notice to such effect from the Principal Employer and/or Main Contractor. The provisions of the Conditions of Contract and specifically of relevance to such termination shall apply;

- be ceded to the Principal Employer upon having received a Notice to such effect from the Principal Employer and/or Main Contractor;

- be ceded to another Employer upon having received a Notice to such effect from the Principal Employer and/or Main Contractor”

SUB-CLAUSE 17.4:	“THE CONTRACTOR’S RISKS DURING THE OPERATION SERVICE PERIOD”

At the end of this sub-clause 17.4, insert new sub-paragraphs as set out hereunder:

“(c)		the risk relating to loss of revenue, resulting, or arising from the design, operation and maintenance of the Works by the Contractor, is shared with the Main Contractor in accordance with the allocation in FORM D13; and

(d)		all risk in respect of loss or damage to the project assets related to the NSC Scope of Works (as described in sub-clause 1.16 (Project Assets), save for the Employer’s and the Main Contractor’s Fixed Assets (fixed type of assets).”

SUB-CLAUSE 20.1 “Contractor’s Claims”

In sub-paragraph (a), replace all references to “28 days” to “21 days”.

In sub-paragraph (c), replace all references to “42 days” to “35 days”.

SUB-CLAUSE 20.3:	“APPOINTMENT OF DISPUTE ADJUDICATION BOARD”

In paragraph 1, delete the last sentence and replace with the following:

“On an ad-hoc basis and whenever either Party gives Notice to the other Party, the Parties shall promptly proceed to appoint a DAB.”

Delete paragraph 4 of this sub-clause 20.3.

SUB-CLAUSE 20.6:	“OBTAINING DISPUTE ADJUDICATION BOARD’S DECISION”

In the first sentence of paragraph 4 of this sub-clause: change “84 days” to “56 days” and “105 days” to “84 days”.

SUB-CLAUSE 20.8:	“ARBITRATION”

In the 4th line of the 1st paragraph, delete the word ‘international’.

In sub-paragraph (a), replace the words ‘International Chamber of Commerce’ with “South African Association of Arbitration”.

SUB-CLAUSE 20.1:	“Contractor’s Claims”

In sub-paragraph (a), replace all references to “28 days” to “21 days”.

In sub-paragraph (c), replace all references to “42 days” to “35 days”.

SUB-CLAUSE 20.10:	“DISPUTES ARISING DURING OPERATION SERVICE PERIOD”

Delete the existing clause 20.10 and replace with the following:

“Disputes arising during the Operation Service Period which cannot be resolved between the Parties shall be settled by a one-person ad-hoc DAB (“Operation Service DAB”).  Such person shall be jointly agreed and appointed by the Parties by the date 28 days after one Party has given Notice to the other Party of its intention to refer a Dispute to a DAB in accordance with sub-clause 20.10 [Disputes Arising during the Operation Service Period].

If the Parties cannot agree on the person who shall be the Operation Service DAB, then the person shall be appointed according to the provisions of sub-clause 20.4 [Failure to Agree Dispute Adjudication Board].

The agreement between the Parties and the Operation Service DAB shall incorporate by reference the General Conditions of Dispute Adjudication Agreement contained in the General Conditions of Contract, with such amendments as are agreed between them.

The terms of remuneration of the Operation Service DAB shall be mutually agreed upon by the Parties when agreeing the terms of appointment.  Each Party shall be responsible for paying one-half of this remuneration.  All Contractor’s costs associated with all DAB matters are deemed to be included in his Rates and Prices.

The procedure of obtaining a decision from the Operation Service DAB shall be in accordance with the provisions of sub-clause 20.6 [Obtaining Dispute Adjudication Board’s Decision], and the DAB shall give its decision no later than 56 days after receiving the response or, if no response is submitted, 84 days after receiving the reference and the supporting documentation form the Parties.

The appointment of the Operation Service DAB shall expire 28 days after it has given its decision in writing to both Parties.

If either Party is dissatisfied with the decision of the Operation Service DAB, the provisions of sub-clause 20.6 [Obtaining Dispute Adjudication Board’s Decision], 20.7 [Amicable Settlement], 20.8 [Arbitration] and 20.9 [Failure to Comply with Dispute Adjudication Board’s Decision] shall apply.”

C1.4	other standard forms

C1.4.2	FORM OF PERFORMANCE SECURITY – SURETY BOND

Note to Tenderer:

This Pro forma is for information only.  The successful tenderer’s Bank will need to reproduce it without amendment, omission or addition for completion and lodgement with the Employer.  A separate copy of this Pro forma will be issued to the successful tenderer with the Letter of Acceptance.

To be provided to the South African National Roads Agency SOC Limited established in terms of  section 2 of  South African National Roads Agency Limited and National Roads Act 1998 (Act No. 7 of 1998) of the Republic of South Africa having its principal place of business in [Pretoria](hereinafter called the "THE EMPLOYER")

Whereas:

The Employer has awarded CONTRACT SANRAL N.001-249-2019/1R NSC FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

(the Contract) to …………………………………………. (the Contractor),

Proforma

the Contractor is required in terms of the Contract to obtain or procure this Bond to be provided to The Employer.

We, the undersigned

………………………………………………….. and ……….………………………………………..
(Name)						(Name)

acting herein as

………………………………………………….. and ………………………………………………….
(Position)					(Position)

of

………………………………………………………………………………………………………………………
(hereinafter called the “Bank”)

being duly authorised to sign and incur obligations in the name of the Bank under and in terms of a Resolution of the Board of Directors of the Bank, a certified copy of which is annexed hereto, hereby irrevocably and unconditionally guarantee and undertake on behalf of the Bank that:

1.	The Bank shall pay amounts not exceeding R …………………………………………                     (………………………………………………….………… Rand) (the “Maximum Amount”) without delay, on receipt by the Bank of the first written demand of the Employer that the amount is due and payable and without proof of any breach or other default.  The Bank shall pay such amount(s) to the Employer (as specified in clause 5 below) upon receipt of a certificate herein after called the “Certificate” which shall be signed by any of the following authorised Employer representative, the Chief Executive Officer, the Chief Financial Officer, the Engineering Executive or the relevant Regional Manager certifying that the Employer is entitled to draw on this Bond pursuant to the provisions of the Contract.  The Employer may make partial and/or multiple demands under this Bond provided that the aggregate amounts paid under this Bond shall not exceed the Maximum Amount.

2.	The demand for payment together with this Bond (or a certified copy hereof) and the Certificate shall constitute prima facie proof of the Bank’s indebtedness hereunder for the purposes of any proceedings including but not limited to provisional sentence proceedings instituted against the Bank in any court of law having jurisdiction.

C1.4.2	FORM OF PERFORMANCE SECURITY – SURETY BOND (CONTINUED)

3.	The failure of the Employer to enforce strict or substantial compliance by the Contractor with its obligations or any act, conduct, or omission by the Employer prejudicial to the interests of the Bank including, without limitation, the granting of time or any other indulgence to the Contractor or any other person or by amendment to or variation or waiver of terms of the Contract or any ancillary or related document (the "Underlying Documents") will not discharge the Bank from liability under this Bond.  For the avoidance of doubt, the Bank's liability under this Bond will not be discharged notwithstanding the winding up, dissolution or judicial management of the Contractor or any other person and the Bond shall be honoured regardless of the invalidity, illegality or unenforceability of the Underlying Documents.

4.	This Bond shall:

4.1	remain in full force and effect from the date hereof, and shall expire on the earlier of:

4.1.1	Four (4) months after the issue of the Contract Completion Certificate;

Proforma

4.1.2	Ninety (90) days after the date of termination of the Contract;

4.2	exist independently of the Contract or any amendment, variation or notation thereof;

4.3	not be ceded, assigned or otherwise transferred by the Employer, or otherwise dealt with in any manner whatsoever (save for the purposes and in the manner referred to above) which has or may have the effect of transferring or encumbering or alienating the Employer rights hereunder;

4.4	be returned to the Bank on its expiry, cancellation, withdrawal or this Bond being fully drawn; and

4.5	be governed by the laws of the Republic of South Africa.

5.	The Bank shall deposit any payment made under this Bond into the account named 
SANRAL held at ABSA Bank Limited, Hatfield, Pretoria, Branch code, under account number: 01045510073.

6.	The Bank shall make any payment demanded under this Bond free, clear of and without any deduction, withholding, counterclaim or set-off of any kind.  If the Bank is required by law to make payments subject to the deduction or withholding of tax, it will make such further payments as are necessary to ensure that the amounts paid to the Employer equal the amounts that would have been paid to the Employer had no such deduction or withholding been made or been required to be made.

7.	The obligations of the Bank under this Bond shall not in any way be affected by the invalidity, illegality or unenforceability for any reason of the obligations of the Contractor.

8.	Addresses and Notices:

8.1	The parties hereto choose domicilium citandi et executandi for all purposes of and in connection with this Contract as follows:

EMPLOYER: The South African National Roads Agency SOC Limited

Telefax:	012 844 8200

The Bank:	………………………………………………………………………………

Telefax	………………………………………………………………………………

C1.4.2	FORM OF PERFORMANCE SECURITY – SURETY BOND (CONTINUED)

8.2	Any party hereto shall be entitled to change its domicilium from time to time, provided that any new domicilium selected by it shall be a physical address in the Republic of South Africa, and any such change shall only be effective upon receipt of notice in writing by the other party of such change.

8.3	All notices, demands, communications or payments intended for any party shall be made or given at such party’s domicilium for the time being.

8.4	Any notice required or permitted to be given under this Bond shall be valid and effective only if in writing.

8.5	A notice sent by one party to another party shall be deemed to be received

Proforma

8.5.1	on the same day, if delivered by hand;

8.5.2	on the same day of transmission, if sent by telefax with a receipt confirming completion of transmission.

8.6	Notwithstanding anything to the contrary herein contained a written notice or communication actually received by a party shall be an adequate written notice or communication to it notwithstanding that it was not sent to or delivered at its chosen domicilium citandi et executandi.

SIGNED ON THIS………... …….... DAY OF ……………………………………………  20  …………….

AT ……………………………………………………………………………………………………… (Place)

SIGNATURE 	………………………………….	SIGNATURE 	…………………………………

[NAME]		………………………………….	[NAME]	…………………………………

[TITLE]		………………………………….	[TITLE]	…………………………………

WITNESS 1	……………………………..……	WITNESS 2	…………………………………

C1.4.3	FORM OF CERTIFICATE

To:		[Name and address of Bank]

Attention:

Proforma

From:		[South African National Roads Agency SOC Limited] hereinafter referred to as “the Employer”

Address:

Dated:

Dear Sirs

Performance Security - Surety Bond Dated [insert date] (the "Bond")

We refer to the above Bond issued by you.  Terms defined in the Bond shall have the same meaning when used in this Bond.

The Employer is entitled to call on this Bond under Clause [insert relevant clause number of the Agreement] and we demand payment of the sum of R[] under the Bond.  Payment is to be made in accordance with the provisions of the Bond.

Payment must be made without delay to [Employer’s bank account details].

Yours faithfully,

...............................……………………….

for and on behalf of

[South African National Roads Agency SOC Limited]

C1.4.4	FORM OF AGREEMENT IN TERMS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT, 1993 (ACT NO 85 OF 1993) AND CONSTRUCTION REGULATIONS, 2014

This AGREEMENT made at……………………………………..……………………..……………...……..

on this the…………..……. day of………………………….……..in the year…………..…………between

THE SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED (hereinafter called "the Employer") on the one part,

herein represented by ……………………………………………………………………

in his capacity as……………………………………………..and delegate of the Employer in terms of the Employer’s standard powers of delegation pursuant to the provisions of Act  No 7 of 1998 and

............................................................................. (hereinafter called "the Mandatory") on the other part,

herein represented by……………….……………………………………………………………………………

in his capacity as ………………….…………................................................................................………

WHEREAS the Employer is desirous that certain Works be constructed, namely

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

and has accepted a tender by the Mandatary for the construction, completion and maintenance of such works and has appointed the Mandatary in terms of Regulation 5(1)(k) of the Construction Regulations 2014, and whereas the Employer and the Mandatary have agreed to certain arrangements and procedures to be followed in order to ensure compliance by the Mandatary with the provisions of the Occupational Health and Safety Act, 1993 (Act No 85 of 1993);

NOW THEREFORE THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	The Mandatary shall execute the work in accordance with the Contract Documents pertaining to this Contract.

2. 	This Agreement shall hold good from its Commencement Date, to either:

(a)  	the date of the Contract of Completion Certificate issued in terms of sub-clause 8.6 of the FIDIC Conditions of Contract for Construction for Design, Build and Operate Projects (2008) published by Federation Internationale des Ingenieurs-Conseils (FIDIC) (hereinafter referred to as "the GCC"), as contained in Volume 1 Book 1 of the Contract Documents pertaining to this Contract, or

(b) 	the date of termination of the Contract in terms of Clauses 15, 16 or 18 of the GCC.

3 	The Mandatary declares himself to be conversant with the following:-

(a)	All the requirements, regulations and standards of the Occupational Health and Safety Act (Act 85 of 1993), hereinafter referred to as "The Act", together with its amendments and with special reference to the following Sections of The Act.

(i)	Section 8: General duties of employers to their employees.

(ii)	Section 9: General duties of employers and self-employed persons to persons other than employees.

(iii)	Section 37: Acts or omissions by employees or mandataries and

(iv)	Sub-section 37(2) relating to the purpose and meaning of this Agreement.

(b)	The procedures and safety rules of the Employer as pertaining to the Mandatary and to all his subcontractors.

4	In addition to the requirements of sub-clauses 4.8, 6.7 and 17.9 of the GCC and all relevant requirements of Volume 3 of the Contract Documents pertaining to this Contract, the Mandatary agrees to execute all the works forming part of this Contract and to operate and utilize all machinery, plant and equipment in accordance with The Act.

5.	The Mandatary is responsible for the compliance with the Act by all his sub-contractors, whether or not nominated and/or approved by the Employer.

6.	The Mandatary warrants that all his and his subcontractors’ workmen are covered in terms of the Compensation for Occupational Injuries and Diseases Act, 1993 (Act No 130 of 1993) which cover shall remain in force whilst any such workmen are present on site.  A letter of good standing from the Compensation Commissioner to this effect must be produced to the Employer upon signature of the Agreement.

7.	The Mandatary undertakes to ensure that he and/or his sub-contractors and/or their respective employees will at all times comply with the following conditions:

(a)	The Mandatary shall assume the responsibility in terms of Section 16.1 of The Act.  The Mandatary shall not delegate any duty in terms of Section 16.2 of The Act without the prior written approval of the Employer.  If the Mandatary obtains such approval and delegates any duty in terms of section 16.2 a copy of such written delegation shall immediately be forwarded to the Employer.

(b)	All incidents referred to in The Act shall be reported by the Mandatary to the Department of Labour as well as to the Employer.  The Employer will further be provided with copies of all written documentation relating to any incident.

(c)	The Employer hereby obtains an interest in the issue of any formal enquiry conducted in terms of section 32 of The Act into any incident involving the Mandatary and/or his employees and/or its sub-contractors.

In witness thereof the parties hereto have set their signatures hereon in the presence of the subscribing witnesses:

SIGNED FOR AND ON BEHALF OF THE EMPLOYER: ....................................................................

AS WITNESSES:

1			…………………………………………………….

SIGNATURE					NAME (IN CAPITALS)

2	 		…………………………………………………….

SIGNATURE					NAME (IN CAPITALS)

SIGNED FOR AND ON BEHALF OF THE MANDATARY: ..................................…............................

AS WITNESSES:

1			…………………………………………………….

SIGNATURE					NAME (IN CAPITALS)

2		             ……………………………………………………

SIGNATURE					NAME (IN CAPITALS)

C1.4.5 (a)	FORM OF APPLICATION FOR A PERMIT TO DO CONSTRUCTION work to DEPARTMENT OF LABOUR

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ANNEXURE 1

Occupational Health and Safety Act, 1993

(Regulation 3(2) of the Construction Regulations, 2014)

APPLICATION FOR A PERMIT TO DO CONSTRUCTION WORK

This application must be submitted with the following documents:

      - Health and Safety specification.

      - Baseline risk assessment.

Name, postal address and telephone numbers of the client:

Proforma

Details of the Agent:

(a)	Title, Surname and Initials:

(b)	Identity number / Passport number:

(c)	Registration number with SACPCMP:

(d)	Office Tel. Number and/or Mobile number:

(e)	Postal address:

Name, postal address and telephone numbers of the appointed principal contractor:

Name, postal address and telephone numbers of the designer of the project:

Name, postal address and telephone numbers of the following persons:

(a)	Construction Manager:

(b)	Construction Health and Safety Manager:

(c)	Construction Health and Safety Officer:

Exact physical address of the construction and site office:

Nature of construction work:

Proforma

Expected commencement date:

Expected completion date:

Estimated maximum number of persons on the construction site:

……………………….……………………….

Planned number of contractors on the construction site accountable to the principal contractor:

Name(s) of contractors appointed:

Signature of Client / Client’s Agent

Signature of the Principal Contractor

FOR OFFICE ONLY Authorization / Unique No. Proforma; LABOUR CENTRE; OFFICIAL APPROVAL STAMP. Date of application: Submitted documents prescribed in Construction Regulation 5(1) (Please tick P): CR 5(1)(a); CR 5(1)(b); CR 5(1); (C-S). Approved; Declined. Result of the application (Please tick P) Reason for declining the application Signature of the Supervisor Signature of revoking officer / Inspector

C1.4.5 (b)	FORM OF NOTIFICATION OF CONSTRUCTION WORK TO DEPARTMENT OF LABOUR

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

ANNEXURE 2

Occupational Health and Safety Act, 1993 (Act No 85 of 1993)

Regulation 4 of the Construction Regulations, 2014

NOTIFICATION OF CONSTRUCTION WORK

# ______

##### 1.	a)	Name and postal address of principal contractor:

##### b)	Name and telephone number of principal contractor’s contact person:

##### 2.	Principal contractor’s compensation registration number:

##### Not applicable to this Contract

3.	a)	Name and postal address of client:

South African National Road Agency SOC Limited

Eastern Region

58 Van Eck Place

Mkondeni

Pietermaritzburg

3207

b)	Name and telephone number of client’s contact person or agent:

Client:

##### Agent:

##### 4.	a)	Name and postal address of designer(s) of the Project:

b)	Name and telephone number of the designer’s contact person:

5.	Name and telephone number of principal contractor’s construction manager on site appointed in terms of Regulation 8(1):

##### 6.	Name(s) of principal contractor’s Assistant Construction Manager on site appointed in terms of Regulation 8(2):

##### 7.	Exact physical address of the construction site or site office:

##### 8.	Nature of construction work:

##### 9.	Expected commencement date:

##### 10.	Expected completion date:

##### ………………………….................................................................................................................

##### Not applicable to this Contract

##### 11.	Estimated maximum number of persons on the construction site:

##### Total: …………………………….  Male:  ………………………  Female:  …………………………

##### 12.	Planned number of contractors on the construction site accountable to the principal contractor:

##### 13.	Name(s) of contractors already selected:

……………………………………………………… 	…………………………………………………

##### PRINCIPAL CONTRACTOR		DATE

………………………………………………………	…………………………………………………

##### CLIENT AGENT (Where Applicable)		DATE

………………………………………………………	…………………………………………………

CLIENT							DATE

•	THIS DOCUMENT IS TO BE FORWARDED TO THE OFFICE OF THE DEPARTMENT OF 	LABOUR PRIOR TO COMMENCEMENT OF WORK ON SITE.

•	ALL PRINCIPAL CONTRACTORS THAT QUALIFY TO NOTIFY MUST DO SO EVEN IF ANOTHER PRINCIPAL CONTRACTOR ON THE SAME SITE HAD DONE SO PRIOR TO THE COMMENCEMENT OF WORK

C1.4.6	FORM OF AGREEMENT FOR DAB MEMBERS

[All italicised text and any enclosing square brackets is for use in preparing the final form and shall be deleted from the final product.]

Name of Contract: 		………………………………………………………………………………

This Agreement made the 	……………. day of ……………………………………………20 ……….

between

Name and address of Employer: 	………………………………………...……………………………

Proforma

Name and address of Contractor: 	………………………………………...……………………………

Name and address of DAB Member: 	………………………………………...……………………………

Whereas the Employer and the Contractor have entered into a Contract and desire jointly to appoint the above-named Member to act on the DAB as the chairman of the [insert 1 or 3 whichever applies] Member DAB during the [insert Contract Period or any other period as may be applicable],

And whereas the Member accepts the appointment.

The Employer, Contractor and Member jointly agree as follows:

The conditions of this Dispute Adjudication Agreement comprise the "General Conditions of Dispute Adjudication Agreement" which are appended hereto, and the following provisions. In these provisions, which include amendments and additions to the "General Conditions of Dispute Adjudication Agreement", words and expressions shall have the same meanings as are assigned to them in the "General Conditions of Dispute Adjudication Agreement".

[Details of any amendments or additions or deletions from the "General Conditions of Dispute Adjudication Agreement" should be given here or in an attachment hereto.]

In accordance with Clause 6 of the "General Conditions of Dispute Adjudication Agreement", the Member shall be paid as follows:

(a)	A retainer fee of ………… per calendar month, and

(b)	A daily fee of ……..… per day spent on Site visits, hearings, and other time in connection with submissions to the DAB made in accordance with the provisions of the Contract between the Employer and the Contractor.

In consideration of these fees and other payments to be made by the Employer and the Contractor in accordance with Clause 6 of the "General Conditions of Dispute Adjudication Agreement", the Member undertakes to act as the DAB Member in the capacity above-mentioned in accordance with the terms of this Dispute Adjudication Agreement.

The Employer and the Contractor jointly and severally undertake to pay the Member in consideration for his acting as the DAB Member as aforementioned in accordance with this Dispute Adjudication Agreement.

This Dispute Adjudication Agreement shall be governed by the laws of the Republic of South Africa.

Signed by: ………………………...  	Signed by: …………………….  	Signed by: …………………………...

(signature)                                    (signature)	                                       (signature)

Proforma

for and on behalf of Employer                     for and on behalf of Contractor 	for and on behalf of Member

in the presence of		          in the presence of			in the presence of

Witness:  ………………………….   Witness:  …………………………  Witness:  …………………………

(signature)	                                        (signature)                                    (signature)

Name:	……………………….	Name:	……………………….	Name:  ………………………

Address:	………………………	Address:	………………………	Address:	……………………

Date:	………………………	Date:	………………………	Date:	………………………

C1.4.7	FORM OF BANKING DETAILS

Notes to Contractor:

1.	The Employer applies an Electronic Funds Transfer system for all payments.

2.	If you are already registered as a vendor with the Employer, you are required to confirm your banking details in the form below but not required to submit documentation as per note 3.1 and 3.2.

3. 	If you are not registered as a vendor with the Employer, you are required to supply:

  - a completed SANRAL Vendor Application Form (to be obtained from the relevant Regional Project Manager); or

  - an original cancelled cheque bearing your company name and account number; or

  - if you are unable to supply an original cancelled cheque, you are to provide a letter on your letterhead as per the pro forma below and return the original letter to the address as stated in clause 1.3 of C1.2.2 - Information provided by the Employer, delivered by hand or sent by post.

To:

The South African National Roads Agency SOC Ltd

The Regional Manager (Northern Region)

38 Ida Street

Menlo Park

Pretoria,

0081

Dear Sir

Proforma

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

BANKING DETAILS

By signing this document, we accept the following:

- The banking details submitted are those of (Contractor Name) and we take full responsibility for their correctness.

- We indemnify the Employer from any and all outcomes if an electronic transfer is made into an incorrect bank account using the banking details submitted.

Account Name:	…………………………………………………………………………………………

Bank:	…………………………………………………………………………………………

Branch Name:	…………………………………………………………………………………………

Branch Code:	…………………………………………………………………………………………

Account Number:	…………………………………………………………………………………………

Yours sincerely

…………………………………………………………….

Authorised Signatory for Contractor                                        Date:

C1.4.8	TAX COMPLIANCE PERMISSION DECLARATION

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

Note:

In terms of National Treasury Instruction No 3 of 2014/2015 with reference to the Public Finance Management Act, 1999 (Act No 1 of 1999) and Regulations, the contractor and subcontractors are required to provide the Employer with written confirmation to access the SARS Electronic Tax Compliance Status (TCS) System to verify and continuously track the tax compliance status of all persons conducting business with the State.

The Contractor shall complete the declaration below.

I, 	 (name)

the undersigned in my capacity as 	 (position)

on behalf of

(name of company)

herewith grant consent that SARS may disclose to the South African National Roads Agency SOC Limited (SANRAL) our tax compliance status on an ongoing basis for the contract term.

For this purpose, our unique security personal identification number (PIN) is 	,

our tax reference number is …………..….. and our tax clearance certificate number is 	.

In addition, the Contractor shall obtain written consent from each of its subcontractors, undisclosed principals and partners involved in this contract confirming that SARS may, on an ongoing basis during the contract term, disclose the subcontractors’ tax compliance status to the Employer. For this purpose, the Contractor shall provide the Employer with the unique security personal identification number (PIN), tax reference number and tax clearance certificate for each of its subcontractors, undisclosed principals and partners involved in this contract.

SIGNATURE:

DATE:

C1.4.9	APPOINTMENT OF PRINCIPAL CONTRACTOR IN TERMS OF REGULATION 5.1(k) OF THE CONSTRUCTION REGULATIONS, 2014 INCORPORATED IN THE OCCUPATIONAL HEALTH AND SAFETY ACT, ACT 85 OF 1993

APPOINTMENT OF PRINCIPAL CONTRACTOR BY CLIENT (EMPLOYER)

This AGREEMENT made at

on this the 	 day of 	 in the year

between (Note to compiler: insert MAIN CONTRACTOR details) (hereinafter called “the Client”) on the one part, herein represented by

in his/her capacity as

and delegate of the Client in terms of the Client’s standard powers of delegation pursuant to the provisions of Act No. 7 of 1998, and

(hereinafter called “the Principal Contractor”) on the other part, herein represented by

in his capacity as

WHEREAS the Client is desirous that certain works be constructed, viz. CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

and has accepted a tender by the Principal Contractor for the construction, completion & maintenance of the works.

NOW THEREFORE THIS AGREEMENT WITNESSETH AS FOLLOWS:

The Principal Contractor shall execute the work in accordance with the contract documents pertaining to this contract.

This Agreement shall hold good from its commencement date, to either:

the date of the Performance Certificate issued in terms of sub-clause 11.9 of the Conditions of Contract for Construction for Building and Engineering Works designed by the Employer (1999) published by Federation Internationale des Ingenieurs-Conseils (FIDIC), as contained in Volume 1 of the contract documents pertaining to this contract, or

the date of termination of the contract in terms of clauses 15, 16 or 19 of the GCC.

The Principal Contractor declares himself to be conversant with all the requirements and standards of the Occupational Health and Safety Act (Act 85 of 1993) together with its amendments and incorporated Regulations, hereinafter referred to as "The Act", and with special reference to the Construction Regulation 7: Duties of Principal Contractor and Contractor.

The Principal Contractor is responsible for the compliance with the Act by all his subcontractors and suppliers when entering the construction site, whether or not nominated and/or approved by the Client.

The Principal Contractor warrants that all his and his subcontractors’ workmen are covered in terms of the Compensation for Occupational Injuries and Diseases Act 1993, which cover shall remain in force whilst any such workmen are present on site. A letter of good standing from the Compensation Commissioner to this effect must be produced to the Employer upon signature of the agreement.

The Principal Contractor warrant that adequate provision has been made for the cost of health and safety measures during the execution of the project, and that sufficient resources (including competent personnel) are available to carry out the construction work safely.

The Principal Contractor warrants that the Employer / Client has carried out his duties in terms of Construction Regulation 5.1(a)(b)(f):

Construction Regulation 5.1(a): A baseline risk assessment for the intended construction work was prepared by the client and included in the tender documentation.

Construction Regulation 5.1(b) & (f): A suitable, sufficiently documented and coherent site-specific health and safety specification for the intended construction work based on the baseline risk assessment was included in the tender documentation.

In witness thereof the parties hereto have set their signatures hereon in the presence of the subscribing witnesses:

SIGNED FOR AND ON BEHALF OF EMPLOYER

WITNESS 1:

SIGNATURE:

NAME (IN CAPITALS)

WITNESS 2:

SIGNATURE:

NAME (IN CAPITALS)

SIGNED FOR AND ON BEHALF OF THE PRINCIPAL CONTRACTOR

WITNESS 1:

SIGNATURE:

NAME (IN CAPITALS)

WITNESS 2:

SIGNATURE:

NAME (IN CAPITALS)

FORM C1.5	CONTRACT DATA – INFORMATION PROVIDED BY THE TENDERER

A:  CONTACT  DETAIL

The Service Provider is Address: Telephone: Facsimile: The authorised and designated representative of the Service Provider is: Name: The postal address for receipt of communications is: Telephone: Facsimile: Address: E-mail Address:

B:  KEY  PERSON

| Key Person | Name |
| --- | --- |
| Contract Engineer (NSC Representative) |  |
| Quality Control Officer |  |
| Maintenance Manager |  |
| System/ Software Support Specialist |  |

C:  INFORMATION  REQUIRED  FOR  THE  PUBLICATION  OF  AWARD  AS  PER  NATIONAL  TREASURY  INSTRUCTION  NOTE

| Name of Director(s) |  | Appointment Date | Designation |
| --- | --- | --- | --- |

PART C2:	PRICING DATA

PART C2	PRICING DATA

TABLE OF CONTENTS	PAGE

C2.1	PRICING ASSUMPTIONS	C71

C2.2	SCHEDULE OF PAYMENTS/COST MATRIX (INCORPORATING SBD3)	C73

C2.1	PRICING ASSUMPTIONS

- The measurement and payment shall be in accordance with relevant provision of the Standard Specification for Operations and Maintenance for CTROM Projects:  Payment Methodology and Description of Payment items (Volume 2 Book 7a) (October 2010).

- The assumptions listed in this section must be read in conjunction with the Preamble to Schedule of Payments in the Standard Specifications for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a) (October 2010).

- The tenderer is to note that Schedule of Payments are in the Cost Matrix format to allow the tenderer to price different monthly rates to cater for the various traffic peaks that may occur during the Contract Period.

- The tenderer shall submit prices for the Contract Period for the Fixed and Variable Cost Payment Mechanism for the Kranskop, Nyl, Capricorn and Baobab Control Centres.

- Items indicated with the term “if triggered” will only be paid on implementation when instructed by the Employer.  Payment for these items will be delayed coinciding with the actual implementation. The prices must include for all developing, procurement, installation and removal of redundant material from site (if applicable).

- An electronic version of the Schedule of Payments/Cost Matrices is included in Volume 4. The tenderer shall provide all entries required in the Schedule of Payments/Cost Matrix for each Control Centre.

- SUBTOTAL (COST CARRIED FORWARD TO SCHEDULE OF PAYMENTS/COST MATRIX). All entries shall be to Rand (R0,00) and shall exclude VAT.  The cells in the electronic version of the Schedule of Payments/Cost Matrix that require input by the tenderer are shaded in light blue “either in the” rate” or in the “month column(s)”.  All the blue shaded cells, including those in the personnel cost breakdown tables, must be filled in, either with zero’s, or otherwise.  THE TENDERER SHALL NOT ALTER THE INPUT IN OTHER CELLS. The tenderer shall submit the priced Schedule of Payments/Cost Matrices in both electronic and hard copy format with its tender “offer”.

- Some of the “light blue” shaded items in the Schedule of Payments/Cost Matrix require a total price for the route instead of a price per Control Centre.

- The “Grey cells” as well as the Items with “Green text” in the electronic version of the Schedule of Payments/Cost Matrix have been locked due to the items either not being applicable or not required for the specific control centres.

- The model, in MS Office Excel format, that is used to determine the Operations and Maintenance Fee, is included in Volume 4. The payment model will automatically read the Operations and Maintenance Fee from the Schedule of Payments/Cost Matrices, which have to be completed by the tenderer.  Please note that for this to happen, both of the payment model and the Schedule of Payments/Cost Matrix Files must be in the same directory.

- The tenderer shall fill in the relevant percentage mark-up values for Provisional Sums in the place cells in column D.  If the relevant percentages are not filled in the Sub-Clause 13.5 shall apply.

- Cost items for the relevant activities/requirements in terms of the Clauses in the Contract are indicated on the Schedule of Payments/Cost Matrix.  Tenderers must ensure that only costs related to the relevant cost items must be included in the specific item.

- The tenderer must note that should there be any statutory levies that are added or removed during the contract period, it shall be added or removed from the Schedule of Payments/Cost Matrix item.

- In the case of “Milestone dependent items”, only the “Blue shaded cell” in column “D” for the relevant items for each Control Centre(s) must be completed.  The tenderer must make provision for all cost described for each item detailed in Clause 3.4 of the Standard Specifications for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a) (October 2010).  This clause also indicates the percentage payments for each item when the various milestones have occurred. Software factory acceptance test, functional compliance, provisional compliance and full compliance will be as defined in the Standard Specifications for Operations and Maintenance of CTROM projects:  Toll Systems (Volume 2 Book 4a) (October 2010).

- Should the tenderer have other costs not described in any of the appropriate items, as in the Schedule of Payments/Cost Matrix, the tenderer must allocate such costs in the most appropriate item as no additional payments related to milestone items will be made.

- The Employer’s Representative may inform the relevant sub-contractors when payments are made for the above-mentioned milestones.

C2.2	SCHEDULE OF PAYMENTS/COST MATRIX (INCORPORATING SBD3)

The spreadsheet containing the Schedule of Payments/Cost Matrix is provided separately in Excel format in Volume 4.

PART C3: 	SCOPE OF WORKS

# PART C3	SCOPE OF WORK

TABLE OF CONTENTS									PAGE

PART C3.1	SCOPE OF WORK (SECTION A) – NOT APPLICABLE	C76

PART C3.1	PROJECT DESCRIPTION (SECTION B)	C77

PART C3.2	PARTICULAR SPECIFICATIONS FOR TOLL OPERATIONS AND MAINTENANCE (SECTION B)	C88

##### PART C3.1	SCOPE OF WORK (SECTION A) – NOT APPLICABLE

##### PART C3.1	PROJECT DESCRIPTION (SECTION B)

PART C3.1	PROJECT DESCRIPTION (SECTION B)

C3.1.1	PROJECT OVERVIEW

C3.1.1.1	Toll Road and Toll Plaza

This section provides the description of the project and the general requirements for executing the work. The work required is the Design Build, Operations and Maintenance of the toll system for the operations and maintenance of toll plazas of the national road.

The declared N1 North Toll Road stretches from km 42.55 on Section 23 (Warmbaths Interchange) to km 106.8 on section 29 (Beitbridge)of the National Route a distance of approximately 76.7 km.  The existing Toll Road sections can be broadly described as follows:

| Section | Toll Plazas |
| --- | --- |
| Bela Bela I/C to Mookghopong South I/C | Kranskop Mainline Toll Plaza |
| Mookghopong I/C to Polokwane Eastern Bypass | Nyl Mainline Toll PLaza |
| Polokwane to Makhado | Capricorn Mainline Toll Plaza |
| Makhado to Beit Bridge | Baobab Mainline Toll Plaza |

There are seven (7) existing Toll Plazas located along the N1 North Toll Road and the general details can be summarised as follows:

| Toll Plaza | Control Centre | Location (Interchange) | Section of N1 | Distance km | Number of Lanes* |
| --- | --- | --- | --- | --- | --- |
| Kranskop Mainline | Kranskop | Modimole I/C | Bela Bela I/C to Mookgopong South I/C | 60 | 7/7 |
| Kranskop Local Ramp | Kranskop | Modimole I/C |  |  | 2/2 |
| Nyl Mainline | Nyl | Mookghopong | Mookgopong North I/C to Polokwane Eastern Bypass | 102 | 6/6 |
| Nyl Local Ramp | Nyl | Mookghopong |  |  | 2/3 |
| Sebetiela Remote Ramp | Nyl | North of Mookghopong |  |  | 4/4 |
| Capricorn Mainline | Capricorn | On the N1 | Polokwane to Makhado | 105 | 4/4 |
| Baobab Mainline | Baobab | On the N1 | Makhado to Beit Bridge | 106 | 3/3 |

* x/y denotes per direction (Northbound/Southbound)

Note that lanes 12RS and 02RN at Kranskop Local Ramp have lane swopping functionality implemented, and can therefore be operated as either local ramp lanes, or mainline lanes.

C3.1.1.2	Alternative Route

The Alternative Route runs parallel to the N1 North Toll Road between Bela – Bela I/C to Polokwane on the Route R101 and this is the alternative route to the Kranskop, Nyl and Sebetiela Toll Plaza section of the Toll route.

There is no alternative route between Polokwane and Makhado. However, some heavy vehicles use the R521 through Deondron and R523 through Waterpoort as an alternative route while some light vehicles use the R81 through Munnik and R36 through Soekmekaar and join the N1 North Toll Road just north of Capricorn Toll Plaza as the other alternative route.

There is no alternative route between Polokwane and Musina. However, some heavy vehicles use the R523 through Waterpoort and the R521 through Alldays and then the R572 through Mapungubwe National Park to Musina as the alternative route.

## C3.1.2	DESCRIPTION OF THE WORKS

### C3.1.2.1	Description of Roles and parties to this Contract

The Principal Employer’s procurement strategy includes tenders for two contracts simultaneously:

- The first contract will be for the Main Contractor, for the Operations and Maintenance of Toll Plazas on the N1 North Toll Road (also known as the CTROM contract).

- The second contract (this contract) will be for the Nominated Subcontractor for the Design Build Operations and Maintenance of the Toll System for the Operations and Maintenance of Toll Plazas on the N1 North Toll Road.

- Once the Principal Employer has selected the two contractors, the Main Contractor will be instructed to appoint the Nominated Subcontractor.

This Contract is the Nominated Subcontract to the Main CTROM Contract for the Operations and Maintenance of the toll system of toll plazas on N1 north Toll roads

The terminology used for the contracts and the various roles versus the FIDIC terminology is tabled and clarified below.

Table 4-1: ASSOCIATED Contracts and terminology

| Contract Entity | Main Contract (MC) (CTROM Operations and Maintenance Contract) | Toll System Subcontract (NSC) | How these should be interpreted in this contract |
| --- | --- | --- | --- |
| SANRAL | Employer | Principal Employer | Principal Employer |
| Main Contractor (MC) (Operations and Maintenance Contractor) | Contractor | Employer | Main Contractor |
| Toll System Subcontractor (NSC) | Nominated Subcontractor (NSC) | Contractor | Nominated Subcontractor (NSC) |
| Employer’s Representative | Employer’s Representative | Main Contractor’s (MC) Representative | MC Representative |
| SANRAL MIS System Integrator |  |  | 3rd Party - SANRAL MIS System Integrator (SI) |
| SANRAL Toll System Integrator |  |  | 3rd Party - SANRAL Toll System Integrator (SI) |

- All references to Contractor in this document refer to the Nominated Subcontractor (NSC).

- The term NSC is used interchangeably with Contractor, and both terms shall have the same meaning.

- All references to Main Contractor refers to the Contractor appointed for the Operations and Maintenance of the toll system of toll plazas on N1 north Toll roads.

In the event where any ambiguity or discrepancy is found in the documents, the Contractor shall request the Main Contractor to issue any necessary clarification or instruction.

C3.1.2.2	General Description

The description of the Works contained in this section is a general outline of the Main Contractor’s responsibilities and shall not limit the Works to be carried out by the Nominated Subcontractor.

- The Nominated Subcontract is for the Design Build, Operations and Maintenance of the Toll System.

- The Principal Employer will appoint the Main Contractor to design, operate, and maintain the Works. The Principal Employer will also select a Nominated Subcontractor who will perform the Toll System Integration work as a nominated subcontractor work for the Main Contract (the CTROM contract).  The Toll System Integration work shall include the design, procurement, installation, testing, and maintenance of the Toll System.

- It should be noted that the Main Contractor and the Nominated Subcontractor (System Integrator)’s scope of works are not separated in different specifications. The Nominated Subcontractor is responsible for the Toll System and should therefore be cognisant of the Toll System specifications.

- The Main Contractor in turn is responsible for all the Works, including the management of the Nominated Subcontractor and to ensure that the Toll System meet the contractual design and performance criteria.

- The Nominated Subcontractor scope of works typically relates to the design, procurement, installation, testing, and maintenance of the Toll System, including the maintenance of the existing Toll System handed over at the Commencement Date.

C3.1.2.3	Toll Plaza Operations

The Works include full responsibility for inter alia the following:

- Collection and control of toll at the various Toll Plazas.

- Traffic management.

- Financial management.

C3.1.2.4	Provision and Maintenance of Employers Facilities and Permanent Design-Build

The Works include the maintenance of all Employers Facilities and Permanent Design-Build Assets, which will remain the property of the Employer.

The Main Contractor’s Works include the maintenance of all Employers Facilities and Permanent Design-Build Assets, which will remain the property of the Employer.

The Main Contractor shall take over, provide, or replace, where applicable, all non-Toll System Permanent Design-Build Assets and all Principal Employer’s Facilities and maintain these Assets for the duration of the Operation Service Period. The Contractor shall take over, provide, or replace all Toll System Permanent Design-Build Assets and maintain these Assets for the duration of the Operation Service Period.

The Main Contractor and the Nominated Subcontractor shall take over and maintain the existing toll system which shall facilitate the collection and control of toll. The Nominated Subcontractor shall take full responsibility for retaining and for the maintenance of portions of the existing toll systems.  The Nominated Subcontractor shall also be responsible for the maintenance and support for the portion of the toll systems described in the Nominated Subcontract.

The Main Contractor is to manage, and coordinate functions related to the Nominated Subcontract to ensure that the Nominated Subcontractor meets the requirements and obligation of this Contract. The Main Contractor and the Nominated Subcontractor must both refer to part C3.2.4 for the allocation of roles and responsibilities between the Main Contractor and the Nominated Subcontractor.

C3.1.2.5	Contractor’s Facilities and Equipment

The Contractor shall provide all necessary Contractor’s facilities and equipment and maintain these Assets for the duration of the Operation Service Period.

### C3.1.2.6	Customer Service Centre (CSC)

The Works includes the implementation, operation and maintenance of the Customer Service Centre along the N1 North Toll Road.

C3.1.2.7	Video Grabbing System (VGS)

A Digital Video Surveillance System (DVSS), as described in Volume 2 Book 2a and Volume 2 Book 4a, are currently installed at the mainline Toll Plaza/s (Kanskop, Nyl, Capricorn and Baobab, as well as Sebetiela Remote Ramps plaza), to monitor queue lengths with surveillance function, record activity in the lane area and to capture images of incidents for the purpose of auditing transactions..  The system may be upgraded to incorporate other functions should it be required, by the Employer at any time during the Contract period.

C3.1.2.8	Queue Length Monitoring System (QLS)

There are QLS’s installed at all the existing Mainline Toll Plaza/s Kranskop, Nyl, Capricorn and Baobab, as well as Sebetiela Remote Ramp plaza), refer to Part D18 of Volume 4 for the summary of the description of system installed.

The existing QLS systems shall be maintained until such time the new QLS is installed. The new QLS shall produce recordings for the specific plaza in line with the latest requirements. The Contractor is to ensure that continuous recordings remain available.

The functionality of the existing DVSS may be incorporated in the Contractor's QLS. The DVSS and QLS is therefore seen as one deliverable.

C3.1.2.9	Video Grabbing System (VGS) and Queue Length Monitoring System (QLS) Remote Access Facility

It is required that a secure remote access facility as stipulated in Volume 2 Book 4a for both the VGS and QLS systems be implemented, in order for the Principal Employer to remotely access the VGS and QLS to view historical data records and/or real time data.  The Contractor shall implement the necessary means to allow for data transfer during the remote access process, over broad band (ADSL) or other means that would be approved by the Employer’s Representative, at a minimum downstream speed of 10Mbps and upstream speed of 10Mbps.

The remote access facility provides the remote user with the same functionality as the user at the Toll Plaza, to query events and or incidents on the VGS and QLS servers.

C3.1.2.10	Cameras

C3.1.2.10.1	Fixed Cameras

The Contractor shall comply with the following minimum specification when installing new cameras during the Operation Service Period:

- IP (Internet Protocol) based and have a resolution of at least 1920 x 1080.

- Minimum illumination of: 	0.5 lux (colour)

0.04 lux (black and white)

- Be capable to automatically switch to infrared sensitive black and white video at low light conditions.

- Auto iris.

- Contain a progressive scan CCD image sensor.

- Support both JPEG and MPEG4.

- H264, H264+ or higher compliant or other non-proprietary compression algorithm approved by the Employer’s Representative in addition to JPEG and MPEG4 support.

- Cameras shall have a frame rate of at least 25 fps.

Existing cameras may be re-used by the Contractor and can make use of IP servers or converters with the following minimum specification:

- IP (Internet Protocol) based and have a resolution of at least 1280 x 720. Camera images shall produce sufficient quality which enables the viewer to be able to identify Vehicle License Plates numbers accurately.

- support both JPEG and MPEG4.

C3.1.2.10.2	PTZ Cameras

All PTZ cameras must comply with the following minimum specifications:

- A frame rate of at least 25 fps.

- Video resolution at least 1920 x 1080.

- Image stabilization of 10%-pixel displacement up to 10 HZ

- Minimum illumination of: 	0.5 lux (colour)

0.03 lux (black and white)

- Auto gain controls up to 28dB – on/off.

- Adjustable auto iris.

- Support both JPEG and MPEG4.

- H264, H264+ or higher compliant or other non-proprietary compression algorithm approved by the Employer’s Representative in addition to JPEG and MPEG4 support.

- PTE functions:

- manual

- sequential positions

- auto pan

- pre-set tours

- Zoom min 20x optical with auto focus.

The Contractor shall ensure that, as a minimum, CAT 6A cable is only utilised within the boundaries of buildings. Cabling provided for any cameras or video servers between buildings shall be connected by means of fibre optic cable or other technology as approved by the Employer’s Representative which is not prone to damage caused by electrical or lightning surges. The Contractor is also to ensure that CAT6 (or later high-speed derivatives) or coax cable shielding be earthed at one end only or as instructed by the Contractor’s surge and lightning protection specialist.

C3.1.3	EXPECTED GENERAL CONTRACT PROGRAMME

C3.1.3.1	Expected Programme

It is anticipated that the Establishment Period at all the Toll Plazas will be approximately six(6) - weeks.  The following key milestones are as follows:

- Design Build Commencement Date – middle January 2024 Expected.

- Commencement of Operation Service Period: 1 March 2024.

## C3.1.4	CONTRACT DURATION

The Contract Period shall be for a maximum duration of 73.5 months, including the Design-Build and Operation Service Period.

Note however that the Principal Employer is planning to roll out their national SANRAL Toll System on all the Toll Plaza/s within the next 6 years, upon which this Nominated Subcontract SANRAL will terminate.  The Contractor will be notified at least 6 months in advance.  The minimum duration of this contract shall be 37.5 months and the maximum duration 73.5 months.

## C3.1.5	OTHER EMPLOYER CONTRACTS

During the Operation Service Period, there will be other Contract(s) between the Employer and third parties executing work within this contract boundaries, such as:

| TABLE C3.1.5/1: PROGRAMME OF CONTRACTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Route |  | Project/Works description | Period |  |
| From | To |  | From | To |
| N1/23 km 42.2 N1/24 km 0.00 N1/25 km 0.00 | Km 54.91 Km 25.00 Km 42.36 | Routine road maintenance | 2021 | 2024 |
| N1/25 km 42.36 | Km 89.04 | Routine road maintenance | 2021 | 2024 |
| N1/26 km 0.00 | Km 28.79 | Routine road maintenance | 2021 | 2024 |
| N1/27X km 0.00 N1/28X km 0.00 | N1/27X km 22.30 N1/28X km 6.51 | Routine road maintenance | 2021 | 2024 |
| N1/28X km 6.51 | Km 51.40 | Routine road maintenance | 2021 | 2024 |
| N1/28X km 51.40 | Km 98.53 | Routine road maintenance | 2021 | 2024 |
| N1/29X km 0.00 | N1/29X 106.80 | N.001-290-2019/2 MOTRM: Makhado 1 | 2021 | 2024 |
| N1-27 km 10.6 | N1-27 km 25.3 | Polokwane Eastern Ring Rd Upgrade | Construction ends - March 2021 ToC | Defects Period ends March 2022 |
| N1-24 km 6.4 | N1-24 km 25 | Kranskop Plaza to Nylstroom: Upgrading | 2024 | 2027 |
| N1-25 km 0 | N1-25 km 30 | Nylstroom to Tobias Zyn Loop: Upgrading | 2023 | 2026 |
| N1-25 km 30 | N1-25 km 60 | Tobias Zyn Loop to Sasol Zebediela: Upgrading | 2024 | 2027 |
| N1-25 km 60 | N1-25 km 89 | N.001-250-2025/2 DNURT: Sasol Zebediela to Rietvley | 2023 | 2026 |
| N1-26 km 0 | N1-26 km 28.7 | Rietvley to Polokwane: Upgrading | 2024 | 2027 |
| N1-28 km 0.0 | N1-28 km 49.00 | Polokwane to Dwarsriver: Upgrading | 2024 | 2027 |
| N1-28 km 49 | N1-28 km98 | Dwarsriver to Louis Trichardt: Upgrading | 2024 | 2027 |
| N1-29 km 27.8 | N1-29 from km 27.80 to km 70 | Masekwaspoort to km 70: Upgrade | 2022 | 2025 |
| N1-29 km 0 | N1-29 km 27.8 | Louis Trichardt to Masekwaspoort: Upgrade | 2022 | 2024 |

## C3.1.6	DRAWINGS

The available As-built drawings of key civil layouts of each Toll Plaza and for the toll system electrical, mechanical and electronic Assets are included in Part C2 of Volume 4.

Selected drawings and figures are included in Part A of Volume 4.

Available As-built drawings of the remainder of the Assets, the Toll Road, including relevant structures, roadside furniture will be made available on request after the Commencement Date at the Employer standard printing tariffs, as applicable. Drawings will, however, be made available for scrutiny during the tender period at the Employer Northern Region offices in Pretoria, if so requested.

## C3.1.7	PENALTIES FOR NON-PERFORMANCE

In instances, where the Main Contractor and/or Nominated subcontractor do not comply with any specific requirement of the Contract, the Employer may:

- Apply a penalty related to the non-compliance by the Main Contractor and/or Nominated subcontractor to a specific requirement of the Contract as described in the Contract, for that specific item, or

- Employ a third party to perform, complete or rectify the item of non-compliance by the Main Contractor and/or to a specific requirement of the Contract and to recover any costs incurred by the Employer from the Main Contractor and/or Nominated subcontractor.

- Where the Termination of this Contract is specified as a penalty that may be applied by the Employer, the Employer may, at its sole discretion apply a penalty of ten percent (10%) of the monthly Operation Service payment (excluding capital expenditure), per Control Centre in lieu of Termination of the Agreement.

## C3.1.8	INTEGRATED TRANSPORTATION INFORMATION SYSTEM

The Principal Employer has developed a comprehensive information management tool called ITIS (Integrated Transportation Information System) to address all facets of its strategic and tactical planning, design, construction and maintenance of the entire road network.  This provides support for the management tasks of the Principal Employer and to allow the Principal Employer’s personnel to make technical decisions more quickly and efficiently.

ITIS is an integrated approach to the sharing and inter-relating of technical performance information for the Employer and relies on people following procedure to populate the system with data.  ITIS currently consist of the following platforms:

- ITIS Web	-	Web enable portal providing online access to various 
			functions, workflows and reports.

- ITIS Desktop	-	Offline data capture tool enabling the capturing of information 
			offline, 	validation and synchronisation of data with ITIS 
			database.

- ITIS Mobile	-	Application (Android 6 or later) that allows
            			the infield capture of information using a smart phone or tablet 
			(must have a camera and GPS), validation of the 
			synchronisation of data with ITIS database.

The Principal Employer then has several ITIS modules running on any of the above ITIS platforms which affect the Main Contractor, who will need to use these modules to perform certain procedures to provide required information.  The current modules applicable to toll operations and maintenance and their description are as follows:

Contract Module		-	Management of Contracts;

- Incident Module		-	Recording of incidents on site;

- Project Information Module	-	Employment and training data; and

- Toll Module 		- 	Management of toll system data and payments.

An ITIS Desktop Project information Module – User Manual is included in Part C9 of Volume 4 and User manuals for the various functions can be downloaded from https://itisnra.co.za/Portal/Myaccount/UserManuals  after the successful registration as a Public user.

## C3.1.9	EMPLOYER’S MANAGEMENT INFORMATION SYSTEM AND TOLL SYSTEM

The Principal Employer is currently planning to design and to develop the Employer’s Management Information System (SANRAL MIS) and Employer Toll System that is expected to be rolled out on all the Toll Plaza/ on the N1 North Toll Road during the Operations Service Period.

The SANRAL MIS forms part of the National Back Office System that will allow for the National Management of all toll related issues that will enable the Principal Employer to provide the Road User with a single point of contact for all toll-related activities and concerns, such as but not limited to queries, discounts, transaction payment clearing, customer care and other value-added services.

The SANRAL MIS deployment, for the purpose of this project will be implemented in two phases. The Contractor will be required to implement a complete data interface, along the line of the TCH interface, as part of the Toll System upgrade. The complete SANRAL MIS interface and integration will follow as a later phase when the SANRAL MIS development reaches the appropriate implementation level.

The Contractor will be required to adapt the standard CTROM architecture to allow for integration with  the SANRAL MIS.  Based on the information available, the expected major changes can be summarised as follow:

- The Toll Plaza Back Office is to be replaced, in part or in full,  by the SANRAL MIS.  It shall not replace all the Toll Plaza Back Office functionality, which means that the Plaza Back Office shall become a lesser involved system and shall be called the Lane Mediator.  The functionalities that  SANRAL MIS does not take over, shall remain on the Mediation Layer. The following toll plaza related function may remain:

- Control room monitoring functions.

- Incident control and exception management.

- Cash-up and shift control functions.

- Site health monitoring and configuration control.

- Local discount control.

- Queue management.

- VGS audits.

- The SANRAL MIS shall therefore take over the following minimum functionality from the Back Office / CTROM equipment:

- Fetching of validation and negative files information and push these lists to the Lane Mediation Layer.

- Manual validation and corrections of incidents, including ANPR and OCR.

- Management of accounts and discounts.

- Customer Service Interface(s).

- The SANRAL MIS shall become the Toll Plaza’s Time Synchronization Master.

- Additional responsibilities shall be required from the Contractor in order to facilitate the successful change over, such as:

- Automated System Checks to ensure that all the communication from the Lane Mediation Layer has been communicated successfully to the SANRAL MIS

- The existing VGS System must be modified to a full time Network Video Recorder only.  The implementation of ANPR and OCR services shall be the responsibility of the SANRAL MIS.  The Contractor shall provide the required interfacing requirements.

- All Cameras shall provide clear enough images to allow for OCR and ANPR processing.  This means that the VLN’s must be humanly readable from the images provided by the Contractor’s Toll System.

- The DCS interface shall now be to the SANRAL MIS and not externally to the Employer’s interface called ITIS.

- Audit Logs of all interaction shall be required.

The Contractor shall make provision for coordination and assisting the SANRAL MIS System Integrator and to develop to implement the required changes to the existing Toll Plaza System which allows for the successful integration between the systems.

The diagram below provides insight on the foreseen changes required.

Figure 2:  SANRAL MIS Interface

The Contractor must make provision for the testing and coordination function to facilitate the rollout of the SANRAL MIS and must make provision for staff training on the SANRAL MIS.

## C3.1.11	MAINTENANCE OF DEDICATED ETC/SHESHA LANE SIGNS

There are Dedicated ETC/Shesha lane signs currently installed in two (2) lane per direction at the Kranskop Mainline Toll Plaza, and in one (1) lane per direction at Nyl, Capricorn and Boabab Mainline Toll Plazas, and Sebetiela Remote Ramp .  The drawings and details of these signs are included in Part C29 of Volume 4.  The Main Contractor is required to maintain these signs for the duration of the Operation Service Period.  If these signs get damaged either through accident and/or due to extreme weather conditions, the Main Contractor is required to provide a rate to replace these signs.  The Main Contractor to refer to the Schedule of Payment/Cost Matrix for the relevant payment items.

## C3.1.12	SANRAL TOLL SYSTEM

The Principal Employer intends to procure a national SANRAL Toll System.

The Principal Employer will select the national SANRAL Toll System from one of the existing nominated subcontractors on all the CTROM routes.

The Nominated Subcontractor, subcontracted through the Main CTROM Operations Contract, may therefore be selected as the national Nominated Subcontractor for the provision of the SANRAL Toll System. In such a case the Nominated Subcontractor may be required, at the rates tendered by the Nominated Subcontractor for the route, to replace the nominated subcontractors on other SANRAL routes and deploy its own Toll System.

The deployment of the SANRAL Toll System will be triggered by the Employer. The SANRAL Toll System deployment will require full integration with the SANRAL MIS.

The SANRAL Toll System will include the following Toll System components;

- Lane System (TCC) and AVC

- DCS

- Back-office system (BOS) inclusive of interfaces and interface management subsystems.

- TCH payment gateway

- VGS

- QLS

- QL1

##### PART C3.2	PARTICULAR SPECIFICATIONS FOR TOLL OPERATIONS AND MAINTENANCE (SECTION B)

In certain Clauses the Standard Specifications allow a choice to be specified in the Scope of Work between alternative materials or methods of operations and maintenance and for additional requirements to be specified to suit a particular Contract.  Details of such alternatives or additional requirements applicable to the contract and some additional specifications required for this particular Contract are contained in this section of the Scope of Works as particular specifications.

C3.2.1	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATIONS FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS:  GLOSSARY OF TERMS AND GENERIC SCOPE OF WORKS

The number of each Clause as a Particular Specification in this section consists of Prefix PS, followed by a number corresponding to the number of the relevant Clause in the Standard Specification for Operations and Maintenance of CTROM Projects:  Glossary of Terms and Generic Scope of Works, (Volume 2 Book 1a).  The number of any new Clause which does not form part of any Clause in the Standard Specifications for Operations and Maintenance of CTROM Projects:  Glossary of Terms and Generic Scope of Works (Volume 2 Book 1a), and which is included herein, is also prefixed by PS followed by a new number.  Such new number flowed on the last Clause used in the relevant section of the Standard Specifications for Operations and Maintenance of CTROM Projects:  Glossary of Terms and Generic Scope of work (Volume 2 Book 1a).

PART A:	GLOSSARY OF TERMS

PS3	DEFINITIONS

“Base date”

The Base Date month shall be March 2024.

‘Control Centre’

The existing Control Centres are listed in the following table:

| TOLL PLAZAS | CONTROL CENTRE |
| --- | --- |
| Kranskop Mainline | Kranskop Control Building |
| Kranskop Local Ramps |  |
| Nyl Mainline | Nyl Nyl Local Ramps Control Building |
| Nyl Nyl Local Ramps Control Building |  |
| Sebetiela Remote Ramps |  |
| Capricorn Mainline Capricorn Control Building | Capricorn Control Building |
| Baobab Mainline | Baobab Control Building |

“Customer Service Kiosk”

In this Contract references will be made to “Customer Service Kiosk” or “Customer Service Centre” which is the same facility.

“Lane Area”

The extent of the Lane Area for each Toll Plaza along the N1 North Toll Road is detailed in the drawings included in Part A4 of Volume 4.

“SANRAL MIS”

Means the centralised management information system developed by the Employer through a 3rd party contract, that allows a Toll Agency to execute the administration, accounting, transaction processing, control and management functions of the toll collection process in a computerised way. The management information system, inter alia, exchanges information with the Nominated Subcontractor’s Toll System  to enable centralised information and control. In the case where ETC is catered for, the Nominated Subcontractor’s Back Office shall be required to interface to the TCH, which shall manage all ETC accounts nationally.

“SANRAL Toll System”

Means the Toll System selected from a nominated subcontractor contracted on one of the CTROM routes. SANRAL intends to standardise this selected system on all the CTROM routes nationally.  This system will typically include the lane, AVC, VGS, QLS and limited BOS functionality interfaced to the SANRAL MIS. The provision of the SANRAL Toll System will be triggered by the Employer and will be procured at the tendered rates within the applicable nominated subcontract. “Road”

The road comprises of the following sections.

| N1 NORTH TOLL ROAD |  |  |  |  |
| --- | --- | --- | --- | --- |
| ROUTE | SECTION | FROM (KM) | TO (KM) | LENGTH (KM) |
| N1 | 23 | 42,55 | 55,0 | 12,5 |
|  | 24 | 0,0 | 25,1 | 25,1 |
|  | 25 | 0,0 | 89,0 | 89,0 |
|  | 26 | 0,0 | 29,0 | 29,0 |
|  | 27 | 0,0 | 15,6 | 15,6 |
|  | 28* | 0,0 | 98,7 | 98,7 |
|  | 29 | 0,0 | 106,8 | 106,8 |
| TOTAL |  |  |  | 376,7 |

“Site for Operations and Maintenance”

The extent of the site for Operations and Maintenance shall include the existing Toll Plaza(s) on the N1 North Toll Road with associated Employer Facilities, as indicated in the drawings included in Part A4 of Volume 4.

“Toll Plaza”

The Toll Plazas that form part of this contract is listed in the following table:

| TOLL PLAZAS | LOCATION |
| --- | --- |
| Kranskop Mainline | N1 – 24, KM 18,066 |
| Kranskop Local Ramp |  |
| Nyl Mainline | N1-25, km 57.820 |
| Nyl Local Ramp |  |
| Sebetiela Remote Ramp | N1 – 25, KM 75,030 |
| Capricorn Mainline | N1 – 28, KM 70.000 |
| Baobab Mainline | N1 – 29, KM 55.260 |

The extent of the Toll Plaza(s) on the N1 North Toll Road(s) are detailed in the drawings included in Part A4 of Volume 4.

“Toll Road”

The extent of the N1 North  Toll Road shall be the National Road Reserve Boundaries from  Bela-Bela I/C (km 42.55 Section N1-23) to Beitbridge (km 106.8 section N1-29) a distance approximately 376.7 m.

C3.2.2 	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATION FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: GENERAL (VOLUME 2 BOOK 2a)

The number of each Clause as a particular specification in this section consists of the prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a). The number of any new Clause which does not form part of any Clause in the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a).

Only the following clauses shall be applicable to this contract:

SECTION 1. OVERVIEW OF OPERATIONAL ENVIRONMENT

All clauses.

PS1.5 	Overall operations responsibilities of the Contractor

Replace all references to “Contractor” to “Main Contractor”.

PS1.6 	Overall responsibilities of the Employer in respect of toll operations

Replace all references to “Employer” to “Principal Employer”.

SECTION 2. PROJECT COMMENCEMENT: HANDOVER AND PROVISION OF DOCUMENTS

Clauses 2.2.1, 2.3.1, 2.3.2, 2.3.3 (where applicable to Toll System maintenance manuals), 2.4 and 2.5.

PS2.2	Employer’s Documents, Drawings and Software

PS2.2.1 	General

PS2.2.1.2	As-Built Drawings

A list of available As-built drawings for existing Toll Plaza(s) is contained in Part C2 of Volume 4.

PS2.2.1.3	Equipment User Manuals

A list of available equipment user manuals is contained in Part C3 of Volume 4.

PS2.2.1.4	Equipment Supplier’s Manuals

A list of available equipment supplier manuals is contained in Part C3 of Volume 4.

PS2.2.1.5	Software and Software User Manuals

The current software licences for the toll system are in the name of the Employer. The Contractor may utilise the existing software and associated licences.

A list of available software and software user manuals is contained in Part C3 of Volume 4.

The list of current software Contractors is included in Part B1 of Volume 4.

PS2.3.2.1   Software Licenses

Replace this clause with the following:

“The Contractor shall comply with the requirements regarding proprietary Software Licences and Escrow agreements as specified in the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a).

All Toll System and Sub-System Licenses shall be perpetual (no expiry date), transferable, non-terminable, non-exclusive, royalty-free and unrestrictive. Other Software from third parties and Software complimentary to the Toll System, but not specifically developed as a Toll System component, shall be valid until the end of the Contract, or, whichever is the latest, valid until the end of the next Contract’s design build period. All off the shelf Software with a license which gets renewed on a yearly basis and requires no specific toll related expertise to update, shall be valid until the end of the Contract period. Software which may influence the Toll System functionality when upgraded, such as operating system, shall be valid until the end of the next Contract’s Design Build period.

| Software Descriptions | Perpetual | End of Contract | End of Contract +3 years |
| --- | --- | --- | --- |
| Toll System Software Developed by Contractor / System Integrator |  |  |  |
| Back Office / MIS | X |  |  |
| LSDU | X |  |  |
| Back Office / MIS Interfaces | X |  |  |
| Lane | X |  |  |
| AVC | X |  |  |
| DCS | X |  |  |
| VGS | X |  |  |
| QLS | X |  |  |
| Other Software Complimentary to the Toll System |  |  |  |
| Operating Systems |  |  | X |
| Anti-Virus Software |  | X |  |
| Microsoft Office Products |  | X |  |
| Helpdesk |  |  | X |
| Asset Management System |  | X |  |
| Network Management Software |  |  | X |
| All firmware |  |  | X |

All Licenses which will roll over into the next Contract period, shall be transferred to the Employer at successful commissioning of the respective equipment and/or systems or in the event of Contract termination.”

SECTION 3. OPERATIONAL FOOTPRINT

None.

SECTION 4. TOLL PLAZA EXPANSIONS AND UPGRADES, ROAD IMPROVEMENTS AND OTHER IMPROVEMENTS

Clause 4.2

SECTION 5. ESTABLISHMENT

Clauses 5.1.1, 5.1.2.

PS 5.1.2.1.3 Contractor’s Minimum Personnel requirements

- The required personnel shall as a minimum meet the below stated Qualification and Training requirements.

- The Contractor shall make provision for the cost of employing the required personnel with the stated minimum requirements in his rates and this cost shall not be specifically measured for payment.

| PERSONNEL CATEGORY | REQUIRED QUALIFICATION AND TRAINING |
| --- | --- |
| 1. Assistant Technician (Electronic) | HEQSF* level 5 (Referring to a minimum qualification of a higher certificate or advanced certificate) in electronics or similar Basic electricity safety awareness Six months practical experience |
| 2. Technician (Electronic) | HEQSF* level 6 National Diploma in Information Technology, Electronic Engineering, Computer Engineering, Digital Technology or Instrumentation and Process Control or similar accredited diploma Preferably registered with the Engineering Council of SA (ECSA) or similar accredited institution Minimum one year experience in similar technical field or proof of logbooks from practical period for Diploma Extensive knowledge in electricity safety Access to transport between Plazas with a valid driver’s licence |
| 3. Senior Technician (Electronic) | HEQSF* level 6 National Diploma in Information Technology, Electronic Engineering, Computer Engineering, Digital Technology or Instrumentation and Process Control or similar accredited diploma Preferably registered with the Engineering Council of SA (ECSA) or similar accredited institution Minimum of three years related technical experience Extensive knowledge in electricity safety Access to transport between Plazas a valid driver’s licence Minimum of 2 years of experience in managing staff and resources |
| 4. Construction Health and Safety Officer | NQF Level 6 National Diploma in Safety Management (NDS MN) equivalent training course as a minimum qualification. Preferably registered with the South African Council for the Project and Construction Management Professions (SACPMP). Minimum five (5) years of experience with regards to implementing and maintaining a health and safety management system compliant. Access to transport between Toll Plazas with a valid driver’s licence. |

Note:	*Reference to the Engineering Qualifications and the Higher Education Qualifications sub-framework (HEQSF) presentation by ECSA (http://www.sasee.org.za/CMS/WP-content/uploads/2014/07/HEQSF-And-Engineering-Qualifications-B-van-Wyk.PDF

SECTION 6. OPERATIONS PERIOD – TRANSACTION MANAGEMENT AND PROCESSING

Add the following:

PS6.1.1.3

The Vehicle Classification Structure that has been published in the latest Government Gazette is as follows:

| CLASS | TYPE OF VEHICLE | DESCRIPTION |
| --- | --- | --- |
| 1 | Light | Light vehicle are motor vehicles, other than heavy vehicles, with or without a trailer and including motorcycles, motor tricycles and motor cars. |
| 2 | Medium Heavy | Medium heavy are heavy vehicles with two (2) axles. |
| 3 | Large Heavy | Large heavy are heavy vehicles with three (3) or four (4) axles. |
| 4 | Extra Large Heavy | Extra-large heavy are heavy vehicles with five (5) or more axles. |

Add the following Sub-Clauses:

PS6.1.1.3.1

“The Contractor is to note that the Employer is considering and may add an additional toll class for motorcycles to the existing vehicle classification structure during the Operation Service Period. The Contractor is to note that the current Toll System/s is already managing and processing Motorcycles at Toll Lane Level, where a Motorcycle Class is catered for and this Vehice type / Class Identification shall be operationally executed as such. The use of the Class 5 type of vehicle class shall not be visible to the motorist, who will experience the passage and financial transaction as being a standard Class 1 Light Vehicle transaction, until instructed to implement the “complete” Class 5 vehicle type functionality in a “motorist-visible” manner.

PS6.1.1.3.2

All Transactions, within the toll system, are being processed and managed as Class 5 Motorcycles (including the AVC system). However, the financial and traffic reporting from the Toll System provides consolidated traffic and income data (combining motorcycles and the remaining Light Vehicles), as Class 1 Traffic, as per the current Government Gazette. Changes to the Government Gazette will be communicated to the Contractor, in time in order to implement the required configuration changes to ITIS data reporting and other performance and financial reporting elements. The Contractor shall be prepared to implement such configuration changes on short notice, as and when required.”

Clause 6.2.2.1.

Replace clause 6.2.2.1 with the following:

“6.2.2.1 	The Contractor shall supply, install and commission an appropriate digital video grabbing system (VGS) with a camera in each Toll Lane, and as specified in the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a). The system shall be compliant and operational no later than 3 (three) months after the Commencement Date. The Contractor shall Operate and Maintain the system for the duration of the Works Period.

6.2.2.2 	The Main Contractor and Contractor shall use the VGS to manage reportable incidents that occur at the Toll Plaza. The VGS shall provide the Employer and Principal Employer with an audit tool to verify operational activities of the Main Contractor and Contractor.

6.2.2.3	For Toll Lanes that operate Manual Mode, the Contractor shall ensure that the VGS records on a continuous basis for those lanes.

6.2.2.4 	The Contractor shall record digital images continuously on a storage device.

6.2.2.5 	A back up of the triggered Incidents and linked images shall be performed on a weekly basis.

6.2.2.6 	The Contractor shall ensure that the Employer and Principal Employer shall have full access to this data if so required by it

6.2.2.7	The VGS and ANPR lane camera shall include the following functions:

- Record video from selected cameras on DVRs or NVR that are time synchronised with the MIS/BOS

- Provide ANPR cameras licence data and text in real-time to the TCC

- Provide incident images to the BOS requested by the BOS Incident Control System

- Provide VGS status information to the BOS health monitoring system (BOS level incident generation)

- Links the following to images, including Transaction Framing:

  - BOS transactions

  - BOS incidents

  - Vehicle number plate and ANPR data

  - Video motion, over the AVC area, that are not associated with BOS transactions in closed and open lanes

  - Queue analytics

- BOS /VGS interface, including Transaction Framing: The interface shall include

  - BOS timeslice/hourly audit summaries which shall be used by VGS to manage the video import process e.g. trigger import when all data for a specific timeslice is available.

  - BOS transactions and Incidents: Import all transactions and incidents. VGS events (passages) shall be created for each transaction. Additional VGS events shall be created for motion that do not match an existing BOS transaction. VGS shall use the AVC first axle and the ETC tag detected incident and/or light curtain (or other sensor input) as a reference point in Transaction Framing process.

  - Transaction audit trail data will be imported and displayed by VGS as part of the VGS event

  - Updates to transaction data will be reflected by VGS and highlighted to auditors

  - Vehicle number plate data captured per transaction by VGS

  - Perform ANPR on images during the video import and add ANPR data to VGS event

  - Time synchronization interface to ensure that the times on the VGS, including DVR’s, are within 200 milliseconds of the BOS and TCC times

  - Feedback to BOS that includes:

        - VGS status for

        - Server

        - DVR

        - Camera

        - Importer

        - Time sync interface

        - VGS software versions and configuration data

- Provide an audit interface that allows the auditor to:

  - Run queries for a combination of the following:

    - Date and time ranges, including times relative to a specific reference point

    - Selected lanes and or plazas

    - Method and means of payment e.g. cash, credit card, violation or Tag

    - Exceptions linked to BOS incidents or VGS exception generated from an analysis of the BOS data and DVR video. These exceptions include but are not limited to (Selection of all, only selected or NOT selected or No Exceptions):

      - Class discrepancies, positive and negative

      - Abnormal passage: Run through, roll-back, vehicle standing, reverse entry, reverse roll-back, wrong direction, excessive axles (>10)

      - Number plate discrepancies: Account, registered TCH VLN and card mismatches

      - Exempt/Credit granted voucher: Check the number plates, captured during incident control for a voucher, against the ANPR value

      - Card/Tag abuse: Usage exceptions, pass back

      - Collector exceptions: Cancel classification, MVC timeout, Simulate button pressed, cancelled classification, cancelled validation (system or collector)

      - Equipment exceptions: Software restarts for lane or AVC, AVC sequence error, Panel door open (AVC or LC)

      - Exceptions detected by VGS: Video without transaction, Transaction without video, Number plate mismatch, possible tailgater and pass back.

    - Tag, card and transaction numbers

    - Road user group e.g. nominal, free passage or local users

    - Vehicle number plate

    - Vehicle class including MVC, AVC, SVC

    - AVC status message-based query including type and number of axles

    - Card source e.g. SCR, Plaza or ETC

    - Shifts and collectors

    - Classifications, including axle types, and Class discrepancies (SVC, MVC and AVC)

    - Transaction source (VGS, lane or plaza)

    - Audit status

    - Highlight and allow the auditor to view an audit trail of changes to a transaction e.g. inserted voucher number, class or MOP changes and supervisor comments

    - Exception cause allocation

  - Make and record audit inputs including:

    - Assigning a cause and corresponding sub cause to exceptions detected by the toll system or VGS including Operator, road user, VGS, Toll System or Operational.

    - Input text comments to explain exception

    - Option to flag exceptions,

      - To be kept

      - As severe

      - Ignore i.e. false alarm

    - Create additional exceptions or events (additional vehicle not accurately detected by the BOS)

    - Assign video to BOS manually created transactions. Match manually created data with Video without Transaction event e.g. if the transaction is created after VGS imported the BOS data.

    - Log auditor inputs and make the audit inputs visible per event for higher level auditors

    - Select the appropriate audit action, and the completion status of actions, based on the findings of the exception audit

    - Allow the batch auditing of certain types of exceptions. For some types of audits batch auditing shall not be allowed.

  - Generate reports, including:

    - Export CSV data and tabular formatted Excel spreadsheet for queried events and reports

    - Detail exception report for queried events and exceptions

    - Audit state report

    - Traffic reports

    - Accuracy reports, including AVC class and count accuracy. Include functionality to handle and audit raised axles

    - ANPR accuracy

    - Identifier defaulters report

    - Fraud investigation report

    - Export a data pack based on query and including images.

    - DVR image export based on selected cameras and periods.

    - BOS Incident and transaction-based query and audit tool. This include displaying incident related images and retrieved images to cover the gaps between retrieved transaction and incident images. This tool is used to view and audit activities and passages around certain reported incidents e.g. panel door open or AVC critical mode.

  - View data and image status

  - Write data, images and video to media

  - VGS camera status viewer

  - Include maintenance functions i.e. Back-up and archive

  - VGS user manual

  - Queue audit functionality. This includes generating audit events for potential queues based on traffic flow rates (parameter driven)

SECTION 7. OPERATIONS PERIOD – FINANCIAL MANAGEMENT

None.

SECTION 8. OPERATIONS PERIOD – CUSTOMER SERVICES

None.

SECTION 9. OPERATIONS PERIOD – MANAGEMENT OF CUSTOMER ACCOUNTS

None.

SECTION 10. OPERATIONS PERIOD – TRAFFIC MANAGEMENT

PS10.4 Digital Queue Length Monitoring System (QLS)

PS10.4.1

All references made to “DVSS” must be deleted and replaced with “VGS/QLS.

Clause 10.4.1.1

SECTION 11. OPERATIONS PERIOD – DATA TRANSMISSION

None.

SECTION 12. OPERATIONS PERIOD – TAG MANAGEMENT

None.

SECTION 13. EQUIPMENT FUNCTIONALITY AND INTERFACES AND AGREEMENTS

Clauses 13.1.1, 13.1.3, 13.2.1, 13.2.2, 13.2.3.1, 13.2.3.5.

PS13.1.1

Add the following:

“The Contractor shall assure full technical responsibility for the design, supply, installation, integration, testing, operation, maintenance and support of the tolling system as required in The Standard Specification for Operations and Maintenance of CTROM projects:  Operations (Volume 2 Book 2a), The Standard Specifications for Operation and Maintenance of CTROM projects:  Toll System (Volume 2 book 4a) and Standard Specifications for Operations and Maintenance of CTROM projects:  Electronic Toll Collection (Volume 2 book 5).  The Contractor to ensure that the tolling system and all peripheral services functions as required at all times.

The Main Contractor and Contractor to ensure that the performance requirements and Operational Business Rules are adhered to as described in the Standard Specifications for Operations and Maintenance of CTROM Projects (Volume 2 Book 6a and 8a) respectively.”

PS13.1.1.5

Replace this clause with:

The Contractor shall accommodate and integrate operations activities with the detail program of all requisite Toll System upgrade/replacement activities, guided by the time frames indicated for the acceptance progress in the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a).

PS13.1.1.6

Replace this clause with:

For the initial Toll System upgrade/replacement, an implementation programme shall be agreed with the Main Contractor and Principal Employer and submitted within 45 (forty-five) calendar days after the Contract Commencement Date or as stated in the Project Document: Volume 3 for approval by the Principle Employer. The approved program will form the basis against which progress on the Toll System acceptance process shall be measured.

PS13.2.1.2

Replace this clause with:

“13.2.1.2	The Contractor will establish and maintain interfaces with inter alia:

  - The TCH;

  - The VPC (if opted-in);

  - The Employer’s acquiring bank for, inter alia, the processing of credit card transactions (e.g. in manual lanes at Conventional, Hybrid and Conventional/ORT Toll Plazas);

  - ITIS and Traffic Analysis System (ITAS) interface;

  - VGS remote access interface.”

PS13.2.2.1	Contractor (TA) – TCH Interface

Add the following:

“The interfaces between the Toll Authority (N1 Great North ) and the TCH has been successfully implemented to serve the base requirements for processing tag transactions on all the existing Toll Plazas from the Commencement Date of the Operation Service Period.

The N1N Efkon Payment Gateway, the module that handles the interface between the TCH and the Toll System, is currently hosted off-site by a service provider (Vodacom business). The Contractor shall implement the TCH payment gateway in the Server at Kranskop (or Nyl) plaza. The Contractor shall ensure the necessary interfaces, links, firewalls, configurations, and hardware to accommodate the Payment gateway. The Contractor shall ensure that the primary and secondary links capacity between the N1N and the TCH can accommodate the direct link between the Payment Gateway and the TCH..

The N1N already utilises the Liquid Telecom Fiber, running along the N1N, to connect the all the N1N plazas. The aim is to establish a fibre link between the N1N and the TCH, utilising theLiquid Telecom Fiber networks. This will require the connection of the  Liquid Telecom N1N Fiber network to the GORT network at the SANRAL offices. The Contractor shall implement the necessary interfaces, links, firewalls, configurations, and hardware to accommodate the establish this fibre connection as the primary network between N1N and TCH, The Contractor shall provide the TCH Contractor with the required configuration and information and completing the commissioning process of the primary TCH link via the fibre link.

The interface between the Customer Service Centre (CSC) installed in the Administration Office on each of the existing Toll Plazas on the N1 Great North and the TCH has been successfully implemented and the Contractor is to operate these CSC stations from Commencement Date of the Operation Service Period.”

PS13.2.3.1	Contractor (TA) – TCH

Add the following:

“The Main Contractor and the Contractor shall comply to the TA/TCH a Service Level Agreement (SLA) with the Operator of the TCH of which a copy of the latest draft SLA is included in Part C12 of Volume 4.

The Contractor is to note, that the Principal Employer is currently in the procurement process to appoint a new Operator for the TCH and the Main Contractor may need to sign a new SLA with the new appointed TCH Operator, if required.”

“PS13.2.3.5	EMV Integrated Circuit Card Requirements

“It is envisaged that chip card technology may be implemented during the Operations Service Period by the banks. To allow for payment system interoperability, all payment systems will have to comply with the “EMV Integrated Circuit Card” specifications. This requirement shall be dealt with as a new requirement in terms of Volume 2 Book 4a.  The new requirement process shall be used to ensure that all systems if supplied and installed, comply with EMV specifications for payment systems.  Relevant details on specifications and implementation dates can be obtained from the following website: www.emvco.com

The Nominated Subcontractor shall be responsible for the cost of software and hardware modification to comply with the relevant EMVCO requirements. The Nominated Subcontractor shall install two EMV compatible contactless card readers per lane fitted outside each booth, just before the payment window. The bottom reader shall be at a level accessible from the driver seat of a light vehicle. The top reader shall be installed at a height accessible from the driver seat of a class 4 heavy vehicle. The two readers shall be positioned to optimise the driver access for most types of vehicles.  The card reader units shall be designed for outside use and have at least IP 65 rating.

The reader shall be equipped with clear status LEDs to indicate, power on (white), success full read (orange), successful payment/Boom open (green) and unsuccessful payment/card rejection(red). The card readers shall process the payment request without the road user having to enter a pin.

A provisional tendered rate sum is allowed in the Schedule of Payments/Cost Matrix for this purpose.  If triggered the Contractor shall implement the EMV requirements to ensure compliance to the relevant EMV specifications.

SECTION 14. ASSET MANAGEMENT

Clauses 14.1, 14.2, 14.3, 14.4.1, 14.4.2, 14.4.4, 14.5, 14.6 (for assets provided by and/or managed and/or maintained by the NSC).

PS14.4.4.8	Spares and replacement parts

Add the following sub-clauses:

“ (b) The Contractor shall supply a complete batch of spares as part of the system implementation, when the system is roll-out to all lanes, which shall be maintained for the period of the contract. The initial batch of spares shall form part of the hardware verification

A full batch of spares shall form part of the handover requirements at the end of the contract.

The Contractor shall maintain the following minimum, or higher, spares levels per workshop:

- Complete set of lane peripherals: One complete spare units for each type of peripheral, including but not limited to a Boom, OHLS, ETC beacon, TCT, VDU, receipt printer, set of light curtain, set of AVC sensors, siren, booth camera, side view camera, ANPR camera etc.

- Components: One complete replacement unit for every 10 units or part thereof e.g., four hard drives for a 12-lane plaza. Comments includes mother boards, CPU’s, serial cards, RAM units, intercom slaves, sirens, traffic light heads, proximity detectors, door switches etc.

- Boom arms: Two spare boom arms for every 10 lanes or part thereof.

- Consumables and additional spares required to ensure a high service level”

“(c)	The Contractor shall supply, install and maintain a Lane test or standby rig in the workshop. The test or standby rig shall be used for testing components and scenarios by the maintenance technician. The test or standby rig shall;

- Be installed in the maintenance workshop and shall consist of a full set of lane equipment, loaded with the correct approved and certified software and settings;

- Where possible and practical, the various components of the test or standby rig shall be mounted against the workshop wall;

- Include all the components required to simulate one of the existing Mixed ETC lanes, including:

  - Lane Controller

    - Complete lane controller, back plate and components, excluding the lane controller enclosure

    - Door switch

    - TCT and swipe card reader

    - Video display unit

    - Receipt printer

    - Barcode scanner

    - Battery low detector

    - Network switch

    - Exit boom

    - ETC Beacon

    - Traffic light

    - UFD

    - ANPR camera and ANPR presence detector

    - Test Tag and cards

    - AVC sensor simulator

  - Complete AVC, back plate and components, excluding the AVC box and sensors

  - AVC/TCC UPS, with limited battery back-up

  - Evaluation, test and verification utilities

- May exclude;

  - VGS cameras

  - AVC sensors

  - Boom arm

- The test or standby rig shall be maintained by the Contractor and shall not use it as spares to replace faulty equipment.”

PS14.4.4.14 Tolling System availability

Add the following sub-clause:

PS14.4.4.15 Support and maintenance levels

“(a)   1st line Support and maintenance: Means the logging and notification of a maintenance incident and the rectification of issues by low level interventions, that exclude modification of the configuration or changes to the system. 1st Line support will identify issues and escalate such issues to higher levels of support staff.

    - Hardware 1st Line support and maintenance (“1st Line HW support and maintenance”) requires site presence and includes, inter alia.

      - Maintenance:

        - Daily inspection of the system,

        - Ensuring that all lanes are operating in normal mode,

        - Ensuring that all AVC are operating in normal mode,

        - Ensure that complete AVC data is submitted via the DCS to ITIS,

        - Identifying components and sensors that need to be replaced as part of routine maintenance,

        - Cleaning and realigning and resetting of components/devices, and

        - Maintenance of the workshop, spares, Test or standby rig, and tools,

        - Oder spares to ensure adequate spares are always available.

      - Support:

        - 1st response to reported issues or issues detected during maintenance inspection.

        - Fault finding and analysis,

        - Resubmit ITIS, if data problems exists,

        - Restarting/rebooting systems, and

        - Replacing components with spare units.

    - Software 1st Line support and maintenance (“1st Line SW support and maintenance”) requires site or remote presence and includes, inter alia.

      - Maintenance:

        - Daily inspection and monitoring of the system processes to ensure that all aspects are running at optimal levels.

        - Ensure that all data is received from all lane,

        - Monitoring problem and resolve problem data.

        - Ensure that all ETC transactions is transmitted to TCH,

        - Ensure that all Toll system/AVC/lane configurations, parameters, tariffs, validation lists, balances and hotlists are up to date. Report issues to 2nd Line software support.

      - Support:

        - Fault finding and analysis,

        - Restarting/rebooting systems or processes.

(b)   2nd line Support and maintenance, means the rectification of issues referred to the 2nd line support by 1st line support, reported by the Operator or detected by 2nd line maintenance. 2nd Line support include configuration changes to the system. Only items that require system change will be escalated by the 2nd line support to 3rd Line support, all other issues will be addressed by second line support.

    - Hardware 2nd Line support and maintenance (“2nd Line HW support and maintenance”) relies on HO staff and includes, inter alia.

      - Maintenance:

        - Route wide site inspections to evaluate equipment statuses and calibration. This will include inter alia.

        - reading zones evaluation, processing speed evaluation, loop megger tests, LED intensities, camera quality and alignment, sensor statuses, workstation and server performance assessment,

        - Evaluate, and replace if necessary, underperforming components and sensors identified by 2nd Line Software maintenance or accuracy reports.

        - Routine replacement of components and sensors as part of routine maintenance,

        - Workshop and site technician assessment, including stock level verification,

        - Assist with the deployment of system updates.

        - Generate the required KPI reports

      - Support:

        - Address issues referred to it by 1st Line support.

        - Correct issues that result in data transmission errors between lane (AVC and TCC) and plaza (BOS, DCS, ICS, VGS) and plaza (BOS and DCS) and external entities (TCH, Banks, SANRAL MIS and ITIS)

        - Address communication and network issues.

    - Software 2nd Line support and maintenance (“2nd Line SW support and maintenance”) is normally performed remotely and includes, inter alia.

      - Maintenance:

        - Perform statistical analysis of Toll System data to detect underperforming components or sensors. This shall include inter alia,

          - AVC data to identify sensor issues.

          - Card processing data to identify faulty SCR heads.

          - ETC processing speed in mixed ETC lane to detect hardware or alignment issues,

          - ETC failure rates in Dedicated ETC lane to detect hardware or alignment issues,

          - AVC and TCC resets and incidents

        - Log the findings of the statistical assessment via the support request system (Help Desk) to ensure that it is addressed by 1st or 2nd Line support and maintenance.

        - Deploy Operating System, Application Software and Antivirus/Security updates.

        - Ensure that all versions and configurations are correct. Log deviations via the support request system (Help Desk) to ensure that it is addressed 2nd Line SW support.

      - Support:

        - Fault finding and analysis for items referred to it by 1st Line software support,

        - Restarting/rebooting systems or processes.

        - Generate required KPI reports.

        - Evaluate TCH rejections and raise support request TCH to address unfair rejections.

        - Evaluate Bank charge backs and

        - Correct all incorrect versions and configurations

(c)  3rd line Support and maintenance, means the specialised support or maintenance required to adjust, rectify, configure, correct, or improve the system, when 2nd line support cannot provide the required support. 3rd Line SW support relates to system software changes and the deployment of such changes.

    - Hardware 3rd Line support and maintenance (“3rd Line HW support and maintenance”) relies on external specialists and includes, inter alia.

      - Maintenance:

        - Routine maintenance provided by the specialist supplier in terms of the hardware support agreement,

      - Support:

        - Specialist support provided by the specialist supplier for issues that cannot be resolved without specialist assistance.

    - Software 3rd Line support and maintenance (“3rd Line SW support and maintenance”) is normally performed remotely and includes, inter alia.

      - Maintenance:

        - System updates required by obsolescence.

      - Support:

        - Development, testing (DTEC and SAT), deployment and commissioning (SAT) of system upgrades required to rectify defects,

        - Development, testing (DTEC and SAT), deployment and commissioning (SAT) of system upgrades related to new requirements and/or system enhancements.

        - Comply with the Escrow requirements in terms of Escrow agreement, including the update of escrow deposits as specified.

        - Comply with the Disaster Recovery Plan requirements, including depositing the DRP with the Escrow Agent in terms of the Escrow agreement. “

SECTION 15. GENERAL

Clauses 15.2, 15.5.

SECTION 16. ENFORCEMENT

None.

SECTION 17. PROJECT COMPLETION AND HAND BACK

Clauses 17.1, 17.2 (only for documents and drawings related to the NSC works), 17.3, 17.4, 17.5 (only for subcontracts related to the NSC works), 17.6 (only for assets provided by and/or managed and/or maintained by the NSC), 17.8, 17.9

The completion date for this contract shall be 31 July 2029.

SECTION 18. REPORTING

Clause 18.1.

Add the following new subclause:

“PS18.1.1.8	While it remains the responsibility of the Main Contractor to fulfil the administrative obligation of preparing and submitting all reports under report categories 1 to 4, and 8 to 9, namely Traffic Reports, Transaction Processing Reports, Financial Reports, Audit Trails, Electrical and Mechanical Reports and Performance Measurement Reports in the table below, it remains the obligation of the Contractor to ensure that the Toll System Back Office System is capable of generating these reports.”

Delete Table 18-1 and replace with the following table:

Table 18-1:  	Report Register

| No. | Report Name | Purpose |  | Minimum Information | Frequency |
| --- | --- | --- | --- | --- | --- |
| #### 5. System Maintenance Reports |  |  |  |  |  |
| - a) | AVC Accuracies | Reports on the overall accuracies of the AVC when comparing the AVC class to the Actual Class. |  | - AVC accuracy per lane / Tolling Point. - AVC accuracy for all lanes / Tolling Points. - Reporting generated from Back Office System. | Monthly |
|  | MTBF | Reports on the calculated MTBFs (based on the up time) for all the major subsystems. |  | - MTBF of the sub-systems. - Reporting generated from Back Office System. | Monthly |
|  | System Availability | Reports on the calculated availability (based on the duration of the downtime) for all the major subsystems, per subsystem and/or lane/Tolling Point. |  | - Time the system is in use. - Time spent on maintenance. - Down-time. - Reporting generated from Back Office System. | Monthly |
|  | Equipment Failures Report | Reports on the equipment failures. |  | - Equipment failures per lane/ Tolling Point and subsystem during a selected period. - Reporting generated from Back Office System. | Monthly |
|  | Incident report | Reports on incidents that occurred on the system. |  | - Incident type. - Date and time when incident occurred. - Corresponding Transaction Record (if available). - Summarized incident information per lane / Tolling Point. - Reporting generated from Back Office System. | Ad Hoc |
|  | Response and Repair Times | To report on the incident response and repair time. |  | - Time Incident occurred. - Time when it was acknowledged. - Time when it was resolved / repaired (If applicable). - Reporting generated from Back Office System. | Monthly |
|  | Dashboard | To report on information as supplied by the dashboard Software applications. |  | - Depends on the dashboard Software application. - Reporting generated from Back Office System. | Ad Hoc |
|  | VGS Availability | To report on the availability of the VGS System. |  | - Daily availability checks. - Daily checks consolidated in monthly report. - Check camera views. - Check auto reporting. - Check incident creation. - Check remote availability for Employer. | Monthly |
|  | QLS Availability | To report on the availability of the QLS System. |  | - Daily availability checks. - Daily checks consolidated in monthly report. - Check camera views. - Check auto reporting. - Check incident creation. - Check remote availability for Employer. | Monthly |
|  | VGS Accuracy | To report the accuracy of the VGS system. |  | - Check trigger accuracy. - Check camera availability. - Check incident and image storage. - Check back-up availability. - Check image quality daily. - Consolidate monthly checks in monthly reports. | Monthly |
| #### 6. Other Maintenance Reports |  |  |  |  |  |
|  | Upgrade Reports | To report on upgrades of system or equipment. |  | - System and hardware upgrade information. - Reporting generated from Back Office System and manually. | Monthly |
|  | Problem Data Reports | To report on any data losses, data corruption, data problems. |  | - Transaction Record and payment data lost. - Corrupt Transaction Record and payment data. - Other data problems. - Reporting generated from Back Office System. | Monthly |
|  | Support Reports | To report on all support and maintenance actions. |  | - Number of support requests. - Support request actions. - Problem resolved status. - Reporting from the support Help Desk. | Monthly |
|  | Stock and Spares Reports | To report on stock and spares levels. |  | - Tags in stock. - Spares levels along the route. - Reporting from the Asset Management System. | Monthly |
| #### 7. Accounting and contractual |  |  |  |  |  |
|  | Financial Statements | To report on the financial status of the Contractor. |  | The Contractor shall supply the Employer within ninety (90) days of the end of the operating year the annual audited financial report and accounts of the Contractor as per the GAAP. |  |
|  | Contractual Reporting | To report on contractual issues. |  | The Contractor shall notify the Employer prior to taking any action which would result in any change in: - Management and organisational structure; - Change in appointment of Chief Executive Officer, Chief Finance Officer or any other senior technical staff of the Contractor; - Contracts to be executed by the Contractor for the purpose of implementing the Agreement; - Change in fiscal year; and - Change in Memorandum and Articles of Association or the shareholders agreement of the Contractor; - Any change shall require consent from the Employer as such a change may not alter the shareholder composition in terms of the tendered black economic empowerment content within the original Tender as well as the associated overall financial position of the Tenderer; - Manually created report. |  |
| #### 9. Performance Measurement Reports |  |  |  |  |  |
|  | Performance Measurement Report |  | To report on all the KPIs that is applicable in the Contract in accordance with The Standard Specifications for Operations and Maintenance of CTROM Projects: Performance Measurement (Volume 2 Book 6a). This report serves as input in the performance adjustments in the monthly payment certificate of the Contractor. | - For each KPI, the Performance Measurement score shall be provided for the immediate previous month. - The comparative previous 12 months scores shall also be provided. - The report shall be supported by an Annexure containing the measurements and calculations to determine the KPI scores. | Monthly |
| #### 10. Toll System Progress Report |  |  |  |  |  |
|  | Progress Report | To report on the progress of the Toll System during the Design-Build period. |  | - As specified in Project Document Volume 3. | To be determined by the Employer’s Representative |

Delete table 18-2 and replace with the following table:

Table 182:  Conventional Toll Plaza Additional Report Register

| No. | Report Name | Purpose | Minimum Information | Frequency |
| --- | --- | --- | --- | --- |
| #### Not applicable |  |  |  |  |

Delete table 18-3 and replace with the following table:

Table 183:  	ORT Additional Report Register

| No. | Report Name | Purpose | Minimum Information | Frequency |
| --- | --- | --- | --- | --- |
| #### not applicable |  |  |  |  |

SECTION 19. TOLL ROAD SERVICES

None

SECTION 20. ANNEXURE A1: SCHEDULE OF ASSETS

All clauses.

C3.2.3	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATION FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: ELECTRICAL AND MECHANICAL EQUIPMENT (VOLUME 2 BOOK 3)

The number of each Clause in a Particular Specification in this section consists of the Prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specification for the Operations and Maintenance of CTROM Projects: Electrical and Mechanical Equipment (Volume 2 Book 3). The number of any new Clause which does not form part of any Clause in the Standard Specification for the Operations and Maintenance of CTROM Projects: Electrical and Mechanical Equipment (Volume 2 Book 3), and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Standard Specification for the Operations and Maintenance of CTROM Projects: Electrical and Mechanical Equipment (Volume 2 Book 3).

Only the following clauses shall be applicable to this contract:

Clauses 1, 6, 7, 10, 16, 21, 36.

PS16	UNINTERRUPTED POWER SUPPLY UP TO 50kVA

PS16.3	Technical Requirements

Delete these Sub-clauses and replace with the following:

“PS16.3.1.1 Technology:	Modular UPS systems with at least 3 x Plug and Play type hot swappable/hot plug power modules shall be provided. Two of the modules must be able to carry the required full load of the site with the third as “spare”. The load will be distributed through all three power modules equally when in full working condition.”

“PS16.3.1.3 Rectifier:	    Latest IGBT technology to be used or better”

“PS16.3.1.4			    Low current distortion: 		Less than 5%”

“PS163.1.8  			    Efficiency:				94% full load (AC-AC)”

Add the following new Sub-clauses:

“PS16.3.1.15 		Load Crest Factor:		3:1 Minimum (6:1 preferred)”

“PS1616.3.1.16 	Input current THDi			<5%”

“PS1616.3.1.17 	    Output voltage THDv	  		<2% for linear load”

“PS1616.3.1.18 	    Operating Temperature		-10°C to +40°C”

“PS1616.3.1.19 	    Humidity				95% max non-condensing”

“PS1616.3.1.20 	    Communication			Modbus TCP or RTU”

PS16.4	Nature of UPS Load

Add the following new Clause:

“PS16.4.4 	Volume 2 Book4a requires the installation of additional UPS systems for some Toll System components. The intension of these UPS systems is to provide the specific component with power during a power failure and must be a well-integrated part of the component that is low powered (<350W max) and energy efficient (>90% at 50% of rated current). Larger UPS systems (>350W) that is not an integrated part of the component design will only be considered if an engineering solution is provided for the Employers Representative approval that was designed and signed off by a professional registered electrical engineer. The engineering solution must take the main UPS installation into consideration.

C3.2.4	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATION FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: TOLL SYSTEMS (VOLUME 2 BOOK 4a)

The number of each Clause in a Particular Specification in this section consists of the Prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specification for the Operations and Maintenance of CTROM Projects: Toll System (Volume 2 Book 4a). The number of any new Clause which does not form part of any Clause in the Standard Specification for the Operations and Maintenance Projects: Toll System (Volume 2 Book 4a) and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Standard Specification for the Operations and Maintenance of CTROM Projects: Toll System (Volume 2 Book 4a).

PS1.1	GENERAL

Add the following clauses:

PS1.2	ROLES AND RESPONSIBILITIES

PS 1.2.1 The Main Contractor  and Nominated Subcontractor (System Integrator) roles are:

The Main Contractor and the Nominated Subcontractor (System Integrator) roles are required for the duration of the Operations Service Period. The role of the Main Contractor and the Nominated Subcontractor (System Integrator) may be one Contractor or a Contractor with Subcontractors.

The role of the System Integrator for the Toll System, for the purposes of this Contract is separated. The Contractor, for the Subcontract for the design build, operations and maintenance of the Toll System, will be appointed as a Nominated Subcontractor by the Main Contractor of the Operations and maintenance of Toll plazas.

The terms “Contractor” and “Nominated Subcontractor” are interchangeable, and both are used here within clauses PS 1.2.2, PS 1.2.4 and PS 1.2.3, from the perspective of the Plaza Operation and Maintenance Tender.

PS 1.2.2 Main Contractor

The Main Contractor shall primarily be contracted for all operations and maintenance related to the CTROM Operations contract (inclusive of the Toll System equipment to be provided and maintained by the Nominated Subcontractor).

The Main Contractor shall be responsible for the maintenance of all Employer’s Assets, Facilities and Equipment, as well as the Contractor-provided Assets, Facilities and Equipment.

The Main Contractor shall ultimately be responsible for the management and control of the Nominated Subcontractor. The Main Contractor shall monitor, measure and report on the performance of the Nominated Subcontractor, to ensure that the Nominated Subcontractor delivers in terms of the Employer’s Requirements. The Main Contractor shall be cognisant of the risk allocated in Part C3.2.6 Performance Measurement.

The Main Contractor shall be responsible to provide and maintain a Help Desk and Equipment Record System and will utilise these systems to allocate, monitor and report on maintenance tasks and tickets assigned to the Nominated Subcontractor, and monitor and report the availability of spares.

For the avoidance of doubt, the following aspects will be maintained by the Main Contractor, and not by the Nominated Subcontractor:

- Road signs in dedicated ETC or Shesha lanes

- Electrical and Mechanical works in the toll plazas

- Air conditioners, ventilation systems, toll booths, toll booth fixtures, and the like

PS 1.2.3 Nominated Subcontractor (System Integrator)

The Nominated Subcontractor shall primarily be responsible for the provision and maintenance of the Toll System (inclusive of the maintenance of the existing Toll System handed over at Commencement Date) and possibly parts of the SANRAL MIS .

The Nominated Subcontractor shall provide the necessary personnel, spares, Test or standby rig, and tools to maintain the Toll System, inclusive of the required 1st, 2nd and 3rd line maintenance and Support activities.

The Nominated Subcontractor shall further establish an interface to the SANRAL MIS system and be required to cooperate fully with the new SANRAL MIS Contractor appointed by the Employer, if triggered, and to provide support to this contractor. Cooperation shall include, inter-alia, continuous liaison, information and documentation transfer (where required in terms of the Contract), etc.

The Nominated Subcontractor shall further be required to assist with the swap over to the SANRAL Toll System and be required to cooperate fully with the new SANRAL Toll System contractor appointed by the Employer, if triggered, and to provide support to this contractor. Cooperation shall include, inter-alia, continuous liaison, information, and documentation transfer (where required in terms of the Contract), etc.

PS 1.2.4 Joint Main Contractor and Nominated Subcontractor (System Integrator) roles

The Main Contractor shall design, execute, and complete the Works and provide the Operation Service Period. The Main Contractor shall ensure that the Toll System is fit for purpose.

The Main Contractor shall therefore be responsible for managing and ensuring the Nominated Subcontractor supply and maintains the Toll System. The Employer’s Representative has no direct contractual role with the Nominated Subcontractor (SI). The Main Contractor will therefore ensure that any designs, documents, procedures, specifications, programs, proposals and test results have been verified and that any issues are corrected before submitting such to the Employer’s Representative. The Main Contractor shall also supervise and attend testing to ensure the veracity of tests and test results.

PS2	GENERAL REQUIREMENTS

PS2.1.9	ESCROW Agreement

For any software and/or software product, provided by the Contractor, the required Escrow agreement(s) shall be concluded during the Establishment Period and for initiation of any triggered Design-Build Section and/or subsection. After deposit of the Escrow package, it will be verified and certified by the Contractor prior to presenting the product as compliant to the ER.  Upon compliant certification by the Contractor, the product or service will be verified by agents appointed by the Employer. Full or partial deposits shall be made after successful deployment of any new version or patch of any system software. At least one full deposit shall be scheduled for and executed every two (2) years for the duration of the Operation Service Period.

An existing deposit of the current Toll System was made with the escrow agent (Escrow Europe) as part of Escrow agreement that covers the Efkon/ TolLinkToll System Nationally. Full Verification of escrow deposit and Disaster Recovery Pack is in progress.

The Contractor shall setup and enter into an Escrow agreement with the Principal Employer, the Main Contractor and the Escrow Agent.  The Principal Employer shall be the only beneficiary of the Escrow Agreement, and both the Principal Employer and the Main Contractor shall be able to call on the release of the Escrow, when so provided for in the terms of the agreement.

The Contractor shall be required to ensure that an Escrow agreement, signed by the Contractor, SANRAL and the Escrow agent, is in place and that an escrow deposit is made and fully verified, which includes compilation of source and testing of compiled executables, by the Escrow agent, within two months after the deployment of the Toll system to all lanes. The escrow package delivered by the Contractor shall include the relevant site executables and disaster recovery pack, which shall also be verified by the escrow agent. The Escrow pack and DRP verification report shall be supplied within three months of the deployment of the Toll System to all lanes.”

Add the following subclause:

PS2.1.11.3	Development Work Scheduling

The minimum calibration or maintenance free period shall be three (3) months.

Toll System Related Upgrade Installation and Certification

The Contractor shall compile a programme (Gantt chart), defining the Contractor’s commitment, in order to comply with any triggered Design-Build Section or Subsection requirement during the contract period.  This program shall include the development, upgrade, testing and verification of each component (software and hardware) to be implemented and certified as compliant by the Employer’s Representative during the upgrade and installation commissioning and verification period.

During the Design-Build Period the Contractor is to provide periodic progress reports which shall include the following::

- Charts and detailed descriptions of progress, including each stage of design, for each Section,

- Contractor’s documents, procurement, manufacture, delivery to site, construction or replacement, erection, testing, commissioning, trial operation and provision of Operation Service;

- Photographs showing the status of manufacture or replacement and of progress on the Site;

- For the manufacture or replacement of each main item of Plant and Materials, the name of the manufacturer, manufacture location, percentage progress, and the actual or expected dates of:

- commencement of manufacture,

(ii)	Contractor’s inspections,

(iii)   tests, and

(iv)   shipment and arrival at the Site;

- Records of Contractor’s Personnel and Equipment;

- Copies of quality assurance documents, test results and certificates of Materials;

- List of Variations and Notices;

- Safety statistics, including details of any hazardous incidents and activities;

- Relating to environmental aspects and public relations; and

- Comparisons of actual and planned progress, with details of any events or circumstances which may jeopardise the completion in accordance with the Contract, and the measures being (or to be) adopted to overcome delays.

The progress reports should be submitted to the Employer’s Representative electronically and the first report shall cover the period up to the end of the first calendar month following the Commencement Date. Reports shall be submitted monthly thereafter, each within seven (7) days after the last day of the period to which it relates. Reporting on progress shall continue until the Contractor has received the Contract Completion Certificate.

PS2.3.1	Communication Infrastructure

The Main Contractor and the Contractor is to investigate the Wide Area Network (WAN) currently installed at all the existing Toll Plazas (Kranskop, Nyl, Sebetiela, Capricorn and Baobab) and upgrade and / or replace the existing WAN communication backbone also referred to as Primary Communication Network, from Back Office System to each toll lane/tolling point.  Refer to Part C11 of Volume 4 for the summary of the description of toll system installed.

Note, the following shall apply, should any upgrades to the WAN be required:

The Contractor shall ensure that as a minimum CAT6 Cable is used within the boundaries of the buildings.  Cable provided for any cameras or video servers between buildings shall be connected by means of Fibre Optic Cable or other technology as approved by Employer Representative which is not prone to damage caused by electrical or lighting surges.  The Contractor is also to ensure that where CAT6 (or later high-speed derivatives) or coax cable is being used, such cabling be shielding and earthed at one end only or as instructed by the Contractor surge and lightning protection specialist.

PS2.4.2.5 	Hardware Verification:

Replace (d) with the following

“(d) 	As soon as the Contractor has received all the hardware, workshop tools, test or standby rig and spares required for the project, the Contractor shall submit:

- A Bill of Quantities (BoQ) which lists all equipment with serial and asset numbers,

- Supplier invoices and

- Proof of ownership letters

to the Employer’s Representative, together with an invite to the Employer’s Representative to verify the equipment before installation, to ensure that it is available on time and in accordance with the program submitted by the Contractor. The test or standby rig, workshop tools and workshop spares shall be allocated/packaged per workshop to assist with verification.

The hardware verification will only be deemed successful once this has been achieved, with only minor outstanding hardware items. Verification shall be conducted at least one (1) month prior to the scheduled start of Site deployment date of the system.”

PS2.7.2 	Systems existing at the Commencement Date

A description of the current toll system, the description of the current ISO Bank Card system and associated procedures for the existing Toll Plazas are provided in Part C10 and Part C11 of Volume 4.

PS2.7.3.1 	System upgrades

Table 5-1: System upgrades

| Sections | Description | Implementation required. (The list of items highlighted here is not exhaustive) |
| --- | --- | --- |
| Section 1 | Establishment period | No new deployment required. The Contractor shall utilize this period to establish the necessary technical resources and acquire all sub-contracts, training, system / network user access credentials and documentation required to maintain and operate the existing Toll System provided at hand over. |
| Section 2 | Existing compliance level: Functional Compliance with the CTROM requirements plus Establishment Upgrades (critical replacement upgrades). | The Contractor shall provide for Establishment Upgrades to the Toll System (Clause 2.7.3.2 in Book 4a). The Contractor shall maintain a high level of the current system performance by appropriate routine and corrective maintenance processes. |
| Section 3 | The supply of a complete Toll System, including additional items detailed in V3B1. (This section runs in parallel with Section 2 and contains the following sub-sections 3.1 to 3.9) | The new deployment shall include, but not be limited to: - Replace and/or upgrade the hardware and software for the complete system to comply to the requirement in Volume 2 Book 4a requirements. Hardware and software replaced in Section 2 (for critical replacement upgrades) may be utilised, but the Toll System handed over must be replaced (as described in more detail in the Toll System Description document in Volume 4 Part C11). - The complete Toll System, except for triggered items and items replaced in Section 2 above, shall be replaced while the old system is maintained and supported. All relevant data shall be ported, reconciled, and closed-off by the Contractor during the upgrade. This process shall include the removal and disposal of all equipment in line with the Employer’s Disposal Policy. - The current ETC OHLS’s (“e-sign”) shall be retained and integrated into the new Toll System. These OHLS shall only be replaced when it is agreed to by the Principal Employer. - All the lanes shall be equipped to operate as Mixed ETC lanes. In addition, lanes will be equipped to operate as Shesha lanes, 14 at Kranskop, 12 at Nyl plaza, 6 at Sebetiela plaza, 7 at Capricorn plaza and 4 at Baobab plaza. Furthermore, some of the Shesha lanes shall be equipped to operate as Dedicated ETC lanes, 2 at Kranskop plaza, 2 at Nyl plaza, 2 at Sebetiela plaza, 2 at Capricorn plaza and 2 at Baobab plaza. - No Card Only lanes are required. - Lane and plaza network upgrades - Supply a full complement of spares, tools and a standby rig. - ANPR, including VLN presence detector in all lanes (if pilot is successful and if triggered). - Health monitoring TCC, BOS, VGS, LSDU, DCS and PGW. - Configuration management for the Toll and VGS/QLS System. - Deploy the OPS level server and the TCH payment gateway at the Server room of the most suitable Control Centre on the Toll Road, as approved by the ER. New payment gateway and OPS level server. - Manage and implement a direct fibre connection, utilizing the national SANRAL WAN where / when available at the most suitable Control Centre on the Toll Road, as approved by the ER. - Upgrade all lane level UPS units and batteries. - Add external EMV contactless card readers (light and heavy vehicles) to all mixed ETC lane (if triggered). - Queue line 1 system for the mainline plaza, both directions. - PCI (level 2 merchant) implementation and certification, - Upgraded WAN, firewall and associated equipment. - Implementation of the basic SANRAL MIS interface (as specified). - Assessment of the Toll System in terms of the national SANRAL Toll System requirements. - Relocate two sets of Dedicated ETC equipment from Kransko to Capricont plaza. This Section contains sub-sections 3.1 to 3.9 defined below, but the Section itself can only be completed if the complete Toll System has been commissioned. |
| Section 3.1 | AVC/DCS: | Count and class accuracy, redundancy, TCC interface, DCS interface, ITIS submission, health monitoring, version control and KPI |
| Section 3.2 | Dedicated ETC lane: | ETC accuracy and processing speed, TCH submission, health monitoring, version control and KPI (if triggered) |
| Section 3.3 | ANPR: | Transaction framing, ANPR accuracy and capture %, ANPR TCH submission, ANPR incl control (ANPR fail, like class fail integration), health monitoring, version control and KPI |
| Section 3.4 | Bank card processing: | Lane level validation, Tap and go, processing speed, PCI, health monitoring, version control, Bank interface, VAT and KPI |
| Section 3.5 | Cash processing: | Lane level process, processing speed, health monitoring, version control and KPI |
| Section 3.6 | Discount and concessions: | Lane level process, processing speed, discrepancy handling, tariffs structure, validation list accuracy, health monitoring, version control and KPI |
| Section 3.7 | Incident control: | Lane level process, Control room process (class/VLN fail, serious/critical mode, other), image capture, processing speed, images to TCH, health monitoring, version control and KPI |
| Section 3.8 | VGS system: | Lane level implementation, transaction framing and video/image extraction, VGS audit/VGS clerk interface, processing speed, images to TCH, health monitoring, version control and KPI |
| Section 3.9 | QLS and QL system: | Queue detection, Queue reporting, queue audit, Control room process and queue reporting to incident control, image capture, processing speed, health monitoring, version control and KPI |
| Section 4 | The deployment of the SANRAL MIS (If triggered item). | The Contractor shall design, test and implement the necessary modifications and interfaces to accommodate the SANRAL MIS. The SANRAL MIS requirements, specifications and test application will be issued to the Contractor at least 6 months before the completion of this Section. The deployment shall include the full 2010 CTROM requirements, as amended by V3B1 and adjusted by the implementation of the SANRAL MIS. The deployment shall Include a six (6) week pilot phase during which operational testing shall be conducted for the SANRAL MIS in parallel to the Toll System MIS. This scope shall include the work required by the Contractor to achieve revised compliance certification. |
| Section 5 | The deployment of the national SANRAL Toll System (If triggered item). | The Contractor shall design, test and implement the necessary modifications and interfaces to accommodate the national SANRAL Toll System during parallel operations (Pilot phase and initial roll-out). The national SANRAL Toll System requirements, specifications and test application will be issued to the Contractor at least 8 months before the completion of this Section. The deployment shall include the full 2010 CTROM requirements, as amended by V3B1 and adjusted by the implementation of the SANRAL toll system. The deployment shall include a three (3) month pilot (Parallel operations) and trial operations phase during which operational testing shall be conducted for the SANRAL Toll System. This scope shall include the time required by the Contractor to achieve revised compliance certification. |

Note: The duration of the different Sections is specified in clause C1.2.3 APPENDIX 1 TO CONTRACT DATA:  SECTION DATA of PART C1.

PS2.7.3.2 	Establishment Upgrades:

Add the following below (l)

“(m)	All servers older than 5 years, including DVR and associated storage,

(n)	All lane and AVC controller components, older than 5 years, including motherboards, CPU, RAM, serial cards, I/O cards, hard drives, PSU, and Lightning, surge, and overvoltage protectors.

(o)	All lane VDU’s and Toll Collector terminals older than 5 years.

(p) 	Upgrade all Microsoft OS to Windows 11, Windows server 19 or later and SQL server 2019 and replace incompatible hardware.

(q)	Replace all non-IP cameras, and associated network infrastructure, with POE IP cameras.

The Contractor shall ensure that the hardware provides an open platform that can accommodate virtualization, various operating systems and conform to open standards. All hardware shall be submitted to the ER for approval and distribution to SANRAL to confirm compatibility with the SANRAL MIS and SANRAL Toll System.”

PS3.3 	Toll Lane Specific Hardware and Software Requirements

PS3.3.2	Toll Collector Computer

PS3.3.2.1

Delete: ” and shall be powder coated matt black on the inside to aid in heat absorption”.

PS3.3.3  	Toll Collection Terminal (TCT)

Add the following sub-Clause:

“PS3.3.3.3

Each TCC and peripheral equipment required to continue the operational tolling activities need to be powered by an independent Uninterrupted Power Supply (UPS) with sufficient reserve capacity to power the TCC and TCT for a minimum of four (4) hours in the event of a failure of the plaza UPS.  The exit barrier(s), traffic lights and siren need not be powered this independent TCC UPS.  Depending on the lane specific characteristic, the ER may consider and approve alternative battery backup solution combining the AVC, TCC, TCT and peripheral lane equipment of maximum three (3) toll lanes to a single power backup source.  Failure of one (1) power backup source shall not result in all the toll lanes at any virtual toll plaza and fall state.

Ramp Toll Plazas with limited lane processing capacity shall be evaluated on a feasibility and security evaluation basis.”

PS3.3.6

After the existing paragraph add the following:

“The panic button alarm functionality shall in no way be effected by any toll system failures, including LAN failures.”

PS3.3.8	Toll Booth Surveillance Camera

This clause to be modified to read as follows:

“The Contractor shall install, operate, and maintain a tamper proof dome or similar camera in each toll booth for surveillance purposes.  The camera shall have a wide dynamic range capability in order to accommodate the glare through the toll booth windows.  The continuous recording of this camera images shall be stored on the DVR’s at 10fps and kept for a minimum period of three (3) months.”

PS3.3.8.1

This clause to be modified to read as follows:

“The video and the audio recordings from the toll booth surveillance camera shall be accessible remotely by the Contractor, Main Contractor and Employer’s Representative for post factor audit purposes on an Ad Hoc basis.”

Add the following new subclauses:

“PS3.3.10	Dedicated ETC Lane

The Dedicated ETC toll lane shall, as a minimum, comply with the following requirements:

Within the guidelines of the ETC specification as described in Volume 2 Book 5, a Dedicated ETC lane shall be operated without any toll collector management or intervention required. Under normal operational conditions, no manual vehicle classification shall take place in these lanes and the User shall be granted passage through the toll lane with the least obstruction or delay during and after validation of the tag credentials. The automated control shall prohibit unauthorised vehicle passage through such toll lanes.

The lay-out and pictograms to be used (Red-cross, Green-arrow and e-sign) will be finalised before or during the design phase (V2B4a clause 2.4.2.2)

Under abnormal vehicle processing conditions, the Employer’s Representative may require the Main Contractor to process non-tag vehicles through these Dedicated ETC lanes, requiring manual vehicle classification - see further requirements reference in this regard.

The Contractor shall ensure that:

- Functionality is provided for a supervisor to take responsibility of transactions being processed. The functionality shall allow for the responsible Supervisor to remotely login and logout from the lane and to open and close the lane remotely by means of controlling the OHLS combination. The Supervisory staff shall be capable of opening the exit boom remotely in the event of an emergency. The same functionality shall be available from within the lane area, after gaining access to the secure cabinet containing the TCC and TCT equipment, similar than that found in a Mixed/Manual ETC Lane;

- The TCC shall monitor the tag reader, other lane processes and peripherals components continuously. If any reader or peripheral component or process failure is detected the system shall report such status in real time to the Supervisory personnel. This shall include AVC error or fail conditions. Where the AVC is in any critical fault/error state simultaneously, the TCC shall evaluate the severity of any detected failure or failures in terms of the system’s ability to maintain its accurate and correct functioning. In the event where the lane is not capable of performing to meet the minimum required integrity levels as required, the system will automatically change the OHLS state to a closed lane state. The OHLS will be turned to the RED “X” and the amber “e” turned off. The software shall automatically follow-up the error or fault state to ensure the Supervisor takes the required corrective action immediately and in order to address any vehicles which might be stuck in such toll lane. The Supervisor shall be capable to override the boom status to the open state in association with proper transaction audit controls and procedure ensuring complete recording of such passage, with no financial risk is passed to the Employer. The Supervisor shall be provided the required tools to resolve the problem in the lane remotely. In the event of a vehicle being present in the lane during the time of the failure, the operator shall ensure that the vehicle is processed using one of the following methods outlined in Subclause 6a) below, (Alternate tag transaction processing methods). The Contractor shall ensure that a legal and valid user, be granted a passage, with the least possible inconvenience caused to the motorist / User;

- Tags are not read prematurely while other vehicle(s) is/are still passing through the lane. However, if such a scenario occurs the system shall be able to track, stack/queue and associate and link the correct tag and VLN information with the correct physical vehicle as recorded in the system transaction record.  As each vehicle or vehicles passes through the Dedicated ETC Lane and the AVC area, removing such unique vehicle from the system transaction queue;

- The Contractor shall ensure the accurate processing and associated AVC classification, of each vehicle, including vehicles being processed, in a queue, be accurately recorded and transmitted to the Back Office like any other transaction, when concluded. The Dedicated ETC toll lane/s shall be capable of processing any vehicle in accordance with the vehicle characteristics and associated vehicle classes, as published in the Government Gazette from time to time. For safety reasons it may be required that specific lanes be equipped with height restriction structures in order to avoid large heavy vehicles to enter such specific toll lanes.  The presence of any such height or other restriction shall in no way alter any detection and classification requirements of the AVC;

- The above is supported by the required logic on the TCC and AVC to accurately detect, classify and reconcile individual vehicle units and their associated axles when exiting the Dedicated ETC toll lane area. The system shall contain sufficient automated error handling in order to manage incoming and exiting vehicle transaction with discrepancies on an ongoing basis without human supervision or maintenance intervention;

- The tag reader does not detect tags from adjacent toll lanes and the local DSRC message shall not interfere with the data communications in any adjacent lane/s. (The objective being the restriction of RF spillage);

- If multiple tags exist in the same vehicle only one tag (or the first valid tag) is used to process the vehicle’s passage transaction.  Multiple tags detected needs to be reported to the supervisory staff in order to validate the period verifying that vehicle was not missed or additional transactions recorded, where these were not physical vehicles associated with the addition tag read;

- While the TCC and AVC keeps track of vehicles passing through the lane in a forward direction, the system logic shall also take care of any vehicle (or part thereof) reversing out of the toll lane or driving into the active lane in a reverse direction. Given the close proximity of typically two axle counters in the entry zone of the lane, the timing of axle and other vehicle presence signals should indicate whether, the vehicle, which was busy passing through this entry zone, was moving forward or in reverse direction. The system shall ensure that pending transactions be recorded, although “cancelled” as financial transactions, as and when systematically confirmed that it will not be financially processed, Buffers are cleared and all pass back timers removed as the vehicle units reverse out of the entry zone. This would imply that should an invalid tag-User enter the lane and valid tag-Users follow, the valid tags, will not enable the invalid Tag-User to pass through the lane and similarly, as vehicles reverse out of the lane, the valid Tag-Users will immediately be allowed to enter the same lane and be processed successfully after the invalid Tag-User was removed from the lane and system queue.

- If a tag reader in the working state fails to read a tag due to a tag failure, or invalid tag, or false or failed tag, or no tag present, the vehicle is processed using one of the following methods outlined in Clause 6a) below (Alternative processing methods). The Supervisor shall notify the road user of the faulty or invalid tag and shall direct him to the next toll lane to conclude a non-tag toll passage transaction as well as to the nearest service centre where the problem can be rectified. This is performed through the messaging on the UFD, the Traffic Light not turning green and the intercom, where installed;

- The tolling system shall record and automatically report all abnormal tag or other identifier processing (Payment Mechanism Identifiers) identified in order to force the Contractor to resolve the cause of transaction processing errors. The Contractor is to systematically follow-up problem transactions, account holders and problem identifiers in order to eliminate vehicle processing delays, causing a reduction in processing capacity;

- All relevant video recordings and image material are captured and accurately associated/linked to the correct vehicle passing through the toll lane and the tag transaction record, as stated in volume 2 book 5, in addition to the standard manual transaction records.  e A quality front side and number plate (ANPR camera) images are a requirement as per the TA/TCH interface “Request Image” function;

- The Dedicated toll lane shall not facilitate the printing of receipts in the lane since all Users passing through these lanes would be registered Account holder Users who could obtain transaction details and TAX-Invoices via the Service Centres. The exception would be in the event when the toll lanes are manned, under the abnormal vehicle processing procedures;

- The Road User does not have the ability to communicate with the remotely stationed Supervisor or with the service centre without leaving his/her vehicle. Road users are required to reverse out of the Dedicated ETC lane and seek assistance in a manned lane;

- The manual processing of a tag transaction can be done remotely. This will require a live interface which will allow for the remote capturing of VLN data and verification against the TCH Validation List to conclude or reject such passage transaction. The Contractor shall ensure that such facility is active and available to remote supervisory personnel at all times, in order to facilitate the and resolve any problem in any lane without any delay.

- The Supervisor has the ability to remotely view the vehicles license number plates from the front and the rear.

- The Road User does not have the capability to scan his own tag in the lane without having to leave his/her vehicle, or move to a manned lane, to verify the tag and conclude the toll transaction in an alternative manner unless otherwise described in Volume 2 Book 5.

- The Supervisor has the ability to remotely reset the lane if required and to clear all buffers, including queuing vehicle data buffers. If the reset of such is performed in the lane area directly on the TCC, such action shall be restricted to authorised personnel.  Such activities shall be logged and monitored to ensure no vehicles pass through such lane while the system is not fully operational. Such facility is typically provided through a high-grade tamper proof security key switch.

- The Dedicated ETC toll lane functionality and efficiency shall be verified by means of verifying the vehicle processing capability by processing mixed vehicle class combinations through the lane at a speed of 60km/h and continued queuing conditions. This ability shall include the safe and accurate functioning of a high-speed exit boom/barrier, with the ability to open and close in 0.6 seconds. The exit boom/barrier will not be required to close on vehicles following too closely (tail gating), avoiding damage.  However, the Contractor should install an additional traffic light, alarm bell and amber strobe light, upstream from the exit boom in order to warn and stop any User entering the Dedicated ETC toll lane where the passage transactions could not be processed successfully. The lane shall be required to accurately, separate, detect, queue, record, validate and exchange the required data elements, pass back the acknowledgement to the Tag (MMI Beep Message) and have the AVC classify and close off or conclude the passage transactions on a continuous basis as vehicles pass through the lane. The Contractor shall maintain a Dedicated ETC processing accuracy of better than 98% for all valid, at the time of the transaction, tags that enter the Dedicated ETC lane, verified via the registered VLN, measured over a sample size of 5 000 valid tags. The Contractor shall implement a Dedicated ETC lane monitoring and reporting tool that uses the ANPR cameras in zone one (1) and three (3) to identify ETC processing accuracy deterioration below 98% within three days. The monitoring tool shall also report on any un-characteristic (above the benchmark) increase, based on percentage of passages (moving average over a 3 to 5 day period), in the percentage of vehicles reversing out of the lane. Such an increase may be point to a possible hardware deterioration e.g. reader alignment or sensor calibration or blockage. Accuracy problems shall be reported to the lane health monitoring system. The dedicated lane monitoring tool shall also report excessive, more than 4 hours, down time (lane not open for traffic and/or not processing traffic) of dedicated lanes to the health monitoring tools.;

- The design capability of the complete Dedicated ETC toll lane shall be based on the required vehicle processing ability associated with an individual or stream of vehicles passing through the toll lane at 80km/h, without any failures detected. Although the system shall be required to operate at the above speed it might be required that the Main Contractor enforce speed reduction in such lane. Such forced speed reduction facility shall be made available by enabling the Contractor to configure the exit boom opening time or delay or alternatively a tag processing delay.

- The Dedicated ETC toll lane functionality shall be capable of recording all the required transaction/data elements as required associated with any Violation or Run-Through passage, in order to activate the required follow-up actions in order to charge or prosecute such User through the appropriate channels, including the legal requirements. Also see VPC requirements for Opt-In contracts which may require different image recording requirements.”

NB: Cross Reference note: The Main Contractor shall, at all times, ensure that any User who approached a Dedicated ETC toll lane, be able to process a tag transaction through a toll lane immediately adjacent to the Dedicated ETC toll lane in the event of such lane failing. This requirement is a safety critical requirement and shall be adhered to at all times. It shall never be allowed that any User would need to cross any active or open toll lane when re-directed to another tag transaction processing toll lane. Failure to provide this service to the Users shall result in an immediate penalty for each vehicle required to any other that the adjacent toll lane. (Refer Volume 3 Book 1.) The reason for the above is to ensure that Users do not need to cross the Toll Plaza approach area in the event where any Dedicated ETC toll lane is closed to traffic.

Dedicated ETC toll lane equipment configuration guidelines. The typical Dedicated ETC toll lane consists of the following:

- Longer civil lane than that employed for Manual or Mixed/Manual ETC toll lanes;

- The lane is equipped with typically three (3) operational zones:

- an entry detection, reader and transaction verification zone;

- A central queuing zone and;

- An exit, AVC and transaction reconciliation zone.

- The entry detection, reader and transaction verification zone (Zone 1): This is a traffic calming and speed reduction zone which facilitate the initial vehicle presence detection, direction of travel and the axle count of the single vehicle unit. At the same time the DSRC communication is initiated and concluded before the vehicle exits the reading zone. Typically, a double light curtain and double axel counter, directly under the light curtains provide the system with presence, direction and axle count data for each unit entering the zone. A DSRC reader is typically installed from the canopy to establish the correct reading zone around the sensors below at road pavement level.

- The central queuing zone (Zone 2): This zone provides both vehicle storage capacity before reaching the exit boom/barrier as well as providing the vehicle sufficient room to safely stop before the exit barrier in the event of the vehicle passage being refused. This area is also employed to accommodate an additional traffic light, an electronic alarm bell/siren and strobe warning light/s. The traffic light goes green during successful transaction processing and the alarm bell plus strobe light remains off. However, in the event where a passage transaction is refused, this upstream traffic light will turn red, the strobe light flash to warn the User or users of a transaction which is being rejected or that of a vehicle ahead is being rejected. The UFD will also change reflecting the fault or error state with a meaningful error message or instruction. The exit barrier/boom will allow the valid transactions and associated vehicles to pass through the lane. The barrier will drop, if safe, to stop the rejected transaction passage vehicle. Typically, no monitoring of vehicle’s presence or direction is performed in this area.

- The exit, AVC and reconciliation zone (Zone 3): This zone consists of the exit barrier/boom, AVC, Traffic Light and UFD. Given the requirement to exactly separate individual vehicles, light curtains are typically employed to determine vehicle presence, direction and axle counters for direction. Accurate axle counts in this area is important in order to reconcile vehicles that entered the lane and those which exit the lane. The logic of the system should allow for the management of error handling and axle count differences. In order to provide some degree of redundancy, an additional DSRC reader is also installed in this area, identical to that of a standard Mixed toll lane. This allows the Main Contractor to convert such Dedicated ETC toll lane to a “standard” Mixed/Manual ETC toll lane (with or without vehicle queuing facility), should the entry beacon fail. ANPR cameras will be installed in zone 1 and 3 and will be triggered by the light curtain to ensure optimal ANPR capturing for vehicles entering and exiting the DETC lane. The ANPR value captured by the exit zone ANPR camera will be link and verified against the VLN of the associated tag user of the vehicle exiting the lane.  The DETC lane will generate an incident to report cases where users without tags, users with invalid tags, or with valid tags with the wrong vehicle is exiting the DETC lane.

- The reconciliation process also allows for the triggering of the alarm bell and strobe light/s in the event where vehicles enter the AVC area without a valid passage transaction being processed for the associated vehicle. Such events are managed in accordance with violation or Run-Through passage procedures since the Main Contractor remains responsible for toll income related to such Run-Through Violations.

- All Dedicated ETC lanes on the N1N shall be configured as “Switchable ETC toll lanes” (The Main Contractor has may use the lane as a Dedicated ETC toll lane or as a Mixed/Manual ETC toll lane or as instructed by the ER or the Employer) it shall be required that the “Exit, reconciliation zone be installed exactly the same as that configuration used in Mixed/Manual ETC toll lanes, except for the deployment of light curtains or similar device which is capable of accurately detect and separate vehicle units. Whether a toll booth is installed or not, the Main Contractor could station a toll collector in the island area and instantly have additional vehicle processing capacity available, accommodating all other Payment Mechanisms. (Refer to Volume 3 Book 1 for further details and instructions).“

General

- All Sensors installed in the Dedicated ETC toll lane carry the monitoring and redundancy requirements as applicable to other AVC sensors. However, the Contractor should take cognisance of the financial and penalty risks associated with the failure of any sensor in the Dedicated ETC toll lane. It is critical to implement multiple levels of redundancy to limit or eliminate system deterioration, downtime and restrict/limit maintenance. For safety and operational reasons maintenance should be restricted to off-peak periods when the Contractor is not at risk of being penalised for both downtime, Vehicle Processing requirements and/or possibly vehicle queues at the Toll Plaza.

- The Contractor shall at all time ensure the correct and automated functioning of the combined OHLSs. The Green Arrow and Red Cross shall be located to the left and the amber “e” on the right of the lane centre line, on the Toll Plaza canopy above such lane. For Dedicated ETC toll lane Operations ONLY the amber “e” shall be illuminated while such lane is open to tag passage transaction processing. In the event where the lane is operated as a Mixed/Manual ETC toll lane, both the Green Arrow and the amber “e” shall be illuminated while such lane is operational. While any Mixed/Manual ETC or Dedicated ETC toll lane is in a fault state or in the closed state, ONLY the Red Cross shall be illuminated. Refer to Volume 2 Book 5 for pictograms of the OHLS’s.

Alternative vehicle and transaction processing methodologies.

- Notwithstanding the possible requirements to process tag transactions manually as noted elsewhere, the Dedicated ETC toll Lane shall facilitate the manual processing of tag transactions or other Payment Mechanisms in the event of a read or related failure. The lane shall be equipped with a secure non-ferritic, 304 stainless steel enclosure to accommodate a TCT for use in the event of abnormal processing conditions. The Contractor shall make it possible to process alternative Payment Mechanisms if the tag cannot be processed and/or the vehicle cannot be removed from the lane. It should be noted that such abnormal processing of passages needs to be limited and avoided at all times unless instructed by the ER or the Employers to do otherwise.

PS3.3.11	Dedicated ETC Toll Lane Equipment and Configuration Option

- Given the real time and active monitoring of the Dedicated ETC toll lane TCC by the Back Office System User Interface, and the real time monitoring of the AVC by the DCS, and the known error/failure rate of the serial communications between the conventional AVCs and TCCs, the Contractor is encouraged to run the Dedicated ETC TCC lane controller application and the AVC application on the same Controller, pending the approval of the Employer’s Representative based on a sound technical proposal to maintain and guarantee 100% up-time and secure continuous error free vehicle processing capabilities by such Combined Lane Controller. Should such option be considered, the Lane Controller shall be required to maintain two (2) independent data communication channels, one from the TCC application to the Back Office and the other from the AVC application to the DCS.

- Dedicated ETC toll lanes are required to be Operated, in a reversible manner, without the loss of any management and control characteristics required.  See required reversible lanes at Kranskop, Nyl, Capricorn and Baobab Mainline and Sebetiela Ramp Toll Plazas.

- It is required to provide the option to operate a “Switchable” Dedicated ETC toll lane as a Mixed/Manual toll lane. In this configuration the TCC in such lane will be located in a toll booth and the only difference to that of a permanent Mixed/Manual ETC toll lane shall be that these lanes shall be “Switchable” between processing tag transactions without toll collector intervention – no MVC Classification before processing the tag transaction. This opposed to the ability of the TCC to switch to the “Mixed/Manual toll lane” functionality, requiring the forced manual vehicle classification by the Toll Collector on duty, before the tag transaction could be processed. The lane in this “Mixed/Manual ETC Lane” state shall be capable of processing all other payment mechanisms as applicable in a standard Mixed/Manual ETC toll lane.”

- The current “Tag-Only or Shesha” toll lanes, deployed at Kranskop, Nyl, Capricorn and Baobab Mainline and Sebetiela Ramp Toll Plazas do not meet the requirements and are the same configuration as Mixed/Manual ETC Toll Lanes with the exception of the use of an “Auto-class” function, allowing the toll lane to operate without any Toll Collector present, allowing tags to be processed automatically.  Given the above, these lanes do not meet the vehicle/tag processing speed defined for Dedicated ETC toll lanes.

PS3.4.6	Ramp/Mainline Swapping

The ramp / mainline swapping functionality is required at Kranskop Toll Plazas.  This functionality has been implemented to date and is available to the Contractor.

Any additional cost for software and / or hardware that is required to meet this functionality must be included in the schedule of Payment/Cost Matrix.  The Contractor is to note, that the Principal Employer may only trigger ramp/mainline swapping functionality on one (1) direction in a Toll Plaza or both.

PS 3.4.8.	Automatic Number plate recognition

Replace clause with:

“3.4.8.1 The Contractor shall implement ANPR in every lane.

- The ANPR system shall be utilised whereby front Vehicle Licence Numbers images will be captured for each vehicle passage, in addition to the requirement for Scene Image/s captured by the VGS.

- An additional ANPR camera will be required for Zone 1 of the DETC lanes. The Zone 1 camera will be used for the DETC entry detection and the Zone 2 for transaction reconciliation.

- The VLN captured by the ANPR and ANPR confidence level shall be stored for every transaction. A VLN value of “No VLN” and a ANPR confidence level 0 shall be stored for all transactions for which, for whatever reason, no ANPR VLN is available.

- The ANPR or OCR engine/s shall reside with the ANPR camera. Additional ANPR may be done centrally, at BOS level, to improve the ANPR accuracy.

- The ANPR camera shall include infra-red illumination to allow for the accurate capturing of VLN under low light conditions.

- The ANPR camera shall be linked to a trigger device. The trigger device shall consistently detect the arrival of a new vehicle and shall trigger when the VLN reaches the optimal ANPR capturing location. This shall ensure the accurate capturing of the VLN for vehicles at the pay-point or in the case of Mixed or Dedicated ETC lanes, the ETC reading zone. The detection device shall accurately trigger the ANPR camera even under high traffic conditions. The Contractor shall not consider trigger devices that cannot accurately separate vehicles.

3.4.8.2 The lane ANPR camera shall utilise advanced image processing techniques to enhance the ANPR process accuracy and that will minimise operator intervention. The ANPR process may use the VLN associated with registered identifiers, including Tags, Bank cards and TA cards, to improve the accuracy and speed of the ANPR process. The Contractor shall disclose the design, the algorithm/process used by the ANPR system when using registered VLN values to assist with determining the ANPR VLN to the ER, for approval.

3.4.8.3 The ANPR system shall capture Vehicle Licence Numbers images and process them to

establish the VLN for every transaction. The image used by the ANPR camera/system to determine the

VLN shall be kept at BOS level, accessible via user interface that allow easy search, retrieval and

reporting (Hard or soft copy), along with the side and front view images as follows:

| Item | Description | Images to be stored | Period to be stored measured from time of associated vehicle passage |
| --- | --- | --- | --- |
| 1) | VLN mismatches: Transaction where the registered VLN (TCH Validation list, local and frequent user account holder) and ANPR VLN do not match. The images associated with TCH validation list mismatches may be required to be transmitted to the TCH via the TCH interface, on request from the TCH. | VGS front view and side view images. The VGS images ANPR images used to determine VLN (Number plate and front view) | 6-month storage as part of the system active data |
| 2) | Violation: This includes all passages for which no payments were received | VGS front view and side view images. The VGS images. ANPR images used to determine VLN (Number plate and front view) | 6-month storage as part of the system active data |
| 3) | Exempt / free passage Transaction | VGS front view and side view images. The VGS images ANPR images used to determine VLN (Number plate and front view) | 6-month storage as part of the system active data |
| 4) | ETC transactions | VGS front view and side view images. The VGS images ANPR images used to determine VLN (Number plate and front view) | 6-month storage as part of the system active data |
| 5) | All other transactions | ANPR images used to determine VLN (Number plate and front view) | 2 weeks as part of the system active data |

3.4.8.4 ANPR and/or OCR engine, shall automatically populate the front ANPR processed Vehicle Licence Number field of the Transaction Record (it is envisaged that the association of the Transaction Record will be performed at the toll collector computer) for all the transactions, and shall the ANPR confidence level.

3.4.8.5 The criteria for correctly mounted and designed South African Vehicle License Number (VLN)

plates shall be in accordance with South African legislation. Legislation on the construction and use of

VLN plates can inter alia be found in the National Road Traffic Act 1996 (Act No. 93 of 1996) and the

National Road Traffic Regulations (1999). Applicable specifications include SANS 1116-1 (SABS 1116-

1) Parts 1 to 4 (Retro-reflective number plates for motor vehicles).

3.4.8.6 A VLN plate is classified as ‘readable’ for the purposes of performance measurement if it is readable to a human enumerator. The following are examples of plates that would not be classified as readable;

(a) One or more characters obscured by a bulbar,

(b) One or more characters obscured by dirt or mud,

(c) A plate that is damaged such one or more characters cannot be enumerated, or

(d) A plate that is missing, etc.

3.4.8.7 Consequently, cameras that are not in focus, tend to over-expose images, are misaligned, not triggered at the right moment, suffer from headlamp glare or the effects of weather or direct sunlight, vehicle queues, are not of sufficient quality and resolution, would not be sufficient grounds for a plate to be considered unreadable at the time of performance measurement.

3.4.8.8 The ANPR processes shall have the capability to interpret all existing and future VLN plate alphanumeric character sets and VLN plate formats for vehicles registered in South Africa.

3.4.8.9 The ANPR processes shall have the capability to interpret all existing VLN plate alphanumeric character sets for foreign vehicles, including vehicles registered in Zimbabwe, Eswatini, Mozambique, Botswana, Namibia and Lesotho. The ANPR process shall report a confidence level and whether the plate is national or foreign.

3.4.8.10 ANPR ACCURACY AND MONITORING

3.4.8.10.1 The ANPR system must facilitate, along with the image quality and OCR Software or OCR engine, an overall accuracy rate as listed below under all operating conditions, or if such accuracies are specified within the Standard Specifications for Operations and Maintenance of CTROM Projects: Performance Measurement (Volume 2 Book 6a), then according to those accuracies.

3.4.8.10.2 For the purpose of this specification, the following terms, and accuracies, based on a sample size of more than 10 000 passages (per lane or group of lanes) shall be defined as follows:

  - “Trigger rate” is the proportion of vehicles (whether or not the Vehicle Licence Number is readable) that pass through the ANPR capture zone that result in a Vehicle Licence Number image i.e. the OCR result may be wrong but at least the Vehicle Licence Number is completely visible and the camera was not triggered falsely. The ANPR system shall in more than 99% of passages capture VLN images for vehicles traveling slower than 60 km/h.

  - “Capture rate” is the proportion of vehicles with a readable Vehicle Licence Number that pass through the ANPR capture zone that result in a usable image i.e. the OCR result may be wrong but at least the Vehicle Licence Number is completely visible, the camera was not triggered falsely and a human operator can read the Vehicle Licence Number. The ANPR system shall in more than 98% of passages capture VLN images for vehicles traveling slower than 60 km/h.

  - “Correct read rate” is the proportion of vehicles that pass through the ANPR capture zone with a readable Vehicle Licence Number that is visible to a human operator and which was interpreted correctly by the OCR engine or ANPR process(es). The ANPR system shall in more than 98% of passages analyse the capture VLN images and determine the correct VLN for vehicles traveling slower than 60 km/h.

  - “ANPR confidence level assignment” is the proportion of vehicles value that pass through the ANPR capture zone with a readable Vehicle Licence Number that is visible to a human operator, and which was interpreted by the OCR engine or ANPR process(es). The ANPR system shall in more than 85% of passages assign an ANPR confidence level of more than 80 (out of 100) for correctly assigned VLN numbers and a value below 40 (out of 100) for incorrectly assigned VLN numbers. The Confidence thresholds may be adjusted by the ER at the Employers discretion.

3.4.8.10.3 In addition, the TCC shall indicate the confidence level, a value between 0 and 100, for every transaction processed via the OCR engine(s) and ANPR system, and if this is below a minimum configurable threshold, and it is required for the type of user, then the Toll System shall allow an operator/System User to manually review and enter a Vehicle Licence Number.

Multiple OCR engines may be required to improve OCR confidence and reduce the number of images requiring manual review and/or verification.

The Contractor shall implement an ANPR, QLS and VGS Pilot project at the Nyl Mainline toll plaza to prove the ANPR and VGS functionality and accuracy before procuring ANPR hardware for any of the other toll plaza. Formal design approval and functional compliance certification in terms of V2B4a clause 2.4.1 and 2.4.2. The VGS, QLS and ANPR pilot shall cover all the Nyl north bound mainline lanes (09MN to 14MN).”

PS 3.8.2.17 The Vehicle data message (AVC/TCC message type ID 2) format, TABLE 3-6:

VEHICLE DATA MESSAGE. Item 12

Add the following item to the message mapping list (This shall also apply to Message type ID 6):

“* AVC vehicle axle-based class to be included with each message, first message in string: Vehicle class based on AVC classification including: 2L, 3L, 4L, 5L, 6L, 2H, 3H, 4H, 5H, 6H, 7H, 8H, 2M, 3M.”

“• AVC classification data string to be included with each message, second message in string: As

followed by the following information:

    - Number of forward moving axles – F1 to F9. Example for a forward moving class 2 vehicle the message will be F2;

    - Number of backward moving axles – R1 to R9. Example for a forward moving class 2 vehicle the message will be R0;

    - Number of motorcycle wheels. Example for a class 2 vehicle the message will be M0;

    - Number of Light Vehicle axles. Example for a forward moving class 2 vehicle the message will be L1;

    - Number or Heavy Vehicle axles. Example for a forward moving class 2 vehicle the message will be H1;

A few examples for clarity:

1) Forward moving 2L: ASF2R0M0L2H0

2) Forward moving 3H: ASF3R0M0L1H2

3) Forward moving 4H: ASF4R0M0L1H3

4) Forward moving 8H: ASF8R0M0L1H7

5) Forward moving motorcycle (2M): ASF2R0M2L0H0

6) Forward moving motorcycle with sidecar (3M): ASF2R0M3L0H0”

PS3.10	Video Grabbing System (VGS) (which includes cameras, VGS network and/or cabling and Power Supply

Delete Clause 3.10.1.1 and replace with the following:

“PS3.10.1.1

The Contractor shall supply, install and maintain a VGS that equals or surpasses the minimum requirements set in this specification. The objective of this system is to serve as the primary, independent and stand-alone control and audit tool for the Principal Employer, Employer and Contractor to ensure that video audits are possible on a continuous basis in order to record and verify all events and abnormal conditions, i.e. class discrepancies, violations and system failures. The VGS DVR shall continuously record images (video stream), at a frame rate of at least twenty five (25) frames per second and must be able to record at WUXGA (1920 X 1200) but should be set a minimum resolution of SXGA+ unless otherwise instructed by the Employer Representative or as specified in the Project document (Volume 3), for the cameras connected to it to ensure that all passages through the toll lane is detected.”

The VGS system shall include transaction framing (Motion, ANPR, lane date linking), user interfaces, finding storage and reporting capabilities. These functionalities shall be optimized and refined functionality to enable the VGS Clerk to perform the following tasks monthly.

- Count accuracy verification,

- Technical violation assessment/audits, e.g. “Green light”, “Red light”, reverse entry, rollback and vehicle standing assessment,

- Audit of VLN discrepancies for exempt, local and frequent users,

- Run though and tailgater investigation,

- Lane incidents and

- Customer complaints”

PS3.10.1.12

This clause to be modified to read as follows:

“The VGS shall record images for all triggers generated by external or internal services, for a window period at set intervals as listed in Clause 3.11.1.4.”

PS5.4 	Auditability

PS5.4.2 	System Auditability

On the second sentence of Clause 5.4.2(k)(i) to be modified to read as follows:

“… daily basis, not later than forty-eight (48) hours after each calendar day, verify ….”

PS 5.4.14 CONFIGURATION CONTROL (ALSO PS 5.7.4.9)

Add:

“The system shall include automated processes, user interfaces and reports to detect discrepancies in the versions of software and settings. The system shall include versions control information as part of all executables and a separate process to verify software components and settings by comparing MD5 hash values against for deployed components against the MD5 hash values of the correct components.

The MD5 hash values will be calculated from the file contents of the executable, script or configuration file.

The System shall include a user interface to report and track the versions for all the components of the system. This shall include:

- Subsystem description

- Component name

- Executable name or script file name or static configuration file name.

- Executable type or script type.

- Executable version (only relevant for executable files and DLL’s)

- File size

- MD5 Hash Value

- Installation date

- Creation date

- Version update log

  - Previous versions

  - Version change dates

The above information shall be published by each sub-system on the network in the form of a web service (SOAP over HTTPS). The BOS shall collate all the version information from all the other subsystems.

The Toll System shall also include routine processes to monitor the accuracy of versions against the approved software version and settings sets. The process shall check the current system against the correct (tested and certified system), based on MD5 hash values generated for the current system deployment and checked against the stored hash values for the corrected (tested and certified system). Processes shall be implemented to correct and report incorrect versions and settings. All detected setting errors shall also be logged and reported as incidents to the supervisor. In cases of subsystems and lanes version verification shall be incorporated in the interfaces between the BOS and such system.

The DCS/AVC shall perform these functions as a separate module (Separate network), the other Toll sub-systems shall be monitored by the BOS.

The Contractor shall structure the sub-systems in such a way that each subsystem and its critical settings is grouped and stored in a manner that will allow hash values to be generated for all components and settings that affect the functionality of the system. Three sets of hash values, that cover executable and configuration, shall be generated:

1) Generic components: This hash value shall incorporate all generic components that are not affected by configuration details. This includes executables, DLL, scripts, database scripts and database configuration data exports. Any hash discrepancies shall be reported as executable version errors.

2) Static configuration: Static configuration that are lane or location specific. This includes .ini, dll, config files and database CSV exports for operating environment settings. Any hash discrepancies shall be reported as configuration errors. 3) Intermittently updated configuration: Configuration that are updated intermittently e.g. tariffs, discounts, messages, receipt lay-outs, timers etc. This includes .ini, dll, config files and database CSV exports for operating environment settings. Any hash discrepancies shall be

reported as configuration errors.

The Contractor shall store hash values for each subsystem that shall include the following:

- Application directory: This shall be a folder/location that contains all the subsystem static critical application software, including executables, scripts, binaries, DLL, .ini,, table export scripts and the hash file generation scripts used to perform version verification. Any hash discrepancies shall be reported as executable version errors.

- Database scripts exported into a text base format. Any hash discrepancies shall be reported as executable version errors.

- Static operating environment configuration table structures exported into sql scripts and xsd schema files. Any hash discrepancies shall be reported as configuration errors.

- Static operating environment configuration table contents exported as CSV files, ini files and XML files. Any hash discrepancies shall be reported as configuration errors.

The Contractor shall present a full design that incorporate the version management system for the ER’s approval. All hash values shall be submitted to the ER prior to all SFAT and SAT tests with the appropriate tools and scripts for the ER to independently verify the accuracy of the version and configurations of any deployed subsystem. The ER may use another MD5 tool of his choice to verify the hash values.

The Contractor’s SAT and SFAT procedures include a process to verify the accuracy of the version monitoring and control mechanism.

The version checking process will be automated to run at system restarts and at regular intervals (per hour or per shift). Any hash value discrepancies shall be reported to the BOS (or in the case of the AVC/DCS to the DCS) with the appropriate data to identify the problem area. The discrepancy reporting shall report configuration errors and executable version errors.

All hash values shall be store as part of the Disaster Recovery Pack (Clause 2.1.13) and escrow package (Clause 2.1.9)”

PS 5.4.5 Protection of the Toll Systems

Add the following after clause 5.4.5.3 (PCI DSS):

“The Contractor level shall comply to the PCI DSS requirements for a level 2 Merchant in line with the requirements of the SANRAL Master/Visa quiring bank prescriptions. The Contractor shall complete the assessment and certification process and the annual confirmation of compliance.”

PS 5.7.2 Support Requirements

Add:

“Help Desk System & QLS

The Main Contractor shall have the Help Desk System and the Contractor the QLS systems upgraded, replace, installed, implemented and tested to full compliance in this respect of the toll system by the end of the first month from the Operations Commencement Date.

The Contractor shall clarify any uncertainty regarding the requirements before the Commencement Date.”

PS 5.7.4.2 Critical and Serious errors

Add the following after clause 5.7.4.2:

“The Contractor shall implement Lane and BOS incidents that evaluate incidents reported under clause 5.7.4.9. The BOS will bring the subsystem Serious and Critical Error Mode status to the Supervisors attention and will require acknowledgment by the Supervisor. The lane and subsystem status will only return to normal status once the problem that caused the Serious or Critical Error Mode status is corrected. The time to repair (start to end of a Serious or Critical Error Mode) and the vehicles processed during these abnormal periods will be report by the BOS as separate incidents which will be used to evaluate the KPI’s associated with maintenance and availability (CT1, CT2, CT12, CT15) and failure related penalties (6.4.3, 6.4.4 and 6.5.6).

Subsystem Serious or Critical Error Mode will be reported to the BOS with a “start of serious (or critical) error mode” when the problem is detected, as specified under clause 5.7.4.5 and 5.7.4.9, by the subsystem or BOS and an “end of Serious Error mode (or Critical Error Mode)” incident when the BOS or subsystem detects, as specified under clause 5.7.4.5 and 5.7.4.9, that the fault status is cleared by the Contractor by replacing, resetting, repairing and/or correcting the offending item or error. Each start/end incident designation will be structured to identify the faulty subsystem and item/device.

The BOS system shall measure and report a Critical/Serious Error mode Time Exceeded incident where a subsystem or lane remain too long in Critical/Serious error mode. In instances where there are contiguously overlapping Critical/Serious Incidents the BOS shall calculate the Critical/Serious Error Mode time duration of this event using the time stamp of the first Critical/Serious Error Mode Incident as the start time of the Critical/Serious error mode event and the time stamp of the last Critical/Serious error Mode OK incident as the end time for the Critical/Serious Error Mode event, for the combination of all such critical Incidents as constitutes this contiguously overlapping set of Critical/Serious Error Mode time exceeded Incidents. The BOS will generate the Critical/Serious Error mode Time Exceeded Incident per lane and per subsystem. The Critical/Serious Error mode Time exceeded incident will be generated for every occurrence if the lane or subsystem remain in critical error mode period is longer than 4 (four) hours, or the value defined in the Project Document (Volume 3). Multiple Critical/Serious Error Mode time exceeded incidents is therefore possible for a single failure/error.

The BOS system shall measure and report a Critical Error mode Traffic Exceeded incident where more than 10 vehicles is processed in a lane that is in Critical Error Mode. Critical Error Mode shall exist for any period where different errors contiguously overlap. The BOS shall count passages for a lane the first Critical Error Mode error to the last Critical Error Mode OK incident. The BOS will generate the Critical Error Mode Traffic Exceeded Incident per lane. The Critical Error mode Traffic Exceeded incident will be generated for every occurrence where more than 10 passages is processed while the lane remain in Critical Error Mode. Multiple Critical Error Mode Traffic exceeded incidents is therefore possible for a single failure/error”

PS 5.7.4.9 System health monitoring

Add the following below the clause:

“5.7.4.9 The system shall create incidents and record incidents on the BOS for, inter alia, the following

conditions:

- Lane related incidents

  - Restarts or reboots;

  - Software version changes, including dll changes;

  - Incorrect software version;

  - Lane settings change for, inter alia, tariff tables, discounts, UFD messages, .ini file changes;

  - Incorrect lane settings for, inter alia, tariff tables, discounts, validation list, UFD messages, hotlist;

  - Tag Reader failures;

  - ANPR camera failures;

  - VGS Camera failures;

  - Lane Serious Error mode Start and End if the any of the following conditions exists and when it is cleared

  - AVC communication failure;

  - UFD failure;

  - Receipt printer failure;

  - VGS Camera failure;

  - Lane local mode exists;

  - Lane Controller door open.

  - Lane Critical Error mode Start and End if the any of the following conditions exists and when it is cleared. Incidents created for affected lanes

  - ETC beacon failure;

  - More than two VGS cameras fail;

  - Boom break away exists;

  - Boom forced open;

  - Plaza local area network failure;

  - Lane UPS battery low;

  - Lane UPS failure;

  - Validation list older than 4 hrs base on the time the current validation list was received by the BOS;

  - ANPR camera failure;

  - Wrong software version;

  - Wrong lane settings version.

  - Failures of any other controller;

- Back Office System;

  - Lane linked Critical error mode time exceeded when critical error mode exists for more than 4 hours, or the value defined in the Project Document (Volume 3), for any lane or subsystem

  - Lane linked Critical error mode traffic exceeded when more than 10 vehicles is processed in a lane that is in critical error mode

  - Lane linked Serious error mode time exceeded when serious error mode exists for more than 24 hours, or the value defined in the Project Document (Volume 3), for any lane or subsystem

  - BOS, VGS, QL1, QL2, TCH payment gateway (PGW) or QLS Serious Error mode Start and End if the any of the following conditions exists and when it is cleared

  - Incorrect settings for BOS, VGS, QL1, QL2, TCH payment gateway (PGW) or QLS. This includes inter alia.

    - Back-up settings

    - Software version changes. This includes inter alia.

    - BOS interface related software

    - BOS reports changes

    - Changes to function or report access level

  - BOS to VGS importer failure

  - BOS/ QL1 failure

  - BOS Critical Error mode Start and End if the any of the following conditions, respectively, exists or it is cleared

  - Incorrect settings for BOS, VGS, QL1, QL2, TCH payment gateway (PGW) or QLS. This includes inter alia.

    - Camera to lane mapping for recordings related to Table 3-10 (VGS actions)

    - VGS/BOS interface settings

    - Software version changes. This includes inter alia.

    - BOS interface related software

    - BOS server software changes

    - VGS server changes

  - VGS/BOS interface failure

  - VGS failure

  - Incident control failure

  - Incident control image retrieval failure

  - QL1 camera failure

  - QL1 failure

  - QL2 camera failure

  - QL2 failure

  - DVR failure

  - TCH link failure

  - Current BOS Validation list older than 4 hours

5.7.4.10 The System shall generate a BOS incident data and deliver it to the SANRAL MIS.”

PS 6.1.3 BACK OFFICE FOR CONVENTIONAL AND HYBRID TOLL PLAZAS

PS 6.1.3.1 The purpose of the Back Office System at Conventional Toll Plazas

Replace with the following:

“The purpose of the Back Office System at Conventional Toll Plazas is to:

(a) 	Receive data from all the lanes, validate data to ensure correctness and completeness, and provide system tools to the plaza supervisory personnel to assist with the efficient management of the data and the plaza.

(b) 	Allow manual input of additional data required for accurate transaction processing, including adding an Actual Class and Actual Vehicle Licence Number for transactions with class discrepancies or Vehicle number plate discrepancies. Allow for adding transaction information not captured in the lane, e.g. transactions processed during Manual Mode operations or data for undetected passages.

(c) 	Verify and consolidate complete data received from each Toll Lane and RSS linked to each virtual plaza linked to the Back Office to process all data including additional payments received, or made at the Back Office level, allow for the employee cash-up and provide employee and period reconciliations (calendar day, operational day and or other shift periods).

(d) 	Allow for local account maintenance, allocate Discounts, perform account maintenance functions, transfer data files to external systems, provide consolidated reconciliations, allow controlled system configuration and provide comprehensive reports on all activities. The Back Office System is also to facilitate the automated interaction with account holders. The system shall also manage the integrated verification interface to the approved financial institution providing Bank Card verification and transaction processing employing a Point-of-Sale (POS) unit.

(e) 	Automate and manage functions required to accurately and completely capture the required information related to all vehicle passages.

(f) 	Ensure system auditability.

(g) 	Integrate, store and disperse data received from lanes, VGS, QLS, QL1 and other interfaced systems e.g., TCH.

(h)	Provide Operations Centre level to facilitate the configuration and performance control and management of multiple control centres and plazas on a route.

(i)	Capture audit trails and ensure auditability.

(j)	Meet TAX requirements.

(k) 	Secure data and protect system processes.

(l)	Comply with applicable industry, statutory and regulatory requirements. “

PS 6.1.3.2 The Back Office System shall provide the functionality to:

Replace with the following:

“

        - Verify the completeness, continuity and authenticity of data received from the lanes continuously and on a scheduled basis;

        - Retain source data and add information required for data completeness;

        - Automatically transmit consistent data to higher levels and via interfaces;

        - Provide visibility of all the background processes and system configurations to allow the supervisory staff to manage the system and identify system problems;

        - Report and manage Incidents that occur at the plaza level or the lane level. This includes amongst others the VGS application, VGS cameras and primary recording devices,;

        - Receive operational lists and configurations and send the information to the lanes;

        - Allow for adequate redundancy and storage capacity, back-up and housekeeping facilities;

        - Manage Toll Revenue, e.g. Control cash Revenue via the cash-up, consolidated cash-up and cash banked functions;

        - Allow account registration and maintenance functions for local account holders;

        - Allocate Discount;

        - Create data files for transmission to external systems for further processing of electronic transactions;

        - Receive and compile operational lists and configurations and send the information to the lower levels.

        - Report on traffic, financial information, audit trails, data status, lane and hardware performance and maintenance.

        - Compile the final complete passage record, for transmission to the SANRAL MIS, that include all raw data, operational and processing amendments, incident/

        - User friendliness

        - The system shall be user friendly. User friendliness shall be measured against the following items:

        - Consistent screen, selection box and report layout.

        - Mouse and hot key functionality.

        - Default values and pick lists.

        - Calendar selection boxes.

        - Consistent error handling.

        - Warning if selection is out of range.

        - The application shall share workstations with other MS Office applications.

        - Allow multiple tasks to be performed by utilising tabs and multithreading.

        - Consolidation of all functions/applications into a single user interface.

        - Exception reporting.

        - User specific profile set-up.

        - Reports must be portable to formatted PDF, tabular CSV and Excel.

        - E-mail reports from BOS.

        - Report maintenance issues via e-mail and/or via the Employer’s helpdesk system (interface to be designed).

        - Online help functions – User manuals in electronic format. ”

PS 6.2.5 MANUAL NUMBER PLATE RECOGNITION (MNPR) FOR OPT-IN TOLL AGENCIES

MNPR and the requirements of this clause and related requirements based on the availability of ANPR shall be required.

PS6.2.7 V-TOLL TRANSACTIONS (OPT-IN TOLL AGENCIES)

V-Toll shall not be required under this contract.

The Contractor and the toll system shall allow for two types of manually captured TCH transactions. Both type of transactions shall be flagged as manual transactions. Manual transaction creation and submission shall only be possible for valid tags, verified against the validation list at the time of creation.

- Fully manual transaction: A transaction created in total based on the vehicles VLN or Tag number.

- Partially manual transaction: A lane created transaction or run through violation, modified at plaza level based on the VLN or tag number.

PS6.2.8.2 Vehicle License Number Discrepancies (Opt-in Toll Agencies)

Replace this clause with:

“6.2.8.2 Vehicle Licence Number Discrepancies:

  - A Tag shall be dedicated to a specific vehicle with a unique vehicle Licence Number. A Tag is not transferable between vehicles.

  - The Back Office System shall provide a function to identify Vehicle Licence Number discrepancies for all Tag linked passages. (If a particular Tag is not eligible for Discount, Exempt or Free Passage, the Vehicle Licence Number need not be verified, unless these transactions are queried by the road user).

  - If the Vehicle Licence Number of the front licence plate differs from the rear licence plate number, the Vehicle Licence Number of the front licence plate shall be used (if available).

  - The Main Contractor shall for all tags associated with Discount, Exempt or Free Passage, compare the Vehicle Licence Number derived from the ANPR process with the Vehicle Licence Number in current the Validation List(s), also known as the registered Vehicle Licence Number. All mismatches, VLN Discrepancies, shall be visually verified and in cases where the ANPR was incorrect the correct MNPR will be entered.

  - The Back Office System shall keep track of the number of mismatches between the registered VLN and the VLN determined through the ANPR process through an automated or manual process.

  - All VLN Discrepancies, that were manually verified as actual discrepancies, and which are linked to Tags the eligible for Discount or Exempt or Free Passage transactions shall be dealt with in terms of the user conditions associated. If there is a continuous mismatch between the registered VLN and the VLN determined through the ANPR process and the mismatches can be verified, the Transaction Records shall be flagged as Vehicle Licence Number discrepancies to inform the TCH System that the road user is possibly abusing the Discount rules, so that the TCH System can take further action, such as to inform the road user about the mismatches. The Main Contractor shall also take the appropriate actions to disqualify users with local user discounts. This shall include applying the nominal tariff to for transactions with verified VLN discrepancies.

  - The N1N plazas do not currently have a local concession system that allow local users to receive discounts after swiping their Toll Authority card. The Contractor will be required to implement a local discount that will allow users to pay a discounted tariff with cash or unregister bank card. The system then accepts payment as cash, or credit card, at a discounted tariff. The ANPR system shall utilize ANPR at lane level to police all TA card transactions at lane level. The TCC shall for discounts that are linked to Toll Authority cards perform a VLN verification that compare the registered VLN against the ANPR VLN. In case of a VLN discrepancy the TCC shall prompt the Toll Collector to accept the ANPR value or enter the correct VLN, from the front view image displayed by TCC on the VDU. All VLN Discrepancies that were manually verified as actual discrepancies shall be dealt with in terms of the user conditions associated with the TA card. The TCC shall cancel the discount and revert the tariff to the nominal value if the TA card conditions of use require that only a specific vehicle (VLN) be used with the TA card. The TCC shall generate an incident to notify the supervisor and the Main Contractor shall take the necessary corrective steps.

  - If a road user continues to misuse the system, the Discount of a road user may be terminated. The Back Office System shall no longer apply the Discount to Transaction Records linked to the Tag Identifier or TA card.“

PS7.4 	The Employers Interface

PS7.4.4 	Interface Definition:  Predefined Data

Delete “Table 7-4” and replace with the following:

Table 7-4: Methods of Payment (Conventional /Hybrid Toll Plazas)

| Payment Group | Possible Payment Mechanism applicable to the Payment Group (identified by) | Possible Discounts applicable to the Payment Type/Group | Payment Type |
| --- | --- | --- | --- |
| Cash | Cash Operator Card (Magnetic Stripe) | Nominal Tariff Local and Regional Discount | Cash |
| TCH Account (Pre- and Post-Paid Account Identifiers on the Green List but EXCLUDING any Exempt Vehicle Identifiers) | ETC Tag issued by the TCH VLN 3rd Identifier | Nominal Tariff Frequent User Discount Local and Regional Discount Payment Mechanism Discount Time of day Discount Public Transport Discount | N/A |
| Pre Payment | Credit Cards Fleet Cards Charge Cards Operator Card (Mag striped) Operator Card (Smart card) Smart Card issued by a Bank Bank Debit Cards | Nominal Tariff Frequent User Discount Local and Regional Discount Discretionary Discounts Heavy Vehicle Discounts | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Other |
| Post Payment | Credit Cards (Registered and Un-registered Users) Fleet Cards Charge Cards Operator Card (Magnetic stripe) Operator Card (Smart card) Smart card issued by a Bank Bank Debit Cards | Nominal Tariff Frequent User Discount Local and Regional Discount Discretionary Discounts Heavy Vehicle discounts | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Other |
| Run-through Violation | Run Through Identifier | Nominal Tariff | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Other |
| Exempt Vehicles (SANDF) (SAPS) (Other) (For ETC Tags this shall be determined by the account type as indicated by means of the Validation List(s)) | Credit Cards Fleet Cards Charge Cards Operator Card (Magnetic stripe) Operator Card (Smart card) Smart card issued by a Bank ETC Tag issued by the TCH (only Exempt Identifiers) Bank Debit Cards Official Warrant | 100 % discount (Taxable Nominal Tariff Transaction in Toll Lane written off in Back Office with Credit Note). | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Credit Notes Other |
| No-Payment | No-Payment identifier | Nominal Tariff | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Other |
| Sundry items: (Pre-paid User account deposits) (Surplus Revenue) (Over collections, Negative discrepancies etc) (Paid passage transactions for Violations, Exempts, No-Payments) (Other income for the Employer’s account) (Other income for Main Contractor account including Main Contractor user account charges) | Credit Cards Fleet Cards Charge Cards Operator Card (Magnetic stripe) Operator Card (smart card) Smart Card issued by a Bank ETC Tag issued by the TCH (only Exempt Identifiers) Bank Debit Cards User Account ID Other depending on transaction type. |  | Cash (Including debit orders, cheques, direct transfers, bank deposits etc.) Clearing of Bank Issued Card payments Main Contractor account dt/ct Other |

Delete “Table 7-5” and replace with the following:

Table 7-5:  Payment Groups

| Payment Group ID | Payment Group |
| --- | --- |
| 01 | Cash |
| 02 | Pre paid |
| 03 | Post paid |
| 04 | Run-through Violation |
| 05 | Exempt Vehicle |
| 06 | No Payment |
| 07 | Sundry: Pre-paid User account deposits |
| 08 | Sundry: Surplus Revenue (Over collections, Negative discrepancies etc) |
| 09 | Sundry: Paid passage transactions – Violations, Exempts, No-Payments |
| 10 | Sundry: Other income for the Employer’s account |
| 11 | Sundry: Other income for Main Contractor account including Main Contractor user account charges |
| 12 | TCH Account (excl. Exempt Vehicle accounts) |
| 13 | Sundry Deposits – other |
| …. | …. |
| N | Payment Groupn |

Delete “Table 7-6” and replace with the following:

Table 7-6: Payment Types

| Payment Type ID | Payment Type |
| --- | --- |
| 01 | Cash |
| 02 | Bank Issued ISO Credit Card |
| 03 | Fleet Card |
| 04 | Charge Card |
| 05 | Main Contractor Account |
| 06 | Credit Notes |
| 07 | Debit Order |
| 08 | EFT |
| 09 | Employer Clearing House (TCH) |
| …. | …. |
| N | Payment Typen |

Delete “Table 7-7” and replace with the following:

Table 7-7: Payment Mechanisms

| Payment Mechanism ID | Payment Mechanism name |
| --- | --- |
| 00 | Cash |
| 01 | ISO Credit Card – unregistered users |
| 02 | Fleet Card – unregistered users |
| 03 | Charge Card |
| 04 | ETC Tag |
| 05 | Operator Card |
| 06 | Smart Card |
| 07 | Operator Smart Card |
| 08 | Official Warrant |
| 09 | Run Through |
| 10 | No-Payment |
| 11 | Registered ISO Credit Card Users |
| 12 | Registered Fleet Credit Card Users |
| 13 | VLN |
| 14 | 3rd Identifier |
| …. | …. |
| N | Payment Mechanismn |

PS 7.4.4.4	Methods of Payment for ORT Type Application

Delete “Table 7-10” and replace with the following:

Table 7-10:  Payment Mechanisms (ORT)

| Payment Mechanism ID | Payment Mechanism name |
| --- | --- |
| 04 | ETC Tag |
| 08 | Exempt Identifier (Tag / VLN / 3rd Identifier) |
| 09 | Run Through |
| 13 | VLN |
| 14 | 3rd Identifier |

PS 7.4.4.5	Discount types for Conventional and Conventional portions of Conventional/Hybrid Toll Plazas

Delete “Table 7-11” and replace with the following:

Table 7-11:  Discount Types

| Discount ID | Discount Name |
| --- | --- |
| 00 | Nominal |
| 01 | Heavy Vehicle Discount |
| 02 | Frequent User Discount |
| 03 | Local and Regional Discount |
| 04 | Main Contractor Account |
| 05 | Official SANDF Warrants |
| 06 | Official SAPS Warrants |
| 07 | Discretionary Discount |
| 08 | Payment Mechanism Discount |
| 09 | Time of Day Discount |
| 10 | Public Transport Discount |
| …. | …. |
| N | Discountn |

Delete “Table 7-13” and replace with the following:

Table 7-13: Vehicle Classes – Axle Based (Illustrative Information – Refer to Government Gazette for Vehicle Class Information)

| ID | Name | Mapped Vehicle Classes |
| --- | --- | --- |
| 01 | Toll Class 1 | 2 or more axle Light Vehicle |
| 02 | Toll Class 2 | 2 axle Heavy Vehicle |
| 03 | Toll Class 3 | 3 axle and 4 axle Heavy Vehicle |
| 04 | Toll Class 4 | 5 and more axle Heavy Vehicle |
| 05 | Toll Class 5 When triggered | Motorcycles |

PS7.4.5  	Interface Definition AVC/DCS and other Toll System Incidents/Fault Messages

Delete “Table 7-15” and replace with the following:

Table 7-15: Incident Messages (Conventional / Hybrid Toll Plazas)

| ID | Name | Source/Comment | Reported to | Required /Optional |
| --- | --- | --- | --- | --- |
| 001 | AVC reboot/restart | AVC/Recorded by AVC on during boot cycle and AVC application restart. | DCS/TCC/VGS/BOS/ITIS | Required |
| 002 | Serious start – AVC/DCS Communication fail | AVC/Detected by AVC when communication is lost with DCS. Trigger Serious Mode. | DCS/TCC/VGS/BOS/ITIS | Required |
| 003 | Serious end – AVC/DCS Communication OK | AVC/Detected by AVC when communication is restored with DCS | DCS/TCC/VGS/BOS/ITIS | Required |
| 004 | Roll-back | AVC/Defined elsewhere in the document | DCS/TCC/VGS/BOS/ITIS | Optional |
| 005 | Reverse entry | AVC/Defined elsewhere in the document | DCS/TCC/VGS/BOS/ITIS | Optional |
| 006 | Vehicle standing | AVC/Defined elsewhere in the document | DCS/TCC/VGS/BOS/ITIS | Required |
| 007 | Vehicle with more than 10 axles | AVC/Maximum number of axles detected by any of the axle counters. Configurable parameter. | DCS/TCC/VGS/BOS/ITIS | Required |
| 008 | AVC sensor type 1 - fail | AVC/Presence detector failure, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 009 | AVC sensor type 1 - OK | AVC/Presence detector reset, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 010 | AVC sensor type 2 - fail | AVC/Axle counter failure, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 011 | AVC sensor type 2 - OK | AVC/Axle counter reset, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 012 | AVC sensor type 3 - fail | AVC/Light/Heavy detector failure, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 013 | AVC sensor type 3 - OK | AVC/Light/Heavy detector reset, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 014 | AVC sensor type 4 - fail | AVC/Height detector failure, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 015 | AVC sensor type 4 - OK | AVC/Height detector reset, detected after three passages | DCS/TCC/VGS/BOS/ITIS | Required |
| 016 | Critical start - AVC panel door open | AVC/Detected by AVC on opening of door. Trigger Critical Mode when associated with vehicle presence. | DCS/TCC/VGS/BOS/ITIS | Required |
| 017 | Critical end - AVC panel door close | AVC/Detected by AVC on closing of door | DCS/TCC/VGS/BOS/ITIS | Required |
| 018 | Serious start - AVC Stand-alone Data | AVC/Reported by AVC if vehicle passage/s were recorded while AVC was in stand-alone mode. Trigger Serious Mode. | DCS/ITIS/TCC/VGS/BOS | Required |
| 019 | Serious end - AVC Stand-alone Data | AVC/Reported by the AVC at the time when the AVC Stand-alone status is restored. The Incident is only reported if vehicles were recorded by the AVC during the AVC Stand-alone period. Incidents 18 & 19 are, therefore, always paired. | DCS/ITIS/TCC/VGS/BOS | Required |
| 020 | Critical start – AVC Storage 90% full | AVC/AVC Data storage device (e.g. Hard drive or flash) disk 90% full. This status is to be checked at least, once every hour and reported when valid. Trigger Critical Mode. | DCS/TCC/IT IS/BOS | Required |
| 021 | Critical start – AVC-UPS Backup battery voltage low | AVC/AVC UPS battery voltage low. Minimum voltage before Incident is generated is described elsewhere. Trigger Critical Mode. | DCS/TCC/VGS/ITIS/BOS | Required |
| 022 | Critical end – AVC-UPS Backup battery voltage OK | AVC/AVC UPS battery voltage recovered above the voltage low threshold described above, ready for repeated standby period. | DCS/TCC/VGS/ITIS/BOS | Required |
| 023 | Serious start – TCC Communication fail | AVC/AVC/TCC communication failure detected and reported by the AVC and TCC. Trigger Serious Mode. | DCS/TCC/VGS/ITIS/BOS | Required |
| 024 | Serious end – TCC Communication OK | AVC/Communication restoration detected by AVC | DCS/TCC/VGS/ITIS/BOS | Required |
| 025 | Un-transmitted data deleted | AVC/AVC Data deleted by user or system before successfully transmitted to the DCS. | DCS/TCC/ITIS/BOS | Required |
| 026 | Plaza UPS power failed | AVC/Power to AVC fail (plaza UPS power) | DCS/TCC/VGS/ITIS/BOS | Required |
| 027 | Plaza UPS power OK | AVC/Power to AVC restored (plaza UPS power) | DCS/TCC/VGS/ITIS/BOS | Required |
| 028 | AVC User access – login | AVC/User accessed AVC (Software login) | DCS/TCC/ITIS/BOS | Required |
| 029 | AVC User access – logout | AVC/User access to AVC terminated (Software log-out) | DCS/TCC/ITIS/BOS | Required |
| 030 | Critical start – Sensor failure | AVC/Generated by the AVC when any two or more sensors fail during a vehicle passage. Trigger Critical Mode. | DCS/TCC/VGS/ITIS/BOS | Required |
| 031 | AVC time update | AVC/AVC time check / updated by User or time server via the TCC. Minimum, once every 24 hours for each AVC. | DCS/TCC/ITIS/BOS | Required |
| 032 | Lane IP address change | TCC/IP address changed by user | DCS/TCC/ITIS/BOS | Optional |
| 033 | Plaza IP address change | BO System/IP address changed by user | BOS/ITIS/BOS | Optional |
| 034 | AVC IP address change | AVC/IP address changed by user | DCS/TCC/VGS/ITIS/BOS | Required |
| 035 | Lane ID change | AVC and/or TCC/Lane ID changed by user | DCS/TCC/BOS/ITIS | Required |
| 036 | Reserved |  |  | - |
| 037 | AVC License expired | AVC/ In the event where any AVC is managed by means of any license and such licence expire. | DCS/TCC/BOS/ITIS | Required where applicable |
| 038 | AVC License updated | AVC/ In the event where any AVC related license is modified. | DCS/TCC/BOS/ITIS | Required where applicable |
| 039 | AVC Data Storage Device reset | AVC/ In the event where the AVC storage device can be reset - be it manual / mechanically or electronically. | DCS/TCC/BOS | Required where applicable |
| 040 | AVC Data Storage Device error | AVC/ In the event where any AVC data storage error is detected, either by the system operating system or in the event where any read or write action failed, for whatever reason. | DCS/TCC/BOS | Required |
| 041 | Wrong Direction | AVC/Defined elsewhere in document. Also see reverse passage. | DCS/TCC/VGS/ITIS/BOS | Required |
| 042 | AVC Mode change | AVC/AVC switches between primary and pseudo lane-Ids (ramp/mainline swapping) Generate Incident when the lane is activated to process transactions for the pseudo lane AND generate the Incident for each passage processed in the pseudo state. | DCS/TCC/VGS/ITIS/BOS | Required if applicable. |
| 043 | Ramp/Mainline barrier | AVC/Incident generated when any vehicle is detected through the Ramp/Mainline barrier. The additional sensors installed in the barrier – typically between mainline and ramp. | DCS/TCC/VGS/ITIS/BOS | Required |
| 044 | Run-Through Violation | AVC/Incident generated when any vehicle pass through the AVC (in any direction) without any valid method of payment. | DCS/TCC/VGS/ITIS/BOS | Required |
| 045 | Critical end – Sensor failure | AVC/Generated by the AVC when two or more of the sensors are no longer faulty. After three consecutive passages without error. | DCS/TCC/ITIS/BOS | Required |
| 046 | Serious start – DCS/AVC comms fail | DCS /Generated by the DCS when a communication failure with the AVC is detected by the DCS. Trigger Serious Mode. | BOS/VGS/ITIS | Required |
| 047 | Serious End – DCS/AVC comms fail | DCS /Generated by the DCS when a communication failure with the AVC is restored | BOS/VGS/ITIS | Required |
| 048 | Critical error mode time exceeded | AVC or DCS/ The DCS will determine the critical error mode time duration of all critical AVC Incident events. In instances where there are contiguously overlapping critical Incidents (e.g. a subsequent AVC critical Incident event occurring prior to the resolution of a previous/current AVC critical Incident event being resolved) the DCS shall calculate the critical mode error time duration of this event using the time stamp of the first critical AVC Incident fail as the start time of the event and the time stamp of the last AVC critical Incident OK as the end time for the event, for the combination of all such critical Incidents as constitutes this contiguously overlapping set of AVC critical Incidents. The DCS will generate this Incident per AVC. It will be generated if the critical mode period is longer than 4 (four) hours, or the period as specified in the Project Document (Volume 3). This Incident will be generated continuously for every continuous 4 (four) hour period interval, or corresponding period interval specified in the Project Document (Volume 3), that the AVC remains in critical error mode | DCS/BOS/ITIS | Required |
| 049 | Critical error mode traffic exceeded | AVC or DCS/ The DCS will generate this Incident per AVC if the traffic processed whilst the AVC is in critical error mode exceeds 10 vehicles. Incident repeated after each tenth vehice during the Critical Error mode period. | DCS/BOS/ITIS | Required |
| 050 | Serious error mode time exceeded | AVC or DCS/ The DCS will determine the AVC Serious mode error time durations of all critical AVC Incident events. In instances where there are contiguous or overlapping serious AVC Incidents (e.g. a subsequent AVC serious Incident event occurring prior to the resolution of a previous/current AVC serious Incident event being resolved) the DCS shall calculate the serious error mode time duration of this event using the time stamp of the first serious AVC Incident fail as the start time of the event and the time stamp of the last serious AVC Incident OK as the end time for the event, for the combination of all such serious Incidents constitute this contiguous or overlapping set of AVC critical Incidents. The DCS will generate this Incident per AVC. It will be generated if the serious mode period is longer than 24 (twenty-four) hours, or the period specified in the Project Document (Volume 3). This Incident will be generated continuously for every continuous 24 (twenty-four) hour period interval, or corresponding period interval specified in the Project Document (Volume 3), that the AVC remains in serious error mode. | DCS/BOS/ITIS | Required |
| 051 | AVC data missing – Critical error mode | DCS/ When compiling the AVC traffic and Incident/Fault log summaries for the previous calendar day (consolidation period), the DCS will check if hourly summaries (audit file) were received from all the AVCs (No less than 24 summaries (audit file periods) must be available for each AVC). The DCS will generate this Incident for every AVC where summaries for the complete consolidation period for that AVC have not been received. | DCS/BOS/ITIS | Required |
| 052 | DCS reboot | DCS/ The DCS shall generate this Incident when the DCS application/service is restarted. Incident is reported to ITIS via DCS Fault Log Data File since it is not Toll Lane related. | BOS/ITIS | Required |
| 053 | ITIS data submission failure | DCS/ The DCS shall generate this Incident indicating any ITIS file submission error. This includes data and reply to retrieval and submission errors. | BOS/ITIS | Required |
| 054 | Positive Discrepancy (PD) | AVC or BOS /The AVC shall generate this Incident in the event where the manual and or registered vehicle classification received from the TCC is a lower Vehicle Class than that detected by the AVC (Based on financial value). This Incident shall also be generated in the event where no manual or registered vehicle classification has been received from the TCC (e.g. Violation without manual classification or valid registered identifier present). Should the discrepancy be identified on the BOS level the BOS shall generate the incident. Also applicable to manually captured or verified transactions. | TCC/DCS/VGS/ITIS/BOS | Required |
| 055 | Negative discrepancy (ND) | AVC or BOS /The AVC shall generate this Incident in the event where the manual and or registered vehicle classification received from the TCC is a higher Vehicle Class than that detected by the AVC (Based on financial value). Should the discrepancy be identified on the BOS level the BOS shall generate the incident. Also applicable to manually captured or verified transactions. | TCC/DCS/VGS/ITIS/BOS | Required |
| 056 | Reversible Lane AVC pair – Active AVC | AVC/Incident generated by the active AVC in a reversible Lane, upon being activated for Vehicle processing. Also generated at the end of the hour to indicate current state of the AVC. | TCC/DCS/ITIS/BOS | Required, if applicable |
| 057 | Reversible Lane AVC pair – Dormant AVC | AVC/Incident generated by the dormant AVC in a reversible Lane upon being made ‘inactive’ for Vehicle processing. Also generated at the end of the hour to indicate current state of the AVC. | TCC/DCS/ITIS/BOS | Required, if applicable |
| 058 | Critical End – AVC Storage 90% Full | AVC/AVC Data storage device (e.g. Hard drive or flash) disk 90% full cleared. | DCS/TCC/ITIS/BOS | Required, if applicable ……. |
| 059 | VGS Camera Failure. | DVR/VGS DVR or Server to record any failure of any VGS camera/s or signal from the VGS camera/s, which will cause this incident to be generated. | DVR/BOS/VGS/ITIS | Required |
| 060 | VGS Camera Failure OK | DVR/VGS DVR or Server to record the correction or restoration of the fault state reported under incident no. 59. | DVR/BOS/VGS/ITIS | Required |
| 061 | QLS Camera Failure | QLS/QLS DVR or Server to record any failure of any QLS camera or signal from the QLS camera/s, which will cause this incident to be generated. | DVR/BOS/VGS/ITIS | Required |
| 062 | QLS Camera Failure OK | QLS/QLS DVR or Server to record the correction or restoration of the fault state reported under incident no. 61. | DVR/BOS/VGS/ITIS | Required |
| 063 | Toll Booth Surveillance Camera Failure | TCC/ When the toll booth surveillance DVR detects any faults with a camera/s or the signal from the camera/s to the DVR or the TCC records the failure of the local TCC DVR, this incident will be generated. | TCC/BOS/VGS/ITIS | Required |
| 064 | Toll Booth Surveillance Camera Failure OK | TCC/When the TCC records the correction or restoration of the fault state reported under incident no. 63. | TCC/BOS/VGS/ITIS | Required |
| 065 | Paper Low | TCC/Detected by the TCC when the Receipt printer paper is low. | TCC/BOS/ITIS |  |
| 066 | Paper Empty | TCC/Detected by the TCC when the printer paper is empty. | TCC/BOS/ITIS | Required |
| 067 | Printer Communications Failure | TCC/Detected by the TCC when the TCC fails to receive a confirmation signal that the print information sent to the printer has been printed successfully. | TCC/BOS/ITIS |  |
| 068 | Load Shift | TCC (or AVC)/When the load shift sensor detects rotation of more than 15° the incident shall be generated. Real time messaging to ER and Enforcement Agency as instructed by ER. | (DCS)/TCC/BOS/VGS/ITIS (Enforcement Authority when triggered) | Required |
| 069 | Height Sensor 4.2m | AVC/When a vehicle with a height exceeding 4.2m but less or equal to 4.8m is detected during any vehicle passage. | DCS/TCC/BOS/VGS/ITIS Enforcement Authority | Required if Triggered |
| 070 | Height Sensor 4.7m | AVC/When a vehicle with a height exceeding 4.7m is detected during any vehicle passage. Real time messaging to ER and Enforcement Agency as instructed by ER. | DCS/TCC/BOS/VGS/ITIS (Enforcement Authority when triggered) | Required |
| 071 | Exit Barrier Breakaway | TCC (or AVC)/When the breakaway sensor(s) is activated as a result of the exit barrier arm being broken away from its normal locked state. Report to DCS if barrier control is performed by AVC. | (DCS)/TCC/BOS/VGS/ITIS | Required |
| 072 | Exit Barrier Force Vertical | TCC (or AVC)/When the exit barrier arm is forced open vertically. Report to DCS if barrier control is performed by AVC. | (DCS)/TCC/BOS/VGS/ITIS | Required |
| 073 | Extra Wide Sensors active | AVC/AVC shall generate if any sensor or combination of sensors are activated from the extra wide area of the AVC area indicating the presence of any object in that area. | DCS/TCC/BOS/VGS/ITIS | Required |
| 074 | Transaction Timeout | TCC/TCC transaction failed to conclude with valid AVC classification message. Systematic procedure employed to conclude TCC transaction. | TCC/BOS/VGS/ITIS | Required |
| 075 | VOSI Vehicle detected | TCC When the VOSI is detected as per the set criteria. Real time messaging to ER and Enforcement Agency as instructed by ER. | TCC/VGS/BOS/ITIS (Enforcement Authority when triggered) | Required |
| 076 | ETC Run-Through Violation | TCC/TCC generate incident when any vehicle passes through the ETC Reading zone (in any direction) without any valid method of payment (Payment Mechanism) attached to such passage transaction. (Incident is not generated where valid transactions are processed, with other payment mechanisms, other than ETC). (V2B5cl:5.3.4.5). | DCS/TCC/BOS/VGS/ITIS | Required |
| 077 | ETC Vehicle Rollback | AVC or TCC/ TCC or AVC will generate the incident in the event where any vehicle rolls back through the ETC reading zone. This incident serves to monitor vehicle queuing in Dedicated ETC Toll Lanes where vehicle separation is monitored by a dual light curtain in the lane entry zone. (V2B5cl:5.3.4.5). | DCS/TCC/BOS/ITIS | Required for Dedicated ETC Toll Lanes |
| 078 | ETC Vehicle Standing | AVC or TCC/ AVC or TCC generate incident in the event where any vehicle remains standing in the ETC reading zone or vehicle fails to exit the Toll Lane. (V2B5cl:5.3.4.5). | DCS/TCC/BOS/ITIS | Required for ETC enabled Toll Lanes. |
| 079 | ETC Vehicle Re-Entry | TCC or BOS/TCC or BOS generate incident when an ETC transaction with (VLN and/or PAN as applicable per application) has been completed or partially completed with a vehicle and the vehicle has moved out of the tolling zone for a period of sufficient length that the Tolling System will try generating a second transaction upon the vehicle re-entering the zone (not applicable to recurrent valid transactions at the same Toll Plaza). Could also be used in the event where valid queued vehicles are to be passed through a toll lane due to an earlier queuing error. (V2B5cl:5.3.4.5). | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 080 | ETC Invalid Identifier | TCC/TCC generate in the event when a vehicle with an invalid Identifier (such as an invalid or fraudulent Tag as described below in V2B5cl:5.3.4.5 d) and/or with an unrecognisable VLN etc. as applicable per application) passes through a Toll Plaza without providing a valid method of payment. (V2B5cl:5.3.4.5). | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 081 | ETC Identifier Discrepancy - Class | TCC or BOS/TCC or BOS generate in the event when a vehicle with a registered identifier (E-Tag or other like ISO Mag-Stripe card) shows any discrepancy to the registered details of the road user’s account. (V2B5cl:5.3.4.5). | BOS/VGS/ITIS | Required |
| 082 | ETC/Identifier Discrepancy - Front VLN | TCC or BOS/TCC or BOS generate in the event when a vehicle with a registered identifier (E-Tag or other like ISO Mag-Stripe card) shows a front VLN discrepancy to that registered to the roar user’s account. (V2B5cl:5.3.4.5). | BOS/VGS/ITIS | Required |
| 083 | ETC/Identifier Discrepancy - Rear VLN | TCC or BOS/TCC or BOS generate in the event when a vehicle with a registered identifier (E-Tag or other like ISO Mag-Stripe card) shows a rear VLN discrepancy to that registered to the roar user’s account. (V2B5cl:5.3.4.5). | BOS/VGS/ITIS | Optional |
| 084 | ETC Identifier Discrepancy - PAN | TCC or BOS/TCC or BOS generate the incidents when an Invalid PersonalAccountNumber (PAN) or issuer number is detected when compared to the available registered users (including validation list from the TCH). (V2B5cl:5.3.4.5.d.i). | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 085 | ETC Identifier Discrepancy - Issuer ID | TCC or BOS/TCC or BOS generate the incidents when an Invalid Issuer Identifier (IssuerIdentifier subset of the ContractProvider Attribute). (V2B5cl:5.3.4.5.d.ii) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 086 | ETC Identifier Discrepancy - Tag Expired | TCC/TCC generate the incident when an expired Identifier is recorded. See Tag validity (PaymentMeansExpiryDate). (V2B5 cl: 5.3.4.5.d.iii) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 087 | ETC/Identifier Discrepancy - Identifier Redlisted | TCC/TCC generate the incident when an identifier (E-Tag or other like ISO Mag-Stripe card) is redlisted (or hotlisted). See (V2B5 cl: 5.3.4.5.d.iv). | BOS/VGS/ITIS | Required |
| 088 | ETC data exceptions - BST | TCC/TCC generate the incident when an ETC identifier is read and results in an exception: a) Tag does not respond to BST - (V2B5cl:5.3.4.5.d.v – see Cl 6.6.1a) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 089 | ETC data exceptions - Corrupt VST | TCC/TCC generate the incident when an ETC identifier is read and results in an exception: b) Tag return corrupt VST - (V2B5cl:5.3.4.5.d.v – see Cl 6.6.1b) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 090 | ETC data exceptions - GET.response | TCC/TCC generate the incident when an ETC identifier is read and results in an exception: a) GET.respnse not received or GET_STAMPED.response not received (V2B5cl:5.3.4.5.d.v – see Cl 6.6.1c) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 091 | ETC data exceptions – SET response | TCC/TCC generate the incident when an ETC identifier is read and results in an exception: a) SET.response not received - (V2B5cl:5.3.4.5.d.v – see Cl 6.6.1h) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 092 | ETC - Account Low Balance | TCC or BOS/TCC or BOS generate the incident when an ETC identifier is flagged with low balance account indicator. (V2B5cl:5.3.4.5.d.vi). | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 093 | ETC - Tag Transaction Aborted | TCC or BOS/TCC or BOS generate the incident when an ETC identifier-based transaction is aborted for whatever reason. (V2B5cl:5.3.4.5.d.viii). | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 094 | ETC - Multiple Tags | TCC/TCC generate the incident in the event where multiple tags are read and queued without associating vehicles to each tag read. (V2B5cl:5.3.4.5). This includes multiple tags in one vehicle. | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 095 | Release Vehicle from Queue | TCC or BOS/TCC or BOS to generate this incident where the TCC or BOS pass a command to the TCC to open an exit boom/barrier in order to allow any vehicle to proceed without processing a normal financial transaction. These incidents shall typically be associated with a VLN transaction or the Main Contractor granting the motorist credit due to some lane processing failure. (V2B5cl:5.3.4.5) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 096 | Image Capturing Requirement fail | BOS/ The BOS generates this incident in the event where the VGS or other image recording device fail to provide the required image material to verify the presence of a specific vehicle, or the quality is of such nature that accurate verification of any event was not possible. (V2B5cl:5.3.4.5) | BOS/VGS/ITIS | Required for all ETC enabled Toll Lanes |
| 097 | Reserved |  |  |  |
| 098 | Reserved |  |  |  |
| 099 | Reserved |  |  |  |
| 100 | Reserved |  |  |  |
| 101 | Reserved |  |  |  |
| 10x | Reserved |  |  |  |
| 10x | Reserved |  |  |  |
| 10x | Reserved |  |  |  |
| n | nth Incident | N’th incident-Incidents to be mapped, unique to each toll system required where deviations were approved. |  | As required |

PS7.4.6	Transmitted Data

Clause 7.4.6.2(a) add the following requirements to table 7-17:

| File Type | Frequency | Interface deadlines for file transmission purposes | Type of Application |
| --- | --- | --- | --- |
| All recorded DCS Incident/Fault Log Data | Daily, the next calendar day | Within four (4) hours after midnight, the end of previous calendar day | Conventional |
| Validated Corrected DCS Incident/Fault Log data | Daily the next calendar day | Within twenty-four (24) hours after midnight, the end of the previous calendar day | Conventional |

PS7.4.6.7 	DCS Incident/faults Log Data Transmission Format for Conventional Tolling Applications:

Delete this Clause and replace with the following:

“DCS Incident/Faults Log Data Transmission Format for Conventional Tolling Applications:

- This file will contain summarised DCS Fault Log data rolled-up per hour for each applicable incident and be named according to the naming convention below. Data transmitted via this DCS-Fault log file shall only contain incidents relating to the applicable DCS activities and not AVC/Lane related incidents. The file shall contain incident reference summaries of the DCS incidents only – refer to Table 7-15. Incidents generated by the DCS on behalf of any specific lane AVC which carries a specific Lane-ID will thus not be included in the DCS Fault Log File but included in the standard AVC Incidents/Faults Log File as per Clause 7.4.6.6 above. DCS incident/faults log data records with zero (0) counts shall be included in the file for each hour of the calendar day.

- File Naming:

Example: 001_2002_04_13.dfl

Table 7-22: DCS Incident / Faults Log Data Transmission Format

| Description | Length | Sample |
| --- | --- | --- |
| Predefined Control Centre ID | 3 | 001 |
| Spacer | 1 | _ (Underscore) |
| Operating Date: yyyy_mm_dd | 10 | 2002_04_13 |
| File extension .dfl: First data file .dfr: Retransmitted file | 4 | .dfl |

- File Content

Example: 001|20100423|1|15|99AA|0|049|3|1245|

Table 7-23: DCS Incident / Faults Log Data Transmission Format

| Field | Field name | Req. | Data Type | Format | Sample |
| --- | --- | --- | --- | --- | --- |
| Field | Field name | Req. | Date Type | Format |  |
| 1 | Predefined Control Centre ID | Yes | Number | 999 | 001 |
| 2 | Operating Date (yyyymmdd) | Yes | Number | 99999999 | 20100423 |
| 3 | Validated 0: Un-validated 1: Validated-Correct – No AVC transaction, incidents or audit files sequence numbers missing from any lane. 2: Validated-Incorrect – Any data discrepancy found based on the criteria in Validation status, 1 above. | Yes | Number | 9 | 1 |
| Field | Field name | Req. | Data Type | Format | Sample |
| Field | Field name | Req. | Date Type | Format |  |
| 4 | Hour (00-23) | Yes | Number | 99 | 15 |
| 5 | Lane ID (constant: 99AA) | Yes | Char (4) | 99AA | 99AA |
| 6 | AVC status mode: 7: Always use default state ‘7’ in each record. | Yes | Number | 9 | 7 |
| 7 | DCS Incident ID (Only incidents applicable to DCS actions) | Yes | Number | 999 | 052 |
| 8 | DCS Critical Error Count (not applicable – default = 0) | Yes | Number | Long | 0 |
| 9 | DCS Incident count for the Hour | Yes | Number | Long | 1245 |

| Description | Length | Sample |
| --- | --- | --- |
| Predefined Virtual Toll Plaza ID | 3 | 001 |
| Spacer | 1 | _ (Underscore) |
| Date & hour : yyyy_mm_dd | 10 | 2002_04_13 |
| File extension .dfl: First data file .dfr: Retransmitted file | 4 | .dfl |

PS 7.5 BACK-OFFICE SYSTEM AND TRAFFIC ANALYSIS SYSTEM INTERFACE

This interface shall not be required.

PS SECTION 9. RELEVANT VPC SYSTEM SPECIFICATIONS

The Contractor shall not be required to comply with the requirements of this section.

PS10.2	Axle-Based AVC Verification for Conventional/Hybrid Toll Plaza

PS10.2.1.8	Sample sizes for AVC Accuracy Calculations

The minimum traffic sample sizes and maximum allowable sampling margins of error per toll lane for the initial AVC Accuracy Certification are specified as follows:

KRANSKOP TOLL PLAZA

| Designated Sample Lanes | Toll Class 1 Classification | Toll Class 2 Classification | Toll Class 3 Classification | Toll Class 4 Classification | Overall Count |
| --- | --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% | 99% |
| Minimum Traffic Sample (n) | 67 227 | 3 752 | 2 226 | 8 572 | 11 000 |
| Maximum Error Margin (d) | 0.048% | 0.697% | 0.814% | 0.211% | 0.078% |

NYL TOLL PLAZA

| Designated Sample Lanes | Toll Class 1 Classification | Toll Class 2 Classification | Toll Class 3 Classification | Toll Class 4 Classification | Overall Count |
| --- | --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% | 99% |
| Minimum Traffic Sample (n) | 42 879 | 2 275 | 1 474 | 4 803 | 11 000 |
| Maximum Error Margin (d) | 0.06% | 0.896% | 1.0% | 0.281% | 0.078% |

CAPRICORN TOLL PLAZA

| Designated Sample Lanes | Toll Class 1 Classification | Toll Class 2 Classification | Toll Class 3 Classification | Toll Class 4 Classification | Overall Count |
| --- | --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% | 99% |
| Minimum Traffic Sample (n) | 65 318 | 4 745 | 2 962 | 7 232 | 11 000 |
| Maximum Error Margin (d) | 0.048% | 0.620% | 0.706% | 0.229% | 0.078% |

BAOBAB TOLL PLAZA

| Designated Sample Lanes | Toll Class 1 Classification | Toll Class 2 Classification | Toll Class 3 Classification | Toll Class 4 Classification | Overall Count |
| --- | --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% | 99% |
| Minimum Traffic Sample (n) | 19 303 | 1 577 | 1 329 | 5 623 | 11 000 |
| Maximum Error Margin (d) | 0.089% | 1.076% | 1.054% | 0.260% | 0.078% |

The Main Contractor shall ensure that all necessary measures, including inter alia selective toll lane usage in a Virtual Toll Plaza, are implemented to ensure that the minimum vehicle throughput levels are processed in each designated sample toll lane during the initial accuracy certification period.

The minimum sample sizes and maximum allowable sampling margins of error per Control Centre, for the Post Initial AVC accuracy Certification (continuous AVC Classification) are specified as follows:

| Kranskop Control Centre | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 403 363 | 22 509 | 13 357 | 51 434 |
| Maximum Error Margin (d) | 0.019% | 0.285% | 0.332% | 0.086% |

| Nyl Control Centre | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 42 879 | 2 275 | 1 474 | 4 803 |
| Maximum Error Margin (d) | 0.06% | 0.896% | 1.0% | 0.281% |

| Capricorn Control Centre | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 65 318 | 4 745 | 2 962 | 7 232 |
| Maximum Error Margin (d) | 0.048% | 0.620% | 0.706% | 0.229% |

| Baobab Control Centre | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 19 303 | 1 577 | 1 329 | 5 623 |
| Maximum Error Margin (d) | 0.089% | 1.076% | 1.054% | 0.260% |

These values represent the minimum traffic samples that must be met over the accuracy monitoring period. As indicated in Volume 2 Book 4(a), the AVC Accuracy will be based on the total traffic throughput over the specified accuracy monitoring period per AVC accuracy category. If the total traffic throughput is less than these minimum traffic sample sizes, the accuracy monitoring period may be extended or an alternate minimum sample size determined using the formulas indicated, for the AVC accuracy category in question. This shall be at the discretion of the Employer Representative.

The minimum sample sizes and maximum allowable sampling margins of error per Virtual Toll Plaza for the Post Initial AVC accuracy Certification (continuous AVC classification), are specified as follows:

| Kranskop Mainline (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 487 340 | 28 245 | 18 008 | 65 409 |
| Maximum Error Margin (d) | 0.018% | 0.254% | 0.286% | 0.076% |

| Kranskop Mainline (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 496 599 | 30 050 | 18 272 | 64 542 |
| Maximum Error Margin (d) | 0.018% | 0.246% | 0.284% | 0.77% |

| Kranskop Local Ramp (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 105 663 | 4 597 | 1 912 | 12 177 |
| Maximum Error Margin (d) | 0.038% | 0.630% | 0.878% | 0.177% |

| Kranskop Local Ramp (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 42 679 | 4 635 | 1 880 | 12 175 |
| Maximum Error Margin (d) | 0.060% | 0.627% | 0.886% | 0.177% |

| Nyl Mainline (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 116 089 | 18 285 | 14 453 | 50 415 |
| Maximum Error Margin (d) | 0.036% | 0.3169% | 0.319% | 0.089% |

| Nyl Mainline (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 118 052 | 6 601 | 14 346 | 50 123 |
| Maximum Error Margin (d) | 0.0369% | 0.526% | 0.321% | 0.087% |

| Nyl Local Ramp (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 40 029 | 1 417 | 724 | 2775 |
| Maximum Error Margin (d) | 0.062% | 1.135% | 1.4279% | 0.370% |

| Nyl Local Ramp (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 83 918 | 4 115 | 2 050 | 6 027 |
| Maximum Error Margin (d) | 0.043% | 0.666% | 0.848% | 0.251% |

| Sebetiela Remote Ramp (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 136 584 | 6 205 | 2 345 | 4 518 |
| Maximum Error Margin (d) | 0.033% | 0.542% | 0.793% | 0.290% |

| Sebetiela Remote Ramp (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 151 605 | 8 452 | 2 935 | 6 229 |
| Maximum Error Margin (d) | 0.032% | 0.465% | 0.709% | 0.247% |

| Capricorn Mainline (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 260 085 | 18 372 | 11 505 | 27 496 |
| Maximum Error Margin (d) | 0.024% | 0.315% | 0.358% | 0.118% |

| Capricorn Mainline (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 262 459 | 19 584 | 12 190 | 30 359 |
| Maximum Error Margin (d) | 0.024% | 0.305% | 0.348% | 0.112% |

| Baobab Mainline (South) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 117 750 | 9 766 | 7917 | 34 330 |
| Maximum Error Margin (d) | 0.036% | 0.432% | 0.432% | 0.105% |

| Baobab Mainline (North) | Toll Class 1 | Toll Class 2 | Toll Class 3 | Toll Class 4 |
| --- | --- | --- | --- | --- |
| Confidence Level | 95% | 95% | 95% | 95% |
| Minimum Traffic Sample (n) | 115 819 | 9 461 | 7 972 | 33 733 |
| Maximum Error Margin (d) | 0.036% | 0.439% | 0.430% | 0.106% |

These values represent the minimum traffic samples that must be met over the accuracy monitoring period. As indicated in Volume 2 Book 4(a), the AVC Accuracy will be based on the total traffic throughput over the specified accuracy monitoring period per AVC accuracy category. If the total traffic throughput is less than these minimum traffic sample sizes, the accuracy monitoring period may be extended or an alternate minimum sample size determined using the formulas indicated, for the AVC accuracy category in question. This shall be at the discretion of the Employers Representative.

The minimum sample sizes and maximum allowable sampling margins of error per Toll Lane or Virtual Plaza for continuous AVC overall count accuracy, are specified as follows:

| Lane or virtual plaza | Overall AVC Count |
| --- | --- |
| Confidence Level | 99% |
| Minimum Traffic Sample (n) | 11 000 |
| Maximum Error margin (d) | 0.078% |

These values represent the minimum traffic samples that must be met over the accuracy monitoring period. If the total traffic throughput is less than these minimum traffic sample sizes, the accuracy monitoring period may be extended or an alternate minimum sample size determined using the formulas indicated, for the AVC accuracy category in question. This shall be at the discretion of the Employers Representative.

PS10.2.1.10

This paragraph to be modified to read as follows:

“The AVC classification accuracy against which the accuracy requirement specified in Clause 10.2.1.1 shall be compared with for certification/penalty/incentive purposes, shall be the Measured AVC accuracy value plus the margin of error (d) based on sample size (n) over the Accuracy Monitoring Period, as follows:

AVC Classification Accuracy = (Measured AVC Classification Accuracy (AVCM) = Margin of error (d).

PS10.2.1.17

This clause to be deleted and replaced with the following:

“For AVC Count Accuracy measurement purposes, the AVC Count error shall be total number of vehicles passages either not detected or incorrectly counted as AVC vehicles passages.  This equates to the total number of “undercounts” plus the total number of “over counts” divided by the total number of actual verified and true vehicle passages which as passed over or through the AVC sensors, over the AVC Monitoring Period.”

PS10.2.1.18

This clause to be deleted and replaced with the following:

“Total Count Error therefore equals the Absolute Sum value of both “Under Counting” and “Over Counting.” “Over Counting” and “Under Counting” does not offset each other, but both append to the Total Count Error:

Count Error = ABS (“Over Counting”) + ABS (“Under Counting”).”

PS 10.2.1.20 The AVC count accuracy verification procedure

Add:

“10.2.1.20. a) The Main Contractor, Contractor and Principal Employer’s Representative shall use the VGS, enhanced by the implementation of lane level ANPR, to verify and certify the AVC Count Accuracy and to report AVC count accuracy on a monthly basis.

For Initial AVC Count Accuracy verification, the Main Contractor shall use the data from the ANPR, VGS, DVSS and the AVC to report the AVC count accuracy per lane.

- The Contractor shall identify and record the AVC count errors in the lane selected to verify count accuracy, using the VGS. The Contractor shall achieve this by auditing possible undetected passages, using the VGS. The Contractors VGS auditor will evaluate each event using the ANPR, side view, front view, and booth camera video recording and flag each over (multiple reporting of a single passage) and under (undetected passage) count for one lane a number of passages exceeding the specified sample size. The VGS shall retain the auditors’ findings and allow a post audit review of such findings. AVC Count errors shall include transactions generated incorrectly (non-existing passage or multiple passages belonging to the same vehicle) by the AVC and transactions missed by the AVC. The events audited by the Contractor, utilising the VGS shall include but not be limited to:

  - Run throughs,

  - Irregular vehicle movements reported by the AVC, including, roll-back, reverse entry, vehicle standing and reverse roll-back,

  - Light vehicles with more than 3 axles,

  - Passages with more than 8 axles, and

  - Video motion-based passage for which no vehicles were registered by the AVC.

- The Contractor shall use the findings of the count accuracy verification, described above, to find similar AVC errors for all lanes. The Contractor shall, based on detected AVC count errors, identify AVC related error messages and conditions that are linked to AVC count errors in all lanes. The Contractor shall use such findings to identify AVC count error in every lane and capture the audit findings for each event on the VGS. The VGS auditors’ findings shall be retained on the VGS and the related video for 6 months. The Contractor shall, for all lanes, use the results of the error identification to:

- Detect and record the total traffic by adding undetected vehicle passages and deducting incorrectly generated passages from the total AVC traffic. The Contractor shall create missing transactions on the BOS system at the correct time and with the correct visually verified classification. The AVC class for the created transactions shall be “NC”.

- Combine the daily traffic and count errors values for the evaluation period and calculate the AVC count accuracy for all lanes.

The Contractor shall keep records of the audit findings during the verification process and list the details of all hours investigated and the allocation of errors and differences. The Contractor shall at the end of the

evaluation periods generate an initial AVC count accuracy verification report that include all the details of the events audited and the event details of each individual AVC error recorded.”

“10.2.1.20. b) For Post Initial AVC Count Accuracy verification the Main Contractor shall use the VGS, identified messages/events and conditions detected during the initial verification period to record and report the AVC count accuracy for each virtual plaza for the month:

- The Main Contractor shall for every calendar day for the month, record total traffic and AVC count errors. The Main Contractor shall detect and record the total AVC count errors in all lanes. The Main Contractor shall, based on previously detected AVC count errors, identify AVC related error messages and conditions linked to AVC count errors, and use the VGS to evaluate the side view camera video recording for all such AVC error messages and conditions and record every identified AVC count error. The VGS auditors’ findings shall be retained on the VGS and the related video for 6 months. The Main Contractor shall create transactions on the BOS system at the correct time and with the correct visually verified classification for all transactions not detected by the AVC. The AVC class for the created transactions shall be “NC”.

- Detect and record the total traffic by adding undetected vehicle passages and deducting incorrectly generated passages from the total AVC traffic per virtual plaza.

- Combine the daily traffic and count errors values per virtual plaza for the month and calculate the AVC count accuracy.

The Main Contractor shall keep records of the audit findings during the verification process and list the details of all hours investigated and the allocation of errors and differences. The Main Contractor shall report the AVC count accuracy monthly as specified (KPI 3d).”

C3.2.5	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATION FOR OPERATIONS AND MAINTENANCE: ELECTRONIC TOLL COLLECTION (VOLUME 2 BOOK 5)

The number of each Clause in particular specifications in this section consists of the prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specification for the Operations and Maintenance: Electronic Toll Collection (Volume 2 Book 5). The number of any new Clause which does not form part of any Clause in the Standard Specification for the Operations and Maintenance: Electronic Toll Collection (Volume 2 Book 5), and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Standard Specification for the Operations and Maintenance: Electronic Toll Collection (Volume 2 Book 5).

PS 1.1.1.8	Interpretation

Add the following Clause:

“1.1.1.8	The TCH has been deployed successfully and therefore all references to the TCH in Book 5 which is or needs to be deployed/established shall be read as having been successfully installed, deployed and has been operational over an extended period of time. “

PS1.3	Definitions

Add the following definition:

“Merchant Agreement”	The term “Merchant Agreement” shall mean the TA/TCH Service Level Agreement (SLA). The Service Level Agreement sets out the operational rules of engagement between the TA and the TCH. Refer to Part E14 of Volume 4. For the latest SLA.

“Business Rules” 	The term “Business Rules” used in this document shall have the same meaning and reference to the Standard Specifications for Operations and Maintenance of CTROM Projects: ETC Interoperability - Business Rules.

“Disastrous Event” 	The term “Disastrous Events” and “Catastrophic Event” used in this document and related documents, shall have the similar if not the same meaning, depending on the context used in, as an “Exceptional Event” as defined in Volume 1 Book 1 (FIDIC). For purposes of processing ETC transactions or interaction with the TCH or any other serviced used to communicate with the TCH, the term “Catastrophic Event” is used. However, the term Catastrophic Event is used in the ETC/TCH environment when processes fail for whatever reason and cannot be restored within the allowed performance parameters. Responsibility and/or Cause of/for any failure is typically identified and allocated, post facto and does not equate to the traditional Force Majeure or Exceptional Event.”

PS 2.1	Purpose and Scope

The Contractor is to note that Dedicated ETC toll lanes has been installed at Kranskop mainline (two (4 of which 2 needs to be relocated to Capricorn mainline plaza) lanes) and Nyl mainline (two (2) lanes, in terms of the requirements in the Standard Specifications for the Operations and Maintenance of CTROM Projects:   Toll systems (Volume 2 Book 4a) and in the Standard Specification for Operation and Maintenance of CTROM Projects:  Electronic Toll System Collector (ETC) (Volume 2 Book 5).

The 8 Dedicated ETC toll lanes and will be accepting, processing, submitting and reconciling tag transactions from the Commencement Date of the Operations Service Period. The Dedicated lanes may from time to time be switched to Mixed ETC lanes, depending on the requirements.

The remainder of the toll lanes for all the Toll Plazas on the N1N Toll Road are mixed Manual/ETC toll lanes and will be accepting, processing, submitting and reconciling tag transactions from the Commencement Date of the Operations Service Period. Some of the Dedicated lanes will be equipped to operate in Tag only mode (auto mode) to improve service levels for road users with tags.

The Contractor must ensure that the upgrade/new toll system meets the following requirements

- It is a requirement for the Contractor to ensure that:

  - The toll system makes provision for the integration of a tag reader, and associated interface software, required in any Lane, in order to implement Mixed/Manual or Dedicated ETC Lane functionality;

  - The toll system is capable of accepting electronic tag as a valid Payment Mechanism and is capable of meeting all the requirements as specified in the Contract relating to the processing of such transactions from toll lane level to the Back Office System, as well as the transmission of transaction records from the Back Office to the Transaction Clearing House (TCH);

  - The toll system is capable of accurately detecting, classifying, processing transaction records and provides sufficient information to accurately conclude vehicle passage transactions from the Mixed/Manual ETC and from the Dedicated ETC toll lanes.

  - The Contractor shall provide, install, integrate and maintain high speed toll lane exit boom barriers, restricting passage to any vehicle type across the entire width of all toll lanes, if not already installed in all toll lanes from the Commencement Date. Automated exit booms shall be controlled by the TCC and shall incorporate a safety device/s safeguarding against the closure of any such barrier during a vehicle passage over or through the AVC sensors, damaging any vehicle. Separation of vehicles shall be accomplished by means of such booms in the Mixed/Manual ETC and Dedicated ETC toll lanes. The Dedicated ETC toll lanes shall also incorporate additional vehicle separation and axle counting devices to accurately determine vehicle position identification and vehicle flow through the Dedicated ETC toll lane;

  - The toll system caters for the recording of the Manual Collector Vehicle classification (MVC), the tag vehicle class (EVC), the Automatic Vehicle Classification System (AVC) vehicle class as well as the verified and corrected vehicle class (SVC).

  - In Mixed/Manual and Dedicated ETC Lanes, the following:

    - The TCC shall have an output signal ready, in addition to the existing OHLS green arrow signal, in order to switch the ETC overhead mounted lane sign (ETC OHLS). It shall be required that the lane control be maintained by the toll collector and that the tag transaction in such toll lanes not be processed without an MVC captured on the toll system. A passage transaction without an MVC class shall be considered to constitute a violation passage or Run-Through.

  - The toll system is capable of interfacing with the required ETC Equipment and interfaces that comply with the relevant standards in Clause 9.2.1 of the Standard Specification for Operations and Maintenance: Electronic Toll Collection (ETC). In terms of tags, the Contractor shall demonstrate that the toll system can interface to all of the Employers approved “Pre-Qualified” tags. A list of such pre-qualified tags is available on request.

- The ETC requirements will, in its entirety or part thereof, be triggered by Employers for implementation. The following is noted:

  - The toll system is capable of accepting, processing and clearing tag transactions as specified in the Standard Specification for Operations and Maintenance: Electronic Toll Collection (ETC) and attention is drawn to Clause 5.3 of the Standard Specification for Operations and Maintenance: Electronic Toll Collection (ETC): Responsibilities of the Toll Agency. The Contractor toll system shall, however, maintain the functionality for accounts that are honoured by means of an ISO bank credit card which shall be honoured via the existing bank interface described elsewhere.

  - It shall not be required that the Contractor prove interoperability by using two (2) different tag readers from two un-related suppliers. The Contractor shall however demonstrate that the toll system shall successfully accept and process toll transactions from all the Prequalified Tag suppliers, or from all the different tags issued by the TCH.

- If the TCH is commissioned before and operational by the Commencement Date, then the Contractor’s toll system, in this case, the phase specified within Clause 3.4 of the Standard Specification for Operations and Maintenance:  Electronic Toll Collection (ETC): Interoperability of ETC systems deployed before the TCH, will not be applicable.

- The Contractor shall only be remunerated for the cost relating to the procurement and installation and successful commissioning of ETC related equipment and functionality on a proven cost-plus mark-up basis if and when the Employer decides to continue with the implementation of ETC outside those options described in the Schedule of Payments/Cost Matrix. This shall include but not limited to the procurement and installation of:

  - Signage, OHLS and User Fare Displays not described in the Contract;

  - The development of specific requirements of the phase specified within Clause 3.4 of the Standard Specification for Operations and Maintenance:  Electronic Toll Collection (ETC).

- The Contractor shall carry all costs relating to any other software modifications, upgrades and enhancements to the toll system required for the implementation of ETC, not specifically excluded above.

- The Main Contractor shall carry all costs relating to the administration of tags.

- Requirements specific relating to the Functional Compliance requirements of the toll system. The Contractor shall provide the necessary procedures, configuration, equipment and test vehicles to test and verify the correct and compliance functioning of the following:

  - Upon request, the Contractor shall receive from Employer, as a minimum five (5), sample tags from every “Prequalified” Tag supplier (to serve as test transaction test input data), together with five (5) legacy tags which shall be sourced from the Bakwena Platinum Corridor Concessionaire (BPCC). This shall mean that the compliance test shall consist of the capturing of fictitious tag Reader/interface data into the toll lane computer to simulate the tag communication (bi-directional) process.

  - As with the rest of the toll system, the Contractor shall bear all costs relating to the compliance testing of all ETC requirements.

PS 8.5 	INFORMATION TO ROAD USERS

Replace subclause 8.5.2 (Before a Toll Plaza) with the following:

The Main Contractor shall provide a “Tags Accepted” road sign of 2.14 by 1.2 m in the approach to the Toll Plaza, as per the following image.

The Main Contractor shall provide a “HEAVY VEHICLES KEEP LEFT” road sign of 3.656 by 1.2 m in the approach to the Toll Plaza, as per the following image.

Replace subclause 8.5.3 (At the Toll Plaza selecting the correct lane)

The Main Contractor shall provide two road signs of 2.2 by 1.2 m each, together with a chevron sign at the bottom on a lane height restrictor for dedicated ETC lanes, as per the following image.

The Main Contractor shall provide 2 “Shesha” road signs of 0.938 by 0.720 m on both sides of the entrance to the Shesha lane, as per the following image.

PS 8.6 	FIXED SIGNS ON THE TOLL PLAZA CANOPY

Delete clause 8.6 (FIXED SIGNS ON THE TOLL PLAZA CANOPY).

PS 8.7	CHANGEABLE MESSAGE SIGNS

Delete clause 8.7 (CHANGEABLE MESSAGE SIGNS).

PS 8.8 	OVERHEAD LANE SIGNS

Delete subclause 8.8.4, add replace it with:

“8.8.4 The green arrow and red cross sign in Figure 8-11, shall be used to indicated if a mixed ETC lane open (green arrow) and closed state (red cross)”

At the end of subclause 8.8.5, add the following:

“8.8.6	The typical specifications of the ETC OHLS (e-sign) shall be:

- An amber colour in the 590 to 610 nm range wavelength

- Display the letter “e”, which design, and font type needs to be approved by the Employer at first

- The same size as the green arrow and red cross OHLS, mounted next to each other and aligned horizontally

- Constructed from a matrix of high brightness surface mount LEDs designed for outdoor use with a IP65 rating as a minimum

- Use less than 50 watts from a 240 Volt ac supply

- Switchable from the Lane Controller to indicate a dedicated, mixed or closed ETC lane configuration

- Automatically dimmable in low light conditions

- Mounted on the approaching edge of the Toll Plaza Canopy above the centreline of each Lane facing the direction of the approaching traffic

- Visible at least 500m from the toll plaza

- Have a wide viewing angle so that it is still visible just before the entrance to the Toll Lane

- Have a high MTBF of more than 60 000 hours

- Have suitable lightning protection

C3.2.6	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATIONS FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS:  PERFORMANCE MEASUREMENT (VOLUME 2 BOOK 6a)

The number of each Clause in a Particular Specifications in this section consists of the Prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specification for the Operations and Maintenance: Performance Measurement (Volume 2 Book 6a). The number of any new Clause which does not form part of any Clause in the Standard Specification for the Operations and Maintenance: Performance Measurement (Volume 2 Book 6a), and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Standard Specification for the Operations and Maintenance: Performance Measurement (Volume 2 Book 6a).

PS3	PERFORMANCE MEASUREMENT

PS3.1.2:	Key Performance Indicators

PS3.1.2.3

The third line of this subclause to be modified to read as follows:

“... Employer may submit a request to the Performance Review Committee to introduce ...”

At the end of the subclause, adding the following:

“…being delivered.  A National Performance Review (NPRC) Committee will be held at least twice (2) a year to align all CTROM Performance Measurement Models.  A member or members from the Main Contractor shall attend these meetings.”

PS3.1.2.6

The subclause 3.1.2.6 to be deleted and replaced with the following:

“Unless otherwise mutually agreed between the Parties, this Performance Management Regime shall be reviewed by the Performance Review Committee when required or at least every four (4) months from the Commencement Date of Operations Services Period.  The first Performance Review Committee meeting must be held within four (4) months from the Commencement Date of the Operations Service Period in order to finalise reports and report formats for input to the Performance Measurement Model.”

PS3.1.2.9

This subclause to be modified to read as follows:

“The derivation of the Performance scores is a multi-stage process that shall be derived from operational processes and timely reporting from the Contractor’s Toll System to the Main Contractor, Employer’s Representative and the Employer at prescribed intervals.”

PS3.2.2:  Aggregation of Performance Scores

PS3.2.2.2

Delete subclause 3.2.2.2 and replace with the following:

The total Performance Scores for all critical success factors shall be summed to derive the total Performance Score per Control Centre per month.”

Add the following clause:

PS3.2.4:	Example of Calculating KPI

PS3.2.4.5

The first bullet to be modified to read as follows:

- “Lane grouping A with accuracy of 99.3% and lane grouping B with an accuracy of 99.99% for the month.”

PS3.2.4.10

The Clause to be modified to read as follows:

“The total score for Control Centre is -105 + 2.7 = -102.3”.

PS3.2.4.11

Replace the table under this Clause with the following:

| Critical Success Factor | Performance Areas | KPI Number | KPI Name | SCORE |
| --- | --- | --- | --- | --- |
| Public Awareness and Understanding | Customer Relations | CT5 | Uninterrupted Electricity Supply | 0.0 |
|  |  | CT6b | Call abandon rate, including IVR calls held pending transfer to a Call centre Operator | 0.0 |
|  |  | CT6c | Call queuing time, including IVR calls held pending transfer o an Operator | -10.0 |
|  |  | CT6d | Call Centre Level of Service (LOS) - Proportion of calls blocked in peak demand period | -20.0 |
|  |  | CT10 | Charging and charge reconciliation processes - accuracy | 0.0 |
|  |  | CT11 | Customer Satisfaction | 20.0 |
|  |  | CT13 | ETC Transaction Records submitted to TCH – timeliness | 50.0 |
|  |  | CT14 | Account Registration Processing - accuracy | 0.0 |
|  |  |  | SUB-TOTAL FOR CUSTOMER RELATIONS: | 40.0 |
|  | Marketing Support | CT18 | Tactical marketing programme Level of Service (LOS) | 10.0 |
|  |  |  | SUB-TOTAL FOR MARKETING SUPPORT: | 10.0 |
|  | Channel Availability | CT6a | Call Centre service availability, including IVR services | 120.0 |
|  |  | CT9 | POP Customer Services Facilities - availability | 0.0 |
|  |  |  | SUB-TOTAL FOR CHANNEL AVAILABILITY: | 120.0 |
|  |  |  | TOTAL FOR PUBLIC AWARENESS AND UNDERSTANDING: | 170.0 |
| Revenue Maximisation | Charging Effectiveness | CT4a | Daily AVC Data Transmission – Un-validated | -15.0 |
|  |  | CT4b | Daily AVC Data Transmission – Validated | -20.0 |
|  |  | CT4c | Daily MIS Data Transmission | -40.0 |
|  |  | CT4d | Monthly MIS Data Transmission | -10.0 |
|  |  | CT4e | Monthly MIS Income Data Transmission | -100.0 |
|  |  |  | SUB-TOTAL FOR CHARGING EFFECTIVENESS: | -185.0 |
|  | Charging Accuracy | CT3c | Automatic Vehicle Classification Accuracy – Axle-based | 2.0 |
|  |  | CT3d | AVC Count | 4.0 |
|  |  |  | SUB-TOTAL FOR CHARGING ACCURACY: | 6.0 |
|  |  |  | TOTAL FOR REVENUE MAXIMISATION: | -179.0 |
| Operational Performance | Quality Control | CT16 | Maintenance | -40.0 |
|  |  | CT17 | Transactions acceptable to TCH and VPC - proportion | 0.0 |
|  |  |  | SUB-TOTAL FOR QUALITY CONTROL: | -40.0 |
|  | Effectiveness | CT1a | Repair Time Compliance – Severity Level 1 Fixed Assets | 0.0 |
|  |  | CT1b | Repair Time Compliance – Severity Level 2 Fixed Assets | 0.0 |
|  |  | CT1c | Repair Time Compliance – AVC | -20.0 |
|  |  | CT1d | Repair Time Compliance – Severity Level 1 Semi-Fixed Assets | 0.0 |
|  |  | CT1e | Repair Time Compliance – Severity Level 2 Semi-Fixed Assets | 0.0 |
|  |  |  | SUB-TOTAL FOR EFFECTIVENESS: | -20.0 |
|  |  |  | TOTAL FOR OPERATIONAL PERFORMANCE: | -60.0 |
| System Health | Service Availability | CT2 | SCADA Service Availability | 0.0 |
|  |  | CT3a | AVC Availability – (Critical Errors) | 0.0 |
|  |  | CT3b | AVC Availability – (Serious Errors) | 0.0 |
|  |  | CT12 | ETC lane availability | -50.0 |
|  |  | CT15 | QLS –availability | 0.0 |
|  |  |  | SUB-TOTAL FOR SERVICE AVAILABILITY: | -50.0 |
|  |  |  | TOTAL FOR SYSTEM HEALTH: | -50.0 |
| Cooperative Relationships | Reporting | CT8a | Compliance with Employer’s reporting requirements – Critical Reports | 0.0 |
|  |  | CT8b | Compliance with Employer’s reporting requirements – Non-Critical Reports | 0.0 |
|  |  |  | SUB-TOTAL FOR REPORTING: | 0.0 |
|  | Governance | CT19 | Contract Performance Management | 10.0 |
|  |  |  | SUB-TOTAL FOR GOVERNANCE: | 10.0 |
|  |  |  | TOTAL FOR COOPERATIVE RELATIONSHIPS: | 10.0 |
|  |  |  | GRAND TOTAL: | -109.0 |

PS3.2.4.13

Modify this subclause to read as follows:

“The Total Score for the Control Centre in the example is -109 points.”

PS3.3.2:	Reporting Requirement

PS3.3.2.2

This subclause to be deleted and replaced with the following:

“The Employer’s Representative shall be responsible to produce the Performance Measurement Model once per month, based on the Contractor’s performance and information provided.  The Performance Measurement Model shall also include all the Section 6 penalties in this model.  Together with the Performance Measure Model the ER shall also provide a penalty balance sheet which shall also reflect deductions made to the Contractor’s Certificate.”

PS3.3.2.4

This subclause to be deleted and replaced with the following:

“To ensure that the provision of services by the Contractor are managed effectively from the Commencement of Operations Services, Performance Review meeting, held as the Performance Review Committee, shall be convened by Employer’s Representative as and when required and agreed between the parties, but not less than every four (4) months.”

PS3.3.2.5:

This subclause to be deleted and replaced with the following:

“The Employer’s Representative shall produce the performance report by ten (10) working days after the Contractor has submitted all the required reporting, as stipulated in the Standard Specifications for Operations and Maintenance of CTROM projects:  General (Volume 2 Book 2a)” or as otherwise instructed by the Employer Representative to satisfy the input requirements to the Performance Measurement Model."

PS.3.3.2.6

This subclause to be deleted.

PS3.3.2.7:

Ten (10) business days.

PS3.3.2.8(a)

This subclause to be deleted and replaced with the following:

“For the purposes of performance measurement, the Performance Review Committee will include the following:

(a)	The Principal Employer’s Executive (or delegated senior official);

(b)	The Principal Employer’s Representative (can include another delegated member);

(c)	The Main Contractor’s Representative (can include another delegated member);

(d)	Auditing Body, as and when required by the Employer (to provide benchmarking and advice on performance issues)”

PS4.1 	Key Performance Indicators

The weightings and specifications to be modified to read as follows:

| Ref | Name | Score weighting, target service levels and other specifications |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Specifications, target service levels and calculation procedures | Scores per increment for Service Level Bands |  |  |  |
|  |  |  | Above target (‘r’) | Band 1 (‘x’) | Band 2 (‘y’) | Band 3 (‘z’) |
| CT1a | Repair Time Compliance – Severity Level 1 - Employer Facilities | - | 0.0 | -1.5 | -3.0 | -15.0 |
| CT1b | Repair Time Compliance – Severity Level 2 - Employer Facilities | - | 0.0 | -0.8 | -1.5 | -7.5 |
| CT1c | Repair Time Compliance – AVC and TCC | - | 0.0 | -1.8 | -2.5 | -15.0 |
| CT1d | Repair Time Compliance – Severity Level 1 Permanent Design Built Assets | - | 0.0 | -1.0 | -2.0 | -10.0 |
| CT1e | Repair Time Compliance – Severity Level 2 Permanent Design Built Assets | - | 0.0 | -0.8 | -1.5 | -7.5 |
| CT2a | SCADA Availability | 95% | 0.0 | -0.8 | -1.5 | -15.0 |
| CT2b | VGS Availability (Critical Errors) | 95% | 0.0 | -3.0 | -5.0 | -15.0 |
| CT2c | QLS Availability (Critical Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT2d | QL1 Availability (Critical Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT2e | QL2 Availability (Critical Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT2f | BOS Availability (Critical Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT2g | PGW Availability (Critical Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT3a | AVC Availability (Critical Errors) | - | 0.0 | -5.0 | -10.0 | -35.0 |
| CT3b | AVC Availability (Serious Errors) | - | 0.0 | -3.0 | -5.0 | -15.0 |
| CT3c | Automatic Vehicle Classification for Class 1 | - | 0.03 | -0.25 | -0.75 | -5.0 |
| CT3c | Automatic Vehicle Classification for Class 2 | - | 0.03 | -0.25 | -0.75 | -8.0 |
| CT3c | Automatic Vehicle Classification for Class 3 | - | 0.06 | -0.25 | -0.75 | -5.0 |
| CT3c | Automatic Vehicle Classification for Class 4 | - | 0.06 | -0.25 | -0.75 | -5.0 |
| CT3d | AVC Count | - | 0.15 | -1.0 | -2.0 | -10.0 |
| CT4a | Daily AVC Data Transmission – Un-validated | - | 0.0 | -5.0 | -10.0 | -40.0 |
| CT4b | Daily AVC Data Transmission – Validated | - | 0.0 | -8.0 | -18.0 | -50.0 |
| CT4c | Daily Back-Office Data Transmission | - | 0.0 | -8.0 | -18.0 | -50.0 |
| CT4d | Monthly Back-Office Data Transmission | - | 0.0 | -12.0 | -18.0 | -60.0 |
| CT4e | Monthly Back-Office Income Data Transmission | - | 0.0 | -12.0 | -18.0 | -60.0 |
| CT6a | Call Centre service availability, including IVR services | If there is not direct one-to-one relationship between Route Call Centres and Control Centres, the average monthly score across all Route Call Centres shall be applicable to each Control Centre. | 0.5 | -1.0 | -1.5 | -10.0 |
| CT6c | Route Call Centre call queuing time, including IVR calls held pending transfer to an operator | - | N/A | -0.2 | -0.5 | -10 |
| CT8a | Compliance with Employer’s reporting requirements – Critical Reports | - | - | - | - | - |
|  | Hourly, Daily & Monthly Traffic Report | Report submission within contractual allowable time | 0 | -5.0 | -10.0 | -60.0 |
|  | Discount / Exempt Report | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
|  | Account Status | Report submission within contractual allowable time | 0 | -3.0 | -5.0 | -30.0 |
|  | Payment Trends | Report submission within contractual allowable time | 0 | -3.0 | -5.0 | -30.0 |
|  | Day/Month Closures | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
|  | AVC Accuracies | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
|  | System Availability | Report submission within contractual allowable time | 0 | -3.0 | -6.0 | -35.0 |
|  | Equipment failures | Report submission within contractual allowable time | 0 | -3.0 | -5.0 | -30.0 |
|  | Response & Repair times | Report submission within contractual allowable time | 0 | -3.0 | -6.0 | -35.0 |
|  | Problem Data | Report submission within contractual allowable time | 0 | -3.0 | -6.0 | -35.0 |
|  | Support Reports | Report submission within contractual allowable time | 0 | -3.0 | -5.0 | -30.0 |
|  | Stock & Spares | Report submission within contractual allowable time | 0 | -3.0 | -5.0 | -30.0 |
|  | Performance Measurement Report | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
|  | KPI 11 | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
|  | KPI 19 | Report submission within contractual allowable time | 0 | -4.0 | -8.0 | -40.0 |
| CT8b | Compliance with Employer’s reporting requirements – Non-Critical Reports | - | - | - | - | - |
|  | Transaction Tariff report | Report submission within contractual allowable time | 0 | -1.0 | -2.0 | -10.0 |
|  | Discount Structure Report | Report submission within contractual allowable time | 0 | -1.0 | -2.0 | -10.0 |
|  | Transaction details report | Report submission within contractual allowable time | 0 | -2.0 | -3.0 | -15 |
|  | Class discrepancy acknowledgement | Report submission within contractual allowable time | 0 | -2.0 | -3.0 | -15 |
|  | Access Control | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | Version Control | Report submission within contractual allowable time | 0 | -2.0 | -3.0 | -15 |
|  | MTBF | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | Incident Report | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | Dashboard Report | Report submission within contractual allowable time | 0 | -2.0 | -3.0 | -15 |
|  | Upgrade Reports | Report submission within contractual allowable time | 0 | -2.0 | -3.0 | -15 |
|  | Contractual Reporting | Report submission within contractual allowable time | 0 | -3.0 | -6.0 | -30.0 |
|  | Generator | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | UPS | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | Earthing& Lighting Protection | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
|  | Corrosion Protection | Report submission within contractual allowable time | 0 | -2.0 | -4.0 | -20.0 |
| CT9 | POP Customer Service Facilities - availability | If there is not direct one-to-one relationship between POP Customer Service Facility and Control Centres, the average monthly score across all POP Customer Service Facilities shall be applicable to each Control Centre. | 1 | -1 | -1.5 | -8 |
| CT10 | Charging and charge reconciliation processes - accuracy | At least 99.99% of ETC Transactions should be reconciled correctly (0.01% incorrectly) Where the accuracies per Control Centre are not available, the overall accuracy shall be applicable to each Control Centre. | 0 | -2 | -5 | -50 |
| CT11 | Customer Satisfaction | If separate scores cannot be associated to each Control Centre, the overall score shall be applied to each Control Centre. | 1.5 | -1.5 | -2.5 | -15 |
| CT12 | ETC lane availability | ETC Lanes should be available for at least 98% of the time in a day. | 0 | -1.5 | -3 | -15 |
| CT13 | ETC Transaction Records submitted to TCH – timeliness. | Measurement of KPI to commence when both commencement of ETC tolling as taken place and the ETC transaction market share for the Control Centre is 50% or more for three consecutive months. This KPI aims to incentive close to real time transaction forwarding to the TCH. The incentive will be applicable when 85% or more of ETC transactions per Control Centre are forwarded to the TCH within 2 hours (‘n’ = 2 hours) | 0.8 | 0.0 | 0.0 | 0.0 |
| CT14 | Account Registration Processing - accuracy | 97.5% accuracy | 0 | -1 | -2 | -10 |
| CT15 | QLS –availability | The QLS should be available for at least 99.7% of the time in a month. | 0 | -0.25 | -0.5 | -10 |
| CT16 | Maintenance | n/a | 2 | -3 | -10 | -30 |
| CT18 | Tactical marketing programme Level of Service (LOS) | If separate scores cannot be associated to each Control Centre, the overall score shall be applied to each Control Centre for the duration of a measurement period. | 1 | -1 | -2.5 | -15 |
| CT20 | Route Patrol Qualification |  | 10.0 | -5.0 | -10.0 | -15.0 |
| CT21 | Fresh Air Supply Management |  | 0.0 | -3.0 | -4.0 | -12.0 |

Table 4-1:

Replace the relevant columns as shown below for “CT16” only with the contents shown here:

|  | Target Service Level | Band 1 | Band 2 | Band 3 |
| --- | --- | --- | --- | --- |
| CT16 | > 55% (‘r’ pts per 1.0%) | 45% to < 50% (‘x’ pts per 1.0%) | 40% to < 45% (‘y’ pts per 1.0%) | < 40% (‘z’ pts per flat rate) |

Table 4-1:	Add the following to the table under the relevant KPI numbers:

| CT2b | Service Availability | VGS Availability (Critical Errors) | The number of occurrences that the VGS downtime, related to Critical Mode, in a VGS exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence) | 11 to 20 (‘y’ pts per occurrence) | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CT2c | Service Availability | QLS Availability (Critical Errors) | The number of occurrences that the QLS downtime, related to Critical Mode, in a QLS exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence) | 11 to 20 (‘y’ pts per occurrence) | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| CT2d | Service Availability | QL1 Availability (Critical Errors) | The number of occurrences that the QL1 downtime, related to Critical Mode, in a QL1 exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence) | 11 to 20 (‘y’ pts per occurrence) | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| CT2e | Service Availability | QL2 Availability (Critical Errors) | The number of occurrences that the QL2 downtime, related to Critical Mode, in a QL2 exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence) | 11 to 20 (‘y’ pts per occurrence) | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| CT2f | Service Availability | Back Office Availability (Critical Errors) | The number of occurrences that the BOS downtime, related to Critical Mode, in a BOS exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence) | 11 to 20 (‘y’ pts per occurrence) | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| CT2g | Service Availability | PGW Availability (Critical Errors) | The number of occurrences that the PGW downtime, related to Critical Mode, in a PGW exceeds the time specified in Volume 2 Book 4a during a month. | Commencement of Operations Services | Zero occurrences | 1 to 10 (‘x’ pts per occurrence | 11 to 20 (‘y’ pts per occurrence | More than 20 (‘z’ pts flat rate) | CTROM limits 20 occurrences |
| CT20 | Quality Control | Route Patrol Personnel Qualifications | This KPI Measures the number of people not suitable qualified to perform the duties of Route Patrol Officers. The minimum qualification requirements are dictated in Volume 2 Book 2a, under Clause 19.4.1.6 of the contract | Commencement of Operations Services | All Officers suitable qualified and certified | 2 to 4 (‘x’ pts per occurrence) | 4 to 6 (‘y’ pts per occurrence) | 6 to 10 (‘z’ pts per occurrence) |  |
| CT21 | Quality Control | Fresh Air Management | The Fresh-air Penalty System ensures that the system is maintained properly, and operational procedures are enforced to ensure a healthy working environment. Fresh-Air pump off, or not working for longer than allowable time = 20 pts. Heater element not working = 3 pts per lane. Obstructions in air vents = 5 pts per lane. Additional heater in lane = 5pts per lane. | Commencement of Operations Services | Zero occurrences | 1 to 10 pts (‘x’ pts per point) | 11 to 24 pts (‘y’ pts per point) | More than 25 pts (‘z’ pts flat rate) |  |

PS4.1	Additional Detail Relating to KPI’s

PS4.1.3	2:  Availability of SCADA

Change the heading Description from “2: Availability of SCADA” to “Availability KPI’s”

PS4.1.3.1

Change the current PS4.1.3.1 Clause to PS4.1.3.1.1

Add Heading PS4.1.3.1 called “2a: Availability of SCADA.”

Add the following new subclause:

“PS4.1.3.1.2

The Main Contractor and Contractor shall define a measuring tool for this KPI and submit to the Principal Employer’s Representative before the first Performance Review Committee meeting for approval, unless such measuring tool is already included in the project information document (Volume 4).”

Add Heading PS4.1.3.2 called “2b: VGS availability”

Add the following new subclause:

“PS4.1.3.2.1

This KPI shall be applied if the VGS downtime, related to Critical Error Mode, for the VGS system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the VGS remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned VGS downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the VGS downtime was pre-approved by the Employer’s Representative.”

”

Add Heading PS4.1.3.3 called “2c: QLS availability.”

Add the following new subclause:

“PS4.1.3.3.1

This KPI shall be applied if the QLS downtime, related to Critical Error Mode, for the QLS system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the QLS remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned QLS downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the QLS downtime was pre-approved by the Employer’s Representative.””

Add Heading PS4.1.3.4 called “2d: QL1 availability”

Add the following new subclause:

“PS4.1.3.4.1

This KPI shall be applied if the QL1 downtime, related to Critical Error Mode, for the QL1 system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the QL1 remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned QL1 downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the QL1 downtime was pre-approved by the Employer’s Representative.”

.”

Add Heading PS4.1.3.5 called “2e: QL2 availability.”

Add the following new subclause:

“PS4.1.3.5.1

This KPI shall be applied if the QL2 downtime, related to Critical Error Mode, for the QL2 system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the QL2 remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned QL2 downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the QL2 downtime was pre-approved by the Employer’s Representative..”

Add Heading PS4.1.3.6 called “2f: Back Office availability.”

Add the following new subclause:

“PS4.1.3.6.1

This KPI shall be applied if the BOS downtime, related to Critical Error Mode, for the BOS system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the BOS remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned BOS downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the BOS downtime was pre-approved by the Employer’s Representative.””

Add Heading PS4.1.3.7 called “2g: PGW availability”

Add the following new subclause:

“PS4.1.3.7.1

This KPI shall be applied in the event that the PGW downtime, related to Critical Error Mode, for the PGW system exceeds the maximum time limit as specified. This KPI shall be applied for every continuous maximum specified period that the PGW remained in critical error mode.

The Contractor shall apply to the Employer’s Representative for approval for planned PGW downtime due to maintenance which will exceed the above periods.

Downtime which will exceed the above periods shall be excluded from the performance measurement if the PGW downtime was pre-approved by the Employer’s Representative.”

PS4.1.13	5:  Uninterrupted Electricity Supply

This subclause to be deleted

PS4.1.15	6c:  Call Queuing Time

This subclause to be deleted.

PS4.1.23	15:  QLS Availability

Add the following new subclause:

“PS4.1.23.3

The Main Contractor and Contractor shall define a measuring tool for this KPI and submit to the Employer’s Representative before the first Performance Review Committee meeting for approval, unless such measuring tool is already included in the Project Information Document (Volume 4).”

Add the following new subclasses:

“PS 4.1.27	20:  Route Patrol Personnel Qualifications

PS 4.1.27.1	This KPI measures the training of the route patrol personnel as par subclause 19.4 Volume 2 Book 2.

PS 4.1.27.2	The Main Contractor shall provide a monthly report listing of all Route Patrol personnel and indicating the Compliance to the requirements for each personnel.  The Main Contractor to provide copies of Certification for each personnel.”

“PS 4.1.28	21: Fresh Air Supply – Management System

PS 4.1.28.1	This KPI measures the level of maintenance and the level of usage of the Fresh Air Supply system to ensure a healthy operating environment of the Main Contractor’s staff.”

PS 4.1.28.2	a)	Fresh Air Supply pump switch off or not operation for longer than the allowable time

equates to twenty (20) points.

- Each heater element that is not functional, three (3) points to be added.

- Each obstruction found in the air vent; five (5) points added per obstruction.

- Stand-alone heaters found in toll booths or lane area; five (5) points added per heater.”

PS6	PENALTIES

PS6.2	Project Commencement:  Handover and Provisions of Documents

PS6.2.1.1

0.15% (point one five percent).

PS6.2.1.2

0,15% (point one five percent).

PS6.3	Operations Period – Financial Management

PS6.3.1

5% (five percent).

PS6.3.2

5% (five percent).

PS6.4 	Operations Period – Traffic Management

PS6.4.1

2% (two percent).

PS6.4.2

1% (one percent).

PS6.4.3

0.5% (point five percent).

PS6.4.4

1% (one percent)

PS6.5  	Equipment Functionality

PS6.5.1

0.5% (point five percent).

PS6.5.2

0.25% (point two five percent).

PS6.5.3

0.1% (point one percent).

PS6.5.4.1

0.5% (point five percent).

“PS6.5.4.2

Add clause PS6.5.4.2 with the following wording:

“Over and above 6,5,4,1 an additional penalty shall be levied for operation in Manual Mode for a period of more than 1 (one) hour for each event of non-compliance.”

0.5% (point five percent).

PS6.5.5

1% (one percent).

PS6.5.6

0.5% (point five percent).

PS6.5.7

1% (one percent).

PS6.5.8

1% (one percent).

PS6.5.9

1% (one percent).

PS6.5.10

3% (three percent).

All reference made in the Clauses 6.5.10.1 to 6.5.10.7 to “Clause 6.8.6” must be deleted and replace with “Clause 6.5.10.”

Add the following subclause:

“PS6.5.10.8

Delete this Clause and replace with the following:

“In the event that the Contractor fails to achieve full system compliance for the toll system upgrades/replacements by the deadline indicated in the Project Document (Volume 3), the Contractor shall pay a penalty each day in line with the table below, according to the compliance level achieved up to that point, until the Toll System has been certified by the Employer's Representative as fully compliant to the agreement. The penalty shall be capped at ten percent (10%) of the design build value per control centre at base date value.”

|  | No Milestones | Functional Spec | Hardware FAT | Software FAT | Functional Compliance | FC + Rollout | Provisional Compliance | Full System Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| * Penalty Value | *R5000 | *R5000 | *R5000 | *R5000 | *R4000 | *R2500 | *R1000 | *R0 |
| % of Full Penalty | 100% | 100% | 100% | 100% | 80% per item | 50% per item | 20% per item | 0% |

“PS6.5.10.9

Delete this clause and replace with the following:

“In the event that the Contractor does achieve full System Compliance on the Toll System, and is certified by the Employers Representative as compliant with the conditions of the agreement, prior to the deadline indicated in the Project Document (Volume 3),  the Contractor shall receive an incentive payment for design build completion prior to the deadline date according to the following table, depending on the month of completion:”

| Month (after Establish-ment Period) | Incentive |  |
| --- | --- | --- |
| 27 | R700,000 |  |
| 28 | R500,000 |  |
| 29 | R320,000 |  |
| 30 | R245,000 |  |
| 31 | R200,000 |  |
| 32 | R160,000 |  |
| 33 | R120,000 |  |
| 34 | R90,000 |  |
| 35 | R75,000 |  |

PS6.6 	Damage to assets

PS6.6.1

The reference made to “Clause 13.2.5” must be deleted and replaced with “Clause 14.3.5”.

0.15% (point one five percent)

PS6.7 	Asset Management – Asset Management System

PS6.7.1

The reference made to “Clause 14.4” must be deleted and replaced with “Clause 14.5”.

PS6.7.1.1

0.15% (point one five percent)

PS6.7.1.2

0.15% (point one five percent)

PS6.8 	Asset management – Electrical and Mechanical Maintenance

PS6.8.1

0.25% (point two five percent)

PS6.8.2

Replace 6.8.2 with the following:

“PS6.8.2 Lighting Mast Luminaires at any Toll Plaza shall be penalised as follows:”

PS6.8.2.1

Add clause PS6.8.2.1 with the following wording:

“In the event that between 10% (ten percent) and 20% (twenty percent) of the lighting mast luminaires are not functional at any Toll Plaza, the Contractor shall pay a penalty for each event of non-compliance”

0.25% (point two five percent)

PS6.8.2.2

Add clause PS6.8.2.2 with the following wording:

“In the event that more than 20% (twenty percent) of the lighting mast luminaires are not functional at any Toll Plaza, the Contractor shall pay a penalty for each event of non-compliance.”

0.5% (point five percent)

PS6.8.3

2,5% (two-point five percent)

PS6.8.4

0,25% (point two five percent)

PS6.9	General – Utilities, Services and Levies

PS6.9.1

Add heading for PS6.9.1 – “Electricity Interruption”

Replace the description of PS6.9.1 with the following:

“In the event of Eskom or Municipal reticulation problems, Account Management problems, Diesel Generator or UPS problems, where such problems lead to power interruptions to the Toll Plaza, the Main Contractor shall pay a penalty. Without prejudice to any other remedy which the Employer may have, either in this agreement, or in law, the Employer shall be entitled to call on the Performance Security”

0.2% (point two percent)

PS6.9.2

Add heading for PS6.9.2 – “Provision of Services”

Replace the description of PS6.9.2 with the following:

"In the event of non-compliance by the Contractor of its obligations pursuant to Clause 15.1 of the Standard Specifications for Operations and Maintenance for CTROM projects: General – Volume 2 Book 2(a), (excluding for the respect of electricity supply), the Main Contractor shall pay for each event of non-compliance)”

0.2% (point two percent)

PS6.9.3

Add heading for PS6.9.3 – “Toll Lane Backup Power”

Replace the description of PS6.9.3 with the following:

“In the event of an interruption in the UPS or emergency electricity supply to the Toll Lanes and related equipment (which excludes the Toll Plaza UPS and Generator), the Contractor shall pay the following penalty:”

PS6.9.3.1

Replace the description of PS6.9.3.1 with the following:”

“For interruptions where the emergency power to the Toll Lanes and related equipment fails within the last hour of the contractual requirement (already lasted 3 hours but did not make 4 hours as required).

0.5% (point five percent)

PS6.9.3.2

Replace the description of PS6.9.3.2 with the following:”

“For interruptions where the emergency power to the Toll Lanes and related equipment fails before the last hour of the contractual requirement (lasted less than 3 hours).”

1% (one percent)

PS6.10 	General Safety and Security

PS6.10.1 Penalties on Safety and SecurityAdd the following two sub-clauses:

PS6.10.1.1

Add the following to PS6.10.1.1:

“In the event that the Main Contractor does not comply with its obligations specified in Clause 15.4.1 of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), the Main Contractor shall pay a penalty for each event of non-compliance”

0.25% (point two five percent)

PS6.10.1.2

Add the following to PS6.10.1.2:

“In the event that the Main Contractor does not comply with its obligations specified in Clause 15.4.2 of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), the Main Contractor shall pay a penalty for each event of non-compliance”

0.25% (point two five percent)

PS6.10.2

0.25% (point two five percent)

PS6.11 	General – Quality Assurance

PS6.11.1

0.5% (point five percent)

Add the following new subclause:

“PS6.11.2

In the event that the Contractor fails to adhere to an instruction from the Employer’s Representative as depicted in Clause 3.3 of the Conditions of Contract, the Contractor shall pay a penalty for each event of non-compliance on a monthly basis until resolved.

0.25% (point two five percent)

PS6.13 	Toll Road Services – Road Incident Management Systems

PS6.13.1

0.1% (point one percent)

PS6.14 	Toll Road Services – Route Patrol Services

Delete PS6.14.1.1 and split into the following two clauses:

PS6.14.1.1 Frequency of Route Service Patrols

Add the following description to PS6.14.1.1.1:

“If the Main Contractor does not comply to the frequency of Route Service Patrols as specified in the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) then the Main Contractor shall pay a penalty for each day of non-compliance”.

0.5% (point five percent)

PS6.14.1.1.2

Add the following description to PS6.14.1.1.2:

“If the Main Contractor does not comply to the number of Patrol Vehicles as specified in the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a) then the Main Contractor shall pay a penalty for each day of non-compliance”.

0.25% (point two five percent)

PS6.14.1.2

Replace PS6.4.1.2 with the following:

“If the Main Contractor does not comply with activities listed in Clause 19.4 of the Standard Specifications for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), then the Main Contractor shall pay a penalty for each activity that have not been performed continuously.”

0.1% per activity (point one percent)

PS6.14.1.3

1.0% (one percent)

Replace PS6.14.1.4 with the heading “PS6.14.1.4 Route Patrol Fittings and Equipment” and add the following three sub-clauses:

PS6.14.1.4.1

Add the following to PS6.14.1.4.1:

“If the Main Contractor does not comply with the minimum required vehicle fittings in Clause 19.4 of the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), then the Main Contractor shall pay a penalty for each day of non-compliance

0.33% (point three percent)

PS6.14.1.4.2

Add the following to PS6.14.1.4.2:

“If the Main Contractor does not comply with the minimum required personnel equipment in Clause 19.4 of the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), then the Main Contractor shall pay a penalty for each day of non-compliance

0.33% (point three percent)

PS6.14.1.4.3

Add the following to PS6.14.1.4.3:

“If the Main Contractor does not comply with the minimum required vehicle equipment in Clause 19.4 of the Standard Specification for Operations and Maintenance of CTROM Projects: General (Volume 2 Book 2a), then the Main Contractor shall pay a penalty for each day of non-compliance

0.33% (point three percent)

PS6.15.1

0.15% (point one five percent)

C3.2.7	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATIONS FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: PAYMENT METHODOLOGY AND DESCRIPTION OF PAYMENT ITEMS (VOLUME 2 BOOK 7A)

The number of each Clause as a Particular Specification in this section consists of the Prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specifications for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a). The number of any new Clause which does not form part of any Clause in the Standard Specifications for Operations and Maintenance of CTROM Projects: Payment Methodology and Description of Payment Items (Volume 2 Book 7a), and which is included herein, is also prefixed by PS followed by a new number. Such new numbers follow on the last Clause used in the relevant section of the Standard Specifications for Operations and Maintenance of CTROM Projects: Payment Methodology and Description of Payment Items (Volume 2 Book 7a).

PART A – PAYMENT METHODOLOGY

PS3.4	Toll System payment items linked to Milestone Testing

Delete the “Table 1.1 milestone dependant items before lane expansion/reversible lane creation” and replace with the following table:

| MILESTONE DEPENDANT ITEMS BEFORE LANE EXPANSION / REVERSIBLE LANE CREATION |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Payment Item | Milestone Description vs Toll System Component | Functional Specification | Hardware Verification | Combined Software Factory Acceptance Test (SFAT) | Functional Compliance (FC) | ETC Functionality | Provisional Compliance (PC) | System Compliance |
| B-2001 | Provision of Toll System Software and Hardware: Back-Office System. | 10% | 20% | 15% | 15% | 10% | 15% | 15 % of the total of the Payment Items |
| B-2002 | Provision of Toll System Software and Hardware: Video Grabbing System (VGS) | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2003 | Provision of Toll System Software and Hardware: Queue Length Monitoring System (QLS) | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2004 | Provision of Toll System Software and Hardware: Data Concentrator System (DCS) | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2005 | Provision of Toll System Software and Hardware: Provision of Back Office Servers storage hardware and archive system complete | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2006 | Additional software and licences complete | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2008 | LAN and Network Connections. Provision and installation of network to all workstations, printers, etc. | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-2011 | Provisions for Toll System Software and Hardware: Interface with TCH. | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3001 | Provision of Toll System Software and Hardware: AVC System for Mixed Manual/ETC Lanes and/or Dedicated ETC Lanes. | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3002 | Provision of Toll System Software and Hardware: Mixed Manual /ETC Lanes for single direction Lanes | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3003 | Provision of Toll System Software and Hardware: Dedicated ETC Lanes | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3006 | Provision of Toll System Software and Hardware: Implementation of Queue Length Cameras. | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3007 | Provision of Toll System Software and Hardware: Implementation of VGS | 10% | 20% | 15% | 15% | 10% | 15% |  |
| B-3008 | Provision of Documentation | 10% | 20% | 15% | 15% | 10% | 15% |  |

PS4.5 	Provision in Opex for Income Cost

Delete the wording and insert the following:

"Void”

PS4.6 	Adjustment of Main Contractor Payments as a Result of Zero Traffic Conditions

PS4.6.3

80% (eighty percent)

PS5 	ADJUSTMENT OF CONTRACTOR’S MONTHLY PAYMENT TO PROVIDE FOR TOLL INCOME LOSS RESULTING FROM TRAFFIC VOLUMES LOSS

Delete the wording and insert the following:

“Void”

PS8.1	Monthly Interim Traffic Volume Statement

Delete the wording and insert the following:

“Void”

PS8.2	Monthly Interim Payment Certificate by Employer’s Representative

Delete the wording and replace with the following:

“8.2.1 	The Contractor shall prepare and submit monthly statements to the Employer showing in detail the amounts to which the Contractor considers himself to be entitled, together with supporting documents to substantiate the progress.

8.2.2	Each statement shall be submitted no later than 7 days before the due date for submission of the Employer’s statement to the Principal Employer, which due date shall be notified to the Contractor by the Employer.

8.2.3	The Employer shall pay the amount due to the Contractor within 10 days of receipt of such amount from the Principal Employer.”

PS8.3	Monthly Interim Payments by the Contractor

Delete the wording and insert the following:

“Void”

PS9.1	Final Traffic Volume Statement

Delete the wording and insert the following:

“Void”

PS9.2	Final Payment Certificate

Delete the wording and replace with the following:

“9.2.1	The Contractor shall prepare and submit a draft final statement to the Employer stating the sum which in the Contractor’s opinion is the Contract Price finally due, showing in detail the value of all work done in accordance with the Contract, and any further sums which the Contractor considers to be due to him, together with supporting documents.

9.2.2	The draft final statement shall be submitted no later than 30 days before the due date for submission of the Employer’s Final Statement to the Principal Employer, which due date shall be notified to the Contractor by the Employer.

9.2.3	If the Employer disagrees with or cannot verify any part of the Contractor’s draft final statement, the Contractor shall submit the further information that the Employer may reasonably require and shall make the changes in this draft statement that may be agreed between the Employer and the Contractor.  The Contractor shall then prepare and submit to the Employer a Final Statement as agreed no later than 7 days before the due date for submission of the Employer’s Final Statement, which due date shall be notified to the Contractor by the Employer.

9.2.4	The Employer shall pay the balance of the Contract Price finally due to the Contractor within 14 days after the Employer has received full payment from the Principal Employer.”

PART B – SECTION 1:  PREAMBLE TO THE SCHEDULE OF PAYMENTS

PS1.9	Contract Price Adjustment

PS1.9.8

This Clause to be modified to read as follows:

“Consumer Price Index for all expenditure groups:  Table B for Urban Areas (Base 2008 = 100) as published ...”

PART B – SECTION 2:  DESCRIPTION OF PAYMENT ITEMS – A SERIES:  OPERATION SERVICE

A - 1000 GENERAL CONTRACTOR’S OBLIGATIONS

Delete the following payment items:

A-1005: Compliance with Environmental Requirements

A-1006: Compliance with Social Responsibility Requirements

A-1010: Training of personnel and other training obligations

A-1012: Extra over costs for taking over of upgraded and new assets during contract period (if triggered)

Add the following New Payment Items:

| Item No | Description | Unit |
| --- | --- | --- |
| A-1014 | Updating Integrated Transport Information System (ITIS) Modules | Month |

In terms of this Item, the Contractor is to price for updating the various Integrated Transport Information System (ITIS) modules described in Clause C3.1.8 of the Project Document (Volume 3).

The tendered rate shall represent full compensation for the Contractor to provide person(s) to gather the relevant information and data in order to update the Employer various ITIS modules.

The unit of measurement shall be a month of the Operation Service period during which the Contractor has updated the Employer various ITIS modules.

The payment will be made to the Contractor for a month of the Operation Service period during which the Contractor has updated the Employer various ITIS Modules.

| Item No | Description | Unit |
| --- | --- | --- |
| A-1015 | Liaison with Service Providers | Month |

In terms of this item, the Contractor is to price for all liaison and interaction activities with the Service Provider for the Other Employer Contracts as listed in the table of Clause C3.1.5 of the Project Document (Volume 3).

The tendered rate shall include for all costs incurred by the Contractor including personnel and transport costs to liaise and to interact with the Service Provider(s).

The unit of measurement shall be a month (pro rata for part of the month) of the Operations Service Period during which the Contractor fulfils the liaison and interaction functions with the Service Provider(s).

The Payment will be made to the Contractor for a month (pro rata for part of the month) of the Operation Service period during which the Contractor has fulfilled the liaison and interaction functions with the Service Provider(s).

| Item No | Description | Unit |
| --- | --- | --- |
| A-1016 | Mentoring Targeted Enterprise | Month |
| A-1016a | Identify and train Targeted Enterprise | Month |
| A-1016b | Oversee of Targeted Enterprise | Month |

In terms of Item A-1016a, the Contractor is to price for identifying, establishing and implementing monitoring and training program, to develop a Targeted Enterprise (TE) to be able to Operate and Maintain a Toll Plaza on their own.

The tendered rate shall include all the costs incurred by the Contractor to:

- Identify and select a suitable Targeted Enterprise (TE)

- to develop and implement a mentoring and training program of all the Operations and Maintenance, including Design-Build Levels/ Sections of the Toll Plaza, such as but not limited to provision and installation of equipment, development of Operations and Maintenance Procedures/Manual, Contract Management, Financial Management, Risk Management, Health and Safety, Procurement Management (including tendering) and any other areas required to ensure the TE is ready for the Operation and Maintenance of a Toll Plaza.

The unit of measurement shall be a month (or pro-rata for part of the month) from when the Contactor implements the duties and the activities indicated in the approved program.

Payment will be made for the month (or pro rata for part of the month) for which the Contractor has provided services, executed tasks and/or achieved milestones indicated in the approved program.

The tendered rate shall include for all the costs incurred by the Contractor to manage and supervise the TE, including the management of perceived additional risks incurred during the period where the TE operates and maintains the selected toll plaza on their own.

The unit of measurement shall be a month (or pro rata of the month) from when the Contractor’s provides the Supervision and Management Services.

The payment will be made to the Contractor for a month (or pro rata for part of the month) for which the Contractor provide this management and supervision services.

| Item No | Description | Unit |
| --- | --- | --- |
| A-1017 | Extra over costs for the supervision of the nominated Subcontractor |  |
| A-1017a | Supervision of NSC during Service period (Section 1) | Month |
| A-1017b | Supervision of NSC during design Service period (Section 2) | Month |
| A-1017c | Supervision of NSC during design Service period (Section 3) | Month |
| A-1017d | Supervision of NSC during design Service period (Section 4) | Month |

In terms of these items a and b, the Contractor shall price for the Supervision of the Nominated Subcontractor, as instructed by the Employer for the phases during the Operation Service period.

The tendered rate shall represent full compensation to the Contractor for the Supervision of the Nominated Subcontractor specified in the Project Document (Volume 3). This tendered rate shall include for, but not limited to, additional staff to manage and supervise the Nominated Subcontractor responsibilities and Contractor Risks in terms of the Project Document (Volume 3) or any other perceived costs due to the Supervision of the Nominated Subcontractor for the duration of the Operation Service period.

The unit of measurement for items A-1017a and b, shall be a month of the Contract period during which the Contractor complied with requirements for the Supervision of the Nominated Subcontractor. The payment will be done to the Contractor for a month or pro-rata month of the Contract Period that Contractor supervised and managed the Nominated Subcontractor.

A - 2000 Provision of Staff and Labour

Delete the following payment items:

A-2001	Toll Collectors

A-2002	Senior Toll Collectors

A-2003	Seasonal Toll Collectors

A-2004	Shift Supervisors

A-2005	Plaza Managers

A-2006	Administrative Personnel

A-2007	Lane, Garden and Plaza Attendants

A-2008	Technical Staff

A-2009	Transport of Personnel

A-2010	Additional Toll Collectors due to Lane Expansion/ Reversible Lane Creation (If triggered)

A-2011	Extra over on Saving of Operational Costs if Dedicated ETC lanes are implemented (if triggered)

A-2012	Management of functional Customer Service, Including Account Registration, Tag Distribution, Account Top-Up as well as Revenue Management (if triggered)

A-2013a Customer Service Operations, Including Account registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Operations of 1 Customer Service Counter)

A-2013b Customer Service Operations, Including Account registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Extra Over for the Operation of an additional Customer Service Centre)

A-2014a Operation of different work-station configurations at Customer Service (CS) kiosks at locations remote from Control Centres, including for Account Registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Operation of a 1 Work-Station Configuration at a CS Kiosk)

A-2014b Operation of different work-station configurations at Customer Service (CS) kiosks at locations remote from Control Centres, including for Account Registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Extra Over, for Operation of an additional Work-Station at a CS Kiosk, if triggered)

A-2014c Operation of different work-station configurations at Customer Service (CS) kiosks at locations remote from Control Centres, including for Account Registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Extra Over, for Operation of 2 additional Work-Stations at a CS Kiosk, if triggered)

A-2014d Operation of different work-station configurations at Customer Service (CS) kiosks at locations remote from Control Centres, including for Account Registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Extra Over, for Operation of 3 additional Work-Stations at a CS Kiosk, if triggered)

A-2014e Operation of different work-station configurations at Customer Service (CS) kiosks at locations remote from Control Centres, including for Account Registration, Tag Distribution, Account Top-Up, Revenue Collection and Administration Services (if triggered) (Extra Over, for Operation of 4 additional Work-Stations at a CS Kiosk, if triggered)

A-2015a Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Fewer than 1 000 calls during a month)

A-2015b Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 1 000 and up to 2 000)

A-2015c Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 2 000 and up to 3 000)

A-2015d Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 3 000 and up to 4 000)

A-2015e Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 4 000 and up to 5 000)

A-2015f Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 5 000 and up to 6 000)

A-2015g Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 6 000 and up to 7 000)

A-2015h Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 7 000 and up to 8 000)

A-2015i Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 8 000 and up to 9 000)

A-2015j Call Handling Function: In-house handling of calls from the public during the Operation Period (If triggered) (Calls for a month between 9 000 and up to 10 000)

Add the following new payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| A-2016 | Contracts Engineer [Contractor’s Representative] | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2017 | Quality Control Officer | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2018 | Maintenance Manager | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2019 | System/ software support specialist | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2020 | Network and Security Specialist | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2021 | Plaza technician(s) | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

| Item No | Description | Unit |
| --- | --- | --- |
| A-2022 | SHEQ Officer | Month |

The Contractor shall comply with all employment requirements for labour as specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with the requirements specified in Clause 3.4 of the Project Document (Volume 3).

The tendered rate shall represent full compensation to the Contractor to comply with all employment requirements for that are specified in Clause 6 of the FIDIC General Conditions of Contract for Design, Build and Operate Projects – Volume 1 Book 1 (2008) and with requirements specified in Clause C3.4 of the Project Document (Volume 3) for the duration of the Contract.  The tendered rate shall include for all the costs incurred by the Contractor for the employment of above position to execute all obligations specified in the Contract.  It shall also include for all the cost related to leave, annual bonus, UIF, overtime/relief support, incentives, Provident Fund, skills levy, COID and any other company costs for this category of staff (as applicable).

The unit of measurement shall be a month of the Operation Service Period.

A-3000 Financial Fees and Risk

Delete the following payment items:

A-3001	Cash Deposit fees

A-3002	Provision for Cash Collecting Service

A-3003	Risk of Income loss/ gain in respect of Exempt User Passages

A-3004	Risk of Income loss/ gain in respect of Local and Regional Discounts

A-3005	Risk of Income Loss/Gain in respect of Frequent User Discounts IncomeA-3006	Risk of Income loss/ gain in respect of Run through Violations

A-3007	Risk of Income loss/ gain in respect of No Payment Passages

A-3008	Contractor Discounts Income Loss

A-4000 UTILITIES, SERVICES AND LEVIES

Delete the following payment items:

A-4001	Cost for the Supply of Electricity

A-4002	Cost for the Supply of Fuel

A-4003	Cost for the Supply of Portable Water

A-4004	Cost for the supply of Sewage and Waste Water Disposal

A-4005	Cost for the supply of Refuse Removal

A-4006	Data Communications Solution between the various Control Centres

A-4007	Data Backup Communications Solution between the Control Centres

A-4008	Data Communications Solution between Control Centre and the TCH

A-4009	Data Back-up Communications Solution between the Control Centre and the TCH

A-4010	Provision and maintenance of Telecommunications System – Other, including Telephone and Internet (Excluding QLS Telkom ISDN Line – see Prov Sums)

A-4011	Collection of Tags at TCH in Centurion and Delivery to Control Centres and Customer Service Kiosks remote from the Control Centres

A-5000 MAINTENANCE OF PROJECT ASSETS

Delete the following payment items:

A-5100	Facility Maintenance, including the following sub-items:

A-5101	Control Building and remote plaza buildings and structures

A-5102	Toll lanes and toll lane areas

A-5103	Provision for Painting of buildings and structures

A-5104	Corrosion protection of steel structures

A-5200	Electrical and Mechanical and Handyman Maintenance, including the following sub-items:

A-5201	Electrical maintenance: Control Building, Virtual Plazas and Toll Lane Areas.

A-5202	Mechanical Maintenance: Control Building, Virtual Plazas and Toll Lane Areas

A-5203	Handyman services: Control Building, Virtual Plazas and Toll Lane Areas

A-5204	Provision for E&M specialist maintenance: Generator Maintenance

A-5205	Provision for E&M specialist maintenance: UPS maintenance

A-5206	Provision for E&M specialist maintenance: Earthing tests

A-5207	Provision for E&M specialist maintenance: Road Lighting Maintenance (Including Group Lamp Replacement

A-5305	Toll System Maintenance and Support: Customer Service Work Stations and related equipment

A-5306	Provision and Maintenance of Toll System Helpdesk System

A-5307	Provision and Maintenance of Asset Management System (AMS)

A-6000 TOLL ROAD SERVICES

Delete the following payment items:

A-6001	Participation in Incident Management System Procedures and Structures

A-6002	Provision for the Supply, Implementation, Operation and Maintenance of the Route Patrol Services A-6003	Provision for Supply, Implementation, Operation and Maintenance of Route Customer Service Call Centre

A-7000 safety and security

Delete the following payment items:

A-7001	Procurement, Upgrade and Maintenance of Security Systems at Plaza Buildings, Lane Area and Remote Plazas (sensors, cameras etc.)

A-7002	Procurement, Upgrade and Maintenance of Security Systems in toll booths in mainline, ramp and remote plazas (sensors, cameras etc.)

A-7003	Support, installation and maintenance of Fire Suppression System in server room(s) and UPS room

A-10000 Provisional Sums

Delete the following payment items:

A-10001		Provision for the repair of Employer's Assets

A-10001a	Provisional Sum for the repair of Employer's Assets

A-10001b	Provision for overhead charges and profit in respect of aforementioned item

A-10002	Provision for the Repair of Electrical and Mechanical Assets

A-10002a	Provisional Sum for repair of Electrical and Mechanical Assets

A-10002b	Provision for overhead charges and profit in respect of aforementioned item

A-10004	Community Participation as described in project document (Volume 3) Book 1 (if triggered)

A-10004a	Community Participation as described in Project Document (Volume 3) Book 1 (If triggered)

A-10004b	Provision for overhead charges and profit in respect of aforementioned item

A-10005		Telecommunication services - Broadband service for remote access to QLS (Application, Installation, Rental and Usage)

A-10005a	Telecommunication Services – Broadband Service for Remote Access to QLS (Application, Installation, Rental and Usage

A-10005b	Provision for Overhead charges and profit in respect of aforementioned item

A-10006	Provision for ETC-related Marketing

A-10006a	Contractor’s execution of parts of Employer’s marketing plan through an expert communication company(ies)

A-10006b	Overhead charges and profit in respect of aforementioned item

A-10007		Provision for transportation and deposition of cash from the Customer Service Kiosks

A-10007a	Transportation and deposition of cash from the customer service kiosks

A-10007b	Overhead charges and profit

A-10008	Space Rental for Permanent and Temporary Customer Service Kiosks

A-10008c	Space Rental for Customer Service Kiosks

A-10008d	Overhead charges and profit in respect of aforementioned item

A-10009	Manual Lanes credit card transactions: Fees/Commissions related to banks for credit card transactions during the Operations Period

A-10009a	Fees and Commissions

A-10009b	Overhead charges and profit in respect of aforementioned item

A-10010	ETC Account Payments: Fees/commissions related to banks and other providers of payment means during the Operation Period

A-10010a	Fees and Commission

A-10010b	Overhead charges and profit in respect of aforementioned item

A-10011	Fees related to TCH services

A-10011a	Fees

A-10011b	Overhead charges and profit in respect of aforementioned item

PART B – SECTION 3:  DESCRIPTION OF PAYMENT ITEMS – B SERIES:  DESIGN-BUILD

B-1000 CONTRACTOR’S ESTABLISHMENT

Replace B-1001b: Time-related obligations for Design-Build and Operations, with the following payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| B-1001b | Contractors General Obligations and Establishment at Contract Commencement date for the Design-Build Section 1 period - Time Related obligations for Design Build and Operations | Week |
| B-1001c | Contractors General Obligations and Establishment at Contract Commencement date for the Design-Build Section 2 & 3 period - Time Related obligations for Design Build and Operations | Month |
| B-1001d | Contractors General Obligations and Establishment at Contract Commencement date for the Design-Build Section 4 - Time Related obligations for Design Build and Operations (if triggered) | Month |
| B-1001e | Contractors General Obligations and Establishment at Contract Commencement date for the Design-Build Section 5 - Time Related obligations for Design Build and Operations (if triggered) | Month |

Replace “sub-item b)” in the payment item description with “sub-item b) to e)”.

Add the following paragraph at the end of the existing payment item description:

"In addition to the above, the weekly and monthly time related payments will be made monthly once the Principal Employer has triggered the relevant Design-Build Section and the Contractor is required to execute the Works in that Section. Monthly time related payments will only be made for the specified duration of the Section.

Add the following payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| B-1003 | Establishment upgrade |  |
| B-1003a | Toll System - Plaza/ Control Centre level: Conventional Plazas/ Hybrid Plaza, and conventional part of A: BOS, VGS, QLS, DCS and network | Lump Sum |
| B-1003b | Toll System – Lane Area Related: AVC, Lane, Tunnel, Booth and Canopy | Lump Sum |
| B-1003c | Toll System – Lane Area Related: VGS, QLS, QL1 and Network | Lump Sum |
| B-1003d | Toll System – Lane Area Related: Lane and AVC UPS and lightning protection | Lump Sum |
| B-1003e | Toll System – Plaza/ Control Centre level: Conventional Plazas/ Hybrid Plaza, and conventional part of A: TCH Payment Gateway at site | Lump Sum |

In terms of these items the Contractor shall price for the Establishment upgrades required during Site establishment and Design Build Optimisation defined under in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a Clause V2B4a 2.7.3.2) and Volume 3 book 1.

The Lump Sum tendered for under B-1003a item, is for the  replacement of the following equipment:

- BOS server and storage

- VGS Server/DVR and storage

- DCS server

- Control building printers

- All workstations

- Network equipment

The Lump Sum tendered for under B-1003b item, is for the  replacement of the following equipment:

- Lane and AVC controller equipment,

- Sensors and loops

- Receipt printers

- VDU, TCT, SCR

The Lump Sum tendered for under B-1003c item, is for the  replacement of the following equipment:

- Cameras

- Network equipment

The Lump Sum tendered for under B-1003d item, is for the  the replacement of the following equipment:

- Lane, AVC, QLS and QL1 UPS units

- Lane, AVC, QLS and QL1 UPS batteries

The Lump Sum tendered shall include for full compensation for the design, supply, installation, testing, including but not limited to, hardware, cabling, installation, Contractor’s internal testing and earthing.

The Lump Sum tendered for under B-1003e item, is for the  implementation of a TCH Payment Gateway at the Operation centre in the computer room at the Nyl (or Kranskop) Toll plaza, to replace the offsite Payment Gateway currently housed offsite. The TCH Payment Gateway implementation shall include, interalia;

- Separate PGW server to be installed in the server rack with the BOS equipment,

- Communication interface to interface with the existing or new primary and secondary TCH interface networks/data links.

- Provision of firewalls for the primary and secondary TCH data connection

- TA certification testing with the TCH contractor, related to the certification of the new TCH payment gateway.

The Lump Sum tendered shall include for full compensation for the design, supply, installation, testing, TCH TA testing, including but not limited to, hardware, cabling, installation, Contractor’s internal testing and earthing.

| Item No | Description | Unit |
| --- | --- | --- |
| B-1004 | System Obsolescence, Routine Maintenance, Performance Related, Software related upgrades and hand-back requirements |  |
| B-1004a | Toll System - Plaza/ Control Centre level: Conventional Plazas/ Hybrid Plaza, and conventional part of A: BOS, VGS, QLS, DCS and network | Lump Sum |
| B-1004b | Toll System – Lane Area Related: AVC, Lane, Tunnel, Booth and Canopy | Lump Sum |
| B-1004c | Toll System – Lane Area Related: VGS, QLS, QL1 and Network | Lump Sum |
| B-1004d | Toll System – Lane Area Related: Lane and AVC UPS and lightning protection | Lump Sum |
| B-1004e | Toll System – Workshop Related: Critical spares, Test or standby rig, ERS, documentation, drawings, licenses, codes, passwords and other hand-over requirements and ERS/Asset update | Lump Sum |

In terms of these items the Contractor shall price for the Obsolescence, Routine Maintenance, Performance Related upgrades, and hand-back requirements defined in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a Clause 2.7.3.3 – 6 and 2.8), Operations (Volume 2 Book 2a Clause14.4.4.8) and Volume 3 book 1.

The Lump Sum tendered for under B-1004a item, is for theupgrade of the following equipment:

- BOS server and storage

- VGS Server/DVR and storage

- DCS server

- Control building printers

- All workstations

- Network equipment

- Operating system and application Software

The Lump Sum tendered for under B-1004b item, is for the  upgrade of the following equipment:

- Lane and AVC controller equipment,

- Sensors and loops

- Receipt printers

- VDU, TCT, SCR

- Operating system and application Software

The Lump Sum tendered for under B-1004c item, is for the  upgrade of the following equipment:

- Cameras

- Network equipment

- Operating system and application Software

The Lump Sum tendered for under B-1004d item, is for the  upgrade of the following equipment:

- Lane, AVC, QLS and QL1 UPS units

- Lane, AVC, QLS and QL1 UPS batteries

- Operating system and application Software

The Lump Sum tendered for under B-1004e item, is for the  the upgrade, replenishment and replacement of the following equipment:

- Replenish all Critical spares to ensure that the levels meet or exceed the specified levels at the end of contract

- Upgrade and refurbish the Test or standby rig to ensure that it is fully operational at the end of contract

- Conduct site survey and stock take and update the Equipment Record and Asset Management System to accurately reflect the levels, location and status of spares and equipment.

- Ensure that all documentation, drawings, manuals, keys, codes, licences, access credentials and passwords are documented, up to date and packaged for handover to the next operator.

The Lump Sum tendered shall include for full compensation for the design, supply, installation, testing, including but not limited to, hardware, software, installation, Contractor’s internal testing.

B-2000 Toll System - Plaza/ Control Centre level: Conventional Plazas/ Hybrid Plaza, and conventional part of A

Delete the current payment item B-2006 and replace with the following:

| Item No | Description | Unit |
| --- | --- | --- |
| B-2006 | Additional software and licences complete |  |
| B-2006a | Additional software and licenses complete not listed in item B-2006b | Lump Sum |

The Lump Sum tendered for under this item, is for provision of additional software and licenses complete that are not listed in payment item B2006b, to meet the requirements of Standard Specifications for Operations and Maintenance of CTROM Projects:  Toll Systems (Volume 2 Book 4a) in order for the Contractor to fulfil his obligation under the contract.

The Lump Sum tendered shall include for full compensation for the delivery of the complete software supply, installation commissioning and/or upgrade including any 3rd party software, database software, etc. and the submission of applicable licenses.  The Contractor shall provide a list and detail of additional software implemented.

Payment shall be made to the Contractor in accordance and subject to successfully delivery, implementation and commissioning by the Contractor and followed by successfully testing and approval by the Employer’s Representative.

| Item No | Description | Unit |
| --- | --- | --- |
| B2006b | Additional software and licenses for Microsoft Product/Oracle RDBMS and SAP (if triggered) | Lump Sum |

The Lump Sum tendered for under this item, is for the provision of additional software and licenses complete, for all Microsoft Products (SQL, Office, Exchange, SharePoint, etc.), Oracle RDBMS and SAP that may need meet the requirements of the Standard Specifications for Operations and Maintenance of CTROM Projects:  Toll System (Volume 2 Book 4a) in order for the Contractor to fulfil his obligations under the contract.

The Lump Sum tendered shall include for full compensation for the delivery of the complete software supply, installation commissioning and/or upgrade including any 3rd party software, database software, etc. and the submission of applicable licenses.  The Contractor shall provide a list and detail of additional software implemented.

Should the Principal Employer choose not to provide the above-mentioned software and licenses themselves and trigger this item, then payment will be made in accordance and subject to successfully delivery, implementation and commissioning by the Contractor and followed by successfully testing and approval by the Employer’s Representative.”.

Add the following payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| B-2011 | Provision for Toll System software and hardware: Interface with TCH | Lump Sum |

The Lump Sum tendered for under this item, is for the provision to interface the Toll Plaza(s) Back Office and / or toll lanes to the National Transaction Cleaning House (TCH) in terms of the Principal Employer Requirements.

The Lump Sum tendered shall include for full compensation for the development and delivery of the completed software in order to interface the plaza(s) Back Office and/or toll lanes with the TCH.  It shall include for all software supply installation, commissioning and/or upgrade of any 3rd party database software, etc. and the submission of applicable licenses.

The Lump Sum tendered under the above item shall include for full compensation for the supply, installation, testing and commission of server(s), workstation(s) and printer(s), including but not limited to hardware, cabling, installation, contractors internal and milestone testing and earth.

Payment shall be made in accordance and subjected to successful completion of the milestone tests during the design-built period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-2012 | Provision for a full set of spares | Lump Sum |

The Lump Sum tendered for under this item, is for the provision of a full sets of spares in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 2a) as amended in Volume 3 Book 1.

The Lump Sum tendered shall include for full compensation for the supply, delivery, capturing/updating of the relevant stock control and asset management system.

| Item No | Description | Unit |
| --- | --- | --- |
| B-2013 | VGS, QLS and ANPR pilot (if Triggeered) | Lump Sum |

The Lump Sum tendered for under this item, is for the Nyl Mainline North Pilot testing of enhanced Video Grabbing System (VGS) Software, Queue Length System (QLS) Software, TCC software, incident control software and server level ANPR software that support  automatic VLN verification and VGS audit functionality,  and include server hardware, network equipment, cameras and dedicated ANPR cameras in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a) and Volume 3 book 1.

The Lump Sum tendered shall include full compensation for the delivery of the complete pilot software of the QLS and VGS System. It shall include for all software supply, installation, commissioning and/or upgrade including any 3rd party software, database software, etc and the submission of applicable licences.

The Lump Sum tendered shall provide for a pilot for implementation of the VGS, QLS System, namely an initial “stand-alone” system before the upgrading of the Toll Lanes. The pilot configuration will operate in parallel with the existing VGS and QLS and will include fully integrated VGS and QLS implementation for the Nyl Mainline North lanes.

The pilot VGS/QLS system shall be used to verify that the implementation meets the VGS, QLS, ANPR, VGS audit, Lane level ANPR accuracy, ANPR accuracy, AVC count accuracy verification, KPI reporting, health monitoring, incident control integration, automatic VLN verification and configuration control. The Contractor shall be responsible for the ANPR camera and ANPR software configuration and training to meet the specified ANPR accuracies for registered and unregistered users. The Contractor shall also implement real-time ANPR at lane/TCC level, that include the ANPR camera triggering and transaction framing.

The Lump Sum tendered shall include for full compensation for the design, development, optimization, supply, installation, testing, pilot operations and commissioning of the cameras, network equipment, server/s and VGS clerk workstation, including but not limited to, hardware, cabling, installation, Contractor’s internal and milestone testing and earthing. The server/s will be located at the Nyl Toll Plaza Control Centre.

| Item No | Description | Unit |
| --- | --- | --- |
| B-2014a | 18% of the Total fee for full access to the Toll system source code, and perpetual license to use at all SANRAL current and future plazas (if triggered). | Lump Sum |
| B-2014b | Delivery of Toll System source code, Toll System build, configuration, and deployment documentation (if triggered). | Lump Sum |
| B-2014c | Delivery of Toll System development and test platform and test environment (if triggered). | Lump Sum |
| B-2014d | Toll System source code verification and site configuration, deployment, commissioning, and version control set-up (if triggered). | Lump Sum |
| B-2014e | Toll System site recovery pack compilation, verification and delivery (if triggered). | Lump Sum |
| B-2014f | SANRAL Toll System pilot deployment and testing (if triggered). | Lump Sum |
| B-2014g | SANRAL Toll System deployment, replacing another Toll System (if triggered). | Lump Sum |

The Lump Sum (B-2014a, b, c, d and e) tendered for under these items, are for the purchase of full access to Toll System source code, the delivery, and the verification thereof.

Items B-2014g and f applies if the Contractor’s Toll system is selected as the national SANRAL Toll System on another route. Item B-2014f covers the Contractor’s costs to pilot deploy and test the SANRAL Toll system at the CapricornToll plaza (or any other mainline as agreed and approved by the ER). Item B-2014g covers the Contractor’s costs to deploy the SANRAL Toll System to all the N1N Toll plazas in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a) and Volume 3 book 1.

The Lump Sum tendered under item B-2014a shall give SANRAL full access to the supplied version of the Toll system source code, and perpetual license to use at all SANRAL current and future plazas. The access shall allow SANRAL the freedom to use other service providers to modify and add to the Toll System. The Contractor remains the owner of the Toll System Intellectual rights and is free to develop and market the Toll System. The Tenderer shall allocate 18% of the total Source Code rate, to the N1N Toll plazas, and allocate 30%, 45%, 15 and 10% proportionally to the Kranskop, Nyl, Capricorn and Baobab plazas respectively. The total Source Code rate or fee must be multiplied with the 18% route allocation for this route and with the respective control centre allocation.

The Lump Sum tendered under item B-2014b shall include full compensation to the Contractor for the delivery of the complete toll system software source code, manuals, utilities, codes, scripts, database schemas, etc., required to allow SANRAL or its appointed agent to successfully build the Toll System.

The Lump Sum tendered under item B-2014c shall full compensation the Contractor for the delivery of the complete Toll System development and test environment, to be delivered to the appropriate site in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a) and Volume 3 book 1. The Test environment shall be configured to allow for the update, compilation, and testing of the complete Toll System, inclusive of the AVC, TCC, DCS, BOS, VGS, QLS, ANPR, QL1, TCH Payment gateway and BOS interfaces.

The Lump Sum tendered under item B-2014d shall include full compensation to the Contractor for the full verification of the Toll System source code and manuals at factory and site level. This shall include building the Toll system from the source code delivered by the Contractor, by the ER or agent appointed by the Employer, based on the manuals, procedures and documentation provided by the Contractor.

The Lump Sum tendered under item B-2014e shall full compensation the Contractor for the delivery of a site recovery pack for each site and the testing and verification thereof. This shall include the configuration and testing of the Toll System at the Test site, which was built from the source code delivered by the Contractor, by the ER or agent appointed by the Employer, based on the manuals provided by the Contractor.

The Lump Sum tendered under item B-2014f, shall include full compensation for the pilot deployment, testing, trail parallel operations and trail operations, commissioning, and test on completion, of the Toll System at the Capricorn Toll plaza.  The Contractor shall deploy the necessary BOS hardware and equipment to allow for the parallel implementation of the new system, without impacting on the performance and operations of the existing toll system. The Contractor shall design and implement data interface modules to the existing lanes and BOS system to allow for the transfer of data between the existing and new Toll System to allow for the implementation of parallel test processes and reporting. This shall include interfacing to the existing cameras and digital recorders and sensors. The Contractor shall provide training to the Operator and provide resources during the pilot operations to minimize the impact of the pilot testing on the Operator and plaza operations. The parallel pilot tests shall include full Functional Compliance tests and tests results, that include the month end process.

The Lump Sum tendered under item B-2014g, shall include full compensation for the deployment, testing, trail operations, commissioning, and test on completion, of the Toll System at the N1N Toll plazas Toll plazas.  The Contractor shall deploy the SANRAL Toll System, approved during the Testing on the existing hardware at the remainder of the route. The Contractor shall procure and implement the necessary additional processes, software, hardware, and equipment to deploy and test the new system, without impacting on the performance and operations. The Contractor shall provide training to the Operator and provide resources during the pilot operations to minimize the impact of the pilot testing on the Operator and plaza operations.

| Item No | Description | Unit |
| --- | --- | --- |
| B-2015 | Workshop: Lane test or standby rigs | Lump Sum |

The Lump Sum tendered for under this item, is for the provision of Workshop Lane test or standby rigs in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 2a) as amended in Volume 3 Book 1.

The Lump Sum tendered shall include for full compensation for the supply, delivery and installation of Lane standby rigs at each mainline Toll Plaza.

B3000 Toll System – Lane Area Related

Add the following payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| B-3009 | Provision of Toll System Software and Hardware: AVC Systems for Mixed/Manual/ETC lanes and or Dedicated ETC lanes (if triggered) | Lump Sum |

The description of the Payment Item B-3001 of the Standard Specification for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a) also applies to this new item.

The payment shall be made to the Contractor after the Employer has triggered the installation of this equipment and subject to the completion of the milestone during this section of the Design Build Period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-3010 | Provision of Toll System Software and Hardware: Ramp/Mainline Swapping | Lump Sum |

The Lump Sum tendered for under this item, to implement Ramp/Mainline Swapping shall be in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems: (Volume 2 Book 4a).

The Lump Sum shall include full compensation for the delivery of the complete supply Ramp/Mainline Swapping functionality, installation, commissioning and/or upgrade including any 3rd party software, database software, etc and the submission of applicable licences.

This Lump Sum as tendered shall further include for all 3rd party software and licences, contractors internal and milestone testing etc.

Payment shall be made in accordance and subject to successful completion of the milestone tests during the Design-Build Period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-3011 | Provision of Toll System Software and Hardware: Mixed Manual/ETC lanes for single direction (if triggered) | Lump Sum |

The description of the Payment Item B-3002 of the Standard Specification for Operations and Maintenance of CTROM Projects: Payment Methodology and Description of Payment Items (Volume 2 Book 7a) also applies to this new Item.

The payment shall be made to the Contractor after the Employer has triggered the installation of this equipment and subject to the completion of the milestone during this section of the Design Build Period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-3012 | Provision of Toll System Software and Hardware: For lane which can switch between Dedicated ETC mode and Mixed Manual/ETC lane Mode. | Lump Sum |

The description of the Payment Item B-3001 of the Standard Specification for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a) also applies to this new item.

The Lump Sum tendered shall include for full compensation for the development and delivery of the completed hardware and software in order to provide a lane or lanes that can switch between operation in Dedicated ETC mode, and Mixed Manual/ETC lane mode. It shall include for all hardware and software supply, installation, commissioning and/or upgrade of any 3rd party database software, etc. and the submission of applicable licenses.

Payment shall be made in accordance and subjected to successful completion of the milestone tests during the design-built period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-3013 | Provision of Toll System and VGS Software and Hardware: Automatic Number Plate Recognition (ANPR) (if triggered) | Lump Sum |

The description of the Payment Item B-2002 of the Standard Specification for Operations and Maintenance of CTROM Projects:  Payment Methodology and Description of Payment Items (Volume 2 Book 7a) also applies to this new item.  This item provides for the roll-out of the VGS and lane ANPR system, proven at Nyl Mainline North plaza (B-2013), to the rest of the lanes and plazas on the N1N.

The Lump Sum tendered shall include for full compensation for the development and delivery of the completed hardware and software in order to provide the lane, incident control, BOS, VGS and TCH interface automatic VLN verification and management and image and data transmission. This item shall include servers, storage, network equipment, application software, ANPR server software, lane level dedicated onboard ANPR cameras and VGS clerk workstations.

Payment shall be made in accordance and subjected to successful completion of the Nyl Mainline North pilot and milestone tests during the design-built period.

| Item No | Description | Unit |
| --- | --- | --- |
| B-3014 | Provision of Toll System and VGS Software and Hardware: EMVCO compatible card readers (if triggered) | Lump Sum |

The Lump Sum tendered for under this item, is for the provision of two EMVCO compatible external contactless card reader hardware and software in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a).

The Lump Sum tendered shall include full compensation for the delivery of the complete EMVCO reader integration into the Toll Collector Compute including software supply, installation, commissioning and/or upgrade including any 3rd party software, database software, etc and the submission of applicable licences.

The Lump Sum tendered under the above item shall include for full compensation for the complete equipment/hardware supply, installation, commissioning and/or upgrade, including but not limited to the contactless reader unit and interfacing to the Lane controller; All fixing mechanisms (e.g. clamps, arms, brackets, poles); and any other equipment not included in items above required for the successful Contactless card reader functionality and operations.

The Lump Sum tendered shall further include for all 3rd party software and licences, contractors internal and milestone testing etc.

Payment shall be made in accordance and subject to successful completion of the milestone tests during the Design-Build Period.

B4000 ELECTRICAL AND MECHANICAL SYSTEMS

Delete the following payment items:

B-4001	 Uninterruptible Power Supply (UPS) unitsB-4002	Electrical: Supply and Installation

B-4003	Air-conditioning and Ventilation

B5000 MISCELLANEOUS: OTHER PAYMENT ITEMS

Delete the following payment items:

B-5001	Access Control System Complete

B-5002	Intercom System Complete

B-5003	Call Centre System

B6000 – Provisional Sums payments

Delete the following payment items:

B-6001		Provision for the Installation and Upgrade of Employer's

B-6001a		Provision for the installation and upgrade of Employer's Assets

B-6001b		Provision for Overhead charges and profit in respect of aforementioned item

B-6002		Provision for the Installation and Upgrade of Electrical and Mechanical Assets

B-6002a		 Provision for the installation and upgrade of Electrical and Mechanical Assets

B-6002b		Provision for Overhead charges and profit in respect of aforementioned item

B-6004		Customer Service Kiosks at locations remote from Toll Plazas - Planning, Design, Supply and Installation

B-6004a		Allowance for Customer Service Kiosk Planning and Design

B-6004b		Overhead charges and profit iro Planning and Design

B-6004c		Procurement of Kiosk Supply and Installation

B-6004d		Overhead charges and profit iro Supply and Installation

B-6005		Customer Service Kiosks at Toll Plazas – Planning, Design, Supply and Installation of Shop-fittings

B-6005a		Allowance for Toll Plaza Customer Service Kiosks - Planning and Design n

B-6005b		Overhead charges and profit iro Planning and Design

B-6005c		Supply and Installation of Customer Service Kiosks Shop-fittings

B-6005d		Overhead charges and profit iro Supply and Installation

B-6006		Information Points and Desks at Locations Remote from Toll Plazas

B-6006a		Allowance for Information Points and Desks and associated Furniture – Planning and Design

B-6006b	Overhead charges and profit in respect of Planning and Design

B-6006c		Supply and Installation of Information Points and Desks and the associated Furniture

B-6006d		Overhead charges and profit in respect of Supply and Installation

B-6007		Fire detection and suppression systems complete per Control Centre

B-6007a		Fire Detection and Suppression Systems

B-6007b		Overhead charges and profit in respect of Planning and Design

B-6008		Provision of PABX telephone system per Control Centre

B-6008a		PABX telephone system

B-6008b		Overhead charges and profit in respect of afore-mentioned item

B-6012a	Provision for the Toll System Development to interface with the TCH

B-6012b	Provision for the Toll System Development to interface with the TCH - Overhead charges and Profit in respect of B-6012a

Replace A-5301: Toll System Software support, with the following payment item:

| Item No | Description | Unit |
| --- | --- | --- |
| A-5301 | Toll System Software support | Month |

In terms of this item, the Contractor shall comply with the requirements related to the Toll System Software support as specified in Volume 2 Book 2a Standard Specifications for Operations and Maintenance of CTROM Projects: General. The tendered rate shall include for, amongst others for the maintenance and support of:

- Back-Office System,

- AVC Systems,

- Toll Lane Systems and peripheral equipment,

- DCS System,

- Communications Systems,

- All workstations.

The tendered rate per month shall include full compensation for the monthly software-related support of the Toll Systems. This includes for the software support of all the BOS and Lane related systems at the Control Centre and remote locations including the communications systems. The support shall include all the scheduled and routine support activities, ad-hoc support, emergency support as well as providing all labour and tools.

The support of the Toll System is to ensure that the equipment and systems will function normally and as intended to ensure that the required performance of the systems is achieved.

The tendered rate per month shall include for the monthly obsolescence, Routine Maintenance and performance related upgrades defined in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a clause 2.7.3.3 – 6 and 2.8), Operations (Volume 2 Book 2a) and Volume 3 Book 1. This shall include, inter alia:

- Maintaining the Operating System, database and any other required software to versions that are actively supported by vendors and to lower the risk of security vulnerabilities,

- Maintaining a software register as required in Volume 2 Book 2a

- Refurbishment and upgrade of the test or standby rig with the applicable software to ensure that it is fully operational,

- Conducting site audits and stock take exercises to ensure the Equipment Record and Asset Management System accurately reflect the levels, location and status of the software,

- Ensure that all documentation, drawings, manuals, keys, codes, licences, access credentials and passwords are documented, up to date and available for verification,

- Maintaining the TCH Payment Gateway, TCH interface and any other required software.

- 1st line maintenance of the TCH software deployed on the route,

The unit of measurement shall be a month for the Toll System Software support.

Payment shall be made to the Contractor on a monthly basis based on the tendered rates in the Schedule of Payments/Cost Matrix for the duration of the Operation Service Period.

Replace A-5302: Toll System Equipment and Hardware Maintenance, with the following payment item:

| Item No | Description | Unit |
| --- | --- | --- |
| A-5302 | Toll System Equipment and Hardware Maintenance | Month |

In terms of this item, the Contractor shall comply with the requirements related to the Toll System Equipment and Hardware Support as specified in Volume 2 Book 2a Standard Specifications for Operations and Maintenance of CTROM Projects: General. The tendered rate shall include for, amongst others for the hardware maintenance of Back Office and Lane related equipment that consist (amongst others) of:

- Back-Office System,

- AVC Systems,

- Toll Lane Systems and peripheral equipment,

- DCS System,

- Communications Systems,

- All workstations.

The tendered rate per month shall include full compensation for the monthly hardware- related maintenance of the systems, such as the servers, AVC’s, Lane controllers etc. This includes for the maintenance of all equipment and systems at the Control Centre and toll lane areas. The maintenance shall include all the scheduled and routine maintenance, ad-hoc maintenance, break-down maintenance, emergency repairs inclusive of providing spares and/or swop-out equipment as well as providing all labour and tools.

This maintenance is to ensure that the equipment and systems will function normally and as intended to ensure that the required performance of the systems is achieved.

The tendered rate per month shall include for the monthly obsolescence, Routine Maintenance and performance related upgrades defined in terms of the Standard Specifications for Operations and

Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a Clause 2.7.3.3 – 6 and 2.8), Operations (Volume 2 Book 2a Clause14.4.4.8) and Volume 3 Book 1. This shall include, inter alia:

- Maintaining of the spare part levels and the replenishment of all spares utilised to ensure that the required service levels are met (the initial provision of a set of spares is provided for in B-2012),

- Refurbishment and upgrade of the test or standby rig to ensure that it is fully operational (the initial provision of a test or standby rig is provided for in B-2015),

- Conducting site audits and stock take exercises to ensure the Equipment Record and Asset Management System accurately reflect the levels, location and status of spares and equipment,

- Ensure that all documentation, drawings, manuals, keys, codes, licences, access credentials and passwords are documented, up to date and available for verification

- Maintaining the TCH Payment Gateway, TCH interface and any other required hardware on the route,

- 1st line maintenance of the TCH hardware deployed on the route.

The unit of measurement shall be a month for the maintenance and support.

Payment shall be made to the Contractor on a monthly basis based on the tendered rate in the Schedule of Payments/Cost Matrix for the duration of the Operation Service Period

Replace A-5308: Hand-Back of Toll System, with the following payment item:

| Item No. | Description | Unit |
| --- | --- | --- |
| A-5308 | Hand-Back of assets and systems |  |
| A-5308a | Hand-Back of Toll System | Lump Sum |
| A-5308b | Hand-Back of assets and systems other than the Toll System | Lump Sum |

The Lump Sum tendered for under the item in A-5308a is for the Hand-Back of the Toll System in terms of Volume 2 Book 2a Standard Specifications for Operations and Maintenance of CTROM Projects:

The Lump Sum tendered for under the item in A-5308b is for the Hand-Back of assets and systems other than the Toll System, in terms of Volume 2 Book 2a Standard Specifications for Operations and Maintenance of CTROM Projects: General.

The Lump Sum tendered shall provide full compensation for the hand-back of the assets after Contract termination to ensure that all the assets and system/(s) are fully functional, that all outstanding maintenance and support-related actions are complete and that all defects are corrected.

The Lump Sum shall further provide compensation for a full complement of spares, test or standby rigs, tools and updated Equipment Record and Asset Management Systems to be handed over to the Employer to facilitate the on-going maintenance and support of the assets and systems. The Contractor shall ensure that all documentation, drawings, manuals, keys, codes, licences, access credentials and passwords are documented, up to date and packaged for handover to the next operator.

Payment shall be made to the Contractor after the successful hand-back of the assets and systems and hand-over of the spares and tools as approved by the Employer..

Add the following payment item:

| Item No | Description | Unit |
| --- | --- | --- |
| A-5309 | Hardware and software maintenance and support for if triggered payment items (if triggered): |  |
| A-5309a | Maintenance and support for item B-2009 (Detection System for vehicles of Special Interest (VOSI)) and item B-2010 (Detection system for vehicles Exceeding the Legal Vehicle Height (if triggered): | Month |
| A-5309b | Maintenance and support for item B-2014c (Delivery of Toll System development and test platform and test environment) (if triggered) | Month |
| A-5309c | Maintenance and support for item B-3009 (Provision of Toll System Software and Hardware: AVC Systems for Mixed/Manual/ETC lanes and or Dedicated ETC lanes (if triggered) | Month |
| A-5309d | Maintenance and support for item B-3011 (Provision of Toll System Software and Hardware: Mixed Manual/ETC lanes for single direction) (if triggered) | Month |
| A-5309e | Maintenance and support for item B-3013 (Provision of Toll System and VGS Software and Hardware: Automatic Number Plate Recognition (ANPR) (if triggered) | Month |
| A-5309f | Maintenance and support for item B-3014 (Provision of Toll System and VGS Software and Hardware: EMVCO compatible card reader system) (if triggered) | Month |

In terms of these items, the Contractor shall comply with the requirements related to the Toll System Software support and hardware maintenance as specified in Volume 2 Book 2a Standard Specifications for Operations and Maintenance of CTROM Projects: General. The tendered rate shall include for all maintenance and support of these if triggered items.

The tendered rate per month shall include for the monthly obsolescence, Routine Maintenance and performance related upgrades defined in terms of the Standard Specifications for Operations and Maintenance of CTROM Projects: Toll Systems (Volume 2 Book 4a Clause 2.7.3.3 – 6 and 2.8), Operations (Volume 2 Book 2a Clause14.4.4.8) and Volume 3 Book 1. This shall include, inter alia:

- Maintaining the Operating Systems, database and any other required software to versions that are actively supported by vendors and to lower the risk of security vulnerabilities, if applicable,

- Maintaining a software register as required in Volume 2 Book 2a,

- Maintaining of the spare part levels and the replenishment of all spares utilised to ensure that the required service levels are met (the initial provision of a set of spares is provided for in B-2012),

- Refurbishment and upgrade of the test or standby rig to ensure that it is fully operational (the initial provision of a test or standby rig is provided for in B-2015),

- Conducting site audits and stock take exercises to ensure the Equipment Record and Asset Management System accurately reflect the levels, location and status of spares and equipment,

- Ensure that all documentation, drawings, manuals, keys, codes, licences, access credentials and passwords are documented, up to date and available for verification, and

- Maintaining all the hardware.

The unit of measurement shall be a month for the maintenance and support.

Payment shall be made to the Contractor on a monthly basis based on the tendered rate in the Schedule of Payments/Cost Matrix once the item has been triggered and commissioned.

Add the following new payment items:

| Item No | Description | Unit |
| --- | --- | --- |
| B-6009 | Supply of EMVCO compliant hardware and software |  |
| B-6009a | Provision for an EMVCO card reader system, over and above B-3014 | Prov Sum |
| B-6009b | Overhead charges and profit in respect of above-mentioned item | Percentage (%) |

The Provisional Sum provided under sub item a) will cover any additional costs over and above item B-3014 for an EMVCO compliant system.

The Provisional Sum shall be expended in accordance with the provisions of Clause 13.5 [Provisional Sums] of Volume 1 Book 1, the “FIDIC Conditions of Contract for Design, Build and Operate Projects”, to pay for the supply of EMVCO Compliant Hardware and Software.

The percentage tendered under sub-item b) for overhead charges and profit shall be applied to the actual expenditure in terms of sub item a).

| Item No | Description | Unit |
| --- | --- | --- |
| B-6010 | Provision for interface with the Employer's MIS |  |
| B-6010a | Provision for the design, modification, development, integration, and installation to enable the Toll System to interface with the Employer's MIS | Prov Sum |
| B-6010b | Overhead charges and profit in respect of above-mentioned item | Percentage (%) |

The Provisional Sum is for the provision to interface the Toll Plaza(s) Back Office and / or toll lanes to the SANRAL MIS, in terms of the Principal Employer Requirements.

The Provisional Sum shall include for full compensation for the development and delivery of the completed software in order to interface the plaza(s) Back Office and/or toll lanes with the SANRAL MIS.  It shall include for all software supply installation, commissioning and/or upgrade of any 3rd party database software, etc. and the submission of applicable licenses.

The Provisional Sum shall be expended in accordance with the provisions of Clause 13.5 [Provisional Sums] of Volume 1 Book 1, the “FIDIC Conditions of Contract for Design, Build and Operate Projects”, to pay for the interface development to the SANRAL MIS.

The percentage tendered under sub-item b) for overhead charges and profit shall be applied to the actual expenditure in terms of sub item a and shall cover the Contractors procurement and management of hardware and software.

| Item No | Description | Unit |
| --- | --- | --- |
| B-6015 | SANRAL MIS interface |  |
|  | (a) Provision for the design, modification, development, integration and installation to enable the Toll System to interface with the SANRAL MIS | Prov Sum |
|  | (b) Support and Maintenance of the Toll System interface with the SANRAL MIS | Prov Sum |

The Provisional Sum provided under sub item a) will cover the costs of the interface between the Toll Plaza(s) Back Office and / or toll lanes to the SANRAL MIS, in terms of the Employer Requirements.

The Provisional Sum shall be expended in accordance with the provisions of Clause 13.5 [Provisional Sums] of Volume 1 Book 1, the “FIDIC Conditions of Contract for Design, Build and Operate Projects”, to pay interface the Toll Plaza(s) Back Office and / or toll lanes to the SANRAL MIS.

B-6015 (a) shall include the development and delivery of the completed software in order to interface the plaza(s) Back Office and/or toll lanes with the SANRAL MIS.  It shall include for all software supply installation, pilot deployment, commissioning and/or upgrade of any 3rd party database software, etc. and the submission of applicable licenses. This shall also cover the supply, installation, testing and commission of server(s), workstation(s) and printer(s), including but not limited to hardware, cabling, installation, contractors internal and milestone testing and earth.

B-6015 (b) shall cover the maintenance and support of the completed software and hardware that interface the plaza(s) Back Office and/or toll lanes with the SANRAL MIS.

C3.2.8	PARTICULAR AMENDMENTS TO THE STANDARD SPECIFICATIONS FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: ETC INTEROPERABILITY BUSINESS RULES (VOLUME 2 BOOK 8a)

The number of each Clause as a Particular Specification in section consist of the Prefix PS followed by a number corresponding to the number of the relevant Clause in the Standard Specifications for Operations and Maintenance of CTROM Projects:  Etc Interoperability – Business Rules (Volume 2 Book 8a).  The number of any new Clause which does not form part of any Clause in the Standard Specifications for Operations and Maintenance of CTROM Projects:  ETC Interoperability – Business Rules (Volume 2 Book 8a) and which is included herein, is also prefixed by PS followed by a number.  Such new numbers follow on the last Clause used in the relevant section of the Standard Specifications for Operations and Maintenance of CTROM Projects:  Etc Interoperability Business Rules (Volume 2 Book 8a).

There are no changes to any Clauses in the Standard Specifications for Operations and Maintenance of CTROM Projects:  ETC Interoperability – Business Rules (Volume 2 Book 8a).

PS1.1	Business Rules

PS1.1.2

The 9th line to be modified to read as follows:

“.../Concession Contract.  The third is applicable to the VPC and will not be discussed in this document.”

PS1.2	Business Processes

Alter subclause 1.2.2 add the following new subclause:

“PS1.2.3

For the purpose of this document, the following definitions will apply for the Transfer and Acceptance of transactions:

- The Transfer of Acceptance of Transactions on a non-recourse basis means the transfer of all rights and obligations under the Transactions Records by the Toll Agency (The Transferor) and the corresponding acceptance of these rights and obligations by the TCH (The Transferee), where the Transferor is not liable for any default, loss or defect relating to the Transaction Records in terms of which the rights and obligations are transferred.

- The Transfer of Acceptance of transactions on a recourse basis means the transfer of all rights and obligations under the Transaction Record by the Toll Agency (the Transferor) and the corresponding acceptance of these rights and obligations by the TCH (The Transferee), where the Transferor may be held liable for any default, loss or defect relating to the Transaction Record in terms of which the rights and obligations are transferred.”

The subclause 1.2.3 to be modified to read as follows:

“PS1.2.4

For an Opt-in Toll Agency, the TCH will accept and pay for all compliant and complete Transaction Records (as far as possible for the TCH to verify) transferred on a non-recourse basis.  The TCH will accept and pay for Transaction Records generated by vehicles associated with a customer account transferred on a non-recourse basis.

Transaction not associated with a customer account will still be accepted by TCH on behalf of VPC under a “back-to-back” arrangement for all compliant Transaction Records.  VPC will make payment for the transfer of these transactions that takes place on non-recourse basis.”

The subclause 1.2.4 to be modified to read as follows:

“PS1.2.5

For an opt Out Toll Agency the VPC element of the transaction accepted and paid for all other compliant transactions transferred on a non-recourse basis will not apply.”

The subclause 1.2.5 to be modified to read PS1.2.6

The subclause 1.2.6 to be modified to read PS1.2.7

The subclause 1.2.7 to be modified to read PS1.2.8

The subclause 1.2.8 to be modified to read as follows:

“PS1.2.9

In addition to the above, the processing fee will be upwardly adjusted for transactions received outside the period specified for the transfer and acceptance of transactions on the non-recourse basis and the specification in TA Business Rule 103.  The higher processing fee will be applied to all transactions received outside of the period specified for the Transfer and Acceptance of transactions on the non-recourse basis but are still processed by the TCH at the Toll Agency’s own risk.”

PS1.3	Layout of this Document

PS1.3.2

The 4th line to be modified to read as follows:

“... to another entity, render a service (including transfer and acceptance of transactions on non-recourse basis) and charge a processing fee ...”

PS2.1	INTER ENTITY RELATIONSHIPS

PS2.1.6

At the end of subclause 2.1.6 add the following:

“The purpose of the steering committee will be to coordinate the interaction/interface between the contractor, the TCH and Toll Agencies or Concessionaires – all under the guidance of SANRAL related to the roll-out of ETC on Concessionaires and CTROM routes and the interfacing and integration to the TCH.  The items discussed in the steering committee will include, inter alia (1) The processing fee model (2) The implementation agreements (3) Marketing planning (4) Integrated roll-out programs (5) Operational matters (6) System integration matters (7) Commercial Mattes (8) Legal matters (9) Financial Matters.”

PS2.1.12

The 1st line of this subclause 2.1.12 to be modified to read as follows:

“The TCH entity will accept transactions transferred from a Toll Agency on a non-recourse basis and pay for each Transaction Record ...”

PS2.1.13

The 1st sentence of subclause 2.1.13 to be modified to read as follows:

“For Opt-in Toll Agencies, the TCH will also accept the transfer of transactions on a non-recourse basis on behalf of the VPC for compliant Transaction Records sent to it but will reject non-compliant transactions.  VPC will pay for the transfer of these transactions on a non-recourse basis.  The VPC will levy ...”

PS2.1.15

The 2nd line of subclause 2.1.15 to be modified to read as follows:

“... fails, the violation will be passed for processing according to the legal requirement (AARTO or CPA).  When a violation ...”

PS3	KEY BUSINESS RULES

PS3.3	Transfer of transactions on a non-recourse basis accepted by the TCH and payment for this transfer to the Toll Agency from TCH

PS3.3.1

The 2nd line of subclause 3.3.1 to be modified to read as follows:

“... is based is the concept of transfer and acceptance of transactions on a non-recourse basis.  A Toll Agency is being ...”

The 4th line of subclause 3.3.1 to be modified to read as follows:

“... TCH entity.  The TA agrees to this because the TCH entity or for Opt-In Toll Agencies.  The VPC entity, undertakes to accept the transfer of transactions on a non-recourse basis and pay the appropriate toll ...”

PS3.3.2

The 2nd line of subclause 3.3.2 to be modified to read as follows:

“... because of the acceptance and payment for the transfer of transactions on a non-recourse basis, there will be a natural ...”

PS3.3.4

The 1st line of subclause 3.3.4 to be modified to read as follows:

“... TCH entity will accept and make payment for the transfer of transactions on a non-recourse basis and this must be ...”

The 3rd line of subclause 3.3.4 to be modified to read as follows:

“... The acceptance and payment for the transfer of transactions on a non-recourse basis is incorporated ...”

PS3.3.4	Key Business Rule 2(b)

The 1st line of this subclause to be modified to read as follows:

“... TCH entity shall accept transactions transferred on non-recourse basis and make payment to Toll Agencies ...”

The 4th line of this subclause to be modified to read as follows:

“... for an Opt-In Toll Agency, the acceptance of transactions transferred on a non-recourse basis and subsequent payment will be extended ...”

The 3rd line of the second paragraph of this subclause to be modified to read as follows:

“... otherwise it will be rejected, and the Toll Agency informed.  In addition, it must ...”

PS3.3.10

The 1st line of this subclause to be modified to read as follows:

“Related to payments and acceptance of transactions transferred on a non-recourse basis is the frequency ...”

PS3.3.10	Key Business Rule 4

This clause to be deleted and replaced with the following:

“Key Business Rule 4.	The normal cycle for invoicing for toll transactions and inter Entity account settlement in relation to payment due shall not exceed seven working days

The normal cycle for invoicing of processing fee shall be daily to coincide with the processing on the TCH but the settlement of the processing fees shall be monthly.”

PS4	BUSINESS RULES FOR TOLL AGENCY

PS4.2.3	TA Business Rule 101

The 1st sentence of this subclause to be modified to read as follows:

“The Actual Class will default either to the MVC class (in mixed/manual lanes) or AVC class (when the collector class is not included in the transaction from a mixed/manual lane) or the AVC class when the AVC classification is available for dedicated lanes or the Registered Vehicle Class, according to the Toll System configuration.”

PS4.2.5

The 1st line of this subclause to be modified to read as follows:

“Activity 4.2.4a) is associated with the potential of acceptance and payment of transactions transferred on a non-recourse basis at the TCH or VPC ...”

PS4.2.6

The 7th line of this subclause to be modified to read as follows:

“In the case of a Catastrophic Event, special permission ...”

The 3rd bullet of this subclause to be modified to read as follows:

“The remaining 10% of the Transaction Records not later than 5 days after the date and time of the Chargeable Event that generated them (The transfer of these transactions on a recourse basis will be accepted and the TCH will endeavour to process them.  If these transactions can be allocated to a valid account before the end of the grace period, payment will be made by the TCH, if not, the transactions will be rejected by the TCH).”

PS4.2.6	TA Business Rule 103(b)

The 2nd line of the 3rd bullet of this subclause to be modified to read as follows:

“... Chargeable Event that generated them (The transfer of these transactions on a recourse basis will be accepted and the TCH will endeavour to process them.  If these transactions can be allocated to a valid account before the end of the grace period, payment will be made by the TCH, if not, the transactions will be rejected by the TCH.”

PS4.2.6	TA Business Rule 104(b)

The 3rd paragraph of this subclause to be modified to read as follows:

“... and under no circumstances, other than the approved Catastrophic Event, shall they be sent later than 5 days ...”

PS4.2.6	TA Business Rule 105(b)

The 1st line of the 1st paragraph of this subclause to be modified to read as follows:

“For conventional electronic toll collection, the acceptance of the transfer of Transactions Records ...”

The last line of the 1st paragraph of this subclause to be modified to read as follows:

“... event that generated them, shall be on a non-recourse basis.”

The 1st and 2nd lines of the 2nd paragraph of this subclause to be modified to read as follows:

“For both open and conventional electronic toll collection, the acceptance of transfer of transactions records sent to the TCH later than 24 hours after the date and time of the Chargeable Event shall be on recourse basis and the TCH shall endeavour ...”

Delete the 4th paragraph of this subclause and replace with the following:

“The acceptance of the transfer of transaction records linked to post-paid account where the payment means is specified as ‘credit card’ and received after 24 hours but not later than 25 days will be on a recourse basis (as 45 days are specified in the Acquiring Bank Agreement and time should be allowed for the TCH to process the transactions received).”

This new subclause to be inserted after subclause PS4.2.6 TA Business Rule 105(b):

“PS4.2.7

For the purpose of this document, a Catastrophic Event means an event or occurrence that is the type of event which is not part of normal operations and results in the situation where the Transaction Records from the Toll Agency require transfer and acceptance for processing outside the normal business rules. The risk and the obligation shall be divided according to the following categories:

Category 1: If the event is not under the control of both the TA and the TCH;

The transfer and acceptance of Transaction Records shall be on a recourse basis. The risk would be in the Transaction Records not recovered from the Customers, e.g.: the transaction which could not be assigned to a Customer account before the end of the grace period or when a Customer disputes the transaction after it was assigned to his/her account.

Where the event is because of a third party, not under the control of either party, the risk shall be shared since the obligation is not directly trace-able to the Toll Agency or the Transaction Clearing House.

The TCH shall record and report on Transaction Records not processed and processed due to a Catastrophic Event. The process to record losses due to transactions disputed after it was assigned to an account will be done outside the system as part of the Toll Agency’s dispute approval and resolution process.

Category 2: If the event is under the control of the TA;

The transfer and acceptance of Transaction Records shall be on a recourse basis. The risk would be in the Transaction Records not recovered from the Customers, e.g.: the transaction which could not be assigned to a Customer account before the end of the grace period or when a Customer disputes the transaction after it was assigned to his/her account.

Where the event is because of a failure of a process under the control of the Toll Agency, the risk and subsequent loss shall be for the Toll Agency.

The TCH shall record and report on Transaction Records not processed and processed due to a Catastrophic Event. The process to record losses due to transactions disputed after it was assigned to an account will be done outside the system as part of the Toll Agency’s dispute approval and resolution process.

Category 3: If the event is under the control of the TCH.

The transfer and acceptance of Transaction Records shall be on a non-recourse basis.

The risk would be in the transactions processed and transferred on a non-recourse basis but not recovered from the Customers.

Since the event is because of a failure of a process under the control of the TCH, the risk and subsequent loss shall be for the TCH.

The TCH shall record and report on Transaction Records not recovered (i.e.: Transaction records accepted and transferred on a non-recourse basis but not assigned to a Customer Account).

PS4.2.7.1	A Catastrophic Event on the side of the Toll Agency may result in (but not be limited to) the following conditions:

- Transactions not being sent by the Toll Agency in the specified time (addressed in TA Business Rule 106); or

- Validation lists not being updated by the Toll Agency in the specified time (the risk of the rejection of these transactions by the TCH remains with the Toll Agency).

PS4.2.7.2	A Catastrophic Event on the side of the Transaction Clearing House may result in (but not be limited to) the following conditions:

- Transactions not being accepted by the TCH even though the Toll Agency attempted to send them in the specified time (addressed in TA Business Rule 106); or

- Validation lists not being available from the TCH at the specified intervals (addressed in TA Business Rule 112 and TCH Business Rule 204).

PS4.2.7.3	The process to declare a Catastrophic Event and to trigger the special processing rules would include the following:

- If the Catastrophic event is on the side of the Toll Agency,

  - The Toll Agency needs to notify SANRAL, the IE, the ER and the TCH Operator of the Catastrophic Event. The notification should include a specification of the affected toll plaza, the period of the catastrophic event i.e. start date and time and end date and time. (The cause of the Catastrophic event should be provided as soon as it is known and will be required before the risk of the loss in income is determined.);

  - The IE and the ER will make a recommendation and SANRAL will approve the application for the declaration of the Catastrophic Event and notify the TCH Operator and the Toll Agency that the event was approved.

  - The TCH Operator will configure the system with the information to allow for acceptance of the transactions and notify the Toll Agency that transactions can be sent. Where possible, the period for transfer and acceptance of the Transaction Records from the Catastrophic Event will be configured to occur outside the period for transfer and acceptance of Transaction Records on a recourse basis to ensure that the validation rules for Transaction Records from the Catastrophic Event do not conflict with the general validation rules. If not possible to wait for the recourse period to pass, the processing and classification rules for a Catastrophic Event will take priority over the general validation rules;

  - The TCH will attempt to process the Transaction Records.

- If the Catastrophic event is on the side of the TCH system,

  - The Toll Agency / Agencies will not be able to send Transaction Records and the status of the Transaction Records will remain “unsent” on the Toll Agency system;

  - The TCH Operator need to notify SANRAL, the IE, the ER and the Toll Agency / Toll Agencies. (The cause of the Catastrophic event should be provided as soon as it is known and will be required before the risk of the loss in income is determined.)

  - The ER will make a recommendation and SANRAL will approve the application for the declaration of the Catastrophic Event and notify the TCH Operator and the Toll Agency/ Toll Agencies that the event was approved.

  - The TCH system error needs to be rectified and it will be communicated to the Toll Agency;

  - After the TCH Catastrophic Event has been rectified, the TCH system will be configured for the Catastrophic Event. Depending on the requirement, the TCH will change the general validation rules, i.e.:

    - The time-period for transfer and acceptance of Transaction Records on a non-recourse basis; and/or

    - The time-period for transfer and acceptance of Transaction Records on a recourse basis; and/or

    - The time-period allowed for the update of the validation lists (Indicated in TA Business Rule 112).

Where possible, the period for transfer and acceptance of the Transaction Records from the Catastrophic Event will be configured to occur outside the period for transfer and acceptance of Transaction Records on a recourse basis to ensure that the validation rules for Transaction Records from the Catastrophic Event do not conflict with the general validation rules. If not possible to wait for the recourse period to pass, the processing and classification rules for a Catastrophic Event will take priority over the general validation rules;

  - The Toll Agency will be able to send the transactions to the TCH;

  - The TCH will accept the transactions and process the transactions.

PS4.2.7.4	The results of the processing of Transaction Records under the Catastrophic Event will be recorded and reported. The report will include the value (loss) of Transaction Records not assigned to valid accounts, but this value will not be the final loss;

PS4.2.7.5	The final loss will include the risk of Customers not paying due to late processing (e.g. fleet banks or vehicle rental and lease companies “rejecting” transactions) or with Customers disputing the transactions during the period allowed for queries as specified in the Terms and Conditions. The final loss of transactions which were successfully processed (assigned to accounts) on TCH will only be quantifiable after payment received from the Customers and/or after transactions are queried by the Customers and credit notes are processed.

PS4.2.7.6	The final loss will therefore be evaluated and determined outside of the system and included in a special “Catastrophic Event” report with the indication of the final loss and where such loss should reside and if necessary, what inter-entity invoicing is required. The compilation of the final report and the inter-entity invoicing shall be a manual process outside of the TCH system.

PS4.2.7.7

With regards to the transfer and acceptance of Transaction Records from the Toll Agency to the Transaction Clearing House, the following rules will apply:

TA Business Rule 106.

For the transfer and acceptance of Transaction Records from the Toll Agency to the Transaction Clearing House:

For open road toll collection, the Transaction Records sent to the TCH after 24 hours after the date and time of the Chargeable Event that generated them shall not be accepted and processed unless approved as being included in a Catastrophic Event that prevented the Toll Agency from sending the transaction to the TCH. The TCH shall record and report on Transaction Records not processed and Transaction Records processed after expiry due to a Catastrophic Event.

For conventional electronic toll collection, the Transaction Records sent to the TCH after 5 days after the date and time of the Chargeable Event that generated them and not linked to a card payment, shall not be accepted and processed unless approved as being included in a Catastrophic Event that prevented the Toll Agency from sending the transaction to the TCH. The TCH shall record and report on Transaction Records not processed and Transaction Records processed after expiry due to a Catastrophic Event.

In the event that the TCH has a technical or communication error that prevents timeous transfer and acceptance of transactions from the Toll Agency, the Catastrophic event procedure will be followed and the TCH will process all transactions after the prescribed time when the TCH communication has been restored.

The subclause 4.2.7 to be modified to read as follows:

“PS4.2.8

The paragraph of this subclause to be modified to read as follows:

“Clause PS4.2.8 and TA Business Rule 107 is not applicable to the conventional electronic toll collection where ANPR (or similar technology) functionality is not implemented”.

The 1st line of the 2nd paragraph of this subclause to be modified to reads as follows:

“For Toll Agencies where ANPR or similar technologies is implemented, the Toll Agency must ensure ...”

Subclause 4.2.8 to be modified to read as follows:

“PS4.2.9

The 1st paragraph of this subclause to be modified to read as follows:

“Clause PS4.2.9 and TA Business Rule 108 is not fully applicable at the conventional electronic toll collection where ANPR (or similar technology) functionality is not implemented.”

The 1st line of the 2nd paragraph of this subclause to be modified to reads as follows:

“For Toll Agencies where ANPR or similar technology is implemented, the Toll Agency most also ensure ...”

Subclause 4.2.9 to be modified to read as follows:

“PS4.2.10

The 1st paragraph of this subclause to be modified to read as follows:

“Clause PS4.2.10 and TA Business Rule 109 is not fully applicable to the conventional electronic toll collection where ANPR (or similar technology) functionality is not implemented.  This subclause only applies to the picture required for a class discrepancy.”

PS4.4	Distribution of Validation Lists

PS4.4.3	TA Business Rule 112

At the end of this subclause add the following:

“(c)	In a Catastrophic Event where the TCH have a technical or communication error that prevents the timeous distribution of the validation lists, the TCH will update the time allowed for the update of the validation list from 4 hours to the time-period determined by the length of the TCH Catastrophic Event.”

PS5	BUSINESS RULES FOR THE TCH

PS5.1	Interface to the Toll Agency

PS5.1.1

The 1st line of this subclause to be modified to read as follows:

“... Toll Agency and for the acceptance of transactions transferred on a non-recourse basis, it has been assumed ...”

PS5.1.3

This subclause to be modified to read as follows:

“For the “Tag in a Bag”, initially the tag will not be on the green or the red list since the Vehicle Licence Number and the vehicle class will be unknown.  The ORT Toll Agency with the required ANPR equipment will add the Vehicle Licence Number and class in the transaction record when it is first detected.  This will enable TCH to add an account with the additional information ...”

PS5.1.4	TCH Business Rule 201

The 4th line of the 5th paragraph of this subclause to be modified to read as follows:

“... the TCH entity shall accept responsibility in relation to its acceptance and payment for transactions transferred on a non-recourse basis for the period until ...”

PS5.1.7

The 2nd line of this subclause to be modified to read as follows:

“... Transaction Record meets the requirements for acceptance of transactions transferred on a non-recourse basis.  It may also be considered ...”

PS5.2	Interface to Customer

PS5.2.4	TCH Business Rule 220

This subclause to be modified to read as follows:

“... Transaction Records from Opt-in Toll Agencies or transactions transferred on a recourse basis from Opt-out Toll Agency that may cause that to a general suspense account while the TCH seeks to obtain an account top-up from the customer.  Transaction Records accepted from an Opt-out Toll Agency and transferred on a non-recourse basis and TCH fees will always be assigned to a pre-paid customer account and shall result in a temporary negative balance.  The TCH shall seek to obtain an account top-up from the customer or recover the outstanding amount via the VPC by sending the outstanding balance for enforcement.”

PS5.3	Interface to VPC

PS5.3.1

The 2nd line of this subclause to be modified to read as follows:

“... dictated by the payment based on the acceptance of transaction transferred on a non-recourse basis that is provided ...”

PS5.3.1	TCH Business Rule 238

This subclause to be deleted and replaced with the following:

“TCH Business Rule 238.  Not applicable.”

PS5.3.1	TCH Business Rule 239

This subclause to be deleted and replaced with the following:

“TCH Business Rule 239.  Not applicable.”

PS5.3.1	TCH Business Rule 240

This subclause to be deleted and replaced with the following:

“TCH Business Rule 240.  Not applicable.”

PS5.3.1	TCH Business Rule 241

This subclause to be deleted and replaced with the following:

“TCH Business Rule 241.  Not applicable.”

PS5.3.1	TCH Business Rule 242

This subclause to be deleted and replaced with the following:

“TCH Business Rule 242.  Not applicable.”

# PART C3.3: ENVIRONMENTAL MANAGEMENT PLAN (SECTION C)

PART C3.3: ENVIRONMENTAL MANAGEMENT PLAN (SECTION C)

Table of Contents	Page

C1001	SCOPE	C219

C1002	Definitions	C219

C1003	LEGAL REQUIREMENTS	C220

C1004	ADMINISTRATION OF ENVIRONMENTAL OBLIGATIONS	C222

C1005	TRAINING	C223

C1006	ACTIVITIES/ASPECTS CAUSING IMPACTS	C224

C1007	ENVIRONMENTAL MANAGEMENT OF CONSTRUCTION ACTIVITIES	C227

C1008	AREAS OF SPECIFIC IMPORTANCE	C235

C1009	Rehabilitation	C235

C1010	RECORD KEEPING	C236

C1011	COMPLIANCE AND PENALTIES	C236

C1012	PROJECT SPECIFIC CONDITIONS	C236

###### C1001	SCOPE

The South African National Roads Agency SOC Limited (SANRAL) recognises environmental management as a key component of road infrastructure development and as part of its Environmental Sustainability Framework has developed this Environmental Management Plan (EMP) as a tool for continual improvement in environmental performance.

This EMP prescribes the methods by which proper environmental controls are to be implemented by the Contractor for construction and maintenance projects. The duration over which the Contractor’s controls shall be in place cover the construction period of the project as well as the limited time after contract completion defined by the “Conditions of Contract for Design, Build and Operate Projects” (2008), published by the Fédération Internationale des Ingénieurs-Conseils, (FIDIC).

The provisions of this EMP are binding on the Contractor during the life of the contract. They are to be read in conjunction with all the documents that comprise the suite of documents for this contract, particularly the conditions of any environmental authorisation and associated site-specific Environmental Management Programme (EMPr). In the event that any conflict occurs between the terms of the EMP and the project specifications or environmental authorisation, the terms herein shall be subordinate.

The EMP is a dynamic document subject to similar influences and changes as are brought by variations to the provisions of the project specification. Any changes to the EMP and/or environmental authorisation cannot occur without being submitted to SANRAL who will manage the process of amending the EMP.

The EMP identifies the following:

- Relevant parties and their responsibilities;

- Construction activities that will impact on the environment;

- Specifications with which the Contractor shall comply in order to protect the environment from the identified impacts; and

- Actions that shall be taken in the event of non-compliance.

###### C1002	Definitions

Alien Vegetation: undesirable plant growth which includes but is not limited to all declared category 1 and 2 listed invader species as set out in the Conservation of Agricultural Resources Act (CARA), 1983 and the National Environmental Management: Biodiversity Act (Act No. 10 of 2004). Other vegetation deemed to be alien are those plant species that show the potential to occupy in number, any area within the defined construction area and which are declared to be undesirable.

Construction Activity: any action taken by the Contractor, his sub-contractors, suppliers or personnel during the construction process as defined in the contract documents.

Environment: the surroundings within which the contract exists and comprises land, water, atmosphere, micro-organisms, plant and animal life (including humans) in any part or combination thereof as well as any physical, chemical, aesthetic or cultural inter-relationship among and between them.

Environmental Aspect: any component of a contractor’s construction activity that is likely to interact with the environment.

Environmental authorisation: a written statement from a Competent Authority, with the general and specific conditions and the EMPr recording its approval of an application for a planned undertaking that triggers listed activities in the Environmental Impact Assessment (EIA) regulations of the National Environmental Management Act (NEMA).

Environmental Impact: any change to the environment, whether desirable or undesirable, that will result from the effect of a construction activity. An impact may be the direct or indirect consequence of a construction activity.

Environmental Impact Assessment (EIA): a systematic process of identifying, assessing and reporting environmental impacts associated with an activity and includes basic assessment and scoping and environmental impact reporting.

Environmental Management Plan: An Environmental Management Plan (EMP) is an environmental management tool used to ensure that adverse impacts of the construction and operation and decommissioning of a project are prevented and/or minimised, and that the positive benefits are enhanced.

Environmental Management Programme (EMPr):  A project-specific Environmental Management Plan approved by a competent authority through an environmental impact assessment process.

Road Reserve: a corridor of land, defined by co-ordinates and/or proclamation, within which the road, including access intersections or interchanges, is situated. A road reserve may, or may not, be bounded by a fence.

Site; the site is defined in the FIDIC Conditions of Contract and in the scope of works. It is bound by the limits of construction as shown in the drawings or the title of the project and extends to also include the following:

- Areas outside the construction zones where accommodation of traffic is placed;

- All borrow pits defined in the applications approved by the Department of Mineral Resources (DMR);

- All haul roads constructed by the Contractor for purposes of access;

- Any non-adjacent sites specified in the contract documentation;

- The Contractor’s and his subcontractors’ camp sites.

For the purposes of this EMP, the site includes areas outside of, but adjacent to, the road reserve that may be affected by construction activities.

Spoil material: is material that is unsuitable for construction of the road pavement and for which no other useful purpose can be found in additional works on the project (e.g. for the provision of protection berms). Such material requires spoiling at convenient areas to be identified by the Engineer and/or Contractor within the Site. Spoil material does not require removal to a designated landfill site unless it contains identifiable hazardous contaminants.

###### C1003	LEGAL REQUIREMENTS

- General

Construction shall be according to the best industry practices, as identified in the project documents. This EMP, which forms an integral part of the contract documents, informs the Contractor as to his duties in the fulfilment of the project objectives, with particular reference to the prevention and mitigation of environmental impacts caused by construction activities associated with the project. The Contractor should note that obligations imposed by the EMP are legally binding in terms of this contract. In the event that any rights and obligations contained in this EMP contradict those specified in the standard or project specifications then the latter shall prevail.

- Statutory and other applicable legislation

The Contractor is deemed to have made himself conversant with all legislation pertaining to the environment, including provincial and local government ordinances, which may be applicable to the contract.

Major environmental legislation, as amended from time to time, includes but is not limited to the following:

(i)	Conservation of Agricultural Resources Act (Act No. 43 of 1983)

This act provides for control over the utilisation of the natural agricultural resources of South Africa in order to promote the conservation of soil, water sources and vegetation, as well as combating weeds and invader plants.

(ii)	The Constitution (Act 6 of 1996)

The Constitution states that everyone has the right to an environment that is not harmful to their health or well-being, and to have the environment protected through reasonable legislative and other measures to prevent pollution and ecological degradation; promote conservation and ensure ecologically sustainable development and use of natural resources.

(iii)	Mineral and Petroleum Resources Development Act (Act No. 28 of 2002)

This act makes provision for equitable access to, and sustainable development of, minerals and petroleum resources.

(iv)	National Environmental Management Act (NEMA), (Act No. 107 of 1998)

This act supports the Bill of Rights within the Constitution and highlights principles of sustainable development including preservation of ecosystems and biological diversity and avoidance, minimisation and remediation of pollution and environmental degradation. It also sets the stage for the EIA Regulations.

(v)	National Environmental Management: Air Quality Act (Act No. 39 of 2004)

This act provides reasonable measures for the prevention of pollution and ecological degradation; and provides for specific air quality measures; for national norms and standards regulating air quality monitoring, management and control by all spheres of government.

(vi)	National Environmental Management: Biodiversity Act (Act No. 10 of 2004)

This act makes provisions to accomplish the objectives of the United Nations’ Convention on Biological Diversity. SANRAL may be required to apply for permits to conduct certain listed activities which, together with the listed threatened or protected species, may be identified by the Minister.

Section 73 (3) of this act empowers a competent authority to direct a person to take steps to remedy any harm to biodiversity resulting from the actions of that person or as a result of occurrence of listed invasive species occurring on land on which that person is the owner. Thus SANRAL may be directed to remedy harm caused by listed invasive species.

(vii)	National Environmental Management: Protected Areas Act (Act No. 57 of 2003)

This act provides for the protection and conservation of ecologically viable areas representative of South Africa’s biological diversity, natural landscapes and seascapes.

(viii)	National Environmental Management: Waste Act (Act No. 59 of 2008)

This act aims to regulate waste management practices through provision of national norms and standards, specific waste measures, licensing and control of waste activities, remediation of contaminated land as well as providing for compliance and law enforcement.

(ix)	National Forests Act (Act No. 84 of 1998)

This act makes provision for promoting the sustainable management and development of forests, and for the protection of certain forests and trees for environmental, economic, educational, recreational, cultural, health and spiritual purposes.

(x)	National Heritage Resources Act (Act No. 25 of 1999)

This act provides for an integrated and interactive system for identification, assessment and management of South Africa’s heritage resources, and empowers civil society to nurture and conserve their heritage resources.

(xi)	National Water Act (Act No. 36 of 1998)

This act makes provision for the protection of surface water and groundwater and their sustainable management for the prevention and remediation of the effects of pollution, as well as for the management of emergency situations.

- The South African National Roads Agency Limited and National Roads Act (Act No. 7 of 1998)

This Act makes provision for a National Roads Agency for the Republic to manage and control the Republic’s national roads system and take charge, amongst others, of the development, maintenance and rehabilitation of national roads within the framework of government policy.

###### C1004	ADMINISTRATION OF ENVIRONMENTAL OBLIGATIONS

Copies of this EMP shall be kept at the site office and must be distributed to all senior contract personnel who shall familiarise themselves with its contents.

Implementation of this EMP requires the involvement of several stakeholders, each fulfilling a different but vital role as outlined herein, to ensure sound environmental management during the construction phase of a project.

(a)	SANRAL

SANRAL and anyone acting on SANRAL’s behalf is accountable for the potential environmental impacts of any activities that are undertaken and is responsible for managing these impacts.

(b)	The Engineer

The Engineer has been appointed by, and acts for, SANRAL as its on-site implementing agent and carries the responsibility to ensure that the Contractor undertakes its construction activities in such a way that SANRAL’s environmental responsibilities are not compromised.

The Engineer will, within seven days of receiving a contractor’s request for approval of a nominated Designated Environmental Officer (DEO), approve, reject or call for more information on the nomination. The Engineer will be responsible for issuing instructions to the DEO where environmental considerations call for action to be taken.

If in the opinion of the Engineer the DEO is not fulfilling his/her duties in terms of this EMP, the Engineer may, after discussion and agreement with SANRAL, exercise his powers under FIDIC general conditions of contract and instruct replacement of the DEO in writing and with stated reasons.

(c)	The Contractor

The Contractor is responsible for project delivery in accordance with the prescribed specifications, among which this EMP shall be included.

The Contractor shall receive and implement any instruction issued by the Engineer relating to compliance with the EMP including the removal of personnel or equipment.

Compliance with the provisions contained herein or any condition imposed by the environmental approvals shall become the responsibility of the Contractor through an approved Designated Environmental Officer (DEO). The Contractor shall nominate a person from among his site personnel to fulfil this function and submit to the Engineer for his approval the curriculum vitae of the proposed DEO. This request for approval shall be given, in writing, at least fourteen days before the commencement of any construction activity clearly setting out reasons for the nomination, and with sufficient detail to enable the Engineer to make a decision.

(d)	The Designated/Dedicated Environmental Officer (DEO)

Once a nominated representative of the Contractor has been approved, he/she shall become the DEO and shall be the responsible person for ensuring that the provisions of this EMP are complied with during the life of the contract. The DEO shall submit regular written reports to the Engineer, but not less frequently than once a month.

The DEO may undertake other construction duties unless Section B: Specification Data, prescribes this position as ‘Full-time’ or ‘dedicated’ as opposed to the standard position being ‘designated’. However, the DEO’s environmental duties shall hold primacy over other contractual duties and the Engineer has the authority to instruct the Contractor to reduce the DEO’s other duties or to replace the DEO if, in the Engineer’s opinion, he/she is not fulfilling his/her duties in terms of the requirements of this EMP. Such instruction will be in writing clearly setting out the reasons why a replacement is required.

As a minimum the DEO shall have an accredited National Qualifications Framework (NQF) level 6  qualification in environmental or natural sciences or equivalent and a minimum of 2 years’ experience in a similar role in construction or other environmental regulatory field.

In addition to the compliance duties relating to EMP the DEO shall also provide full cooperation whenever the Contractor is subjected to environmental audits.

(e)	Environmental Control Officer (ECO)

The Environmental Control Officer (ECO) is an independent environmental specialist appointed by SANRAL or the Engineer to objectively and regularly monitor the Contractor’s compliance with the conditions of the authorisations issued for the project and the approved EMPr (that is this EMP augmented with specifics of the project). These are external audits and the regularity is determined by the environmental authorisations.

###### C1005	TRAINING

(a)	Qualifications

The (DEO) shall have the minimum qualifications as prescribed above and must be conversant with all legislation pertaining to the environment applicable to the contract. He/she must be appropriately trained in environmental management and possess the skills necessary to impart environmental management skills to all personnel involved in the contract.

The Contractor shall ensure that adequate environmental training takes place. All employees shall have been given an induction presentation on environmental awareness. Where possible, the presentation needs to be conducted in the language of the employees.

(b)	Content

Apart from induction environmental training should, as a minimum, include the course content below and no induction or course should be given until the Engineer has been afforded the opportunity to appraise it and provide comment.

(i)	The importance of conformance with all environmental policies and the consequences of departure from standard operating procedures;

(ii)	Environmental impacts, actual or potential, caused by work activities, prevention measures to avoid them and mitigation measures when they occur;

(iii)	Work force roles and responsibilities in achieving conformance with the environmental policy and procedures, including emergency preparedness and response requirements;

(iv)	The environmental benefits of improved personnel performance and

(v) 	Consequences of non- compliance

(c)	Induction

In the case of permanent staff the Contractor shall provide evidence that such induction courses have been presented. In the case of new staff (including contract labour) the Contractor shall inform the Engineer when and how he intends concluding his environmental training obligations.

###### C1006	ACTIVITIES/ASPECTS CAUSING IMPACTS

Typical environmental aspects and impacts associated with road construction are listed in Table 1: Aspects and Impacts Associated with Road Construction. Actual impacts will differ from project to project and, therefore, so may the mitigation measures employed. The most common aspects and impacts are addressed separately, and typical avoidance and/or mitigation measures described. The list and descriptions are not by any means exhaustive, and they shall be used for guideline purposes only.

Table 1: Aspects and Impacts Associated with Road Construction

| Aspect | Potential Impact |
| --- | --- |
| Waste generation/storage | Water pollution; nuisance; visual impact |
| Water use and stormwater discharge | Change in flow regime and/or reduction in downstream availability; soil erosion: water pollution |
| Vehicle use and maintenance | Air pollution; noise |
| Chemical/fuel storage | Water/air/soil pollution; health impacts; accidents e.g. spills, fire |
| Site clearing; earthworks; layer-works; seal works | Change in landform; impact on heritage resources; noise; soil erosion; air pollution |
| River bridges; installing drainage structures | Water pollution; impact on river flows; noise |
| Land acquisition | Loss of land and/or livelihood; change in land use; |
| Acquisition of building material from borrow pits | Change in landform and use |

(a)	General approach

# The role of the DEO cannot be underestimated and once approved he/she shall be on the site at all times, and before the Contractor begins each construction activity, he/she shall give to the Engineer a written statement setting out the following:

(i)	The type of construction activity about to be started.

(ii)	Locality where the activity will take place.

(iii)	Identification of the environmental aspects and impacts that might result from the activity.

(iv)	The methodology of impact prevention for each activity or aspect.

(v)	The methodology of impact containment for each activity or aspect.

(vi)	Identification of the emergency/disaster potential for each activity (if any) and the reaction procedures necessary to mitigate impact severity.

(vii)	Treatment and continued maintenance of impacted environment.

The Contractor shall programme his work in such a way that each cause and effect of a construction activity is also identified, and the activity planned so as to prevent any impact from happening and shall demonstrate that he is capable of carrying out any repair and reinstatement of the damaged environment. These requirements shall be concurrent with the time constraints to produce method statements for each construction activity in compliance with the provisions of these project specifications.

The Contractor shall provide such information in advance of any or all construction activities provided that new submissions shall be given to the Engineer whenever there is a change or variation to the original.

The Engineer may provide comment on the methodology and procedures proposed by the DEO, but he shall not be responsible for the Contractor’s chosen measures of impact mitigation and emergency/disaster management systems. However, the Contractor shall demonstrate at inception and at least once during the contract that the approved measures and procedures function properly.

(b)	Spillages

Streams, rivers and dams shall be protected from direct or indirect spillage of pollutants such as refuse, garbage, cement, concrete, sewage, chemicals, fuels, oils, aggregate, tailings, wash water, organic materials and bituminous products. In the event of a spillage, the Contractor shall be liable to arrange for professional service providers to clear the affected area.

Responsibility for spill containment and treatment (whether hazardous or not) lies with the Contractor. The individual causing a spill, or who discovers a spill, must report the incident to his/her DEO or to the Engineer. The DEO will assess the situation in consultation with the Engineer and act as required. In all cases, the immediate response shall be to contain the spill. The exact treatment of polluted soil/water shall be determined by the Contractor in consultation with the DEO and the Engineer. Areas cleared of hazardous waste shall be re-vegetated according to the Engineer’s instructions.

Should water downstream of the spill be polluted, and fauna and flora show signs of deterioration or death, specialist hydrological or ecological advice will be sought for appropriate treatment and remedial procedures to be followed. The requirement for such input shall be agreed with the Engineer. The costs of containment and rehabilitation shall be for the Contractor’s account, including the costs of specialist input as well as the sampling and testing of the water quality upstream and downstream of the spill. Water quality sampling and testing, and further treatment shall continue until upstream and downstream results correspond with each other.

(c)	Water use and control

# The Contractor’s use of water shall take into consideration that it is a scarce commodity and shall be optimised. Authorisation shall be obtained from the Department of Water and Sanitation (DWS) before water is drawn from streams or new boreholes developed.

# The Contractor shall also ensure that any stream deviations or diversions are undertaken in such a manner that the impact on the environment is minimised. Method statements shall be submitted to the Engineer for comment, detailing how the work will be undertaken, what risks are foreseen and what measures will be employed to minimise such risks. Notwithstanding any comments by the Engineer, no work on stream deviations or diversions shall be undertaken in accordance with GN 509 in GG 40229 of 26 August 2016 - General Authorisation in terms of Section 39 of the National Water Act, 1998 (Act No. 36 Of 1998) for Water Uses as defined in sections 21(c) and (i) .

The quality, quantity and flow direction of any surface water runoff shall be established prior to disturbing any area for construction purposes. Cognisance shall be taken of these aspects and incorporated into the planning of all construction activities. Before a site is developed or expanded, it shall be established how this development or expansion will affect the drainage pattern. Recognised water users/receivers shall not be adversely affected by the expansion or re-development. No water source shall be polluted in any way due to proposed changes.

Streams, rivers, pans, wetlands, dams, and their catchments shall be protected from erosion and flooding by dredging, daylighting, removal of debris and vegetation, etc. These shall also be protected from direct or indirect spillage of pollutants such as refuse, garbage, cement, concrete, sewage, chemicals, fuels, oils, aggregate, tailings, wash water, organic materials and bituminous products.

# The Contractor shall submit to the Engineer his proposals for prevention, containment and rehabilitation measures against environmental damage of the identified water and drainage systems that occur on the site. Consideration shall be given to the placement of sedimentation ponds or barriers where the soils are of a dispersive nature or where toxic fluids are used in the construction process. The sedimentation ponds must be large enough to contain runoff so that they function properly under heavy rain conditions up to 1:5 year severity.

# The Contractor shall submit to the Engineer the results of the baseline water quality test taken above and below the site of the proposed activity, and thereafter monthly testing results or at the frequency as may be specified by the Water Use Licence/General Authorisation, where applicable. No taking-over can be authorised until the water quality is shown to be at pre-construction levels or better.

# (d)	Vegetation management

The Contractor shall be responsible for the management of vegetation by protection of indigenous vegetation, especially identified protected species, and the prevention of alien vegetation germinating in areas disturbed by road construction activities within and outside the road reserve. This includes, for example, service roads, stockpile areas, stop/go facilities, windrows and wherever material generated for or from road construction has been stored temporarily. This responsibility shall continue for the duration of the defects notification period. The project specification may instruction the removal of CARA and/or NEMBA-listed category 1 and 2 alien species and planting of specified indigenous species.

# (e)	Dust control

# Dust caused by construction activities shall be controlled by appropriate means and applied at sufficient frequency so as not to cause nuisance to adjacent habitation or affect farming activities or natural vegetation. Vegetation cover should also be kept for as long as possible to reduce the area of exposed surfaces. Dust emissions from batching and screening plants shall be subject to the relevant legislation and shall be the subject of inspection by the relevant authorities.

# (f)	Noise control

The Contractor shall endeavour to keep noise generating activities to a minimum. Noises that could cause a major disturbance, for instance blasting and crushing activities, should only be carried out during the hours prescribed by the conditions of contract (i.e. normal hours). Should such noise generating activities have to occur at any time outside normal hours the people in the vicinity of the noise-generating activity shall be warned about the noise well in advance and the activities kept to a minimum. Relevant legislation shall also be taken into consideration, and any practical mitigation measures adopted. No noise generating activity outside of normal hours, regardless of its proximity to residences, can take place without application to the Engineer for approval. The application shall be accompanied by the noise containment measures proposed.

# (g)	Energy consumption

# The Contractor shall take into consideration the impacts of high energy consumption, both from a cost and emissions point of view. Energy use shall be minimised, and where possible, alternative energy sources such as solar utilised.

Furthermore, the Contractor shall measure and keep records of the consumption of carbon units his chosen method of construction produces in the execution of his programme. In conjunction with the Engineer who will provide complete cooperation, a month by month output shall be compiled and efforts made to see how these outputs can be curtailed and reduced.

###### C1007	ENVIRONMENTAL MANAGEMENT OF CONSTRUCTION ACTIVITIES

The Contractor shall undertake “good housekeeping” practices during construction as stated in the COTO Standard Specifications for Roads and Bridges and the FIDIC conditions of contract. This will help avoid disputes on responsibility and allow for the smooth running of the contract as a whole. Good housekeeping extends beyond the wise practice of construction methods that leaves production in a safe state from the ravages of weather to include the care for and preservation of the environment within which the site is situated.

The construction activities addressed below shall become part of the Contractor’s obligations regarding his programme of work and incorporated into the required method statements for workmanship and quality control.

# a)	Site establishment

i)	Site Plan

The site refers to an area with defined limits on which the project is located. The Contractor shall establish his construction camps, offices, workshops, staff accommodation and testing facilities on the site in a manner that does not adversely affect the environment. However, before any site establishment can begin, the Contractor shall submit to the ECO for his comments and to the Engineer for his approval, plans of the exact location, extent and construction details of these facilities and the impact mitigation measures the Contractor proposes to put in place.

The plans shall detail the locality as well as the layout of the waste management facilities for litter, kitchen refuse, sewage and workshop-derived effluents. The site offices should not be sited in close proximity to steep areas, as this will increase soil erosion. Preferred locations would be flat areas along the route. If the route traverses water courses, streams and rivers, it is recommended that the offices, and in particular the ablution facilities, aggregate stockpiles, spoil areas and hazardous material stockpiles are located as far away as possible from any water course. No camp establishment, including satellite camps, can be placed within 150 metres of an identified watercourse unless the Contractor has applied to DWS and received authorisation to do so. Regardless of the chosen site, the Contractor’s intended mitigation measures shall be indicated on the plan. The site plan shall have been submitted and approved before establishment commences. Detailed, electronic colour photographs shall be taken of the proposed site before any clearing may commence. These records are to be kept by the ECO and the Engineer for consultation during rehabilitation of the site in order that rehabilitation is, as a minimum, done to a standard similar to pre-construction activities.

ii)	Vegetation

The Contractor has a responsibility to inform his staff of the need to be vigilant against any practice that will have a harmful effect on vegetation.

The natural vegetation encountered on the site is to be conserved and left as intact as possible. Vegetation planted at the site shall be indigenous and in accordance with instructions issued by the Engineer. Only trees and shrubs directly affected by the works, and such others as may be indicated by the Engineer in writing, may be felled or cleared. In wooded areas where natural vegetation has been cleared out of necessity, the same species of indigenous trees as were occurring shall be re-established. Protected trees may not be removed without a permit from the Department of Forestry, Fisheries and Environment.

Contravention of a notice of listed protected tree species under the National Forests Act, 1998 is regarded as a first category offence that may result in a fine or imprisonment for a period up to three years, or to both a fine and imprisonment. The DEO must be conversant with the latest gazette of declared protected trees.

Rehabilitation shall be undertaken using only indigenous tree, shrub and grass species. Special attention shall be given to any search and rescue operation identified during the environmental assessment process and any removal to an on-site nursery for continuous nurturing and protection and later replanting.

Any proclaimed weed or alien species that propagates during the contract period shall be cleared by hand before seeding.

Fires shall only be allowed in facilities or equipment specially constructed for this purpose. The need for a firebreak shall be determined in consultation with the Engineer and the relevant authorities, and if required a firebreak shall be cleared and maintained around the perimeter of the camp and office sites.

iii)	Water management

Water for human consumption shall be available at the site offices and at other convenient locations on site.

All effluent water from the camp/office sites shall be disposed of in a properly designed and constructed system, situated so as not to adversely affect water sources (streams, rivers, pans, dams etc.). Only domestic type wastewater shall be allowed to enter this system.

iv)	Heating and cooking fuel

The Contractor shall provide adequate facilities for his staff so that they are not encouraged to supplement their comforts on site by accessing what can be taken from the natural surroundings. The Contractor shall ensure that energy sources are available at all times for construction and supervision personnel for heating and cooking purposes.

# b)	Sewage management

Particular reference in the site establishment plan shall be given to the treatment of sewage generated at the site offices, site laboratory and staff accommodation and at all localities on the site where there will be a concentration of labour. Sanitary arrangements should be to the satisfaction of the Engineer, the local authorities and legal requirements.

Safe and effective sewage treatment will require one of the following sewage handling methods: septic tanks and soak-aways, dry-composting toilets such as “enviro loos”, or the use of chemical toilets which are supplied and maintained by a specialist service provider. The type of sewage management will depend on the geology of the area selected, the duration of the contract and proximity (availability) of providers of chemical toilets. Should a soak-away system be used, it shall not be closer than 800 metres from any natural water course or water retention system. The waste material generated from these facilities shall be serviced on a regular basis. The positioning of the chemical toilets shall be done in consultation with the Engineer. Should a soak-away system be used, it shall not be closer than 800 metres from any natural water course or water retention system and shall be approved by the Engineer in consultation with the ECO.

Toilets and latrines shall be easily accessible and shall be positioned within walking distance from wherever employees are employed on the works. Use of the veld for this purpose shall not, under any circumstances, be allowed.

Outside toilets shall be provided with locks and doors and shall be secured to prevent them from blowing over. The toilets shall also be placed outside areas susceptible to flooding. The Contractor shall arrange for regular emptying of toilets and shall be entirely responsible for enforcing their use and for maintaining such latrines in a clean, orderly and sanitary condition to the satisfaction of the Engineer.

# c)	Waste management

The Contractor’s intended methods for waste management shall be outlined and implemented at the outset of the contract and shall be to the satisfaction of the Engineer. A waste inventory shall be drawn up of all waste streams that will possibly be generated by the site/project and an integrated approach shall be taken to its management. Records shall be kept of all waste disposed. Opportunities for avoiding, reducing, reusing and recycling of materials should be identified upfront, as should constraints for their implementation. All personnel shall be instructed to dispose of all waste in the proper manner.

i)	Solid waste

Solid waste shall be stored in an appointed area in covered, tip-proof metal drums or similar container for collection and disposal. Disposal of solid waste shall be at a licensed landfill site or at a site approved by the relevant authority in the event that an existing operating landfill site is not within reasonable distance from the project area. No waste shall be burned or buried at or near the project area.

ii)	Litter

No littering by construction workers shall be allowed and particular emphasis on litter control measures shall apply at stop/go facilities.

During the construction period, the various contractors’ facilities shall be maintained in a neat and tidy condition and the site shall be kept free of litter. At all places of work the Contractor shall provide litter collection facilities for later safe disposal at approved sites.

iii)	Hazardous waste

Hazardous waste such as oils shall be disposed of at an approved landfill site and proof of such disposal kept by the Contractor. Special care shall be taken to avoid spillage of bitumen products such as binders or pre-coating fluid to avoid water-soluble phenols from entering the ground or contaminating surface water.

Under no circumstances shall the spoiling of bituminous products on the site, over embankments, in borrow pits or any burying, be allowed. Unused or rejected bituminous products shall be returned to the supplier’s production plant. Any spillage of bituminous products shall be attended to immediately and affected areas shall be promptly reinstated to the satisfaction of the Engineer.

iv)	Construction and demolition waste

The opportunity for recycling and reuse of construction and demolition waste as fill for road embankments, land reclamation and drainage control must first be explored and take priority before the option of declaring these materials a ‘waste’.

The Contractor is encouraged to actively engage with authorities and landowners adjacent to the site and identify where such materials can be usefully deployed to repair existing environmentally damaged areas such as erosion dongas.

# d)	Control at the workshop

The Contractor’s management and maintenance of his plant and machinery will be monitored according to the criteria given below.

i)	Hazardous Material Storage

Petrochemicals, oils and identified hazardous substances shall only be stored under controlled conditions. All hazardous materials such as bitumen binders shall be stored in a secured, appointed area that is suitably fenced, bunded and has restricted entry. Storage of bituminous products shall only take place using suitable containers to the approval of the ECO and the Engineer.

The Contractor shall provide proof to the Engineer that relevant authorisation to store such substances has been obtained from the relevant authority. In addition, hazard signs indicating the nature of the stored materials shall be displayed on the storage facility or containment structure. Before containment or storage facilities can be erected, the Contractor shall furnish the Engineer with details of the preventative measures he proposes to install in order to mitigate pollution of the surrounding environment from leaks or spillage. The preferred method shall be a concrete floor that is bunded. Any deviation from the method will require proof from the relevant authority that the alternative method proposed is acceptable to that authority. The proposals shall also indicate the emergency procedures in the event of misuse or spillage that will negatively affect an individual or the environment.

ii)	Fuel and gas storage

The Contractor shall take cognisance of the limits set by legislation for the storage of fuels and acquire the necessary authorisation for storage capacity beyond these. An adequate bund wall, 110% of volume, shall be provided for fuel and diesel areas to accommodate any leakage spillage or overflow of these substances. The area inside the bund wall shall be lined with an impervious lining to prevent infiltration of the fuel into the soil. Any leakage, spillage or overflow of fuel shall be attended to without delay.

# Gas welding cylinders and LPG cylinders shall be stored chained in a secure, well-ventilated area exterior to any building wall.

iv)	Oil and lubricant waste

Used oil, lubricants and cleaning materials from the maintenance of vehicles and machinery shall be collected in a holding tank and sent back to the supplier. Water and oil should be separated in an oil trap. Oils collected in this manner, shall be retained in a safe holding tank and removed from site by a specialist oil recycling company for disposal at approved waste disposal sites for toxic/hazardous materials. Oil collected by a mobile servicing unit shall be stored in the service unit’s sludge tank and discharged into the safe holding tank for collection by a specialist oil recycling company.

Drip trays shall be used to collect any lubricants or fuel spilled where any vehicle and machinery are repaired or refuelled. The lubricants and fuel collected shall be handled as specified above.

All used filter materials shall be stored in a secure bin for disposal off site. Any contaminated soil shall be removed and replaced. Soils contaminated by oils and lubricants shall be collected and disposed of at a facility designated by the local authority to accept contaminated materials.

# e)	Clearing the site

In all areas where the Contractor intends to or is required to clear the natural vegetation and soil, either within the road reserve, or at designated or instructed areas outside the road reserve, a plan of action shall first be submitted to the Engineer for his approval. Working areas shall be clearly defined and demarcated on site to minimise the construction footprint. ‘No-go- areas’ and other sensitive areas shall also be clearly demarcated on site, and staff must be made aware of them.

The plan of action shall contain a photographic record and chainage/land reference of the areas to be disturbed. This shall be submitted to the Engineer for his records before any disturbance/stockpiling may occur. The record shall be comprehensive and clear, allowing for easy identification during inspections.

# f)	Soil management

i)	Topsoil

Topsoil shall be removed from all areas where physical disturbance of the surface will occur and shall be stored and adequately protected. The contract will provide for the stripping and stockpiling of topsoil from the site for later re-use. Topsoil is the natural soil covering, including all the vegetation and organic matter. Depth may vary at each site. The areas to be cleared of topsoil shall include all storage areas. All topsoil stockpiles and windrows shall be maintained throughout the contract period in a weed-free condition. Weeds appearing on the stockpiled or windrowed topsoil shall be removed by hand. Soils contaminated by hazardous substances shall be disposed of at an approved waste disposal site. The topsoil stockpiles shall be stored, shaped and sited in such a way that they do not interfere with the flow of water to cause damming or erosion, or itself be eroded by the action of water.

The Contractor shall ensure that no topsoil is lost due to erosion – either by wind or water. Areas to be top-soiled and grassed shall be done so systematically to allow for quick cover and reduction in the chance of heavy topsoil losses due to unusual weather patterns. The Contractor’s programme shall clearly show the proposed rate of progress of the application of topsoil and grassing. The Contractor shall be held responsible for the replacement, at his own cost, for any unnecessary loss of topsoil due to his failure to work according to the progress plan approved by the Engineer. The Contractor’s responsibility shall also extend to the clearing of drainage or water systems within and beyond the boundaries of the road reserve that may have been affected by such negligence.

ii)	Subsoil

The subsoil is the layer of soil immediately beneath the topsoil. It shall be removed, to a depth instructed by the Engineer, and if not used for road building it shall be stored and maintained separately from the topsoil so that neither stockpile is contaminated by the other. This soil shall be used for rehabilitation purposes by first spreading it over the excavated slopes without interfering with or contaminating the stockpiled topsoil.

Whilst in stockpile it shall be maintained free from erosion and weed infestation in the same way as for topsoil stockpile maintenance.

# g)	Earthworks and layerworks

This section includes all construction activities that involve the mining of all materials, and their subsequent placement, stockpile, spoil, treatment or batching, for use in the permanent works, or temporary works in the case of deviations. Before any stripping prior to the commencement of construction, the Contractor shall have complied with the requirements of this EMP. In addition, the Contractor shall take cognisance of the requirements set out below.

# i)	Quarries and borrow pits

The Contractor’s attention is drawn to the requirement of the Department of Mineral Resources, that before entry into any quarry or borrow pit, an Environmental Authorisation for the establishment, operation and closure of a quarry or borrow pit shall have been approved by the Department where applicable. It is the responsibility of the Contractor to ensure that he is in possession of the authorisation prior to entry into the quarry or borrow pit. The conditions imposed by the relevant authorisation are legally binding on the Contractor and may be more extensive and explicit than the requirements of this specification. In the event of any conflict occurring between the requirements of the specific authorisation and this EMP, the former shall apply.

ii)	Excavation, hauling and placement

The Contractor shall provide the ECO and the Engineer with detailed plans of his intended construction processes prior to starting any cut or fill or layer. The plans shall detail measures by which the impacts of pollution (noise, dust, litter, fuel, oil and sewage), erosion, vegetation destruction and deformation of landscape will be prevented, contained and rehabilitated. Particular attention shall also be given to the impact that such activities will have on the adjacent built environment. The Contractor shall demonstrate his “good housekeeping”, particularly with respect to closure at the end of every day so that the site is left in a safe condition.

iii)	Spoil sites

The Contractor shall be responsible for the safe siting, operation, maintenance and closure of any spoil site he uses during the contract period, including the defects notification period. This shall include existing spoil sites that are being re-entered. Before spoil sites may be used proposals for their locality, intended method of operation, maintenance and rehabilitation shall be given to the ECO for his/her comments and to the Engineer for his approval. The location of these spoil sites shall have signed approval from the affected landowner before submission to the ECO and the Engineer. No spoil site shall be located within 50m of any watercourse. A photographic record shall be kept of all spoil sites for monitoring purposes. This includes before the site is used and after re-vegetation.

The use of approved spoil sites for the disposal of any waste shall be prohibited. Spoil sites will be shaped to fit the natural topography. Depending on availability these sites shall receive a minimum of 75mm topsoil and be grassed with the recommended seed mixture. Appropriate grassing measures to minimise soil erosion shall be undertaken by the Contractor. This may include both strip and full sodding. The Contractor may motivate to the Engineer for other acceptable stabilising methods. The Engineer may only approve a completed spoil site at the end of the defects notification period upon receipt from the Contractor of a landowner’s clearance notice.

iv)	Stockpiles

The Contractor shall plan his activities so that materials excavated from borrow pits and cuttings, in so far as possible, can be transported direct to and placed at the point where it is to be used. However, should temporary stockpiling become necessary, the areas for the stockpiling of excavated and imported material shall be indicated and demarcated on the site plan submitted in writing to the Engineer for his approval. The Contractor’s proposed measures for prevention of environmental damage, containment and subsequent rehabilitation shall also be submitted.

The areas chosen shall have no naturally occurring indigenous trees and shrubs present that may be damaged during operations. Care shall be taken to preserve all vegetation in the immediate area of these temporary stockpiles. During the life of the stockpiles the Contractor shall at all times ensure that they are positioned and sloped to create the least visual impact, constructed and maintained so as to avoid erosion of the material and contamination of surrounding environment and kept free from all alien/undesirable vegetation.

After the stockpiled material has been removed, the site shall be re-instated to its original condition. No foreign material generated/deposited during construction shall remain on site. Areas affected by stockpiling shall be landscaped, top soiled, grassed and maintained at the Contractor’s cost until clearance from the Engineer and the landowner is received.

Material milled from the existing road surface that is temporarily stockpiled in areas approved by the Engineer within the road reserve, shall be subject to the same condition as other stockpiled materials. Excess materials from windrows, in situ milling or any leftover material from road construction activities may not be swept off the road and left unless specifically instructed to do so in the contract documentation or under instruction from the Engineer.

The ECO shall comment on and the Engineer shall approve the areas for stockpiling and disposal of construction rubble before any operation commences and shall approve their closure only when they have been satisfactorily rehabilitated.

v)	Blasting activities

Wherever blasting activity is required on the site (including quarries and/or borrow pits) the Contractor shall rigorously adhere to the relevant statutes and regulations that control the use of explosives.

h)	On site plant

i)	Crusher, screening plants and concrete batching plants

Crushing plants and concrete batching plants, whether sited inside or outside of defined quarry or borrow pit areas, shall be subject to the requirements of the applicable industrial legislation that governs gas and dust emissions into the atmosphere. Such sites will be the subject of regular inspections by the relative authorities during the life of the project. In addition, the selection, entry onto, operation, maintenance, closure and rehabilitation of such sites shall be the same as for those under section C1007(g)(i) of this EMP, with the exception that the Contractor shall provide additional measures to prevent, contain and rehabilitate against environmental damage from toxic/hazardous substances. In this regard the Contractor shall provide plans that take into account such additional measures as concrete floors, bunded storage facilities, linings to drainage channels and settlement dams. Ultimate approval of these measures shall be from the relevant authority, as shall approval of closure. The Engineer will assist the Contractor in his applications to the relevant authority.

Screening activities shall be undertaken so that dust and noise is minimised. This can be done by carefully choosing the site for the activity, and by using slightly damp material.

Effluent from concrete batch plants and crusher plants shall be reused where possible or treated in a suitable designated sedimentation dam to the legally required standards to prevent surface and groundwater pollution. The designs of such a facility should be submitted to the Engineer for approval.

ii)	Asphalt Plant

Asphalt plants shall be subject to the applicable legislation that governs establishment and operation of batching plants. The Contractor shall be responsible to obtain the necessary permit from the relevant authority.

Operation of the plant shall conform to the same requirements as for a crushing plant or concrete batching plant under C1007(h)(i) above.

###### C1008	AREAS OF SPECIFIC IMPORTANCE

Any area, as determined and identified within the project documents as sensitive or of special interest within the site shall be treated according to the express instructions contained in these specifications or the specific environmental authorisation, as well as the approved EMPr. The Contractor may offer alternative solutions to the Engineer in writing should he consider that construction will be affected in any way by the hindrance of the designated sensitive area or feature. However, the overriding principle is that such defined areas requiring protection should not be changed. Every effort to identify such areas within the site will have been made prior to the project going out to tender. The discovery of other sites with archaeological or historical interest that have not been identified shall receive ad hoc treatment.

a)	Archaeological sites

If an artefact on site is uncovered, work in the immediate vicinity shall be stopped immediately. The Contractor shall take reasonable precautions to prevent any person from removing or damaging any such article and shall immediately upon discovery thereof inform the Engineer of such discovery. The South African Heritage Resource Agency (SAHRA) is to be contacted, and a SAHRA-registered archaeological consultant may undertake the necessary work involved in confirming the find and advising on how it should be preserved or removed. Work may only resume once clearance is given in writing by the archaeologist. (Read with FIDIC condition of contract clause 4.24)

If a grave or midden is uncovered on site then all work in the immediate vicinity of the graves/middens shall be stopped, and the Engineer informed of the discovery. The South African Heritage Resource Agency and the South African Police Services (SAPS) should be contacted and in the case of graves, arrangements made for an undertaker to carry out exhumation and reburial. The undertaker will, together with SAHRA, be responsible for attempts to contact family of the deceased and for the place where the exhumed remains can be re-interred.

###### C1009	Rehabilitation

# The Contractor shall be responsible for the re-establishment of grass within the road reserve boundaries for all areas disturbed during construction. This includes, for example, service roads, stockpile areas, stop/go facilities, windrows and wherever material generated for, or from, construction has to be stored temporarily, and designated or instructed areas outside the road reserve. It also includes the area where site offices were erected which may require rehabilitation at the end of the contract. All construction material, including concrete slabs and barbecue (braai) areas shall be removed from the site on completion of the contract unless written approval from the relevant landowner demonstrates it is to be left in place.

Responsibility for re-establishment of vegetation shall extend until expiry of the defects notification period. However, SANRAL reserves the right to continue holding retention monies (or not releasing guarantees in lieu of retention) depending upon the state of cover at the end of the defects notification period. Such extension may continue until closure of the relevant quarry or borrow pit has been secured,

Rehabilitation of affected areas should be undertaken as early as possible when the relevant activities are done in order to reduce further environmental damage. All re-vegetation should be undertaken using indigenous vegetation. The standard of rehabilitation should be to the satisfaction of the Engineer and the relevant authorities. The Department of Minerals Resources will only issue closure certificates for borrow pits and quarries when they are satisfied with the rehabilitation undertaken. It should also be noted that in some cases there is a requirement for a final environmental audit covering the extent of the project.

###### C1010	RECORD KEEPING

The Engineer and the DEO will continuously monitor the Contractor’s adherence to the approved impact prevention procedures and the DEO shall submit regular written reports to the ECO and to the Engineer at least once a month. The DEO will report the environmental compliance performance of the project at regular site meeting. The Engineer shall issue to the Contractor a notice of non-compliance whenever transgressions are observed. The DEO shall document the nature and magnitude of the non-compliance in a designated register, the action taken to discontinue the non-compliance, the action taken to mitigate its effects and the results of the actions. The non-compliance shall be documented and reported to the Engineer in the monthly report.

Copies of all authorisations shall be kept on site and made available for inspection by visiting officials from SANRAL, relevant authorities or internal/external auditors.

###### C1011	COMPLIANCE AND PENALTIES

The Contractor shall act immediately when a notice of non-compliance is received and correct whatever is the cause for the issuing of the notice. Complaints received regarding activities on the construction site pertaining to the environment shall be recorded in a dedicated register and the response noted with the date and action taken. This record shall be submitted with the monthly reports and an oral report given at the monthly site meetings.

Any non-compliance/omissions with the procedures in this EMP, environmental authorisations and the approved EMPr constitute a breach of the Conditions of Contract. Regulatory financial penalties imposed on SANRAL shall be passed onto the defaulting parties.

###### C1012	PROJECT SPECIFIC CONDITIONS

Notes to compiler:

- The Contractor will be bound by the terms of this EMP regardless that some of them might not be part of an EMPr authorised by a competent authority.

- It is intended that this standard EMP be the base document for the development of the draft of each EMPr that is to accompany each application to the relevant competent authority.

- The EAP or ECO’s identification of an activity requiring inclusion of mitigation or action in the EMPr should preferably use verbatim the relative text in this EMP. However, if the EAP can show that his/her version is an improvement then the Engineer in liaison with the relevant project manager should be aware of the amendment and approve the change.

- It is preferable to improve this EMP than create different versions of the same mitigation. Proposals for improvement are encouraged.

- This section of the EMP should be used by the EAP to record site specific activities and proposed mitigation measures. A graphic display of these will be a useful visual aid.

- The EAP must ensure that this section is project-specific and complies with the relevant regulations.

SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

# SECTION D (PART D): C3.4 STAKEHOLDER AND COMMUNITY LIAISON, AND TARGETED LABOUR AND TARGETED ENTERPRISES UTILISATION AND DEVELOPMENT

PART D (SECTION D):	STAKEHOLDER AND COMMUNITY LIAISON, AND TARGETED LABOUR AND TARGETED ENTERPRISES UTILISATION AND DEVELOPMENT

TABLE OF CONTENTS	PAGE

D1001	SCOPE	C241

D1001.01	Principles for Project Liaison, Sub-contracting, and Labour Sourcing in SANRAL Projects (Fourteen Point Plan)	C241

D1002	DEFINITIONS AND APPLICABLE LEGISLATION	C242

D1002.01	Definitions	C242

D1002.02	Applicable Legislation, Regulations and Standards	C248

D1003	TARGET GROUP PARTICIPATION	C248

D1003.01	Objectives of Target Group Participation	C248

D1003.02	Targeted Labour Database	C249

D1003.03	Targeted Enterprise Database	C249

D1003.04	Contract Participation Goal (CPG)	C250

D1003.05	Contract Participation Performance (CPP)	C251

D1003.06	Accredited Registration	C253

D1003.07 	Contractor’s Responsibility	C253

D1004	STAKEHOLDER AND COMMUNITY liaison AND SOCIAL FACILITATION	C253

D1004.01	Purpose of Stakeholder and Community Liaison	C253

D1004.02	Contractor’s Responsibilities in Stakeholder and Community Liaison	C253

D1004.03 	Project Liaison Committee (PLC)	C254

D1004.04	Project Liaison Officer	C259

D1005	MOBILISATION PERIOD	C261

D1005.01	Purpose of the Mobilisation Period	C261

D1005.02 	Duties of the Contractor	C262

D1006	THE ROLE OF THE ENGINEER	C263

D1006.01	Duties During the Design Phase	C263

D1006.02	Duties During the Design Build Operate Phase	C264

D1007	TENDER PROCESS FOR TARGETED ENTERPRISES	C264

D1007.01	Targeted Enterprise (TE) Procurement Coordinator	C265

D1007.02	Procedures for Targeted Enterprises Sub-contracting	C265

D1008	GENERAL RESPONSIBILITIES OF THE CONTRACTOR TOWARDS TARGETED ENTERPRISES	C274

D1008.01	Targeted Enterprise (TE) Operations Manager	C274

D1008.02	General Obligations	C275

D1008.03	Sub-contract Agreements	C276

D1008.04	Payment of Targeted Enterprises	C277

D1008.05	Quality of Work and Performance of Targeted Enterprises	C277

D1008.06	Dispute Avoidance and Resolution Procedures	C278

D1009	WORK suitable for execution BY TARGETED ENTERPRISES	C279

D1010	TRAINING, COACHING, GUIDANCE, MENTORING and assistance	C280

D1010.01	Purpose of the Training and Skills Development Programme(s)	C280

D1010.02	Skills Audit and Analysis	C280

D1010.03	Developing the Training and Skills Development Programme	C280

D1010.04	The Training Service Provider (Not Applicable)	C281

D1010.05	Training and Skills Development Programme:  General Requirements	C281

D1011	LABOUR ENHANCED CONSTRUCTION (Not applicable)	C287

D1012	COMMUNITY DEVELOPMENT	C287

D1012.01	Corporate Social Investment (CSI)	C287

D1013	MEASUREMENT AND PAYMENT	C287

D10.01	Target Group Participation	C287

D10.02	Stakeholder and Community Liaison and Social Facilitation	C287

D10.03	Tender Process for Targeted Enterprises	C288

D10.04 	Responsibilities of the Contractor towards Targeted Enterprises	C289

D10.05	Construction Works by Targeted Enterprises	C289

D10.06	Training, coaching, guidance, mentoring and assistance	C290

D1001	SCOPE

Section D of the Specifications describes the structured engagement with project Stakeholders and affected Communities to the project.  It also guides the selection and the enhanced utilisation and development of Targeted Labour and Targeted Enterprises.

Note to Tenderer.

This contract may not have a stand-alone PLC as required in terms of Item D1004. For that purpose, it will be incorporated into Employer’s established PLC for the contract area (as per clause C3.4.4(e) of the Contract Data).  The Contractor is obliged to participate in the PLC activities related or having a direct bearing on this contract and fulfil the Contractor’s responsibilities as stipulated below.

Reference to CIDB grading shall apply to work activities where CIDB registration is a requirement such as civil construction, electrical works and building works.

D1001.01	Principles for Project Liaison, Sub-contracting, and Labour Sourcing in SANRAL Projects (Fourteen Point Plan)

The scope of the work described in this Section D of the Specifications shall be based on the Employer’s 14 principles for project liaison, sub-contracting, and labour sourcing in all SANRAL projects, which are stipulated below:

- SANRAL will establish a Project Liaison Committee (PLC) for every project to create a platform for project communication with the aim to facilitate successful works execution, subcontracting, procurement, participation with MOU partners, supply of material, services and goods, and employment facilitation.

- SANRAL will chair PLCs and provide secretarial support through the Consulting Engineer or its Agent.  Representation on the PLC will comprise SANRAL, the Contractor, the Consulting Engineer or SANRAL’s Agent, business representatives, traditional authority representatives, provincial and municipal government representatives (not politicians), community representatives, and any other critical local stakeholder that may be deemed necessary by SANRAL.  While serving on the PLC, PLC members must declare any conflict of interest and recuse themselves if requested by the PLC Chairperson.

- The selection of a Project Liaison Officer (PLO), who will be employed by the Consulting Engineer, must be acknowledged, and supported by the PLC.

- The definition of a target area (sometimes referred to as a local area or traffic area) will be determined by SANRAL in consultation with the PLC.

- The setup of databases for contractors, sub-contractors, consultants, and suppliers will be conducted with the input and support of the PLC.  The final database will be disseminated to the PLC.  The entities on the database must be assisted by the Consulting Engineer and the Contractor to be compliant with the relevant legislation required to conduct work for a SANRAL project.

- The setup of databases for local labour in the target area will be done with the input and support of the PLC.  The final list will be disseminated to the PLC.  Entities on the database must be registered on the National Treasury Central Supplier Database (CSD).  A system of labour selection from the database must be agreed at the PLC.

- The databases for sub-contracting will be handed over to the Contractor for open tender processes.  The labour database will be disseminated to the PLC and handed over to the Contractor to use for recruitment of local labour.

- Tender processes for sub-contracting must be conducted by the Contractor using government principles (e.g., public opening of received bids, announcement of bidders and prices).  Winning bidders shall be tabled, by the Contractor, in the PLC meeting for information purposes.

- Appeals to the tender process must be escalated to SANRAL for an independent review which will be facilitated by the Transformation Unit.

- Capability assessments of sub-contractors and suppliers will be done with the input and support of the PLC, prior to the sub-contract tender stage commencing, to identify any deficiencies in skills and experience.  For labour, skills assessments will be done at recruitment stage.

- Sub-contractor development support and training must be coordinated and conducted, prior to the sub-contract tender stage commencing, with the input and support of the PLC.

- The PLC may identify works areas that are deliverable by local service providers, and areas where capabilities are not available locally.  All works areas where capabilities are not available locally will be imported and local service providers will be given an opportunity to learn.

- The PLC and Consulting Engineer must ensure that formal contracting arrangements between the main contractor and the sub-contractor are in place in all projects.

- Communication will be streamlined through the PLC and used to manage expectations of local business and communities.

These principles must be applied to facilitate better project level liaison with project Stakeholders and affected Communities.  In addition, these principles serve to ensure communication and transparency in the execution of the Works and to facilitate inclusivity in the allocation of projects to benefit black business and local communities.

D1002	DEFINITIONS AND APPLICABLE LEGISLATION

The definitions and legislation listed below informs the requirements of this Section D of the Specifications for Stakeholder and Community Liaison, Targeted Labour employment and Targeted Enterprise sub-contracting.

D1002.01	Definitions

Unless inconsistent with the context, in these specifications, the following words, terms or expressions shall have the meanings hereby assigned to them:

- Business Coaching

Business coaching establishes an atmosphere of mutual trust, respect, responsibility, and accountability to motivate the emerging business owner and his team.  To that end, the business coach must conduct an ethical and competent practice, based on appropriate professional experience and business knowledge.

- Community

South African Citizens, as defined in terms of the South African Citizenship Act, 1995 (Act 88 of 1995), who permanently reside within the Target and Project Area(s) of the project.

- Contract Participation

A process by which the Employer implements Government’s objectives by setting targets to enhance Targeted Labour and Targeted Enterprises’ utilisation and development, which the Contractor shall achieve as a minimum.

- Contract Participation Goal (CPG)

- In the case of Targeted Enterprises, including manufacturers and suppliers, the amount equal to the value of goods, services and works for which the principal Contractor contracts to engage Targeted Enterprises in the performance of the Contract, expressed as a percentage of the tender value excluding escalation, contingency and value added tax associated with the targeting strategy that is identified in the Specification Data; or

- In the case of Targeted Labour:

  - the sum of the wages and allowances, for which the principal Contractor, Sub-contractor, or Targeted Enterprises contract to engage Targeted Labour in the performance of the Contract, expressed as a percentage of the contract amount associated with the targeting strategy that is identified in the Specification Data; or

  - the amount equal to the person days worked for which the principal Contractor, Sub-contractors or Targeted Enterprises contract to engage Targeted Labour expressed as a percentage of the total person days worked associated with the targeting strategy that is identified in the Specification Data.

- Contract Participation Goal Plan (CPG Plan)

The plan which outlines how the Contractor intends to achieve the various CPG targets as stated in the Contract Data and includes the detail of the Targeted Enterprise work programme, as well as the contents and value of the work packages.  See Annexure X1 for the CPG Plan template.

- Contract Participation Performance (CPP)

The measure of the Contractor’s progress in achieving the CPG.

- Contract Skills Development Goals (CSDG)

The number of hours or head count of skills development opportunities that a Contractor contracts to provide in relation to work directly related to the contract or order up to:

- completion in the case of a professional service contract,

- the end of the service period in the case of a service contract, and

- practical completion in the case of an engineering and construction works contract.

- Designated Group

Unless otherwise permissible in terms of procurement regulations or the PPPFA, “Designated Group” means:

- black designated groups,

- black people,

- women, or

- people with disabilities.

- Domestic Sub-contractors

A Domestic Sub-contractor is one in whose selection and appointment the Employer traditionally plays no part in other than simply giving consent when that is required under the terms of the main contract.  The appointment of the sub-contractor is treated as something entirely for the benefit of Main Contractor and is a purely "domestic matter".

- Final Contract Value

Final Contract Value as defined under Section D1003.04 - Contract Participation Goal (CPG) of the Specifications, also means Contract Price as defined in FIDIC, sub-clause 1.1.4.2, (excluding CPA, adjustments for reduced payments, Rise and Fall adjustments, penalties, and VAT)

- Guidance

Guidance is anticipating where one might go wrong, or where one is doing a task in a complicated, inefficient, or ineffective way, and giving help, advice, and direction as to how to achieve a better result. Guidance is mostly given by a person in the direct reporting line but can be given by anyone.  Guidance is not imparting skills but suggesting ways to improve performance.

- Labour

Persons:

- who are employed by the Contractor or a Sub-contractor in the performance of the Contract, and

- whose monthly earnings are derived from hours worked for a fixed hourly rate which is adjusted from time to time by legislation (as a statutory minimum) and the Contractor’s or Sub-contractor’s employment policies, but

- who are not Targeted Labour as stated in the Specification Data.

The personnel employed by the suppliers of goods and material are not defined as “Labour” for the purposes of this Contract.

- Mentoring

Mentoring is a professional relationship in which an experienced businessperson assists another by giving advice and imparting their knowledge in developing special skills and knowledge that will enhance the less experienced businessperson’s professional and personal growth.  The objective is to equip the emerging business owner and his team to improve their decision-making skills, being focussed and make positive progress quickly.

- Mobilisation Period

The period between the Commencement Date and the date of Access to Site, which period (duration) is stated in the Contract Data.  This part of Section D of the Specifications describes the requirements of the Mobilisation Period.

- Project Area

The area through which the road under construction traverse or which is adjacent to and/or in proximity to project operations.

Based on market research and/or requisite resources availability, Project Areas other than defined above may be identified where preference would be given to Targeted Enterprises for sub-contracting opportunities.

- Project Liaison Committee (PLC)

The Committee that represents the Employer, Engineer, Contractor, project Stakeholders and the Communities affected by the project. It is important to note that:

- elected and/or nominated political office bearers shall not be members of the PLC, and

- the Engineer and Contractor becomes members of the PLC on their appointment and participate in the Committee within the scope of their respective roles and responsibilities.

- Project Liaison Officer (PLO)

The person who acts as the liaison officer for the project.  The PLO facilitates the selection of Targeted Labour to be employed by the Contractor and attends to the day-to-day project, Stakeholder, and Community matters that impact on the parties to the PLC.

- Stakeholders

Any Stakeholder listed in the Employer’s Communication Policy who is affected by the Employer’s operations in the Project Area(s) and/or who has an interest or concern in the project, either as a decision maker, participant or affected party and may include, amongst others, the following entities:

- Relevant Provincial departments.

- Relevant Municipal departments.

- Traditional authorities.

- Community interest groups.

- Organised youth representation.

- Organised women representation.

- Organised disabled people representation.

- Other structured community groups such as religion, education, farming, etc.

- Local transport industry forums, e.g., Bus and taxi.

- Business sector forums.

- Road user forums.

- Environmental interest groups.

- Road safety interest groups.

- Any other recognised relevant and representative structure.

- Sub-contractor

An entity appointed by the Contractor to execute a portion of the Works as defined in the Conditions of Contract under FIDIC subclause 1.1.2.8.  This includes both Domestic Sub-contractors and Targeted Enterprises.

- Target Area

The geographic area defined in the Specification Data for Targeted Labour, and which typically are:

- one or more Provinces,

- one or more Metropolitan or District Municipalities,

- one or more Local Municipalities,

- one or more Wards that are predominantly located within the Project Area, or

- one or more of the areas listed in the definition of Designated Groups.

- Targeted Enterprise

A Targeted Enterprise is an entity to which the Contractor sub-contracts a percentage of the contract value as a condition of contract, and which is:

- an EME or QSE which is at least 51% owned by black people; or

- an EME or QSE which is at least 51% owned by black people who are youth; or

- an EME or QSE which is at least 51% owned by black people who are women; or

- an EME or QSE which is at least 51% owned by black people with disabilities; or

- an EME or QSE which is at least 51% owned by black people who are military veterans; or

- an EME or QSE which is 51% owned by black people living in rural or underdeveloped areas or townships; or

- a cooperative which is at least 51% owned by black people; or

In addition, Targeted Enterprises must be:

  - CIDB registered where applicable,

  - registered with National Treasury’s Central Supplier Database,

  - tax compliant prior to award of the sub-contract, and

  - COIDA compliant prior to award of the sub-contract where applicable.

Targeted Enterprises are also Sub-contractors as defined in the Conditions of Contract under FIDIC subclause 1.1.2.8.

- Targeted Enterprise Operations Manager (TE Operations Manager)

The appointed ,  staff member or sub-service provider appointed by the Contractor to develop, implement, and monitor the training, development and support of Targeted Labour and Targeted Enterprises as and when required.  The Targeted Enterprise Operations Manager also mentors, guides and coaches the Targeted Enterprises.

- Targeted Enterprise Monitor

The Targeted Enterprise Monitor is an independent service provider, or individual, appointed by the Employer’s Transformation Unit, to audit the Contractor and his TE Construction Manager’s activities with respect to their obligations to Targeted Enterprises.

- Targeted Enterprise Procurement Coordinator (TE Procurement Coordinator)

The staff member or sub-service provider appointed by the Contractor to facilitate the procurement of Targeted Enterprise sub-contractors.

- Target Group

It is a group of entities and/or persons selected from the Designated Group as defined in the in the tender document, and may include both Targeted Enterprises and Targeted Labour.

- Targeted Labour

Persons:

  - who are unemployed, and

  - who are then employed by the Contractor or a Sub-contractor (including Targeted Enterprises) in the performance of this Contract, and

  - whose monthly earnings are derived from hours worked for a fixed hourly rate which is adjusted from time to time by legislation (as a statutory minimum) and the Contractor’s or Sub-contractor’s or Targeted Enterprise’s employment policies, and

  - permanently reside in the Target Area(s) or who are recognized as being residents of the Target Area(s) based on identification and association with, and recognition by, the residents of the Target Area(s), and

  - who are stated as being Targeted Labour in the Specification Data.

The personnel employed by the suppliers of goods and material are not defined as “Targeted Labour” for the purposes of this Contract.

- Trainee Targeted Enterprise

A Targeted Enterprise as defined in this Section D of the Specifications, but which is selected and sub-contracted as a Trainee in terms of the Community Development Project associated with this Contract.

- Training

Training refers to the process of teaching a Trainee, usually in a classroom or simulated work environment situation where principles, theory, knowledge, and skills are taught, and demonstrations are given.  Assignments are set to ensure that the Trainee can apply what has been taught.  Training is done by a specialist in the subject, and who is qualified and accredited to train.  The objective is to improve the competency of the Trainee.

- Training and Skills Development Programme

The programme which outlines how the Contractor intends to achieve the CSDG targets, as per Section D1010 of the Specifications and in line with the CIDB Standard for Developing Skills through Infrastructure Contracts (refer to latest version on cidb.org.za), by applying the various training methods described in Section D1010 of the Specifications.

- Nominated Subcontractor

Means the Contractor for the Design Build, Operations and Maintenance of the Toll System for the Operations and Maintenance of Toll Plazas on the N1 North Toll Road (this contract) as defined in Part C1.

- Main Contractor

Means the Contractor for the Operations and Maintenance of Toll Plazas on the N1 North Toll Road as defined in Part C1.

D1002.02	Applicable Legislation, Regulations and Standards

The following Acts, as amended from time to time, are predominant amongst those which apply to the Road Tolling/Construction Industry and are listed here for reference purposes only:

- The Constitution of South Africa.

- Public Finance Management Act, 1999 (Act No. 1 of 1999).

- Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000) and its latest applicable regulations.

- Construction Industry Development Board Act, 2000 (Act No. 38 of 2000).

- Broad-Based Black Economic Empowerment Act, 2003 (Act No. 53 of 2003).

- The South African National Roads Agency Limited and National Roads Act, 1998 (Act No. 7 of 1998).

- The Skills Development Act, 1998 (Act No. 97 of 1998).

- The Skills Development Levies Act, 1999 (Act no. 9 of 1999).

- The amended Construction Sector Codes published in Notice 931 of 2017 of Government Gazette No. 41287 on 1 December 2017 by the Department of Trade and Industry.

- The amended Codes of Good Practice published in Notice 303 of 2019 of Government Gazette No. 42496 on 31 May 2019 by the Department of Trade, Industry and Competition.

- The Information and Communication Technology (ICT) Sector Codes (Published in Notice 1387 of Government Gazette No. 40407 of 7 November 2016).

- Financial Sector (Published in Notice 1325 of Government Gazette No. 41287 of 1 December 2017).

- The Integrated Transport Sector Codes (Published in Notice 1162 of Government Gazette No. 32511 of 21 August 2019).The National Small Enterprises Act, 1996 (Act 102 of 1996) as amended.

The following Standards and Practice Notes, as amended from time to time, are applicable in terms of Targeted Labour and Targeted Enterprises and are used fully or portions thereof in this Section D of the Specifications:

- SANS 10845:  2015, Parts 5, 7 and 8; and

- CIDB Standard for Contract Participation Goals for Targeted Enterprises and Labour through Construction Works Contracts (refer to latest version on www.cidb.org.za).

D1003	TARGET GROUP PARTICIPATION

This part of Section D of the Specifications describes the Employer’s requirements for the establishment of Target Group databases from which participants in the project will be selected for employment and sub-contracting.

It also describes the measurement of, and penalties or bonus to be applied, with respect to the CPG as defined in the Specification Data.

D1003.01	Objectives of Target Group Participation

Amongst others, the key objectives of Government are to extend economic opportunities and build entrepreneurial capacity in rural and underdeveloped areas and townships by:

- optimising the utilisation of local resources in the Project Area,

- developing these local resources in the execution of the project, and

- maximising the amount of funds retained within the Project Area.

To give effect to these objectives the Contractor shall, over the full duration of the contract, from site establishment up to the completion of the works:

- employ Targeted Labour from the Target Area(s) as stated in the Specification Data, and

- sub-contract Targeted Enterprises as stated in the Specification Data, and

- give preference to Targeted Enterprises which are from rural and underdeveloped areas and townships within the Project Area(s).

D1003.02	Targeted Labour Database

A system for the recruitment of Targeted Labour shall be agreed with the PLC prior to the commencement of labour recruitment.  This system shall be fair and transparent.

Based on the system for recruitment, a Targeted Labour Database shall be compiled by the Contractor, with the assistance of the PLO and the input and support of the PLC, for the Target Area(s) as stated in the Specification Data.  If necessary, the assistance of the Department of Labour may be called upon to provide a labour database of labourers with the required skills and within the required designated groups and Target Area.  Once the Database has been disseminated to the PLC it shall be utilised to facilitate the selection of Targeted Labour as per the resources and skills required by the Contractor during the different construction stages.

The Targeted Labour Database shall be updated as and when required to reflect new employment seekers in the labour market.

Only Labour recruited from the Targeted Labour Database will be measured for Contract Participation Performance (CPP).

D1003.03	Targeted Enterprise Database

The Contractor shall, with the assistance and inputs of the PLC, compile a Targeted Enterprise Database from which Targeted Enterprises shall be sub-contracted to construct portions of the work as described in this part of Section D of the Specifications.

      - Market Analysis and Requisite Resources Availability Audit

The Contractor shall conduct a market analysis and requisite resources availability audit to determine the availability, expertise, abilities, and proficiency of Targeted Enterprises in the Project Area.

To inform the market analysis and requisite resources availability audit, the Contractor shall, as a minimum, use the National Treasury’s Central Supplier Database (CSD) which can be obtained from the Employer’s Supply Chain Management department via the Project Manager, as well as the CIDB contractor database (if applicable).

The market analysis and requisite resources availability audit, and all updates thereof for the duration of the Contract, shall be submitted to the Engineer and the Employer’s Project Manager in a format acceptable to the Employer.

Following the market analysis and a requisite resources availability audit, the Contractor shall apply the CPG Target Group criteria in the Specification Data to compile a preliminary Targeted Enterprise Database (see D1003.03(c) below).

      - Call for an Expression of Interest

In addition to the CSD and the CIDB database (for works where cidb registration is required), the Contractor shall call for an expression of interest from Targeted Enterprises in the Project Area.  The call for an expression of interest shall outline the anticipated eligibility, functionality, preference, and compliance criteria, as well as the anticipated Works content.

      - Preliminary Targeted Enterprise Database

Based on the information obtained from the CSD, CIDB and the call for an expression of interest, the Contractor shall compile a Preliminary Targeted Enterprise Database.

The purposes of the Preliminary Targeted Enterprise Database are:

    - for the Contractor to determine if the required resources and skills to execute the identified Targeted Enterprise work packages are available in the Project Area(s),

    - for the PLC to verify that Targeted Enterprises on the Preliminary Targeted Enterprise Database are authentic in terms of the Specification Data and other Database criteria, and

    - for the PLC to alert prospective Targeted Enterprises that are not on the Preliminary Database of the opportunity.

Based on the market analysis and requisite resources availability audit, and the information obtained from the call for an expression of interest, additional criteria for the Preliminary Targeted Enterprise Database may be tabled by the PLC to the Contractor to ensure Target Group participation as intended by the Employer.

      - Final Targeted Enterprise Database

Once the Preliminary Targeted Enterprise Database has been disseminated to the PLC, the Contractor shall invite Targeted Enterprises to tender for the Targeted Enterprise work packages.  The Preliminary Targeted Enterprise Database shall remain a “live” database until the day of tender closure when a print-out of the CSD, based on the Database criteria, shall become the Final Targeted Enterprise Database for the tender and shall be disseminated to the PLC.

Any Targeted Enterprise may respond to the invitation to tender, but preference shall be given to those Targeted Enterprises that satisfy the tender criteria.

The Targeted Enterprise Database shall be updated at every instance that a new sub-contract tender or group of similar sub-contract tenders are to be let for Targeted Enterprise work packages.

Targeted Enterprises within the Project Area shall be encouraged and assisted to register on the CSD and to become compliant with all other statutory requirements.

D1003.04	Contract Participation Goal (CPG)

The CPG is the monetary value of the participation targets set by the Employer for Targeted Labour and Targeted Enterprises expressed as a percentage of the Final Contract Value.  The participation targets comprise of the following:

% Targeted Labour (TLTotal%)	=	the sum of the % Targeted Labour employed by the Contractor, Sub-contractors, and Targeted Enterprises.

% Targeted Enterprises (TETotal%)	=	the % Targeted Enterprises, including the % Targeted Labour employed by Targeted Enterprises.

While the individual participation targets, i.e., TLTotal% and TETotal% must be met, the total CPG (CPGTotal) is not the sum thereof, but are calculated as follows:

CPGTotal 	= 	Final Contract Value x [TLTotal% + (TETotal% - Targeted Labour 		employed by the Targeted Enterprises))

Where:

Final Contract Value	=	the total value of the Contractor’s final certified work measured at the date of issue of the Taking-Over Certificate.  The Final Contract Value includes the value of scheduled work and extra work but excludes any Contract Price Adjustment and adjustments for reduced payments, Rise and Fall, Retention Money, Penalties and VAT.

The Contractor shall strive to distribute and implement the participation targets and opportunities equally and continuously over the duration of the Contract.  Where the Contractor deems such an equal and continuous distribution of the participation targets to be unachievable, he shall provide reasons and motivate it clearly in the preliminary CPG Plan submitted with the tender document.

Both the Targeted Labour and Targeted Enterprise participation targets may consist of sub-targets which are stipulated in the Specification Data, clause D1003.  The Contractor is required to achieve these individual sub-targets.  If the Contractor fails to achieve any one of the individual sub-targets and does not substantiate that such failure is due to quantitative underruns, the elimination by the Employer of items contracted to targeted enterprises, or any other reason beyond the Contractor’s control which may be acceptable to the Employer, penalties shall apply as stated in Section D1003.05 of the Specifications, and as provided for in clause 8.7 of the FIDIC Conditions of Contract.

The value of the Provisional Sum scheduled under item D10.05 will not necessarily make up the full value of the work required to meet the minimum target set by the Employer for Targeted Enterprises.  It is the Contractor’s responsibility to assess the work required to meet the targets and, if necessary, to engage additional Targeted Enterprises to execute work on the Contract as well to ensure that the minimum targets are achieved.

D1003.05	Contract Participation Performance (CPP)

The CPP is the monetary value of the Contractor’s actual progress towards achievement of the CPG calculated as follows:

CPP 	= 	CPGActual

=	total monetary value (excluding VAT) of Targeted Labour employed by the Contractor + total monetary value (excluding VAT) of Targeted Enterprises contribution, including Targeted Labour employed by the Targeted Enterprises.

The Contractor’s CPP shall be monitored monthly to determine the extent to which it is striving to achieve the CPG.  The basis of monitoring shall be a comparison of the actual expenditure on Targeted Labour and Targeted Enterprises with the planned expenditure for Targeted Labour and Targeted Enterprises as per the accepted CPG Plan.  Monthly returns, in the format required by the Employer, shall be submitted by the Contractor with each interim Payment Certificate.

To assist in the measurement of the CPP the Contractor shall include the envisaged CPG programme in its initial contract programme which is to be submitted within 28 days after the Commencement Date.  The CPG programme shall be updated in the accepted construction programme on acceptance of the CPG plan and with every subsequent revision.

As an incentive to encourage the Contractor to exceed the CPG, a bonus is offered, measured as follows:

      - CPP Bonus

The bonus = 0.25 x (CPP – CPGTotal)

Any bonus due (or portion thereof) shall be calculated on the Final Contract Value (excluding CPA).  No bonus shall apply if either the Targeted Labour, Targeted Enterprises and/or any individual sub-targets for Target Groups are not reached.

      - CPP Penalties

Conversely, failure to reach either the CPG or any individual Target Group targets shall render the Contractor liable for a penalty as prescribed in clause 8.7 of the FIDIC Conditions of Contract unless there are compelling reasons why the target or sub-targets could not be achieved as stipulated in Section D1003.04 of the Specifications.  Penalties for Targeted Labour and for Targeted Enterprises shall be calculated as follows:

Penalty Targeted Labour = 0.5 x ((TL – TG) + Sum (TL n – TG n) - 1.2 x L dp)

Where:

n 	=	Each lowest order sub-group of Targeted Labour stipulated in 	the Specification Data.

TL 	=	Monetary value of the Targeted Labour calculated at the 	percentage stipulated in the Specification Data applied to the 	final contract value (excluding VAT).

TG 	=	Cumulative monetary value of Targeted Labour employed on 	the contract by the Contractor and all Sub-contractors.

L dp 	=	Cumulative monetary value of black Disabled Persons 	employed on the Contract by the Contractor and all 	Sub-contractors.

(TL n - TG n) 	=	The monetary values calculated unless if any calculated value 	is negative, then it shall be a zero value.

Penalty Targeted Enterprises = 0. 5 x ((TE – TGE) + Sum (TE n – TGE n) - 1.2 x TE mv - 1.2 x TE dp)

Where:

n 	=	Each lowest order sub-group of Targeted Enterprise stipulated in 	the Contract Data.

TE 	=	Monetary value (excluding VAT) of Targeted Enterprises 	calculated at the percentage stipulated in the Specification Data 	applied to the final contract value (excluding VAT).

TGE 	=	Cumulative monetary value (excluding VAT) by Targeted 	Enterprises sub-contracted to the contract by the Contractor and 	50% of the cumulative monetary value (excluding VAT) by 	Targeted Enterprise suppliers of goods and/or services.

TE mv 	=	Cumulative monetary value (excluding VAT) by Targeted 	Enterprises being majority owned by black Military Veterans, 	sub-contracted to the Contract by the Contractor.

TE dp 	=	Cumulative monetary value (excluding VAT) by Targeted 	Enterprises being majority owned by black Disabled Persons, 	sub-contracted to the Contract by the Contractor.

(TE n – TGE n) =	The monetary values calculated unless if any calculated value is 	negative, then it shall be a zero value.

The total Penalty value shall be the sum of the Targeted Labour and Targeted Enterprises Penalty values unless the total Penalty value is negative then it shall be a zero value.

Interim penalty valuations, based on the accepted CPG Plan, shall be calculated to interim Payment Certificate values (excluding VAT) to establish the anticipated outcome, and to plan corrective actions for non-adherence to the CPG Plan.

Interim penalty valuations shall not be applied to the interim certificate value, but the Contractor shall by notice be placed on terms to correct as prescribed in sub-clause 15.1 of the FIDIC Conditions of Contract.  Failure to correct by completion of the Contract will lead to an Employer’s Claim in terms of sub-clause 2.5 of the FIDIC Conditions of Contract.

Any Penalty payable shall be calculated on and applied to the Final Contract Value.

D1003.06	Accredited Registration

The CPP for Targeted Enterprises shall only be accepted if the respective Targeted Enterprises comply fully with the definition of a Targeted Enterprise, and documentary evidence to support the claim lodged with the Engineer before the work, goods or service may be considered as having been performed by a Targeted Enterprise.  The responsibility for producing evidence of the respective documentation shall rest with the Contractor.

The Contractor shall assume responsibility for the compilation and maintenance of comprehensive records detailing each Targeted Enterprise’s progress.

D1003.07 	Contractor’s Responsibility

In terms of the Conditions of Contract, all Targeted Labour recruitment and employment and Targeted Enterprises sub-contracting, as well as its associated risks, shall remain the sole responsibility of the Contractor.

The Employers CPG requirements, and the compulsory utilisation of project specific Targeted Labour and Targeted Enterprises databases, shall not relieve the Contractor of its obligations under the Contract and shall not attract any liability to the Employer.

D1004	STAKEHOLDER AND COMMUNITY liaison AND SOCIAL FACILITATION

This part of Section D of the Specifications describes the Employer’s requirements with respect to Stakeholder and Community liaison and social facilitation.  It also describes the roles and responsibilities of the Project Liaison Committee (PLC) and the Project Liaison Officer (PLO).

D1004.01	Purpose of Stakeholder and Community Liaison

To give effect to the need for transparency and inclusion in the process of delivering services, the Contractor shall liaise with the project Stakeholders and affected Communities for the duration of the Contract’s life cycle.  This shall be achieved through structured engagement with the PLC which was established by the Employer for this purpose.

D1004.02	Contractor’s Responsibilities in Stakeholder and Community Liaison

The Contractor shall have the following general responsibilities in the Stakeholder and community Liaison process:

    - Stakeholder and Community engagement shall be executed based on the Employer’s social facilitation principles and processes described in this Section D of the Specifications.

    - The Contractor shall make use of the PLC as the official communication channel, and utilise it to facilitate harmonious relationships, with project Stakeholders and affected Communities.

    - PLC members, to which the Contractor is a party, shall be held accountable to disseminate project information discussed at the PLC meetings to the entities that they represent.

    - As a party to the PLC, the Contractor shall delegate from among his site personnel a responsible person to participate in the PLC and its business.

    - The Contractor shall provide the PLC with any assistance and information that it requires to execute its duties, which amongst others, include training, providing a meeting venue on site, provide Target Group reports, etc.

It is important to note that in terms of the Conditions of Contract, all Targeted Labour recruitment and employment, and Targeted Enterprises’ selection and sub-contracting, as well as its associated risks, shall remain the sole responsibility of the Contractor.

The Contractor shall take cognisance of the Employer’s PLC and PLO Forms, attached as Annexure X2 Project Liaison Committee and Project Liaison Officer Forms), which shall be provided to the Contractor by the Engineer.  While the Employer holds its own staff accountable for the deliverables listed in the checklist, the Contractor and the Engineer shall assist the Employer in accomplishing the deliverables.

The Employer’s establishment of the PLC and the Engineer providing a PLO to the Contractor shall not relieve the Contractor of its obligations under the Contract and shall not attract any liability to the Employer.

D1004.03 	Project Liaison Committee (PLC)

The PLC is the official communication channel through which the Employer, Engineer, Contractor, and project Stakeholders and affected Communities communicates on project matters.  This platform is also used to communicate the impact that the project has or may have on project Stakeholders and the affected Communities.  This part of Section D of the Specifications describes the general processes pertaining to the PLC, as well as its role and responsibilities.

- Establishment of the PLC

A PLC has either been established prior to commencement of the Contract or shall be established as soon as possible by the Employer.  The PLC consists of the Employer, Engineer, Contractor, and representatives of project Stakeholders and affected Communities.  To ensure that all relevant Stakeholders are represented in the PLC, the Employer did, or will, consult with the Executive Mayor’s office, as well as with the LED Department of the Local Municipalities in the Project Area.  Once, the PLC has be established, the Employer’s further Stakeholder engagement activities shall not prevent the Contractor from continuing with construction.

Typical Stakeholder representation on the PLC may include:

- A PLC member from the relevant RRM PLC.

- Local Municipality LED Office.

- Traditional leadership representation.

- Forums representing people with disabilities.

- Forums representing women.

- Forums representing youth.

- Forums representing business sector.

- Forums representing transport sector.

- Any other Stakeholder forum/organisation recognised by the Employer and the Local Municipality’s LED Office.

Every forum/organisation/constituency shall have one (1) representative on the PLC, which representation shall be confirmed by a duly signed nomination form.

It should be noted that the PLC is not a political platform.  While Councillors may be invited to some PLC meetings, they may not be PLC members and hence, will not have voting rights when attending a PLC meeting.

- Seating Allowance for PLC Members

PLC membership is voluntary and PLC members shall not be renumerated for any time spent or work done associated with representing their constituency on the PLC.

Provision for the cost of liaison, social facilitation and PLC support has been made under pay-item D10.02(a).  This pay-item provides for the Contractor’s cost incurred in executing his responsibilities w.r.t. Stakeholder and Community liaison.

This pay-item may also be utilised to pay an allowance to PLC members for actual costs incurred in executing their PLC duties (other than time or work done related).  The Contractor will determine and table to the PLC a realistic seating allowance which will be substantiated by an outline of the anticipated actual costs envisaged to be incurred by PLC members.

The seating allowance shall be increased annually based on the CPI figure contained in Table B2 of Statistical Release P0141 by StatsSA.

- Induction of the PLC

The Employer shall conduct an induction meeting with the PLC to acquaint PLC members with the following information:

- SANRAL’s Horizon 2030 Strategy.

- SANRAL’s Fourteen Point Plan.

- The role and responsibilities of PLC members.

- SANRAL’s Transformation Policy.

- How the Transformation Policy impacts on SMMEs.

- Relevant details of the Contract, e.g.

  - Start and end dates

  - Important milestones

  - CPG targets

  - Envisaged Targeted Enterprise packages

  - Envisaged work for other SMMEs (non-CPG).

- Rules of Engagement for the PLC

In the execution of their duties, members of the PLC shall adhere to the undertakings listed below and the Contractor shall inform the Engineer of any transgression of these undertakings.

- General Matters and Membership

        - A PLC member may not be a politically elected representative and political party representation will not be allowed in the PLC.

        - Ward Councillors may interact with the project team through the Mayor’s Office.

        - If required, and in consultation with the Employer, a Political Steering Committee (PSC) may be established to address political matters.  A PSC will only be established where the Project Area traverse over more than one municipal area.

- Term of Office for the PLC

- The duration of PLC members’ participating in the PLC (term of office) shall depend on the duration of the project.

- If the Employer finds the performance of a PLC member to be below expectation or their conduct to be unacceptable, the affected member will be discharged from their obligations and a new nomination process shall commence.

- Targeted Enterprise and Targeted Labour

PLC members shall:

- ensure that they, or companies in which they hold equity, will not tender on the Contract for any work or sub-contract that may be issued.  Should they tender, this will be treated as a conflict of interest and the tender proposal submitted will not be evaluated.

- not have private or business interests in any of the sub-contract tenders tabled to the PLC or considered in this Contract.

- shall recuse themselves from discussions that deal with a sub-contract tender if any other member is of the opinion that a member’s participation in deliberations, which is rightly or wrongly construe as improper or irregular, may lead to the award of a sub-contract to a tenderer known to the member or to the member itself.

- recuse themselves from the operations of the PLC following a situation as described in paragraphs ii) above and shall cease to be a PLC member for this Contract.

- during the tender and tender evaluation processes, neither deliberately favoured nor prejudiced a person or tenderer, as intended, or contemplated in treasury Regulation 16, A8.3 (a), (b) & (c).

- ensure that no conflict of interest arises from members’ involvement in the PLC and potential involvement in targeted labour recruitment and/or targeted enterprises procurement and/or any other supplier/sub-contractor/service provider procurement or involvement in the contract.

- Confidentiality

        - PLC members shall accept that all information, documentation, and decisions regarding any matter serving before the PLC are confidential and undertake not to communicate decisions or discussions of PLC meetings to external or internal parties unless so directed and approved by the Project Manager.

        - Information for public dissemination shall be clearly indicated by the committee to ensure that sensitive information is only disseminated to the correct audience.

- Removal from Office

- PLC members who violate the provisions of these Rules of Engagement for PLCs will be removed from their role as a PLC member at the sole discretion of the Employer.

- The Employer reserves the right to recover any costs from PLC members whose actions can be regarded as detrimental to the Employer or to the execution of the project.

- The Employer also reserves the right to recommend criminal prosecution if the offence warrants such action.

- The Employer reserves the right to dissolve the entire PLC should it believes that such an action is in its best interest, or that of the project.  The Employer will not be obliged to reconstitute the PLC if such a dissolution occurs.

- Responsibilities and Duties of the PLC

The PLC shall execute specific duties during the design and construction phases of the project.

Some of the PLC’s duties during the design and construction stages overlap and hence, for completeness, a description of the PLC’s duties in both project stages is provided here.

The PLC shall execute the following duties:

- Project Design Stage

- Meet as often as required to discuss and resolve the project’s design stage matters which are of interest or concern to the parties to the PLC.

- Peruse the Project Liaison Committee duties outlined in this Section D of the Specifications and agree on the duties of, and procedures to be followed by, the PLC to fulfil its duties.

Note:  The principles outlined in this section shall not be amended, but duties and procedures may be altered to be project specific and to improve the functionality of the PLC.

- Act in accordance with the agreed terms of reference for the PLC.

- Inform the Employer’s Project Manager of any training that project Stakeholder and affected Community representatives of the PLC require to execute their duties.

- Assist the Engineer to source suitable candidates, based on the Employer’s qualifying criteria, for the position of PLO.

- Observe and verify that the qualifying criteria and procedures applied by the Engineer to select and employ the PLO were executed in a fair and transparent manner and were within the prescripts of the relevant labour legislation and regulations.

- Assist the Engineer to identify the project’s Target and Project Area(s) from which Targeted Labour and Targeted Enterprises could be employed and sub-contracted, respectively.

- Assist the Engineer to identify the project’s Target Groups for inclusion in the Tender Documents and provide input and support the identified Target Groups.

- Project Construction Stage

- Meet formally prior to the Employer’s monthly site meeting, or as may be required, to discuss and resolve project matters which are of interest or concern to the parties to the PLC.

- Assist the Contractor to establish the selection criteria and process to employ Targeted Labour

- Assist the Contractor to identify the eligibility, functionality, preference, and compliance criteria to select and sub-contract Targeted Enterprises.

- Provide input and support for the Databases compiled by the PLO and the Contractor from which Targeted Labour will be selected and employed and Targeted Enterprises will be sub-contracted, respectively.

- Verify that the criteria and methodologies applied by the Contractor to select and employ Targeted Labour and sub-contract Targeted Enterprises are executed in a fair and transparent manner and are within Government legislation and regulations and the Employer’s Policies.

- Verify that the conditions of employment and the conditions of sub-contracting, in the employment of Targeted Labour and sub-contracting of Targeted Enterprises are applied in a fair and transparent manner and according to the Employer’s employment and sub-contracting requirements.

- Make recommendations to the Contractor on the training needs, eligibility criteria and selection criteria for the provision of training to Targeted Labour, Targeted Enterprises, Designated Groups, project Stakeholders and the affected Communities.

- Verify that training and skills development programmes, which the Contractor committed to, are implemented, and executed as approved and intended.

- Inform the entities whom they represent of any project matters which the respective party to the PLC wishes to communicate with each other.

- Inform the entities whom they represent of any project matters that are impacting or may impact, either positively or negatively, on the respective parties to the PLC.

- Inform the Contractor of Stakeholder and/or Community requests and/or needs, which could possibly be addressed within the project’s Scope of Work.

- Inform the Employer’s Project Manager, Engineer, and Contractor of any road safety concerns within the Project Area(s) and advise them of possible mitigating measures and/or road safety programs that will be most suitable for acceptance by the affected Communities to promote road safety.

- Assist parties to the PLC to agree on a dispute resolution mechanism to resolve any disputes that may arise between the parties to the PLC.

- Assist parties to the PLC to liaise with their respective entities to resolve any disputes amongst the parties which may occur due to the project.

- PLC Meetings

## Frequency

- Meetings will be conducted monthly or as required by the Stakeholders or the project matters.

## Notice of Meetings

- The notice of the PLC meeting shall be given at least seven (7) calendar days prior to the meeting date.

- Where meetings have been diarised over a period by the PLC, it shall be the duty of each PLC member to ensure his/her attendance on the set dates.

- Where a PLC member has missed any meeting, he/she bears the onus of establishing the date and venue of the next meeting.

## Venue

- The venue for PLC meetings shall be the project site office or any other venue agreed to by the members of the PLC and approved by the Employer’ Project Manager.

- During the COVID-19 lockdown, or any other lockdown as announced by government, the meetings shall be held on an online platform such as WhatsApp, MS Teams, Zoom or similar.

### Agenda

- An agenda shall be made available or displayed to all participants at the commencement of such meetings or the minutes of the previous meeting will serve as the agenda of such meetings.

- The agenda shall not be amended without prior approval from the Employer’s Project Manager.

## Chairperson

- PLC meetings shall be chaired by the Employer which will typically be the Employer’s Project Manager, or a SANRAL staff member, with decision--making delegation, or the Engineer.  The Chairperson shall:

        - chair all meetings of the PLC,

        - co-ordinate all the activities of PLC,

        - ensure that members are fulfilling their tasks as assigned by the PLC,

        - see to the execution of decisions taken by the PLC,

        - ensure the validity of members’ claim for allowance,

        - ensure compliance of all activities of the PLC with current rules, law and general SANRAL policy, and

        - be a co-signatory to all official documents of the PLC.

- Secretariate

        - The Engineer’s staff shall provide a secretarial service to take minutes of PLC meetings.

        - Secretarial support other than taking minutes at PLC meetings shall be provided by the PLO.

## Quorum

- The quorum for PLC meetings shall be constituted by 50%+1 ratio excluding co- opted members.

### Apologies and Non-attendance

- Apologies shall be in writing except in emergency where the member apologising cannot communicate the apology in writing.

- Apologies may be sent through any media agreed to prior by the PLC for example through SMS or WhatsApp messaging or similar application.

- The organization, represented by a member who fails to attend three (3) consecutive meetings without an apology, will be informed in writing and asked to nominate a replacement member.

### Language

- The meetings will be conducted in English to enable all participants at the meeting to understand the discussions of the meeting.

- However, care and consideration must be given to provide non-English speakers an opportunity to participate. Therefore, where desirable, any of the 11 official languages maybe be used to conduct the meeting. If another language other than English is used, the minutes of the meeting will need to be transcribed, translated, and recorded in English.

### Other

- The PMT shall provide a finger lunch for PLC members at PLC meetings.

D1004.04	Project Liaison Officer

The PLO facilitates the selection and employment of Targeted Labour and coordinates communication between the members of the PLC to address the day-to-day project, Stakeholder, and Community matters that impact on the parties represented in the PLC.

- Appointment of the PLO

The Engineer appoints the PLO in accordance with the Employer’s criteria for a PLO. The appointment of the PLO must be acknowledged and supported by the PLC.

Although the PLO provides social facilitation support to the Contractor, the PLO shall report to the Engineer or his delegated representative, e.g., the Resident Engineer.

- Duties of the PLO

The PLO shall execute specific duties during the design and construction phases of the project.  These duties include the following:

- Except for taking the minutes of PLC meetings which is a duty of the Engineer, the PLO shall provide a secretariat function to the PLC which includes, amongst others, the following:

  - Schedule meetings.

  - Compile meeting agendas.

  - Compile document packages for meetings.

  - Distribute minutes of meetings.

  - Assist representatives of project Stakeholders and affected Community to formulate their communication to the PLC in writing.

  - Distribute written communication between the parties to the PLC.

  - Keep records of all PLC correspondence and documentation; and

  - Provide any other reasonable secretariat function required by the PLC.

- Attend all PLC meetings to report on the day-to-day project, Stakeholder and Community matters that impact on the parties to the PLC.

- Attend all monthly project site meetings to report on the day-to-day project, Stakeholder and Community matters that impact on the parties to the PLC.

- Attend any other meetings related to the project and in which any of the project Stakeholders, affected Communities, Targeted Labour and Targeted Enterprises are involved.

- Maintain a full-time presence on site to monitor and address the day-to-day project, Stakeholder and Community matters that impact on the parties to the PLC.

- Maintain a full-time presence on site to assist the parties to the PLC in the day-to-day liaison with each other.

- Assist the Engineer and the Contractor to disseminate information to PLC members such as:

- the basic Scope of the Works and how it will affect the Community,

- the project programme and regular progress updates,

- the anticipated employment and sub-contracting opportunities,

- the project programme as it pertains to the employment of Targeted Labour and sub-contracting of Targeted Enterprises,

- Occupational Health and Safety precautions, and

- any other information relevant to project Stakeholders and the affected Communities.

- Be well acquainted with the contractual requirements as it pertains to Targeted Labour employment and training.

- Assist the PLC to establish and agree the criteria to follow when selecting and employing Targeted Labour.

- Assist the Engineer and the Contractor in their resources and skills audits by providing a coordinating function between the Engineer, the Contractor, project Stakeholders and the affected Communities.

- Ensure that the Contractor compiles the Targeted Labour databases based on the eligibility and selection criteria and that he updates it as and when required.

- Coordinate the selection and employment of Targeted Labour based on the agreed eligibility and selection criteria and based on the Contractor’s labour and skills requirements.

- Ensure that each Targeted Labourer enters an employment contract which adheres to current and relevant Labour legislation.

- Ensure that each Targeted Labourer understands the conditions of his/her employment contract, with an emphasis on the employment start date, end date and wages payable.

- Identify and inform the Contractor of any relevant training required by the Targeted Labour.

- Attend all disciplinary proceedings to ensure that hearings are fair and conducted in accordance with the current and relevant Labour legislation.

- Be proactive in identifying project Stakeholder and affected Communities’ (including Targeted Labour and/or Targeted Enterprise Sub-contractor), requirements, disputes, unrest, strikes, etc., and bring it to the attention of the PLC.

- Assist the parties to the PLC to resolve any disputes, which may occur due to the project.

- Other than the document records to keep as mentioned above, keep record of all other documents and processes pertaining to the employment of Targeted Labour.

- Produce and submit a monthly report to the PLC on PLC and other meetings attended by the PLO, as well as on Targeted Labour employment, and project Stakeholder, affected Community and any other project matters that impact on the parties to the PLC.

D1005	MOBILISATION PERIOD

The Mobilisation Period is defined in Section D1002 of the Specifications.  This Section describes the requirements of the Mobilisation Period.

D1005.01	Purpose of the Mobilisation Period

The Mobilisation Period was introduced as an aid to the Contractor to:

- become acquainted with the Stakeholder and Community liaison requirements of the Contract as prescribed in this Section D of the Specifications,

- allow for the Contractor’s planning to obtain the CPG as required in the Specification Data,

- allow for the Contractor’s planning to obtain the Contract Skills Development Goals (CSDG) as required in Section D1010 of the Specifications,

- follow the processes prescribed in this Section D of the Specifications to employ the initially required Targeted Labour and enter the first sub-contracts with Targeted Enterprises, and

- provide the training required by Targeted Labour and Targeted Enterprises to commence with the construction of the Works.

Access to site for the Commencement of the Works shall thus only be issued once the following deliverables have been submitted and/or completed by the Contractor:

- Submission of the CPG Plan, followed by acceptance of the Engineer.

- Submission and the Training and Skills Development Programme, followed by acceptance of the Engineer.

- Appointment of the initial Targeted Enterprise sub-contractors.

D1005.02 	Duties of the Contractor

During the Mobilisation Period, the Contractor shall execute the following duties:

          - Compile a CPG Plan

The Contractor shall compile an acceptable CPG Plan, which sets out how he intends to achieve the various CPG targets as stated in the Specification Data.  The Contractor shall distribute and implement the participation targets and Targeted Enterprise work opportunities equally and continuously over the duration of the Contract, i.e., from site establishment to completion of the Works.  Where the Contractor deems such an equal and continuous distribution of the participation targets to be unachievable, he shall provide reasons and motivate it clearly in the CPG Plan.

The CPG Plan shall provide the detail of the Targeted Enterprise work programme, as well as the contents and value of the work packages.  See Annexure X1 Contract Participation Goal (CPG) Plan Format for the CPG Plan format.

The Targeted Enterprise work programme shall be in line with the Works Programme and once the CPG Plan has been accepted by the Engineer, it shall be captured in the Works Programme.

The Employer’s Project Manager and the Engineer shall monitor progress and adherence to the CPG Plan in the same manner as they would monitor the Works Programme.

          - Compile a Training and Skills Development Plan

The Contractor shall compile an acceptable Training and Skills Development Plan, which sets out how he intends to achieve the various CSDG targets as per Section D1010 of the Specifications.

The Training and Skills Development Plan shall provide the detail of the training methods selected for implementation as described in Section D1010 of the Specifications and shall include an execution programme for acceptance by the Engineer, which shall demonstrate its correlation with the Works Programme.

The Employer’s Project Manager and the Engineer shall monitor progress and adherence to the Training and Skills Development Plan in the same manner as they would monitor the Works Programme.

          - Sub-contracting of Targeted Enterprises

During the Mobilisation Period the Contractor shall execute the following duties w.r.t. the sub-contracting of Targeted Enterprises:

- Liaise with the Employer’s Project Manager, the Engineer and the PLC to structure and finalise the work packages to be sub-contracted to Targeted Enterprises.

- Liaise with the Employer’s Project Manager, the Engineer, and the PLC to determine the Targeted Enterprise Database criteria for the sub-contracting of Targeted Enterprises.

- Compile the Targeted Enterprise Database(s) for input and support by the PLC.

- Undertake a skills audit of the Targeted Enterprises which appear on the Targeted Enterprise Database(s).

- Based on the skills audit, and in consultation with the PLC, identify the pre-tender training requirements of Targeted Enterprises.

- Provide an opportunity to Targeted Enterprises to receive the identified pre-tender training.

- Tender the initial work packages and sub-contract the first group of Targeted Enterprises for commencement of the Works.

          - Employment of Targeted Labour

During the Mobilisation Period the Contractor shall execute the following duties w.r.t. the employment of Targeted Labour:

  - Liaise with the PLC and the PLO on the compiled Targeted Labour Database(s) for the employment of Targeted Labour.

  - Undertake a skills audit of the Targeted Labour which appear on the Targeted Labour Database(s).

  - Based on the skills audit, and in consultation with the PLC, identify the training requirements of Targeted Labour to enhance their employability.

  - Provide an opportunity to eligible Targeted Labour to receive the identified training to enhance their employability.

  - Select and appoint the first group of Targeted Labour for commencement of the Works .

          - Training Requirements

The Contractor will not be able to address all the training requirements identified for Targeted Labour and Targeted Enterprises during the Mobilisation Period and it is accepted that training will take place over the duration of the Contract.

The training provided to both Targeted Enterprises and Targeted Labour during the Mobilisation Period shall focus on the activities and/or skills required for the commencement of the Works and shall include the mandatory Occupational Health and Safety training.

D1006	THE ROLE OF THE ENGINEER

The role and responsibilities of the Engineer are clearly described in the Conditions of Contract.  This section elaborates on the Engineer’s duties with respect to Stakeholder and Community Liaison, Targeted Labour Employment and Targeted Enterprise sub-contracting.

Together with the Employer and the Contractor, the Engineer is also a party to the PLC and hence, is co-responsible for successful project Stakeholder and Community liaison.

In addition, the Engineer shall play a supporting role to the Contractor in the successful implementation of the Employer’s Targeted Labour and Targeted Enterprise utilisation and development goals.

D1006.01	Duties During the Design Phase

During the design phase, the Engineer undertook a preliminary skills and resources audit of the Targeted Enterprises in the Project Area.  The purpose of the audit was to:

          - obtain an understanding of the Community’s skills, both academically and occupationally,

          - obtain and understanding of the resources within the Community, i.e., Targeted Enterprise availability and capabilities,

          - establish the CPG targets for Targeted Enterprises and Targeted Labour for inclusion of the Specification Data; and

          - identify tender and other relevant training to be offered to Targeted Enterprises and Targeted Labour to prepare them for tendering and to enhance their employability.

D1006.02	Duties During the Design Build Operate Phase

To implement the Employer’s Targeted Labour and Targeted Enterprise goals the Engineer shall provide support to the Contractor by executing the following duties:

- Targeted Enterprise Sub-contracting

- Make recommendations to the Contractor in identifying and structuring the work packages to be sub-contracted to Targeted Enterprises and approve the scope and extent of the work packages.

- Verify that the Targeted Enterprise Database(s) has been updated prior to the letting of every new set of sub-contracts.

- Approve tender procedures, tender documents, tender submission requirements and adjudication processes for the sub-contracting of Targeted Enterprises.

- Review all tender adjudication reports and monitor that the criteria and procedures applied by the Contractor to sub-contract Targeted Enterprises are executed in a fair and transparent manner and are within the Employer’s and Government’s Supply Chain Management Policies.

- Verify that sub-contract agreements and the conditions of sub-contracting with Targeted Enterprises are fair and transparent and within the prescripts of the Contract requirements.

- Monitor the management of Targeted Enterprise sub-contracts and ensure that conditions such as the application of penalties, the termination of contracts, etc. are applied in a fair and transparent manner and within the prescripts of the agreement.

- Targeted Labour Employment

- Verify that the Labour Database(s) from which Targeted Labour will be employed is updated prior to every new Labour intake.

- Monitor that the criteria and procedures applied by the Contractor to employ Targeted Labour are executed in a fair and transparent manner and is within the Contract requirements.

- Monitor that the conditions of employment of Targeted Labour are applied in a fair and transparent manner and within the prescripts of the current and relevant Labour legislation.

- Target Group Training Requirements

- Make recommendations to the Contractor in identifying the training requirements of Targeted Labour and Targeted Enterprises and approve the proposed training programmes.

- Monitor that training programmes and support programmes, which the Contractor committed to, are implemented, and executed as intended.

D1007	TENDER PROCESS FOR TARGETED ENTERPRISES

While the Contractor may utilise service providers, sub-contractors and suppliers of its choice and selected via its own internal processes, for the sub-contracting of Targeted Enterprises based on the Employer’s Contract Participation Goals, the Contractor shall follow the prescripts of this Section D of the Specifications.

D1007.01	Targeted Enterprise (TE) Procurement Coordinator

The Contractor shall appoint a TE Procurement Coordinator to facilitate the sub-contracting of work to Targeted Enterprises as defined in the Specification Data.  For Contracts with a value of less than R 200 million per annum the Contractor may appoint a TE Procurement Coordinator from its site staff.  For Contracts with a value of more than R 200 million per annum the Contractor shall employ or sub-contract a dedicated TE Procurement Coordinator, whose sole responsibility will be the management of Targeted Enterprise procurement and sub-contracting matters.

The TE Procurement Coordinator shall be knowledgeable of, and have experience in, the management of civil, electrical, or electronic engineering projects, National Treasury supply chain management legislation and regulations, and stakeholder relations management.

With the input and support of the PLC, the TE Procurement Coordinator shall conduct the tender processes and procedures for Targeted Enterprise sub-contracting as prescribed in this Section D of the Specifications and shall adhere to the Employer’s and Government’s Supply Chain Management Policies and requirements.

D1007.02	Procedures for Targeted Enterprises Sub-contracting

The Contractor shall utilise the suitable, fit for purpose tender and contract document for Targeted Enterprise sub-contracting.  The Employer  sub-contract document attached as Annexure X3 may be used as guideline document and an electronic version will be provided to the Contractor on award.

The identification and application of the eligibility and functionality criteria, and conducting the tender processes and procedures for sub-contracting include, amongst others, the following tasks:

- Tender Preparation

- Compile preliminary list of sub-contracting work packages.

Based on the Specification Data and the Scope of the Works, the Contractor shall compile a preliminary list of the work packages (scope of work and number of packages) that are anticipated to be sub-contracted to Targeted Enterprises.

The Contractor shall refer to the construction activities that has been identified as being suitable for construction by Targeted Enterprises as listed in Section D1009 of these Project Specifications, and to any other construction activities which are required to execute the Works in terms of this Contract, to determine how to unbundle or package sub-contracts for Targeted Enterprises.

- Conduct a market analysis and resources and skills audit.

Based on the preliminary list of work packages, the Contractor shall conduct a market analysis and resources and skills audits to determine the availability of the required resources and skills in the Project Area to execute the anticipated Targeted Enterprise work packages.  The Contractor shall consult the following databases as a minimum:

  - Construction Industry Development Board (CIDB)’s contractor database (not applicable to suppliers and non-construction services).

  - National Treasury’s Central Supplier Database (CSD) to be obtained from the Employer’s Supply Chain Management Department.

- Call for an expression of interest.

In addition to consulting the CIDB contractor database and National Treasury’s CSD, the Contractor shall call for an expression of interest, which shall be published in newspapers and at locations as agreed by the PLC.

For each group of work packages, the call for an expression of interest shall outline:

  - evaluation and selection criteria such as eligibility, preference, and functionality.

  - compliance requirements such as CSD and CIDB registration, tax clearance and COID.

  - the anticipated scope of the works to be undertaken.

- Establish a Targeted Enterprise Helpdesk

Other than informing the Contractor’s market analysis and resources and skills audits, the purpose of the call for an expression of interest is to alert Targeted Enterprises of the sub-contracting opportunities and inform them of the anticipated eligibility, preference, and functionality criteria, as well as of the compliance requirements.

The Contractor shall enhance the readiness of Targeted Enterprises to participate in the sub-contracting opportunities by establishing a helpdesk at a suitable and easily accessible location in the Project Area.

The Contractor shall provide guidance to Targeted Enterprises in getting their statutory requirements in order in anticipation of the sub-contracting opportunities.  The helpdesk shall assist with, or provide guidance in, registering with the CSD and the CIDB, obtaining tax clearance and COID compliance and any other relevant qualifying requirements.

- Compile Preliminary Targeted Enterprise Database

Based on the CPG targets listed in the Specification Data and the information obtained from the activities described in paragraphs ii) and iii) above, the Contractor shall compile a Preliminary Targeted Enterprise Database.

In compiling the preliminary Targeted Enterprise Database, the Contractor must bear in mind that the benchmark for an adequate number of tenderers to ensure a competitive tender process is ten (10) tenderers that are able to achieve the functionality threshold during the tender evaluation.

- Identify Targeted Enterprises, Target Groups and Project Area(s).

Based on the CPG targets listed in the Specification Data and the Preliminary Targeted Enterprise Database, the Contractor shall identify the:

  - Targeted Enterprises (CIDB grades and types); and

  - Designated Groups (woman, youth, etc.) which are anticipated to benefit from the sub-contracting opportunities; and

  - Project Area(s) from which Targeted Enterprises will be given preference for sub-contracting opportunities.

- Compile a Contract Participation Goal (CPG) Plan.

The Contractor shall utilise all the information gathered from the activities described in the paragraphs above to compile an acceptable CPG Plan.  The plan shall contain:

  - a list of work packages (scope of work and number of packages) to be subcontracted to Targeted Enterprises,

  - procurement, award and execution dates for the work packages, distributed over the duration of the Works Contract (from site establishment to completion of the Works) to ensure continuous work opportunities,

  - the preliminary Targeted Enterprise Database(s) for each work package,

  - the Targeted Enterprises (CIDB grades and types) and Designated Groups (woman, youth, etc.) which are to benefit from the sub-contracting opportunities,

  - the Project Area(s) from which Targeted Enterprises will be given preference for sub-contracting opportunities, and

  - the tender evaluation and selection criteria for the respective work packages.

- Acceptance of the CPG Plan

The Contractor shall submit the CPG Plan to the Engineer for acceptance after which it shall be tabled to the PLC for their information.

The Contractor shall ensure that the tender requirements and the outcome of different tendering scenarios are explained to the PLC, specifically with respect to the outcomes of evaluating:

  - Eligibility criteria,

  - Functionality structuring and scenarios,

  - Price and Preference,

  - Compliance requirements, and

  - Negotiation processes (if applicable).

If required, the Contractor shall make amendments to the CPG Plan based on the Engineer’s instructions.

- Compile tender documents.

The Contractor shall compile the tender documents for each Targeted Enterprise sub-contract work package and shall utilise the suitable bid document for Targeted Enterprise sub-contracting (see Annexure X3)

In compiling the sub-contract tender documents, the Contractor shall include in each tender document relevant Conditions of Tender and the FIDIC sub-contract agreement/suitable conditions of contract.  The Contractor shall compile each sub-contract tender document in a manner that facilitates the achievement of all objectives and principles pertaining to the development of the Targeted Enterprises.

The draft sub-contract tender documents shall be approved by the Engineer before letting the tender.

- Tender Process

- Advertise the sub-contract packages.

The Contractor shall advertise and invite tenders from Targeted Enterprises for the respective sub-contract packages.  Advertisements shall be placed in local newspapers, on community notice boards, on SANRAL’s electronic supply development desk portal (https://sanralesdd.co.za), and any other place or medium as agreed with the PLC.

If the Employer have a pro-forma Tender Notice available, the Contractor shall use this document.

- Conduct a tender briefing and tender training session.

For each group of sub-contract packages, the Contractor shall conduct a compulsory briefing session to explain the tender process, the evaluation and selection criteria and the scope of the works to the Targeted Enterprises.

An Attendance Register shall be completed by all attendees and Minutes shall be taken during the briefing session.  The Minutes of the briefing session shall be distributed to all attendees as an Addendum to the Tender Documents.

The Contractor shall conduct a “how to complete a tender document” training session as a component of the tender briefing to interested Targeted Enterprises.  The level of detail and hence the duration, of the training session shall be informed by the findings of the resources and skills audit conducted during the Tender Preparation Phase.

The Contractor shall engage with the Employer’s Regional Transformation Officer on the Employer’s SMME Pre-tender Training and Development Programme and utilise this programme if it is available at the time in the Project Area.  The Regional Transformation Officer’s contact details shall be provided by the Project Manager on award.

Notes of this training session shall be distributed to all attendees of the briefing session as an Addendum to the Tender Documents, irrespective if they have attended the training session or not.

A separate Attendance Register shall be completed for the training session for future reference.

- Minimum tender submission documents.

It shall be a condition of tender that Targeted Enterprises include in their tender submissions the following documentation (if applicable, based on the sub-contract type, e.g., construction, supply, or services):

  - Proof of the Tenderer’s B-BBEE contributor level.

- Proof that the Tenderer is an EME or QSE entity.

- Proof that the Tenderer is registered on National Treasury’s CSD.

- Proof of the Tenderer’s locality (address registered with the CIPC).

- Proof that the Tenderer is registered with the CIDB in the required grading and class (not applicable to suppliers).

- Proof that the Tenderer is compliant with the COID act.

- Proof that the Tenderer is tax compliant.

- Tender closure and opening of tenders.

Tenders for the sub-contract packages shall close at a stipulated time and date.  Tenders shall be submitted to the Contractor in the format and at the address prescribed by the Contractor in the sub-contract Tender Data.

The tender opening shall be conducted by the Contractor who shall publicly announce and record the names of all bidders and their tender prices.

- Finalise Targeted Enterprise Database

The purposes of the preliminary Targeted Enterprise Database are described in the Tender Preparation phase above of which one is to alert Targeted Enterprises to assess their readiness to participate in the project’s sub-contractor opportunities.

The period between the Contractor’s call for an expression of interest and the date of closure of the relevant sub-contract tender allows for prospective Tenderers to become compliant to the database criteria.  The preliminary database is thus a “live” database until the date of tender closure.

On the date of tender closure, the Contractor shall request the Employer’s Supply Chain Management Department to print out a list from National Treasury’s CSD, of entities that adheres to the Targeted Enterprise Database criteria.  This list shall become the Final Targeted Enterprise Database for relevant sub-contract tender and shall be submitted to the PLC for sign-off.

- Tender Evaluation

The Contractor shall evaluate the tenders and it shall be a condition of tender that tenders will only be accepted from Targeted Enterprises that fully comply with the definition of a Targeted Enterprise as described in Section D1002 of the Specifications.

The Contractor shall evaluate the tenders based on (1) Eligibility, (2) Functionality, (3) Price and Preference, and (4) Compliance.

- Stage 1 – Eligibility

Tenderers shall be checked for their eligibility to tender for the advertised sub-contract packages based on the following eligibility criteria:

      - Proof that the Tenderer is registered with the CIDB (if applicable).

      - Proof that the Tenderer is registered on National Treasury’s CSD.

      - Proof that the Tenderer is registered with the CIPC.

      - Proof that the Tenderer is a level 1 to 4 B-BBEE contributor.

      - Proof that the Tenderer is an EME or a QSE.

Proof that the Tenderer falls within one or more of the designated groups as per the Specification Data (if applicable).

Eligible Tenderers shall be further evaluated against the functionality criteria.

- Stage 2 – Functionality

No Targeted Enterprise may be prohibited from responding to the invitation to tender, however, preference shall be given to those Targeted Enterprises that adheres to the tender criteria, which amongst others, shall be measured by means of a functionality evaluation.

To ensure Targeted Enterprise participation as it is intended by the Employer and as defined in the Specification Data, Functionality shall be scored based on the type of sub-contract package, e.g., construction or the supply of goods or services and at least three (3) or more of the criteria listed below shall be applied.

The points allocated for the listed criteria shall be clearly demonstrated to tenderers as a matrix in the tender document.  The functionality matrixes provided in the Employer’s proforma document for Targeted Enterprise sub-contracting (Annexure X3) shall be used as a refence  to determine criteria to evaluate the functionality of Tenderers.

Tenderers must score a minimum of 75% for functionality and Tenderers that do not obtain the threshold shall not be evaluated further.

- Locality

For lower CIDB grade packages, the points allocated for Locality typically has a higher weighting in the total evaluation points but shall not be more than 65% of the total evaluation points.

Points scored shall be based on the Targeted Enterprise’s registered address with the CIPC.

- If the Targeted Enterprise is more than twelve (12) months old and the company address:

- was changed with the CIPC in the twelve (12) months prior to the tender advertisement; or

- does not correlate with the company address recorded on the CSD,

the Targeted Enterprise shall provide additional proof of its address in the twelve (12) months preceding the tender advertisement date and that the address is current by submitting the following:

- for urban areas:

- signed lease agreement confirming occupation in the preceding twelve (12) months; or

- mortgage statement confirming ownership in the preceding twelve (12) months; and

- a current utility bill (not older than three (3) months) confirming that occupation is current; or

- for semi-urban and rural areas

      - an affidavit from the relevant ward councillor or traditional authority, signed and stamped by a registered commissioner of oaths, which confirms that the business has been operating from the said address in the preceding twelve (12) months.

- If Targeted Enterprise is less than twelve (12) months old and the company address:

        - was changed with the CIPC in the twelve (12) months prior to the tender advertisement; or

        - does not correlate with the company address recorded on the CSD,

the oldest registered address on either the CIPC or the CSD will be accepted as the Targeted Enterprise’s address for the purpose of scoring locality points.

- If the Targeted Enterprise intends to operate from a branch office for the purpose of the anticipated sub-contract, the same additional proof that the company has been operating from the branch office in the twelve (12) months prior to the tender advertisement date must be provided as listed in the paragraphs above.

- If the above additional proof of address cannot be provided, locality points shall be awarded based on the tenderer’s address registered with the CIPC in the twelve months prior to the tender advertisement date.

- Equipment

For lower CIDB grade packages, the points allocated for Equipment typically has a lower weighting in the total evaluation points.

The combined points allocated for Equipment and Experience shall not be more than 35% of the total evaluation points.

- Experience

For lower CIDB grade packages, the points allocated for Experience typically has a lower weighting in the total evaluation points.

The combined points allocated for Equipment and Experience shall not be more than 35% of the total evaluation points.

- CIDB grade and class

The points allocated for CIDB grade and class shall not be more than 35% of the total evaluation points.

CIDB grade and class shall not be used as an evaluation criterion for packages pertaining to the supply of material, goods and/or services.

- Project Specific Designated Groups, e.g., woman, youth, etc.

In addition to the eligibility criteria for preferential procurement functionality points may also be allocated for the following Designated Groups:

- Tenderer is 51%+ owned by black people who are youth.

- Tenderer is 51%+ owned by black people who are women.

- Tenderer is 51%+ owned by black people with disabilities.

- Tenderer is 51%+ owned by black people who are military veterans.

The points allocated for Designated Groups shall not be more than 15% of the total evaluation points.

One, two or three of the Designated Groups listed above may be selected to count towards the score for Designated Groups.

If any one of the Designated Groups listed above is already an eligibility criterion, it must not be included as a functionality criterion as well.

The inclusion of any of the Designated Groups listed above shall be based on the Contractor’s Resources and Skills Audit.

Youth and veterans may not be selected together.

- Stage 3 – Price and Preference

Tenderers that obtained the minimum threshold for functionality shall be further evaluated on their Price and Preference submissions, i.e.

- Price		= 80 / 90 %

- Preference	= 20 / 10 %

The highest scoring tenderer for each sub-contract package shall be checked for compliance.

The Contractor shall state in the tender advertisement and in the tender documents that only one sub-contract package shall be awarded to an entity at any one time for this project, meaning that a Targeted Enterprise may be awarded a work package and on conclusion thereof may be awarded a subsequent work package, but more than one work package may not be awarded simultaneously for this project.

If a tenderer tendered for more than one sub-contract package and scored the highest points in more than one package, the Contractor shall award to the tenderer the work package that has the most economic benefit to the Employer.

- Stage 4 – Compliance Check

The highest scoring tenderer for each sub-contract package shall be checked for compliance with respect to the following criteria:

      - Proof that the Tenderer is compliant with the COID Act (excl. CIDB 1 and 2 CE sub-contractors).

      - Proof that the Tenderer is tax compliant.

If the highest scoring tenderer fails to meet any of the compliance criteria, he will be given seven (7) calendar days to become compliant.

If the highest scoring tenderer fails to submit the requested compliance information in the required timeframe, he shall be deemed non-compliant, and the evaluator shall check the second highest tenderer for compliance.  This process is repeated until a compliant tenderer has been identified.

- Appoint successful Targeted Enterprises

        - Table the Tender Report to the PLC.

The Contractor shall present the Tender Report for each sub-contract package to the Employer’s Project Manager and the Engineer and thereafter table it to the PLC prior to award of the sub-contract.

        - Negotiating tender sum and/or rates with Targeted Enterprises.

          - Rates

If the Contractor choose to include work for which he has tendered rates in the sub-contract package and the tenderer who scored the highest points tendered higher rates than that of the Contractor, the Contractor may negotiate rates and the final sum with the tenderer.

If the Contractor fails to negotiate a reasonable tender sum or rates with the tenderer, he may:

- approach the second highest points scoring compliant tenderer for negotiation.  This process may be repeated up to the third highest points scoring compliant tenderer, where after the package shall be retendered.  the Contractor shall be limited to negotiate down to 25% above his own rates (this process must be clearly explained prior to negotiation, when the tender report is tabled to the PLC); or

- accept the highest points scoring tenderer’s higher rates and total sum and remunerate the sub-contractor, at the sub-contractor’s tendered rates, from the Lump Sum which the Contractor has tendered for the fluctuation between the Contractor’s rates and that of the Targeted Enterprise sub-contractors.

- Provisional Sum

If the Employer has provided a Provisional Sum for the work items in the sub-contract package, the Contractor shall report on the feasibility of the highest point scoring compliant tenderer’s tender rates and tender sum to the Employer’s Project Manager and the Engineer.

    - If the highest points scoring compliant tenderer’s rates and tender sum are deemed market related by the Engineer, the Contractor shall obtain the Employer’s approval to utilise the Provisional Sum provided for the work items.

    - If the highest points scoring compliant tenderer’s rates and tender sum are deemed not market related and the Employer does not approve the utilisation of the relevant Provisional Sum, the Contractor may negotiate with the tenderer for market related rates and tender sum.

    - If the Contractor fails to negotiate market related rates and a tender sum with the tenderer, he may:

    - approach the next highest point scoring compliant tenderer for negotiation.  This process may be repeated up to the third highest points scoring compliant tenderer, where after the package shall be retendered; or

    - accept the highest points scoring tenderers rates and total sum and remunerate the sub-contractor from the Lump Sum which the Contractor has tendered for the fluctuation between the Contractor’s rates and that of the Targeted Enterprise sub-contractors.  The Contractor shall not pay rates or tender sums that is more than 15% higher than what are deemed market related by the Engineer.

- Low tender sums submitted by Targeted Enterprises.

The Contractor shall report to the Employer’s Project Manager and the Engineer on the feasibility of tendered rates, sums, or Provisional Sums of tenderers who tendered exceptionally.  Exceptionally low rates, sums or Provisional Sums are those that are more than ten percent (10%) less than what the Contractor tendered, or in the case of a Provisional Sum, what is deemed market related by the Engineer.

        - If the tendered rates, sums, or Provisional Sums of those tenderers who tendered exceptionally low are deemed by the Engineer to still be feasible, the Contractor may continue to include these tenders in his tender evaluation.

        - If the tendered rates, sums, or Provisional Sums of those tenderers who tendered exceptionally low are deemed by the Engineer to not be feasible, the Contractor may disqualify these tenders from his tender evaluation.

The Employer strongly discourages the appointment of Targeted Enterprises that did not tender feasible rates, sums, or Provisional Sums.  If all prices submitted are deemed exceptionally low by the Engineer, the sub-contract package shall be retendered.

The consequences of exceptionally low prices must be clearly outlined in the Tender Report and clearly explained to the PLC prior to award or retendering of the sub-contract packages.

- Payment to the Contractor

          - The Employer shall not remunerate the Contractor, other than what have been provided for in the payment items, for accepting higher tender sums tendered by Targeted Enterprises.

          - If the Contractor accepts tender sums that are higher than what have been provided for in the Contractor’s tendered rates, or the Employer’s provisional and/or prime cost sums, the costs shall be paid by the Contractor from the Lump Sum which he tendered for the fluctuation between the Contractor’s rates and that of the Targeted Enterprise sub-contractors.

- Entering the Sub-contract Agreement

The Contractor’s TE Procurement Coordinator shall assist successful Targeted Enterprises to enter into a sub-contract agreement with the Contractor as described in this Specifications.

D1008	GENERAL RESPONSIBILITIES OF THE CONTRACTOR TOWARDS TARGETED ENTERPRISES

The Contractor shall have the responsibilities described in this Section, D1008 of the Specifications, towards all Targeted Enterprises sub-contracted in terms of the CPG as stated in the Specification Data.

            - The Employer’s Independent Targeted Enterprise Monitor

The Employer shall, through its Transformation Unit, appoint an independent Targeted Enterprise Monitor, who shall audit the Contractor with respect to his obligations to Targeted Enterprises and who shall report his findings to the Employer’s Project Manager, the Engineer, and the Regional Transformation Officer (RTO) monthly.

            - Failure to Comply with Responsibilities Towards Targeted Enterprises

If the Contractor, in the opinion of the Employer’s Project Manager or the Engineer, fails to comply with its responsibilities towards Targeted Enterprises, the Engineer shall issue a written warning to the Contractor, stating all the areas of non-compliance.  The Contractor’s time to correct shall be stated in the letter and shall be in accordance with the relevant specifications for the aspects of non-compliance.

A copy of the letter of warning shall be forwarded to the Employer’s Project Manager and the Targeted Enterprise Monitor shall monitor that corrective action is taken by the Contractor.

Failure by the Contractor to comply with a deadline, will be sufficient grounds for the Employer to apply a penalty or institute a claim in accordance with the relevant Conditions of Contract.

D1008.01	Targeted Enterprise (TE) Operations Manager

The Contractor shall appoint a dedicated TE Operations Manager whose sole responsibility shall be to assist the Contractor with the execution of his responsibilities towards Targeted Enterprises and Target Groups as prescribed in this Section D of the Specifications, with an emphasis on D1008 and D1010. The Targeted Operations Manager Operations shall spend at least 10 working days on this project.  Irrespective of the contractual relationship between the TE Operations Manager and the Contractor, the TE Operations Manager shall not perform any other duties than that of a dedicated TE Operations Manager on a full-time basis for this Contract.

- TE Operations Manager’s Obligations

Amongst others, the TE Operations Manager shall facilitate the training, mentoring, guidance, coaching, development, and support of Targeted Enterprises as per the Contractors approved Training and Skills Development Programme (see Section D1010 of the Specifications).

The TE Construction Manager shall submit monthly TE Progress Reports in the Employer’s reporting format.  The report shall be submitted to the Employer’s Project Manager and Regional Transformation Officer, the Engineer and the Contractor, at least one week prior to the monthly site progress meeting.

This report shall include, amongst others:

      - Details of TEs trained, e.g., number, hours, value, modules, credits obtained, etc.

      - Details of TEs sub-contracted, e.g., number, packages, values, etc.

      - Details of TEs performance on the work packages, and skills gaps to be addressed, etc.

      - Details of TEs growth and sustainability, e.g., CIDB grading upgrades, business success, etc.

      - Details of disputes and the associated interventions and/or resolutions.

- TE Operations Manager’s Qualifications and Experience

The TE Operations Manager shall have as a minimum a National Diploma: Management of Engineering Construction Processes (NQF Level 5) or an equivalent qualification.

The TE Operations Manager shall have at least 5 years’ experience as a Site Agent or equivalent position, or in the management or execution of civil, electrical or electronic engineering projects (construction or operation projects). In addition, he shall have ample knowledge of, and experience in, the requirements of training and mentoring in the civil, electrical or electronic engineering environment.

- TE Operations Manager’s Team

No Senior TE Site Supervisors, and no TE Site Supervisors will be required. The obligations of Senior TE Site Supervisors and TE Site Supervisors will be carried out by the TE Operations Manager.”

D1008.02	General Obligations

The Contractor shall, with the assistance of the TE Operations Manager, comply with the following general obligations:

- Assist the Targeted Enterprises in instituting a quality assurance system.

- Provide adequate training, coaching, guidance, mentoring and any other identified and approved assistance to Targeted Enterprises and their employees.

- Provide support and any other identified and approved assistance to ensure that the Targeted Enterprises meet their obligations and commitments with respect to their sub-contracts.

- Assist Targeted Enterprises to monitor and manage the schedules, costs, and cash flows of their sub-contracts.

- Endeavour to avoid sub-contract disputes and if disputes do arise, facilitate a process to find an amicable solution.

- Ensure that the CPG objectives are achieved.

D1008.03	Sub-contract Agreements

The Contractor shall conclude sub-contract agreements with each sub-contracted Targeted Enterprise and shall utilise the Employer’s proforma document for Targeted Enterprise sub-contracting (see Annexure X3)as an example, which is based on the 2011 FIDIC Conditions of Sub-contract for Construction and shall be in accordance with the provisions of amended sub-clause 4.4 of the Conditions of Contract and shall be consistent with the terms and conditions of this Contract.

- Special Conditions of Contract

The following Special Conditions of Contract forms part of the sub-contract agreement:

      - The Targeted Enterprise’s entitlement to receive the training contemplated in this Contract (Part C1, C1.2.1, Part B, clause 6.8).

      - The Targeted Enterprise’s obligation to participate and co-operate in the training provided for in this Contract (Part C1, C1.2.1, Part B, clause 6.5).

      - The allowable sources from which Labour may be drawn in terms of the Contract (Part C1, C1.2.1, Part B, clause 6.8).

      - The terms and conditions relating to the recruitment, employment and remuneration of Labour engaged on the Contract (Part C1, C1.2.1, Part B, clause 6.5).

      - The training to be provided to the Targeted Enterprise’s workforce (Part C1, C1.2.1, Part B, clause 6.8).

      - The terms and conditions related to payment of the Targeted Enterprise (Part C1, C1.2.1, Part B, clauses 14.6 to 14.8 and 15.3).

      - Sanctions in the event of failure by the Targeted Enterprise to comply with the terms and conditions of the sub-contract agreement (Part C1, C1.2.1, Part B, clauses 14.6 and 20.4 to 20.7).

      - Dispute avoidance and resolution procedures (Part C1, C1.2.1, Part B, clauses 20.4 to 20.7).

Further Special Conditions of Contract required by the Contractor shall only be included into the sub-contract agreement once approved by the Employer and the Engineer.

- Monitoring of Sub-contract Agreements

The proforma sub-contract agreement for each group of work packages shall be tabled to the Employer’s Independent Targeted Enterprise Monitor for his review and confirmation that sub-contract agreements are in terms of the Employer’s requirements and policies.

In addition, the PLC may request proof that sub-contract agreements were entered into with the sub-contracted Targeted Enterprises.  The PLC may request insight into the Conditions of Subcontract and Sub-contract Data.

To protect Targeted Enterprises’ competitive advantage and/or tender strategy, only the sub-contract agreement shall be available to the PLC for perusal and not the pricing structure and/or Schedule of Quantities.

A copy of each sub-contract agreement shall be filed with the Engineer after confirming that it is in accordance with the provisions of this Contract.

D1008.04	Payment of Targeted Enterprises

Targeted Enterprises shall be paid the rates and/or Provisional Sums, which they have tendered, or which have been negotiated as described in this Section D of the Specifications.

    - Payment of Provisional and General Obligations

Provision shall be made in the sub-contract agreement for the Targeted Enterprise’s preliminary and general obligations (P&Gs), which shall be calculated as a minimum of 15% of the value of the scheduled sub-contract work items.

Where the Contractor’s sub-contract work is not paid from a Provisional Sum, the P&Gs of the Targeted Enterprise shall be paid from the Lump Sum tendered by the Contractor for the P&Gs of Targeted Enterprises.

P&Gs shall be paid to Targeted Enterprises as per Section PC1.3.1 of the COTO specification payment items, i.e.:

C1.3.1.1 paid in 3 instalments of 50%, 35% and 15%.

C1.3.1.2 paid as a percentage of the total value progressively per certificate.

C1.3.1.3 paid monthly for the sub-contractor’s contract duration.

- Monitoring of Payment of Targeted Enterprises

The Employer’s independent Targeted Enterprise Monitor shall audit the Contractor’s Payment of Targeted Enterprises to ensure timeous and correct payment in terms of the Employer’s requirements and Policies and shall report his findings to the Employer’s Project Manager on a regular basis.

D1008.05	Quality of Work and Performance of Targeted Enterprises

          - Ensuring Quality of Work and Performance

The purpose of the Employer’s CPG is to, amongst others, enhance the utilisation and development of Targeted Enterprises.  Thus, while the Contractor remains responsible for the quality of work and performance of Targeted Enterprises, he may not neglect the developmental requirements in the sub-contracting of Targeted Enterprises.

It is thus emphasised that the Contractor’s TE Construction Manager shall closely monitor and supervise all Targeted Enterprises and shall train, coach, guide, mentor and assist each Targeted Enterprise in all aspects of management, execution, and completion of its sub-contract.  This shall typically include assistance with planning of the Works, sourcing and ordering of materials, labour relations, monthly measurements, and invoicing procedures.  The extent and level of such training, coaching, guidance, mentoring, and assistance to be provided by the Contractor shall commensurate with the level of sub-contract applicable and shall be directed at enabling the Targeted Enterprise to achieve the successful execution and completion of its sub-contract.

          - Failure by the Targeted Enterprise to Comply

If the Targeted Enterprise, in the opinion of the Engineer, fails to comply with any of the criteria listed below, the Engineer shall issue a written warning to the Contractor, stating all the areas of non-compliance.  A copy of the letter of warning shall be forwarded to the Employer's Project Manager and the Employer’s independent Targeted Enterprise Monitor.  The criteria are as follows:

- Deliver acceptable standard of work as set out in the specifications.

- Progress in accordance with the time constraints in the sub-contract agreement.

- Punctual and full payment of the workforce and suppliers.

- Site safety.

- Accommodation of traffic.

          - Assist the Targeted Enterprise to Make Good

The Contractor shall, in terms of the sub-contract agreement (Part C, clause 3.1.12), give reasonable warning to the Targeted Enterprise when any contravention of the terms and conditions of the sub-contract agreement has occurred or appears likely to occur.

The Contractor shall, together with the Targeted Enterprise, identify the causes that led to failure to comply and jointly develop a plan to rectify, which plan shall be submitted to the Employer’s Project Manager and the Engineer for information purposes.

Based on the plan to rectify, the Contractor shall give the Targeted Enterprise reasonable opportunity to make good any such contravention, or to avoid such contravention, and shall render all reasonable assistance to the Targeted Enterprise in this regard.

          - Monitoring Execution of the Plan to Make Good

The Employer’s independent Targeted Enterprise Monitor shall review plans to rectify and monitor the execution thereof to ensure that Targeted Enterprises are given a fair opportunity to rectify within a developmental environment.  He shall report his findings to the Employer’s Project Manager monthly.

D1008.06	Dispute Avoidance and Resolution Procedures

When any disputes arise, the Contractor shall within seven (7) calendar days inform the Employer's Project Manager, the Employer’s Targeted Enterprise Monitor, and the Engineer, in writing, of the details of the dispute.

      - Facilitate Dispute Avoidance

Prior to taking any action, the Contractor shall commence with a facilitation process by arranging a formal meeting with the Targeted Enterprise with the aim to find an amicable solution to the dispute.  The meeting shall be attended by the Employer’s Project Manager, the Employer’s Targeted Enterprise Monitor, and the Engineer to ensure a fair and transparent process in reaching a settlement.

If the parties are unable to find an amicable solution, the Contractor shall explain fully to the Targeted Enterprise the provisions in the sub-contract agreement to address disputes.  If action is necessary, it shall be discussed with the Employer’s Project Manager and the Engineer prior to any action being taken.

      - Support to Targeted Enterprise during Dispute Resolution Process

While the Employer’s Project Manager and the Engineer will observe the dispute resolution process to ensure fairness and transparency, the Targeted Enterprise may request consultation and assistance from the Targeted Enterprise Monitor.  The Targeted Enterprise Monitor will assist the Targeted Enterprise with the interpretation of the Conditions of Sub-contract and will guide the Targeted Enterprise during the dispute resolution process.

      - Issuing a Letter of Warning to Targeted Enterprise

The Contractor shall issue a letter of warning to the Targeted Enterprise, whom shall have 21 calendar days from the date of receipt of the letter of warning by the Contractor to address and rectify the issues raised by the Engineer, except for issues pertaining to Site Safety and Accommodation of Traffic, for which the reaction time shall be in accordance with the relevant specifications for those aspects of the Works, but which shall not be longer than 24 hours.

      - Failure by the Targeted Enterprise to Comply

Failure by the Targeted Enterprise to comply with a deadline, will be sufficient grounds for the Contractor to apply a penalty or terminate the sub-contract agreement provided that the Employer’s Project Manager and the Engineer are satisfied that the Contractor has made every effort to correct the performance of the Targeted Enterprise.

The Targeted Enterprise may dispute any ruling given or deemed to be given by the Contractor or the Engineer, within 21 calendar days after receipt thereof by submitting a written Dispute Notice to the Contractor, in terms of the relevant Conditions of the Sub-contract.

On request by the Targeted Enterprise, the Targeted Enterprise Monitor will assist the Targeted Enterprise with the interpretation of the Conditions of Sub-contract and will guide the Targeted Enterprise during the dispute resolution process.

D1009	WORK suitable for execution BY TARGETED ENTERPRISES

To assist the Contractor in achieving his CPG, the following work items have been identified as being suitable for execution by Targeted Enterprises:

- Erection and maintenance of the Contractor’s camp site

- Electronics works.

- CCTV cameras

- Provision of traffic control facilities.

- Installation and maintenance of lane equipment

- Construction of small concrete and other structures.

- Construction of concrete walkways.

- Pitching, stonework and protection against erosion.

- Erection of guardrails.

- Landscaping.

- Fencing.

- Road signs.

- Road markings.

- Finishing the road and road reserve.

- Plaza Security Services.

- Supply of plant.

- Supply of fuel.

- Specialised subcontract work such as:

    - General Building and Plaza Maintenance

    - Route Patrols

- Cleaning and Routine maintenance

The work to be carried out by Targeted Enterprises is not limited to the work listed above and the Contractor may need to engage Targeted Enterprises on other aspects of the Works to achieve the CPG.

In the event that the work is not or cannot specifically be designated for CIDB 1 and 2 Targeted Enterprise sub-contractors, then the Contractor shall use his best endeavours to define and package work for Targeted Enterprise sub-contractors with experience in aspects of Toll System Installation and Maintenance, Toll Plaza Lane maintenance, Toll Plaza security and Traffic Accommodation work.

D1010	TRAINING, COACHING, GUIDANCE, MENTORING and assistance

The Contractor shall with the input and support of the PLC develop a Training and Skills Development Programme which shall be managed by the Contractor’s TE Operations Manager

D1010.01	Purpose of the Training and Skills Development Programme(s)

Skills development forms an integral part of the Employer’s Transformation and Community Development Policies and hence, it is important to the Employer that Targeted Labour and Targeted Enterprises be equipped with skills that can be used to gain meaningful future employment and secure sub-contracting opportunities.

It is, therefore, a requirement of this Contract that the Contractor provide adequate training, coaching, guidance, mentoring and assistance to the Targeted Labour and Targeted Enterprises, to ensure skills development within the Construction Industry.

D1010.02	Skills Audit and Analysis

To develop the Training and Skills Development Programme(s), the Contractor shall conduct a skills audit and analysis of Labour on the Targeted Labour database and the Targeted Labour of sub-contracted Targeted Enterprises to determine their levels of education, existing qualifications, and skills sets.  The outcome of the skills audit and analysis shall be used to develop a Training and Skills Development Programme(s) that will benefit both the employee and the Construction Industry at large.

Included in the skills audit and analysis shall be a separate section, analysing the education, qualifications and skills sets of the Targeted Enterprise’s owners and their supervisors sub-contracted by the Contractor, to develop a Training and Skills Development Programme that will develop and improve the ability of small business owners and their supervisory staff to better manage their enterprises.

D1010.03	Developing the Training and Skills Development Programme

The Employer shall, through its Project Manager, be involved in the decision making and quality control pertaining to the development and implementation of the Training and Skills Development Programme facilitated through this Contract.

The Employer has no service agreement or memorandum of understanding with any education and training quality assurance body and, therefore, does not function as the “Employer” as defined under any three-party-agreement between the Trainee, the Training Provider, and the Employer.

The complete Training and Skills Development Programme shall be developed during the 1st  6 Months of the Contract, accepted by the Engineer after consultation with the Employer’s Project Manager, and tabled to the PLC for their information..

D1010.04	The Training Service Provider (Not Applicable)

D1010.05	Training and Skills Development Programme:  General Requirements

The Training and Skills Development Programme shall consist of Learnerships that include multiple, but related Unit Standards which are (1) relevant to the Works to be constructed, (2) aimed at achieving the skills development objectives of the Programme, and (3) lead towards a formal qualification in the Construction Industry.

Learnerships shall include both the theoretical and practical components of each Unit Standard and shall be in accordance with the various laws and regulations contained in the South African Qualification Authority (SAQA) statutes.

      - Training Programme Requirements and Considerations

The Skills Audit and Analysis shall inform the Contractor of every employee’s Recognised Prior Learning (RPL) skills and competencies, which shall be taken into consideration in the development of the Training and Skills Development Programme so that the RPL skills and competencies, together with the Training Programme Unit Standards offerings, will lead to a full Learnership outcome and hence a formal qualification.

It is recognised that the Training and Skills Development Programme may consist of several Unit Standards but totalling insufficient credits for a full Learnership qualification.  Nevertheless, the competencies and credits achieved in the Programme shall contribute to a full Learnership by a later acquisition of the outstanding Unit Standards required for the full Learnership.

The Training and Skills Development Programme shall be structured in a manner to prioritise those Unit Standards that will equip Trainees with the minimum skills and competencies required to become economically involved in the execution of the Works as soon as possible.

The Training Service Provider shall apply the SAQA Learnership criteria of which the basic elements are listed below to demonstrate the Employer’s requirements:

        - Minimum credits for qualification.

        - Fundamental Unit Standards and credit values.

        - Core Unit Standards and credit values.

        - Elective Units Standards and credit values.

        - Assumption that NQF Level 3 literacy, numeracy, and computer competencies exist.

        - RPL processes.

        - Exit level outcomes.

The above criteria are not exhaustive, and the Training Service Provider shall apply the systems and processes required by the relevant SAQA and other related legislation pertinent to training.  The Training Service Provider shall regularly consult the SAQA website (www.saqa.org.za) to ensure that the most current Unit Standards are presented.  In the event of any conflict, the legislated requirements shall apply.

While structuring the Learnership offerings, the Training Service Provider shall distinguish between the levels of learning required.  The bulk of the training shall focus on NQF Levels 4 and 3.  NQF Level 5 training is not anticipated but may be suitable for qualifying staff of established small contractors.  The qualification titles for the respective NQF Levels are:

- NQF Level 3 	National Certificate:	Construction Roadworks.

- NQF Level 4	National Certificate:	Supervision of Construction Processes

- NQF Level 4	National Certificate:	Business Management

- NQF Level 5 	National Diploma:   	Management of Civil Engineering 			Construction Processes

It may be necessary to include additional Core Unit Standards, e.g., “Tendering” or “Entrepreneurship” as an additional Unit Standard for NQF Level 4, to achieve the Contract’s development objectives.  The identification of any additional Unit Standards shall be discussed with the Engineer and shall not be implemented without prior approval.

Before qualifying, Trainees will be expected to demonstrate competence in a practical situation that integrates the assessment of all specific outcomes, for all Unit Standards in the Learnership Programme.

All training shall take place within normal working hours, or as agreed with the trainees.

      - Selection of Trainees

To complete a Learnership successfully requires minimum literacy and numeracy competencies as defined by SAQA.  The Training Service Provider shall utilise the skills audit and analysis and conduct additional skills analysis to benchmark the literacy and numeracy levels of Targeted Labour and Targeted Enterprises and their employees.  This information shall guide the Training Service Provider in formulating the Trainee selection methodology(ies) and process(ess).  The Training Service Provider shall make provision for:

- baseline assessments, e.g., conducting RPL enquiries and tests, and

- a skills gap programme consisting of Fundamental Unit Standards, to facilitate the selection process.

Trainees identified as having already acquired some tertiary training, particularly in the field of Civil Engineering, may be suitable for a specialised Trainee programme or a higher NQF Level programme.  The Training and Skills Development Programme shall, therefore, make provision for Trainees with a variety of competency levels and shall make provision for different levels of training.

It should be noted that where this Section D of the Specifications refers to the selection and training of Trainees, any person, employed by any national, provincial, or local authority, being it full time or part time, is expressly excluded from being considered for this training.

      - Learning Material

Learning material is required for each Unit Standard.  This learning material is the equivalent of prescribed textbooks for other qualifications.  Each Trainees shall receive a copy of the learning material to learn the contents and to use it as reference source after obtaining the qualification.

The SAQA Unit Standard curriculums define the contents of the learning material. The learning material shall not only comply with the SAQA and CETA guidelines but shall be technically and practically aligned to road construction and/or road maintenance.  Any input from a subject matter expert required to ensure the appropriateness of a learning material contents shall be included in the Training Service Provider’s costs.

The requirements to be addressed in learning material as outlined by the SAQA Unit Standard curriculums are, amongst others, the following:

- Purpose of the Unit Standard.

- Specific outcomes (typically 4 per Unit Standard).

- Assessment criteria (typically 4 per specific outcome).

- Range as is defined for each specific outcome.

- Critical cross-field outcomes for the Unit Standard.

- Unit Standard essential embedded knowledge.

      - Student Experiential Training or Learnerships or Internships

The Employer may deploy students to the construction site to obtain experiential training.  The Contractor shall provide experiential training to these students in accordance with the relevant academic institution’s requirements, which is typically a university, a university of technology, or a TVET.

The Contractor shall also provide students with all the tools (including appropriate information technology hardware and software) and site office space necessary to carry out engineering work as if they were the Contractor’s own permanent staff.

Reporting on training progress of each student shall be compiled according to the formats and intervals set be the relevant academic institution.

      - Keeping of Records

The Training Service Provider shall keep comprehensive records of the training provided to each Trainee and shall ensure that Trainees’ successful completion of successive Unit Standards are entered onto the national SAQA database.  After the successful completion of generic skills courses each Trainee shall be issued with a certificate indicating the course contents as proof of attendance and completion.  The Contractor shall keep a register of certificates issued.  Whenever required, the Contractor shall provide copies of such records to the Engineer.

(Note to Compiler: for projects with a Works Construction Period of 12 months or more, the CIDB Standard for Developing Skills through Infrastructure Contracts (August 2013) – Government Gazette No. 36760, should apply as set out under D1010(g) below.  Sub-clause (e) and (f) above should then be deleted and (g) and the rest of the sub-clauses renumbered starting with (e).)

      - Skills Development Requirements

- Contract Skills Development Goals (CSDG)

This section establishes a minimum CSDG which is to be achieved in the performance of a Contract (as per the CIDB Standard for Developing Skills through Infrastructure Contracts August 2013) in relation to the provision of different types of workplace opportunities linked to work associated with a Contract which culminate in or lead to:

      - a part- or full occupational qualification registered on the National Qualification Framework,

      - a trade qualification leading to a listed trade (GG No. 35625, 31 August 2012),

      - a national diploma registered on the National Qualification Framework, and

      - registration in a professional category by one of the professional bodies listed in Table 1 of the Standard.

The Contractor shall achieve or exceed the CSDG in the performance of the Contract.  The Contractor may, if need be, devolve their obligations onto Sub-contractors.

The CSDG shall not be less than the contract amount multiplied by 0.25 percent (%) for Civil Engineering work (CE).  For this reason, the Contractor shall insert the CSDG amount in Form C.2.3 Summary of Pricing Schedule.

- Achieving Contract Skills Development Goal (CSDG)

The Contractor shall achieve the CSDG by providing employment opportunities to Trainees requiring structured workplace learning using one or a combination of any of the following methods in relation to work directly related to the Contract:

Method 1:	Structured workplace learning opportunities for Trainees (LoL) towards the attainment of a part or a full occupational qualification.

This training method shall apply to Targeted Enterprises and Targeted Labour.

Method 2:	Structured workplace learning opportunities for apprentices or other artisan Trainees (LoA) towards the attainment of a trade qualification leading to a listed trade (GG No. 35625, 31 August 2012) subject to at least 60% of the artisan Trainees being holders of public FET college qualifications.

This training method shall apply to Targeted Enterprises and Targeted Labour.

Method 3:	Work integrated learning opportunities for University of Technology or Comprehensive University students (LoUS) completing their national diplomas.

This training method shall apply to P1 and P2 Trainees, or Trainees with a 240 credits qualification.  Both the permanently employed and temporary employed Trainees shall be considered under this training method.

Method 4:		Structured workplace learning opportunities for candidates (LoC) toward registration in a professional category by a statutory council listed in Table 1 of the Standards.

This training method shall apply to Candidates with 480 credits qualification.  Both the permanently employed and temporary employed Trainees shall be considered under this training method.

No single method shall contribute more than 75 percent of the CSDG. Permanently employed Trainees may not account for more than 33 percent (%) of the CSDG, and not more than one method may be applied to any individual concurrently in the calculation of the CSDG.

- CSDG Credits

The CSDG shall be calculated by multiplying the number of people employed by the Contractor and placed for continuous training opportunities in a three-month period by the notional values contained in Table 3 of the Standard, or as revised in a Gazette notice.

The Contractor may source beneficiaries of the CSDG from a Skills Development Agency (SDA) recognised by the cidb.

All beneficiaries shall be registered with a construction Skills Development Agency (SDA) recognised by the cidb.

- Denial of Credits

Credits towards the CSDG shall be denied should the Contractor not fulfil all the requirements listed in clause 3.4 (a) to (f) of the Standards.

- Compliance with Requirements

The Contractor shall comply with the requirement as set out in clause 4 of the Standards.

- Records

The Contractor shall submit all the documentation required in terms of clause 4 of the Standards, in a timely manner and according to a prescribed format where applicable.

The Engineer shall certify the value of the credits counted towards the CSDG, if any, whenever a claim for payment is issued to the Employer and shall notify the Contractor of this amount.

The Contractor shall, upon termination of the opportunities provided to satisfy the CSDG, certify the quantum and nature of the opportunity and submit the certificate, counter-certified by the relevant individual, to the Engineer for record-keeping purposes.

- Sanctions

Failure to achieve the CSDG shall render the Contractor liable for a penalty as prescribed in clause 8.7 of the FIDIC Conditions of Contract.  Penalties shall be as follows:

- Penalty = 0.5 x {[LoAs + LoLs + LoUSs + LoCs]}

Where:

LoLs =	Monetary Value of the shortfall for structured workplace learning opportunities for Trainees towards the attainment of a part or a full occupational qualification.

LoAs =	Monetary Value of the shortfall for structured workplace learning opportunities for apprentices or other artisan Trainees towards the attainment of a trade qualification leading to a listed trade (GG No. 35625, 31 August 2012) subject to at least 60% of the artisan Trainees being holders of public FET college qualifications.

LoUSs =	Monetary Value of the shortfall for work integrated learning opportunities for University of Technology or Comprehensive University students completing their national diplomas (LoUS).

LoCs =	Monetary Value of the shortfall for structured workplace learning opportunities for candidates towards registration in a professional category by a statutory council listed in Table 1 of the Standards (LoC).

- Delay the issuing of the Performance Certificate until all the required records described in clause 5 of the Standards are received.

      - Toll Plaza maintenance and systems related Training

The Contractor’s Training and Skills Development Programme shall include Toll Plaza maintenance and systems related training.

The Contractor shall make representation to the Employer’s Project Manager and the Engineer, who shall approve candidate trainees that should attend such courses as they deem appropriate. Selected trainees shall comprise of Target Enterprises or selected members of Affected Communities. Trainees shall receive formal Toll Plaza maintenance and systems skills training in a programmed and progressive manner.

Typical training programmes could comprise some or all the following modules:

- Electrical and Mechanical systems,

- General computer and IT systems

- Toll Plaza Operations and Maintenance.

- Other suitable general plaza maintenance

Where possible skills training shall be accredited by the relevant Sector Education and Training Authority (SETA) and shall be provided with accredited entities and/or individuals.

      - Generic Skills Training

Generic skills shall be taught where the need has been identified and approved by the Employer’s Project Manager and the Engineer.

The Contractor shall make representation to the Employer’s Project Manager and the Engineer, who shall approve candidates that should attend such courses as they deem appropriate.  Those selected shall receive formal generic skills training in a programmed and progressive manner.  The PLC may also identify a need for generic skills training.

Typical training programmes could comprise some or all the following modules:

- Basic hygiene and HIV/AIDS awareness.

- Road safety.

- Basic management of the environment.

- Tourism awareness and opportunities.

- Managing personal finance.

- Adult Basic Education and Training (ABET).

- Community based training programmes (e.g., knitting, computer skills, plant/ machine operator, etc.).

All generic skills training shall be accredited by the relevant Sector Education and Training Authority (SETA) and shall be provided with accredited entities and/or individuals.

      - Community Training

Community training shall be taught where the need has been identified.  Affected Communities may submit their training needs to the PLC for the Contractor’s consideration and inclusion into the Training and Skills Development Programme.

While considering the training needs of affected Communities, the Engineer shall inform the PLC of the Contract’s training limitations, as well as of the training that could be undertaken through the Contract.

Trainees from the Community shall be identified through the Community structures and with the input and support of the PLC.  Trainees selected from the Community shall receive formal skills training in a programmed and progressive manner in compliance with sub-clause (d).  Priority shall be given to training that will equip Community members with skills that will enhance their employability.

All community skills training shall be accredited by the relevant Sector Education and Training Authority (SETA) and shall be provided with accredited entities and/or individuals.

      - Training Facilities

The Contractor shall be responsible for providing everything necessary to offer the various training workshops and modules including:

- a suitable venue with sufficient furniture, lighting, and power,

- all necessary stationery consumables and study material,

- transport for attendees.

D1011	LABOUR ENHANCED CONSTRUCTION (Not applicable)

D1012	COMMUNITY DEVELOPMENT

D1012.01	Corporate Social Investment (CSI)

The Contractor shall demonstrate its willingness to actively participate in the social development initiatives for local Communities affected by the Contract.  To this end, the Contractor shall provide details of CSI initiatives it will actively pursue under Form D15: Corporate Social Investment.

D1013	MEASUREMENT AND PAYMENT

Item			Unit

D10.01	Target Group Participation

|  | Contract Participation Performance bonus. | Prime Cost (PC) Sum |
| --- | --- | --- |

The prime cost sum for item D10.01(a) shall cover any CPP bonus due as specified in clause D1003(e). The prime cost sum shall be expended in accordance with clause 13.5 of the FIDIC Conditions of Contract.

Note:

No separate payment shall be made for any costs incurred by the Contractor, whether direct or indirect, for his efforts in accomplishing the specified requirements, and which are not recoverable from the pay-items allowed.  Such costs shall be deemed to have been included in the rate offered under pay sub-item C1.3.1.3 Contractor’s Establishment on Site and General Obligations:  Time Related Obligations.

Item			    Unit

D10.02	Stakeholder and Community Liaison and Social Facilitation

| (a) | Cost of liaison, social facilitation, and PLC support. | Prime Cost (PC) Sum |
| --- | --- | --- |
| (b) | Handling cost and profit in respect of sub-item D10.02(a). | Percentage (%) |

The prime cost sum for item D10.02(a) shall cover the direct costs incurred by attending members of the PLC.  The rate of compensation shall be fair and agreed by the Engineer in accordance with clause 13.5 of the FIDIC Conditions of Contract.  The tendered percentage for sub-item D10.02(b) shall include full compensation for all handling costs and profit of the Contractor associated with sub-item D10.02(a).

The liaison with, and assistance provided by the Contractor to the PLC to perform its duties shall not be paid from the prime cost sum.  The Contractor’s costs to liaise with the PLC and render such assistance shall be deemed to have been included in its rate offered for pay sub-item C1.3.1.3, Contractor’s Establishment on Site and General Obligations:  Time Related Obligations.

Item		  		Unit

D10.03	Tender Process for Targeted Enterprises

| (a) | Contractor’s charge for the management and execution of the Targeted Enterprise procurement process: |  |  |
| --- | --- | --- | --- |
|  |  | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise sub-contractors for value of work ranging between R 500 000 to R 1 000 000 or if applicable of CIDB 1 and 2 contractor grading. | Number (No) |
|  | (ii) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise sub-contractors for value of work ranging between R 1 000 001 and 6 000 000 or if applicable of CIDB 3 and 4 contractor grading. | Number (No) |
|  | (iii) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise sub-contractors of above R 6 000 000 or CIDB 5 and higher contractor grading. | Number (No) |
|  | (iv) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise suppliers. | Number (No) |
| (b) | Targeted Enterprise Procurement Coordinator |  | Month |

The unit of measurement for item D10.03(a) shall be the number of individual sub-contract agreements concluded with Targeted Enterprise sub-contractors and suppliers in accordance with the procurement process described in this Section D of the Specifications.

The tendered monthly rate for sub-item D10.03(b) shall include full compensation for the provision of the relevant personnel on a full-time basis to carry out the requirements in terms of sub-item D10.03(a) and the full contents of this Section D of the Specifications.

Each tendered rate shall be in full compensation for the management and execution of the Targeted Enterprise procurement process in the relevant CIDB contractor grading designation scheduled, including for the appointment of a TE Procurement Coordinator (if required), the pre-tender training of eligible Targeted Enterprises, the compilation, printing, binding and issue of the tender documents for each tender, for the advertising of each tender, for the provision of the venue and the conducting of each compulsory briefing session for tenderers, for the conducting of each tender opening process, for the adjudication of the tenders received for each tender, for the preparation of each tender adjudication report and the review thereof in conjunction with the Employer, Engineer and the PLC, for the award of each tender and for the conclusion of the sub-contract agreement with each successful Targeted Enterprise tenderer, and any other relevant requirement described in this Section D of the Specifications.

Item			    Unit

D10.04 	Responsibilities of the Contractor towards Targeted Enterprises

| (a) | Contractor’s establishment, management, management support, assistance, coaching, guidance, mentoring and supervision of Targeted Enterprises. | Month |
| --- | --- | --- |
| (b) | Targeted Enterprise Operations Manager | Person Month |

The tendered monthly rate for sub-item D10.04(a) shall include full compensation for the registration of all the sub-contract agreements and the management of all the Targeted Enterprise sub-contracts, including for the provision of the necessary management, support, coaching, guidance, mentoring and supervision of the Targeted Enterprise sub-contractors.

The tendered monthly rate for sub-items D10.04(b) shall include full compensation for the provision of the relevant personnel on a full-time basis to carry out the requirements in terms of sub-item D10.04(a) and the full contents of this Section D of the Specifications.

Item			Unit

D10.05	Construction Works by Targeted Enterprises

| (a) | Payments associated with the construction works executed by Targeted Enterprise sub-contractors of CIDB 1 and 2 contractor grading designation appointed in terms of Section D of the Specifications. (Note to Compiler: The Prov sum allowance in the pricing schedule shall be the CPG target percentage, for CIDB 1 and 2 contractors as stated in Section B clause D1003.04. | Provisional (Prov) sum |
| --- | --- | --- |
| (b) | Handling costs and profit in respect of payment associated with sub-item D10.05(a). | Percentage (%) |
| (c) | Fluctuation between the main contractor’s rates and that of the Targeted Enterprise sub-contractors. | Lump Sum (LS) |
| (d) | Preliminary and General Obligations of Targeted Enterprise sub-contractors appointed in terms of Section D of the Specifications. | Lump Sum (LS) |

Expenditure under sub-items D10.05(a) shall be in accordance with clause 13.5 of the FIDIC Conditions of Contract.

The Provisional Sum for sub-item D10.05(a) is provided to cover the cost of the construction works, including preliminary and general obligations, carried out by the Targeted Enterprise sub-contractors of CIDB 1 and 2 contractor grading designation as certified by the Engineer, in separate payments for each Targeted Enterprise in accordance with Section D of the Specifications.  Expenditure under sub-item D10.05(a) shall be limited to the Provisional Sum amount stated in the Pricing Schedule. Construction works by Targeted Enterprise sub-contractors of CIDB 1 and 2 contractor grading designation, exceeding the Provisional Sum amount shall be measured for payment from the applicable work items in the Contractor’s pricing schedule

The tendered percentage for sub-item D10.05(b) is the percentage of the amount spent under sub-item D10.05(a) and shall include full compensation for the Contractor’s handling costs, profit or any other costs associated with the work conducted by the Targeted Enterprise sub-contractors, which are not provided for in other pay-items.

The Lump Sum tendered under item D10.05(c) is for fluctuation of the Targeted Enterprise sub-contractor rates more than the contractor’s tendered rates, for work not paid under items D10.05(a).  Payment of the Lump Sum shall be on a prorata basis to provide compensation for the fluctuation between the tendered rates of the Main Contractor and that of the Targeted Enterprise sub-contractors until the Lump Sum is depleted.  Any costs incurred due to fluctuation in tendered rates more than that tendered for under item D10.05(c) will be for the Contractor’s account.  Item D10.05(c) is applicable where the Target Enterprise sub-contractor’s tender amount is higher than the Main Contractor’s tender amount.  The Lump Sum will cover the fluctuation for all the tendered rates of the sub-contractors.

The Lump Sum tendered under item D10.05(d) is for the Preliminary and General Obligations of Targeted Enterprise sub-contractors (excluding CIDB 1 and 2 contractor grading designation) paid from the Provisional Sum.  Payment of the Lump Sum shall be on a prorata basis to provide compensation for the P&Gs of Targeted Enterprise sub-contractors until the Lump Sum is depleted.  Any costs incurred for the P&Gs of Targeted Enterprise sub-contractors more than that tendered for under item D10.05(d) will be for the Contractor’s account.

Item    	          Unit

D10.06	Training, coaching, guidance, mentoring and assistance

| (a) | Training Costs |  |  |
| --- | --- | --- | --- |
|  | (i) | Accredited NQF training. | Provisional (Prov) sum |
|  | (ii) | Accredited generic skills training. | Provisional (Prov) sum |
|  | (iii) | Community skills training | Provisional (Prov) sum |
|  | (iv) | CTROM maintenance specific training | Provisional (Prov) sum |
|  | (v) | Handling cost and profit in respect of sub-items D10.06(a)(i), (ii), and (iii) and (iv). | Percentage (%) |
| (b) | Student experiential training. |  |  |
|  | (i) | Student stipends | Prime cost (PC) sum |
|  | (ii) | Provision of experiential training | Person month |
| (c) | Other costs during training. |  | Provisional (Prov) sum |
| (d) | Training venue. |  | Lump Sum |

The Provisional Sums under sub-items D10.06(a) shall be paid in accordance with the provisions of sub-clause 13.5 of the FIDIC Conditions of Contract.  The Provisional Sums shall include all charges for the provision and delivery of the service including an accredited Training Service Provider (if required), learning material and any other requirement as described in Section D1010 of the Specifications.

The rate tendered under sub-item D10.06(a)(v) shall be deemed to cover all costs required to organise accredited trainers to provide training and shall include the Contractor's handling cost, profit, record keeping, reporting and all other costs associated with sub-items D10.06(a)(i) - iv).

The prime cost sum under sub-item D10.06(b)(i) shall be paid in accordance with the provisions of sub-clause 13.5 of the FIDIC Conditions of Contract.  The prime cost sum shall cover the monthly stipend as prescribed by the Employer to be paid to students receiving experiential training.

The unit of measurement for sub-item D10.06(b)(ii) shall be the person-month, with pro-rata payments made for partial months for training provided based on 23 workdays per month.

The rate tendered under sub-item D10.06(b)(ii) shall include full compensation for the Contractor to provide training to the students provided by the Employer inclusive of all costs to communicate with the Employer and any other body or organisation in respect of work assigned to the students.  The rate tendered shall include telephone calls and charges, stationery and information technology hardware, software, connection or licence costs and lost production, profits, and all other incidentals as well as all administrative and overhead costs.

The Provisional Sum under pay-item D10.06(c) shall be paid in accordance with the provisions of sub-clause 13.5 of the FIDIC Conditions of Contract.  The Provisional Sum shall cover the Contractor’s costs for payment of wages of employed trainees attending training courses during working hours, for the provision of meals to trainees, for provision of transport and for all other incidentals required for the trainees and approved by the Engineer.  No mark-up is payable to the Contractor under this item.

The unit of measurement for pay-item D10.06(d), shall be the Lump Sum.  The sum tendered shall include full compensation for the provision of the training venue, for all necessary lighting, power, furniture, stationery, consumables and study material and all other costs necessary to maintain the venue for the duration of the contract.  Payment of the Lump Sum shall be made in two instalments as follows:

The first instalment, 75% of the Lump Sum, shall be paid after the Contractor has met all his obligations regarding the provision of the training venue as specified.

The second and final instalment, 25% of the Lump Sum, shall be paid after the provision of all the accredited training as specified in the document.

No payment, nor pro rata payment, shall be made for trainees that, once selected, do not attend or only partially complete structured training courses.  The Contractor’s own staff may attend the courses provided.  However, such attendants from the Contractor’s staff shall not be considered for measurement and payment purposes unless they also qualify as Targeted Labour.

ANNEXURE X1 – CONTRACT PARTICIPATION GOAL (CPG) PLAN FORMAT

Contractor Logo and details

Contract Participation Goal Plan

SANRAL Contract Number: XXXX

Contract Name: XXXX

(SANRAL Logo)

Author:

Date:

Version

# INTRODUCTION

# OBJECTIVE

# TARGETED ENTERPRISES

## List of Work Packages for Targeted Enterprises

## List of Work Packages for Main Contractor

Table 1:  CPG Expenditure Breakdown

| Project Number |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |
| Designated Groups | Final Contract Value |  | R |  |
|  | Min (TE) CPG Target |  | % |  |
|  | Min (TE CPG Target Amount |  | R |  |
| Description of CPG Category | CPG Target as per Contract |  | CPP Planned Achievement |  |
|  | Min. Target % as per Contract | Target Amount | Min. Allocated % as per Market Analyses | Expected Amount |
| Targeted Labour (TL) | Min. xx% of Final Contract Value | R | % | R |
| Youth |  |  |  |  |
| Women |  |  |  |  |
| Disabled |  |  |  |  |
| Other |  |  |  |  |
| Targeted Enterprise (TE) | Min. xx% of Final Contract Value | R | % | R |
| Youth |  |  |  |  |
| Women |  |  |  |  |
| Military Veterans |  |  |  |  |
| Disabled |  |  |  |  |
| CIDB 1 and 2 |  |  |  |  |
| CIDB 3 and 4 |  |  |  |  |
| Other |  |  |  |  |

## Breakdown of Work Packages

The table below describes the work package breakdown with reference to Designated Groups and Functionality:

Table 2:  Breakdown of Work Packages

| Project Number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract Price |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CPG Target % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CPG Target Value |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Type of Work Package | EME or QSE | TE Amount | % of CPG Value | Proposed CIDB Grading | Tender Value Limit | Proposed No. of Work Packages | Proposed TE Target Group Amount |  |  |  |  | CIDB Expenditure |  |  |
|  |  |  |  |  |  |  |  | Black Youth | Black Woman | Black Military Veterans | Black Disabled | Other | Black 1&2CE | Black 3&4 CE | Comment |
| TE Sub-contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TE Suppliers and Service Providers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TE Sub-contractor Sub-total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TE Supplier/Service Provider Sub-total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provisional Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provisional % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Target Amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Target % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Schedule of works and CPG Expenditure Plan

    - Schedule of work (Insert Programme)

    - CPG Expenditure Plan

Table 3:  Example:  CPG Expenditure Plan

| Planned CPG Expenditure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Final Contract Value | R 100 000 000 |  |  |  |  |
| CPG (TE) Value | R 30 000 000 |  |  |  |  |
| Timeline | 2021/2022 | 2021/2022 | 2021/2022 | 2021/2022 | Total |
| Project Expenditure | R 20 000 000 | R 30 000 000 | R 30 000 000 | R 20 000 000 | R 100 000 000 |
| Work Packages (CPG %) Expenditure | R 6 000 000 | R 9 000 000 | R 9 000 000 | R 6 000 000 | R 30 000 000 |
| Cumulative % Spend | 20% | 50% | 80% | 100% |  |
| Cumulative Amount Spend | R 6 000 000 | R 6 000 000 | R 6 000 000 | R 6 000 000 | R 6 000 000 |
| Package 1 | R 2 000 000 |  |  |  |  |
| Package 2 | R 2 000 000 |  |  |  |  |
| Package 3 | R 2 000 000 |  |  |  |  |
| Total | R 6 000 000 | R | R | R | R |

## Targeted Enterprises Procurement Program

Table 4:  Example:  Targeted Enterprise Procurement program

| Item | Activity Name | Duration (Days) | Start | Finish |
| --- | --- | --- | --- | --- |

## Procedures for Targeted Enterprises Sub-contracting (As Per Section D1000 of the Specifications)

### Tender Preparation

#### Compilation of TE Work Packages

#### Establishment of a Help Desk

#### Market Analysis and Resources and Skills Audit

#### Compilation of Tender Documents

### Tender Process

#### Advertising of Works Packages

#### Tender Briefing Sessions

#### Minimum Tender Submission Documents

#### Tender Closure and Opening of Tenders

### Tender Evaluation

#### Eligibility

#### Functionality

#### Price and Preference

#### Compliance Check

### Appointment of Successful Targeted Enterprise

#### Price and Rates Discussion

#### Sub-contract Agreement

# TARGETED LABOUR

## Appointment of Targeted Labour

# TRAINING DEVELOPMENT AND IMPLEMENTATION PLAN

## General Overview

## Purpose of the Training Interventions

## Proposed Training for Targeted Enterprises and Targeted Labour

The table below depicts the proposed training for the Targeted Enterprises.

Table 5:  Proposed Targeted Enterprise Training

| Training Summary |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Course Content | Facilitator or Mentor | No. of Participants | Duration of the Course | Training Type | Start Date | Comments |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |  |

The table below depicts the proposed training for the Targeted Labour.

Table 6:  Proposed Targeted Labour Training

| Training Summary |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Course Content | Facilitator or Mentor | No. of Participants | Duration of the Course | Training Type | Start Date | Comments |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |  |

## Training Methodology

## Selection of Participants

## Targeted Participants

## Training Materials

## Training Times

## Training Implementation Plan

## Supporting Documents

ANNEXURE X2

PROJECT LIAISON COMMITTEE AND PROJECT LIAISON OFFICER FORMS

FORM A1:  PROJECT LIAISON COMMITTEE – MEMBER NOMINATION FORM

Notes to Nominators and Nominees:

          - General Principles of Membership:

- Membership is open to any person residing within the boundaries of the Project Area and that are duly nominated by their constituency.

- Persons nominated as co-opted members do not necessarily have to reside within the boundaries of the Project Area (see explanation in c) below).

- The nomination process will be conducted in consultation with the Local Municipalities within the Project Area.

          - Nominations for Membership

- Nominators will submit this prescribed nomination form and include the following information:

        - Name of the nominee,

        - Name of the proposer and five (5) seconders,

        - Residential address of the nominee,

        - Constituency whom the nominee will represent, and

        - Acceptance of nomination by the nominee.

          - Co-opted Members

- Co-opted members are members that the PLC chooses to add in addition to PLC members selected through the representative nomination process.

- Co-opted members may include a PLC member from the RRM PLC within the Project Area, Councillors, and specialists such as environmental specialists, etc.

- Co-opted members will have limited participation rights in PLC meetings, will not have voting rights and will not receive any seating allowance for participating in the PLC meeting.

          - Duration of Membership

- The duration of a nominee’s membership of the PLC will depend on the duration of the project or the duration of the PLC, whichever occurs first.

- A nominee’s membership will end with immediate effect in terms of the Rules of Engagement for PLC members.

            - Details of individual or organisation making the nomination:

I, ……………………………………………, representing ………………………………………………… hereby nominate …………………………………………………………………………………………….

to be a member of the PLC for Project …………………………………………………………………….

…………………………………………………………………………………………………………………

Signature ……………………………………………………………. Date ………………………………..

            - Details of the seconders (individuals supporting the nomination):

|  | Name | Surname | Organisation | Signature |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |

            - Details of the individual accepting the nomination (nominee):

| Name and Surname |  |
| --- | --- |
| Organisation |  |
| Residential Address |  |
| Ward Number |  |
| Municipality |  |

I, ……………………………………………, I.D. number ………………………………………………… hereby accept the nomination to be a member of the PLC for Project ………………………………….

…………………………………………………………………………………………………………………

I further accept to be bound by the rules, responsibilities and duties prescribed for the Project Liaison Committee Members and the Project Liaison Officers and will always act in good faith.

Signature ……………………………………………………………. Date ………………………………..

Witnesses:

Name and Surname ……………………………………………….. Signature …………………………..

Name and Surname ……………………………………………….. Signature …………………………..

FORM A2:	PROJECT LIAISON COMMITTEE – RULES, RESPONSIBILITIES AND DUTIES (Derived from D1004.03)

The PLC is the official communication channel through which SANRAL, the Engineer, Contractor and project Stakeholders and affected Communities communicates on project matters.  This platform is also used to communicate the impact that the project has or may have on project Stakeholders and the affected Communities.  This part of Section D of the Specifications describes the general processes pertaining to the PLC, as well as its role and responsibilities.

      - Establishment of the PLC

The PLC will be established prior to commencement of the Contract or as soon as possible by SANRAL.  The PLC consists of SANRAL, the Engineer, Contractor and representatives of project Stakeholders and affected Communities.  To ensure that all relevant Stakeholders are represented in the PLC, SANRAL did, or will, consult with the Executive Mayor’s office, as well as with the LED Department of the Local Municipalities in the Project Area.  Once the PLC has been established, the Employer’s further Stakeholder engagement activities shall not prevent the Contractor from continuing with construction.

Typical Stakeholder representation on the PLC may include:

- A PLC member from the relevant RRM PLC.

- Local Municipality LED Office.

- Traditional leadership representation.

- Forums representing people with disabilities.

- Forums representing women.

- Forums representing youth.

- Forums representing business sector.

- Forums representing transport sector.

- Any other Stakeholder forum/organisation recognised by SANRAL and the Local Municipality’s LED Office.

Every forum/organisation/constituency may have one (1) representative on the PLC, which representation will be confirmed by a duly signed nomination form.

It should be noted that the PLC is not a political platform.  While Councillors may be invited to some PLC meetings, they may not be PLC members and hence, will not have voting rights when attending a PLC meeting.

      - Seating Allowance for PLC Members

PLC membership is voluntary and PLC members will not be renumerated for any time spent or work done associated with representing their constituency on the PLC.

Provision has been made in the Contract for a seating allowance (stipend) to PLC members for actual costs incurred in executing their PLC duties (other than time or work related).  The Contractor will determine and table to the PLC a realistic seating allowance which will be substantiated by an outline of the anticipated actual costs envisaged to be incurred by PLC members.

The seating allowance will be increased annually based on the CPI figure contained in Table B2 of Statistical Release P0141 by StatsSA.

      - Induction of the PLC

SANRAL will conduct an induction meeting with the PLC to acquaint PLC members with the following information:

- SANRAL’s Horizon 2030 Strategy.

- SANRAL’s Fourteen Point Plan.

- The role and responsibilities of PLC members.

- SANRAL’s Transformation Policy.

- How the Transformation Policy impacts on SMMEs.

- Relevant details of the Contract, e.g.

  - Start and end dates

  - Important milestones

  - CPG targets

  - Envisaged Targeted Enterprise packages

  - Envisaged work for other SMMEs (non-CPG).

- Rules of Engagement for the PLC

In the execution of their duties, members of the PLC shall adhere to the undertakings listed below and the Contractor shall inform the Engineer of any transgression of these undertakings.

- General Matters and Membership

- A PLC member may not be a politically elected representative, and political party representation will not be allowed in the PLC.

- Ward Councillors may interact with the project team through the Mayor’s Office.

- If required, and in consultation with SANRAL, a Political Steering Committee (PSC) may be established to address political matters.  A PSC will only be established where the Project Area traverse over more than one municipal area.

- Term of Office for the PLC

- The duration of PLC members’ participating in the PLC (term of office) shall depend on the duration of the project.

- If SANRAL finds the performance of a PLC member to be below expectation or their conduct to be unacceptable, the affected member will be discharged from their obligations and a new nomination process shall commence.

- Targeted Enterprise and Targeted Labour

PLC members shall:

- ensure that they, or companies in which they hold equity, will not tender on the Contract for any work or sub-contract that may be issued.  Should they tender, this will be treated as a conflict of interest and the tender proposal submitted will not be evaluated.

- not have private or business interests in any of the sub-contract tenders tabled to the PLC or considered in this Contract.

- shall recuse themselves from discussions that deal with a sub-contract tender if any other member is of the opinion that a member’s participation in deliberations, which is rightly or wrongly construe as improper or irregular, may lead to the award of a sub-contract to a tenderer known to the member or to the member itself.

- recuse themselves from the operations of the PLC following a situation as described in paragraphs ii) above and shall cease to be a PLC member for this Contract.

- during the tender and tender evaluation processes, neither deliberately favoured nor prejudiced a person or tenderer, as intended, or contemplated in treasury Regulation 16, A8.3 (a), (b) & (c).

- ensure that no conflict of interest arises from members’ involvement in the PLC and potential involvement in targeted labour recruitment and/or targeted enterprises procurement and/or any other supplier/sub-contractor/service provider procurement or involvement in the contract.

- Confidentiality

- PLC members shall accept that all information, documentation, and decisions regarding any matter serving before the PLC are confidential and undertake not to communicate decisions or discussions of PLC meetings to external or internal parties unless so directed and approved by the Project Manager.

- Information for public dissemination shall be clearly indicated by the committee to ensure that sensitive information is only disseminated to the correct audience.

- Removal from Office

- PLC members who violate the provisions of these Rules of Engagement for PLCs will be removed from their role as a PLC member at the sole discretion of SANRAL.

- SANRAL reserves the right to recover any costs from PLC members whose actions can be regarded as detrimental to SANRAL or to the execution of the project.

- SANRAL also reserves the right to recommend criminal prosecution if the offence warrants such action.

- SANRAL reserves the right to dissolve the entire PLC should it believes that such an action is in its best interest, or that of the project.  SANRAL will not be obliged to reconstitute the PLC if such a dissolution occurs.

- Responsibilities and Duties of the PLC

The PLC will execute specific duties during the design and construction phases of the project.

Some of the PLC’s duties during the design and construction stages overlap and hence, for completeness, a description of the PLC’s duties in both project stages is provided here.

The PLC will execute the following duties:

- Project Design Stage

- Meet as often as required to discuss and resolve the project’s design stage matters which are of interest or concern to the parties to the PLC.

- Peruse the Project Liaison Committee rules, responsibilities and duties outlined in this Form and agree on the rules, responsibilities, and duties of, and procedures to be followed by, the PLC to fulfil its duties.

Note:  The principles outlined in this Form shall not be amended, but duties and procedures may be altered to be project specific and to improve the functionality of the PLC.

- Act in accordance with the agreed terms of reference for the PLC.

- Inform SANRAL of any training that project Stakeholder and affected Community representatives of the PLC require to execute their duties.

- Assist the Engineer to source suitable candidates, based on SANRAL’s qualifying criteria, for the position of PLO.

- Observe and verify that the qualifying criteria and procedures applied by the Engineer to select and employ the PLO were executed in a fair and transparent manner and were within the prescripts of the relevant labour legislation and regulations.

- Assist the Engineer to identify the project’s Target and Project Area(s) from which Targeted Labour and Targeted Enterprises could be employed and sub-contracted, respectively.

- Assist the Engineer to identify the project’s Target Groups for inclusion in the Tender Documents and agree to and support the identified Target Groups.

- Project Construction Stage

- Meet formally prior to SANRAL’s monthly site meeting, or as may be required, to discuss and resolve project matters which are of interest or concern to the parties to the PLC.

- Assist the Contractor to establish the selection criteria and process to employ Targeted Labour

- Assist the Contractor to identify the eligibility, functionality, preference, and compliance criteria to select and sub-contract Targeted Enterprises.

- Agree to and support the Databases compiled by the PLO and the Contractor from which Targeted Labour will be selected and employed and Targeted Enterprises will be sub-contracted, respectively.

- Verify that the criteria and methodologies applied by the Contractor to select and employ Targeted Labour and sub-contract Targeted Enterprises are executed in a fair and transparent manner and are within Government legislation and regulations and SANRAL’s Policies.

- Verify that the conditions of employment and the conditions of sub-contracting, in the employment of Targeted Labour and sub-contracting of Targeted Enterprises are applied in a fair and transparent manner and according to SANRAL’s employment and sub-contracting requirements.

- Make recommendations to the Contractor on the training needs, eligibility criteria and selection criteria for the provision of training to Targeted Labour, Targeted Enterprises, Designated Groups, project Stakeholders and the affected Communities.

- Verify that training and skills development programmes, which the Contractor committed to, are implemented, and executed as approved and intended.

- Inform the entities whom they represent of any project matters which the respective party to the PLC wishes to communicate with each other.

- Inform the entities whom they represent of any project matters that are impacting or may impact, either positively or negatively, on the respective parties to the PLC.

- Inform the Contractor of Stakeholder and/or Community requests and/or needs, which could possibly be addressed within the project’s Scope of Work.

- Inform the SANRAL, the Engineer and Contractor of any road safety concerns within the Project Area(s) and advise them of possible mitigating measures and/or road safety programs that will be most suitable for acceptance by the affected Communities to promote road safety.

- Agree on a dispute resolution mechanism to resolve any disputes that may arise between the parties to the PLC.

- Assist parties to the PLC to liaise with their respective entities to resolve any disputes amongst the parties which may occur due to the project.

- PLC Meetings

## Frequency

- Meetings will be conducted monthly or as required by the Stakeholders or the project matters.

## Notice of meetings

- The notice of the PLC meeting shall be given at least seven (7) calendar days prior to the meeting date.

- Where meetings have been diarised over a period by the PLC, it shall be the duty of each PLC member to ensure his/her attendance on the set dates.

- Where a PLC member has missed any meeting, he/she bears the onus of establishing the date and venue of the next meeting.

## Venue

- The venue for PLC meetings shall be the project site office or any other venue agreed to by the members of the PLC and approved by SANRAL.

- During the Covid 19 lockdown, or any other lockdown as announced by government, the meetings shall be held on an online platform such as WhatsApp, Teams, Zoom or similar.

### Agenda

- An agenda shall be made available or displayed to all participants at the commencement of such meetings or the minutes of the previous meeting will serve as the agenda of such meetings.

- The agenda shall not be amended without prior approval from SANRAL.

## Chairperson

- PLC meetings shall be chaired by SANRAL which will typically be the SANRAL’s Project Manager, or a SANRAL staff member with decision--making delegation, or the Engineer.

- The Chairperson shall:

- chair all meetings of the PLC,

- co-ordinate all the activities of PLC,

- ensure that members are fulfilling their tasks as assigned by the PLC,

- see to the execution of decisions taken by the PLC,

- ensure the validity of members’ claim for allowance,

- ensure compliance of all activities of the PLC with current rules, law and general SANRAL policy, and

- be a co-signatory to all official documents of the PLC.

- Secretariate

- The Engineer’s staff shall provide a secretarial service to take minutes of PLC meetings.

- Secretarial support other than taking minutes at PLC meetings shall be provided by the PLO.

## Quorum

- The quorum for PLC meetings shall be constituted by 50%+1 ratio excluding co- opted members.

### Apologies and Non-attendance

- Apologies shall be in writing except in emergency where the member apologising cannot communicate the apology in writing.

- Apologies may be sent through any media agreed to prior by the PLC for example through SMS or WhatsApp messaging or similar application.

- The organization, represented by a member who fails to attend three (3) consecutive meetings without an apology, will be informed in writing and asked to nominate a replacement member.

### Language

- The meetings will be conducted in English to enable all participants at the meeting to understand the discussions of the meeting.

- However, care and consideration must be given to provide non-English speakers an opportunity to participate. Therefore, where desirable, any of the 11 official languages maybe be used to conduct the meeting. If another language other than English is used, the minutes of the meeting will need to be transcribed, translated, and recorded in English.

### Other

- The PMT shall provide a finger lunch for PLC members at PLC meetings.

- Amendments or Additions

The rules, responsibilities, and duties for PLC members in this Form are adopted and will be in force with effect from this ……………………. day of ……………………………………………………... 20………

|  | Name and Surname | Signature | Date |
| --- | --- | --- | --- |
| Accepted for SANRAL |  |  |  |
| Accepted for Engineer |  |  |  |
| Accepted for Contractor |  |  |  |
| Accepted for PLC |  |  |  |
| Accepted by PLC |  |  |  |

FORM A3:  CHECKLIST – PROJECT LIAISON COMMITTEE – MEMBER APPOINTMENT

Notes:

          - The checklist consists of several sections.  Only print the relevant sections.

          - Indicate what has been completed and sign off at the end.

          - While other individuals can assist in this process, the Project Manager (PM) remains accountable for all deliverables.

          - All forms/records to be kept by the PM and availed to line management upon request.

| Form No. | Item | Explanatory Note for Compliance Check |  | Responsibility |  | Complete (Yes/No or N/A) |
| --- | --- | --- | --- | --- | --- | --- |
| A3.1 | PLC Member Appointment: |  |  |  |  |  |
| 1 | Nomination forms completed. | a) | Form must indicate the nominee and the individual or organisation making the nomination. | Stakeholder Coordinator (SC) /Contracts Engineer (CE) |  |  |
|  |  | b) | Forms circulated with the assistance of Municipality's LED office. | SC/CE |  |  |
|  |  | c) | All completed forms collected from the Municipality's LED office. | SC/CE |  |  |
| 2 | Members selected. | a) | Confirm the membership of the PLC. | SC/Project Management Team (PMT) |  |  |
|  |  | b) | Where there are multiple entries, the team can select the member with the highest number of nominations. | SC/PMT |  |  |
|  |  | c) | Where there is an equal number of nominations, the team will request the nominating organisation to confirm the member who should join the PLC. | SC/PMT |  |  |
|  |  | d) | The last alternative is to allow for a snap election in a community meeting. | SC/PMT |  |  |
|  |  | e) | Communicate the PLC membership to the affected stakeholders. | SC/PMT |  |  |
| 3 | Formal appointment to PLC signed. | a) | Ensure that the PLC membership is confirmed in line with Form A3.2 | SC/Project Manager (PM) |  |  |
|  |  | b) | All members must be provided with a copy of the PLC Duties and Responsibilities (extract from D1004.03). The signed duties and responsibilities must be scanned and shared with all members. The PM retains a copy for future reference. | SC/PMT |  |  |
|  |  | c) | Document must be signed again when the membership changes. The PM must add the version of the document to ensure that the various versions can be tracked. | PM |  |  |
| Stakeholder Coordinator: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |
| Project Manager: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |

FORM A3.2:  PROJECT LIAISON COMMITTEE – MEMBER LIST

| No. | Sector/Entity/Forum | Name and Surname | Signature |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |
| 11 |  |  |  |
| 12 |  |  |  |
| 13 |  |  |  |
| 14 |  |  |  |
| 15 |  |  |  |
| 16 |  |  |  |
| 17 |  |  |  |
| 18 |  |  |  |
| 19 |  |  |  |
| 20 |  |  |  |

FORM A4:  CHECKLIST – PROJECT LIAISON OFFICER – APPOINTMENT

Notes:

          - The checklist consists of several sections.  Only print relevant sections.

          - Indicate what has been completed and sign off at the end.

          - While other individuals can assist in this process, the Project Manager (PM) remains accountable for all deliverables.

          - All forms/records to be kept by the PM and availed to line management upon request.

| Form No. | Item | Explanatory Note for Compliance Check |  | Responsibility |  | Complete (Yes/No or N/A) |
| --- | --- | --- | --- | --- | --- | --- |
| A4 | PLO Appointment: |  |  |  |  |  |
| 1 | Post advertised in local media. | a) | Job profile prepared. | CE/PMT |  |  |
|  |  | b) | Post advertised in the media. | CE/PMT |  |  |
|  |  | c) | Copy of advert kept on file. | CE/PMT |  |  |
| 2 | Shortlisting completed. | a) | All CVs received collated. | CE/PMT |  |  |
|  |  | b) | Shortlisting done by the PMT. | CE/PMT |  |  |
|  |  | c) | PLC provided with the final shortlist. | CE/PMT |  |  |
| 3 | Interviews held. | a) | Candidates invited. | CE/PMT |  |  |
|  |  | b) | Interview grid prepared. | CE/PMT |  |  |
|  |  | c) | The PLC can nominate a member to sit on the interview panel as an observer to ensure transparency in the process. | CE/PMT |  |  |
|  |  | d) | Formal interviews carried out. | CE/PMT |  |  |
|  |  | e) | Interview scores collated. | CE/PMT |  |  |
| 4 | Formal appointment of PLO. | a) | PLO appointment letter issued. | CE |  |  |
|  |  | b) | PLO employment contract signed. | CE |  |  |
|  |  | c) | PLO performance agreement signed. | CE |  |  |
| Stakeholder Coordinator: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |
| Project Manager: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |

FORM A5:  CHECKLIST – PROJECT LIAISON COMMITTEE – MEETINGS

Notes:

          - The checklist consists of several sections.  Only print relevant sections.

          - Indicate what has been completed and sign off at the end.

          - While other individuals can assist in this process, the Project Manager (PM) remains accountable for all deliverables.

          - All forms/records to be kept by the PM and availed to line management upon request.

| Form No. | Item | Explanatory Note for Compliance Check |  | Responsibility |  | Complete (Yes/No or N/A) |
| --- | --- | --- | --- | --- | --- | --- |
| A5 | PLC Meeting Checklist: |  |  |  |  |  |
| 1 | Attendance register completed. | a) | All members of the PLC to sign the attendance register in ink. | PLO/PM |  |  |
|  |  | b) | Where meetings are on an online platform such as MS Teams, the attendance list must be downloaded from that platform. | PLO/PM |  |  |
| 2 | Quorum met. | a) | The quorum for PLC meetings shall be constituted by 50% + 1 ratio excluding co-opted members. | PLO/PM |  |  |
| 3 | Agenda approved. | a) |  | PM |  |  |
| 4 | Previous minutes approved. | a) | Minutes must be prepared, signed off and dated by the Chairperson at the following meeting. | PLO/PM |  |  |
| 5 | Minutes and resolutions captured. | a) |  | RE/PLO |  |  |
| 6 | Declaration of interest completed. | a) | All members of the PLC to sign the DoL in ink. | PLO/PM |  |  |
| Stakeholder Coordinator: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |
| Project Manager: |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |

FORM A6:  PROJECT LIAISON COMMITTEE – DECLARATION OF INTEREST

Notes:

        - This declaration of interest shall be signed by all attendees at every PLC meeting.

| THE SOUTH AFRICAN NATIONAL ROADS ANGECY LTD |  |  |
| --- | --- | --- |
| PROJECT LIAISON COMMITTEE - DECLARATION OF INTEREST |  |  |
| We, as members of the PLC and persons present in the meeting, hereby solemnly swear and declare that we have no private or business interest or stake in any of the Work Packages or Tender Reports tabled here today or to be discussed in this project. |  |  |
| If one of us is of the opinion/view that some people may, rightly or wrongly construe as improper/irregular, his/her participation/involvement in deliberations that may lead to the award of a tender to a tenderer known to him/her, that person shall then recuse himself/herself from the proceedings/discussions that deal with that Work Package or Tender Report. Additionally, such a member shall recuse himself/herself from the operations of this PLC going forward and shall cease to be a PLC member for this project. |  |  |
| We certify that we, during the process neither deliberately favoured nor prejudiced and person or tenderer, as intended or contemplated in treasury Regulation 16, A8.3 (a), (b) & (c). |  |  |
| We further accept that all information, documentation, and decisions regarding any matter serving before the Committee are confidential. We, therefore, undertake not to communicate decisions/discussions of the meeting to external or internal parties unless so directed and approved by the Project Manager. |  |  |
| Members | Signature | Date |

FORM B:  CHECKLIST – TARGETED ENTERPRISE TENDERING PROCESS

| Form No. | Item | Explanatory Note for Compliance Check |  | Responsibility | Complete (Yes/No or N/A) | Source Document |
| --- | --- | --- | --- | --- | --- | --- |
| B1 | Target Area: |  |  |  |  |  |
| 1 | Target Area Defined by PLC. | a) | Target Area for Targeted Labour and Targeted Enterprises identified and disseminated to the PLC. | PLO/PM |  |  |
|  |  | b) | Target Groups identified and disseminated to the PLC. | PLO/PM |  |  |
| 2 | Database of Contractors and Suppliers. | a) | Database criteria setup and disseminated to the PLC. | PLO/PM |  |  |
|  |  | b) | Signed off database criteria handed over to PLC. | PLO/PM |  |  |
| B2 | Tender Phase: |  |  |  |  |  |
| 1 | Tender Advert. | a) | Copy of advert on file. | Contractor |  |  |
|  |  | b) | Proof of publication in selected local publications. | Contractor |  |  |
|  |  | c) | Proof of publication on SANRAL website. | Contractor |  |  |
| 2 | Tender Document. | a) | Copy of specification available on file, copy of the Tender CD, or printed. | Contractor |  |  |
| 3 | Clarification Meeting Attendance register. | a) | Attendance register signed by all attendees of the clarification meeting | Contractor |  |  |
| 4 | Clarification Meeting Minutes. | a) | Minutes must be prepared, signed off and dated by the Chairperson within 14 days of the date of the meeting | Contractor |  |  |
| 5 | Clarification Meeting Presentation. | a) | Copy of the presentation on file. | Contractor |  |  |
| 6 | Addenda | a) | All addenda issued must be recorded on the file. | Contractor |  |  |
|  |  | b) | Proof (e-mail) of those persons that the addenda was sent to (if applicable). | Contractor |  |  |
| 7 | Register of tenders issued (if applicable). | a) | Record the names of persons / companies that collected tender documents (website/by hand). | Contractor |  |  |
| B3 | Tender Opening: |  |  |  |  |  |
| 1 | Register of Tenders Received. | a) | Record the names of persons / companies that submitted tender offers. | Contractor |  |  |
| 2 | Tender Opening, Declaration of Interest. | a) | Declaration by SANRAL officials at the opening. | Contractor |  |  |
| 3 | Tender Opening, Attendance Register. | a) | Record the names of persons present at the opening of tenders. | Contractor |  |  |
| 4 | Register for late tenders received. | a) | Record names and time of late tenders received. | Contractor |  |  |
| 5 | Tender Opening, Opening Data. | a) | Register of the opening of the Technical Offer on the Tender Data sheet. | Contractor |  |  |
| B4 | Tender Evaluation: |  |  |  |  |  |
| 1 | Extension of validity period. | a) | Confirmation of issue of letters of extension of validity period. | Contractor |  |  |
|  |  | b) | Confirmation of response on extension of validity period by the bidders. | Contractor |  |  |
| 2 | Declaration of Interest. | a) | All members of the Bid Evaluation Committee to sign the DoI in ink. | Contractor |  |  |
| 3 | Attendance Register. | a) | All members of the BEC to sign the attendance register in ink. | Contractor |  |  |
| 4 | Minutes | a) | Minutes must be prepared, signed off and dated by the Chairperson within 14 days of the date of the meeting. | Contractor |  |  |
| 5 | Signed evaluation report. | a) | Report signed by the Chairperson of the BEC detailing deliberations and discussions of the BEC meeting. | Contractor |  |  |
| 6 | PPPFA Scoring sheet | a) | Scoring sheet detailing the scores of all tenders evaluated as per the PPPFA. | Contractor |  |  |
| 7 | CSD Compliance Report. | a) | Printout of the CSD Report for compliance verification for the successful tenderer. | Contractor |  |  |
| 8 | CIDB grade confirmation (if applicable). | a) | Verification of active status. | Contractor |  |  |
|  |  | b) | JV calculator for Joint Ventures. | Contractor |  |  |
| 9 | B-BBEE Certificate. | a) | B-BBEE Certificate of winning tenderer on file for verification of preference points. | Contractor |  |  |
| 10 | SANRAL List of Restricted Bidders. | a) | Verification that the winning tenderer is not restricted from doing business with SANRAL. | Contractor |  |  |
| 11 | Clarification correspondence after tender closing (individual tenderers or all). | a) | All correspondence relating to RFT correction of arithmetic errors/balancing of rates etc. | Contractor |  |  |
| 12 | Report for the award of the contract. | a) | Report detailing information from tender phase to evaluation phase, and a recommendation with motivation for the approval of the winning tenderer. | Contractor |  |  |
| 13 | Review Report. | a) | Receive high level reports and ensure transparency in the appointment of Targeted Enterprises. The reports must exclude sensitive evaluation information. | PLC /PLO/PM | Report not to be supplied to PLC*. |  |
| B5 | Award of Contract: |  |  |  |  |  |
| 1 | BAC Declaration of Interest. | a) | All members of the BAC to sign the DoI in ink. | Project Bid Adjudication Committee Secretariat (PBAC) |  |  |
| 2 | BAC Attendance Register. | a) | All members of the BAC to sign the attendance register in ink. | PBAC Secretariat |  |  |
| 3 | BAC Minutes. | a) | Minutes must be prepared, signed off and dated by the Chairperson within 14 days of the date of the meeting. | PBAC Secretariat |  |  |

FORM C:  CHECKLIST – TARGETED ENTERPRISE CONTRACT ADMINISTRATION

| Form No. | Item | Explanatory Note for Compliance Check |  | Responsibility |  | Complete (Yes/No or N/A) | Source Document |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C | Contract Administration Phase |  |  |  |  |  |  |
| 1 | Letter of award / Letter of Acceptance. | a) | Copy of letter issued to the successful bidder. | Contractor |  |  |  |
| 2 | Letters to unsuccessful bidder(s). | a) | Standard letter informing unsuccessful bidders of the tender outcome with proof of emails. | Contractor |  |  |  |
| 3 | Publication of award, within 7 working days from date of award. | a) | Proof of publication on SANRAL website. | Contractor / PLO / Project Manager |  |  |  |
| 4 | Contract document. | a) | Original signed contract on file. | End-User / Contractor |  |  |  |
| 5 | Closure of contract. | a) | Copy of close-out report (SIPDM). | End-User / Contractor |  |  |  |
| 6 | Performance report (for Engineering contracts). | a) | Copy of contractor performance report. | End-User / Contractor |  |  |  |
| Project Manager: |  |  |  |  |  |  |  |
| Name |  | Sign |  | Date |  |  |  |

ANNEXURE X3 – PROFORMA SUB-CONTRACT DOCUMENT FOR TARGETED ENTERPRISES

https://docs.nra.co.za/otcs/cs.exe/link/19334307

SOUTH AFRICAN NATIONAL ROADS AGENCY SOC LIMITED

CONTRACT SANRAL N.001-249-2019/1R NSC

FOR THE NOMINATED SUB-CONTRACT FOR THE DESIGN BUILD, OPERATIONS AND MAINTENANCE OF THE TOLL SYSTEM FOR THE OPERATIONS AND MAINTENANCE OF TOLL PLAZAS ON THE N1 NORTH TOLL ROAD

# PART C3.4 (SECTION E):	REQUIREMENTS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT AND REGULATIONS

Note to tenderer:

Wherever reference is made in this section of the Scope of Works to contractor this is the equivalent of the principal contractor in the Occupational Health and Safety Act and Regulations. Similarly, reference to subcontractors is equivalent to other contractors.

PART C3.4 (SECTION E): REQUIREMENTS OF THE OCCUPATIONAL HEALTH AND SAFETY ACT AND REGULATIONS

TABLE OF CONTENTS	PAGE

E1001	SCOPE	C324

E1002	DEFINITIONS AND ABBREVIATIONS	C324

E1003	health and safety policy	C327

E1004	ROLES AND RESPONSIBILITIES	C327

E1005	HSE TRAINING AND COMPETENCE	C327

E1006	application for construction work permit	C328

E1007	DUTIES	C329

E1008	MANAGEMENT AND SUPERVISION	C329

E1009	RISK MANAGEMENT	C329

E1010	LEGAL COMPLIANCE AND DOCUMENT CONTROL	C331

E1011	operational integrity	C333

E1012	OCCUPATIONAL HEALTH AND HYGIENE	C334

E1013	Waste management	C335

E1014	HAZARDOUS SUBSTANCE MANAGEMENT	C336

E1015	Contractors	C336

E1016	DESIGNING FOR HEALTH, SAFETY AND THE ENVIRONMENT	C340

E1017	incident management	C340

E1018	PROJECT SPECIFIC CONSTRUCTION REQUIREMENTS	C342

E1001	SCOPE

The Occupational Health and Safety Act, Act 85 of 1993 (OHS Act) and its Regulations together with SANS Codes set out minimum standards with regards to Occupational Health and Safety. The South African National Roads Agency SOC Limited (SANRAL), has developed this Occupational Health and Safety Specifications with these minimum standards in mind and in certain aspects the requirements of SANRAL exceeds the minimum legal requirements to follow best practices and to ensure a healthy and safe workplace for all.

SANRAL in no way assumes The Principal Contractors legal liabilities and responsibilities. The Principal Contractor is and remains accountable for the quality and execution of his health and safety program for his employees. This Health and Safety Specification reflects minimum legal and SANRAL requirements and should not be construed as all encompassing.

It is realized that The Principal Contractor have its own Health and Safety Management system and safe work practices. The intention of this Health and Safety Specification is not to change The Principal Contractors Health and Safety management system, but for The Principal Contractor to use its current Health and Safety management system to draw up a project specific Health and Safety plan according to these specifications as well as to legally comply with the any applicable Regulations under the OHS Act and incorporated Standards.

It is the responsibility of the Principal Contractor and other Contractors to make themselves conversant and comply with the requirements and conditions contained in the various legislation pertaining to their profession and scope of works at all times.

This specification is not exhaustive of all duties imposed by the OHS Act and its Regulations, governing the duties and obligations, of a Designer, Principal Contractor and Contractor performing duties in terms of an agreement with the client (SANRAL). These duties are fully described in the OHS Act and its Regulations and it is the duty of every Designer, Principal Contractor and Contractor to acquaint themselves therewith before commencing work.

This specification is compiled to ensure that the Principal Contractor and any other Contractors working for SANRAL directly or through a Principal Contractor, are aware of the Occupational Health and Safety requirements when working on a SANRAL contract, as well as to make them aware of their legal liabilities and responsibilities as per the Occupational Health & Safety Act, Act 85 of 1993, and its Regulations.

Words used herein in the singular shall be deemed to include the plural and male shall include female and vice versa unless the context otherwise requires.

E1002	DEFINITIONS AND ABBREVIATIONS

Assessment – An opinion or a judgment about someone or something that has been thought about very carefully.

At-risk behavior – Conduct that unnecessarily increases the likelihood of an injury or incident.

Audit – A systematic and documented review of the effectiveness of implementation of processes, programs and procedures, based on general process criteria.

Baseline risk assessment: This is the initial assessment of risk in a workplace. It is a broad assessment and includes all activities taking place on site but does not include risk control measures or safeguards.

Client – Any organization or person for whom construction work is performed. For the purpose of this document, the client is the South African National Roads Agency SOC Limited, also identified in the contract document as the Employer.

Competence – A combination of attributes such as knowledge, training, experience and qualifications to assure successful performance.

Competent Person – Means a person who has in respect of the work or task to be performed the required knowledge, training and experience and, where applicable, qualifications, specific to that work or task: Provided that where appropriate qualifications and training are registered in terms of the provisions of the National Qualification Framework Act, 2000 (Act No. 67 of 2000), those qualifications and that training must be regarded as the required qualifications and training; and is familiar with the Act and with the applicable regulations made under the Act.

Consequence – Outcome or impact of an event.

Continual Improvement – A recurring process of enhancing performance to achieve consistent improvements in overall performance.

Contractor – An employer as defined in section 1 of the OHS Act, who performs construction work and includes Principal Contractors and Sub-Contractors.

Construction Work – any work in connection with:

- The construction, erection, alteration, renovation, repair, demolition or dismantling of or addition to a building or any similar structure; or

- The construction, erection, maintenance, demolition or dismantling of any bridge, dam, canal, road, railway, runway, sewer or water reticulation system; or the moving of earth, clearing of land, the making of excavation, piling, or any similar civil engineering structure or type of work.

Corrective Action – An action taken to eliminate the cause of a detected non-conformity or other undesirable situation.

Construction Regulations (CR) – Construction Regulations, GNR. 84 of 2014

Critical equipment – A piece of equipment or a structure whose failure to perform to design specification, has the potential to result in a major accident event.

Design – in relation to any structure, includes drawings, calculations, design details and specifications.

Designer –

- competent person who:

- Prepares a design;

- Checks and approves a design;

- Arranges for a person at work under his or her control to prepare a design, including an employee of that person where he or she is the employer; or

- Designs temporary work, including its components;

b)		an architect or engineer contributing to, or having overall responsibility for a design;

c)	a building services engineer designing details for fixed plant;

d)	a surveyor specifying articles or drawing up specifications;

e)	 a contractor carrying out design work as part of a design and building project; or

f)	an interior designer, shop fitter or landscape architect.

DMR – Driven Machinery Regulations, GNR. 295 of 26 February 1988

Documents – Structured units of recorded information and its supporting medium (paper or electronic). Most records are documents, but not all documents are records. A document becomes a record when it is part of a business transaction, is kept as evidence of that transaction and is managed within a record-keeping system.

EIR – Electrical Installation Regulations, GNR. 242 of 6 March 2009

Emergency – An abnormal occurrence that pose a threat to the safety or health of employees, customers, or local communities, or which can cause damage to assets or the environment.

Employee – An individual who is employed by or works for an Employer and who receives or is entitled to receive any remuneration or who works under the direction or supervision of an employer or any other person.

Employer – Any person who employs or provides work for any person and remunerates that person or expressly or tacitly undertakes to remunerates him but excludes a labour broker as defined in section 1(1) of the Labour Relations Act, 1956 (Act No. 28 of 1956). The South African National Roads Agency SOC Limited, also identified in the contract document as the Employer.

EMR – Electrical Machinery Regulations, GNR. 250 of 25 March 2011

Environment – The surroundings or conditions in which a person, animal or plant lives or operates, including air, water, land, natural resources and habitats.

Epidemic Disease - An epidemic disease is one affecting many persons at the same time and spreading from person to person in a locality where the disease is not permanently prevalent. The World Health Organization (WHO) further specifies epidemic as occurring at the level of a region or community.

Excavation work – The making of any man-made cavity, trench, pit or depression formed by cutting, digging or scooping

GAR – General Administrative Regulations, GNR. 929 of 25 June 2003

GMR – General Machinery Regulations, GNR. 1521 of 5 August 1988

GSR – General Safety Regulations, GNR. 1031 of 30 May 1986

Harm – A significant and or long-lasting adverse effect on people, the environment or the community.

Hazard – A source, situation or act with a potential for harm in terms of human injury or ill health.

Health and Safety File – Means a file, or other record in permanent form, containing the information in writing as required by the Construction Regulations, GNR. 84 of 7 February 2014, Section 7(1)(b).

Health and Safety Plan – Means a project specific documented plan in accordance with the client’s health and safety specifications, as required by the Construction Regulations, GNR. 84 of 7 February 2014, Section 7(1)(a).

Health and Safety Specification – Means a project specific document prepared by the client pertaining to all health and safety requirements related to construction work, as required by the Construction Regulations, GNR. 84 of 7 February 2014, Section 5(1)(b).

HSE – Health, Safety and Environment. Commonly used in the format HSE.

Incident – Work-related events (including accidents which give rise to injury, ill health, fatality or emergencies) that have resulted in, or has the potential to result in adverse consequences to people, the environment, property, reputation or a combination of these.

Likelihood – A description of probability or frequency, in relation to the chance that something will occur.

Lost Time Injury (LTI) – When a person is injured during the execution of his/her duties and as a result of the injury is unable to perform his/her regular duties for one full shift or more on the day following the day on which the injury has incurred, whether a scheduled work day or not(weekend).

Management System – Management processes and documentation that collectively provide a systematic framework for ensuring that tasks are performed safely, correctly, consistently and effectively to achieve a specified outcome and to drive continual improvement in performance.

Mandatory – An agent, contractor or sub-contractor for work, but without derogating from his status in his own right as an employer or a user.

MSDS – Material Safety Data Sheet

Near Hit / Near Miss – Any occurrence or situation which had the potential for adverse consequences to people, the environment, property, reputation or a combination of these.

Non-conformance – Any deviation from work standards, practices, procedures, regulations that could either directly or indirectly lead to injury or illness, property damage, damage to the environment or a combination of these.

OHS Act – Occupational Health & Safety Act, 85 of 1993

Pandemic Disease - a pandemic disease is an epidemic disease that has spread over a large area, that is, it is prevalent throughout an entire country, continent, or the whole world.

Policy – Statement by an organization of its intentions and principles in relation to its overall performance which provides a framework for action and for the setting of its objectives and targets.

PPE – Personal Protective Equipment

Preventive Action – An action implemented to eliminate the cause of a potential non-conformity or other undesirable potential situation.

Principal Contractor – An employer appointed by the client to perform construction work and who is in overall control and management of a part of or the whole construction site.

Procedure – A specific documented way to carry out an activity or a process.

Records – Recorded information, in any form that is kept as evidence. Records include monitoring results, evidence of training, audits, inspections and calibration reports.

Risk Assessment – A process of evaluating the risk(s) arising from hazards taking into account the adequacy of any existing controls and deciding whether or not the risk(s) is acceptable.

Risk Management – The ongoing treatment of risks through the application of management policies, processes, procedures and risk control measures.

Risk – A combination of the likelihood of an occurrence of a hazardous event or exposure and the severity of injury or ill health that can be caused by the event or exposure.

Root Cause – The cause of the incident that, when rectified, will prevent the recurrence of not just incidents with those exact circumstances, but others with similar causes.

SACPCMP – South African Council for Project and Construction Management Professions

SANRAL - South African National Roads Agency SOC Limited

Supplier – A person or company that supplies material or equipment to a contractor on a construction site but does not physically carry out construction work on the construction site.

The Act – The Occupational Health and Safety Act No. 85 of 1993

The Site – The area where work is carried out for SANRAL as defined on the front page of this document.

WAH – Acronym for Working at Heights.

E1003	health and safety policy

Contractors are expected to have their own written Health and Safety Policy. The policy should declare their attitude and approach to the health, safety and welfare of their employees and others. The policy should include a description of the company and provision must be made to review the policy annually and the CEO or Managing Director must sign and date the policy to indicate his commitment to ensuring the health and safety of his employees, as per Section 7 of the OHS Act.

E1004	ROLES AND RESPONSIBILITIES

Every Contractor is considered to be an employer in his own right and shall comply with all legal requirements pertaining to an employer, which include the responsibility to provide as far as reasonably practicable a safe and healthy working environment for his employees, as per Section 8 of the OHS Act.

In conjunction with Section 8 of the OHS Act, all employees on the project are responsible for their own health and safety as well as the safety of persons who may be affected by their acts, as per Section 14 of the OHS Act. It is the responsibility of each employee to ensure that he acts in a safe manner before and during work is carried out.

The Principal Contractor shall ensure that where required by the OHS Act and Regulations, competent employees are appointed in writing. These appointments must be project/contract specific and specific to the tasks that will be performed. Every appointment must display the duties of the person appointed and training certificates from a registered training provider must be attached to such appointment (where applicable). A list of possible appointments can be found in clause E1010 below.

E1005	HSE TRAINING AND COMPETENCE

Where appropriate qualifications and training are registered in terms of the provisions of the National Qualifications Framework Act, 2000 (Act No. 67 of 2000), those qualifications and training must be regarded as the required qualifications and training and employees must have attended courses of the aforementioned nature to be considered competent in the task.

All employees that forms part of the construction work must be trained and competent. Employees formally appointed to perform a certain duty must be in possession of a training certificate (where applicable), received from a registered training provider. All employees must as a minimum have received site specific safety induction training and must receive daily safe task instruction training (DSTI) before any work commences and thereafter on a daily basis.

- Training Needs

There shall be a system in place to determine the training requirements of each individual, based on the tasks that the employee will perform as well as to ensure the health and safety of fellow employees and the public. Special attention should be given to employees who are new hires, new to the task or have combined responsibilities.

- Basic Safe Work Training (Induction Training)

Every contractor shall ensure that his employees are inducted into his own company Health and Safety System as well as basic safe work training (HSE Induction Training). The Principal Contractor shall ensure that his, all his Contractor’s employees and visitors are inducted on the specific site safety procedures.

A Daily Safe Task Instruction (DSTI) must be conducted on site with all employees involved in the project. The DSTI must be carried out each day before work commences and proof thereof must be available on site. Each work crew may conduct their own specific DSTI to discuss the hazards, risks and control measures associated with their task for the day.

Where two or more contractors or work crews work in the same area, they should have a combined DSTI to ensure they know of the additional hazards the other contractor or work crew will introduce to their operations and what precautions to put in place.

The Principal Contractor shall have evidence that employees have been trained on the relevant procedures prior to and during the project duration. The evidence will be in a form of attendance register.

- Formal Training

All qualifications for which there are SAQA registered training courses, must be regarded as the minimum required qualifications and training. To be deemed “competent” an employee must have received training at a registered training provider, the training course must be registered and if there is an assessment, the employee must have been found competent after the assessment. A person cannot be deemed competent after awareness training only.

The Principal Contractor shall ensure that his employees, as well as the employees of any contractors that may be used, have received appropriate training for the type of work that will be performed, e.g. First Aid, Flag Man, Mobile Plant Operator, Working at Heights, Risk Assessment training etc.

- Records

Record of all training shall be kept by the employer and shall be readily available. Records shall make provision for refresher training where applicable. Where an employee is legally appointed with certain duties and responsibilities a copy of the training certificate must be attached to the appointment.

E1006	application for construction work permit

Construction Regulation, 2014 Section 3 requires that the client apply for a construction work permit at least 30 days before construction work is started, if the intended construction work will:

- exceed 365 days AND will involve more than 3 600 person days of construction work; or

- if the tender value limit is a CIDB grade 7, 8 or 9.

If approved, the provincial director will issue a construction work permit in writing to perform construction work within 30 days of receiving the application and assign a site-specific number for the construction site. It is the intention of SANRAL to apply for a construction work permit as soon as The Principal Contractor is appointed and his Health and Safety Plan is received, in order to minimize construction delays.

The site-specific construction work permit number must be displayed at the main entrance to the site and a copy of the construction work permit must be kept in the principal contractor’s health and safety file for inspection purposes.

E1007	DUTIES

Various duties are imposed on the client, designer, principal contractor and other contractors by the Construction Regulation, 2014, Sections 5, 6 & 7. SANRAL will comply and carry out the required duties as contemplated in Section 5 of the Construction Regulations, 2014 and it is expected from the designer and every contractor to make themselves conversant with the requirements and duties imposed on them and to ensure that they comply with the requirements of section 6 & 7 at all times.

E1008	MANAGEMENT AND SUPERVISION

The Principal Contractor shall ensure that the project is managed safely, and legal compliance is ensured at all times.

A full-time competent person must be appointed as a Construction Manager to manage all construction work, including health and safety compliance. The construction manager may not be appointed to manage more than one single construction site. An Alternate Construction Manager must be appointed, to carry out the duties in the absence of the Construction Manager.

The construction manager must appoint construction supervisors responsible for construction activities and ensuring occupation health and safety on the construction site.

The Principal Contractor must appoint a full-time construction health and safety officer, who is registered with the SACPCMP, to assist in the control of health and safety aspects on site.

E1009	RISK MANAGEMENT

The Principal Contractor must follow a formal risk-based approach to ensure hazard control measures are implemented to an acceptable reasonable practical level. The Principal Contractor and his employees shall be responsible to ensure all hazards pertaining to his scope of activity are proactively identified, the risks assessed and appropriately eliminated or minimized and managed on an ongoing basis. Risk assessments shall also identify possible and potential environmental, health and hygiene issues pertaining to each hazard with potential exposures and limits.

- Risk Assessment

- Hazard Identification and Risk Assessment (Construction Regulation 9)

The Principal Contractor shall, before the commencement of any construction work or work associated with the aforesaid construction work and during such work, conduct a risk assessment by a competent person, appointed in writing and the risk assessment so produced shall form part of the OH&S plan and be implemented and maintained as contemplated in Construction Regulation 9(1). Competence is a factor of training, knowledge, experience and/or appropriate qualifications.

The risk assessment shall include, as far as is reasonably practicable, at least:

- The task or task step

- the identification hazards to which persons may be exposed to during the task or task step;

- The analysis and evaluation of the risks associated to the hazards identified, inclusive of a residual risk rating methodology. The method to be used is not prescribed;

- a documented plan of safe work procedures, to mitigate, reduce or control those residual risks that have been identified as unacceptably high, by means of the rating system;

- a monitoring plan;

- a review plan, inclusive of dates to be adhered to; and

- Ergonomic related risks are to be analysed, evaluated and addressed as part of the process.

Based on the risk assessments, The Principal Contractor shall develop a set of site-specific OH&S rules that shall be applied to regulate the OH&S aspects of the construction. The risk assessments, together with the site-specific OH&S rules shall be submitted to the Employer before construction on site commences. SANRAL has conducted a Baseline Risk Assessment as per clause E1009 (b) below, which must be used by The Principal Contractor to develop task specific risk assessments before work commences. This does not mean that all possible Risk Assessments must be attended to before work commences, but that all relevant Risk Assessments receive the necessary attention as the contract progresses, and this is the responsibility of The Principal Contractor.

All variations to the scope of work shall similarly be subjected to a risk assessment process.

- Risk Assessment Monitoring

The Principal Contractor shall ensure that a monitoring plan for all risk assessments are in place. Risk assessments must be monitored to ensure effectiveness and employee understanding. The monitoring of risk assessments shall be formal, and records thereof shall be available for audit purposes.

- Review of Risk Assessment

The Principal Contractor shall review the hazard identification, risk assessments and standard safe working procedures:

- prior to any work activity commencement,

- where changes are affected to the design and construction that result in a change to the risk profile,

- when an incident has occurred, or

- at least quarterly.

The Principal Contractor shall provide the Employer, sub-contractors and all other concerned parties with copies of any changes, alterations or amendments as contemplated above.

Activities carried out without conducting a risk assessment or found to be non-compliant with the risk assessment, will be stopped until such time a risk assessment is compiled, and work is carried out according to the risk assessment.

Risk assessments must be fully communicated to all relevant personnel and must be considered when establishing training, awareness and competency requirements. Records of risk assessment communications must be kept for inspection purposes.

  - Baseline Risk Assessment

SANRAL prepared a Baseline Risk Assessment from which the Health and Safety Specifications for this project was prepared. The Baseline Risk Assessment highlights all work for which The Principal Contractor must prepare safe work procedures and or work method statements. It must be noted that the Baseline Risk Assessment is not exhaustive and Principal Contractors are required to identify risks and come up with control measures, this must be identified by Principal Contractor when preparing the Issue Based Risk Assessments.

The Baseline Risk Assessment for this Project can be found in clause E1018.

  - Continuous Risk Assessment

The Principal Contractor shall continuously assess the risks of the activities that are carried out. Risk assessments must be in writing, site specific and must be reviewed continuously as per E1009 a(iii) to ensure it is current and it address all the relevant hazards and risks associated with the specific activity at the specific site.

The Risk assessment must be discussed with the whole work crew before the activity starts and the work crew must acknowledge in writing having discussed the risk assessment and that they understand it. This acknowledgement must be on site and must be available to the client for audit purposes.

E1010	LEGAL COMPLIANCE AND DOCUMENT CONTROL

The Principal Contractor is required to implement systems and procedures to ensure legal compliance through:

- Identification of all relevant HSE legislation, standards and codes applicable to its operations.

- Have available copies of all relevant HSE legislation, standards and codes for reference purposes.

- Update systems and procedures with changed/updated legislation, standards and codes.

- Communicate to all employees any changes that may affect their accountabilities and conformances

- Incorporate any legal requirements into their HSE management system

- Monitor and review their HSE management system for effectiveness.

The Principal Contractor shall, as a minimum, comply with:

- The Occupational Health and Safety Act and Regulations (Act 85 of 1993), an up-to-date copy of which shall be available on site at all times.

- The Compensation for Occupational Injuries and Diseases Act (Act 130 of 1993), an up-to-date copy of which shall be available on site at all times.

- Where work is being carried out on a quarry/borrow pit/“mine”, The Principal Contractor shall comply with the Mines Health and Safety Act and Regulations (Act 29 of 1960) and any other OH&S requirements that the mine may specify. An up-to-date copy of the Mines Health and Safety Act and Regulations shall be available on site at all times.

Wherever in the Construction Regulations or this specification there is reference to other regulations (e.g. Construction Regulation 24: Electrical Installations and Machinery on Construction Sites) The Principal Contractor shall be conversant with and shall comply with these regulations.

All legal appointments of The Principal Contractor regarding the Health and Safety of his employees who are to work on the project are addressed and governed by the OHS Act and applicable Regulations. Legal appointments must be in place and must reflect in the project safety file before work commences.

- Overall Supervision and Responsibility for OH&S

SANRAL will appoint the Principal Contractor in terms of Construction Regulation 5(1)(k). A Mandatory agreement as per Section 37.2 of the OHS Act, shall be signed between SANRAL and the Principal Contractor.

It is a requirement that the Principal Contractor, when he appoints other contractors in terms of Construction Regulations 7(1)(c), 7(1)(d), 7(1)(f) and 7(3) includes in his agreement with such Contractors the following:

- OH&S Act (85 of 1993), Section 37(2) agreement: “Agreement with Mandatory”.

- OH&S Act (85 of 1993), Section 16(2) appointee(s) as detailed in his/her/their respective appointment forms. (Where applicable).

The signed Mandatory agreements shall be placed in the project file for reference and for audit trail purposes.

- Specific Supervision Responsibilities for OH&S

The Principal Contractor shall appoint designated competent employees and/or other competent persons as required by the OHS Act and Regulations, as well as this specification. Appointments shall be in writing and the responsibilities clearly stated together with the period for which the appointment is made. This information shall be communicated to and agreed with the appointees. Where applicable, the training certificate must be attached to the appointment. Notice of appointments shall be submitted to the Employer. All changes shall also be communicated to the Employer.

Below is a list of possible appointments for the project, which is not an all-inclusive list, but for reference purposes only:

| Appointment | Legal Reference |
| --- | --- |
| Assistant to CEO | OHS Act 16(2) |
| Health and Safety Representative | OHS Act 17(1) |
| Nominated Health and Safety Committee Member | OHS Act 19(3) |
| Contractor (Sub-contractor) | CR 7(1)(c)(v) |
| Construction Manager | CR 8(1) |
| Alternate Construction Manager | CR 8(1) |
| Assistant Construction Manager | CR 8(2) |
| Health and Safety Officer | CR 8(5) |
| Construction Supervisor | CR 8(7) |
| Assistant Construction Supervisor | CR 8(8) |
| Risk Assessor | CR 9(1) |
| Fall Protection Plan Developer | CR 10(1)(a) |
| Structure Inspector | CR 11(2)(a) |
| Temporary Works Designer | CR 12(1) |
| Temporary Works Supervisor | CR 12(2) |
| Excavation Supervisor | CR 13(1)(a) |
| Demolition Supervisor | CR 14(1) |
| Competent Person in the use of Explosives | CR 14(11) |
| Scaffold Supervisor | CR 16(1) |
| Suspended Platform Supervisor | CR 17(1) |
| Rope Access Supervisor | CR 18(1)(a) |
| Material Hoist Inspector | CR 19(8)(a) |
| Bulk Mixing Plant Supervisor | CR 20(1) |
| Explosive actuated fastening device Inspector | CR 21(2)(b) |
| Explosive actuated fastening device cartridge Controller | CR 21(2)(g)(i) |
| Construction Vehicle & Mobile Plant Operator Authorised | CR 23(1)(d)(i) |
| Temporary Electrical Installation Controller | CR 24(c ) |
| Stacking and Storage Supervisor | CR 28(a) |
| Fire Equipment Inspector | CR 29(h) |
| Incident investigator | GAR 9(2) |
| Lifting tackle inspector | DMR 18(10)(e) |
| Ladder inspector | GSR 13(a) |
| Certified Explosives Manager | ER 12(1) |
| First Aider GSR | GSR 3(4) |
| Lifting machine Operator | DMR 18(11) |

In addition to the above, the Employer requires that a Traffic Safety Officer be appointed.

It is a requirement that The Principal Contractor shall provide the Employer with an organogram of all sub-contractors that he/she has appointed or intends to appoint and keep this list updated and prominently displayed on site.

- Designation of OH&S Representatives (Section 17 of the OH&S Act)

Where the Principal Contractor employs more than 20 persons (including the employees of sub-contractors) he has to appoint 1 (one) OH&S representative for every 50 employees or part thereof. This is a minimum (legal) requirement. The Principal Contractor may at his own discretion appoint more OH&S representatives according to site specific requirements. General Administrative Regulation 6 requires that the appointment or election of the OH&S representatives be conducted in consultation with employee representatives or employees (Section 17 of the Act and General Administrative Regulation 6 & 7). OH&S representatives shall be designated in writing and the designation shall include the area of responsibility of the person and term of the designation. OH&S representatives must be experienced, permanently employed by The Principal Contractor or his sub-contractors, trained and able to move freely within their designated area of responsibility.

- Duties and Functions of the OH&S Representatives (Section 18 of the OH&S Act)

The Principal Contractor shall ensure that the designated OH&S representatives perform their functions in respect of the workplace or section of the workplace for which they have been appointed. These functions include to conduct continuous monitoring and monthly inspections of their respective areas of responsibility, focusing on unsafe acts and unsafe conditions and report thereon to The Principal Contractor and OH&S Committee. OH&S representatives shall participate in accident or incident investigations. OH&S representatives shall attend all OH&S committee meetings. The complete list of functions can be found in Section 18 of the OHS Act.

- Appointment of OH&S Committee (Sections 19 and 20 of the OH&S Act)

The Principal Contractor shall establish an OH&S committee, which shall meet at least once a month, where two or more Health and Safety Representatives have been appointed. OH&S representatives must be appointed as OH&S committee members. The number of members nominated by management may not exceed the number of OH&S representatives on the committee and must be appointed in writing.

E1011	operational integrity

The operational integrity of plant, equipment, structures and protective systems must be monitored and assured on an ongoing basis throughout the project cycle. Hazards must be identified, risks assessed and as far as reasonably practicable, eliminated or the risks treated to as low as reasonably practicable (ALARP).

  - Construction Plant & Equipment

The Principal Contractor shall maintain all items of plant and equipment necessary to perform the work in a safe condition.

SANRAL reserves the right to inspect items of plant and equipment brought to site and used on site by The Principal Contractor. Should it be found that any item is inadequate, faulty, unsafe or in any other way unsuitable for the safe and satisfactory execution of the work for which it is intended, The Principal Contractor will be advised of such observation/inspection, and The Principal Contractor shall be required to repair, make safe or remove such item from operation and replace it with a safe and adequate substitute.

The Principal Contractor shall ensure that all plant, equipment, and power tools that are brought onto and used on site are:

- Appropriate for the type of work to be performed

- Placed on a register and inspected by a competent person and/or the authorized operator before use, daily or monthly dependent on Legislation.

- Record inspection findings on a register that must be kept on site.

- The inspection register shall reflect the serial number of the plant, equipment or power tool.

- Maintained and used in accordance with the manufacturers’ recommendations

- Have adequate machine guarding fitted to all exposed rotating or moving parts, as reasonably practicable, that have the potential to cause harm

- All electrical power supply units are protected with operational earth leakage devices.

- Any defective, damaged or sub-standard equipment must be marked as unsafe for use and removed from operation as soon as possible

    - Standards and Registers

As standard project procedures, The Principal Contractor is expected to:

- Set up an initial set of registers as per the requirements of the OHS Act and Regulations.

- Complete the registers for each piece of plant, tool and equipment brought on and used on site

- Maintain a complete, continuous and comprehensive inspection and service history in these registers or checklists

- Ensure daily, weekly, monthly inspections are done and recorded for all plant, tools & equipment by a competent person and/or authorized operator as required by the OHS Act and Regulations.

- Have the inspection and maintenance records available for audit purposes.

E1012	OCCUPATIONAL HEALTH AND HYGIENE

  - Medical Fitness for Duty

All contractor employees shall undergo medical examinations and be certified fit for duty by an Occupational Health Practitioner before they are allowed to work on site.

The medical certificate must be in the form of Annexure 3 of the Construction Regulations and stipulate the possible exposures the employee might be exposed to during the execution of the project.

It is recommended and in the best interest of The Principal Contractor to implement pre-employment, periodic, as well as exit medical surveillance, especially with regards to Section 8 of the Noise Induced Hearing Loss Regulation.

  - First Aid

According to GSR 3(4), where more than 10 employees are employed at a workplace/worksite, The Principal Contractor shall ensure that there is at least one trained first aider for every group of 50 employees at the workplace/site. First Aid boxes must be provided where more than 5 employees are employed and must be readily available and accessible for the treatment of injured persons at the workplace.

To ensure immediate treatment of an injured person, it is recommended that all work crews have at least one trained first aider, with a fully stocked first aid box, irrespective of the number of people in the work crew. This is especially important when contractors work at great distances from the nearest emergency facility or town. These persons shall be appointed in writing as the first aiders with their certificates attached as proof of competency.

The minimum contents of the first aid box shall be as per the supplied list in the General Safety Regulations.

All treatments done must be recorded on a register and kept with the first aid box. A trained and appointed first aider must be responsible for the first aid box and its content. Used content must be replenished as soon as possible.

In order to ensure prompt response at the emergency facility it is recommended that the W.Cl 2 forms be partially completed with the Employers’ details.

  - Hygiene Facilities

The Principal Contractor and his contractors shall ensure compliance to Section 30 of the Construction Regulations with regards to facilities on the construction site as well as where accommodation is provided to employees on remote sites. The Principal Contractor shall ensure that the facilities are kept clean at all times, either through a service provider or self-employed persons. The Principal Contractor shall provide employees with at least one sanitary facility for each sex and for every 30 workers, changing facilities for each sex and sheltered eating areas.

  - Health related Epidemics and Pandemics

The contractor shall, as far as reasonably practicable describe in his health and safety plan how health related epidemics and pandemics will be dealt with. The Employer is aware that this section in the health and safety plan will not speak to specifics, but generic procedures. The Contractor must ensure that the requirements stipulated in the Hazardous Biological Agents (HBA) Regulation are addressed in his health and safety plan, training and information given to staff and procedures implemented on site to prevent health risks on site.

Once the nature and scale of the epidemic or pandemic is known, the Contractor must update his health and safety plan with the relevant information and send the updated plan to the relevant appointed OHS Agent for approval. Once approved, the Contractor must implement the updated health and safety plan and maintain the updated plan on site.

E1013	Waste management

The Principal Contractor shall comply with all applicable and relevant Waste management legislation, as well as municipal bylaws applicable to waste management.

The Principal Contractor shall remove all waste generated at the construction site as soon as possible after generation to ensure good housekeeping at all times. The Principal Contractor shall have a waste management plan which must be implemented on the construction site and which will have the objective to ensure that waste is managed according to the Waste Management Hierarchy:

- Reduce what you can. If you cannot reduce then,

- Re-use what you can. If you cannot re-use then,

- Recycle what you can. What you cannot recycle,

- Convert into energy sources. If it cannot be converted to an energy source,

- Dispose of in a landfill – this is only to be done as a last resort and disposed without endangering human health and without using processes or methods which could harm the environment.

E1014	HAZARDOUS SUBSTANCE MANAGEMENT

The Principal Contractor shall ensure that hazardous substances brought onto site are easily identifiable and stored according to the requirements of the General Safety Regulations, GNR. 1031 of 1986, Section 4.

Where flammable liquids are being used or stored, this must be done in a manner which would not cause a fire or explosion hazard.

The Principal Contractor shall have Material Safety Data Sheets (MSDS) readily available for flammable, hazardous and toxic chemical substances and materials brought onto site and shall ensure that his employees are trained in these MSDS’s.

Flammable, hazardous or toxic chemical substances may not be stored in empty food or drink containers. Empty flammable, hazardous and toxic containers must be disposed of in a safe manner, which will prevent further use of such a container.

A survey of the construction site must be done during site establishment, to locate any asbestos. Should asbestos be located, the conditions of the Asbestos Regulations, GNR. 155 of 2002 must be followed and complied with.

E1015	Contractors

  - Consultations, Communications and Liaison

OH&S liaison between the Employer, The Principal Contractor, The Contractors, the designer and other concerned parties will be through the OH&S committee. In addition to the above, communication may be directly to the Employer or his appointed agent, verbally or in writing, as and when the need arises.

Consultation with the workforce on OH&S matters will be through their construction managers and supervisors, OH&S representatives and the OH&S committee. The Principal Contractor shall be responsible for the dissemination of all relevant OH&S information to The Contractors e.g. design changes agreed with the Employer and the designer, instructions by the Employer and/or his/her agent, exchange of information between subcontractors, the reporting of hazardous/dangerous conditions/situations etc. The Principal Contractors’ most senior manager on site shall be required to attend all OH&S meetings.

  - Operational Procedures

Each construction activity shall be assessed by The Principal Contractor so as to identify operational procedures that will mitigate against the occurrence of an incident during the execution of each activity. This specification requires The Principal Contractor:

- to be conversant with all relevant Regulations;

- to comply with their provisions;

- to include them in his OH&S plan where relevant

  - Checking, Reporting and Corrective Actions

- Monthly Audit by Employer (Construction Regulation 5(1)(o)

The Employer will conduct monthly health and safety and document verification audits in compliance with Construction Regulation 5(1)(o) in order to ensure that The Principal Contractor has implemented and is maintaining the agreed and approved OH&S plan.

The Principal Contractor will be provided with a copy of the Health and Safety audit report within seven days after the audit. The Employer or his representative may stop any Principal Contractor from executing a construction activity which poses a threat to the health and safety of persons which is not in accordance with the client’s health and safety specification and the Principal contractor’s health and safety plan for the specific site.

- Other Audits and Inspections by the Employer

The Employer reserves the right to conduct other ad hoc audits and inspections as deemed necessary. This will include site safety walks.

- Principal Contractor’s Audits and Inspections

The Principal Contractor must conduct his own regular internal audits to verify compliance with his own OH&S management system, as well as with this specification.

The Principal Contractor shall furthermore ensure that each contractor`s health & safety plan is being implemented and maintained. The Principal Contractor will ensure that periodic health and safety audits and document verification are conducted at intervals mutually agreed upon between the Principal Contractor and any contractor, but at least once every 30 days.

- Inspections by OH&S Representatives and other Appointees

OH&S representatives shall conduct monthly inspections of their areas of responsibility and report thereon to their foreman or supervisor, as well as the OH&S Committee, whilst other appointees shall conduct inspections and report thereon as specified in their appointments e.g. vehicle, plant and machinery drivers, operators and users must conduct daily inspections before start-up.

- Recording and Review of Inspection Results

All the results of the abovementioned inspections shall be in writing, reviewed at OH&S committee meetings, endorsed by the chairman of the meeting and placed on the OH&S File.

  - Project Health and Safety Management Plan

As per Section 5(1) (l) and Section 7(1) (a) of the Construction Regulations of 2014, The Principal Contractor shall develop, implement and administer a Health and Safety Management Plan. The plan shall be in writing and shall be negotiated between The Principal Contractor and SANRAL or designated OHS Agent and must be approved by SANRAL or the designated OHS Agent prior to the commencement of work on site. The plan shall demonstrate management’s commitment to ensure employee health and safety as their primary objective during the contract. The H&S plan shall be site and project specific and must address all aspects of the project H&S specification.

  - Project Health and Safety File

The Principal Contractor shall compile a project specific Health and Safety File that consist of all the relevant project specific documentation. The Health and Safety file may consist of multiple files, which when combined should contain all the required documentation.

It is recommended that the project specific Health and Safety file contain at least the following:

- Scope and summary of the project as well as any scope changes.

- Notification of Construction Work to DoL / Copy of Work Permit

- Proof of COID registration (Letter of Good Standing)

- Contractor Health and Safety Policy statement signed by management

- Appointment of Principal Contractor

- Mandatory Agreement – OH&S Act 37.2 (Between Employer and Principal Contractor)

- Client Health and Safety specification

- Latest copy of the OHS Act end Regulations

- Company Organogram depicting Health and Safety Responsibilities, including sub-contractors

- Employee list including copy of IDs and medicals

- Project specific Health and Safety Management Plan agreed with the Employer – See E1015(d) above

- Relevant OH&S Legal appointments which includes duties and responsibilities as well as competencies (training certificate)

- Copies of minutes of meetings – OH&S committee and other relevant OH&S meeting minutes

- Site specific Fall Protection Plan (if applicable)

- Risk Assessments

- Contractor Induction material

- Waste management Plan

- Emergency preparedness (first aid, firefighting, emergency plan, etc.)

- Emergency Contact Telephone numbers

- List of hazardous chemical substances used on site

- Material Safety Data Sheets of hazardous chemicals on site

- List of plant & equipment to be used on site

- Inspection Checklists/Registers of plant & equipment and emergency equipment

- List of Sub-contractors including type of work

- Sub-contractor 37.2 Mandatary Agreements

- Sub-contractor appointments which shall include the type of work The Principal Contractor is appointed for.

  - Contracting Philosophy

Any site-specific hazards and safety management expectations will be made known to the Principal Contractor prior to the work commencing on site. This will be done through the OH&S Specification for the project. SANRAL as the Employer/Client may specify requirements that are stricter than Legislative requirements in this OH&S Specification. Legal OHS requirements contained in the OHS Act and Regulations, SANS Codes and the project OH&S Specifications are the minimum requirements the Principal Contractor must apply during this contract with regards to Occupational Health and Safety. The Principal Contractor shall implement the minimum OH&S requirements and ensure conformance to these at all times.

  - Workers Compensation Registration

The Principal Contractor shall ensure that his employees are covered for any occupational injuries and illnesses in terms of the Occupational Injuries and Diseases Act 130 of 1993, which cover shall remain in place and up to date for the duration of the project.

The Principal Contractor shall ensure that his sub-contractor employees are covered for any occupational injuries and illnesses in terms of the Occupational Injuries and Diseases Act 130 of 1993, which cover shall remain in place and up to date for the duration of the project.

  - HSE Non-Compliance

It is a legal duty of the client according to the Construction Regulation 5(1)(q) that a Principal Contractor is stopped from executing any activity which poses a threat to the health and safety of persons. Depending on the seriousness of the non-compliance only the specific activity may be stopped until the non-compliance is rectified or the whole operation may be stopped.

It is also the duty of every employee to take reasonable care of his own health and safety and of other persons who may be affected by his acts as per OHS Act, Section 14(a). Keeping this in mind, it is required of The Principal Contractor to ensure his employees has the right to remove themselves from any unsafe situation or work activity, without any negative consequence to them until such time as The Principal Contractor has made the unsafe situation or activity as safe as practicable possible.

  - Indemnity by Contractor

The Principal Contractor shall indemnify the Employer against and from all damages, losses and expenses (including legal fees and expenses) resulting from:

- the loss of output and delay caused by the slowing down or partial or total stoppage of work caused by:

- all or any of The Principal Contractor’s workforce as a result of a dispute between all or any of the Principal Contractor’s workforce and The Principal Contractor; or

- all or any of the Principal Contractor’s suppliers’ difficulty or impossibility to deliver goods or materials needed to perform the Works;

- Any unlawful, riotous or disorderly conduct by or amongst the Principal Contractor’s personnel.”

  - The Principal Contractor Conduct

Guidelines to the most important rules that shall be implemented and maintained by the Principal Contractor:

- Complete compliance to the OH&S Act 85 of 1993 and Regulations,

- Hazard identification and Risk Assessments for all activities,

- Daily communication of DSTI’s before work commences, even if it is a repetitive task,

- Safe access and egress to and from work areas,

- Compulsory use of lifelines, Safety Harnesses and Fall Arrestors (Lanyards to be attached at all times), when working in elevated positions,

- Scaffold shall comply with Legal and SANS standards at all times,

- Good housekeeping and stacking practices,

- Safe lifting, rigging and slinging practices,

- Complying to Legal standards for lifting machinery & equipment,

- No lifting in wind conditions exceeding 30km/h (This is a guide and is dependent on risk assessments),

- Securing of tools, equipment and material at heights,

- Wearing of appropriate personal protective equipment as identified in the risk assessment.

Supervisors in charge are responsible for ensuring that the employees are aware of the hazards/risks involved in the work they will be doing/are doing and shall ensure the safety rules are obeyed.

No person shall act in a manner that endangers or is likely to endanger, the safety of any other person, or cause harm to any other person.

An employee who observes any dangerous situation, shall as soon as possible inform the person who is responsible for that section of the site.

Any employee who becomes aware of any person disregarding any safety rules, shall remind that person of the rules. If he persists in disregarding the rules, the matter must be reported to his supervisor.

No person shall damage, alter, remove, render ineffective or interfere with anything that has been provided for the protection of the site, or for the health and safety of persons.

No person shall interfere with or use firefighting equipment without authority and training.

No person in a state of intoxication or condition that render him incapable of controlling himself shall enter or be allowed to enter the site.

No alcohol or illegal drugs shall be taken onto the site.

All safety and warning signs shall be obeyed.

Always be alert of construction vehicles as well as traffic. Never turn your back to oncoming traffic, always have a line of sight.

  - Principal Contractor and Contractor Management

The Principal Contractor shall establish, maintain and ensure that all his contractors establish and maintain OH&S standards and systems as necessary and to comply with the Legal requirements as well as these OH&S specifications.

The Principal Contractor shall be solely responsible for carrying out work on the project, having the highest regard for the health and safety of his employees and people in the vicinity of his work area.

  - Public Health and Safety

The Principal Contractor shall, as far as is reasonably practicable, be responsible for ensuring that non-employees affected by the construction work are made aware of the dangers likely to arise from said construction work as well as the precautionary measures to be observed to avoid or minimise those dangers.

This includes:

- Non- employees entering the site for whatever reason

- The surrounding community

- Passers-by to the site.

E1016	DESIGNING FOR HEALTH, SAFETY AND THE ENVIRONMENT

Designing for safety is a process aimed at minimizing injury, death, property damage or destruction and harm to the environment, by utilizing an approach to identify and eliminate or control hazardous conditions and material during the design process. The Principal Contractor is responsible for appointing the temporary works Designer and shall ensure that the temporary works Designer implement a process and designs the temporary works in such a way that ensure the safety of employees during the erection, use and dismantling of the temporary works. The temporary work designer shall comply with the duties of the Temporary Work Designer as per the Construction Regulations, 2014 Section 6(2).

The Principal Contractor must communicate the anticipated risks and hazards resulting from the design to his employees and establish safe work procedures for the temporary works.

E1017	incident management

The Principal Contractor shall ensure that a culture exists within his company that promotes the recognition, response, reporting and investigation of incidents, including near misses (near hits). The Principal Contractor must implement a procedure for reporting and investigating accidents, incidents and near misses. The Principal Contractor should have a clear objective and target to obtain zero injuries for the duration of the project and such an objective must be communicated to all employees.

Appropriate corrective actions must be implemented, and the applicable learnings must be shared within The Principal Contractors business to prevent a recurrence of the incident or to prevent the near miss from becoming an incident in future.

- Incidents and Accidents

The Principal Contractor and his contractors shall coordinate their investigation of all accidents/incidents where employees and non-employees were injured to the extent that he had to be referred for medical treatment by a doctor, hospital or clinic. The results of the investigation shall be entered into an accident/incident register, which must be updated with each accident/indent.

The Principal Contractor shall notify the relevant SANRAL Project Manager and or SANRAL OHS Specialist of any incident/accident within the Principal Contractors or his Contractors area of responsibility in writing as soon as possible.

Although the accident/incident is reported to the client, the Principal Contractor has a responsibility and is required by law to report any Section 24 accidents and incidents to the Department of Labour. Any road traffic accident must be reported to the relevant authorities.

It is essential that the Principal Contractor demonstrate that corrective and preventative action has been taken to prevent a similar incident in future and that it is communicated to all the Principal Contractors affected staff. A copy of the investigation, corrective and preventative action taken as well as the attendance register of the employees who attended the discussion of the incident and the action implemented to prevent a similar incident, must be forwarded to the SANRAL Project Manager and or the SANRAL OHS Specialist.

Investigations must be completed for:

- Near Miss Incidents (To prevent it from becoming an incident)

- First Aid case Incidents

- Medical treatment case Incidents

- Fatalities

  - Incident Reporting

The Principal Contractor shall provide the Employer with copies of all statutory reports required in terms of the Act within 7 days of the incident occurring. In addition, The Principal Contractor shall update monthly the Disabling Injury Frequency Ratio (DIFR) and display this information on a signboard at the site office.

The Principal Contractor is responsible for collecting, recording, calculating and reporting his and his sub-contractors Health & Safety statistics to the SANRAL OHS Specialist.

The statistics should contain at least the following for all employees of all contractors working on the project:

- Total Number of workers

- Total Number of hours worked (on the SANRAL project)

- Total Number of Near Miss Incidents

- Total Number of First Aid case Incidents

- Total Number of Medical Treatment case Incidents (Excluding Section 24 type incidents)

- Total Number of Section 24 type Incidents

- Preventative actions taken on incidents that have occurred

- Communication to employees and contractors of incidents and preventative actions.

E1018	PROJECT SPECIFIC CONSTRUCTION REQUIREMENTS

The clause contains specific requirements for Contract SANRAL N.001-249-2019/1R NSC which must be adhered to in addition to minimum legislative requirements.

  - Baseline Risk Assessment (Part C3.5 Risk Assessment Plan)

The following is a list of activities, hazards and risks identified which forms the Baseline Risk Assessment for the project prepared by the Client in terms of Construction Regulation 5(1) (a):

Risks associated for identified activities and hazards:

  - Daily Site Attendance Register

The Principal Contractor shall keep a daily site register so as to be able to identify the entire Contractors personnel on site in case of an emergency or evacuation situation. The attendance register must include permanent as well as temporary workers working on the site.

All contractors shall report to security/reception upon arrival at site. The Principal Contractor will only grant first time access to work on the site if all required documentation has been provided by the contractor and has been approved by the Principal Contractor.

All site visitors, suppliers and any new contractors shall report to security/reception upon arrival at site. All visitors need to sign an attendance register when visiting the site. Visitors include all persons which are not permanently working on the site but excludes temporary site workers. Visitors must undergo site induction training before they are allowed on site to make them aware of the site dangers.

  - Emergency Numbers / Emergency Evacuation

A list with emergency numbers must be readily available to first aiders and supervisors. Emergency numbers must be site specific and must display the nearest emergency facilities.

The Principal Contractor shall identify and formulate emergency procedures in the event an incident does occur. The emergency procedures thus identified shall also be included in The Principal Contractor’s OH&S plan and communicated as part of induction training. It is the responsibility of the first aid worker, together with the construction supervisor, to make an assessment regarding the severity of injuries and which actions are appropriate. For example: transfer to a medical facility by ambulance or helicopter.

The Principal Contractor must implement an emergency evacuation procedure on site to ensure that in case of an emergency, all staff will leave their place of work when the emergency siren is sound and proceed to the designated emergency assembly point. The emergency assembly point at the site office must display the sign “Emergency Assembly Point”.

An evacuation route diagram must be displayed and visible at strategic points in the site office buildings and on notice boards.

All staff working on site must be given awareness training on the emergency evacuation procedure and evacuation drills must be exercised to ensure all staff know the correct procedure to follow in case of an emergency.

  - Site Security

Certain areas where work must be carried out, is recognized unsafe areas and certain other areas may from time to time become unsafe, due to 3rd party actions. The Principal Contractor must, as far as reasonably possible, anticipate unsafe areas and must ensure that his site staff is safe from 3rd party actions, which include but is not limited to:

- Unrests,

- Violent Demonstrations,

- Theft,

- Injury to staff due to 3rd party actions.

The Principal Contractor must, when work is to be carried out in the above-mentioned areas, make provision for security services to accompany site staff during the execution of their work, as The Principal Contractor is responsible for the Health, Safety and Security of his own staff. The provision for security services must form part of The Principal Contractors tender.

  - Personal Protective Equipment

Comply with General Safety Regulations, Section 2

The Principal Contractor shall identify the hazards in the workplace and follow the hierarchy of controls to prevent incidents. Where possible, hazards must be eliminated or, where impracticable, mitigate the hazards through implementing control measures. Where mitigated hazards still pose a risk to the health and safety of workers, take steps to protect workers and make it possible for them to work safely and without risk to their health under the hazardous conditions, by wearing personal protective equipment and clothing.

Personal protective equipment (PPE) should, however, be the last resort and there should always first be an attempt to apply engineering and other solutions to mitigate hazardous situations before the wearing of PPE is considered. The hierarchy of hazard control must be followed before the option of personal protective equipment is considered. The following hierarchy of controls must be followed:

- Elimination

- Passive Controls

  - Substitution – Using a cherry picker or man-lift instead of a ladder.

  - Engineering Controls – Installing barrier railings; Installing stairs instead of using vertical ladders.

- Active Controls

  - Administrative policies and procedures

  - Personal protective equipment

Where it is not possible to create an absolutely safe and healthy workplace, the Principal Contractor shall inform employees regarding this and issue, free of charge, suitable equipment to protect them from any hazards being present and that allows them to work safely and without risk to health in the hazardous environment.

It is a further requirement that the Principal Contractor maintain the said equipment, that he instructs and trains the employees in the use of the equipment and ensures that the prescribed equipment is used by the employee/s.

Employees do not have the right to refuse to use/wear the equipment prescribed by the Employer and, if it is impossible for an employee to use or wear prescribed protective equipment through health or any other reason, the employee cannot be allowed to continue working under the hazardous condition/s for which the equipment was prescribed but an alternative solution has to be found that may include relocating the employee.

The Principal Contractor shall include in his OH&S plan the PPE he intends issuing to his employees for use during construction and the sanctions he intends to apply in cases of non-conformance by his employees. Conformance to the wearing of PPE shall be discussed at the DSTI and Toolbox Talk meetings.

The Principal Contractor shall ensure that all his personnel, excluding those who are permanently office bound, are equipped with reflective safety jackets and that these are worn at all times when working on site. Any person found not wearing a reflective jacket on site must be removed from the site until such time as he is in possession of and wearing a reflective jacket. Reflective safety jackets shall be kept in good condition and any jackets that are ineffective must immediately be replaced by The Principal Contractor.

  - Site Supervision

Comply with Construction Regulation, Section 8.

The Principal Contractor shall appoint a competent Construction Manager who shall be responsible for the construction activities and for ensuring occupational health and safety compliance on the construction site.

  - Working in Elevated Positions

Comply with Construction Regulation, Section 10

The Principal Contractor shall ensure that a fall protection plan, developed by a competent person who is designated as the Fall Protection Plan Developer, is available on site and understood by all employees who will be working in elevated positions.

All employees working in elevated positions shall protected themselves from falls by wearing a full body harness and the lanyard shall be attached as far as possible above the head of the worker to a life-line or other approved and anchor point indicated in the fall protection plan.

In addition to obvious elevated work activities, work activities which include:

- Working on the edge of an excavation where there is a risk of falling into the excavation; or

- Work on the edge of a vertical drop where there is a risk of falling;

shall be considered work in elevated positions and Section 10 of the Construction Regulations must be adhered to at all times. The hierarchy of controls must be implemented when such activities are carried out. As a minimum the employee must wear PPE as identified in the risk assessment, which shall include a full body harness.

  - Structures

Comply with Construction Regulations, Section 11.

The Principal Contractor shall ensure that all practicable measures are taken to prevent the uncontrolled collapse of new or existing structures or any part thereof, which may become unstable or is in a temporary state of weakness or instability due to the carrying out of construction work. No structure may be loaded in a manner which would render it unsafe.

When a structure is of temporary nature, all conditions as required by the Construction Regulations Section 12 - Temporary Works, must also be complied with.

  - Excavations

Comply with Construction Regulations, Section 13

The Principal Contractor shall ensure that all excavations are carried out under the supervision of a competent person who has been appointed in writing as Excavation Supervisor.

The Principal Contractor must evaluate the stability of the ground before excavation work begins as well as during excavation work.

Excavations must be barricaded to prevent unauthorized access.

Material removed from excavations, as well as heavy machinery and construction vehicles, must not be closer than 1 meter to the edge of the excavation, to prevent additional loads on the excavation edge, which could cause cave-ins, to prevent construction vehicles from falling into the excavation and to prevent the accumulation of carbon monoxide gas inside the excavation.

The principal contractor and its contractors must cause every excavation which is accessible to the public or which is adjacent to the public roads or thoroughfares, or whereby the safety of persons may be endangered, to be –

- Adequately protected by a barrier or fence and as close to the excavation as is practicable; and

- Provided with warning illuminants or any other boundary indicators that are clearly visible at night or when visibility is poor.

People working in the excavation must be adequately protected from cave-ins, by means of protection systems such as trench boxed and shielding and must have a safe means of access into the excavation and egress from the excavation.

  - Scaffolding

Comply with Construction Regulations, Section 16, General Safety Regulations, Section 6 and SANS 10085 – The Design, erection, use and inspection of access scaffolding

The Principal Contractor shall appoint a competent person in writing as scaffolding Supervisor. Scaffolding Inspectors and Scaffolding Erectors must be trained and found competent to carry out scaffolding work. It is important to note that only competent scaffold erectors are allowed to build the scaffolding. The scaffold inspector is not allowed to build the scaffold with the scaffold erector team.

Scaffolding shall be erected according to SANS 10085 and shall be tagged “Unsafe for use” while it is being build and “Safe for Use” after inspection indicated that the scaffold is safe to use. The inspection of the scaffold shall be in writing and proof thereof shall be available for any user of the scaffold as well as for audit purposes.

Scaffold left erected while The Principal Contractor is not in attendance, must be tagged with a “Not Safe for Use” tag and all reasonably practicable measures must be taken to prevent unauthorised access to the scaffold.

Scaffold must be inspected by the competent scaffold inspector on completion of the scaffold build, weekly thereafter or following severe weather conditions.

Hazards such as overhead power lines must be identified before the scaffold is build and must be reflected in the risk assessment.

When using mobile scaffold, employees and materials must be removed from scaffold before moving the mobile scaffold. Hazards such as overhead power lines must be identified before moving mobile scaffold and must reflect in the risk assessment.

  - Suspended Platforms

Comply with Construction Regulation, Section 17, SANS 10295-2 - Suspended access equipment Part 2: Temporary suspended platforms (TSPs)

All suspended platform work must be carried out under the supervision of a competent appointed Suspended Platform Supervisor. Suspended platform erectors, operators and inspectors must be competent.

The Principal Contractor must be in possession of a certificate of design for the use of the suspended platform system.

  - Cranes

Comply with Construction Regulation, Section 22, Driven Machinery Regulation, Section 18.

Crane operators must be trained and found competent to operate the particular type of lifting machine and have a valid operator’s card. The crane operator must be in possession of a valid medical certificate of fitness, issued by an occupational health practitioner.

The wind factor should always be taken into consideration when operating cranes and a wind speed device must be fitted so that it provides the operator with an audible warning when the speed exceeds the safe lifting speed. Upon noticing that the wind speed is equal or more than the specified speed limit, the operator should stop immediately.

  - Construction Vehicles & Mobile Equipment

Comply with Construction Regulation, Section 23, National Road Traffic Act, 1996

Construction vehicle operators must have received training to operate the class of construction vehicle or mobile equipment and must be in possession of an operator’s card as proof of competency. Construction vehicle operators must be authorised in writing and have a medical certificate of fitness issued by an occupational health practitioner to operate the construction vehicle and/or mobile equipment.

All construction vehicles operating on a public road, must be roadworthy, licenced and when operated on a public road, comply with the National Road traffic Act.

  - Electrical Equipment

Comply with Construction Regulations, Section 24.

The Principal Contractor shall take adequate steps to ascertain the presence of and guard against danger to workers from electrical cables or apparatus which is under, over or on the site.

The exact location of underground electric power cables must be determined before any excavators are used for excavation purposes.

The location of overhead electrical cables must be assessed when working with cranes and lifting equipment. Injury may be possible from touching the electrical cables with the crane boom, or from arching when the crane boom comes too close to the electrical cable.

All temporary electrical installations must be inspected at least once a week by a competent person and the records of the inspections must be recorded in a register which must be kept on site.

Electrical machinery and extension cords must be is a serviceable condition and must be inspected on a daily basis before use on a construction site by the authorised operator and the inspection checklist must be kept on the construction site.

Comply with Electrical Installation Regulations.

All electrical installations shall be inspected and approved by an accredited electrical inspector and a valid Certificate of Compliance must be issued for the installation.

All electrical installations carried out on site (permanent and temporary) must be in accordance and comply with the Electrical Installation Regulations.

All power supplies and generating units must be fitted with a functional earth leakage device.

  - Temporary Storage of Flammable Liquids

Comply with Construction Regulation, Section 25 and General Safety Regulations, Section 4

The Principal Contractor must ensure storage areas of flammable liquids are well ventilated and “No Smoking” signs are placed at the entrances and ventilation ducts of the storage areas. Firefighting equipment must be available in suitable positions around the storage areas.

The Principal Contractor must ensure that good housekeeping is practiced in and around the flammable storage areas.

  - Water Environments

Comply with Construction Regulation, Section 26.

The Principal Contractor must ensure that a lifejacket forms part of the employees PPE and is worn when the employee is exposed to the risk of drowning, by falling into water.

The risk assessment must make provision for the rescuing of persons in danger of drowning and for preventing employees from falling into the water.

When working next to a river, the Principal Contractor shall put a system in place to monitor the river water level in order to evacuate employee in case of a flood.

When working over water environments, Section 10 of the Construction Regulations – Fall Protection will also apply.

  - Housekeeping

Comply with Construction Regulation, Section 27, Environmental Regulations for Workplaces, Section 6(3).

The Principal Contractor shall ensure that suitable and acceptable housekeeping is continuously implemented and maintained on the construction site. Off-cuts and waste must be removed as soon as practicable.

  - Stacking & Storage of Material, Plant & Equipment

Comply with Construction Regulations, Section 28 and General Safety Regulations, Section 8.

The Principal Contractor shall appoint a competent person in writing with the duty of supervising all stacking and storage operations on site.

Stacking shall only take place in areas specifically demarcated for this purpose. Circular items must be secured with wedges or chocks.

Items removed from a stack shall only take place from the topmost layer of the stack.

Stacks shall not obstruct any fire extinguishing equipment, first aid equipment, electrical switchgear (DB Boxes) and ventilation or lighting installations.

Unstable stacks must be broken down immediately.

  - Fire Precautions

Comply with Construction Regulation, Section 29.

The Principal Contractor must provide his own firefighting equipment that is within the service date and safe for use. Firefighting equipment must be on a register and inspected by a competent person who has been appointed in writing.

Suitable and sufficient fire extinguishing equipment must be placed at strategic locations and a sufficient number of firefighters must be available, which must be trained in the use of it.

  - Intoxicating Liquor and Drugs

Comply with General Safety Regulations, Section 2A.

The principal Contractor must compile a Substance Abuse Policy, which must be communicated to all employees. This policy should form part of the induction material for employees as well as visitors.

The Substance Abuse Policy should set the limit for intoxication to zero in order to complement a vision of zero tolerance.

Any person found to be intoxicated, or consuming intoxicating liquor or illegal drugs, shall not be allowed onto the premises and/or must be removed from the premises.

The Principal Contractor has the right to test any person entering the premises for intoxicating liquor or illegal drugs and may refuse entrance on the basis of the outcome of the test.

The Principal Contractor shall ensure that employees taking prescription medicine informs the Principal Contractor of such and shall ensure that the side effect of such medicine does not constitute a hazard to the employee himself or people working with, or in close proximity to the employee.

  - Confined Space Work & Tunnelling

Comply with Construction Regulation, Section 15 and General Safety Regulations, Section 5.

The Principal Contractor shall ensure that only authorized persons enter confined spaces.

An entrance log must be kept to ensure people are not left inside the confined space. Adequate air monitoring must be carried out before entering the confined space. When air monitoring indicated the oxygen to be less than 20% by volume, the confined space must be purged and ventilated to obtain a safe atmosphere or self-contained breathing apparatus must be used.

  - Site Services

The Principal Contractor shall provide and maintain on the site adequate facilities for employees to use, which must be serviced and kept sanitary and hygienic at all. The following site services should be taken not of:

- Drinking Water

The Principal Contractor must ensure that an adequate supply of potable drinking water is available for all persons engaged in managing and working on the construction site and, if necessary, similar facilities elsewhere for such personnel off the site. Employees working in hot conditions must consume enough water per hour to prevent dehydration.

Where water is unsafe for human consumption, it must be so indicated by means of adequate signage.

- Accommodation

The Principal Contractor shall comply with the requirements of Construction Regulation 30 with regards to employee’s accommodation. Reasonable and suitable living accommodation must be provided to employees who are far removed from their homes.

- Sanitary Facilities

The Principal Contractor shall comply with the requirements of Construction Regulation 30 with regards to employee’s sanitary facilities. Sanitary facilities must be positioned in close proximity of the work area. Sanitary facilities must be serviced regularly and kept in a clean and hygienic condition.

  - Traffic Accommodation

The Principal Contractor must develop a clear Traffic Management Plan, which must be approved by the Engineer. Traffic must be organized and controlled in accordance to the Traffic Management Plan and any work area must have adequate signage, signaling or other control arrangements to guard against the dangers relating to the movement of vehicles. Where reasonably practicable, solid barriers must be placed between workers and traffic passing by.

When the Principal Contractor is executing night work, permission should be obtained from the Engineer. The Principal Contractor must put in place visible or reflective signs that can be seen by motorist at a distance. If a stop and go method is used flag persons must be properly trained on how to control the traffic.

PART C4:	SITE INFORMATION

PART C4 – SITE INFORMATION

The contents of all site information in the Project Information Document (Volume 4) are as follows:

|  | PAGE |
| --- | --- |
| PART A General |  |
| A1 Locality map | A1 |
| A2 Lane area schematic layout | A2 |
| A3 Building layouts | A3 |
| A4 Toll plaza and lane area layout | A4 |
| PART B Matters Relating to FIDIC CONDITIONS OF CONTRACT for THE DESIGN-BUILD AND OPERATE PROJECTS (vOLUME 1 BOOK 1) |  |
| B1 Current contractors / suppliers (toll system related) | B1 |
| B2 NOT APPLICABLE | B2 |
| B3 AVC LOOP AND PAD REPORTS | B3 |
| B4 OTDR TEST RESULTS | B4 |
| B5 UPS & Generator 6 monthly report for all plazas (Not applicable) | B5 |
| B6 LIGHTNING PROTECTION AND EARTHING REPORT (Not applicable) | B6 |
| PART C Matters Relating to the Standard Specification for Operations and Maintenance OF CTROM PROJECTS: General (VOLUME 2 BOOK 2a) |  |
| Section 2: PROJECT COMMENCEMENT: HANDOVER AND PROVISION OF DOCUMENTS |  |
| C1 Plaza maintenance cost statistics (Not applicable) | C1 |
| C2 List of all available as-built drawings | C2 |
| C3 List of available equipment manuals, supplier manuals and user manuals | C3 |
| C4 Asset Registers: Civil, structural, building, O&M, E&M, LE and MIS | C4 |
| C5 SANRAL Asset Management System format | C5 |
| C6 ELECTRICAL CERTIFICATE OF COMPLIANCE (COC) (not applicable) | C6 |
| Section 4: Toll Plaza Expansions, UPGRADES Road Improvements and Other Improvements |  |
| C7 CURRENT AND PLANNED PLAZA CONFIGURATION AFTER IMPLEMENTATION OF DEDICATED ETC LANES | C7 |
| Section 7: OPERATIONS PERIOD - Financial Management |  |
| C8 Schematic of EXISTING queue length system camera position | C8 |
| C9 ITIS DESKTOP PROJECT INFORMATION MANUAL | C9 |
| C10 Credit and fleet card procedures | C10 |
| C11 Description of the current toll system | C11 |
| C12 Merchant AgreementS | C12 |
| C13 Toll System Compliance INCLUDING SNAG LIST | C13 |
| C14 Existing AVC Accuracy Data | C14 |
| C15 Typical Frequent User Information Flier (not applicable) | C15 |
| Section 10: OPERATIONS PERIOD - Traffic Management |  |
| C16 Historic avc MIS, TEL1 and TEL2 traffic figures from JULY 2011 to MAY 2023 | C16 |
| - Daily traffic per virtual plaza |  |
| C17 avc, MIS AND TEL Hourly Traffic FROM JULY 2011 to MAY 2023 (not applicable) | C17 |
| C18 TRAFFIC MONITORING SERViCES (not applicable) | C18 |
| C19 Historic Hourly Traffic – Alternative Route (TEL stations) FROM 2013 TO 2022 FOR CTO’S (not applicable) | C19 |
| C20 Financial reports from JULY 2011 to APRIL 2023 (not applicable) | C20 |
| - AGI, cash, credit cards, run-through, credit granted, no payments, local user discount AND frequent user discounts |  |
| C21 Key summary traffic data (NOT APPLICABLE) | C21 |
| C22 TEL Quality Assurance System (not applicable) | C22 |
| Section 14: ASSET MANAGEMENT |  |
| C23 typical General Maintenance and Inspection Checklist (not applicable) | C23 |
| C24 CORROSION REPORT (not applicable) | C24 |
| Section 15: GENERAL |  |
| C25 Historic utility costs (not applicable) | C25 |
| Section 19: Toll Road Services |  |
| C26 MEDIAN BARRIER DIAGRAMS (not applicable) | C26 |
| C27 Frequency of accidents in toll plaza area (not applicable) | C27 |
| c28 locality sketch of rims boundaries (not applicable) c29 DETAILS OF SHESHA LANE SIGNS (not applicable) c30 NOT USED/APPLICABLE c31 Typical rims fact sheets (not applicable) c32 NOT USED/APPLICABLE c33 NOT USED/APPLICABLE c34 LANE UPS INSTALLATION c35 ASSETS TO bE REPLACED OR UPGRADED (TOLL SYSTEM RELATED) c36 ENERGY CONSUMPTION (TOLL SYSTEM RELATED) c37 RIMS DETAILS (NOT APPLICABLE) | c28 c29 c30 c31 c32 c33 C34 C35 C36 C37 |
| PART D MATTERS RELATING TO THE STANDARD SPECIFICATIONS FOR OPERATIONS AND MAINTENANCE OF CTROM PROJECTS: PAYMENT METHODOLOGY AND DESCRIPTION OF PAYMENT ITEMS (VOLUME 2 BOOK 7A) |  |
| D1 PREDICTED MONTHLY TRAFFIC VOLUMES | D1 |
| D2 PREDICTED TOLL TARIFFS (NOT APPLICABLE) | D2 |
| D3 PREDICTED TRAFFIC GROWTH RATES (NOT APPLICABLE) | D3 |
| D4 PREDICTED CPI INCREASE (NOT APPLICABLE) | D4 |

PART C5: ANNEXURES TO CONTRACT DOCUMENT

the power, by one person or a group of persons holding the majority of the equity of an enterprise, alternatively, the person/s having the deciding vote or power to influence or to direct the course and decisions of the enterprise.

Joint venture or Consortium means an association of persons for the purpose of combining their expertise, property, capital, efforts, skill and knowledge in an activity for the execution of a contract.

CIDB Standard for Contract Participation Goals for Targeting Enterprises and Labour through Construction Work Contracts, Refer to latest version on www.cidb.org.za, and as adapted from SANS 10845, Suite for Construction Procurement, 2015.

Adapted from the CIDB Standard for Contract Participation Goals for Targeting Enterprises and Labour through Construction Work Contracts, Refer to latest version on www.cidb.org.za, and as adapted from SANS 10845-5:2015 and SANS 10845-8:20SANS 10845, Suite for Construction Procurement, 2015.

CIDB Standard for Developing Skills through Infrastructure Contracts, Refer to latest version on www.cidb.org.za.

.

CIDB Standard for Minimum Requirements for Engaging Contractors and Sub-Contractors on construction Works Contracts, Refer to latest version on www.cidb.org.za.

CIDB Standard for Minimum Requirements for Engaging Contractors and Sub-Contractors on construction Works Contracts, Refer to latest version on www.cidb.org.za, CLO definition.

Derived from SANRAL communication Policy, Refer to latest version.

.

Derived from SANS 10845-7:2015, definition 2.12