# Part 3: Scope of Work

| Document reference | Title |  |
| --- | --- | --- |
|  | This cover page |  |
| C3.1 | Employer’s Service Information |  |
| C3.2 | Contractor’s Service Information (insert at award stage or delete if not applicable) |  |

# C3.1: Employer’s service Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s service Information	2

1	Description of the service	5

1.1	Executive overview	5

1.2	Abbreviations	5

1.3	Employer’s requirements for the service	5

1.3.1	Extent of the Scope	5

1.3.2	Boundaries	6

1.3.3	Base Crew Composition (Minimum Requirements)	7

1.3.4	Maintenance and plant excluded from the scope of work	7

1.3.5	Maintenance Philosophy	7

1.3.6	Outage and Opportunity Work	9

1.3.7	Shift and Standby	9

1.3.8	Over Time	10

1.3.9	Modifications	10

1.3.10	Work Interface	10

1.3.11	Working Hours	10

1.3.12	Spillages and leaks	10

1.3.13	House keeping	10

1.3.14	Plant Criticality	11

1.3.15	Maintenance Planning	11

1.3.16	Spares Management	12

1.3.17	Plant and plant equipment Alignment	12

1.3.18	Quality Control	13

1.3.19	Rigging Service related to the Execution of Work	13

1.3.20	Welding	13

1.3.21	Strike Action	13

1.3.22	KPIs	14

1.3.23	Plant Hazards	14

1.3.24	Delegation of Contract roles	14

1.3.25	Procedures	14

1.3.26	Contract Conclusion	14

1.4	The Contractor’s plan for the service	14

1.5	Meetings	15

1.6	Contractor’s management, supervision and key people	16

1.7	Documentation	18

1.7.1	Correspondence	18

1.7.2	Work packages	18

1.7.3	Procedure, work packages, QCP, SMPs created during this contract	18

1.7.4	Other Documentation	18

1.7.5	Contract Conditions	18

1.8	Invoicing and payment	18

1.8.1	Purchase order or Purchase requisition	18

1.8.2	Emergency work	18

1.8.3	Assessments	19

1.8.4	Tax Invoice	19

2	Health and safety, the environment and quality assurance	19

2.1	Health and Safety	19

2.1.1	Eskom Life Saving Rules	19

2.1.2	Plant Safety Regulations	19

2.1.3	Fire Precautions	20

2.1.4	Reporting of incidents	20

2.1.5	Vehicle Safety	20

2.1.6	Barricading / Screens and Scaffolding	21

2.1.7	Health and Safety Arrangements	21

2.1.8	Company Branding	22

2.1.9	Special requirements	22

2.1.10	Exposure to Silica	22

2.2	Environmental constraints and management	22

2.2.1	Work carried out in terms of:	22

2.2.2	New Environmental Legislation	22

2.2.3	Existing Environmental Legislation	23

2.2.4	Liability	23

2.2.5	Hazardous substances	23

2.3	Quality control and assurance requirements	23

2.3.1	Personal Competency	23

2.3.2	Quality Requirements	23

2.3.3	Quality Control Documents	23

2.4	General Requirements	23

2.4.1	Direction and Instructions	23

2.4.2	Workmanship	23

2.4.3	Section 27(2)	23

2.4.4	Non-Compliance	24

2.4.5	Labour Laws	24

3	Procurement	24

3.1	Subcontracting	24

3.2	Plant and Materials	25

3.2.1	Correction of defects	25

3.2.2	Plant & Materials provided “free issue” by the Employer	25

4	Working on the Affected Property	25

4.1	Employer’s site entry and security control, permits, and site regulations	25

4.1.1	Security and Access Arrangements	25

4.2	People restrictions, hours of work, conduct and records	26

4.2.1	Only authorised persons may have site access and perform work.	26

4.2.2	Majuba Power Station normal working hours are:	26

4.2.3	Working Hours	26

4.2.4	Removal from Site	26

4.3	Health and safety facilities on the Affected Property	26

4.4	Cooperating with and obtaining acceptance of Others	26

4.5	Records of Contractor’s Equipment	26

4.6	Equipment provided by the Employer	27

4.6.1	General	27

4.6.2	Rigging	27

4.7	Site services and facilities	27

4.7.1	Provided by the Employer	27

4.7.2	Provided by the Contractor	27

4.7.3	Contractor’s yard	27

4.8	Control of noise, dust, water and waste	28

4.8.1	Waste Disposal	28

4.8.2	Noise	28

4.9	Tests and inspections	28

5	Service Level Table	28

6	List of Documents	29

6.1	Drawings issued by the Employer	29

6.2	Relevant Documents	30

# Description of the service

## Executive overview

The objective of this contract is for the Contractor to provide a Comprehensive Mechanical, Electrical and Control and Instrument Maintenance Service for Majuba Power Station Fuel Oil Plant. The delivery of this Service does not include Plant Spares.

The Contractor performs Planned, Corrective, preventative, opportunity and Outage Maintenance.

The Contractor Provides a Base crew for preventative and Corrective Maintenance to be based on Site and additional crews for Outage work execution when required.

The Contractor Provides For a duct repair service on an as and when required basis.

The Contractor has an effective quality management system in place and be ISO 9001 approved.  Furthermore, all activities will be done as per to the level of quality management stipulated therein, also taking into account Input from Majuba Engineering Section, Risk assurance department and Management.

The Contractor provides qualified and competent teams with all the necessary equipment to provide the Service.  The Contractor’s teams must always be led and Supervised by Qualified, Competent and experienced supervisors.  The Contractor must provide the equipment needed to provide the Service. Spares will be supplied by the Employer.

The Contractor has identified a representative as a key person approved by the Employer on site during working hours and when otherwise required who will report to the Service manager and co-ordinate all activities. The Site representative must be a Qualified and experienced Site Manager.

The Contractor performs all planning and scheduling associated with the Plant in line with the Eskom Works Management Process.

The Contractor is Subject to low Performance Penalties as indicated in The Service Level Table in Sub Section 6 below.

The Contractor ensures that the contracted service is performed regardless of strike and industrial action.

The Contractor establishes his own yard with all the relevant facilities on the site indicated by the Employer.

## Abbreviations

FOB 	-	Fuel Oil Burners ( Also Fuel oil plant Planner Group in SAP)

SAP 	-	Systems Applications and Products

NEC	-	New Engineering Contract

SOW	-	Scope of Work

KPI	-	Key Performance Indicators

RBO	-	Reliability Basis Optimising

PSR   -	Plant Safety Regulations

## Employer’s requirements for the service

### Extent of the Scope

#### To perform Mechanical Maintenance on the Fuel Oil plant in a safe, efficient and effective manner, to meet the demands of Majuba Power Station.

NOTE: Contractor ensures that the Fuel Oil Plant is Available & Reliable to such an extent that ZERO load losses have to be taken on the Units due to the Fuel Oil Plant.

.

### Boundaries

#### The boundaries of the plant where maintenance is to be performed will cover the following systems:

- The Fuel Oil Offloading Plant and pipework up to the Storage tanks.

- The Fuel Oil Pump House, Storage and reticulation up to the Fuel Oil Burners.

- The Fuel Oil Burners and Core Air Ducts.

- The Low Pressure (LP) Gas Reticulation and Distribution System.

#### Maintenance , repair, optimization, implementation, commissioning, Investigations and Clarification of Problem areas, review of planned maintenance programs, Specialized fault finding, Re-commissioning and return of units to service from outage, cold reserve or Two Shifting.

#### Electrical Maintenance of fuel oil plant cubicles which are positioned in the equipment rooms and switchgear rooms. This includes primary elements up to and including the switchgear.

#### Control and Instrumentation Standby duties on the fuel oil plant, also including two shift coverage.  The C&I maintenance includes the primary elements up to and including the Siemens control system. Duties also include fault finding in the Siemens software (logic). C&I Technicians to have at least 3 years working Experience in Siemens Teleperm Me and Teleperm XP control Software.

#### All installed Mechanical equipment will be maintained.

#### Where access is required to perform Maintenance work the Contractor will be required to supervise the removal and then reinstating of cladding and sheeting and the Construction of Scaffolding.

#### Structure, Welding and Boiler Making

- Ensuring that Structural Bolts, fasteners etc. are in place and Tight

- Manufacturing, turning, welding and fitting of brackets and other simple fittings

- Replacement and maintenance of Holding down Bolts, Anchor points and grouting

- Replacement and maintenance of floor grating

- Replacement and maintenance of hand railing

- Corrosion protection and painting of plant and equipment.

- Repairs to Core and Secondary Air ducts

- Duct and pipe hangers

#### Where Structural work is required to be removed and reinstated the Contractor will perform this in accordance with an approved procedure. The Contractor is required to provide this documented procedure.

#### The Contractor implements modifications where:

- Plant is obsolete and replacement items are supplied

- The Modification will not interfere with the execution of Maintenance work.

#### The Following minimum Plant Safety Regulation requirements will be adhered to:

- 2 personnel to be PSR Authorised to Accept Mechanical Permits.

- 3 personnel to be PSR Authorised to Accept C&I Permits.

- 2 personnel to be PSR Authorised to Accept Electrical Permits.

#### Test Rig

- The Contractor maintains the Majuba Test rig.

- The Contractor Tests and calibrates burner blocks, lances and tips as per QC requirements.

### Base Crew Composition (Minimum Requirements)

| Designation | Patterson Band Level | Numbers |
| --- | --- | --- |
| Site Manager | M14 | 1 |
| Supervisor | T13 | 1 |
| Control and Instrumentation Mechanician | T09 | 6 |
| Electrical Artisan | T09 | 2 |
| Mechanical Fitter | T09 | 4 |
| Semi-Skilled | T05 | 10 |
| Safety Officer | T11 | 1 |
| Total Base Crew |  | 26 |
| As and When Required |  |  |
| Boilermaker | T09 | 2 |
| Welder | T09 | 2 |
| Semi-skilled Assistant | T05 | 4 |
| OUTAGE WORK PER YEAR |  |  |
| C&I Technician | T09 | 1 |
| Fitter | T09 | 1 |

### Maintenance and plant excluded from the scope of work

- All fire protection systems

  - The Contractor is required to notify Fire Maintenance and engineering when work is done where these systems are installed so that measures can be taken to reduce damage.  In the event that the Contractor Damages such equipment the Contractor repair the fire system at his cost.

- Plant Hoists, cranes and load beams.

  - Hoists, crawls and cranes installed in the plant that are required for plant maintenance work are to be requested through the Plant Supervisor in writing at least 2 weeks before the time.

- Air conditioning and ventilation systems for buildings.

### Maintenance Philosophy

#### Running Maintenance

Running maintenance inspections is seen as the Daily walk downs that will be done by the Contractor.  During these walk downs qualified & experienced artisans will do inspections while the plant is in operation.  All defects or potential failures will be recorded in SAP as a basis for planning and history capturing.  The Inspections will be documented by the Contractor.

The defects will be listed and corrective actions will be planned according to the priority of the defects. The detailed planning of critical/major activities, together with, Standard Maintenance Package (SMP) including QCP’s and risk assessments will be done by the Contractor and approved by the Service Manager.  Where Permits to Work are required, the work will be planned with the Production Manager of Majuba P/S via the Service Manager).

#### Planned Maintenance

Planned maintenance schedules initiated by Employer will be followed to prevent any potential breakdowns or failures of equipment. Appendix Ai contains a Sample Service plan and Appendix Aii contains a list of Maintenance Planned Tasks currently in the SAP system.

#### Corrective and Breakdown Maintenance

All unpreventable and unforeseen plant failure occurrences, replacement of damaged plant and equipment are included.

The Authority for determining the criticality of Work rest with the Production Managers , repairs to plant on breakdown are to start as soon as possible and continue until the plant is back in operation.  Except for safety reasons the Service manager’s permission is required to postpone breakdown work.

#### Condition based maintenance / monitoring

The purpose of Condition Based Maintenance is to enable the monitoring of the performance, physical condition and potential failure modes of equipment. Majuba’s engineering department performs most of the Condition Based Monitoring.  Condition Based Maintenance tasks are included in the Appendix Ai.  The replacement of wearing parts might be postponed or brought forward based on the plant condition.  There will also be Corrective actions based on the Finding from Condition monitoring activities.

#### Daily Plant Inspections

Defects that put the plant at risk are to be reported to the Service Manager immediately and action taken to correct the fault as soon as possible.

It is expected that all plant deterioration or faults be identified and corrected by the Contractor before they become a major risk to the plant or a break down.

#### Repair Times

Eskom’s Works Management process requires that work be prioritised and that corrective action be taken as follows:

Priority 1 – 24 hours to affect the repair

Priority 2 – 72 hours to affect the repair

Priority 3 – planned and completed within 5 weeks

#### Revision of Maintenance Scope

The Maintenance Schedule is reviewed annually as part of the Reliability Basis Optimising process.

Improvements to the Preventative Maintenance Strategy in line with the RBO process are expected during the duration of the contract.

The Contractor makes experienced personnel available for the revision of Maintenance Strategies through the RBO process.

### Outage and Opportunity Work

#### Units 1-6

Maintenance Opportunities are sometimes provided on short notice. When a Unit comes down for repairs it is expected that all outstanding work on the units is planned, in readiness for execution on short notice and that when the Unit returns to service that there are no outstanding Work orders Planned or Corrective.

In line with point 1.3.4.5 above it is expected that there will be no unidentified Faults on the plant when it returns to service.

Planned outages are provided on the Units on a 3 yearly interval 14 days and 6 yearly intervals for 60 days.  Refer to Appendix C for a sample of the scope.

The scope contained in Appendix C is a sample of the scope of work that has been executed during outages and is subject to confirmation and revision.

The Contractor is to provide sufficient resources to perform the required work as per a defined scope of work on the plant during opportunities provided.

The Contractor provides a dedicated crew for outage work.

All outage work will be conducted on a 24 hour basis.

### Shift and Standby

This Contract makes allowance for Standby:

#### Standby

The Contractor makes provision is made for a standby crew in the event of plant failures outside of normal working hours.

The Standby team will report to Site within 1 hours of being called and attend to the Break down Situation.

The Contractor ensures that there is a 2nd call team available to ensure that the Standby persons do not exceed the legal limit on consecutive time worked and to attend to additional Emergency work in the event of the first call team being already engaged in breakdown work.

#### Standby Roster

The Contractor maintains and up-to-date standby roster and communicates all changes ans relevant list to Majuba Electrical Operator Desk EOD.

The Person on C&I standby will be responsible to be on site 4 hours before the light up of a unit.

This person will attend to all C&I problems experienced during the light up.

The expected action time is included as a KPI.

### Over Time

No planned Over Time will be paid on this contract only shift and standby or outage work because the objective of this contract is for the Contractor to provide a Comprehensive All inclusive Maintenance Service for Majuba Power Station Fuel Oil Plant.

### Modifications

Only approved modifications with the appropriate Drawings and documentation from the Service Manager will be allowed on the affected plant.

### Work Interface

The Mechanical Field is the Lead Discipline during plant Maintenance and the Contractor will coordinate work on the effected plant between all interfacing disciplines and other contractors and departments.

The Contractor will be responsible for Planning and coordinating and providing Permits for the following work performed by others.

- Engineering and Plant Specialists

- Civil works, Structural steelwork and Sheeting

- Repair of Plant Hoists, cranes and load beams

### Working Hours

The Contractor’s personnel including the Site manager and Supervisors will be on site during Eskom working hours as specified in 4.2.3 below.

### Spillages and leaks

The Prevention of Spillages is viewed to be very important for ensuring plant housekeeping and should be actioned as one of the top priorities.

Any leak must be attended to Immediately, It is acceptable that a Short term repair be instituted immediately and then a permanent repair be effected on a planned opportunity.

Any spillage caused as a direct result of the Contractor will be cleaned by the Contractor at Their Cost.

### House keeping

#### General Plant

The Contractor is to ensure that the Plant areas where work is to be performed is clean before and during the maintenance process.  Possible sources of contamination are to be addressed by the contractor Before Work Starts.

All materials, consumables and spares (new, used or damages) etc. are to be removed from the Plant and deposited in the appropriate areas.

These are unless otherwise directed by the Employer:

- All Spares whether Damaged, Repaired or New are to be Booked into the Majuba Store.

- Scrap steel is to be deposited in the allocated metals Bins at the Africa Store.

- Domestic waste is to be deposited in rubbish bins or a Domestic waste skip.

- Oil used or new is to be returned to the oil Store.

- Hazardous and contaminated Material or waste is to be deposited in the Skips provided for this purpose, usually at the Fuel oil offloading Station.

#### Work Shop

The allocated Work shop area is to be kept neat and managed according to good housekeeping practices.  Only Spares in transition between the Plant and the Stores when planned may be kept in the Area.  The Contractor must clean this Area on Inception of the Contract.

### Plant Criticality

The Fuel Oil Plant and Burners are classified as Critical Plant.  The Plant is required to be available at all times.  During High Load situations the redundant Plant is required to be in operation because the plant cannot always cope with the load.

#### Redundant Plant

Where redundant Plant Fails the Contractor will effect repairs immediately and this work will be supervised by a competent and Qualified Supervisor.

#### Major Plant Break Down

When there is a Major plant Break down that can result in a Load loss or put the Plant Fuel oil Supply at risk the Contractor will effect repairs immediately and the Contractor’s site manager will be on site coordinating the work.

In the event that Majuba Power Station site personnel (Eskom or others) need to be used to provide Supervision, the Contractor will be charged at the hourly cost to company rate for the Person doing the supervision to recover the costs incurred.

### Maintenance Planning

#### General Planning

The Employer requires that the Fuel Oil systems are maintained according to a defined maintenance programme developed by the Employer. With each and every system the planned maintenance activities are listed with periods at which stage the activity is to be carried out. The scope of work will focus on a specific plant area & equipment.

The Employer has a planning system called SAP PM, which records all corrective maintenance identified and all planned maintenance schedules.

All of the Employer’s documentation will be used in each and every activity performed on the respective plant with accurate information of the required actions undertaken to restore the plant back to working condition.

All work orders completed to be verified and approved by Contractors Supervisor and submitter to the Planning Department on the same day that the work is complete. All man-hours, staff used, material used, corrective or planned actions taken must be recorded on the corrective maintenance (CM) or planned maintenance (PM) documentation which is forwarded to the Planning Division for recording.

The Contractor will be responsible for planning and scheduling all Work being executed in the Affected Area. The Planning work will be done by competent and qualified Planners in line with the Employers Work Management principles, Including Scoping of Breakdown Work, the Writing of Standard Maintenance packages, Reserving Spares and returning Spares to the Store, Creating Purchase requisitions for Services and spares in Sap System.

The Contractor’s Site Manager, Supervisor, Planners and Artisans will be required to attend and Pass the Employer’s OMO training. Training Duration ranges from 2 to 14 days depending on the job description.

#### Qualification

The Planning personnel are to be Qualified as Per the Eskom Job Profile for a Planner/scheduler Gen 030109.

The Employer will provide the required SAP and Works Management training.

All scheduling activities will be undertaken by the Contractor’s planning schedulers - corrective maintenance is also catered for in the same way.

#### Plan Submission

Comprehensive plans will be submitted to the Service Manager or Delegated Supervisor.

Confirmation or commitment of resources is required on submission of the Plan.

Planning Resolution is to be at least 1 hour.

Plans to be updated in SAP and submitted with all required SAP fields populated.

### Spares Management

The Contractor will contribute to spares management by timelessly providing detail of the spares required to the contract supervisor as well as by assisting in identifying and cataloguing spares.

Cataloguing includes the completion and submission of the required from to make items stock.

The Contractor will also be required to verify the existence and correctness of spares and to perform quality checks on a regular basis.

The Contractor will also be required to perform preventative maintenance on the spares associated with the Service scope, including in this scope is rotating gearbox and pump shafts, replacing lubricants, performing internal inspections replacing Seals and gaskets and applying preservation material.

### Plant and plant equipment Alignment

The Contractor will perform all the Machine alignment required, including:

- All installed equipment but not limited to pumps motors etc. this is to include all alignment methods.

- The hire of all equipment will be at the contractor’s expense.

- Consumables will be for the Contractor’s account.

- Unless otherwise agreed upon the tolerance for all alignment will be 0.05 mm or less in all planes of alignment.

### Quality Control

Majuba Power Station reserves the right to do quality checks at any time.  It will be the philosophy of this contract that if a problem is identified while carrying out an inspection, a defect is raised to rectify the problem as corrective maintenance.

The Contractor is required to be certified in accordance to ISO9001.

#### QCPs

The Contractor is responsible for creating QCP documents and having them approved by the Service Manager.

The Contractor will ensure that all critical work will be performed using a Procedure and QCP.  Where no procedure exists the Contractor will write the procedure and have it approved by the Employer.

The Employer’s agent will witness the work and a results report (hardcopy) will be provided to the Employer and uploaded into the SAP system.

All specifications and actions stipulated within plant specific procedures shall be strictly adhered to with exception of any changes stated within the Service Information.  Further exceptions to the above procedures must be approved by the Service Manger before it may be implemented.

### Rigging Service related to the Execution of Work

The Contractor will perform all the rigging work required to execute the work and will ensure that the work is performed by competent and Qualified Personnel and that all work is executed safely and in accordance with Eskom Procedures and regulations.

The Contractor will be responsible for the training of rigging Personnel.

### Welding

All welding work done by the Contractor will be performed in accordance with Eskom Procedures, regulations and the Welding Rule Book 36-505 and 36-775.

The hot work Procedure will Apply as per 2.1.3 below.

The Contractor provides Welders and Boilermakers on an as needed basis.

### Strike Action

Majuba Power Station is a National Key Point and as such strike action and the associated intimidation and other activities associated with industrial action place the power station at risk.  The Contractor is to ensure that the contracted service is performed regardless of strike and industrial action.

The Contractor is to take all possible steps to ensure that strike action and the associated intimidation and other activities associated with industrial action do not take place on the premises of the Power Station.

The Contractor is required to provide an action plan for approval on how this situation is going to be mitigated.

### KPIs

The Employer uses KPI’s to determine the successful performance of the plant area.  The Contractor is required to perform maintenance in order to meet these targets.  The KPI’s are Subject to change on an Annual basis.  The Service Level Table in Section 5 Below contains Penalties that are Tied to theses KPI’s.

The Current KPI:

| Scheduled Compliance | More than 95% |
| --- | --- |
| PM compliance | More than 98% |
| Statutory work order violation | No violations |
| P1 work order not closed within 24 hours | Less than 1 outstanding |
| P2 work order not closed within 24 hours | Less than 3 outstanding |
| Safety Work orders not attended to within 24 hours | No violations |
| Work order back log | No more than 10 outstanding |
| Unit light up delay time | < 30 minutes |

### Plant Hazards

The Contractor will Conduct a Base line risk assessment and provide to the Service Manager and abide by Safe work procedures that mitigate each risk identified.

240-77471499 - Annexure A - Supplier Risk Category contains the possible hazards identified by the Employer.

Weather conditions are to be taken into account and the Contractor is to put measures in place to execute the work Regardless of weather conditions.

### Delegation of Contract roles

The Service Manger may in terms of NEC Claus14.2 Delegate Certain Planning and coordinating rolls to others.

### Procedures

In the event that an Eskom policies and Procedures should change, the Contractor is required to adopt the replaced or revised Procedure.

### Contract Conclusion

The Contractor Provides Safety File on conclusion of the contract to the Service Manager

The Safety fine contains Excite medical certificates for all employees associated with the contract including persons leaving employment of the Contractor before the end of the contract.

## The Contractor’s plan for the service

#### The Contractor shall provide an overall plan which stipulates how the provision of the services shall be facilitated in order to meet the Employer’s needs.  This will include the availability of competent staff and necessary equipment, team/s reporting to site within the stipulated time, meeting quality requirements, including defect correction and management of incompetency and ill-discipline.

#### For the duration of the Contract the Contractor will provide Comprehensive rolling programme which will contain duration, planned start dates and times for a specific type of activity.  This will be especially required where work will affect other activities on site, including during outages.  Such programme will be in the form of either a Microsoft Excel spread sheet with durations and resources stated for all the different activities/levels of work to be undertaken.  Programmes must be revised whenever necessary to contain relevant information.  The planning Information will be required to be updated in SAP by the Contractor’s Planners.

## Meetings

Meetings will be convened and chaired by the Service Manager as and when required, including the following:

Table 2.2:  Meeting Schedule

| Name | Frequency | Attendance by relevant Employer’s personnel: | Attendance by relevant Contractor’s personnel: |
| --- | --- | --- | --- |
| Contract kick-off | Once off | Service manager, Plant supervisor/manager and/or other necessary representatives. | Site manager, Site supervisor and/or other necessary representatives. |
| Early Warning | As and when notified by either party | Service manager and Plant supervisor/manager and other relevant personnel. | Site manager and Site supervisor/manager and other relevant personnel. |
| Technical and/or non- conformance | At least once every 3 months | Service manager, Plant supervisor and technical representative. | Site manager, Site supervisor and technical representative. |
| Safety Incidents | For each occurrence | Safety Representative, Service manager and Plant supervisor and others involved. | Safety Representative, Site manager and Site supervisor and others involved. |
| Section Meeting | Daily | Fuel Oil Plant Maintenance manager and supervisor, Engineer, and others involved. | Site manager, Site supervisors Safety Representative and planner. |
| Scope freeze meeting | weekly | Contract Supervisor, planning Supervisor | Planner, Site Supervisor |
| Planning meeting | weekly | Contract Supervisor, planning Supervisor | Planner, Site Supervisor |
| Prioritization meeting | Daily | Contract Supervisor, planning Supervisor, Production Manager and others involved | Planner, Site Supervisor |
| Contractor Safety meeting | Monthly | Fuel Oil Plant Maintenance Manager | Site manager, Site supervisors Safety Representative |
| Outage planning meeting | When Required | Service manager and supervisor, Engineer, and others involved. | Site manager, Site supervisors Safety Representative and planner. |

Additional ad-hoc meetings may be convened as required by either party.  All meetings on site shall be recorded using the Employer’s attendance register and minutes taken.  Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Contractor’s management, supervision and key people

Roles and responsibilities requirements for the contractor’s key people required to render the service:

| Designation | Safety Officer | Site Manager | Supervisor | C&I Mechanician | Electrical Artisan | Mechanical Fitter |
| --- | --- | --- | --- | --- | --- | --- |
| Number of | X1 | X 1 | X 1 | X 6 | X 2 | X 3 |
| Grading (Patterson Band Level) | T11 | M14 | T13 | T09 | T09 | T09 |
| Qualifications | Samtrec | NEC National Diploma (Technical) | National Diploma (Technical) | Grade 12 or N3 and trade test(NQF level equivalent) | •Grade 12 or N3 and trade test(NQF level equivalent) | Minimum of 3 years of Related Experience |
| Experience | Minimum of 1 years of Related Experience | Minimum of 3 years of Related Experience | Minimum of 3 years of Related Experience | Minimum of 3 years of Related Experience | Minimum of 2 years of Related Experience | Minimum of 2 years of Related Experience |
| Name: |  |  |  |  |  |  |
| Tel |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |
| Tel: |  |  |  |  |  |  |

#### The Employer and Contractor shall appoint a competent and trained Contract Manager / Employer’s Representative who shall manage all contract related matters and if necessary, may also manage technical issues.  Change of this person shall be communicated in writing within one week of such change to the other party.

#### The Contractor’s Site Manager is required to meet the minimum Qualification in Line with Gen 090211.

#### The Contractor’s site Manager will be available after hours telephonically.  Where the Site Representative is not available due to excessive hours worked, leave or Illness a Suitably qualified alternate must be made available.

#### The Contractor shall ensure that there is a competent supervisor for all site work to perform supervision duties.  The Supervisor/s shall be qualified and experienced in line with Eskom Job Description Gen 090211 and proof of this must be submitted within one week of the contract start date.

#### The Contractor shall ensure that his Supervisor/s become authorized as Authorised Supervisor/s (AS), in terms of the Eskom Plant Safety Regulations (PSR) within 2 Months of the contract start date and Authorised as a Responsible Person (RP) within 6 months of the contract start date.  This authorisation is obtained by attending a course which includes written evaluations (allow 10 days duration) and undergoing a verbal evaluation (1 to 2 hours) within three months after course results indicate that the Supervisor has passed.  As authorisations are valid for two years only, the Contractor must ensure that Supervisors are re-authorised before the authorisation lapses.  The necessary training and evaluations will be provided by Majuba free of charge and the Contractor’s Supervisors must be available to attend, when the course is scheduled.  If the Contractor’s Authorised Supervisor/s is not available on site, this implies that work may not be done and therefore Low Service Damages will be charged.

#### Additionally, the Supervisor/s must be able to communicate satisfactorily in English and have formal education as per Eskom Job description requirements.  If at any time, it is found that the Supervisors’ ability to either supervise the workers, practice good communication skills (verbal or written) or exercise competency is lacking, the Employer may give instruction for the removal of such person from site.

#### Qualified & Experienced mechanical artisans qualified according to Job Profile GEN 210211 and technicians qualified according to Job Profile PS Gen 286 assisted by semi-skilled workers will be responsible for all maintenance. They will be knowledgeable and understand hydraulic and, mechanical work.  These artisans must be competent and thus been able to do basic welding and manufacturing.

#### All key people undertaking work shall be appropriately trained, Qualified, Skilled and competent to perform such work and proof thereof must be submitted.  Incidence of poor quality work and non-adherence to site regulations and procedures will prompt the Employer to request the immediate and permanent removal of such person from all site activities.

#### Qualification and Qualified are to be interpreted according to the minimum requirement as per the Occupational Health and Safety Act, firstly and then Eskom’s “job profile” (listed under Section 6.2) for positions within the Contractor’s organizational structure and be supported by Eskom’s “Recruitment and selection procedure” Unique Identifier: 32-1023.

#### The Contractor is required to get the Service Manager’s Approval in writing before appointing any person on a position listed in 6.2 below.

## Documentation

### Correspondence

Correspondences shall be written formally on the letterhead format of the organisation and addressed to the relevant person.  Additionally, each correspondence shall be numbered uniquely in the following manner:

Employer to Contractor; EC, followed by a sequential three digit number e.g. EC001,

Contractor to Employer; CE followed by a sequential three digit number e.g. CE002

### Work packages

The Contractor shall provide Eskom with a completed quality control procedure (QCP) and work report / job card for each and every job undertaken and this must include technical specifications, findings, space for the client to sign off and comment and include any other relevant information required by the client.  The Contractor shall always have the approved safety file on site with all current and relevant documents.  Working without a safety file and QCP is not allowed on site and the Employer can claim delay damages if this occurs, as the Contractor will be sent off site and can only return once the required documentation is available and in order.

### Procedure, work packages, QCP, SMPs created during this contract

All Procedure, Work Packages, SMPs, QCPs and other when required check list will be provided to the Service manage when requested and will remain the property of the Employer.

A Complete copy of these documents must be returned to the Service manager on completion of the Contract.

### Other Documentation

All other documentation issued to the Contractor must be duly completed and returned to the Employer.

### Contract Conditions

The conditions of this Contract are to be taken as the Agreed term. NO other terms and conditions are to appear in the Contractor job cards, Quotations, invoices or any other standard documentation.

## Invoicing and payment

### Purchase order or Purchase requisition

A purchase order number shall be supplied to the Contractor prior to any work undertaken on site.  The Contractor’s supervisor shall ensure that a job card is correctly completed with all the relevant information including date, start time, completion time, waiting time (if applicable), plant description and KKS number, description of the work undertaken and spares/consumables used, including quantities thereof.  A signed copy shall be handed to the site representative to check, sign off and retain a copy.

### Emergency work

Where Emergency work is performed the Contractor shall within one week of the work being done, supply a quote, delivery note and/or a job card reflecting the tasks undertaken, plant description and KKS number and costs, as per the price schedule items. This is so that the Service Manager can create purchase orders.

### Assessments

The Employer will conduct an assessment of services provided between the 25th and 31st of every month.

### Tax Invoice

Within one week of receiving a payment certificate (contract assessment) from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Service Manager’s payment certificate.

Invoices are to be submitted as per the attached e-invoicing letter.

# Health and safety, the environment and quality assurance

## Health and Safety

The Contractor shall comply with the health and safety requirements that follow:

### Eskom Life Saving Rules

Five Life Saving Rules have been developed that will apply to all Eskom employees, agents, consultants and Contractors.

- Rule 1:	Open, Isolate, Test, Earth, Bond, And/Or Insulate before touch - that is any plant operating above 1000 V.

- Rule 2:	Hook up at heights - no person may work at height where there is a risk of falling.

- Rule 3:	Buckle up – no person may drive any vehicle on Eskom business and/or on Eskom premises: unless the driver and all passengers are wearing seat belts.

- Eskom takes a "ZERO TOLERANCE" attitude to drivers and passengers who do not wear safety belts when driving in any vehicle on Eskom Business and/or on Eskom premises.  The violation of this very important safety rule as well as any safety rule while performing work for or on behalf of Eskom may result in Eskom terminating your obligation to perform work in terms of your contract with Eskom.

- All occupants must wear their safety belts properly, and must never put the shoulder belt under their arm or behind their backs.  Drivers and all passengers must buckle-up at all times for the sake of themselves and their families.

- No Person may be on or within a Vehicle that is in any way in motion with our wearing a safety belt

- Rule 4:	Be sober -no person is allowed to work under the influence of drugs and alcohol.

- Rule 5:	Use a permit to work – where an authorization limitation exists, no person shall work without the required permit to work.

### Plant Safety Regulations

  - The Employer shall arrange the isolation of the plant from all sources of danger as described in the Plant Safety Regulations.  The Permit to Work shall be issued to the Responsible Person (RP) (site Maintenance staff/client) and be shown to the Contractor with the risk assessment, indicating which plant has been isolated and any special conditions applicable.

  - The RP Shall conduct a pre job Brief on the job site before the work commences.

  - The RP shall ensure that all of the Contractors workers sign in on the Worker’s Register in order to declare that they understand the work requirements and dangers.

  - The Employer shall, on request, make available a copy of the latest revision of the Plant Safety Regulations to the Contractor.

  - All work on plant is governed by the Plant Safety Regulations and Contractors must comply fully No permit to Work available implies that no work may be done.

  - The Contractor is to ensure that All Artisans are authorised in terms of PSR within 3 months on the Commencement of the contract.

    - NOTE: the contractor is requested to have at least 50% of RP’s available as soon as possible upon commencement of the contract.

  - Each of the Contractor’s teams performing work most have its own RP and Authorised Supervisor.

  - This contract includes for the PTW requirements for outside Contractors doing specialized work or upgrades/projects for the Fuel Oil Plant.  Continuous supervision of outside Contractors must be provided for and cost must be included in the monthly contract amount.

  - The Employer is to supply all their RP and AP persons with Arc flash suits as per the PC requirements.  These are to be supplied at the contractors cost.

    - One Suit per RP every 2 Years

### Fire Precautions

  - Any tampering with the Employer’s fire equipment is strictly forbidden.

  - All exit doors, fire escape routes, walkways, stairways and stair landings and access to electrical distribution boards must be kept free of obstruction and is not be used for work or storage at any time. Fire fighting equipment must remain accessible at all times.

  - In case of fire, report the location and extent of the fire to Electrical Operating Desk at 017 799 3803 and it is expected that the Contractor shall take the necessary action to safeguard the work area in order to prevent injury and spreading of fire.

  - All Hot Work on site must be done as per the Hot Work Procedure, SERV/FIRE02.

### Reporting of incidents

- The Employer follows an incident prevention policy which includes the investigation of all incidents involving personnel and property.  This is done with the intention of introducing control measures to prevent a recurrence of the same incident.  The Contractor is expected to co-operate fully to achieve this objective and have his own incident reporting system which is compatible to the site system.  The Employer's Representative (Plant Supervisor) and Service Manger must be informed immediately of all safety incidents including fatalities, medicals and first aids and near misses. Any damage to property or equipment must be reported to the Employer's Representative as soon as reasonably practicable but not later than 4 hours after the incident.  A Summary of the Incident is to be Submitted to the Employer’s Representative and Service Manger within 4 hours of the Incident.

- NOTE: The above-mentioned reporting does not relieve the Contractor of his legal obligation to report incidents to the Department of Labour, or to keep records in terms of the Occupational Health and Safety Act, and Compensation for Occupational Injuries and Diseases Act and to perform investigations of all incidents.

- The Contractor must provide the Safety Risk Officer with a monthly safety statistics report by the first working day of every month, even if no incidents have occurred.

### Vehicle Safety

  - Drivers, passengers and pedestrians must obey safety requirements in terms of the National Road Traffic Act, No 93 of 1996, as amended, including other relevant provincial or local requirements.

  - All drivers must possess a valid, national driver’s licence of the correct category/class, must not be under the influence of alcohol or other drugs which will impair the senses and must be authorised by the Contractor to drive the company vehicle.

  - All vehicles must be roadworthy and vehicle specifications must include at least front airbags for the driver and the front passenger and an anti-lock braking system (ABS).

  - All vehicles must be driven with due consideration for personnel and property. A maximum speed limit of 40 km/hour will be adhered to on the premises at all times.

  - Transportation of passengers on the back of open or closed light delivery vehicles (LDVs), trailers, trucks or any other form of transportation is not allowed.  It is a legal requirement for all Employers to provide safe transportation of all employees both on and off site.

  - No person may be transported in the back of vehicles closed by means of canopies, unless provided with factory-fitted or manufactured-approved, proper seating and safety belts, i.e. crew cabs.

  - Drivers and others entering Majuba Power Station will be subjected breathalyser testing.

  - The driver/s must ensure that their passengers are seated and wear seatbelts at all times.

  - Tools and equipment in vehicles must always be properly secured.

### Barricading / Screens and Scaffolding

- The Contractor shall be responsible to adequately barricade off of working areas and display warning signs to ensure that people and plant are not exposed to danger or to prevent access to work areas.

- The Employer will supply scaffolding and barricading if with at least 24 hour notice given.  Tampering, adjustment, moving or dismantling of any approved scaffold is not allowed – this may only be done by the scaffolding service provider.

### Health and Safety Arrangements

- The Contractor shall comply with the guidelines set out in the Eskom Standard  23-726 titled SHE REQUIREMENTS FOR ESKOM COMMERCIAL PROCESS, 32-136 titled CONTRACTOR HEALTH AND SAFETY REQUIREMENTS and 32-296 titled INTEGRATED SHE ORGANISATION; ROLES AND RESPONSIBILITIES AND STATUTORY APPOINTMENTS

- The Contractor must ensure that all his personnel attend a Health and Safety Induction Course prior to starting with the works.  A one hour course will be provided free of charge by the Employer and will be valid for the duration of one year.  It is the Contractor’s responsibility to make an appointment for the induction and ensure that re-induction is done timeously.

- Safety Risk Management has the right and authority to visit and inspect the Contractor’s workplace or site establishment to ensure that tools, machinery and equipment comply with the minimum safety requirements.

- The Employer's Representative shall be entitled to instruct the Contractor to stop work, without penalty to the Employer, where the Contractor’s personnel fail to conform to safety standards or contravene health and safety regulations.  The Employer's Representative is entitled to instruct the Contractor to discipline his employees, to enforce disciplinary action and to submit a report to the Employer's Representative.  The Contractor shall implement additional health and safety precautions wherever necessary.

- The following Health & Safety requirements should be complied with:

  - The Contractor is required to supply a Certificate of Competency for his/her employees if the work will be done under the following conditions:

    - Confined Spaces

    - Heights

    - Heat stresses

    - Cold stresses

  - The Contractor to provide the Employer with a signed register as proof of free issue of adequate Personal Protective Equipment (PPE) to be used by his/her employees (preferably SABS approved).  Additionally, the Contractor shall provide overalls for his staff with clearly identifying motifs depicting the company name.

  - Sub-contractors - the principal contractor must request approval for the use of any sub-contractor.  Proof must be given to Eskom that the sub-contractor/s have the necessary competence and resources to carry out the work safely and to ensure that due care of the environment will be exercised.

  - Medical certificate of fitness shall be issued by a Registered Occupational Health Medical Practitioner only.

- The Contractor appoints a person, qualified in accordance with the SHE Requirements, as the liaison with the Eskom Safety Officer for all matters related to health and safety and this person shall be contactable telephonically 24 hours a day.

- The Contractor confirms that it has been provided with sufficient written information regarding the health and safety arrangements and procedures applicable to the Services to ensure compliance with it and all employees, agents, Subcontractors or mandatories with the SHE Requirements while providing the Works in terms of this contract.  As such, the Contractor confirms that this contract and the relevant Eskom Regulations referred to in this contract constitute written arrangements and procedures between the Contractor and the Employer regarding health and safety for the purposes of section 37(2) of the OHSA.

### Company Branding

The Contractor shall provide all overalls (when needed) for his staff with clearly identifying motifs depicting the company name.

### Special requirements

The Contractor Allows for staffing based on a full running Station of Which some of the Unit may two Shift.  The Light up Requirement will vary depending on National electricity Demand.

The Contractor seeks Employees from the local Seme Districs as per “ANCYL PROTEST Majuba Actions “.

### Exposure to Silica

The Risk of exposure to Silica and coal dust is High

The Contractor is responsible for ensuring that ALL employees working in the Boiler Area wear appropriate SABS approved dust mask and that they are used correctly.

The Contractor is to ensure that Lung X-rays are performed on an annual basis and that the reports are issued by a Medical Doctor Qualified to recognise Silica related dust Lung ailments or Diseases.

The above reports must be submitted to the Employers Doctors for verification.

## Environmental constraints and management

All Legislative, Eskom and Majuba environmental policies are to be adhered to:

### Work carried out in terms of:

The Contractor will be required to ensure that all works are carried out as per the ISO 14001 standard and Majuba’s Environmental Policy, BIA/ENV/04 and Waste management Policy, BIA/ENV/01.  The following environmental requirements are complied with at all times:

  - Zero liquid effluent discharge.

  - No chemicals will be dumped into the station drains or on the premises.

  - No oil or waste will be dumped in an unauthorised area or unlicensed waste site.

  - Asbestos will be handled and stored according to Act 15 of 1973 (Hazardous Substances Act).

  - No materials or waste will be burnt on site.  Hazardous substances shall be handled and stored according to the hazardous substances Act no 15 of 1973.  No effluent shall be discharged into the public streams.

  - Contractors’ activities/ services shall be carried out as per the above procedures and BIA/RM/STD/01

### New Environmental Legislation

The Contractor will be responsible for complying with any new environmental requirements, relevant to the Services Information that may come into effect as part of Majuba Power Station’s Environmental Management System (EMS) during the duration of this contract.

### Existing Environmental Legislation

In order to protect Eskom's environmental interests whenever a product or service is provided by a Contractor, the Contractor complies with all relevant and appropriate environmental legal requirements contained in governmental notices, laws and regulations promulgated by the central and provincial governments.

### Liability

The Contractor also accepts all responsibilities, accountabilities and liabilities associated with such legal requirements, unless specifically excluded from a contract by a mutually acceptable written agreement.

### Hazardous substances

If product is classified as a hazardous substance, material safety data sheets (MSDS) must accompany delivery/use. In accordance with the Occupational Health and Safety Act (OHSA), Act 85 of 1993 section 10 and 11.  If any hazard is identified by the Contractor, he must immediately inform the Employer.

## Quality control and assurance requirements

The Contractor must possess an accredited Quality Management System.  A pre-approved Quality Control Plan (QCP) is to be used for the tasks at hand.

### Personal Competency

Proof of the Contractor’s personnel competency in terms of Regulation 18 (5 and 6) of the OHS Act is required by the Employer.

### Quality Requirements

The Contractor will additionally comply with the Employer’s Quality Requirements as specified in Standard QM58.  This includes the Contractor’s ISO 9001 Registration Certification of Compliance

### Quality Control Documents

All quality control documentation must be submitted to the Project Manager/ Employer's Representative/ Employer's Agent within two weeks after contract award for written approval.

## General Requirements

The Contractor to note and comply with the following:

### Direction and Instructions

The Contractor shall operate under the direction and instructions of the Employer or such appointed person/s who may give instruction without transgression of the contract, any legislation and regulations including the Occupational Health and Safety Act and the Generation Plant and Safety Regulations.

### Workmanship

The Contractor shall maintain a high standard of workmanship as expected by the Employer and shall comply with any quality assurance and quality procedures implemented by the Employer.

### Section 27(2)

Contracts shall include, in terms of Section 37(2) of the OHS Act an agreement to ensure compliance by the mandatory with the provisions of the Act.

### Non-Compliance

The non-compliance of the Contractor in terms of safety and quality requirements is claimable as Low Services Damages by the Employer.  It is the Contractor’s responsibility to clarify all requirements and ensure that compliance is maintained during the contract period.

### Labour Laws

The Contractor shall comply with all local and statutory labour laws (LRA, BCEA UIF etc) and agreements and shall promptly attend to any labour grievances that may arise.  The Contractor shall not remunerate employees at less than the proclaimed statutory wage (Minimum Wages Act).  Failure in this regard will result in non-performance and therefore immediate termination of the contract.

# Procurement

## Subcontracting

The Contractor may not use a Subcontractor unless a written request is made to the Employer and approval is given.  All terms and conditions applicable to the Contractor, will also apply to the approved Subcontractors e.g. legal requirements, appointments, authorisations, safety, quality and therefore all relevant documentation must be submitted in order for the Employer to consider the Subcontractor for approval.

Additionally, the prices listed in the price list will remain unchanged if any Subcontractors are used.

## Plant and Materials

### Correction of defects

All defects to be repaired within the same day.

### Plant & Materials provided “free issue” by the Employer

Scaffolding, forklifts and/or cranes will be provided without cost to the Contractor upon the Contractor’s request, if available at the time.  These may only be installed/operated by persons who have authorisation to do so.

The Contractor will at his cost ensure that his employees are authorised for the use of all lifting equipment including folk lifts, hoists, cranes, and that all Artisans are trained and Authorised to do basic rigging.

The Employer will provide the Spares and Materials required for maintaining the Plant.

# Working on the Affected Property

Whilst working on site the Contractor will adhere to all Eskom and Majuba Power Station site regulations.

## Employer’s site entry and security control, permits, and site regulations

The Contractor shall prepare and submit the safety plan and other documents in a file within one week of the contract start date and which shall be corrected if necessary to be approved within one week thereafter.  Safety induction is provided subject to the safety file being approved by one of the Safety Risk Officers of Majuba Power Station and thereafter, the file must always be available when work is done on site.

Access to site is dependent on the all workers undergoing a short (1 hour) safety induction and then only will access permits be issued for workers and construction vehicles to enter.  Work will not be allowed without induction provided by the Employer for each and every worker.

Medical certificates of workers can only be issued by Occupational Health Practitioners and includes hearing, sight and lung-function tests and may include psychological evaluations for workers who work at heights and/or any other requirement stipulated by the Safety Risk Officers.

See BIA/RM/STD/01 for all relevant details or contact the Safety Risk Officers at 017 799 3121

or 017 799 3445.

### Security and Access Arrangements

- The Contractor may apply for a temporary or permanent photo permit (if on site for longer than two months) as well as vehicle permits at the Security office, after completing induction.

- The following information is required for permits to be approved (temporary permit forms will be provided by the Safety Risk Officer conducting the safety induction):

- Employee name and ID Number

- Company

- Contract validity date

- Employer's Representative signature

- Copy of the first page of the ID book of each employee

- The Contractor’s personnel will be required to be in possession of their access permit at all times and will produce them at the security gate on every occasion or whenever requested.  All Contractors’ permits must be returned to Protective Services when the relevant personnel leave the site permanently and upon Completion of the services.  Any lost photo permits will be paid for by the Contractor.

- The Contractor’s visitors and all personnel shall conform at all times, to the security arrangements in force at the time.  Application forms for visitors must be completed by the Contractor’s Site Manager and approved by the Employer's Representative at least one day before the visit and submitted to the Protective Services office.  Visitors will not be allowed on site if the necessary forms are not in the possession of security staff.

- Protective Services may with valid cause, remove any of the Contractor’s personnel from the site, either temporarily or permanently.  Access may be denied to site to any person, whom in the opinion of Protective Services, constitutes a security risk. No compensation is claimable by the Contractor if this occurs.

- No unauthorised vehicles will be allowed on site.  Only Contractor’s vehicles with contract vehicle permit disks will be allowed on site.  Contract Vehicle Permit Applications should be directed to the Employer's Representative.

- The Contractor will be restricted to the working areas associated with his place of work.  The Contractor is forbidden to enter any other area, and must ensure that his employees abide by these regulations.

- Parking inside the Power Station buildings or in front of driveways, doors and gates is strictly forbidden, except for loading purposes.

- No recruiting of casual labour may be done on the Employer’s premises, including the area outside the Power Station security gate.

## People restrictions, hours of work, conduct and records

### Only authorised persons may have site access and perform work.

### Majuba Power Station normal working hours are:

- Monday to Thursday – 07:30 to 16:45

- Friday – 07:30 to 12:30

The Contractor will however, provide the services during all hours.

### Working Hours

As per the Labour Regulations Act and the Basic Conditions of Employment Act, no person is allowed to work more than 12 continuous hours per shift.  The Contractor shall ensure that workers are relieved from duty after working twelve hours.

### Removal from Site

The Employer reserves the right to have any of the Contractor’s personnel removed off site if, in the Employer’s opinion, it is warranted.

## Health and safety facilities on the Affected Property

There is a medical station on site and a fire and rescue service for assistance with serious incidents and treatment of all serious injuries during normal working hours.  Emergency services are available during normal working hours by dialling 9222 from any site phone or else 017 799 2138 (medical centre) 017 799 3192 (fire and rescue) and also available after hours by dialling 9222 from any site phone or else contacting the Electrical Operating Desk (EOD) at 017 799 3803 (all hours).  However, the Contractor is expected to handle all minor incidents in-house by providing a first aider and a first aid kit.

## Cooperating with and obtaining acceptance of Others

Proper co-ordination and work planning must be done when working in any area where others are performing work or activities.  Interfacing may be required with the site maintenance personnel and others.

## Records of Contractor’s Equipment

The Contractor will bring a typed list of all his equipment and tools (with serial numbers, wherever possible).  This list needs to be approved by the Security office before the items are taken onto site on each occasion. Equipment that is not listed on a tool/equipment list cannot be removed from site.  Equipment and vehicles left on site is done so at the Contractor’s own risk.

## Equipment provided by the Employer

Scaffolding can be supplied after notification and call-out of the relevant scaffolding service provider.  Other equipment such as forklift and cranes may be supplied upon request and if available at the time on site.

Rigging Equipment, lights, hand tools and other equipment will not be provided by the Employer and The Contractor is to conduct his operation is such a way as to make lending of tools from the Employer or other contractors on Site unnecessary.

### General

All equipment, tools, transport and consumables for performing the services are to be supplied by the Contractor.  The Contractor’s tools and equipment must be on a planned maintenance schedule and must be inspected before dispatched to Majuba Power Station.

The Contractor shall maintain a calibration and inspection schedule for all measuring equipment used and shall make the Schedule and results available to the Employer upon request.

Access to site with equipment and tools will only be granted upon the submission of a printed tool/equipment list to the security department.  Any items not on the list and brought onto site, may not be removed from site thereafter.

The Contractor will maintain his equipment in a serviceable condition and comply with legal requirements regarding testing and maintenance of equipment.  The Contractor presents the Maintenance and inspection schedule to the Service manager on a 6 monthly basis.

### Rigging

The Contractor will provide all rigging equipment, for performing the services  All the Contractor’s equipment must be serviceable and on a planned maintenance schedule and must be inspected each time before being used on the Plant.  All the Contractor’s Rigging equipment must comply with the Relevant Legal requirements.

The Employer will provide the following Equipment Required to Maintain the Plant:

- Flatbed Truck

- 25 ton Crane

- 100 Ton Jacks and power Pack

- Fork Lift Truck

## Site services and facilities

### Provided by the Employer

Sanitary services, water, compressed air and electricity shall be provided by Eskom at fixed points on the plant.  There is also a site kitchen which serves lunch only and meal tickets may be purchased at the Petty Cash Office in the Finance Building.  Furthermore there is also a tuck-shop on site but both of these operate only on week days and are for the Contractor’s own cost.

### Provided by the Contractor

The Contractor is to supply all the personal protective equipment, transport, accommodation, tools, equipment and consumables to perform all the required tasks on site.

### Contractor’s yard

The Contractor is to establish a Site yard in the location indicated by the Employer.  Permission will be granted once the Contractor provides an accepted layout plan. Expected site yard size 40 by 40 meters.

The Contractor will be responsible for supplying all the required buildings including separate venues for eating ablution and office work, etc.

The Contractor will ensure that all the required services are connected and that the relevant building codes and by laws are adhered to.

Site Establishment will only be assessed for payment once a Certificate of Compliance issued by a duly Authorised person is provided to the Service Manager.

## Control of noise, dust, water and waste

### Waste Disposal

Waste is to be disposed of in bins supplied by Eskom – yellow bins for general waste and red bins for hazardous waste.  However, the Contractor is expected to remove all his own waste from site, as far as possible.

### Noise

Noisy equipment and tools emitting noise more than 105dB (A) may not be supplied/utilised by the supplier.

## Tests and inspections

The site maintenance staff or Quality Control personnel shall inspect the Contractor’s work and sign off all relevant documentation, if the work is satisfactory.  Thereafter, plant shall be test run and the Contractor informed of any defects.  The Contractor may be present for any test running.

# Service Level Table

The following table depicts the level of performance required of the Contractor.  Should the Contractor be unable to meet these requirements, Low Service Damages will be claimed from the Contractor.

The total Low Service Damages will be limited to 10% per month.

Table 6:  Service Level Table for Low Service Damages

| No. | Description | Employer’s Requirement | Damages payable by Contractor |
| --- | --- | --- | --- |
| 1 | Approval of safety file | 2 weeks Before Contract Commences | R500.00 per day without approved safety file. |
| 2 | Approval of Quality Management System | Within 2 weeks of contract start date. | R500.00 per day without approved quality file. |
| 3 | Authorisation of Supervisors | Within 2 months of contract start date. | R750.00 per day without an Authorised Supervisor. |
| 4 | Authorisation of Artisans | Within 3 Months of contract start date. | R750.00 per day without an Authorised Artisan. |
| 5 | Arrival on site for call-out | Within 1 hours of call-out. | R1,000.00 per hour of delay or part thereof. |
| 6 | Non Attendance of meetings | Every listed meeting to be attended | R500.00 per incident. |
| 7 | Excessive Task Duration | Within the time specified by Contractor’s plan as approved By the Service Manager. | R500.00 per hour of extended Duration or 10% of the monthly contract value whichever value is lower |
| 8 | Scheduled Compliance | More than 95% | 1% of monthly contract value |
| 9 | PM compliance | More than 98% | 1% of monthly contract value |
| 10 | Statutory work order violation | No violations | 5% of monthly contract value |
| 11 | P1 work order not closed within 24 hours | Less than 1 outstanding | R1000 for each one per month |
| 12 | P2 work order not closed within 24 hours | Less than 3 outstanding | R1000 for each one per month |
| 13 | Safety Work orders not attended to within 24 hours | No violations | 1% of monthly contract value |
| 14 | Work order back log | No more than 60 outstanding | R100 for each outstanding |
| 15 | Major break downs not identified and actioned | All failure that put the plant or redundant plant at risk must be prevented | 1% of monthly contract value |
| 16 | Planning information not submitted as required | Work executed without Approved Plan | 1% of monthly contract value |
| 17 | Work Not Executed as Planned | Work committed By the contractor not executed | R250 per Job per day of not complying up to 10% of the monthly contract value. |
| 17 | Plant Failure after returning from Maintenance work and rework | No Delays when returning plant to service or rework | R500.00 per hour of extended Duration or 10% of the monthly contract value whichever value is lower |
| 18 | Standby team arrive to site late on callout | Standby team to start with repair work within 1.5 hours of being called | R1000 per Hour or 10% of the monthly contract value whichever value is lower |
| 19 | Reaction to Breakdowns | Permit must be requested within 30 minutes and be correct. | R500.00 per hour of delay in requesting permit 10% of the monthly contract value whichever value is lower |
| 20 | Maintenance crew on work site in time | Maintenance crews to be on the job within 30 minutes of permit issue. With all the correct tools. | R500.00 per hour of delay in team being on site, 10% of the monthly contract value whichever value is lower |
| 21 | Supervision | No Supervision and Management during high Risk break downs | As per Major Plant Break Down in 1.3.above. limited to 10% of the contract value |
| 22 | Spares Requirements | Spares and Materials not requested at least 2 moths before being required | R500.00 per day or 10% of the monthly contract value whichever value is lower |
| 23 | Safety File not Submitter for Monthly Audit on time | Safety File must be Submitted Monthly to the Employers Safety Department For Audit. | 5% of Monthly Contract Value. |
| 24 | COID and SARS Letter of Good Standing | Letters not Provided to the Service Manager before the previous year expires | 15% of Monthly contract Value. |
| 25 | Exit Medical | All excite medical certificates not included in the Safety File | Final contract payment. |

# List of Documents

## Drawings issued by the Employer

The following drawing will be issued to the appointed Contractor.

| Drawing number | Revision | Title |
| --- | --- | --- |

## Relevant Documents

The following Employer documents are relevant for this contract.

| Drawing number | Revision | Title |
| --- | --- | --- |
| 32-727 | - | SHEQ Policy |
| RA/RM/STD/01 |  | SHE Specification for Contractors Rev 1 |
| MAJ/187 | 0 | S.H.E. PLAN CHECKLIST |
| 37.2 Agreement |  | SECTION 37(2) AGREEMENT |
|  |  | APPOINTMENT OF THE PRINCIPAL CONTRACTOR |
| 240- 77471499 |  | Annexure A SUPPLIER RISK CATAGORY |
| 240- 77471499 |  | Annexure B ACKNOWLEDGEMENT FORM FOR ESKOM SHE RULES AND OTHER REQUIREMENTS |
| 240-77471969 |  | Annexure C 2: SHE Tender Evaluation and Scoring Card |
| 240-77472561 |  | Annexure D 1 : SHE Post-contract Reviews |
| 240-77471651 |  | Annexure C 1 (1) : SHE Tender Evaluation and Scoring Card |
| 32-1034 | - | ESKOM PROCUREMENT AND SUPPLY CHAIN MANAGEMENT PROCEDURE |
| 23-726 | - | SHE REQUIREMENTS FOR ESKOM COMMERCIAL PROCESS |
| BRIEFING NOTE 23-726 |  | SHE REQUIREMENTS FOR ESKOM COMMERCIAL PROCESS |
| 32-136 | - | CONTRACTOR HEALTH AND SAFETY REQUIREMENTS |
| 32-296 | - | INTEGRATED SHE ORGANISATION; ROLES AND RESPONSIBILITIES AND STATUTORY APPOINTMENTS |
| 240-62196227 | - | LIFE-SAVING RULES |
| 32-418 | - | WORKING AT HEIGHTS |
| 32-345 | - | ESKOM VEHICLE SAFETY SPECIFICATIONS |
| QM-58 |  | SUPPLIER CONTRACT QUALITY REQUIREMENTS SPECIFICATION |
| Gen 030109 |  | JOB PROFILE: PLANNER WORK MANAGEMENT |
| GEN 090211 |  | JOB PROFILE: SUPERVISOR |
| Gen 220211 |  | JOB PROFILE: ARTISAN RIGGER |
| GEN 210211 |  | JOB PROFILE: ARTISAN FITTER |
| Gen 180211 |  | JOB PROFILE: ARTISAN CODED WELDING |
| PS Gen 286 |  | JOB PROFILE: MECHANICAL TECHNICIAN/ ENGINEERING ASSISTANT |
| 36-505 | 1 | WELDING RULE BOOK: Personnel and Entities Performing Welding Related Special Processes on Eskom Plant |
| 36-775 | 1 | WELDING RULE BOOK: Control of Plant Construction Repair and Maintenance Welding Activities |
| APPENDIX Ai |  |  |
| APPENDIX Aii |  | SAMPLE MAINTENANCE PLANNED TASK LIST |
| APPENDIX B |  |  |
| APPENDIX B1 |  |  |
| APPENDIX C |  | SAMPLE UNIT OUTAGE SCOPE |
|  |  | ANCYL PROTEST Majuba Actions |