TERMS OF REFERENCE:

KIMBERLEY DIAMOND CUP ACTION SPORTS PROJECT & EVENT MANAGEMENT SERVICES

TENDER NO. DEDaT 0004/1/2022

ELIGIBILITY:	Event management service providers with verifiable experience in managing mega action sports events and build-up programmes to promote tourism and support economic development for the benefit of Northern Cape communities.

DUTY STATION:	Kimberley – Project Management Office, Khaya la Bantu Building, 2 Cecil Sussman Street, Kimberley 8301 South Africa.

CONTRACT PERIOD:	3 years

REPORTING TO:	Chief Director: Tourism.

APPOINTED BY:	Department of Economic Development and Tourism, Northern Cape.

NB: TWO ENVELOPE SYSTEM

Envelope 1:	Technical proposal with ALL supporting documents

Envelope 2:	Financial proposal

The bidder must submit four (4) copies of the original technical proposal at the closing date and time.

- TABLE OF CONTENTS

1.	BACKGROUND	4

2.	COLLABORATIVE PARTNERSHIPS AND RELATIONSHIPS	4

3.	PROJECT RATIONALE	5

4.	RATIONALE FOR PROJECT CONTENT STRUCTURING	6

5.	SCOPE OF WORK	6

6.	REQUIRED KEY COMPETENCIES	19

7.	PROPOSAL REQUIREMENTS	20

8.	REQUEST FOR BID TERMS AND CONDITIONS	20

9.	REQUEST FOR BID REQUIREMENTS	21

10.	INDEMNITY	23

11.	TRANSFER AND CESSION	23

12.	BREACH AND TERMINATION	23

13.	COMPULSORY BID CRITERIA	23

14.	SUB-CONTRACT	24

15.	SERVICE LEVEL AGREEMENT	24

16.	GOVERNING LAW	24

17.	TENDER DEFAULTERS AND RESTRICTED SUPPLIERS	24

18.	FRONTING	24

19.	EVALUATION CRITERIA	25

20.	CONTRACTUAL AGREEMENT	29

21.	REPORT	30

22.	MONITORING AND EVALUATION	30

23.	SUPPLIER DUE DILIGENCE	30

24.	SUBMISSION OF BID	30

Table

Table 1. KDC Major Open Competition - Male	9

Table 2. KDC Major Open Competition - Female	9

Table 3. KDC Major Amateur - Male	10

Table 4. KDC Major Amateur - Female	10

Table 5. KDC Grand Slam - Male	12

Table 6. KDC Grand Slam - Female	12

Table 7. KDC Grand Slam Amateur - Male	13

Table 8. KDC Grand Slam Amateur - Female	13

Table 9. KDC SFH - Male	14

Table 10. KDC SFH - Female	14

Table 11. KDC SFH final - Male	15

Table 12. KDC SFH final - Female	15

Table 13. Project Management	16

Table 14. Cost Table	18

Table 15. Standard Bidding Documents	22

Table 16. The evaluation processes	25

Table 17. Functionality criteria	25

Table 18. Proven experience	26

Table 19. Positive working capital	26

Table 20. Public interest score	27

Table 21. Human Resource	27

Table 22. Evaluation criteria for proof of municipal account	27

Table 23. Evaluation criteria for official functioning office in Northern Cape	28

Table 24. Proof of verifiable clients within Northern Cape	28

Table 25. Methodology	28

Table 26 Specific Goals Evaluation	29

# BACKGROUND

The department of Economic Development and Tourism (DEDAT) in the Northern Cape will appoint a service provider with suitable experience and sufficient own financial resources to deliver the Kimberley Diamond Cup (KDC) action sport project on behalf of the department.

The KDC is a respected action sport brand that belongs to DEDaT. The seat of this brand is at the Kimberley Skate Plaza in Kimberley, the capital city of the Northern Cape. The KDC brand is also closely associated with four mini skate parks, all located in the provincial regional commercial centres – Kuruman, De Aar, Springbok, Upington. The KDC action sports project must make use of all 5 skate parks to ensure that the project maintains a province wide presence and to ensure widely distributed economic opportunities.

The KDC action sport project will consist of several Skateboarding for Hope events (for provincial skaters), grand slam events (open events staged in the major commercial centres of South Africa and not restricted to skateboarding only) and a major action sport championship event presented at the Kimberley Skate Plaza in Kimberley. It is the desire of the department to have international athletes compete in the KDC major action sport championship event.

The KDC action sport project has as its key objectives the following –

  - Employment creation (permanent and temporary employment opportunities).

  - Enterprise beneficiation (as service providers & vendors at events).

  - Destination positioning and promotion, especially as adventure sport destination.

  - To attract tourists to the provincial skate parks.

  - Skate Park management (all 5 skate parks).

  - Social investment for the benefit of the youth (life skills programme, sport development, mentorship).

DEDAT owns all the trademarks and designs of logos and other product identity assets associated with the KDC. The successful service provider will be afforded the right to use such for purposes of delivering the project.

# COLLABORATIVE PARTNERSHIPS AND RELATIONSHIPS

The project working relationships that are key to the successful presentation of the Kimberley Diamond Cup action sport project are the following:

  - The Department of Economic Development and Tourism.

  - The Northern Cape Tourism Authority.

  - The Northern Cape Economic Development, Trade, and Investment Promotion Agency.

  - Northern Cape Youth Development Agency.

  - Local Chambers of Commerce.

  - The Department of Public Works and Roads.

  - The Department of Sport, Arts and Culture.

  - The Department of Social Development.

  - The Office of the Premier of the Northern Cape.

  - The Sol Plaatje Municipality.

  - The Frances Baard District Municipality.

  - South African Police Services.

  - The National Department of Tourism.

  - South African Tourism.

  - Skateboarding Association of South Africa.

  - Service providers to the Kimberley Diamond Cup, especially the local small enterprises.

  - And other relevant stakeholders as identified from time to time.

  - Service Providers to the Kimberley Diamond Cup, especially the local small enterprises;

  - And other relevant stakeholders as identified from time to time

# PROJECT RATIONALE

The project rationale is to achieve the following -

  - To create a minimum of 150 employment opportunities per contract year, 8 of them to be permanent for the duration of the contract period - in support of the government Expanded Public Works Programme for the duration of the contract period. Such employment opportunity creation shall be in all 5 provincial districts and benefit mostly the youth, women and people with disability that are unemployed or under-employed.

  - To maximise economic opportunities for Northern Cape-based SMMEs – both as service providers and as event vendors - especially where it relates to event management, service providing tents, grand stands, stage, sound, fencing, plumbing, electrical, security, promotional materials, vendoring, transport, crafts, fashion, entertainment, tour operating, travel agencies, photography, videography, catering, food, and beverage supplies and any other equipment required for purposes of the project. This will also necessitate regional spread in the use of SMMEs especially in the location of the 4 mini skate parks.

  - To create trade opportunities for provincial fashion designers, crafters, and musical performing acts.

  - To promote awareness of the Northern Cape as action sport and adventure destination.

  - To increase tourist arrival numbers to the Northern Cape and especially where the provincial skate park is located.

  - To manage, promote and maintain the Kimberley Skate Plaza as a top-rated action sport destination in South Africa.

  - To manage and promote the mini skate parks in the province to increase their popularity and frequency of use.

  - To create community benefits through a social investment programme to be implemented and managed by the project service provider. Such a programme will include youth entrepreneurial skills development related to the action sports environment (training workshops, mentorships, internships), as well as a life skills programme at the Kimberley Skate Plaza in Kimberley to contribute to community well-being, youth discipline and positioning skateboarding and action sports as a positive alternative lifestyle.

  - To create and enhance local tourism culture where the skate parks are located.

  - To build prosperous relationships with project sponsors and stakeholders as a contribution to the

growth and sustainability of the KDC action sport project.

# RATIONALE FOR PROJECT CONTENT STRUCTURING

  - KIMBERLEY SKATE PARK

The Kimberley Skate Park is one of the biggest skate parks in South Africa. Its association with the KDC brand ensured that the skate park remains an action sport destination and such status must be maintained and promoted by the appointed service provider. Opportunities to promote the Kimberley Skate Park as Olympic qualifier facility or training venue for Olympic hopefuls must be exploited.

  - SKATEBOARDING FOR HOPE

The essence of the Skateboarding for Hope (SFH) events is to popularize skateboarding as sport and alternative but positive lifestyle. With this format the aim is to constantly draw more skaters, especially women skaters, to the sport. This means that skate clinics are an important component of the event and to enable the new skaters to skate regularly by providing good quality entry level skateboards as giveaway.

  - KDC GRAND SLAMS

The essence of the KDC Grand Slam action sport events is to recruit the best action sport athletes (e.g., skateboarders, BMXers) in South Africa to qualify for participating in the KDC major action sport championship. At the same time, it is a valuable platform to promote the Northern Cape as action sport and adventure tourism destination. The KDC Grand Slam events are premium, well branded, and highly visible action sport events and must contribute to further promote and strengthen the KDC brand and credibility.

  - KDC MAJOR ACTION SPORT CHAMPIONSHIP

The KDC major action sport championship is the biggest and most spectacle-filled action sport event in South Africa. As such the event must attract not only the best action sport athletes from South Africa and the rest of Africa or any other country but also attract scores of tourists to the Northern Cape and Kimberley. Winners in the different categories of action sport presented as part of the KDC major action sport championship should be regarded as the South African champion for a respective year.

The KDC major action sport championship must also offer action sport demonstrations (e.g., Free Motocross) to drive the popularity of the championship event and contribute to excitement and publicity of the event.

# SCOPE OF WORK

  - EMPLOYMENT CREATION

    - The appointed project service provider for the KDC action sport project shall create a minimum of 150 employment opportunities per year for each of the project contract years. Most of such employment opportunities must be reserved for residents of the Northern Cape.

    - Temporary employment opportunities must be created at all 5 of the mini skate parks.

    - Preference will be given to youth, women, and people with disabilities.

    - The temporary employment component of the KDC action sport project shall be done as a registered Expanded Public Works Project (EPWP) and will be done in keeping with the general guidelines of EPWP projects including guidelines for wages and record keeping.

    - The appointed KDC action sport project service provider will be responsible for employee management, workplans, remuneration of appointed staff and adhere to applicable labour relations and human resource management requirements.

  - SKATE PARK MANAGEMENT AT KIMBERLEY SKATE PLAZA

    - To appoint a Facility Manager and support staff to oversee daily operations and safe functioning of the facility, to ensure that the facility is open to the public during the advertised business hours, provide first aid by a qualified first aid staff member and to support and promote the skate park programmes and events on KDC social media platforms.

    - To ensure that the Skate Plaza is an alcohol, drugs, smoke, and gun free facility.

    - To keep an attendance register for skaters.

    - To keep a register of loaner skateboards issued and returned.

    - To develop a monthly programme of action sports which is to include at least one competition with prizes for winners per month. Such monthly programmes must be published on KDC social media platforms and poster to be placed at each of the 5 skate parks.

    - To present a life skills development and entrepreneurial development programmes as per the annual project schedule.

    - To provide free coaching lessons for skaters and promote awareness of the opportunity.

    - To keep a record of prize winners, what prizes they won and the value of each prize won.

    - To maintain KDC social media platforms (Facebook, Instagram, Twitter, TikTok) and website and ensure that the department is the main administrator and key controller of such platforms.

    - To regularly post updates on action sport activities at the 5 skate parks to maintain interest

in the KDC social media platforms and website.

    - To accommodate a local SMMEs to sell snacks and drinks to skaters and fans at all 5 skate

parks. The service provider must keep a record of such vendors and include photos of the vendoring on the KDC social media platforms and website.

    - To provide cleaning services – waste management, housekeeping, terrain neatness, weed

control.

    - To manage assets – infrastructure (civil, electrical), sound system, computers, cameras,

furniture, shipping containers and content, branding material, loaner skateboards and any other

assets at the Kimberley Skate Park and mini skate parks.

    - To produce monthly progress reports reflecting on activities and other data collected – visiting

skaters, visiting fans, competitions presented, prize winners, jobs created, skaters coached, skills developed, SMMEs used, maintenance needs, social media use, photographic portfolio, incidents e.g., injuries and security breaches and the following month’s programme. Data must also reflect number of youth (under 35), women and disabled.

    - To attend monthly project progress reporting meetings with DEDaT.

  - SKATE PARK MANAGEMENT AT MINI SKATE PARKS

    - To appoint a Facility Manager in consultation with the District Structures, to oversee daily operations and safe functioning of the facility, to provide first aid as a qualified first aid staff member and to support and promote the skate park programmes and events on KDC social media platforms.

    - To ensure that the Skate Plaza is an alcohol, drugs, smoke, and gun free facility during programmes.

    - To keep an attendance register for skaters.

    - To keep a register of loaner skateboards issued and returned, where applicable

    - To develop a monthly programme of action sports which is to include at least one competition with prizes for winners per month. Such monthly programmes must be published on KDC social media platforms and poster to be placed at each of the 5 skate parks.

    - To present a life skills development and entrepreneurial development programmes as per the annual project schedule.

    - To provide free coaching lessons for skaters and promote awareness of the opportunity

    - To keep a record of prize winners, what prizes they won and the value of each prize won.

    - To regularly post updates on action sport activities at the mini skate parks to maintain interest in the KDC social media platforms and website.

    - To accommodate a local SMMEs to sell snacks and drinks to skaters and fans at all 5 skate

parks. The service provider must keep a record of such vendors and include photos of the vendoring on the KDC social media platforms and website.

    - To keep the skate park clean and ensure waste removal.

    - To manage assets – sound system, computers, cameras, furniture, branding material, loaner 	skateboards and any other assets at the mini skate parks.

    - To produce monthly progress reports reflecting on activities and other data collected – visiting 	skaters, visiting fans, competitions presented, prize winners, jobs created, skaters coached,

skills developed, SMMEs used, maintenance needs, social media use, photographic portfolio, incidents e.g., injuries and security breaches and the following month’s programme. Data must also reflect number of youth (under 35), women and disabled.

  - EVENT MANAGEMENT OF KDC MAJOR ACTION SPORT CHAMPIONSHIP

    - To design and present a world class action sports festival that attracts 65 of South Africa and Africa’s best action sport athletes, with 60 South Africa and 5 from Africa, while showcasing other action sports in demonstration format.

    - To ensure widespread awareness and marketing of the KDC major action sport championship to drive higher visitor numbers and tourism to the Northern Cape and Kimberley.

    - To create opportunities for Northern Cape SMMEs as service providers and vendors. This will include the establishment of a SMME village as opportunity to sell food, beverages, art, craft and fashion produced by Northern Cape entrepreneurs.

    - To present an entertainment programme – concert for the KDC action sport championship event and in the SMME village. The concert for the KDCS major action sport championship must include local and national artists while the SMME village stage is for local performers only.

    - To present an official welcome function for athletes, sponsors and invited guests, the evening before the start of the KDC major action sport championship

    - Identify and utilize Northern Cape-based SMMEs to design and produce the trophies for winners as well as a range of summer and winter clothing suitable for the action sports world.

    - To provide accredited commentators and judges and provide travel arrangement and accommodation.

    - To award trophies and prizes for championship winners in each of the championship formats.

    - Capture and provide live streaming of the event via Facebook and other cost-effective opportunities.

    - Create and sell Corporate Hospitality packages.

    - Allow for ten (10) wild card entries to participate in the respective action sport disciplines. Such 	wild card entries will be the prerogative of the department.

    - Fund all travel costs related to qualifying athletes

    - To take care of all event logistics supplies (tents, grand stands, stage, sound, lighting, fencing,

plumbing, electrician, security, cleaning, promotional material, printing, production of branding materials, food, and beverage).

    - To produce a detailed report on the KDC major action sport championship demonstrating what

transpired and to provide event data in relation to demonstrate the economic impact of the event.

    - The KDC major action sport championship will have the following championship categories 	included for each of the championship action sport disciplines –

- KDC Major Open for males and females.

- KDC Major Open Best Trick for males and females.

- KDC Major Amateur for males and females (under 16).

- KDC Major Amateur Best trick for males and females (under 16).

    - The KDC Major Open competition prize purse per action sport discipline will be as follows:

Table 1. KDC Major Open Competition - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 35 000 |
| 2 | R 25 000 |
| 3 | R 15 000 |
| 4 | R 3000 |
| 5 | R 2000 |
| Best Trick | R 10 000 |

Table 2. KDC Major Open Competition - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 20 000 |
| 2 | R 15 000 |
| 3 | R 10 000 |
| 4 | R 3000 |
| 5 | R 2000 |
| Best Trick | R 5 000 |

    - The KDC Major Amateur competition prize purse per action sport discipline will be as follows:

Table 3. KDC Major Amateur - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 15 000 |
| 2 | R 10 000 |
| 3 | R 7 500 |
| 4 | R 1 000 |
| 5 | R 500 |
| Best Trick | R 5 000 |

Table 4. KDC Major Amateur - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 10 000 |
| 2 | R 7 500 |
| 3 | R 5 000 |
| 4 | R 1 000 |
| 5 | R 500 |
| Best Trick | R 3 000 |

    - Event logistics related to the KDC major action sport championship must, as a minimum include the following (but not limited to):

      - To prepare the Kimberley Skate Plaza to be fully ready to present the skateboarding competition. This will include cleaning inside and outside the park, painting of facility, servicing the electrical infrastructure including high mast floodlights, plumbing, and preparing village area.

      - To ensure approvals to present a mass event including certification of infrastructure according to the relevant regulations.

      - To provide office facilities for event organisers – air-conditioned containers.

      - To provide grand stands for four thousand (4 000)

      - To provide an air-conditioned hospitality tent for athletes– 65 people (60 South African and 5 African)

      - To provide an air-conditioned hospitality tent for sponsors and invited guests – 50 people.

      - To provide catering services to skater and sponsor tents.

      - To provide a tent for qualified paramedical team on standby.

      - To provide an air-conditioned tent for media with work stations and electrical plug points.

      - To provide flooring for tents and hospitality areas outside of tents.

      - To provide flooring for open spaces inside the skate park for dust control and

aesthetical purposes.

      - To provide DJs for skater tent.

      - To provide furniture for tents.

      - To provide Physiotherapists for skater tent.

      - To provide Medical Emergency Services to be on stand-by during skateboarding

championships and to treat any medical emergencies of fans and KDC staff.

      - To ensure technical people on standby, e.g., electricians, plumbers, engineers, fire-

prevention.

      - To provide sound for live comment and announcements.

      - To provide branding of skate area.

      - To provide additional lighting where needed.

      - To provide large high quality outdoor daylight screens for televising the championship

to fans.

      - To provide infrastructure for television cameras to film event (e.g. camera towers).

      - To provide mobile toilets sufficient to service four thousand (4 000) people.

      - To provide security fencing for skate and other areas.

      - To prepare and manage the parking area (including banner branding of parking area

and security).

      - To ensure that an approved full risk and disaster management plan is available and

ready for implementation.

    - To create an SMME village are to accommodate the following –

      - To provide mini concert stage for Northern Cape-based artists to perform in the SMME Village area.

      - To provide a minimum of 20 gazebo trading areas with electrical points for vendors.

      - To provide a small skate area for fans.

      - To provide mobile toilets to serve 500 people.

      - To provide a closed off beer tent with air-conditioning, furniture, seating for 200 people.

      - To provide security fencing.

      - To provide manned security services for 24 hours of the day during build-up, duration of the event and break-down phase.

      - To recruit vendors in consultation with DEDaT for selling of skate apparel, equipment, arts, crafts, fashion, food, and drink.

  - EVENT MANAGEMENT FOR KDC GRAND SLAMS

The KDC Grand Slam events must be staged in peak season or when other events are in the selected location to enhance the prospect of attracting more visitors to the Grand Slam events.

    - To design and present a premium action sports event that attracts the best action sport athletes vying to qualify for participation in the KDC major action sport championship. KDC Grand Slams will be presented in consultation with the department at a suitable skate park as follows: –

      - Central South Africa (Northern Cape / Free State),

      - Gauteng,

      - KwaZulu-Natal,

      - Western Cape and

      - Eastern Cape.

    - To ensure widespread awareness and marketing of the KDC Grand Slam events to drive higher visitor numbers and tourism to the event location and to promote the Northern Cape as action sport destination.

    - To create opportunities for local SMMEs as service providers and vendors.

    - To provide accredited commentators and judges and provide travel arrangement and accommodation.

    - To award trophies and prizes for championship winners in each of the   championship formats.

    - Capture and provide live streaming of the event via Facebook and other cost-effective opportunities.

    - To take care of all event logistics supplies (tents, grand stands, stage, sound, lighting, fencing, plumbing, electrician, security, cleaning, promotional material, printing, production of branding materials, food, and beverage).

    - To produce a detailed report on each of the KDC Grand Slam events demonstrating what transpired and to provide event data in relation to demonstrate the economic impact of the event.

    - The KDC Grand Slam action sport championship will have the following championship categories included for each of the championship action sport disciplines –

- KDC Grand Slam for males and females.

- KDC Grand Slam Best Trick for males and females.

- KDC Grand Slam Amateur for males and females (under 16).

- KDC Grand Slam Amateur Best trick for males and females (under 16).

    - The KDC Grand Slam Open competition prize purse per action sport discipline will be as

follows (note that First, Second and Third placings will have their travel costs (transport, accommodation, meals) to and from Kimberley paid as part of the prize purse) –

Table 5. KDC Grand Slam - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 15 000 |
| 2 | R 10 000 |
| 3 | R 7 500 |
| 4 | R 1 000 |
| 5 | R 500 |
| Best Trick | R 5 000 |

Table 6. KDC Grand Slam - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 10 000 |
| 2 | R 7 500 |
| 3 | R 5 000 |
| 4 | R 1 000 |
| 5 | R 500 |
| Best Trick | R 3 000 |

    - The KDC Grand Slam Amateur competition prize purse per action sport discipline will be as

follows –

Table 7. KDC Grand Slam Amateur - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 7 500 |
| 2 | R 5 000 |
| 3 | R 3 000 |
| 4 | R 1 000 |
| 5 | R 500 |
| Best Trick | R 2 000 |

Table 8. KDC Grand Slam Amateur - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 5 000 |
| 2 | R 3 000 |
| 3 | R 2 000 |
| 4 | R 500 |
| 5 | R 300 |
| Best Trick | R 1 000 |

  - EVENT MANAGEMENT FOR KDC SKATEBOARDING FOR HOPE

    - To design and present a low-cost action sports event that attracts wannabe and beginner skaters to popularize the sport of skateboarding and participate in a competition to select qualifiers for the SFH final to be presented at the Kimberley Skate Plaza. Such events (six in total) will be presented at the skate parks in Kimberley, De Aar, Kuruman, Springbok, Upington with a final to crown the SFH champion in Kimberley.

    - To present a skate clinic to coach wannabe and beginner skaters how to skate best.

    - To give away ten (10) good quality entry level skateboards per event to the best of the clinic participants at all six events.

    - To ensure widespread awareness and marketing of the KDC Skateboarding for Hope events to drive higher number of wannabe and beginner skaters to the events.

    - To create opportunities for local SMMEs as service providers and vendors.

    - To provide coaches, a commentator and judges and provide for their travel arrangements (transport, meals, accommodation).

    - To provide the three best placings per qualifier event with transport, accommodation, and meals to attend the SFH finals in Kimberley.

    - To award trophies and prizes for championship winners in each of the championship formats.

    - To take care of all event logistics supplies (tents, security, cleaning, production of branding materials, food, and beverage for athletes).

    - To produce a detailed report on each of the KDC SFH events demonstrating what transpired

and to provide event data in relation to demonstrate the economic impact of the event.

    - The KDC SFH competition prize purse for qualifier events will be as follows (note that First, 	Second and Third placings will have their travel costs (transport, accommodation, meals) to

and from Kimberley paid as part of the prize purse) –

Table 9. KDC SFH - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 2 000 |
| 2 | R 1 500 |
| 3 | R 1 000 |
| 4 | R 500 |
| 5 | R 300 |
| Best Trick | R 500 |

Table 10. KDC SFH - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 1 500 |
| 2 | R 1 000 |
| 3 | R 500 |
| 4 | R 300 |
| 5 | R 200 |
| Best Trick | R 300 |

The KDC SFH final competition prize purse will be as follows –

Table 11. KDC SFH final - Male

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 5 000 |
| 2 | R 3 000 |
| 3 | R 2 000 |
| 4 | R 750 |
| 5 | R 500 |
| Best Trick | R 1 500 |

Table 12. KDC SFH final - Female

| PLACING | AMOUNT IN SOUTH AFRICAN RAND |
| --- | --- |
| 1 | R 3 000 |
| 2 | R 2 000 |
| 3 | R 1 000 |
| 4 | R 500 |
| 5 | R 300 |
| Best Trick | R 1 000 |

  - PROJECT MANAGEMENT

    - To implement the annual project implementation plan in consultation with DEDaT and the NCTA and adhere to the agreed milestones and timelines to be met.

    - To establish and coordinate a project steering committee and ensuring that all meetings are recorded and minute.

    - To take responsibility for all logistics related to sittings for project steering committee meetings.

    - To prepare and submit monthly project progress and oversight reports in writing and as per template provided, together with a portfolio of photographic evidence.

    - To prepare and do presentations of the monthly reports.

    - To be available for meetings as scheduled and as requested by DEDaT.

    - To submit accurate invoices after reaching pre-determined milestones (all payments will be in line with achieving the set milestones to the satisfaction of DEDaT and NCTA and payments will not be made if milestones are not achieved).

    - Prepare and produce an annual project report as per template provided.

    - General project management requirements

      - To develop an annual project implementation plan in consultation with DEDaT and the NCTA. The project implementation plan will include basic operational detail on the (1) management of the Kimberley Skate Plaza programme – daily management (security, attendance registers – skaters, cleaning, asset management, vendor management, brand management), maintenance checks, village management, skateboarding competitions, entrepreneurial development initiatives, life skills development initiatives,  (2) presenting of the KDC championship events – annual event schedule, event presentation (venue preparations, vendor management, attendance registers, skate competitions, fan engagement, prize presentation, entertainment -  fashion show, DJs, bands, dancers, singers, sponsor management); (3) project sponsor management; (4) project meeting schedule; (5) project progress reporting schedule; and (6) payment milestone schedule.

      - To ensure that all KDC signature events are accredited by a South African body for the advancement of the skateboarders and skateboarding.

      - To produce an electronic copy (PDF format) presentation of the project implementation plan for distribution to project stakeholders, sponsors and prospective sponsors.

      - To produce a detailed annual project close-out report (PDF format) and presentation for distribution to project stakeholders and sponsors / prospective sponsors.

      - To provide a highly detailed costing in accordance with each section of the project scope in the following format –

Table 13. Project Management

| ITEM | QUANTITY | UNIT COST (Incl. VAT) | TOTAL COST (Incl. VAT) |
| --- | --- | --- | --- |
| Athletes accommodation (65 People) | 4 |  |  |
| Flights/Bus Tickets | 2 |  |  |
| Commentators | 4 |  |  |
| Accredited judges | 5 |  |  |
| Northern Cape artist | 1 |  |  |
| National Artist | 1 |  |  |
| Stage and Audio-Visual Equipment | 1 |  |  |
| Grandstand seating for 4 000 people | 3 |  |  |
| Musical Concert (For at least 4 000 people) | 1 |  |  |
| VIP Tent (50 People) | 1 |  |  |
| VIP Catering (10 People) | 1 |  |  |
| Skaters Catering | 1 |  |  |
| Audio Visual equipment for live streaming | 1 |  |  |
| Security and fencing for 4 000 people | 1 |  |  |
| Paramedics | 1 |  |  |

  - MARKETING AND PUBLIC RELATIONS

    - The appointed service provider must design and implement an annual project marketing and public relations plan in consultation with DEDaT and the NCTA to promote awareness of all KDC events and programmes presented at the 5 provincial skate parks, annual event and the Grand Slams and to popularize such.

    - To generate content for KDC website, Facebook, Instagram, Twitter, TikTok and management of these platforms as well as share it with the NCTA for inclusion on their social media and marketing platforms.

    - To ensure that the championship events are broadcasted live on KDC Facebook and other platforms that are available.

    - To accommodate provincial community radio stations at the KDC major action sport championship in Kimberley.

    - To cooperate and consult with NCTA on marketing, media, and public relations programme implementation to ensure as wide as possible coverage of the events and promotion of the destination.

    - To produce a 3-minute-long high-definition vignette to showcase the Northern Cape as action sport destination to assist with persuading prospective project sponsors and to publish on KDC social media platforms and website.

  - SPONSORSHIPS

    - To engage in sponsorship activation at a commission rate of 10% on cash sponsors only. No commission will be payable on goods sponsorships / sponsorship in kind.

    - To manage sponsors and prospective sponsors and to ensure that contractual agreements with such sponsors are implemented as agreed.

    - Any cash sponsorships attracted may be used to increase the size and scope of the KDC events.

  - ATHLETE MANAGEMENT

    - To support the top provincial action sport athletes to attend KDC Grand Slam events and

deserving beginner skaters to attend the SFH events by providing transport, accommodation, and meals.

    - To endeavour to have the KDC major championship be accredited as an Olympic qualifier

event.

    - It is also important for the KDC extreme sporting events to be accredited by the specific South

African body that advances the specific sporting code. The same goes for using accredited judges. This is critically important to ensure that KDC events are regarded as credible competitions and to ensure that the provincial athletes improve their positions on the respective ranking systems.

  - LOCAL ECONOMIC BENEFICIATION

    - To present a mentorship and skills development programme for the youth entrepreneurs.

    - To ensure local service providers, SMMEs, crafters, fashion designers, DJs and performing acts

benefit significantly from opportunities inherent to presenting the KDC programme.

    - To cooperate with Small Business Development programme (DEDAT).

    - To cooperate with Sol Plaatje Municipality LED Unit.

    - To cooperate with the local taxi association.

    - To procure event logistics from Northern Cape-based suppliers (tents, grand stands, stage and

sound, fencing, security, promotional materials to name a few). If any goods or services are not available within the Northern Cape these need to be highlighted in your Bid document

    - To appoint Northern Cape-based food and beverage suppliers.

    - To attract Northern Cape craft suppliers.

    - To attract Northern Cape fashion designers as suppliers.

    - To present an entertainment programme (DJs and performing acts).

    - To appoint photography and videography suppliers.

    - To appoint tour operators to provide half day tours of Kimberley.

    - To appoint transport suppliers.

    - To utilize Northern Cape-based travel agencies.

Table 14. Cost Table

| ITEM | QUANTITY | UNIT COST (Incl. VAT) | TOTAL COST (Incl. VAT) |
| --- | --- | --- | --- |
| Accredited Judge | 2 |  |  |
| VIP Tent and furniture (20 People) | 1 |  |  |
| VIP Catering (20 People) | 1 |  |  |
| Skater Catering (15 People) | 1 |  |  |
| Toilets VIP | 1 |  |  |
| Toilets | 2 |  |  |
| Sound System | 1 |  |  |
| Paramedic | 1 |  |  |
| Athletes’ accommodation | 15 |  |  |
| Transport Mini-Bus Kombi | 1 |  |  |
| Photographer | 1 |  |  |
| ITEM | QUANTITY | UNIT COST (Incl. VAT) | TOTAL COST (Incl. VAT) |
| Sound System | 1 |  |  |
| Accredited Judges | 3 |  |  |
| VIP Tent and furniture (Number of People) | 1 |  |  |
| VIP Catering (20 People) | 1 |  |  |
| Skaters Catering (15 People) | 1 |  |  |
| Skaters Hospitality Tent | 1 |  |  |
| Mobile toilets (if required) | 4 |  |  |
| Security and fencing (200 People) | 1 |  |  |
| Mobile toilets (Only if the venue does not have toilet facilities) | 1 |  |  |
| Paramedics | 1 |  |  |
| Transport (15 skaters Kimberley) | 1 |  |  |
| Photographer | 1 |  |  |
| Transport & Accommodation for athletes & judges (17 People) | 1 |  |  |
| Live Streaming | 1 |  |  |
| Hiring of venue -Skatepark | 1 |  |  |
| Crew and Athletes Accommodation (Number of Crew members and Athletes) | 1 |  |  |

# REQUIRED KEY COMPETENCIES

The minimum required competencies are the following:

  - Proven event management experience, especially in successfully leading large and complex projects.

  - Proven experience of an ability to coordinate and communicate effectively with a widely dispersed project stakeholder group.

  - Proven experience in team management, resolving conflict management situations and effective problem-solving skills.

  - Experience in developing marketing strategies and implementing marketing plans.

  - Proven experience in event / project management reporting and communication skills

  - Proven experience in computer and technical event / project management skills.

  - Experience in working with international projects States-based companies, would be an added advantage.

  - Experience in small enterprise promotion would be an added advantage.

  - Experience in managing large projects on behalf of government would be an added advantage.

  - Experience in skills development and team capacity building would be an added advantage.

# PROPOSAL REQUIREMENTS

The service provider must clearly outline the following:

  - Project management methodology

  - Project management experience, also where it relates to events management (Company)

  - Project management and leadership competencies(team)

  - Fees and disbursement requirements as per annexure (costing)

  - Referrals of past clients.

  - Be willing to make a presentation in Kimberley to NCPG.

  - Financial capability

  - Identified presence or office within the northern cape

# REQUEST FOR BID TERMS AND CONDITIONS

The following guidelines are provided to assist a Bidder in completing a response:

  - The bid should be written in simple English for easy understanding and perusal.

  - Over and above all conditions stipulated by the Provincial Supply Chain Management, Bidders are advised to familiarize themselves with the following policy document:

    - PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000, (ACT NO.5 OF 2000) and the

    - PREFERENTIAL PROCUREMENT REGULATIONS, 2022. (PPPFA,2022)

  - The terms and conditions specified in this bid must be read in conjunction with the PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000, (ACT NO.5 OF 2000) and the PREFERENTIAL PROCUREMENT REGULATIONS, 2022 obtainable at http://www.parliament.gov.za and which forms an integral part of this bid. Prospective service providers will be well advised to also familiarize themselves with the contents of the Act.

  - All costs incurred in the preparation and presentation of the bid shall be wholly absorbed by the Bidder.

  - All information, supporting materials and other documentation submitted with the bid will become the property of the Northern Cape Department of Economic Development and Tourism (NC-DEDaT).

  - All prices must be South Africa Rand (ZAR), including VAT. All prices must be valid for a period of 120 days from date of submission.

  - NC-DEDaT shall not be liable for any costs incurred by the Bidder in the preparation of response to this Request For Bid. The preparation of response will be made without obligation to acquire any of the items included in the Bidder’s proposal or to select any proposal, or to discuss the reasons why such Bidder’s or any other proposal was accepted or rejected.

  - All invoices shall only become payable after service has been delivered and within 30 days upon receipt of an invoice by NC-DEDaT.

  - No interest shall be payable in the event of a dispute nor accrue on any payments due during a period of dispute.

  - Responses received after the specified due date and time will not be accepted under any

circumstances.

  - The lowest or only bid would not necessarily have to be accepted by the NC-DEDaT and as

such, the NC-DEDaT reserves the right to accept any or no bid at all.

  - The NC-DEDaT reserves the right to enter into negotiations with Bidders (who have been short-

listed) under the conventions embodied in the principles of “Best And Final Offer” (BAFO).

  - Instructions to the Bidder on what needs to be included in the bid and indicating the failure to

which non-compliance will be dealt with as well as how any dispute or grievances are to be dealt with are indicated in the bid documents. The terms of the general condition of contract (GCC) forms the general basis of the contract which will be further espoused in the special condition of contract (SCC) in the form of a service level agreement (SLA).

  - The Department will become the owner of all information. Documents, programmes, advice

and reports collected and compiled by the service provider in the execution of this tender.

  - The copyright of all documents, programmes and report must be regarded as confidential and

may not be made available to any unauthorized person or institution without the written consent of the Department.

  - The Department reserves the right to terminate this appointment or temporarily defer the work,

or any part thereof, at any stage of completion should the Department decide not to proceed with the tender.

  - The service provider must be a single legal entity with all other necessary expertise secured via

sub-contractor under a joint venture arrangement. The Department will enter into a single contract with a single entity for the delivery of the work set out in this tender.

  - The bidding entity shall be the same entity that will execute the bid. Any bid found to be

fronting for another entity or entities shall be disqualified immediately.

  - Bidders may ask for clarification on these tender documents or any part thereof up to close of

business 1 (one) week before the deadline for the submission of the bids.

  - Bidders may not contact the Department on any matter pertaining to their bid from the time

when the bids are submitted to the time the contract is awarded. Any effort by the bidder to influence bid evaluation, bid comparison or bid award decisions in any manner, may result in rejection of the bid concerned.

  - After the closure of the bid the Supply Chain Management Unit (SCM) will open the proposal

and draft a long list of all responsive service providers. Thereafter service providers who are non-responsive and do not meet the stipulated functionality evaluation criteria per the terms of this bid will be disqualified.

  - At any time prior to the deadline for submission of bids, the department may for any reason

whether at its own initiative or in response to a clarification requested by a service provider, modify the tender document. The Department may, at its discretion extend the deadline for submission of bids by amending the bid documents.

  - No bid may be withdrawn in the interval between the deadline for submission of bids and the

expiration of the validity period.

# REQUEST FOR BID REQUIREMENTS

The following will be the minimum requirements that must be disclosed in the bid/proposal:

  - General background.

  - The name and contact details (telephone and/or mobile, fax, email, and postal address) of the project leader (on the front cover of the proposal).

  - Particulars of project team members who will be involved in the project on an on-going basis (including qualifications and experience –CV’s to be included)) and a breakdown of race, gender, and disability.

  - The name of company, business addresses and contact details.

  - Overview of the organisation’s capabilities and experience, i.e., Credentials How long have you been in business?

  - What is your company’s core business, and how long has this been your core business?

  - What is the total complement of your staff, and what is the statistical breakdown in terms of gender and previously disadvantaged individuals?

  - What is the complement of your management and technical staff, and what is the numerical breakdown in terms of gender and previously disadvantaged individuals?

  - Provide details of clients who make use of products and services similar to the ones you offer in this bid, including names, contact persons and the nature of the services.

  - Any other additional information to strengthen your bid/proposal will be considered.

  - The taxes of the successful Bidder must be in order, or satisfactory arrangements must have

been made with the Receiver of Revenue to meet his/her tax obligations. This information must be clearly updated on the CSD.

  - In bids where Consortia / Joint Ventures / Sub-contractors are involved, each party must have

a separate Tax Clearance Certificate, SBD 3.1, 4, 6.1 and a combined BBBEE certificate. International companies are to make arrangements with South African Revenue Services for a Tax Clearance certificate

  - In the event of a consortium, details of roles and responsibilities of each party are to be provided

and the overall management structure of the consortium and business model thereof must be submitted with the bid.

  - The Standard bidding documents to be completed SBD 3.1, 4, and 6.1 must be completed in

full and the signed declaration forms must be attached to the bid.

Table 15. Standard Bidding Documents

| SBD 2 | Tax Clearance certificate requirements as reflected on CSD. Need not submit |
| --- | --- |
| SBD 3.1 | Pricing schedule – firm prices |
| SBD 4 | Declaration of interest |
| SBD 6.1 | Preference points claim |

  - MANDATORY REQUIREMENTS

    - Registration on Central Supplier Database (CSD)

All prospective bidders must be registered as a service provider on the Centralized Supplier Database. If you are not registered proceed to complete the registration of your company prior to submitting your proposal. Refer to https://secure.csd.gov.za/ to register your company. Ensure that all documentation on the database is updated and valid Attach a copy of the CSD registration “Summary Report” to your bid.

    - Valid and original tax clearance certificate

The validity of the tax clearance certificate issued by the South African revenue services certifying that the taxes of the Bidder are in order will be verified against the information recorded in the Central Supplier Database (CSD).

# INDEMNITY

The Northern Cape Department of Economic Development and Tourism shall not be liable for any injury, loss or damage to the preferred bidder’s employees, equipment, or vehicles whilst on the premises during the contract period.

# TRANSFER AND CESSION

The successful bidder shall render the service as required.  The successful bidder shall not cede, transfer, sell or alienate in any way this contract awarded in terms of Bid DEDaT 0004/1/2022 or any part thereof to any person or company.

# BREACH AND TERMINATION

Should either party commit or breach the provisions of this contract and fail to remedy that breach (es) within 14 (fourteen) days after the receipt of a written complaint, the party that is not in default shall be entitled to cancel this contract per written notice delivered to the other party’s domiccilium et executandi as per bid documents without prejudice to any other right which the non-defaulting party may have as a result of such breach.

# COMPULSORY BID CRITERIA

The following bid criteria will apply for pre-qualification which is compulsory and must be fully complied with.

  - Must be registered on the Centralised Supplier Database System (CSD). Service providers not registered must do so before submitting their proposal. Submit proof of registration on the Central Supplier Database. The tax matters of the bidder must be compliant and in good standing. It must reflect on the CSD. In a case where arrangements have been made with SARS to comply, the proof must be submitted.

  - It is a requirement that bidders must comply with Broad Based Black Economic Empowerment Act by submitting BBBEE certificate to meet our procurement objective criteria as indicated in the terms of reference. In bids where Consortia / Joint Ventures / are submitted a combined BBBEE certificate must be submitted.

  - All SBD documents (3.1,4, and 6.1) indicated in this tender must be completed, signed, and submitted. (As issued).

  - All bids must be submitted on the official forms.

  - This bid is subject to the general conditions of the bid, the special conditions of the bid, the General Conditions of Contract (GCC) and, if applicable, any other special conditions of contract. A Service Level Agreement will be signed upon appointment to administer the contract.

  - The Department reserve the right to terminate the tender or its process or not to appoint any service provider.

  - All prices must be in South African Rand

  - All prices are inclusive of VAT.

  - The bid validity period is 120 days. In exceptional cases, the Department may solicit the Bidder’s consent to extend the validity period.

  - No bid may be withdrawn in the interval between the deadlines of submission and appointment.

  - Submission of bids and expiration of period of bid validity specified by the bidder on the invitation to the bid form.

  - No interest will be payable in the event of a dispute accruing on any payment due during a period of dispute.

  - Bidders should ensure that bids are delivered in time to the correct address. If the bid is late, it shall not be accepted.

# SUB-CONTRACT

A person awarded a contract may not sub-contract more than 30% of the value of the contract to any other enterprise that does not have an equal or higher BBBEE status Level than the person concerned, unless the contract is sub-contracted to an Exempted Micro Enterprise (EME) that has the capability and ability to execute the contract. This request for proposal is prepared in accordance with the Public Finance Management Act, 1999 and its regulation and relevant procurement legislation.

# SERVICE LEVEL AGREEMENT

The Service Level Agreement (SLA) will enforce the General and Special Conditions of the Bid and the General conditions of Contract (GCC). The requirements/conditions of the SLA are non-negotiable and must be always adhered to. Failure to adhere will necessitate a consequence management in regards to non-performance. Insufficient materials or the lack thereof will be purchased by the Department and deducted from the service provider’s payment.

# GOVERNING LAW

South African law governs this bid and the bid response process. The bidder agrees to submit to the exclusive jurisdiction of the South African courts in any dispute of any kind that may arise out of or in connection with the subject matter of this bid, the bid itself and all processes associated with the bid. This agreement is binding upon submitting your bid.

# TENDER DEFAULTERS AND RESTRICTED SUPPLIERS

No tender shall be awarded to a bidder whose name (or any of its members, directors, partners, or trustees) appear on the Register of Tender Defaulters kept by National Treasury, or who have been placed on National Treasury List of Restricted Suppliers. The DEDaT reserves the right to withdraw an award, or cancel a contract concluded with a bidder should it be established at any time that the bidder has been blacklisted with National Treasury or by another government institution.

# FRONTING

Government supports the spirit of broad based black economic empowerment and recognizes that it can only be achieved through individuals and businesses conducting themselves in accordance with the constitution and in an honest, fair, equitable, transparent, and legally compliant manner. Against this background the Department of Economic Development and Tourism condemn any form of fronting

The government in ensuring that Bidders conduct themselves in an honest manner will as part of the bid evaluation processes, conduct, or initiate the necessary/investigations to determine the accuracy of the representation made in the bid documents. Should any of the fronting indicators as contained in the guidelines on complex structures and transactions and fronting, issued by the Department of Trade and Industry, be established during such enquiry/investigation, the onus will be on the Bidder/contractor to prove that fronting does not exist. Failure to do so within a period of 14 days from date of notification may invalidate the bid/contract and may also result in the restriction of the Bidder/contractor to conduct business with the public sector for a period not exceeding ten years, in addition to any other remedies the Department of Economic Development and Tourism may have against the Bidder/contractor concerned.

# EVALUATION CRITERIA

Table 16. The evaluation processes

| Phase I Mandatory requirements | Phase II Functionality | Phase III Recommendation and appointment |
| --- | --- | --- |
| Compliance to mandatory bid requirement | Bids will be evaluated in terms of functionality (Failure to comply will invalidate the bid). | Recommendation from the evaluation and adjudication for appointment. |

The functionality assessment involves evaluating the capabilities and abilities of the service provider to undertake the contract. The technical proposal must be separated from the financial proposal but both envelopes must be submitted at the same time.

  - PREQUALIFICATION

    - Phase I: Mandatory Requirements

The appointment of the successful Bidders will be based on the mandatory compliance as prequalification. During this phase Bidder’s response will be evaluated based on the mandatory requirements indicated hereunder. This phase is not scored and Bidders who fail to comply with all mandatory criteria will be disqualified.

      - Registration on central supplier database (CSD)

The service provider must be registered as a service provider on the Centralized Supplier Database. If you are not registered proceed to complete the registration of your company prior to submitting your proposal. Refer to https://secure.csd.gov.za/ to register your company. Ensure that all documentation on the database is updated and valid. Attach a copy of the CSD registration Report.

  - FUNCTIONALITY CRITERIA

Bidders must obtain at least 75% to qualify on functionality. Bidders who do not achieve the minimum of 75% will be disqualified. The Assessment will have a weight of 100 based on the criteria below.

Table 17. Functionality criteria

| TECHNICAL ASSESSMENT – 100 POINTS |  |  |  |
| --- | --- | --- | --- |
| CRITERIA | RATING | WEIGHT | TOTAL |
| - Proven experience in scope of work |  | 30 |  |
| - Financial capability |  |  |  |
| - Positive working capital (Cash flow) |  | 5 |  |
| - Financial reporting compliance |  | 5 |  |
| - Human Resource Capabilities |  | 10 |  |
| - Identified presence or office within the Northern cape |  |  |  |
| - Proof of municipal account (3months statement) of the business in Northern Cape. |  | 2 |  |
| - Proof of official functioning office of the business in Northern Cape on CSD. |  | 5 |  |
| c. Verifiable clients within the Northern cape |  | 3 |  |
| - Demonstration of methodology to achieve project scope |  | 40 |  |
| Total |  | 100 |  |

    - Proven experience in the scope of work or similar work done. Verifiable referrals and/or

Contract.

Table 18. Proven experience

| Criteria | Rating |
| --- | --- |
| O year | 0 |
| ≤1 year | 1 |
| 2 years | 2 |
| 3 years | 3 |
| 4 years | 4 |
| ≥5 years | 5 |

    - Financial Capability – Positive working capital (Cash flow)

      - Positive working capital (Cash flow)

Table 19. Positive working capital

| Criteria | Rating |
| --- | --- |
| R 0 | 0 |
| R 1-10 000 | 1 |
| R 10 001 – R30 000 | 2 |
| R 30 001 – R 500 000 | 3 |
| R 500 001 – R 1 000 000 | 4 |
| ≥ R1 million | 5 |

      - The bidder must submit compliance with public interest score regulation in terms of

financial reporting compliance.

Table 20. Public interest score

| Indicator | Rating |
| --- | --- |
| Non-Compliant | 0 |
| Compliant | 5 |

    - Human Resource

      - Organisational structure indicating number of employees.

      - The company must have a comprehensive Human Resource Policy and planning

      - Qualified employees

      - Proper service benefits

      - Proper code of practice

      - Proper training and development.

Table 21. Human Resource

| Criteria | Indicator | Rating |
| --- | --- | --- |
| 0 % | Did not meet the minimum requirements. Non compliance | 0 |
| 20 % | Satisfied one (1) requirement with major reservations. Considerable reservations of the supplier’s relevant ability, understanding, experience, skills, resource and quality measures required to provide the goods / services, with little or no supporting evidence. | 1 |
| 40 % | Satisfied two (2) of the requirements with major reservations. Some major reservations of the supplier’s relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services, with little or no supporting evidence. | 2 |
| 60 % | Satisfied three (3) of the requirements. Demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services, with supporting evidence with minor reservations. | 3 |
| 80 % | Satisfied four (4) of the requirements with minor additional benefits. Above average demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services. Response identifies factors that will offer potential added value, with supporting evidence. | 4 |
| 100% | Satisfied and exceeds five (5) of the requirements. Exceptional demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services. Response identifies factors that will offer potential added value, with supporting evidence. | 5 |

    - Identified presence or functioning office within the Northern Cape

- Proof of municipal account (3months statement) of the business in Northern Cape

Table 22. Evaluation criteria for proof of municipal account

| Indicator | Rating |
| --- | --- |
| Non-Compliant | 0 |
| Greater or equivalent to 3 months | 5 |

- Proof of official functioning office of the business in Northern Cape.

Table 23. Evaluation criteria for official functioning office in Northern Cape

| Indicator | Rating |
| --- | --- |
| Non-Compliant | 0 |
| Outside Kimberley | 2 |
| In Kimberley | 5 |

- Verifiable clients within the Northern Cape.

Table 24. Proof of verifiable clients within Northern Cape

| Indicator | Rating |
| --- | --- |
| Did not submit any client or contract or contact details. Non compliance | 0 |
| Submitted one (1) or more contracts with only one corresponding correct contact details. | 1 |
| Submitted two (2) or more contracts with only two corresponding correct contact details. | 2 |
| Submitted three (3) or more contracts with only three corresponding correct contact details. | 3 |
| Submitted four (4) or more contracts with only four corresponding correct contact details. | 4 |
| Submitted five (5) or more contracts with only five (5) corresponding correct contact details. | 5 |

    - Methodology

      - The proposal should be properly structured with a layout that is easy to understand and

follows a sequential flow of the scope of work.

      - Completeness of response to achieve project scope with an outlined project

methodology to cover: Risk management process i.e., risk assessment, mitigation strategies and business continuity

      - Mitigation plan for security risk or threats

      - Qualified project Manager

Table 25. Methodology

| Criteria | Description | Rating |
| --- | --- | --- |
| 0 % | Does not satisfy the minimum requirements. Non compliance | 0 |
| 20 % | Satisfies the requirement with major reservations. Considerable reservations of the supplier’s relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services, with little or no supporting evidence. | 1 |
| 40 % | Satisfies the requirement with minor reservations. Some minor reservations of the supplier’s relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services, with little or no supporting evidence. | 2 |
| 60 % | Satisfies the requirement. Demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services, with supporting evidence. | 3 |
| 80 % | Satisfies the requirement with minor additional benefits. Above average demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services. Response identifies factors that will offer potential added value, with supporting evidence. | 4 |
| 100% | Exceeds the requirement. Exceptional demonstration by the supplier of the relevant ability, understanding, experience, skills, resource, and quality measures required to provide the goods / services. Response identifies factors that will offer potential added value, with supporting evidence. | 5 |

  - POINT SYSTEM CALCULATION

Bidders who qualify on functionality will then move to the point system calculation. The bidder with the highest point will be the successful bidder for each service. The 80/20-point system will be applicable.

The 100 points system will be allocated as follows; Price= 80 and Departmental specific goals=20

In terms of the Departmental specific goals, the following will apply;

Table 26 Specific Goals Evaluation

| DEDaT Goal Specific APP |  | SCM % | New Point System | CSD % | Points for Specific Goal |
| --- | --- | --- | --- | --- | --- |
|  | Youth | 35 | 9,72 | 0 | 0,00 |
|  | Women | 35 | 9,72 | 0 | 0,00 |
|  | People With Disabilities | 2 | 0,56 | 0 | 0,56 |
|  |  | 72 | 20,00 |  | 0,56 |

# CONTRACTUAL AGREEMENT

  - The Service Level Agreement (SLA) will be administered in relation to the conditions of the

General and Special contracts of the Bid and the General conditions of Contract (GCC). The requirements/conditions of the SLA are non-negotiable and must be always adhered to. Failure to adhere will necessitate a consequence management in regards to non-performance.

  - The successful bidder will be required to enter a formal contract with NC-DEDaT that shall

be based on this bid specification, the accepted bid, and the letter of acceptance. The contractual agreement may be extended upon mutual agreement between the successful service provider and NC-DEDaT.

  - The bidder shall not, after the bid has been awarded, assign, or cede the contract to any other

party without the prior written consent.

  - Variations and amendments to the contract shall be valid only if they are done in writing and

by mutual consent. Any contract between the Department and the successful bidder shall be governed by the laws of the Republic of South Africa.

  - Contract commencement

Date: To be concluded in the SLA

Duration: 36 months

# REPORT

The successful bidder will submit monthly reports in one original and copies if necessary. This will be incorporated into the Service Level Agreement (SLA).

# MONITORING AND EVALUATION

The project manager will be responsible for the monitoring and evaluation of the execution of the service.

# SUPPLIER DUE DILIGENCE

The Department of Economic Development and Tourism reserves the right to conduct supplier due diligence prior to final award or at any time during the contract period. This may include site visit. A negative report might lead to performance management with its related issues.

# SUBMISSION OF BID

Interested Service Providers must place bid in the Tender Box with the following details:

- Physical Address

Northern Cape Economic Development and Tourism

Cnr. of Knight and Stead Street

MetLife Towers (Entrance)

Ground Floor

Kimberley

8301

- Closing Details

Date: 11 April 2023

Time: 11:00

- Briefing session

Date :  24 March 2023

Time : 10H00

MS Team Link

Click here to join the meeting<https://teams.microsoft.com/l/meetup-join/19%3ab82c29234fcf45779a1fdf46e4d1a5b3%40thread.tacv2/1679051820955?context=%7b%22Tid%22%3a%2288c19a74-3c3b-445a-87e0-94c155bc09cf%22%2c%22Oid%22%3a%22c7766fb9-1dc7-450f-989b-f6f1d3e7093c%22%7d>

Meeting ID: 327 728 404 522

Passcode: PiY9qS

- Collection of documents

Departmental website –

http://www.northern-cape.gov.za/dedat/index.php?option=com_phocadownload&view=category&id=14&Itemid=824

Eportal

https://www.etenders.gov.za/

PART A

INVITATION TO BID

| YOU ARE HEREBY INVITED TO BID FOR REQUIREMENTS OF THE (NAME OF DEPARTMENT/ PUBLIC ENTITY) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BID NUMBER: | DEDaT 0004/1/2022 |  |  | CLOSING DATE: | 11 APRIL 2023 |  |  | CLOSING TIME: |  |  |  | 11H00 |
| DESCRIPTION | APPOINTMENT OF AN EVENTS MANAGEMENT COMPANY TO MANAGE THE KIMBERLEY DIAMOND CUP |  |  |  |  |  |  |  |  |  |  |  |
| BID RESPONSE DOCUMENTS MAY BE DEPOSITED IN THE BID BOX SITUATED AT (STREET ADDRESS) |  |  |  |  |  |  |  |  |  |  |  |  |
| GROUND FLOOR(ENTRANCE) |  |  |  |  |  |  |  |  |  |  |  |  |
| METLIFE TOWERS |  |  |  |  |  |  |  |  |  |  |  |  |
| MARKET SQUARE |  |  |  |  |  |  |  |  |  |  |  |  |
| KIMBERLEY |  |  |  |  |  |  |  |  |  |  |  |  |
| BIDDING PROCEDURE ENQUIRIES MAY BE DIRECTED TO |  |  |  |  |  | TECHNICAL ENQUIRIES MAY BE DIRECTED TO: |  |  |  |  |  |  |
| CONTACT PERSON |  |  | S. MAMPE |  |  | CONTACT PERSON |  |  | Y. PHEIFFER |  |  |  |
| TELEPHONE NUMBER |  |  | 053 839 4000 / 082 414 0295 |  |  | TELEPHONE NUMBER |  |  | 053 839 4006 / 076 673 9917 |  |  |  |
| FACSIMILE NUMBER |  |  | 053 831 3668 |  |  | FACSIMILE NUMBER |  |  | 053 831 3668 |  |  |  |
| E-MAIL ADDRESS |  |  | SMampe@ncpg.gov.za |  |  | E-MAIL ADDRESS |  |  | YPheifer@ncpg.gov.za |  |  |  |
| SUPPLIER INFORMATION |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME OF BIDDER |  |  |  |  |  |  |  |  |  |  |  |  |
| POSTAL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |
| STREET ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |
| TELEPHONE NUMBER |  | CODE |  |  | NUMBER |  |  |  |  |  |  |  |
| CELLPHONE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| FACSIMILE NUMBER |  | CODE |  |  | NUMBER |  |  |  |  |  |  |  |
| E-MAIL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |
| VAT REGISTRATION NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| SUPPLIER COMPLIANCE STATUS |  | TAX COMPLIANCE SYSTEM PIN: |  |  |  | OR | CENTRAL SUPPLIER DATABASE No: |  |  | MAAA |  |  |
| B-BBEE STATUS LEVEL VERIFICATION CERTIFICATE |  | TICK APPLICABLE BOX] Yes No |  |  |  | B-BBEE STATUS LEVEL SWORN AFFIDAVIT |  |  |  |  | [TICK APPLICABLE BOX] Yes No |  |
| [A B-BBEE STATUS LEVEL VERIFICATION CERTIFICATE/ SWORN AFFIDAVIT (FOR EMES & QSEs) MUST BE SUBMITTED IN ORDER TO QUALIFY FOR PREFERENCE POINTS FOR B-BBEE] |  |  |  |  |  |  |  |  |  |  |  |  |
| #### ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS /SERVICES /WORKS OFFERED? |  | Yes No [IF YES ENCLOSE PROOF] |  |  |  | #### ARE YOU A FOREIGN BASED SUPPLIER FOR THE GOODS/SERVICES /WORKS OFFERED? |  |  |  |  | Yes No [IF YES, ANSWER PART B:3 ] |  |
| QUESTIONNAIRE TO BIDDING FOREIGN SUPPLIERS |  |  |  |  |  |  |  |  |  |  |  |  |
| IS THE ENTITY A RESIDENT OF THE REPUBLIC OF SOUTH AFRICA (RSA)? YES NO DOES THE ENTITY HAVE A BRANCH IN THE RSA? YES NO DOES THE ENTITY HAVE A PERMANENT ESTABLISHMENT IN THE RSA? YES NO DOES THE ENTITY HAVE ANY SOURCE OF INCOME IN THE RSA? YES NO IS THE ENTITY LIABLE IN THE RSA FOR ANY FORM OF TAXATION? YES NO IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN IT IS NOT A REQUIREMENT TO REGISTER FOR A TAX COMPLIANCE STATUS SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 BELOW. |  |  |  |  |  |  |  |  |  |  |  |  |

PART B

TERMS AND CONDITIONS FOR BIDDING

- BID SUBMISSION:

- BIDS MUST BE DELIVERED BY THE STIPULATED TIME TO THE CORRECT ADDRESS. LATE BIDS WILL NOT BE ACCEPTED FOR CONSIDERATION. - ALL BIDS MUST BE SUBMITTED ON THE OFFICIAL FORMS PROVIDED–(NOT TO BE RE-TYPED) OR IN THE MANNER PRESCRIBED IN THE BID DOCUMENT. - THIS BID IS SUBJECT TO THE PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000 AND THE PREFERENTIAL PROCUREMENT REGULATIONS, 2017, THE GENERAL CONDITIONS OF CONTRACT (GCC) AND, IF APPLICABLE, ANY OTHER SPECIAL CONDITIONS OF CONTRACT. - THE SUCCESSFUL BIDDER WILL BE REQUIRED TO FILL IN AND SIGN A WRITTEN CONTRACT FORM (SBD7).

- TAX COMPLIANCE REQUIREMENTS

- BIDDERS MUST ENSURE COMPLIANCE WITH THEIR TAX OBLIGATIONS. - BIDDERS ARE REQUIRED TO SUBMIT THEIR UNIQUE PERSONAL IDENTIFICATION NUMBER (PIN) ISSUED BY SARS TO ENABLE THE ORGAN OF STATE TO VERIFY THE TAXPAYER’S PROFILE AND TAX STATUS. - APPLICATION FOR TAX COMPLIANCE STATUS (TCS) PIN MAY BE MADE VIA E-FILING - THROUGH THE SARS WEBSITE WWW.SARS.GOV.ZA. - BIDDERS MAY ALSO SUBMIT A PRINTED TCS CERTIFICATE TOGETHER WITH THE BID. - IN BIDS WHERE CONSORTIA / JOINT VENTURES / SUB-CONTRACTORS ARE INVOLVED, EACH PARTY MUST SUBMIT A SEPARATE TCS CERTIFICATE / PIN / CSD NUMBER. - WHERE NO TCS IS AVAILABLE BUT THE BIDDER IS REGISTERED ON THE CENTRAL SUPPLIER DATABASE (CSD), A CSD NUMBER MUST BE PROVIDED. - NO BIDS WILL BE CONSIDERED FROM PERSONS IN THE SERVICE OF THE STATE, COMPANIES WITH DIRECTORS WHO ARE PERSONS IN THE SERVICE OF THE STATE, OR CLOSE CORPORATIONS WITH MEMBERS PERSONS IN THE SERVICE OF THE STATE.”

NB: FAILURE TO PROVIDE / OR COMPLY WITH ANY OF THE ABOVE PARTICULARS MAY RENDER THE BID INVALID.

SIGNATURE OF BIDDER:……………………………………………

CAPACITY UNDER WHICH THIS BID IS SIGNED: ……………………………………………

(Proof of authority must be submitted e.g. company resolution)

DATE:	 …………………………………………...

SBD 3.1

PRICING SCHEDULE – FIRM PRICES

(PURCHASES)

NOTE:	ONLY FIRM PRICES WILL BE ACCEPTED. NON-FIRM PRICES (INCLUDING PRICES SUBJECT TO RATES OF EXCHANGE VARIATIONS) WILL NOT BE CONSIDERED

IN CASES WHERE DIFFERENT DELIVERY POINTS INFLUENCE THE PRICING, A SEPARATE PRICING SCHEDULE MUST BE SUBMITTED FOR EACH DELIVERY POINT

Name of bidder………………….…… Bid number…………………................................. Closing Time 11:00 Closing date…………………………………………...

OFFER TO BE VALID FOR…120…DAYS FROM THE CLOSING DATE OF BID.

__________________________________________________________________________

ITEM	QUANTITY	DESCRIPTION		BID PRICE IN RSA CURRENCY

NO.						            ** (ALL APPLICABLE TAXES INCLUDED)

- Required by:					………………………………….

-	At:						………………………………….

…………………………………

- Brand and model				………………………………….

- Country of origin				………………………………….

-	Does the offer comply with the specification(s)?			*YES/NO

- If not to specification, indicate deviation(s)	………………………………….

- Period required for delivery			………………………………….

*Delivery: Firm/not firm

- Delivery basis 					……………………………………

Note:	All delivery costs must be included in the bid price, for delivery at the prescribed destination.

** “all applicable taxes” includes  value- added tax, pay as you earn, income tax, unemployment  insurance fund contributions and skills development levies.

*Delete if not applicable

SBD 4

BIDDER’S DISCLOSURE

1. 	PURPOSE OF THE FORM

Any person (natural or juristic) may make an offer or offers in terms of this invitation to bid. In line with the principles of transparency, accountability, impartiality, and ethics as enshrined in the Constitution of the Republic of South Africa and further expressed in various pieces of legislation, it is required for the bidder to make this declaration in respect of the details required hereunder.

Where a person/s are listed in the Register for Tender Defaulters and / or the List of Restricted Suppliers, that person will automatically be disqualified from the bid process.

2. 	Bidder’s declaration

2.1  Is the bidder, or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest1 in the enterprise,

employed by the state? 	 	 	 	 	 YES/NO

2.1.1 If so, furnish particulars of the names, individual identity numbers, and, if applicable, state employee numbers of sole proprietor/ directors / trustees / shareholders / members/ partners or any person having a controlling interest in the enterprise, in table below.

| Full Name | Identity Number | Name of institution | State |
| --- | --- | --- | --- |

2.2 Do you, or any person connected with the bidder, have a relationship with any person who is employed by the procuring institution? YES/NO

2.2.1     If so, furnish particulars:

…………………………………………………………………………………

……………………………………………………………………………………………………………………………………………………………………

2.3  Does the bidder or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise have any interest in any other related enterprise whether or not they are bidding for this contract? 	 	 	YES/NO

2.3.1 If so, furnish particulars:

……………………………………………………………………………. …………………………………………………………………………….

3 	DECLARATION

I, ,(name)………………………………………………………………….	the undersigned

in submitting the accompanying bid, do hereby make the following statements that I certify to be true and complete in every respect:

3.1  	I have read and I understand the contents of this disclosure;

3.2 I understand that the accompanying bid will be disqualified if this disclosure is found not to be true and complete in every respect;

3.3  The bidder has arrived at the accompanying bid independently from, and without consultation, communication, agreement or arrangement with any competitor. However, communication between partners in a joint venture or consortium will not be construed as collusive bidding.

3.4  In addition, there have been no consultations, communications, agreements or arrangements with any competitor regarding the quality, quantity, specifications, prices, including methods, factors or formulas used to calculate prices, market allocation, the intention or decision to submit or not to submit the bid, bidding with the intention not to win the bid and conditions or delivery particulars of the products or services to which this bid invitation relates.

3.4 The terms of the accompanying bid have not been, and will not be, disclosed by the bidder, directly or indirectly, to any competitor, prior to the date and time of the official bid opening or of the awarding of the contract.

3.5  	There have been no consultations, communications, agreements or arrangements made by the bidder with any official of the procuring institution in relation to this procurement process prior to and during the bidding process except to provide clarification on the bid submitted where so required by the institution; and the bidder was not involved in the drafting of the specifications or terms of reference for this bid.

3.6 I am aware that, in addition and without prejudice to any other remedy provided to combat any restrictive practices related to bids and contracts, bids that are suspicious will be reported to the Competition Commission for investigation and possible imposition of administrative penalties in terms of section 59 of the Competition Act No 89 of 1998 and or may be reported to the National Prosecuting Authority (NPA) for criminal investigation and or may be restricted from conducting business with the public sector for a period not exceeding ten (10) years in terms of the Prevention and Combating of Corrupt Activities Act No 12 of 2004 or any other applicable legislation.

I CERTIFY THAT THE INFORMATION FURNISHED IN PARAGRAPHS 1, 2 and 3 ABOVE IS CORRECT.

I ACCEPT THAT THE STATE MAY REJECT THE BID OR ACT AGAINST ME IN TERMS OF PARAGRAPH 6 OF PFMA SCM INSTRUCTION 03 OF 2021/22 ON PREVENTING AND COMBATING ABUSE IN THE SUPPLY CHAIN MANAGEMENT SYSTEM SHOULD THIS DECLARATION PROVE TO BE FALSE.

……………………………… 	 ..……………………………………………

Signature 	                          Date

……………………………………            ……………………………………………

Position  				         		Name of bidder

SBD 6.1

PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2017

This preference form must form part of all bids invited.  It contains general information and serves as a claim form for preference points for Broad-Based Black Economic Empowerment (B-BBEE) Status Level of Contribution

NB:	BEFORE COMPLETING THIS FORM, BIDDERS MUST STUDY THE GENERAL CONDITIONS, DEFINITIONS AND DIRECTIVES APPLICABLE IN RESPECT OF B-BBEE, AS PRESCRIBED IN THE PREFERENTIAL PROCUREMENT REGULATIONS, 2017.

- GENERAL CONDITIONS

  - The following preference point systems are applicable to all bids:

- the 80/20 system for requirements with a Rand value of up to R50 000 000 (all applicable taxes included); and

- the 90/10 system for requirements with a Rand value above R50 000 000 (all applicable taxes included).

a) The value of this bid is estimated to not exceed R50 000 000 (all applicable taxes included) and therefore the …80/20…….. preference point system shall be applicable; or

b) Either the 80/20 or 90/10 preference point system will be applicable to this tender (delete whichever is not applicable for this tender).

  - Points for this bid shall be awarded for:

- Price; and

- B-BBEE Status Level of Contributor.

  - The maximum points for this bid are allocated as follows:

|  | POINTS |
| --- | --- |
| PRICE |  |
| B-BBEE STATUS LEVEL OF CONTRIBUTOR |  |
| Total points for Price and B-BBEE must not exceed | 100 |

  - Failure on the part of a bidder to submit proof of B-BBEE Status level of contributor together with the bid, will be interpreted to mean that preference points for B-BBEE status level of contribution are not claimed.

  - The purchaser reserves the right to require of a bidder, either before a bid is adjudicated or at any time subsequently, to substantiate any claim in regard to preferences, in any manner required by the purchaser.

- DEFINITIONS

- “B-BBEE” means broad-based black economic empowerment as defined in section 1 of the Broad-Based Black Economic Empowerment Act;

- “B-BBEE status level of contributor” means the B-BBEE status of an entity in terms of a code of good practice on black economic empowerment, issued in terms of section 9(1) of the Broad-Based Black Economic Empowerment Act;

- “bid” means a written offer in a prescribed or stipulated form in response to an invitation by an organ of state for the provision of goods or services, through price quotations, advertised competitive bidding processes or proposals;

- “Broad-Based Black Economic Empowerment Act” means the Broad-Based Black Economic Empowerment Act, 2003 (Act No. 53 of 2003);

- “EME” means an Exempted Micro Enterprise in terms of a code of good practice  on black economic empowerment issued in terms of section 9 (1) of the Broad-Based Black Economic Empowerment Act;

- “functionality” means the ability of a tenderer to provide goods or services in accordance with specifications as set out in the tender documents.

- “prices” includes all applicable taxes less all unconditional discounts;

- “proof of B-BBEE status level of contributor” means:

- B-BBEE Status level certificate issued by an authorized body or person;

- A sworn affidavit as prescribed by the B-BBEE Codes of Good Practice;

- Any other requirement prescribed in terms of the B-BBEE Act;

- “QSE” means a qualifying small business enterprise in terms of a code of good practice  on black economic empowerment issued in terms of section 9 (1) of the Broad-Based Black Economic Empowerment Act;

- “rand value” means the total estimated value of a contract in Rand, calculated at the time of bid invitation, and includes all applicable taxes;

- POINTS AWARDED FOR PRICE

  - THE 80/20 OR 90/10 PREFERENCE POINT SYSTEMS

A maximum of 80 or 90 points is allocated for price on the following basis:

80/20	                    or				90/10

or

Where

Ps	=	Points scored for price of bid under consideration

Pt	=	Price of bid under consideration

Pmin	=	Price of lowest acceptable bid

- POINTS AWARDED FOR B-BBEE STATUS LEVEL OF CONTRIBUTOR

  - In terms of Regulation 6 (2) and 7 (2) of the Preferential Procurement Regulations, preference points must be awarded to a bidder for attaining the B-BBEE status level of contribution in accordance with the table below:

| B-BBEE Status Level of Contributor | Number of points (80/20 system) |
| --- | --- |
| 1 | 20 |
| Non-compliant contributor | 0 |

- BID DECLARATION

  - Bidders who claim points in respect of B-BBEE Status Level of Contribution must complete the following:

- B-BBEE STATUS LEVEL OF CONTRIBUTOR CLAIMED IN TERMS OF PARAGRAPHS 1.4 AND 4.1

  - B-BBEE Status Level of Contributor:	.      =     ………(maximum of 10 or 20 points)

(Points claimed in respect of paragraph 7.1 must be in accordance with the table reflected in paragraph  4.1 and must be substantiated by relevant proof of B-BBEE status level of contributor.

- SUB-CONTRACTING

  - Will any portion of the contract be sub-contracted?

(Tick applicable box)

| YES |  | NO |  |
| --- | --- | --- | --- |

    - If yes, indicate:

- What percentage of the contract will be subcontracted............…………….…………%

- The name of the sub-contractor…………………………………………………………..

- The B-BBEE status level of the sub-contractor......................................……………..

- Whether the sub-contractor is an EME or QSE

(Tick applicable box)

| YES |  | NO |  |
| --- | --- | --- | --- |

- Specify, by ticking the appropriate box, if subcontracting with an enterprise in terms of Preferential Procurement Regulations,2017:

| Designated Group: An EME or QSE which is at last 51% owned by: | EME √ | QSE √ |
| --- | --- | --- |
| Black people |  |  |
| Black people who are youth |  |  |
| Black people who are women |  |  |
| Black people with disabilities |  |  |
| Black people living in rural or underdeveloped areas or townships |  |  |
| Cooperative owned by black people |  |  |
| Black people who are military veterans |  |  |
| OR |  |  |
| Any EME |  |  |
| Any QSE |  |  |

- DECLARATION WITH REGARD TO COMPANY/FIRM

  - Name of company/firm:………………………………………………………………….

  - VAT registration number:……………………….…………………………………

  - Company registration number:………….……………………….…………………….

  - TYPE OF COMPANY/ FIRM

Partnership/Joint Venture / Consortium

One person business/sole propriety

Close corporation

Company

(Pty) Limited

[Tick applicable box]

  - DESCRIBE PRINCIPAL BUSINESS ACTIVITIES

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

  - COMPANY CLASSIFICATION

Manufacturer

Supplier

Professional service provider

Other service providers, e.g. transporter, etc.

[Tick applicable box]

  - Total number of years the company/firm has been in business:……………………………

  - I/we, the undersigned, who is / are duly authorised to do so on behalf of the company/firm, certify that the points claimed, based on the B-BBE status level of contributor indicated in paragraphs 1.4 and 6.1 of the foregoing certificate, qualifies the company/ firm for the preference(s) shown and I / we acknowledge that:

- The information furnished is true and correct;

- The preference points claimed are in accordance with the General Conditions as indicated in paragraph 1 of this form;

- In the event of a contract being awarded as a result of points claimed as shown in paragraphs 1.4 and 6.1, the contractor may be required to furnish documentary proof to the satisfaction of the purchaser that the claims are correct;

- If the B-BBEE status level of contributor has been claimed or obtained on a fraudulent basis or any of the conditions of contract have not been fulfilled, the purchaser may, in addition to any other remedy it may have –

  - disqualify the person from the bidding process;

  - recover costs, losses or damages it has incurred or suffered as a result of that person’s conduct;

  - cancel the contract and claim any damages which it has suffered as a result of having to make less favourable arrangements due to such cancellation;

  - recommend that the bidder or contractor, its shareholders and directors, or only the shareholders and directors who acted on a fraudulent basis, be restricted by the National Treasury from obtaining business from any organ of state for a period not exceeding 10 years, after the audi alteram partem (hear the other side) rule has been applied; and

  - forward the matter for criminal prosecution.

WITNESSES

- ……………………………………..

- …………………………………….

WITNESSES

- ……………………………………..

- …………………………………….

……………………………………….

SIGNATURE(S) OF BIDDERS(S)

DATE:	       …. …………………………………..

ADDRESS      ……………………………………..

……….……………………………..

……………………………………..

……………………………………….

SIGNATURE(S) OF BIDDERS(S)

DATE:	       …. …………………………………..

ADDRESS      ……………………………………..

……….……………………………..

……………………………………..

Joint venture or Consortium means an association of persons for the purpose of combining their expertise, property, capital, efforts, skill and knowledge in an activity for the execution of a contract.