ANNEXURE K

TECHNICAL EVALUATION CRITERIA

|  | - Mandatory Technical Evaluation Criteria / Gatekeepers |  |  |  |
| --- | --- | --- | --- | --- |
| No | Mandatory requirements | Minimum evidence required | Evaluation basis | Outcome |
| 1. | Ability to design and construct an integrated waste reception, drying/ feed preparation, incineration, flue gas treatment, stack monitoring, instrumentation and data acquisition facility. | Technical proposal, process description, preliminary PFD, preliminary GA layout and equipment list. | Yes / No | Failure to comply is technically nonresponsive |
| 2. | Compliance with applicable South African environmental, safety and engineering requirements including NEMA, relevant SANS requirements and Eskom site requirements. | Compliance matrix and proposed approach to statutory approvals, environmental compliance, occupational health and safety, and emissions management. | Yes/ No | Failure to comply is technically nonresponsive |
| 2. Qualitative Technical Scoring Methodology |  |  |  |  |
| 5 | 100% | Fully compliant: meets the requirement with no foreseen technical risk. |  |  |
| 4 | 80% | Compliant with minor qualifications: meets the requirement with acceptable technical risks, exceptions or conditions. |  |  |
| 2 | 40% | Partially compliant / weak response: does not fully meet the requirement or presents material technical risk. |  |  |
| 0 | 0% | Non-responsive or totally deficient: no adequate evidence provided. |  |  |
|  | Note: Scores of 1 and 3 are not used. Weighted score = criterion weighting x score percentage. |  |  |  |
|  | 3. Qualitative Technical Evaluation Criteria |  |  |  |
| No | Criteria | Scoring guidance / evidence required | Weighting | Maximum score |
| 1 | Company experience and reference projects | Evidence of completed projects of similar complexity involving waste-to energy, incineration, thermal treatment, combustion systems, flue gas treatment, pilot/test/commercial plants. Returnables must include project name, client, scope, value, start and completion dates, commissioning status and traceable references. 5 = three or more directly relevant completed projects; 4 = two relevant completed projects; 2 = one relevant project; 0 = no adequate evidence. | 20% | 20 |
| 2 | Technical solution, methodology and design approach | Assessment of proposed technical solution for the 50 to 100 kW test facility, including but not limited to waste reception, storage, drying/feed preparation, controlled incineration, flue gas treatment, stack/emissions monitoring, instrumentation, control and data acquisition. 5 = comprehensive, integrated and fitfor- purpose design approach; 4 = compliant with minor clarifications required; 2 = incomplete or high-risk approach; 0 = inadequate or nonresponsive. | 25% | 25 |
| 3 | Resource capability and key personnel | Relevant qualified and experienced personnel for civil/structural, mechanical, electrical, control and instrumentation, process/chemical engineering, project management, construction supervision, SHEQ and commissioning. CVs, statutory registrations where applicable and project roles must be provided. 5 = all required disciplines adequately covered; 4 = most disciplines covered with acceptable mitigation; 2 = significant gaps in personnel or experience; 0 = no adequate resource evidence. | 20% | 20 |
| 4 | Project programme and delivery capability | Detailed programme for design, procurement, construction, installation, commissioning, performance testing, documentation handover and training. The programme must identify critical path activities, interfaces, assumptions and key risks. 5 = achievable completion within 12 months from contract award; 4 = achievable completion within 16 months; 2 = completion within 18 months or programme lacks detail; 0 = no credible programme. | 15% | 15 |
| 5 | Compliance, safety, quality and environmental management | Approach to statutory compliance, environmental management, emissions control, occupational health and safety, QA/QC, inspection and testing, risk management and site execution controls. 5 = comprehensive compliance, SHEQ and environmental approach; 4 = compliant with minor clarification 2 = incomplete or high-risk approach 0 = inadequate evidence. | 10% | 10 |
| 6 | Commissioning, performance testing, documentation and training | Commissioning plan, performance test procedure, acceptance criteria, operating and maintenance manuals/plans, training plan and post commissioning support. 5 = complete and practical commissioning and handover approach; 4 = acceptable with minor clarifications; 2 = incomplete or weak approach; 0 = inadequate evidence. | 10% | 10 |
|  | Total scoring |  | 100% |  |
|  | Minimum technical threshold: Tenderers must achieve a minimum weighted technical score of 70% to be considered technically acceptable and to proceed to the next stage of evaluation. |  |  |  |