{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Pricing Option A"],"read":"whole","date_system":"1900"}

{"sheet":"Pricing Option A","index":0,"n_rows":20,"n_cols":5,"rows_kept":20,"merged":[[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4]]}
[]
["Item","Programme Reference","Activity description","Frequncy","Price (excl VAT)"]
["No."]
[null,null,"The following activities are to be Priced for all the Ingula and small hydro dams:"]
[1,null,"Training of Employer’s staff","At the start of the contract"]
[2,null,"Liaison with authorities for the whole of the services","As required in order to complete the scope of services."]
[3,null,"Providing designs, scope of works and technical specifications for the actions or recommendations","As required in order to complete the scope of services."]
[4,null,"Dam Safety Evaluation Report","At the start and end of the contract"]
[5,null,"Undertake Stability Checks","At the start and end of the contract"]
[6,null,"Provide Closeout Documentation and Sign Offs of the Dams for the the Findings of the Dam Safety Evaluation Report.","At the start and end of the contract"]
[7,null,"Review and update the existing Dam Information;Iincluded but not limited to EPP, Hydrology, Dam Break Analysis etc. and Issue the Assessment Report.","At the start of the contract"]
[8,null,"Reviewing, updating and compilation of Operating and Maintenance manuals","At the start and end of the contract"]
[9,null,"Inspections and reporting","Bi-annually"]
[10,null,"Providing designs, scope of works and technical specifications for the actions or recommendations","As and when required"]
[11,null,"Conduct lidar and bathymetric survey and issue report.","During the 2nd year of the contract"]
[]
[null,null,"The following activities are to be Priced for all the small hydro dams only:"]
[12,null,"Conduct topographical surveys","Bi-annually"]
[]
[null,null,"Total of the Prices"]