{"text_format":"3","workbook":"xls","n_sheets":29,"sheets":["COVER SHEET","REVISION CONTROL","DEFINITIONS","NOTES","LOSS INDEX","LOSS GTR P20E 001","LOSS GTR P20F 001","LOSS IA P20","LOSS FW P20F 020","LOSS DW P20F 120","LOSS WTP P20F 002","LOSS P20E CIVIL","LOSS P20F CVL ","LOSS P20E ELEC","LOSS P20F ELEC","LOSS P20E&P20F( PLC + DCS)","LOSS P20E FM5","LOSS P20F FM5","LOSS P20E PM1","LOSS P20F PM1","LOSS P20E PM4","LOSS P20F PM4","LOSS P20E BV1","LOSS P20F BV1","LOSS P20E BV2","LOSS P20F BV2","LOSS P20F FDS","LOSS P20F CCTV","LOSS P20F ACN1"],"not_rendered":{"images":1,"macros":1,"external_links":1,"defined_names":4},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"COVER SHEET","index":0,"n_rows":20,"n_cols":3,"rows_kept":20,"merged":[[0,0,1,0],[0,1,1,1],[2,0,2,2],[3,0,3,2],[4,0,13,0],[7,1,9,1],[15,0,16,0],[15,1,16,1],[15,2,16,2],[19,0,20,0],[19,1,20,1],[19,2,20,2]],"flags":["formulas_cached_only"]}
[null," Document","Generaion"]
[null,null,"Engineering"]
["TITLE:  MEDUPI POWER STATION N2H2 PLANT"]
["LIMIT OF SUPPLY & SERVICES (LOSS)"]
[" ","Template Identifier:","240-90320365 (Rev 1)"]
[null,"Unique Identifier:","348-9976938"]
[null,"Alternative Reference Number:","N/A"]
[null,"Area of Applicability:","Medupi Power Station N2H2 Plant"]
[null,null,"Strategy Document"]
[null,null,"Limit of Supply Services (LOSS)"]
[null,"Revision:",2]
[null,"Date issued","2025-08-20"]
[null,"Disclosure Classification:","CONTROLLED DISCLOSURE"]
[]
["Compiled by","Accepted by","Authorised by"]
["Matswele Molabe","Zak Jiyane","Rofiwha Nemutandani"]
[]
[]
["Mechanical Engineer"," Engineering Design Work Lead","Project Engineering Manager"]
["Date: ……………………………","Date: ……………………………","Date: ……………………………"]

{"sheet":"REVISION CONTROL","index":1,"n_rows":11,"n_cols":4,"rows_kept":11,"merged":[[0,0,0,3],[4,0,4,3]],"flags":["formulas_cached_only"]}
["LOSS Revision Control"]
["Revision No:","Revised by: ","Date","Key Updates"]
[1,"Tony Haupt","2021-01-17","LOSS created"]
[2,"Matswele Molabe","2025-08-20","LOSS revised"]
["LOSS Approval"]
["Name ","Designation ","Date","Signature"]
["Zak Jiyane","Engineering Design Work Lead"]
["Banele Mbendane","Lead Discipline Engineer – Electrical "]
["Mdu Shozi","Lead Discipline Engineer - C&I "]
["Morapeli Matjoi","Lead Discipline Engineer – LPS"]
["Tau Chokoe  /   Justin Padiachy","Lead Discipline Engineer – Civil "]

{"sheet":"DEFINITIONS","index":2,"n_rows":63,"n_cols":3,"rows_kept":63,"merged":[[0,0,0,2],[14,0,14,2],[15,1,15,2],[16,1,16,2],[17,1,17,2],[18,1,18,2],[19,1,19,2],[20,1,20,2],[21,1,21,2],[22,1,22,2],[23,1,23,2],[24,1,24,2],[25,1,25,2],[26,1,26,2],[27,1,27,2],[28,1,28,2],[29,1,29,2],[30,1,30,2],[31,1,31,2],[32,1,32,2],[33,1,33,2],[34,1,34,2],[35,1,35,2],[36,1,36,2],[37,1,37,2],[38,1,38,2],[39,1,39,2],[40,1,40,2],[41,1,41,2],[42,1,42,2],[43,1,43,2],[44,1,44,2],[45,1,45,2],[46,1,46,2],[47,1,47,2],[48,1,48,2],[49,1,49,2],[50,1,50,2],[51,1,51,2],[52,1,52,2],[53,1,53,2],[54,1,54,2],[55,0,55,2],[56,1,56,2],[57,1,57,2],[58,1,58,2],[59,1,59,2],[60,1,60,2],[61,1,61,2],[62,0,62,2],[63,0,63,2],[64,0,64,2],[65,0,65,2],[66,0,66,2],[67,0,67,2],[68,0,68,2],[69,0,69,2],[70,0,70,2],[71,0,71,2],[72,0,72,2]],"flags":["formulas_cached_only"]}
["PACKAGE KEY"]
["Package Number","Abbreviation","Description"]
[]
["E = ENGINEER (ESKOM)"]
["P20E = H2 CONTRACTOR-GENERATING UNIT"]
["P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
{"$rows_empty":8}
["ABBREVIATIONS"]
["DCS","Distributed Control System"]
["LV","Low Voltage"]
["MV","Medium Voltage"]
["OP","Operator Panel"]
["AM","Analysers"]
["BB","Black Box Interfaces"]
["BD","Binary Damper"]
["BLD","Bag Leak Detection"]
["BV","Binary Valves"]
["CD","Control Damper"]
["CV","Control Valves"]
["DC","DC Voltage Drives"]
["DCD","Direct Control Drives"]
["ELE","Electrical"]
["ERT","Earthing"]
["FDS","Fire Detection System"]
["FM","Flow measurement"]
["INT","Interfaces to 3rd party systems"]
["JN","Junction Box Interfaces"]
["LM","Level Measurement"]
["LMT","Limit Switches"]
["LVB","Low Voltage Breaker"]
["LVD","Low Voltage Drives"]
["LVS","Low Volatge Supply"]
["MAG","Magnet"]
["MCC","Motor Centre Control"]
["MD","Metal Detector"]
["MM","Mass Meter"]
["MVB","Medium Voltage Breaker"]
["MVD","Medium Voltage Drives"]
["NLP","Non-Loop Powered"]
["PM","Pressure Measurement"]
["PS","Promimity Switch"]
["PSM","Position Measurement"]
["RTU","Remote Terminal Unit"]
["TM","Temperature Measurement"]
["UPS","Uninterruptable Power Supply"]
["VM","Vibration Measurement"]
["VSD","Variable Speed Drives"]
[]
["DEFINITIONS"]
["Specification","Refers to information or requirements to enable conceptual design or detailed design for the component or system"]
["Conceptual Design","Refers to design concepts principles and philosophies to enable detailed design"]
["Detailed Design","Refers to a detailed design of the component "]
["Construction","Refers to the construction of the relevant structures, components or systems "]
["Installation","Assembly of different components to form a system"]
["Commissioning","Refers to the testing of components or systems to prove that the component/system meet and function to the requirement as stated in the specification"]
["NOTES"]

{"sheet":"NOTES","index":3,"n_rows":7,"n_cols":7,"rows_kept":7,"merged":[[0,0,1,6],[2,0,2,6],[3,1,3,5],[4,1,4,5],[5,1,5,5],[6,1,6,5],[7,1,7,5],[14,0,14,6]],"flags":["formulas_cached_only"]}
["MEDUPI POWER STATION \nN2H2 PLANT"]
[]
["LOSS REGISTER"]
["NOTES","NOTE DESCRIPTION",{"$nulls":4},"COMMENTS"]
[1]
[]
[2]

{"sheet":"LOSS INDEX","index":4,"n_rows":36,"n_cols":7,"rows_kept":36,"merged":[[0,0,1,6],[2,0,2,6],[9,0,9,6],[16,0,16,6],[18,0,18,6],[21,0,21,6]],"flags":["formulas_cached_only"]}
["MEDUPI POWER STATION \nMedupi Power Station N2H2 Plant"]
[]
["LOSS REGISTER"]
["PAGE","LOSS","LOSS DESCRIPTION","REASON FOR REVISION","Rev.","DATE","COMMENTS"]
[1,null,"COVER SHEET"]
[2,null,"REVISION CONTROL"]
[3,null,"DEFINITIONS"]
[4,null,"LOSS INDEX"]
[5,null,"CHANGE LOG"]
["Mechanical LOSS-H2N2 Plant"]
[null,"LOSS-GTR-P20E-001","HYDROGEN INTERFACE (6 UNITS GENERATORS)"]
[null,"LOSS-GTR-P20F-001","NITROGEN INTERFACE TURBINE GENERATOR UNITS"]
[null,"LOSS-IA-P20E&P20F","INSTRUMENT AIR INTERFACE"]
[null,"LOSS-FW-P20F-020","FIRE WATER INTERFACE"]
[null,"LOSS-DW-P20F-120","DEMIN WATER INTERFACE"]
[null,"LOSS-WTP-P20F-002","NITROGEN INTERFACE WITH WTP"]
["Civil LOSS - H2N2 Plant"]
[null,"LOSS-P20F-CVL","CVL LOSS"]
["Electrical LOSS - H2N2 Plant"]
[null,"LOSS-P20E-ELEC","H2 PLANT ELECTRICAL LOSS"]
[null,"LOSS-P20F-ELEC","N2 PLANT ELECTRICAL LOSS"]
["C&I  LOSS - H2N2 Plant"]
[null,"LOSS-P20E&P20F-PLC+DCS","PLC AND DCS INTERFACE"]
[null,"LOSS-P20E-FM5","H2 PLANT FLOW MEASUREMENT - inline"]
[null,"LOSS-P20F-FM5","N2 PLANT FLOW MEASUREMENT - inline"]
[null,"LOSS-P20E-PM1","H2 PLANT PRESSURE MEASUREMENT AND OR SWITCH (PRESSURE TRANSDUCER)"]
[null,"LOSS-P20F-PM1","N2 PLANT PRESSURE MEASUREMENT AND OR SWITCH (PRESSURE TRANSDUCER)"]
[null,"LOSS-P20E-PM4","H2 PLANT PRESSURE MEASUREMENT (PRESSURE GAUGE)"]
[null,"LOSS-P20F-PM4","N2 PLANT PRESSURE MEASUREMENT (PRESSURE GAUGE)"]
[null,"LOSS-P20E-BV1","H2 PLANT, 400V AC ELECTRICAL ACTUATED BINARY VALVE WITH INTEGRATED SWITCHGEAR"]
[null,"LOSS-P20F-BV1","N2 PLANT, 400V AC ELECTRICAL ACTUATED BINARY VALVE WITH INTEGRATED SWITCHGEAR"]
[null,"LOSS-P20E-BV2","H2 PLANT, 24V DC SOLENOID OPERATED BINARY VALVE"]
[null,"LOSS-P20E-BV2","H2 PLANT, 24V DC SOLENOID OPERATED BINARY VALVE"]
[null,"LOSS-P20F-FDS","FIRE DETECTION SYSTEM "]
[null,"LOSS-P20F-CCTV","CCTV MONITORING / RECORDING SYSTEM TYPE 1"]
[null,"LOSS-P20F-ACN1","ACCESS CONTROL NETWORK"]

{"sheet":"LOSS GTR P20E 001","index":5,"n_rows":49,"n_cols":24,"rows_kept":49,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[46,10,46,15],[47,4,47,9],[48,10,48,15]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nHYDROGEN INTERFACE (6 UNITS GENERATORS)\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-GTR-P20E-001"]
[null,"UPSTREAM"]
{"$rows_empty":7}
[null,"HYDROGEN GENERATING UNITS",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[null,"FLANGE",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"GASKET, BOLTS",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"FLANGED VALVE",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"GASKET, BOLTS",null,"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"FLANGE",null,"E",null,"P20E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"P20E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[null,"H2 SUPPLY TO UNITS"]
[]
[]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":8},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":10},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS GTR P20F 001","index":6,"n_rows":49,"n_cols":24,"rows_kept":49,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[46,10,46,15],[47,4,47,9],[48,10,48,15]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nNITROGEN INTERFACE TURBINE GENERATOR UNITS\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-GTR-P20F-001"]
[null,"UPSTREAM"]
[]
[null,"NITROGEN SUPPLY from High Pressure Vessels",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"FLANGE",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"GASKET, BOLTS",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"FLANGED VALVE",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"GASKET, BOLTS",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"FLANGE",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"Generator Turbines at the Units                                                      "]
{"$rows_empty":11}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":8},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":10},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS IA P20","index":7,"n_rows":53,"n_cols":24,"rows_kept":53,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[48,4,48,9],[52,4,52,9],[52,13,52,17],[55,4,55,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nINSTRUMENT AIR INTERFACE\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-IA-P20E&P20F"]
[null,"UPSTREAM"]
{"$rows_empty":16}
[null,"PIPING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"TAP OFF",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"TAP OFF",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[]
[]
[null,"PIPING ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20 F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"EQUIPMENT",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"EQUIPMENT",null,"P20F",null,"P20F",null,"E",null,"P20 F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"EQUIPMENT",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"EQUIPMENT",null,"P20F",null,"P20F",null,"E",null,"P20 F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":4},"REVISION :",{"$nulls":8},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":8},"20/08/2025"]

{"sheet":"LOSS FW P20F 020","index":8,"n_rows":53,"n_cols":24,"rows_kept":53,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[48,4,48,9],[52,4,52,9],[52,13,52,17],[55,4,55,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nFIRE WATER INTERFACE\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-FW-P20F-020"]
[null,"UPSTREAM"]
{"$rows_empty":7}
[null,"Tap into Fire Main lines.                             "]
[]
[]
[]
[null,"PIPE ",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"FLANGE",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"GASKET, BOLTS",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"FLANGED VALVE",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"GASKET, BOLTS",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"FLANGE",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"Passive and other Fire Protection System e.g  dulge system, sprinlkers"]
[]
[]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":4},"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS DW P20F 120","index":9,"n_rows":49,"n_cols":24,"rows_kept":49,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[46,10,46,15],[47,4,47,9],[48,10,48,15]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nDEMIN WATER INTERFACE\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-DW-P20F-120"]
[null,"UPSTREAM"]
[]
[null,"Water Treatement Plant Raw and Demi Water Supply                                                       "]
[]
[]
[null,"PIPE ",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"FLANGE",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"GASKET, BOLTS",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"FLANGED VALVE",null,"E",null,"E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"GASKET, BOLTS",null,"E",null,"E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"FLANGE",null,"E",null,"E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"H2 Generating Units                                   "]
{"$rows_empty":13}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":8},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":10},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS WTP P20F 002","index":10,"n_rows":49,"n_cols":24,"rows_kept":49,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[46,11,46,16],[47,4,47,9],[48,11,48,16]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nMECHANICAL: LOW PRESSURE SERVICES\n\nINTERFACE:\nNITROGEN INTERFACE 6 UNITS (CONDENSATE STORAGE TANKS)\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-WTP-P20F-002"]
[null,"UPSTREAM"]
{"$rows_empty":7}
[null,"NITROGEN GENERATING UNITS",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"FLANGE",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"GASKET, BOLTS",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"FLANGED VALVE",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"GASKET, BOLTS",null,"E",null,"P20F",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[null,"FLANGE",null,"E",null,"P20F",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"PIPE ",null,"E",null,"P20F",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"Distritbution to WTP            "]
[]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":9},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":11},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E CIVIL","index":11,"n_rows":34,"n_cols":35,"rows_kept":34,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,8],[1,10,2,10],[1,12,2,12],[1,14,2,14],[1,16,2,16],[1,18,2,18],[1,20,2,20],[1,22,2,22],[1,24,2,25],[1,27,2,27],[1,29,2,29],[1,31,2,32],[1,34,2,34],[32,6,32,10]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nCIVIL\n\nINTERFACE:\nHYDROGEN AND NITROGEN GENERATING PLANT\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION INFORMATION",null,"SURVEYING AND LOCATION DETAILS/SETTING OUT",null,"CONCEPTUAL/BASIC DESIGN AND REVIEW",null,null,"DETAILED DESIGN AND REVIEW",null,"FINAL DETAILED DESIGN REVIEW and DESIGN FREEZE",null,"SUBMISSION OF PERMITS,  AND QC/QA DOCUMENTATION",null,"FINAL SETTING OUT ON SITE",null,"APPROVED FOR CONSTRUCTION DRAWINGS",null,"FABRICATION, MANUFACTURE & SUPPLY",null,"CONSTRUCTION AND INSTALLATION",null,"CONSTRUCTION/INSTALLATION REVIEWS",null,null,"DATABOOKS AND FINAL INSPECTIONS",null,"CERTIFICATION and AS BUILT Submission",null,"HANDOVER",null,null,"REMARKS"]
[null,"LOSS-P20E-CVL"]
[null,"UPSTREAM"]
[null,"(Refer to detailed aspects covered in the SoW and Works Information)"]
[null,"Surveying - (Supportive works for routing and drawings) ",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[null,"Prefabricated Containerized Unit and on site modifcations (interface with bulk vessels)",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[null,"Architectural, Structural steel and General Arrangment",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[null,"Integration works ",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[null,"Container Unit/Supportive works (Steelwork, Access ladders and platforms, Pipe support Plinths)",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[null,"Building Management Systems",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E",null,"REFER TO LPS AND C&I LOSS"]
[null,"Double check Building management aspects and transfer to P20F or check "]
[null,"Lighting and Small Power",{"$nulls":32},"REFER TO ELECRICAL LOSS"]
[]
[null,"Structural Earthing/Lightining Protection System",{"$nulls":32},"REFER TO ELECRICAL LOSS"]
[]
[null,"Earth Matt Connection",{"$nulls":32},"REFER TO ELECRICAL LOSS"]
[]
[null,"Fire Protection",{"$nulls":32},"REFER TO ELECRICAL LOSS"]
[]
[null,"Supportive Structures for Plumbing and Civil Services (Potable supply, Drainage, Piping )",null,"E",null,"P20E",null,"P20E","E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E","E",null,"P20E",null,"P20E",null,"P20E","E"]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = EMPLOYER (ESKOM)"]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[null,"NOTE: Eskom PLCM and relevant project phases still apply in accordance to Medupi and Eskom procedures."]

{"sheet":"LOSS P20F CVL ","index":12,"n_rows":38,"n_cols":40,"rows_kept":38,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,8],[1,10,2,10],[1,12,2,12],[1,14,2,14],[1,16,2,16],[1,18,2,18],[1,20,2,20],[1,22,2,22],[1,24,2,25],[1,27,2,27],[1,29,2,30],[1,32,2,32],[1,34,2,34],[1,36,2,37],[1,39,2,39],[36,6,36,10]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nCIVIL\n\nINTERFACE:\nHYDROGEN AND NITROGEN GENERATING PLANT\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION INFORMATION",null,"SURVEYING AND LOCATION DETAILS/SETTING OUT",null,"CONCEPTUAL/BASIC DESIGN AND REVIEW",null,null,"DETAILED DESIGN AND REVIEW",null,"FINAL DETAILED DESIGN REVIEW and DESIGN FREEZE",null,"SUBMISSION OF PERMITS,  AND QC/QA DOCUMENTATION",null,"FINAL SETTING OUT ON SITE",null,"APPROVED FOR CONSTRUCTION DRAWINGS",null,"FABRICATION, MANUFACTURE & SUPPLY",null,"CONCRETE MIX DESIGN SUBMISSION",null,"CONCRETE MIX DESIGN REVIEW",null,null,"CONSTRUCTION AND INSTALLATION",null,"CONSTRUCTION/INSTALLATION REVIEWS",null,null,"DATABOOKS AND FINAL INSPECTIONS",null,"CERTIFICATION and AS BUILT Submission",null,"HANDOVER",null,null,"REMARKS"]
[null,"LOSS-P20F-CVL"]
[null,"UPSTREAM"]
[null,"(Refer to detailed aspects covered in the SoW and Works Information)"]
[null,"Surveying - (Topographical, Layouts, Supportive works for routing and drawings, Surveying verification during the project) ",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[null,"Designs (Architectural, Concrete, Structural steel and General Arrangment )",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[null,"Concrete works (Bulk vessel blast walls, Container unit support slab/foundation, Support plinths, Apron slabs, Road-crossing Trenches)",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[null,"Integration works ",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"Check this with TM"]
[]
[null,"Supportive Infrastructure (Geotechnical works, Roadways, Perimeter/safety Fence)",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"Align to "]
[]
[null,"Other Building/Superstructures (Covered structures for bulk tank loading, Sheltered Canopy for Container unit)",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[null,"Electrical Cabling from Substation building",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[null,"Building Management Systems",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"REFER TO LPS AND C&I LOSS"]
[]
[null,"Lighting and Small Power",{"$nulls":37},"REFER TO ELECRICAL LOSS"]
[]
[null,"Structural Earthing/Lightning Protection System",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"REFER TO ELECRICAL LOSS"]
[]
[null,"Earth Matt Connection",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"REFER TO ELECRICAL LOSS"]
[]
[null,"Fire Protection (Passive and Active)",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E",null,"REFER TO ELECRICAL/MECHANICAL/LPS LOSS"]
[]
[null,"Supportive Civil Services/Structures for Plumbing and Civil Services (Potable supply, Drainage, Piping )",null,"E",null,"P20F",null,"P20F","E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F","E",null,"P20F",null,"P20F",null,"P20F","E"]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = EMPLOYER (ESKOM)"]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE WORKS with other P20 Contractors"]
[null,"NOTE: Eskom PLCM and relevant project phases still apply in accordance to Medupi and Eskom procedures."]

{"sheet":"LOSS P20E ELEC","index":13,"n_rows":44,"n_cols":30,"rows_kept":44,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[41,13,41,18],[42,4,42,9],[43,13,43,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nELECTRICAL\n\nINTERFACE:\nH2 GENERATING PLANT\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E-ELEC"]
[null,"UPSTREAM"]
[]
[]
[null,"400V POWER DISTRIBUTION",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
{"$rows_empty":8}
[null,"POWER CABLE TRENCHING AND SLEEVES",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Cable must be Ex rated cable"]
[]
[null,"400V POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"H2/N2 GENERATING PLANT SWITCHGEAR",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"Switchgear must be Ex rated"]
[]
[]
[null,"RACKING TO PLANT",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":10}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = EMPLOYER (ESKOM)",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F ELEC","index":14,"n_rows":44,"n_cols":30,"rows_kept":44,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[41,15,41,20],[42,4,42,9],[43,15,43,20]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nELECTRICAL\n\nINTERFACE:\nN2 GENERATING PLANT\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-ELEC"]
[null,"UPSTREAM"]
[]
[]
[null,"400V POWER DISTRIBUTION",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
{"$rows_empty":8}
[null,"POWER CABLE TRENCHING AND SLEEVES",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Cable must be Ex rated cable"]
[]
[null,"400V POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"H2/N2 GENERATING PLANT SWITCHGEAR",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Switchgear must be Ex rated"]
[]
[]
[null,"RACKING TO PLANT",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":10}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = EMPLOYER (ESKOM)",{"$nulls":13},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":15},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E&P20F( PLC + DCS)","index":15,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,15,63,20],[64,4,64,9],[65,15,65,20]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\n\nPLC AND DCS INTERFACE\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E&P20F-PLC+DCS"]
[null,"UPSTREAM"]
[]
[null,"BOP"]
[null,"DCS CONTROL SYSTEM                                  ",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
{"$rows_empty":11}
[null,"BUS CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"FOR H2 PLANT"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"FOR N2 PLANT"]
[]
[]
[]
[null,"HARDWIRED CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"FOR H2 PLANT"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"FOR N2 PLANT"]
{"$rows_empty":7}
[{"$nulls":3},"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"FOR H2 PLANT"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"FOR N2 PLANT"]
[null,"P20 PLC"]
[null,"CONTROL SYSTEM"]
[]
[]
[]
[]
[null,"CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"FOR H2 PLANT"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"FOR N2 PLANT"]
[]
[]
[]
[{"$nulls":3},"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"FOR H2 PLANT"]
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"FOR N2 PLANT"]
[null,"LOCAL CONTROL STATION"]
{"$rows_empty":12}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":13},"REVISION :",{"$nulls":5},2]
[null,"P20E = H2 CONTRACTOR-GENERATING UNIT"]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C",{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E FM5","index":16,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,13,63,18],[64,4,64,9],[65,13,65,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\n\nFLOW MEASUREMENT\nIn-line type\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E-FM5"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL SYSTEM",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":10}
[null,"TRUNK CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":13}
[null,"JUNCTION BOX",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"POWER DISTRIBUTION",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"INSTRUMENT CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"POWER CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[null,"TRANSDUCER  &  "]
[null," SUPPORTING  RACK",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[null,"INSTRUMENT CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"If separate from primary device"]
[]
[]
[]
[]
[]
[]
[null," FLOW METER ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F FM5","index":17,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,13,63,18],[64,4,64,9],[65,13,65,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\n\nFLOW MEASUREMENT\nIn-line type\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-FM5"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL SYSTEM",null,"E",null,"E",null,"E",null,"E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E&P20F"]
{"$rows_empty":10}
[null,"TRUNK CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":13}
[null,"JUNCTION BOX",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"POWER DISTRIBUTION",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"INSTRUMENT CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"TRANSDUCER  &  "]
[null," SUPPORTING  RACK",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"INSTRUMENT CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"If separate from primary device"]
[]
[]
[]
[]
[]
[]
[null," FLOW METER ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E PM1","index":18,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,13,63,18],[64,4,64,9],[65,13,65,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\nPRESSURE MEASUREMENT AND/OR SWITCH (PRESSURE TRANSDUCER)\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E-PM1"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL  SYSTEM",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":9}
[null,"TRUNK CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":10}
[null,"JUNCTION BOX",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[]
[null,"FIELD CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[]
[]
[null,"TRANSDUCER & ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"SUPORTING  RACK"]
[]
[null,"TRANSDUCER ISOLATING ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"VALVE"]
[]
[]
[null,"IMPULSE PIPING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[]
[null,"FIRST SHUT-OFF VALVE ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"TAPPING POINT ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F PM1","index":19,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,13,63,18],[64,4,64,9],[65,13,65,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\nPRESSURE MEASUREMENT AND/OR SWITCH (PRESSURE TRANSDUCER)\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20-PM1"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL  SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":9}
[null,"TRUNK CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":10}
[null,"JUNCTION BOX",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[]
[null,"FIELD CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[]
[]
[null,"TRANSDUCER & ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"SUPORTING  RACK"]
[]
[null,"TRANSDUCER ISOLATING ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"VALVE"]
[]
[]
[null,"IMPULSE PIPING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[]
[null,"FIRST SHUT-OFF VALVE ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",{"$nulls":3},"1/2 inch BSP tapered"]
[]
[null,"TAPPING POINT ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",{"$nulls":3},"1/2 inch BSP tapered"]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E PM4","index":20,"n_rows":65,"n_cols":30,"rows_kept":65,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[62,13,62,18],[63,4,63,9],[64,13,64,18]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\nPRESSURE MEASUREMENT (PRESSURE GAUGE) \n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E-PM4"]
[null,"UPSTREAM"]
[]
[null,"PRESSURE GAUGE",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"INSTRUMENT ISOLATION VALVE",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"IMPULSE PIPING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"PRODUCT ISOLATION VALVE ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"1/2 inch BSP tapered"]
[]
[null,"TAPPING POINT ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"1/2 inch BSP tapered"]
{"$rows_empty":45}
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":11},"REVISION :",{"$nulls":5},2]
[null,"P20E = H2 CONTRACTOR-GENERATING UNIT"]
[{"$nulls":13},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F PM4","index":21,"n_rows":65,"n_cols":30,"rows_kept":65,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[62,14,62,19],[63,4,63,9],[64,14,64,19]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\nPRESSURE MEASUREMENT (PRESSURE GAUGE) \n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-PM4"]
[null,"UPSTREAM"]
[]
[null,"PRESSURE GAUGE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"INSTRUMENT ISOLATION VALVE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"IMPULSE PIPING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"PRODUCT ISOLATION VALVE ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"1/2 inch BSP tapered"]
[]
[null,"TAPPING POINT ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"1/2 inch BSP tapered"]
{"$rows_empty":45}
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)",{"$nulls":12},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":14},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E BV1","index":22,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,12,63,17],[64,4,64,9],[65,12,65,17]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\n400V AC ELECTRICAL ACTUATED BINARY VALVE WITH INTEGRATED SWITCHGEAR\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-BV1"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL SYSTEM",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":10}
[{"$nulls":3},"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[null,"TRUNK CABLING"]
[]
[]
[]
[]
[null,"MCB SUPPLY",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":12}
[null,"POWER CABLING",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
{"$rows_empty":8}
[null,"SPLITTER BOX",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[null,"FLY LEEDS ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"ACTUATOR WITH FEEDBACKS",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"LINKAGE ",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[null,"VALVE",null,"P20E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E"]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":10},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":12},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F BV1","index":23,"n_rows":66,"n_cols":30,"rows_kept":66,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[63,11,63,16],[64,4,64,9],[65,11,65,16]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\n400V AC ELECTRICAL ACTUATED BINARY VALVE WITH INTEGRATED SWITCHGEAR\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-BV1"]
[null,"UPSTREAM"]
[]
[]
[null,"CONTROL SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":10}
[{"$nulls":3},"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[null,"TRUNK CABLING"]
[]
[]
[]
[]
[null,"MCB SUPPLY",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":12}
[null,"POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":8}
[null,"SPLITTER BOX",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"FLY LEEDS ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"ACTUATOR WITH FEEDBACKS",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"LINKAGE ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"VALVE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   ",{"$nulls":9},"REVISION :",{"$nulls":5},2]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":11},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20E BV2","index":24,"n_rows":70,"n_cols":30,"rows_kept":70,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[65,4,65,9],[69,4,69,9],[69,15,69,19],[72,4,72,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nH2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\n24V DC SOLENOID OPERATED BINARY VALVE\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20E-BV2"]
[null,"UPSTREAM"]
[]
[]
[]
[null,"CONTROL SYSTEM"]
[{"$nulls":3},"E",null,"E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
{"$rows_empty":12}
[null,"TRUNK CABLINGS"]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
{"$rows_empty":15}
[null,"JUNCTION BOX"]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
[]
[]
[]
[]
[]
[]
[null,"INSTRUMENT CABLING"]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
[]
[]
[]
[]
[null,"24V DC SOLENOID  "]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
[]
[null,"VALVE"]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C",null,null,"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F BV2","index":25,"n_rows":70,"n_cols":30,"rows_kept":70,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[65,4,65,9],[69,4,69,9],[69,15,69,19],[72,4,72,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2 PLANT\nCONTROL AND INSTRUMENTATION LOSS\n\nINTERFACE:\n24V DC SOLENOID OPERATED BINARY VALVE\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-BV2"]
[null,"UPSTREAM"]
[]
[]
[]
[null,"CONTROL SYSTEM",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
{"$rows_empty":13}
[null,"TRUNK CABLINGS",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
{"$rows_empty":16}
[null,"JUNCTION BOX",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
{"$rows_empty":7}
[null,"INSTRUMENT CABLING",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
[{"$nulls":3},"E",null,"P20E",null,"E",null,"P20E",null,"E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"P20E",null,"H2 Plant"]
[]
[]
[]
[]
[null,"24V DC SOLENOID  ",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
[]
[]
[null,"VALVE",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"N2 Plant"]
[]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C",null,null,"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F FDS","index":26,"n_rows":86,"n_cols":30,"rows_kept":86,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[81,4,81,9],[85,4,85,9],[85,15,85,23],[88,4,88,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nFIRE DETECTION SYSTEM \n\n\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-FDS"]
[null,"UPSTREAM"]
[]
[]
[null,"230 VAC MAIN POWER SUPPLY",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"CBMS",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20FF",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"POWER CABLING",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"SIGNAL CABLING",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"AREA FIRE DETECTION PANEL",null,"E",null,"E",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"SIGNAL CABLING",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"POWER CABLING",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F/E",null,"P20F/E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"LOCAL FIRE DETECTION PANEL",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"FIRE DETECTION LOOP CABLING",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":10}
[null,"OPTICAL SMOKE DETECTORS",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"OTHER LOOP DEVICES",null,"E",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
{"$rows_empty":14}
[null,"SIGNAL CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"HVAC SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Shutting down the HVAC system in the event of a fire"]
[]
[null,"SIGNAL CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"ACCESS CONTROL SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":4},"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F CCTV","index":27,"n_rows":70,"n_cols":30,"rows_kept":70,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[65,4,65,9],[69,4,69,9],[69,15,69,23],[72,4,72,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT CBMS\nCCTV MONITORING / RECORDING SYSTEM TYPE 1\n\n\n\n\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-CCTV"]
[null,"UPSTREAM"]
[]
[]
[]
[null,"230 VAC MAIN POWER SUPPLY",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[]
[null,"POWER CABLING ",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"CCTV SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Including cameras and related works"]
[]
[]
[]
[]
[]
[null,"SIGNAL BUS CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[]
[]
[null,"BUILDING MANAGEMENT SYSTEM",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[null,"REDUNDANT LOCAL NETWORK CABLE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"NETWORK INTERFACE POINT",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"CBMS NETWORK INFRASTRUCTURE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null," 24-core single mode fibre of which 2"]
[{"$nulls":29},"  will be used for this interface."]
{"$rows_empty":20}
[null,"DOWNSTREAM"]
[]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C",null,null,"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]

{"sheet":"LOSS P20F ACN1","index":28,"n_rows":70,"n_cols":30,"rows_kept":70,"merged":[[1,3,2,3],[1,5,2,5],[1,7,2,7],[1,9,2,9],[1,11,2,11],[1,13,2,13],[1,15,2,15],[1,17,2,17],[1,19,2,19],[1,21,2,21],[1,23,2,23],[1,25,2,25],[1,27,2,27],[1,29,2,29],[65,4,65,9],[69,4,69,9],[69,15,69,23],[72,4,72,9]],"flags":["formulas_cached_only"]}
[]
[null,"MEDUPI POWER STATION\nN2H2 PLANT\nACCESS CONTROL NETWORK\n\n\nINTERFACE:\nDESCRIPTION\n\n\nLIMITS OF SUPPLY AND SERVICES",null,"FUNCTIONAL SPECIFICATION",null,"CONCEPTUAL DESIGN",null,"DESIGN REVIEW",null,"DETAILED DESIGN",null,"DESIGN REVIEW",null,"SYSTEM ENGINEERING",null,"LOCATION DETAILS/SET OUT POINT",null,"CONNECTION DETAILS",null,"DESIGTN FREEZE",null,"PRODUCTION ENGINEERING",null,"MANUFACTURE & SUPPLY",null,"CONSTRUCTION/INSTALLATION",null,"COMMISSIONING",null,"REMARKS"]
[null,"LOSS-P20F-ACN1"]
[null,"UPSTREAM"]
[]
[]
[null,"CBMS FIBRE NETWORK",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[]
[null,"PATCH PANEL",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[null,"FIBRE OPTIC CABLE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"CBMS NETWORK INTERFACE",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Including Copper to Fibre Converter"]
[]
[]
[null,"TCP/IP NETWORK CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"UPS",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E",null,"E"]
[]
[null,"POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"PSU",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[{"$nulls":11},"E"]
[null,"POWER CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",{"$nulls":3},"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[null,"ACCESS CONTROL SERVER",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[]
[null,"LON NETWORK CABLING",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F"]
[]
[]
[]
[null,"ACCESS POINT CONTROLLER",null,"P20F",null,"P20F",null,"E",null,"P20F",null,"E",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"P20F",null,"Number of access points subject to number of doors requiring controlled access"]
{"$rows_empty":24}
[null,"DOWNSTREAM"]
[]
[null,"E = ENGINEER (ESKOM)"]
[null,"P20E =  Hydrogen Generating Unit- Purchase and commissioning of Hydrogen Generating Unit   "]
[null,"P20F = H2N2 CONTRACTOR-INTEGRATED SCOPE-CONSTRUCTION, COMMISSIOING AND INTEGRATE OF SCOPE C"]
[{"$nulls":4},"REVISION :",{"$nulls":5},2]
[]
[]
[]
[{"$nulls":4},"DATE :",{"$nulls":5},"20/08/2025"]