1

REQUEST FOR QUOTATION (RFQ)

RFQ NUMBER: [……10342676………………]

REQUEST FOR QUOTATION (RFQ) FOR THE REFURBISHMENT AND UPGRADE OF LEVEL CROSSINGS IN THE WESTERN CAPE METRORAIL REGION

1

SECTION 1: SBD1

PART A INVITATION TO BID

| YOU ARE HEREBY INVITED TO BID FOR REQUIREMENTS OF PASSENGER RAIL AGENCY (PRASA) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BID NUMBER: | …10342676……………. |  |  |  | CLOSING DATE: |  |  |  | …18/09/2023……… |  | CLOSING TIME: |  |  | 12H00 |
| DESCRIPTION | REFURBISHMENT AND UPGRADE OF LEVEL CROSSINGS IN THE WESTERN CAPE METRORAIL REGION |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BID RESPONSE DOCUMENTS SHALL BE ADDRESSED AS FOLLOWS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BID RESPONSE DOCUMENTS MAY BE DEPOSITED IN THE BID BOX SITUATED AT (STREET ADDRESS): 1 ADDERLEY STREET METRORAIL SUPPLY CHAIN MANAGEMENT 6TH FLOOR, ROOM 622 PROPNET BUILDING CAPE TOWN Please note: All Submissions must be Manual Drop in the Tender Box or Hand delivery) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BIDDING PROCEDURE ENQUIRIES MAY BE DIRECTED TO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTACT PERSON |  |  |  | Bonwell Booi |  |  |  |  |  |  |  |  |  |  |
| TELEPHONE NUMBER |  |  |  | (021) 837-7945 |  |  |  |  |  |  |  |  |  |  |
| E-MAIL ADDRESS |  |  |  | Bonwell.booi@prasa.com |  |  |  |  |  |  |  |  |  |  |
| SUPPLIER INFORMATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME OF BIDDER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| POSTAL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STREET ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TELEPHONE NUMBER |  |  | CODE |  |  |  |  |  | NUMBER |  |  |  |  |  |
| CELLPHONE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FACSIMILE NUMBER |  |  | CODE |  |  |  |  |  | NUMBER |  |  |  |  |  |
| E-MAIL ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VAT REGISTRATION NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUPPLIER COMPLIANCE STATUS |  |  | TAX COMPLIANCE S:YSTEM PIN: |  |  |  |  | OR |  | CENTRAL SUPPLIER DATABA SE No: |  |  | MAAA…………….. |  |
| - ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS /SERVICES /WORKS OFFERED? |  | Yes No [IF YES ENCLOSE PROOF] |  |  |  |  | - ARE YOU A FOREIGN BASED SUPPLIER FOR THE GOODS /SERVICES /WORKS OFFERED? |  |  |  |  | Yes No [IF YES, ANSWER THE QUESTIONNAIRE BELOW ] |  |  |
| QUESTIONNAIRE TO BIDDING FOREIGN SUPPLIERS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IS THE ENTITY A RESIDENT OF THE REPUBLIC OF SOUTH AFRICA (RSA)? YES NO DOES THE ENTITY HAVE A BRANCH IN THE RSA? YES NO DOES THE ENTITY HAVE A PERMANENT ESTABLISHMENT IN THE RSA? YES NO DOES THE ENTITY HAVE ANY SOURCE OF INCOME IN THE RSA? YES NO IS THE ENTITY LIABLE IN THE RSA FOR ANY FORM OF TAXATION? YES NO IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN IT IS NOT A REQUIREMENT TO REGISTER FOR A TAX COMPLIANCE STATUS SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 BELOW. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PART B: TERMS AND CONDITIONS FOR BIDDING

- BID SUBMISSION:

- BIDS MUST BE DELIVERED BY THE STIPULATED TIME TO THE CORRECT ADDRESS. LATE BIDS WILL NOT BE ACCEPTED FOR CONSIDERATION. - ALL BIDS MUST BE SUBMITTED ON THE OFFICIAL FORMS PROVIDED–(NOT TO BE RE-TYPED) OR IN THE MANNER - PRESCRIBED IN THE BID DOCUMENT. - THIS BID IS SUBJECT TO THE PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT, 2000 AND THE PREFERENTIAL PROCUREMENT REGULATIONS, 2022, THE GENERAL CONDITIONS OF CONTRACT (GCC) AND, IF APPLICABLE, ANY OTHER SPECIAL CONDITIONS OF CONTRACT.

- TAX COMPLIANCE REQUIREMENTS

- BIDDERS MUST ENSURE COMPLIANCE WITH THEIR TAX OBLIGATIONS. - BIDDERS ARE REQUIRED TO SUBMIT THEIR UNIQUE PERSONAL IDENTIFICATION NUMBER (PIN) ISSUED BY SARS TO ENABLE THE ORGAN OF STATE TO VERIFY THE TAXPAYER’S PROFILE AND TAX STATUS. - APPLICATION FOR TAX COMPLIANCE STATUS (TCS) PIN MAY BE MADE VIA E-FILING THROUGH THE SARS WEBSITE WWW.SARS.GOV.ZA. - BIDDERS MAY ALSO SUBMIT A PRINTED TCS CERTIFICATE TOGETHER WITH THE BID. - IN BIDS WHERE CONSORTIA / JOINT VENTURES / SUB-CONTRACTORS ARE INVOLVED, EACH PARTY MUST SUBMIT A SEPARATE TCS CERTIFICATE / PIN / CSD NUMBER. - WHERE NO TCS PIN IS AVAILABLE BUT THE BIDDER IS REGISTERED ON THE CENTRAL SUPPLIER DATABASE (CSD), A CSD NUMBER MUST BE PROVIDED. - NO BIDS WILL BE CONSIDERED FROM PERSONS IN THE SERVICE OF THE STATE, COMPANIES WITH DIRECTORS WHO ARE PERSONS IN THE SERVICE OF THE STATE, OR CLOSE CORPORATIONS WITH MEMBERS PERSONS IN THE SERVICE OF THE STATE.”

NB: FAILURE TO PROVIDE / OR COMPLY WITH ANY OF THE ABOVE PARTICULARS MAY RENDER THE BID NVALID.

SIGNATURE OF BIDDER:					……………………………………………

CAPACITY UNDER WHICH THIS BID IS SIGNED:		……………………………………………

(Proof of authority must be submitted e.g. company resolution)

DATE:								…………………………………………...

NB:

- Quotation(s) must be addressed to PRASA before the closing date and time shown above.

- PRASA General Conditions of Purchase shall apply.

SECTION 2

NOTICE TO BIDDERS

# Responses to RFQ

Responses to this RFQ [Quotations] must not include documents or reference relating to any other quotation or proposal. Any additional conditions must be embodied in an accompanying letter.

Proposals must reach the PRASA before the closing hour on the date shown on SBD1 above, and must be enclosed in a sealed envelope.

# Communication

Respondent/s are warned that a response will be liable for disqualification should any attempt be made either directly or indirectly to canvass any SCM Officer(s) or PRASA employee in respect of this RFQ between the closing date and the date of the award of the business.

# BIDDERS COMPLAINTS PROCESS

# Bidders are advised utilize this email address (SCM.Complaints@prasa.co.za) for lodging of complains to PRASA in relation to this bid process. The following minimum information about the bidder must be included in the complaint:

    - Bid/Tender Description

    - Bid/Tender Reference Number

    - Closing date of Bid/Tender

    - Supplier Name;

    - Supplier Contact details

    - The detailed compliant

# Legal Compliance

The successful Respondent shall be in full and complete compliance with any and all applicable national and local laws and regulations.

# Changes to Quotations

Changes by the Respondent to its submission will not be considered after the closing date and time.

# Pricing

All prices must be quoted in South African Rand on a fixed price basis, including all applicable taxes.

# Binding Offer

Any Quotation furnished pursuant to this Request shall be deemed to be an offer. Any exceptions to this statement must be clearly and specifically indicated.

# Disclaimers

# PRASA is not committed to any course of action as a result of its issuance of this RFQ and/or its receipt of a Quotation in response to it. Please note that PRASA reserves the right to:

# Modify the RFQ’s goods / service(s) and request Respondents to re-bid on any changes;

# Reject any Quotation which does not conform to instructions and specifications which are detailed herein;

# Reject Quotations submitted after the stated submission deadline or at the incorrect venue ;

## Should a contract be awarded on the strength of information furnished by the Respondent, which after conclusion of the contract, is proved to have been incorrect, PRASA reserves the right to cancel the contract.

## PRASA reserves the right to award business to the highest scoring bidder/s unless objective criteria justify the award to another Respondent.

## Should the preferred fail to sign or commence with the contract within a reasonable period after being requested to do so, PRASA reserves the right to award the business to the next highest ranked Respondent provided that he/she is still prepared to provide the required goods at the quoted price.

# LEGAL REVIEW

Proposed contractual terms and conditions submitted by a Respondent will be subjected to review and acceptance or rejection by PRASA’s Legal Counsel, prior to consideration for an award of business.

# NATIONAL TREASURY’S CENTRAL SUPPLIER DATABASE

# Respondents are required to self-register on National Treasury’s Central Supplier Database (CSD) which has been established to centrally administer supplier information for all organs of state and facilitate the verification of certain key supplier information. PRASA is required to ensure that price quotations are invited and accepted from prospective bidders listed on the CSD. Business may not be awarded to a respondent who has failed to register on the CSD.  Only foreign suppliers with no local registered entity need not register on the CSD. The CSD can be accessed at https://secure.csd.gov.za/.

# PROTECTION OF PERSONAL DATA

In responding to this bid, PRASA acknowledges that it may obtain and have access to personal data of the Respondents. PRASA agrees that it shall only process the information disclosed by Respondents in their response to this bid for the purpose of evaluating and subsequent award of business and in accordance with any applicable law.

Furthermore, PRASA will not otherwise modify, amend or alter any personal data submitted by Respondents or disclose or permit the disclosure of any personal data to any Third Party without the prior written consent from the Respondents. Similarly, PRASA requires Respondents to process any personal information disclosed by PRASA in the bidding process in the same manner.

- EVALUATION METHODOLOGY

PRASA will utilise the following criteria [not necessarily in this order] in choosing a Supplier/Service Provider, if so required:

| EVALUATION CRITERIA | WEIGHTING |
| --- | --- |
| Stage 1 – Compliance |  |
| Stage 1A | Mandatory Requirements |
| Stage 1B | Other Mandatory Requirements |
| Stage 2 |  |
| Technical/Functional Requirements | Threshold of 70% |
| Stage 3 |  |
| Price | 80 |
| Specific Goals | 20 |
| TOTAL | 100 |

- ADMINISTRATIVE RESPONSIVENESS

The test for administrative responsiveness will include completeness of response and whether all returnable and/or required documents, certificates; verify completeness of warranties and other bid requirements and formalities have been complied with. Incomplete Bids will be disqualified.

- Validity Period

  - PRASA requires a validity period of …………60……………….Working Days from the closing date.

  - Respondents are to note that they may be requested to extend the validity period of their response, on the same terms and conditions, if the internal processes are not finalized within the validity period.   However, once the delegated authority has approved the process the validity of the successful respondent(s)’ bid will be deemed to remain valid until finalization of the of  award.),

- PUBLICATION OF INFORMATION ON THE National Treasury e-tender portal

# Respondents are to note that, bid awards, amendments and cancellations will be published on the e-tender portal and or media used to advertise the bid. For the award of business, PRASA is required to publish the prices and preferences claimed of the successful and unsuccessful Respondents inter alia on the National Treasury e-Tender Publication Portal, (www.etenders.gov.za), on CIDB website for construction related RFQ’s. (Where applicable).

- Returnable Documents

Returnable Documents means all the documents, Sections and Annexures, as listed in the tables below. There are three types of returnable documents as indicated below and Respondents are urged to ensure that these documents are returned with the quotation based on the consequences of non-submission as indicated below:

# 15.1. Mandatory Returnable Documents

Failure to provide Mandatory Returnable Documents at the Closing Date and time of this RFQ will result in a Respondent’s disqualification. Respondents are therefore urged to ensure that all documents are returned with their Quotations.

SECTION 3

- EVALUATION CRITERIA:

Bidders are to comply with the following requirements and failure to comply may lead to disqualification.

Stage 1A – Mandatory Requirements

If you do not submit/meet the following mandatory documents/requirements, your bid will be automatically disqualified.

Only bidders who comply with stage 1A will be evaluated further.

| No. | Description of requirement |  |
| --- | --- | --- |
| a) | Completion of ALL RFP documentation (includes ALL declarations) |  |
| b) | Briefing Session Form D. Bidders must also reflect on the Compulsory Briefing Session Attendance Register (Delete if not applicable) | Applicable |
| c) | Joint Venture, Consortium Agreement or Partnering Agreement signed by all parties. The agreement should indicate the leading bidder where applicable. (Delete if not applicable) |  |
| d) | Proof of CIDB grading …3CE…. or higher (Delete if not applicable) | Applicable |

Stage 1B –Other Mandatory Requirements

If you do not submit/meet the following mandatory documents/requirements, PRASA may request the bidder to submit the information within five (5) working days. Should this information not be provided, your bid proposal will be disqualified.

Only bidders who comply with stage 1B will be evaluated further.

| No. | Description of requirement |  |
| --- | --- | --- |
| a) | Letter of Good Standing: COID. (Delete if not applicable) |  |
| b) | Supply of valid SARS Pin |  |
| c) | CSD supplier registration number |  |
| d) | Engineering Technician with proof of National Diploma in Civil Engineering |  |

  - Stage 2

Technical / Functionality Requirements

Scoring of Functionality:

The minimum threshold for the Technical/functionality criteria is (70%) and bidders who score below this minimum will not be considered for further evaluation in terms of price and Specific Goals.

| CRITERIA | WEIGHT | SCORES |
| --- | --- | --- |
| - PREVIOUS COMPANY EXPERIENCE Supply evidence of previous company experience of previous projects of a similar nature i.e. road construction and/or road maintenance for the past seven years. The evidence shall be in the form of contactable reference letters. Attached reference letter template can be used. The reference letter must be sent to the company/business where services were previously rendered for. Should the bidder be in possession of an existing letter, the letter shall cover all aspects listed outlined below. - Previous client and completed works / services information - Name of the organisation - Summary and description of works/ goods/ services that were provided - Year - Duration - Evaluation of service Provider’s performance - Were the work/ service/ product completed/delivered on time - Did the work/ service/ product meet the expected and specified quality | Excellent; 5. Very Good; 4. Good; 3. Average; 2. Poor; 1. Not Submitted; 0. | 20 |
| - Civil Engineering Technician Civil Engineering Technician is required. CV’s to be submitted detailing work experience as a Civil Engineering Technician in any rail and/or road construction/road maintenance projects. NOTE: The bidder will be given the lowest score if : - CV submitted does not meet the minimum required years of experience. - NO CV is submitted. | More than 7 years of experience; 5. Between 6 – 7 (inclusive) years of experience; 4. Between 5 - 6 (inclusive) years of experience; 3. Between 3 - 5 (inclusive) years of experience; 2. Less than 3 years of experience; 1. No qualification or CV provided; 0. | 50 |
| Site Foreman Experienced Site Foreman is required. CV to be submitted detailing work experience as a Site Foreman in road construction/road maintenance with contactable references. NOTE: The bidder will be given the lowest score if : - CV submitted does not meet the minimum required years of experience. - NO CV is submitted | More than 7 years of experience; 5. Between 6 – 7 (inclusive) years of experience; 4. Between 4 - 5 (inclusive) years of experience; 3. Between 2 - 3 (inclusive) years of experience; 2. Less than 2 years of experience; 1. No qualification or CV provided; 0. | 30 |

FUNCTIONAL EVALUATION CRITERIA

Details of the scoring methodology presented above are outlined in the table below1

|  | Quality Criteria Experience of personnel | Indicators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 - Not Submitted (0) | 1 – Poor (4) | 2 – Average (8) | 3 - Good (12) | 4 - Very Good (16) | 5 – Excellent (20) |
| 1 | Previous Company / Organisational Experience: Supply evidence of previous company experience of previous projects of a similar nature i.e. road construction and/or road maintenance for the past seven years. The evidence shall be in the form of contactable reference letters The reference letter must address the below items. Attached is a reference letter template that can be used. The reference letter must be sent to the company/business where services were previously rendered for. Should the bidder be in possession of an existing letter, the letter shall cover all aspects listed outlined below. A. Previous client and Completed works/services Information - Name of the organisation. - Summary and Description of works/goods/services that were provided. - Year. - Iv. Duration. B. Evaluation of service - Provider’s performance - Were the work/service/ Product completed/ Delivered within the Stipulated Timeframes. - Were the work/service/ product meet the expected and specified quality | No evidence submitted | Less than or equal to one project completed with one relevant reference letter. Note: The reference letter must be signed and stamped by the company/business where the services were previously rendered and comply with the two listed criteria. If the reference letter does not feature all criteria, then that bidder will be given the lowest score. | Two projects successfully completed with two relevant reference letters Note: The reference letter must be signed and stamped by the company/business where the services were previously rendered and comply with the two listed criteria. If the reference letter does not feature all criteria, then that bidder will be given the lower score. | Three projects successfully completed with three relevant reference letters Note: The reference letter must be signed and stamped by the company/business where the services were previously rendered and comply with the two listed criteria. If the reference letter does not feature all criteria, then that bidder will be given the lower score. . | Four projects successfully completed with four relevant reference letters Note: The reference letter must be signed and stamped by the company/business where the services were previously rendered and comply with the two listed criteria. If the reference letter does not feature all criteria, then that bidder will be given the lower score. | Five or more projects successfully completed with five or more relevant reference letters Note: The reference letter must be signed and stamped by the company/business where the services were previously rendered and comply with the two listed criteria. If the reference letter does not feature all criteria, then that bidder will be given the lower score. |
| 2.2 | ENGINEERING TECHNICIAN | 0 - Not Submitted (0) | 1 – Poor (10) | 2 – Average (20) | 3 - Good (30) | 4 - Very Good (40) | 5 – Excellent (50) |
|  | Civil Engineering Technician Civil Engineering Technician is required. CV’s to be submitted detailing work experience as a Civil Engineering Technician in any rail and/or road construction/road maintenance projects. NOTE: The bidder will be given the lowest score if: - CV submitted does not meet the minimum required years of experience. - NO CV is submitted. | No qualification or CV provided | CV submitted with less than 3 years of experience | CV submitted with 3 to 5 (inclusive) years of experience. | CV submitted with 5 to 6 (inclusive) years of experience | CV submitted with 6 to 7 (inclusive) years of experience | CV submitted with more than 7 years of experience. |
| 2.3 | SITE FOREMAN | 0 - Not Submitted (0) | 1 – Poor (10) | 2 – Average (15) | 3 - Good (20) | 4 - Very Good (25) | 5 – Excellent (30) |
|  | Experienced Site Foreman is required. CV to be submitted detailing work experience as a Site Foreman in road construction/road maintenance with contactable references. NOTE: The bidder will be given the lowest score if : - CV submitted does not meet the minimum required years of experience. - NO CV is submitted | No qualification or CV provided | CV submitted with less than 2 years of experience | CV submitted with 2 to 3 (inclusive) years of experience | CV submitted with 4 to 5 (inclusive) years of experience | CV submitted with 6 to 7 (inclusive) years of experience | More than 7 years of experience |

  - Stage 3- Price and Specific Goals

The following formula, shall be used to allocate scores to the interested bidders :

The maximum points for this tender are allocated as follows:

| DETAILS | POINTS |
| --- | --- |
| PRICE | 80 |
| SPECIFIC GOALS | 20 |
| TOTAL POINTS FOR PRICE AND SPECIFIC GOALS | 100 |

FORMULAE FOR PROCUREMENT OF GOODS AND SERVICES

POINTS AWARDED FOR PRICE

THE 80/20 PREFERENCE POINT SYSTEMS

A maximum of 80 points is allocated for price on the following basis:

80/20

PS = 80 1-Pt-PminPmin

Where

Ps = Points scored for price of tender under consideration

Pt = 	Price of tender under consideration

Pmin = Price of lowest acceptable tender

POINTS AWARDED FOR SPECIFIC GOALS

  - In terms of Regulation 4(2); 5(2); 6(2) and 7(2) of the Preferential Procurement Regulations, preference points must be awarded for specific goals stated in the tender. For the purposes of this tender the tenderer will be allocated points based on the goals stated in table 1 below as may be supported by proof/ documentation stated in the conditions of this tender:

Table 1: Specific goals for the tender and points claimed are indicated per the table below.

Note to tenderers: The tenderer must indicate how they claim points for each preference point system.)

| The specific goals allocated points in terms of this tender | ACCEPTABLE EVIDENCE | Number of points allocated (80/20 system) (To be completed by the organ of state) | Number of points claimed (80/20 system) (To be completed by the tenderer |
| --- | --- | --- | --- |
| Level 2 or Level 1 B-BBEE status | B-BBEE Certificate/ Affidavit (in case of JV,a consolidated score card will be accepted ) showing a Level 2 or Level 1 | 4 |  |
| Black youth owned | Certified copy of I.D Documents of the Owners | 4 |  |
| 51% Black Owned | CIPC Documents / B-BBEE Certificate / Affidavit | 4 |  |
| Black women owned | Certified copy of I.D Documents of the Owners | 4 |  |
| EME or QSE 51% black owned | Audited Annual Financial/ B-BBEE Certificate / Affidavit | 4 |  |

SECTION 4

PRICING AND DELIVERY SCHEDULE

Respondents are required to complete the attached Pricing Schedule Annexure: page 38/39

- Prices must be quoted in South African Rand, inclusive of all applicable taxes.

- Price offer is firm and clearly indicate the basis thereof.

- Pricing Bill of Quantity is completed in line with schedule if applicable.

- Cost breakdown must be indicated.

- Price escalation basis and formula must be indicated.

- To facilitate like-for like comparison bidders must submit pricing strictly in accordance with this price schedule and not utilise a different format. Deviation from this pricing schedule could result in a bid being declared non-responsive.

- Please note that should you have offered a discounted price(s), PRASA will only consider such price discount(s) in the final evaluation stage on an unconditional basis.

- Respondents are to note that if price offered by the highest scoring bidder is not market related, PRASA may not award the contract to the Respondent. PRASA may:

- negotiate a market-related price with the Respondent scoring the highest points;

- if that Respondent does not agree to a market-related price, negotiate a market-related price with the Respondent scoring the second highest points;

- if the Respondent scoring the second highest points does not agree to a market-related price, negotiate a market-related price with the Respondent scoring the third highest points;

- If a market-related price is not agreed with the Respondent scoring the third highest points, PRASA must cancel the RFQ.

I / We ______________________________________________________________ (Insert Name of Bidding Entity) of _________________________________________________________________________________________

_____________________________________________________________________ code _________________

(Full address) conducting business under the style or title of: _________________________________________    represented by: ________________________________________________________________ in my capacity as:

____________________________________________________________________ being duly authorised, hereby offer to undertake and complete the above-mentioned work/services at the prices quoted in the bills of quantities / schedule of quantities or, where these do not form part of the contract, at a lumpsum, of                                                                  R _________________________________________________________________ (amount in numbers); _____________________________________________________________________________________________________________________________________________________________    (amount in words) Incl. VAT.

DELIVERY PERIOD: Suppliers are requested to offer their earliest delivery period possible.

Delivery will be effected within …………. working days from date of order. (To be completed by Service provider)

SECTION 5

# PRASA GENERAL CONDITIONS OF PURCHASE

# General

PRASA and the Supplier enter into an order/contract on these conditions to supply the items (goods/services/works) as described in the order/contract.

## Conditions

These conditions form the basis of the contract between PRASA and the Supplier.  Notwithstanding anything to the contrary in any document issued or sent by the Supplier, these conditions apply except as expressly agreed in writing by PRASA.

No servant or agent of PRASA has authority to vary these conditions orally.  These general conditions of purchase are subject to such further special conditions as may be prescribed in writing by PRASA in the order/contract.

## Price and payment

The price or rates for the items stated in the order/contract may include an amount for price adjustment, which is calculated in accordance with the formula stated in the order/contract.

The Supplier may be paid in one currency other than South African Rand.  Only one exchange rate is used to convert from this currency to South African Rand.  Payment to the Supplier in this currency other than South African Rand, does not exceed the amounts stated in the order/contract.  PRASA pays for the item within 30 days of receipt of the Suppliers correct tax invoice.

## Delivery and documents

The Supplier’s obligation is to deliver the items on or before the date stated in the order/contract.  Late deliveries or late completion of the items may be subject to a penalty if this is imposed in the order/contract. No payment is made if the Supplier does not provide the item as stated in order/contract.

Where items are to be delivered the Supplier:

Clearly marks the outside of each consignment or package with the Supplier’s name and full details of the destination in accordance with the order and includes a packing note stating the contents thereof; On dispatch of each consignment, sends to PRASA at the address for delivery of the items, an advice note specifying the means of transport, weight, number of volume as appropriate and the point and date of dispatch;  Sends to PRASA a detailed priced invoice as soon as is reasonably practical after dispatch of the items, and states on all communications in respect of the order the order number and code number (if any).

## Containers / packing material

Unless otherwise stated in the order/contract, no payment is made for containers or packing materials or return to the Supplier.

## Title and risk

Without prejudice to rights of rejection under these conditions, title to and risk in the items passes to PRASA when accepted by PRASA.

## Rejection

If the Supplier fails to comply with his obligations under the order/contract, PRASA may reject any part of the items by giving written notice to the Supplier specifying the reason for rejection and whether and within what period replacement of items or re-work are required.

In the case of items delivered, PRASA may return the rejected items to the Supplier at the Supplier’s risk and expense.  Any money paid to the Supplier in respect of the items not replaced within the time required, together with the costs of returning rejected items to the Supplier and obtaining replacement items from a third party, are paid by the Supplier to PRASA.

In the case of service, the Supplier corrects non-conformances as indicated by PRASA.

## Warranty

Without prejudice to any other rights of PRASA under these conditions, the Supplier warrants that the items are in accordance with PRASA’s requirements, and fit for the purpose for which they are intended, and will remain free from defects for a period of one year (unless another period is stated in the Order) from acceptance of the items by PRASA.

## Indemnity

The Supplier indemnifies PRASA against all actions, suits, claims, demands, costs, charges and expenses arising in connection therewith arising from the negligence, infringement of intellectual or legal rights or breach of statutory duty of the Supplier, his subcontractors, agents or servants, or from the Supplier’s defective design, materials or workmanship.

The Supplier indemnifies PRASA against claims, proceedings, compensation and costs payable arising out of infringement by the Supplier of the rights of others, except an infringement which arose out of the use by the Supplier of things provided by PRASA.

## Assignment and sub-contracting

The successful Respondent awarded the contract may only enter into a subcontracting arrangement with PRASA’s prior approval. The contract will be concluded between the successful Respondent and PRASA, therefore, the successful Respondent and not the sub-contractor will be held liable for performance in terms of its contractual obligations.

## Governing law

The order/contract is governed by the law of the Republic of South Africa and the parties hereby submit to the non-exclusive jurisdiction of the South African courts.

SECTION 6						   						SBD4

BIDDER’S DISCLOSURE

- PURPOSE OF THE FORM

Any person (natural or juristic) may make an offer or offers in terms of this invitation to bid. In line with the principles of transparency, accountability, impartiality, and ethics as enshrined in the Constitution of the Republic of South Africa and further expressed in various pieces of legislation, it is required for the bidder to make this declaration in respect of the details required hereunder.

Where a person/s are listed in the Register for Tender Defaulters and / or the List of Restricted Suppliers, that person will automatically be disqualified from the bid process.

- Bidder’s declaration

2.1 	Is the bidder, or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise,

employed by the state?						YES/NO

2.1.1	If so, furnish particulars of the names, individual identity numbers, and, if applicable, state employee numbers of sole proprietor/ directors / trustees / shareholders / members/ partners or any person having a controlling interest in the enterprise, in table below.

| Full Name | Identity Number | Name of State institution |
| --- | --- | --- |

2.2	Do you, or any person connected with the bidder, have a relationship with any person who is employed by the procuring institution? YES/NO

2.2.1     If so, furnish particulars:

……………………………………………………………………………………

……………………………………………………………………………………

2.3 	Does the bidder or any of its directors / trustees / shareholders / members / partners or any person having a controlling interest in the enterprise have any interest in any other related enterprise whether or not they are bidding for this contract?				YES/NO

    - If so, furnish particulars:

…………………………………………………………………………….

…………………………………………………………………………….

- DECLARATION

I, the undersigned, (name)……………………………………………………………………. in submitting the accompanying bid, do hereby make the following statements that I certify to be true and complete in every respect:

3.1 	I have read and I understand the contents of this disclosure;

3.2	I understand that the accompanying bid will be disqualified if this disclosure is found not to be true and complete in every respect;

3.3 	The bidder has arrived at the accompanying bid independently from, and without consultation, communication, agreement or arrangement with any competitor. However, communication between partners in a joint venture or consortium will not be construed as collusive bidding.

3.4 	In addition, there have been no consultations, communications, agreements or arrangements with any competitor regarding the quality, quantity, specifications, prices, including methods, factors or formulas used to calculate prices, market allocation, the intention or decision to submit or not to submit the bid, bidding with the intention not to win the bid and conditions or delivery particulars of the products or services to which this bid invitation relates.

3.4	The terms of the accompanying bid have not been, and will not be, disclosed by the bidder, directly or indirectly, to any competitor, prior to the date and time of the official bid opening or of the awarding of the contract.

3.5 	There have been no consultations, communications, agreements or arrangements made by the bidder with any official of the procuring institution in relation to this procurement process prior to and during the bidding process except to provide clarification on the bid submitted where so required by the institution; and the bidder was not involved in the drafting of the specifications or terms of reference for this bid.

  - I am aware that, in addition and without prejudice to any other remedy provided to combat any restrictive practices related to bids and contracts, bids that are suspicious will be reported to the Competition Commission for investigation and possible imposition of administrative penalties in terms of section 59 of the Competition Act No 89 of 1998 and or may be reported to the National Prosecuting Authority (NPA) for criminal investigation and or may be restricted from conducting business with the public sector for a period not exceeding ten (10) years in terms of the Prevention and Combating of Corrupt Activities Act No 12 of 2004 or any other applicable legislation.

I CERTIFY THAT THE INFORMATION FURNISHED IN PARAGRAPHS 1, 2 and 3 ABOVE IS CORRECT.

I ACCEPT THAT THE STATE MAY REJECT THE BID OR ACT AGAINST ME IN TERMS OF PARAGRAPH 6 OF PFMA SCM INSTRUCTION 03 OF 2021/22 ON PREVENTING AND COMBATING ABUSE IN THE SUPPLY CHAIN MANAGEMENT SYSTEM SHOULD THIS DECLARATION PROVE TO BE FALSE.

………………………………	 ..……………………………………………

Signature	                          Date

………………………………	………………………………………………

Position 	Name of bidder

# SBD 6.1

PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2022

This preference form must form part of all tenders invited.  It contains general information and serves as a claim form for preference points for specific goals.

NB:	BEFORE COMPLETING THIS FORM, TENDERERS MUST STUDY THE GENERAL CONDITIONS, DEFINITIONS AND DIRECTIVES APPLICABLE IN RESPECT OF THE TENDER AND PREFERENTIAL PROCUREMENT REGULATIONS, 2022

- GENERAL CONDITIONS

  - The following preference point systems are applicable to invitations to tender:

- the 80/20 system for requirements with a Rand value of up to R50 000 000 (all applicable taxes included); and

- the 90/10 system for requirements with a Rand value above R50 000 000 (all applicable taxes included).

  - To be completed by the organ of state

(Delete whichever is not applicable for this tender).

- The applicable preference point system for this tender is the 90/10 preference point system.

- The applicable preference point system for this tender is the 80/20 preference point system.

- Either the 90/10 or 80/20 preference point system will be applicable in this tender. The lowest/ highest acceptable tender will be used to determine the accurate system once tenders are received.

  - Points for this tender (even in the case of a tender for income-generating contracts) shall be awarded for:

- Price; and

- Specific Goals.

  - To be completed by the organ of state:

The maximum points for this tender are allocated as follows:

|  | POINTS |
| --- | --- |
| PRICE | 80 |
| SPECIFIC GOALS | 20 |
| Total points for Price and Specific Goals | 100 |

  - Failure on the part of a tenderer to submit proof or documentation required in terms of this tender to claim points for specific goals with the tender, will be interpreted to mean that preference points for specific goals are not claimed.

  - The organ of state reserves the right to require of a tenderer, either before a tender is adjudicated or at any time subsequently, to substantiate any claim in regard to preferences, in any manner required by the organ of state.

- DEFINITIONS

- “tender” means a written offer in the form determined by an organ of state in response to an invitation to provide goods or services through price quotations, competitive tendering process or any other method envisaged in legislation.

- “price” means an amount of money tendered for goods or services, and includes all applicable taxes less all unconditional discounts.

- “rand value” means the total estimated value of a contract in Rand, calculated at the time of bid invitation, and includes all applicable taxes;

- “tender for income-generating contracts” means a written offer in the form determined by an organ of state in response to an invitation for the origination of income-generating contracts through any method envisaged in legislation that will result in a legal agreement between the organ of state and a third party that produces revenue for the organ of state, and includes, but is not limited to, leasing and disposal of assets and concession contracts, excluding direct sales and disposal of assets through public auctions; and

- “the Act” means the Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000).

- FORMULAE FOR PROCUREMENT OF GOODS AND SERVICES

  - POINTS AWARDED FOR PRICE

3.1.1   THE 80/20 OR 90/10 PREFERENCE POINT SYSTEMS

A maximum of 80 or 90 points is allocated for price on the following basis:

# 80/20

Ps=801-Pt-PminPmin

Where

Ps	=	Points scored for price of tender under consideration

Pt	=	Price of tender under consideration

Pmin	=	Price of lowest acceptable tender

  - FORMULAE FOR DISPOSAL OR LEASING OF STATE ASSETS AND INCOME GENERATING PROCUREMENT

    - POINTS AWARDED FOR PRICE

A maximum of 80 or 90 points is allocated for price on the following basis:

# 80/20

Ps=801+Pt-PmaxPmax

Where

Ps	=	Points scored for price of tender under consideration

Pt	=	Price of tender under consideration

Pmax	=	Price of highest acceptable tender

- POINTS AWARDED FOR SPECIFIC GOALS

  - In terms of Regulation 4(2); 5(2); 6(2) and 7(2) of the Preferential Procurement Regulations, preference points must be awarded for specific goals stated in the tender. For the purposes of this tender the tenderer will be allocated points based on the goals stated in table 1 below as may be supported by proof/ documentation stated in the conditions of this tender:

  - In cases where organs of state intend to use Regulation 3(2) of the Regulations, which states that, if it is unclear whether the 80/20 or 90/10 preference point system applies, an organ of state must, in the tender documents, stipulate in the case of—

- an invitation for tender for income-generating contracts, that either the 80/20 or 90/10 preference point system will apply and that the highest acceptable tender will be used to determine the applicable preference point system; or

- any other invitation for tender, that either the 80/20 or 90/10 preference point system will apply and that the lowest acceptable tender will be used to determine the applicable preference point system,

then the organ of state must indicate the points allocated for specific goals for both the 90/10 and 80/20 preference point system.

Table 1: Specific goals for the tender and points claimed are indicated per the table below.

(Note to organs of state: Where either the 90/10 or 80/20 preference point system is applicable, corresponding points must also be indicated as such.

Note to tenderers: The tenderer must indicate how they claim points for each preference point system.)

| The specific goals allocated points in terms of this tender | ACCEPTABLE EVIDENCE | Number of points allocated (80/20 system) (To be completed by the organ of state) | Number of points claimed (80/20 system) (To be completed by the tenderer) |
| --- | --- | --- | --- |
| Level 2 or Level 1 B-BBEE status | B-BBEE Certificate/ Affidavit (in case of JV,a consolidated score card will be accepted ) showing a Level 2 or Level 1 | 4 |  |
| Black youth owned | Certified copy of I.D Documents of the Owners | 4 |  |
| 51% Black Owned | CIPC Documents / B-BBEE Certificate / Affidavit | 4 |  |
| Black women owned | Certified copy of I.D Documents of the Owners | 4 |  |
| EME or QSE 51% black owned | Audited Annual Financial/ B-BBEE Certificate / Affidavit | 4 |  |

DECLARATION WITH REGARD TO COMPANY/FIRM

  - Name of company/firm…………………………………………………………………….

  - Company registration number: …………………………………………………………...

  - TYPE OF COMPANY/ FIRM

Partnership/Joint Venture / Consortium

One-person business/sole propriety

Close corporation

Public Company

Personal Liability Company

(Pty) Limited

Non-Profit Company

State Owned Company

[Tick applicable box]

  - I, the undersigned, who is duly authorised to do so on behalf of the company/firm, certify that the points claimed, based on the specific goals as advised in the tender, qualifies the company/ firm for the preference(s) shown and I acknowledge that:

- The information furnished is true and correct;

- The preference points claimed are in accordance with the General Conditions as indicated in paragraph 1 of this form;

- In the event of a contract being awarded as a result of points claimed as shown in paragraphs 1.4 and 4.2, the contractor may be required to furnish documentary proof to the satisfaction of the organ of state that the claims are correct;

- If the specific goals have been claimed or obtained on a fraudulent basis or any of the conditions of contract have not been fulfilled, the organ of state may, in addition to any other remedy it may have –

  - disqualify the person from the tendering process.

  - recover costs, losses or damages it has incurred or suffered as a result of that person’s conduct.

  - cancel the contract and claim any damages which it has suffered as a result of having to make less favourable arrangements due to such cancellation.

  - recommend that the tenderer or contractor, its shareholders and directors, or only the shareholders and directors who acted on a fraudulent basis, be restricted from obtaining business from any organ of state for a period not exceeding 10 years, after the audi alteram partem (hear the other side) rule has been applied; and

  - forward the matter for criminal prosecution, if deemed necessary.

……………………………………….

SIGNATURE(S) OF TENDERER(S)

SURNAME AND NAME:	 ……………………………………………………….

DATE:			………………………………………………………

ADDRESS:		………………………………………………………

………………………………………………………

………………………………………………………

………………………………………………………

SECTION 9

CERTIFICATE OF ATTENDANCE OF COMPULSORY RFQ BRIEFING

| Request number: |  |
| --- | --- |
| Request for Proposal: | REFURBISHMENT AND UPGRADE OF LEVEL CROSSINGS IN THE WESTERN CAPE METRORAIL REGION |

Attendance

This is to certify that _____________________________________ has / have today attended the site inspection / RFQ briefing session to which this enquiry relates. THUS, DONE and SIGNED at ________________________________________________ on this _________________ day of ___________________________ ___________________________ ___________________________ for / on behalf of PRASA Designation

Acknowledgement

This is to certify that the Bidder attended the above mentioned briefing session/ site inspection and has / have acquainted himself / themselves with the Contract, Project Specification / Special Conditions, Specifications and / or Bills of Quantities / Schedule of Quantities / Schedule of Prices, together with the drawings enumerated therein, as laid down by the PRASA for the carrying out of the proposed WORKS to which the enquiry relates

THUS DONE and SIGNED at ________________________________________________ on this _________________ day of ___________________________ DULY AUTHORISED SIGNATORY(IES) WITNESSES 1. ___________________________________ 1. __________________________ 2. ___________________________________ 2. __________________________ 3. ___________________________________ 3. __________________________

SECTION 11

C3.1	DESCRIPTION OF THE WORKS

STANDARD/PROJECT SPECIFICATION

REFURBISHMENT AND UPGRADE OF LEVEL CROSSINGS IN THE WESTERN CAPE METRORAIL REGION

C3.1	DESCRIPTION OF THE WORKS

C3.1.1	Overview and extent of the works:

This contract covers refurbishment and upgrade of level crossings at various locations within Cape Metrorail region hereinafter also referred to as the “Works” and any other work arising out of or incidental to the above, or required of the contractor to the proper completion of the works in accordance with the true meaning and intent of the contract.  The crossings are divided in different categories:

C3.1.2	Location of the works

The location and extent of the site of the Works is as Metrorail Level crossings between the property boundaries of the Passenger Rail Agency of South Africa along the railway line in Cape Metrorail Region. The Contractor shall acquaint himself with the available access to the site and the condition of the road during site inspection.

| Road name | EMPAC Asset no. | Station before | Station after | KM distance (On railway) | GPS Coordinate (Lat) | GPS Coordinate (Long) |
| --- | --- | --- | --- | --- | --- | --- |
| Kenilworth Road | JK/LCR001 | Harfield Road | Kenilworth | 11.744 | -33.994856 | 18.472958 |
| Austell Road | JL/LCR001 | Heathfield | Retreat | 18.137 | -34.051183 | 18.464175 |
| White Road | JL/LCR002 | Retreat | Steenberg | 20.214 | -34.069861 | 18.463506 |
| Military Road | JL/LCR003 | Retreat | Steenberg | 20.863 | -34.075714 | 18.463731 |
| Uxbridge Road | JL/LCR004 | Lakeside | Valsbaai | 22.821 | -34.092744 | 18.464722 |
| Albertyn Road | JL/LCR005 | Valsbaai | Muizenberg | 24.085 | -34.103528 | 18.468986 |
| Essex Road (Kalkbaai entrance to Harbour) | JL/LCR006 | Kalkbaai | Clovelly | 27.679 | -34.129214 | 18.448106 |
| Belmont Road (Vishoek entrance to Harbour) | JM/LCR001 | Vishoek | Sunny Cove | 30.117 | -34.140825 | 18.431572 |
| Sarepta Road | OF/LCR001 | Sarepta | Kuilsrivier | 4.508 | -33.923278 | 18.669694 |
| Buttskop Road | OF/LCR002 | Blackheath | Meltonrose | 10.669 | -33.970083 | 18.722389 |
| Quarry/Stasie Road | OF/LCR003 | Eerste Rivier | Lynedoch | 15.017 | -34.001847 | 18.733069 |
| George Blank Road | OG/LCR015 | Stellenbosch | Du Toit | 29.394 | -33.934364 | 18.852028 |
| Kromme Rhee Road | OG/LCR020 | Koelenhof | Muldersvlei | 37.170 | -33.872917 | 18.819233 |
| Entrance/exit to Vredenheim Cellars | OG/LCR010 | Vlottenburg | Stellenbosch | 24,147 | -33,959367 | 18,805517 |

C3.1.3	Temporary works

Void

C3.2	ENGINEERING

Void

C3.3	PROCUREMENT

C3.3.1	Preferential procurement procedures

Procurement works contract shall be done in accordance with Metrorail Policies and Procedures

C3.3.2	Subcontracting

C3.4	CONSTRUCTION

C3.4.1	Applicable SANS/SANS Standards

SABS 1200: Standardized Specifications for Civil Technical Offering Works

SANS 3000 2-2-1: Technical Requirements for Engineering and Operational Standards- Track, Civil and Electrical Infrastructure – Level Crossings

C3.4.2	Applicable national and international standards

None

C3.4.3	Particular / Generic specifications

The following particular – and generic PRASA specifications are applicable to this contract:

C3.4.3.1 Particular Specification (also referred as “Project Specifications”)

Refurbishment and Upgrade of level crossings at various locations within Cape Metrorail Region

C3.4.3.2 Generic Specification (also referred as “Standard Specification)

E10 Gen – 1996 GENERAL: Specification for Railway Track Work

E7/1:  Specification for works on, over, under or adjacent to Railway lines and near High Voltage equipment (Also referred to as the SPK7/1 specification)

E.4E: Safety arrangements and procedural compliance with occupational Health and safety Act, (Act 85 of 1993) and applicable regulations

SANS 3000-2-2-1: Technical requirements for engineering and operational standards – Track Civil and Electrical Infrastructure – Level Crossings

C3.4.3.3 Discrepancy between specifications

In the event of any discrepancy between the particular specification and the generic specification the Particular specification shall prevail.

C3.4.4	Plant and materials

No material and plant will be supplied by Metrorail.

C3.4.5 Construction Equipment

The Contractor shall supply all construction equipment required for the proper execution of the Work.

C3.4.6	Existing services

Information regarding the location of known existing services will be pointed out at the time of the site inspection where possible, but Metrorail will accept no responsibility for the accuracy of this information.

Where the position of a known service cannot be determined with sufficient accuracy by visual inspection, the Contractor shall open up and make further investigation before commencing with any of his activities related to the work, so that the position of such services may be determined with sufficient accuracy. Thereafter the Contractor shall assume responsibility for all known services.

The Contractor shall take all reasonable precautions to protect existing services during his activities on the site, and any known service damaged as a result of the Contractor's operations, shall be repaired and reinstated by the Contractor or the Authority concerned, all at the expense of the Contractor and to the satisfaction of the Technical Officer.

C3.4.7	Site establishment

C3.4.7.1	 Services and facilities provided by Metrorail

No services or facilities will be provided by Metrorail.

C3.4.7.2 	Services and facilities provided by the Contractor:

- Site Storage / Camp Site

N/A

- Housing of employees

No housing of employees of the Contractor will be allowed on the property of the Passenger Rail Agency of South Africa and the Contractor shall make his own arrangements for the housing of his employees.

- Water supply, light, power etc.

The contractor shall make his own arrangements for the supply of water (for all purposes), light, power, approved portable sanitation facilities, and telephones, as required for on the site for the duration of the contract.

- Contractor’s agent and communication

The Contractor or his duly authorised agent shall at all times be in possession of a cellular phone, in working condition, so as to enable the Technical Officer to communicate with the Contractor at all times during the duration of the contract. The Contractor shall allow for this in his rates tendered for the Works.

- Site office and Accommodation for the Technical Officer

No site office will be required for the Technical Officer.

- Security

The Contractor shall provide his own security for the protection of his workmen and assets

- Tidiness of site

The contractor shall continuously clear and dispose of waste and surplus materials to maintain the site in a tidy state unless otherwise agreed with the Project Manager.

- Removal of facilities established on site

On completion of the contract the Contractor shall remove all established facilities from the site and restore the site as directed by the Technical Officer.

C3.4.8	 Occupations and Work Permits

No occupations and work permits will be granted and the contractor shall plan and execute the Work in such a manner that the safe passage of trains will not be affected. Clearances as set out in the E7/1 specification shall at all times be adhered to.

C3.4.9	 Safety Clothing

The Contractor shall supply all relevant safety clothing to all supervision and labour. The Contractor shall also supply reflective vests to all supervision and labour so that they are more visible to train drivers. No separate payment will be made for safety clothing, as the contractor shall

C3.5	MANAGEMENT

C3.5.1	Management of the Works

C3.5.1.1	Project manager and Technical Officer

The Project Manager for this contract will be the Regional Engineer Perway Maintenance, Infrastructure, Metrorail, Cape. The Technical Officer will be appointed by the Project Manager to administer the performance and the execution of the Works according to the powers and rights held by and obligations placed upon him in terms of the Contract.

C3.5.1.2	Construction programme

The contractor shall submit, within one (1) weeks of the date of acceptance of his tender, a programme of work in the form of a bar chart or as otherwise directed by the Technical Officer showing the duration, starting time and completion date of each major activity in the contract. Where the activity is ongoing and not of a one-of nature the proposed weekly production rate shall be indicated

C3.5.2	Health and Safety

C3.5.2.1	Health and Safety specifications

Most of the activities pertaining to the Works will be executed on, over, under or adjacent to Railway lines and near High Voltage equipment.

Trains will be operated on the railway lines while work is in progress.  The contractor shall at all times perform the work in such a manner that the tracks are safe for the passage of trains.

The contractor shall at all times be responsible for the safety of his personnel on the site of the works while paying special attention to the danger of them being over-run by passing trains.

The following generic (Standard) PRASA specifications are applicable to this contract:

- E7/1: Specification for works on, over, under or adjacent to Railway lines and near High Voltage equipment. (Also referred to as the E7/1 specification)

- E.4E Transnet (Jan 2004 - As adapted for PRASA): Safety arrangements and procedural compliance with the Occupational Health and Safety Act (Act 85 of 1993) and applicable Regulations. (Also referred to as the E4E specification)

C3.5.2.2	Site Access certificate

Refer Annexure 4 of the E4E specification: A Site Access Certificate will not be issued unless the following documentation has been approved by the Technical Officer:

- Health and Safety Programme

- Construction programme

- Construction Methodology

- Risk Assessment

Two (2) weeks will be allowed for submission and approval of above mentioned documents. Any delay after this two weeks which cannot be attributed to Metrorail Technical Officer, will be considered part of the contract duration. No extension of time will be granted in lieu of delays in this regard.

C3.6	ANNEXES

C3.6.1	Particular Specifications: (Also referred to as “Project Specifications”)

- Specification for Refurbishment and Upgrade of Level Crossings

C3.6.2	Manufacturer’s Specifications:

  - N/A

C3.6.3	Generic Specifications: (also referred to as “Standard Specifications)

- E10 GEN: General Specification for Railway Works

- E7/1: Specification for works on, over, under or adjacent to Railway lines and near High Voltage equipment. (Also referred to as the E7/1 specification)

- E.4E Transnet (Jan 2004 - As adapted for PRASA): Safety arrangements and procedural compliance with the Occupational Health and Safety Act (Act 85 of 1993) and applicable Regulations. (Also referred to as the E4E specification)

STANDARD/PROJECT SPECIFICATION Refurbishment and Upgrade of level crossings at various locations within Cape Metrorail region

P1	SCOPE OF WORK

The envisioned works covers the refurbishment and upgrade of level crossings at various level crossings indicated in clause C3.1.2 (location of the works) of PRASA within Western Cape Region. This will be done by:

- The breaking up, transportation and dumping of existing surface material.

- Supply and Installation of level crossing end pieces if needed

- Provision and placing of new wearing course.

- Testing - Density test and, Material Grading

- Traffic accommodation

- Painting of Road Markings

- Level crossing assessment as per the Rail Safety Regulator (RSR) requirement

P2	OCCUPATION

All refurbishment and upgrading of level crossings and related activities, shall be carried out between trains i.e. no total occupations and or work permits will be granted for this activities. If it is identified that the train/motor vehicle traffic is of such a volume that works cannot be carried out during peak, the Contractor must submit a motivation in writing. If this is approved by the Technical Officer, works will be carried out during a night occupation i.e. between 9pm and 5am.

P3 	BREAKING UP OF EXISTING SURFACE MATERIAL

The rate tendered for the breaking up of existing surface material shall allow for excavating, loading, transporting and dumping of the material at an approved disposal area. No overhaul will be paid for.

P.4	PROVISION AND LAYING OF CONCRETE-END PIECES

The contractor shall provide all precast end pieces (2100 mm x 200 mm). The Contractor shall install end pieces as per instruction of the Technical Officer. The vertical height of end pieces will at no point be more than 10mm higher than the height of the rail level.

Trenches for the precast sections shall be excavated to the required depth and all loose material shall be removed and the bottom compacted to the density required for the adjacent material. The precast sections shall be bedded on a layer of class 15/13 concrete, placed on 100 mm thick sub-base, at least 50mm thick.

P5	 RE-ALIGN AND PLACING OF E1 PATHWAY KERBS

The Contractor shall re-align and place existing E1 precast concrete kerb units that will comply with the relevant requirements of SABS 927.

The standard length of kerbs shall be one meter.

P.6	PROVISION, COMPACTION AND CONSTRUCTION OF BASE COURSE MATERIAL

The road shall be excavated to 200mm depth and 5000mm wide over the length of the road or otherwise indicated by the Technical Officer. The excavated material shall be removed from the site. Imported material, similar or equal to G10 subgrade material, shall be spread, laid and compacted to 98% Mod AASHTO.

The base course layer shall consist of an approved 37mm G4 Hornfels base course, which after compaction shall be 100mm thick for vehicular and 50mm thick for pedestrian crossings. Compaction of base course layers to be 95% Modified AASHTO.

P.7	PROVISION AND CONSTRUCTION OF NEW WEARING COURSE LAYER

Before the placing of the wearing course the Contractor shall prime with an approved bituminous basis primer. Application shall be done to the manufacturer’s specification.

The PREMIX wearing course shall be similar or equal to Messrs “More Asphalt” mix design with a bitumen content of 5 to 5.5%. The thickness of the wearing course for vehicular level crossings shall not be less than 40mm. The thickness for footway premix shall not be less than 25mm.

When tested with a 3m straightedge, the surface of the wearing course shall nowhere vary from the lower edge, by more than 3mm.

P.8 	SAMPLING AND TESTING

The Contractor shall make use of an approved Geotechnical testing laboratory for the in-situ and laboratory testing of:

- In-situ density of compacted wearing layer (Hydrodensimeter)

SHALL READ: In-situ density of compacted wearing layer (TROXLER)

- Material Grading and properties as and when ordered by the Technical Officer.

P.9 	ACCOMODATION OF TRAFFIC

P.9.1 	Safety

All construction workers shall always wear high visibility safety clothing when working alongside public traffic.

P.9.2 	Traffic Safety Officer

A competent person shall be appointed as traffic safety officer on site. The traffic safety officer shall inspect and assess the traffic control facilities / measures on site to ensure an orderly flow of traffic past the construction area.

P.9.3 	Parking of construction vehicles and plant

Where there is no parking space off the road, construction vehicles may be parked on the shoulder only during working hours in which case flagmen and traffic cones shall be utilised to warn public traffic of the hazard. During non-working hours all obstructions shall be removed from the road.

P.9.4 	Traffic-control devices

Traffic accommodation shall be carried out in strict accordance with the requirements of the South African Road Traffic Signs Manual (SARTSM) – Volume 2 – Chapter 13: Roadworks Signing (June 1999).

Flagmen shall be provided on either side of the level crossing, equipped with high visibility safety jackets, red flags, STOP/GO-RY signs and two-way radios to ensure an orderly flow of traffic past the work area. All signals must be clear and the flagmen shall be intelligent and responsible personnel. In areas of high traffic density, the assistance of the relevant traffic authorities’ officials shall be solicited.

Cost to be included in rates.

P.10 	PAINTING OF LEVEL CROSSINGS

  - P10.1    Painting of Road Markings

Painting of road markings shall be done in accordance with the standards and specifications mentioned under the scope of works. Any painting done with paints, colours and material not conforming to these standards will be rejected.

    - P10.1.1 	Site Preparation

Clause 5.32: SANS 1200MM

    - Before the paint is applied, the surface shall be cleaned, dry and completely free from any soil, grease, oil, acid, or any other material which will be detrimental to the bond between paint and the surface. The surface where the paint is to be applied shall be properly cleaned by means of watering, brooming or compressed air if required

    - P10.1.2	Specification of Paint

The paint and the application thereof shall comply with SABS 731 1:200 and SABS –CKS 192.

Paint type 3: Retro- reflective Solvent base road marking paint with the following minimum parameters shall be used.

| Parameter | Colour |  |  |
| --- | --- | --- | --- |
|  | White | Yellow | Red |
| a) Luminance Factors | 036 | 0.4 | +/-0.08 |
| b) Coefficient of Retro-reflection(minicandelas/lux/m2) | 150 | 100 | +/-30 |
| c) Skid Resistance | 50 | 50 | 50 |

    - P10.1.3	Application of Paint

Where painting is done by hand, it shall be applied in two layers and the second layer shall be applied before the first layer has dried properly. Paint must be applied with one stroke of brush or one pass of the roller over the part being painted. Paint shall be applied at a nominal rate of 0.4l/m2.

    - P10.1.4	Road Markings Dimensions

Road marking shall be in accordance with SADC – RTSM Volume 1 and SABS 1200 MM -1984 clause 5.3.1 to clause 5.3.8

Painting shall be done in accordance with the Cape Town Metrorail Level Crossing Signage Design Plans. In most cases, the positions for markings for the level crossing already exist and the marking only requires re-establishment. In cases where the existing road marking is different to the one in the plan in terms of dimensions and colour, the contractor shall inform the TO and the TO will issue an instruction to blackout or sandblast the existing marking. No payment will be made for unauthorised sandblasting or blackout of road markings

| Road markings |  |  |  |
| --- | --- | --- | --- |
| Stop Line | White | RTM1 | 300mm thick |
| Centre line | White | RM1 | 100mm white line and length 9m |
| No Stopping line | Red | RM12 | 150mm red line |
| Box Junction | Yellow | RM10 | 100 mm wide Yellow |

P.11	LEVEL CROSSING PHYSICAL ASSESSMENT AS PER RSR REQUIREMENT

P11.1 	Level crossing risk management shall be carried out in accordance with the South African National Standard, SANS 3000-2-2-1:2012.

The Risk Management process shall cover the following assessments:

P11.1(a)	Physical assessment of level crossings as per ANNEXURE A of SANS 3000 2-2-1:2012.

P11.1(b)		Risk Assessment methodology as per ANNEXURE B of SANS 3000 2-2-1.

P11.1(c)		Signage for Level Crossings as per ANNEXURE C of SANS 3000 2-2-1.

P11.2	The Contractor shall allocate a team from his employees or sub-contract the level crossing risk management process for the completion of the physical assessment, risk assessment as well as the signage of level crossings. The team should comprise of a co-ordinator and one (1) or more team members with the following knowledge:

- Railway Safety

- Road Safety

- Traffic Operations

- Geometric Design

- Railway Operations

P11.3	The deliverables required are as follows:

- Physical Assessment

- Completed field sheets (sheet 1 up to and including sheet 14) as per section A.17 of ANNEXURE A

- Physical assessment report

- Risk Assessment

- Risk assessment Table B.1 of ANNEXURE B

- Signage

- Classification of level crossings as per Table C.1 and Table C.2 of ANNEXURE C

P.12	MEASUREMENT AND PAYMENT

Payment will be made in accordance with the rates tendered in the schedule of prices and as follows:

Item 1: 	Break up existing surface material, remove, load, transport and dump at an approved municipal site.

The unit of measurement will be per m3 (cubic meter) for the breaking up of existing surface material, the removal, loading, transporting and dumping of the material at an approved municipal site.

Rate is all inclusive, covering personnel, plant, tools and equipment required to carry out these works.

Item 2: 	Supply and Install Level Crossing concrete end pieces 2100mm x 200mm

The unit of measurement will be the number of Level Crossing concrete end pieces damaged at each level crossing before works commences. Please note that this item covers concrete end pieces at Level Crossings identified to already be damaged before works commence. This item does not cover concrete end pieces damaged by the contractor. Any concrete end pieces damaged by the contractor will be replaced at the contractor’s own cost.

Rate is all inclusive, covering personnel, plant, tools, and equipment required to:

- Purchase concrete end pieces,

- Loading concrete end pieces,

- Transport concrete end pieces by road,

- Off-loading and stacking concrete end pieces near the level crossing and

- Installing concrete end pieces at the level crossing

Item 3: 	Re-align and place E1 pathway kerb

The unit of measurement will be the number of E1 kerbs re-aligned and placed in the correct position.

Rate is all inclusive, covering personnel, plant, tools, and equipment required to carry out these works.

Item 4: 	Provide and compact base course

The unit of measure will be per m3 (cubic meter) for the excavating, removal, and re-instating new base course layer.

Rate is all inclusive, covering personnel, material, plant, tools, and equipment required to carry out these works.

Item 5: 	Prepare and prime base course to receive premix wearing course

The unit of payment will be per m2 (square meter) for the application of premix as a primer for wearing course.

Rate is all inclusive, covering personnel, material, plant, tools, and equipment required to   carry out these works.

Item 6: 	Provide and compact PREMIX wearing course

The unit of measurement will be per m3 (cubic meter) for the supply, reinstating and compaction of PREMIX wearing course.

Rate is all inclusive, covering personnel, material, plant, tools, and equipment required to carry out these works.

Item 7:       Density test by Hydrodensimeter

The unit of measurement will be per number of tests performed as per the instruction of the Technical Officer.

Rate is all inclusive, covering personnel, plant, tools, and testing equipment required to carry out these works.

Item 8:       Material Grading and Property Test

The unit of measurement will per number of tests performed as per the instruction of the Technical Officer.

Rate is all inclusive, covering personnel, plant, tools, and laboratory testing required to carry out these works.

Item 9:	Painting

The unit of measure will be per m (meter) of lines painted.

Item 10:	Level Crossing Risk assessment

The unit of measure will be a provisional sum for the following items

Physical assessment (as per ANNEXURE A of SANS 3000 2-2-1:2012, Edition 1)

Risk assessment (as per ANNEXURE B of SANS 3000 2-2-1:2012, Edition1)

Signage (as per ANNEXURE C of SANS 3000 2-2-1:2012, Edition 1)

Bill of Quantities

      - A bill of quantities has been included as part of this contract. Tenderers are required to submit their Prices for ALL the line items in the BOQ.

      - Very important! All line items in the BOQ should include VAT at the end.

      - The Tenderer shall tender on a Once off Supply, Deliver and Installation to perform work as described in the Scope of Work, on request from PRASA or their duly elected representatives in the relevant region.

      - The items quoted for should include all relevant costs. No additional payment will be made for items not catered for.

      - If a tenderer leaves any item/s blank which are materially important for the award of the contract/business or fails to tender in an amount expressed or calculable in Rands and cents (e.g., total amount, unit price, and hourly rate), PRASA reserves the right to disqualify such a tender.

      - It will be assumed that prices included in the Bill of Quantities are based on Acts, Ordinances, Regulations, By-laws, International Standards and National Standards that were published 28 days before the closing date for tenders. (Refer to

      - www.stanza.org.za or www.iso.org for information on standards).

SCHEDULE OF QUANTITIES: Refurbishment and Upgrade of level crossings at various locations within Metrorail Western Cape Region for a period of 12 months

| SCHEDULE OF WORK AND PRICES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ITEMS | DESCRIPTIONS | UNIT | ESTIMATED QUANTITY | RATE | AMOUNT |
| 1 | Break up existing surface material, remove, load, transport and dump at an approved municipal dumping site | m3 | 350 |  |  |
| 2 | Supply and Install Level Crossing end pieces (2100mm x 200mm) | each | 40 |  |  |
| 3 | Re-align and place end pieces (2100mm x 200mm) | each | 250 |  |  |
| 4 | Provide and compact base course | m3 | 200 |  |  |
| 5 | Prepare and prime base course | m2 | 2000 |  |  |
| 6 | Provide and compact PREMIX wearing course | m3 | 100 |  |  |
| 7 | Density test by hydrodensimeter | each | 10 |  |  |
| 8 | Material Grading and property tests | each | 4 |  |  |
| 9 | Painting |  |  |  |  |
| 9.1 | White lines |  |  |  |  |
| 9.1.1 | 100mm wide (Centre line) | m | 250 |  |  |
| 9.1.2 | 300mm wide (stop line) | m | 200 |  |  |
| 9.2 | Yellow lines |  |  |  |  |
| 9.2.1 | 100mm wide (box Junction) | m | 1200 |  |  |
| 9.2.2 | 200mm wide | m | 300 |  |  |
| 9.3 | Red lines |  |  |  |  |
| 9.3.1 | 150mm wide (no stopping line) | m | 500 |  |  |
| 10 | Level Crossing Risk Assessment |  |  |  |  |
| 10.1 | Physical assessment (as per ANNEXURE A of SANS 3000 2-2-1:2020, Edition 1) | sum | 1 |  |  |
| 10,2 | Risk assessment (as per ANNEXURE B of SANS 3000 2-2-1:2020, Edition1) | sum | 1 |  |  |
| 10,3 | Signage (as per ANNEXURE C of SANS 3000 2-2-1:2020, Edition 1) | sum | 1 |  |  |
| TOTAL COST |  |  |  |  |  |
| 10% CONTINGENCY FEE |  |  |  |  |  |
| 15% VAT |  |  |  |  |  |
| TOTAL COST INCLUDING VAT |  |  |  |  |  |

GENERIC (STANDARD) SPECIFICATIONS

PART 2 - E.10 Gen: GENERAL

CONTENTS

Clause

1. 	SCOPE

2. 	INTERPRETATION

3. 	MATERIALS

4.	PLANT

5. 	CONSTRUCTION

5.1 	GENERAL

5.2 	SAFETY PRECAUTIONS

5.3 	PROGRAMME

5.4 	METHODS AND PROCEDURES

5.4.1 	HANDLING OF MATERIAL

5.4.2 	LEVEL CROSSINGS

5.4.3 	MATERIAL TRAINS

5.4.4 	PLATELAYING

5.4.5 	FINISHING

5.4.6 	RELEASEMENTS AND SURPLUS MATERIAL

5.5 	STANDARDS

5.5.1 	GENERAL

5.5.2 	TRACK GAUGE

5.5.3 	SUPERELEVATION

5.5.4 	TORQUE

5.5.5 	CLEARANCES

5.6 	COMPLETION

5.6.1 	TAKING OVER

5.6.2 	MAINTENANCE PERIOD

6. 	TOLERANCES

6.1 	HORIZONTAL ALIGNMENT

6.2 	VERTICAL ALIGNMENT

6.3 	TRACK GAUGE

6.4 	SLEEPER SPACING

6.5 	SQUARENESS OF SLEEPERS

6.6 	BALLAST PROFILE

6.7 	STRUCTURE GAUGE

7. 	TESTING

LIST OF ANNEXURES

A - TOLERANCES ON TRACK GEOMETRY STANDARDS

E - SLEEPER SPACING

1. 	SCOPE

This specification covers the general requirements for all types and methods of railway trackwork.

2. 	INTERPRETATIONS

This specification must be read together with all contract documents and specifications, (specifically with the E7/1 Specification for work on, over, under or adjacent to railway lines and near high voltage equipment), the specific supplementary specifications hereof applicable to the project as well as the Project Specification.

2.1 	SUPPORTING SPECIFICATIONS

The following specifications shall form part of the contract documents.

    - Spoornet's Track Welding Specification SSS-8.

2.2 	DEFINITIONS

To ALIGN TRACK means to correct the horizontal geometry of a track to a defined centre line, to within the specified geometric standards.

BALLAST means broken stone used to support sleepers.

To BOX IN AND TRIM means to place the correct quantity of ballast between the sleepers and on the ballast shoulders to form the specified ballast profile.

To CLEAN BALLAST means to remove all ballast and fouling matter to a specified depth below the required rail level, screen the ballast and return it to the track.

CONSTRUCTION SIDING means a railway line built for the purpose of handling construction traffic, or an incomplete new line on which construction traffic is handled.

CONSTRUCTION TRAFFIC means wagons carrying material required by the Contractor or others for construction purposes.

CONTINUOUS WHEEL SPIN DAMAGE means wheel spin damage to the rail crown occurring continuously over a length of more than 150 mm.

Cr Mn RAILS means chrome - manganese rails.

CROSSING FROG means that part of the crossing of a set which enables a train wheel on one rail to cross over another rail at the same level. (See Annexure B).

To CURVE a RAIL means to give a rail a permanent set of the required radius, by bending of the rail.

DESTRESSING means the process whereby rails are relieved from all internal stresses existing in them at that moment in time.

To DISTRIBUTE MATERIAL means to place material on the formation clear, of the structure gauge of open lines and drains, in the required quantities along the track to suit the Works.

FORMATION, when referring to the laying of new track, means the prepared layer works on which railway tracks are to be laid. When referring to an existing track on which work must be done, FORMATION means the earthworks to a specified width at a specified depth below the required rail level.

FREE HAUL DISTANCE means the distance specified in the Project Specification over which the Contractor moves material without separate compensation for distance travelled.

GAUGE, when referring to a railway track, means the shortest distance between the running edges of a pair of rails which are fastened to the sleepers, measured as shown in Annexure F hereof.

BROAD GAUGE TRACK means track with a nominal gauge of 1065 mm, and NARROW GAUGE TRACK means track with a nominal gauge of 610 mm.

HEAVY MACHINE means an on-track machine which may not be operated on open lines without a prior notice having been issued by an operating office of the Railway Authority.

INSULATING JOINT, INSULATED RAIL JOINT or BLOCK JOINT means a rail joint at which the adjacent rails are electrically insulated from each other.

To LAY TRACK means to lay sleepers on the formation, place rails on the sleepers, apply or tighten sleeper and rail fastenings, adjust the gauge and expansion gaps, and pack.

To LIFT means to raise the track from one level to another level.

LIGHT MACHINE means a machine which may be operated on open lines, without a prior notice having been issued by an operating office of the Railway Authority.

LONG WELDED RAILS (LWR) or CONTINUOUS WELDED RAILS (CWR) means rails which have been welded into lengths longer than 36m.

To MAINTAIN means to do the day-to-day repairs and adjustments necessary to keep earthworks and drains in good order and to keep the track at the required standard for trains to run at the prescribed speeds.

MATERIAL TRAIN means a train of wagons and a locomotive for loading or offloading of material at a construction siding, or open lines.

MULTIPLE LINES means a group of tracks of which the maximum distance between any 2 adjacent tracks does not exceed 7,5 m.

OPEN LINE means a railway track that is already in use by the Railway Authority for its everyday business, and under control of its operating department.

To OPEN UP a TRACK means to remove all ballast and fouling matter above the level of the bottom of the sleepers.

To PACK means to insert approved material under a sleeper in such a way that the sleeper will have even bearing over at least 450mm of its length under each rail seat for the full width of the sleeper and will carry a train without damage to the permanent way material or the formation.

RAILWAY AUTHORITY means the owner and his appointed operator of the railway system designated in the Project Specification.

RAILWAY TRACK, TRACK or LINE means a route on which trains travel on steel rails.

RAIL FASTENINGS means the components used to fasten rails to rails.

To REALIGN TRACK means to align the track on the specified centre line, where the horizontal movements are not more than 100mm.

To RELAY means to perform the combined operations defined as RESLEEPER , RERAIL, LIFT, TAMP and ALIGN.

To RERAIL means to remove the rails and rail fastenings from the track and to replace them with other rails and rail fastenings of the same or different mass and/or length with minimum disturbance of the sleepers or ballast.

To RESLEEPER means to remove designated sleepers and sleeper fastenings from the track, and replace them with other sleepers and sleeper fastenings, at the same or a different spacing.

To RESPACE SLEEPERS means to loosen the sleeper fastenings, move the sleepers along the length of the track to the required spacing, thereafter tighten the sleeper fastenings, and tamp the sleepers.

SET means the arrangement of permanent way material, assembled so as to form a unit which enables a train to switch from one railway line to another, or to cross another railway line at the same level. Turnouts, slips and diamond crossings are examples of sets.

SLEEPER means an item of permanent way material designed to support the rails and to hold them at the correct gauge.

SLEEPER FASTENINGS means the components used to fasten rails to sleepers or other railbeds.

To SLEW TRACK means to move a track horizontally by more than 100mm to a different defined centre line of the track.

SPLICE JOINT means an expansion joint inserted in the track.

STABILISED TRACK means track of which the ballast remaining loose after completion of tamping, has been compacted either by the passing of a sufficient number of trains, or by mechanical means designed to expedite the compacting action.

SUPERELEVATION or CANT means the difference in level between the two rails of a track.

To TAMP, TAMP BALLAST or TAMP TRACK means to place and compact sufficient ballast under the sleepers to form a firm interlocking mass which will support the sleepers at the correct level and enable trains to run at the permissible speed.

TOTAL OCCUPATION - is defined in specification E7/1.

TRANSITION CURVE means a curve of decreasing or increasing radius used to connect a straight track to a curved track of uniform radius, or a curved track of one uniform radius to a curved track of another uniform radius.

WAGON means a goods-carrying on-track vehicle.

WORK, OR OCCUPATION, BETWEEN TRAINS - is defined in specification E7/1.

WORK PERMIT - is defined in specification E7/1.

3. 	MATERIALS

3.1 	The Railway Authority will supply all permanent way material and ballast required for the Works except that detailed in the Project Specification and in 3.2 hereof.

3.2 	Unless otherwise stated in the Project Specification, the Contractor shall supply the following:-

i) Exothermic portions and moulds for welding of rail joints.

ii) Welding rods.

iii) Cleaning materials, oil, grease, black lead and graphite for treating contact surfaces and sliding surfaces of items of permanent way material.

iv) Track thermometers for measuring rail temperature.

v) Shims for setting expansion gaps at rail joints.

vi) Tar.

vii) Dowels and creosote for plugging holes in wood sleepers.

viii) Grease for rail and flange lubricators in accordance with Transnet specification CSS 181/63/1315.

ix) White P.V.A. paint for switch boxes, tumbler mass pieces, clearance marks, scotch blocks, derailers, stop blocks and cattle guards.

x) Steel pegs at least 10mm diameter and 300mm long for survey and setting out.

xi) Concrete materials and ingredients for fixing steel pegs in position.

xii) Suitable carbon books with detachable sheets, as required.

xiii) Other miscellaneous items as stated in the Project Specification.

3.3 	All material delivered for the works prior to the Contractor starting work on site, will be distributed or stacked by the Technical Officer, as detailed in the Project Specification.

3.4 	Should the Contractor fail to start work by the time specified in the Project Specification, the Technical Officer may, at his sole discretion, offload and stack or distribute material, and recover money as a penalty from the Contractor, as specified in the Project Specification.

3.5	Immediately after he starts work, the Contractor shall check the quantities of all the material distributed or stacked by the Technical Officer and give the Technical Officer a receipt therefore, and thereafter, accept responsibility for the protection and safe custody of such material. Should the Technical Officer agree that it is necessary, the Contractor shall move the material in order to check the quantities.

3.6 	The Contractor shall provide the Technical Officer together with all construction programs, a detailed Schedule of required dates of delivery of materials, for approval. When approved the Technical Officer will base orders for material thereon. The Contractor shall continuously ascertain whether the material provided by the Technical Officer satisfies his needs, and he shall advise the Technical Officer of any shortages which might delay progress in terms of his approved tender programme. All requests for and advice concerning material shall be made in writing, numbered consecutively and dated. Should the Contractor require material outside his approved schedule, he shall provide the Technical Officer with detail and a revised schedule for approval. The Technical Officer will not be obliged to approve the revised schedule, if the material cannot be supplied in accordance therewith.

3.7 	The Contractor shall give the Technical Officer receipts for material offloaded from wagons. These receipts shall show the date on which the material was offloaded and the numbers of the wagons from which it was offloaded. The wagon labels shall be attached to the receipts.

3.8 	The Contractor shall bring to the notice of the Technical Officer any shortages or defects in any material supplied and shall endorse the relevant receipt accordingly. If steel or concrete sleepers or second-hand permanent way material is supplied, the Contractor shall examine each and every item and shall not use any item which he considers damaged or sub-standard unless the Technical Officer instructs otherwise.

4. 	PLANT

4.1 	The Contractor shall submit with his tender a list of vehicles, heavy machines, light machines and other tools and equipment he intends to use, with a statement of how these will be applied in his proposed method of construction.

4.2 	The Contractor shall submit for the approval of the Technical Officer, a list of any additional heavy machines he intends using prior to the use thereof.

4.3 	 The Technical Officer may by his written instructions, hire the Contractor's vehicles or plant, including operators at the rates quoted in the Schedule of Quantities and Prices.

4.4 	When laying track on new formation the Contractor shall not use machines that may damage the formation.

4.5 	The Contractor shall make his own arrangements with the relevant Railway Authorities, for transport of heavy machines to and from the site. Such transport shall be at the cost of the Contractor. Delays due to whatever reasons, occurring while the Contractor's heavy machines travel to the site on open lines as trains controlled by the operating department of the Railway Authority shall be at the risk of the Contractor, subject to extension of time claims in accordance with the Contract document.

4.6 	Once the use of heavy machines have been accepted in terms of 4.1 or 4.2, the risk of delays caused by actions of the Technical Officer or the Railway Authority to these machines once they are on the worksite or travelling to the worksite from the specified or approved staging point, will be on the Railway Authority.

The estimated cost to the Railway Authority of hauling these machines on site, during the execution of the works, will be taken into account to the extent as specified in the Project Specification.

4.7 	Heavy machines used on the works, shall comply with the following basic requirements:-

4.7.1 	All machinery shall be in good condition initially, and the Contractor shall maintain the machinery in good condition for the duration of the contract.

4.7.2	 Axle loads shall not exceed 20 tons.

4.7.3 	All machines shall have service brakes and independent emergency brakes capable of providing retardation of not less than 12,5% and 6% of gravitational acceleration respectively, on dry rail.

4.7.4 	All machines shall actuate all signalling equipment used by the Railway Authority for traffic control.

4.7.5 	Each machine shall be operated by a qualified operator.

5. 	CONSTRUCTION

5.1 	GENERAL

5.1.1 	The Contractor may use machine based or labour based methods, or a combination thereof, for the execution of the Works. He shall submit with his tender a method statement of how he proposes to carry out the work.

5.1.2 	The Technical Officer and the Contractor may agree on normal working hours other than those defined in the contract, to suit local conditions.

5.1.3 	The Contractor shall only employ supervisors with knowledge and experience of railway trackwork construction and maintenance, and capable of supervising all phases of the work. Their competence to undertake the work will be assessed by the Technical Officer.

5.1.4 	The Technical Officer will have the right to stop any work where adequate supervision is not present and no claims will be considered in respect of such stoppage.

5.1.5 	The Contractor shall record daily in a triplicate carbon copy book sufficient information (and any additional information requested by the Technical Officer), to enable the contract to be efficiently managed and to have available all relevant facts for payment purposes. Each and every sheet of the book must be signed and dated, on the day it is completed, by the Contractor and by the Technical Officer who will remove and retain the original of each set of sheets immediately after he signs it. The Contractor may remove the first copy but the book with the second copy shall remain on site.

5.1.6 	When the Contractor causes work planned to be done during normal working hours, to extend to outside normal working hours, the cost of overtime payable to the Technical Officer's staff, will be recovered from the Contractor, at the rates specified in the Project Specification. Vice versa, when the work is caused to go outside normal working hours by actions of the Technical Officer or the Railway Authority, the Contractor's cost of overtime will be paid for at the extra-over rate quoted for in the Schedule of Quantities and Prices.

5.2 	SAFETY PRECAUTIONS

5.2.1 	The safety of the public, the employees of the Railway Authority and the Technical Officer's and the Contractor's own staff shall be the primary consideration of the Contractor.

5.2.2 	The Contractor shall not do any work on an open line without the knowledge and consent of the Technical Officer.

5.2.3 	The Technical Officer will decide whether a temporary speed restriction is required or not and will arrange for it to be applied. The Contractor shall keep the track safe for the passage of trains at the maximum speed allowed, and he and his workmen shall be prepared to stand aside to allow trains to pass.

5.2.4 	The Contractor shall ensure that he obtains the temporary speed restriction notices applicable to the site and that he does no work outside the limits given in such notices. The Contractor shall check that the temporary speed-reduction boards have been erected and that the speed shown on the boards agrees with the notice. If there is any discrepancy, the Contractor shall immediately advise the Technical Officer.

5.2.5 	During and after completion of each day's work, the Technical Officer will evaluate the safety of the track, and the Contractor shall do all work deemed necessary by the Technical Officer to make it safe for the passage of trains at the arranged speed. The line will not be reopened until the Technical Officer certifies in writing that it is safe to do so.

5.2.6 	Before the start of any occupation, the Contractor shall ensure that he has sufficient workmen, tools and material on site to complete the work planned to be done during the occupation.

5.2.7 	The Contractor shall not move any clearance mark or obscure it unless work is being done in its immediate vicinity, in which case he shall replace or clear it as soon as it is physically possible to do so and before the end of each working day. Clearance marks shall be replaced in position where the adjacent track centres are 3,45m or 2,75m apart for broad-gauge and narrow-gauge tracks respectively. If the rails are bonded, the Technical Officer must be advised before a clearance mark is moved, and it shall be repositioned as directed by him.

5.2.8	The Contractor shall not move any electrified track vertically or horizontally unless the Technical Officer gives permission to do so.

5.3 	PROGRAMME

5.3.1 	Details of available occupation times and other limitations will be given in the Project Specification, around which the Contractor shall plan his programme.

5.3.2 	The Contractor shall submit with his tender a proposed programme of work. The Contractor shall indicate, as part of this programme, the total number of occupations required, as well as for each occupation, the duration thereof, and the production rate for and type of work intended during that occupation.

The above information will be taken into account when adjudicating the tender.

5.3.3 	Before he starts work, the Contractor shall, if requested by the Technical Officer, elaborate on the proposed programme, in writing, for approval by the Technical Officer. Work on open lines tends to disrupt railway traffic, and the work itself is subject to disruption due to the needs of the Railway Authority. The programme must therefore allow for work to be limited as specified in the Project Specification. Should the Contractor be prevented from carrying out a particular activity, he must be prepared to carry on with other activities, when and where possible.

5.4 	METHODS AND PROCEDURES

5.4.1 	HANDLING OF MATERIAL

5.4.1.1 	After he has started work, the Contractor shall load, offload, transport, stack as directed by the Technical Officer, and distribute permanent way material and ballast as required for the works and as approved by the Technical Officer. The sites at which material is to be stacked shall be cleared of all rubbish and vegetation by the Contractor.

5.4.1.2	 Failure on the part of the Contractor to offload wagons built specially for the conveyance of ballast or rails could result in delays in delivery of subsequent consignments of such materials and this aspect will be taken into consideration if a claim for late supply is made. The Contractor shall as far as is reasonably possible plan and execute the Works so that it will not be unduly delayed by the late arrival of any specific item of material. Demurrage charges as specified in the Project Specification will be applicable to delaying of wagons.

5.4.1.3 	The Contractor shall take the utmost care when off-loading wagons, that offloaded material or ballast does not damage or interfere with drainage, cables, wires, the movement of the wagons or the running of trains after offloading is complete.

5.4.1.4 	If permanent way material or ballast is incorrectly offloaded and/or distributed by the Contractor, he shall bear all costs of rectifying the errors. If material has been incorrectly distributed by the Railway Authority, the Contractor shall rectify the errors as directed by the Technical Officer. Payment at daywork rates will be made for such correction of errors.

5.4.1.5 	The Contractor shall obtain the approval of the Technical Officer for the route over which he intends conveying material.

5.4.1.6 	The Contractor shall record at least the following information about material handled on site:-

(a) Wagon numbers and details of contents of any wagons loaded or offloaded.

(b) The kilometre distances at or over which materials were loaded or offloaded.

(c) The type and quantity of material handled.

(d) Deficiencies in quality of material.

(e) Delays in delivery.

(f) Shortages of material.

5.4.1.7 	The Contractor shall provide the driver of each lorry with a suitable triplicate carbon book with detachable numbered sheets. All such books shall be written up in the same manner. Each time a lorry is loaded, one set of 3 sheets of the book shall be legibly completed by the Contractor or his representative to show the following:

a) The lorry registration number.

b) The date.

c) The time loading was completed.

d) The quantity and type of material loaded.

e) The odometer reading.

f) The signature of the driver.

The driver shall also record the time of arrival and odometer reading on the same set of `sheets in the book. Both the driver and the Technical Officer’s representative shall sign the book and the Technical Officer's representative will retain the original sheet.

5.4.1.8 	Should the odometer of any lorry become defective, the lorry shall be withdrawn from service until the odometer has been repaired.

5.4.2 	LEVEL CROSSINGS

5.4.2.1 	When it is necessary for the Contractor to disturb the road surface at a level crossing, he shall give the Technical Officer 3 weeks' written notice, or such other period specified in the Project Specification, and shall carry out all instructions and comply with all requirements laid down by the road authority as directed by the Technical Officer and as specified in the Project Specifications. When the crossing is fitted with precast concrete slabs, they shall be uplifted and replaced by the Contractor as directed by the Technical Officer. On lines within 30 m of an electrified line, the Contractor shall paint the buried lengths of rail at level crossings with tar.

5.4.2.2 	The Contractor shall remove cattle guards, repaint them with white P.V.A. paint and reaffix them as shown on the drawings and shall correct the drainage if necessary. While any portion of a cattle guard is not in it's proper position, the Contractor shall, at his own cost, ensure that no animals gain access to the right-of-way.

5.4.3 	MATERIAL TRAINS

5.4.3.1 	The Technical Officer will arrange material trains for off-loading of material, under the same conditions specified in clause 3.6. The Contractor shall order material trains for loading of released material timeously, as specified in the Project Specifications. The Technical Officer will give the Contractor at least 24 hours notice of the date and time for which a material train has been arranged and give details of types and approximate quantities of material to be offloaded.

5.4.3.2 	The Contractor shall supply sufficient supervision and labour to offload or load all the wagons in material trains during the hours which the trains are scheduled to work. The Contractor shall close all doors before the train departs whether he opened them or not.

5.4.3.3 	If a material train is delayed in any way by any act of the Contractor, he will he held liable for demurrage charges on any wagons so delayed at the rates specified in the Project Specifications for the full period of such delay.

5.4.3.4 	The Technical Officer will keep the Contractor informed as to the running times of material trains and their expected arrival times. The Contractor shall arrange his work to avoid, as far as possible, any loss of working time while waiting for a material train to arrive. The Contractor will be compensated for time lost due to a material train being late only if the material train arrives more than 30 minutes late, or is cancelled, and provided that the Technical Officer certifies that no other work was available within a reasonable distance of where the train was arranged to stop first.

5.4.3.5 	The Contractor shall record at least the following information about material trains :-

a) The time a material train was due.

b) The time a material train stopped at the site.

c) All interruptions in excess of 30 minutes in working a material train.

d) The time a material train left the site.

e) The names of the Contractor's and the Technical Officer's representatives attending to a material train.

f) The number of the Contractor's workmen assigned to work with a train.

5.4.4 	PLATELAYING

5.4.4.1 	The Technical Officer will provide the Contractor with survey information as specified in specification E10/11, as well as in the Project Specification, for alignment of the works.

5.4.4.2 	Before any items of permanent way material subject to movement are assembled, all contact surfaces shall be cleaned, oiled, greased or blackleaded and polished as required. The contact surfaces between the rails, sleepers and sleeper fastenings shall be kept free of oil, grease and foreign matter.

5.4.4.3 	Unless self-locking nuts are supplied, spring washers must be fitted under the nuts.

5.4.4.4 	Permanent way material shall be assembled as shown on the relevant drawings.

5.4.4.5 	When curved track is aligned, the high leg must be positioned at 533 mm from the centre line pegs for broad gauge track, and at 305 mm for narrow gauge track.

5.4.4.6 	The Contractor shall destress the rails after certain operations on open lines, as specified in the Project Specification.

5.4.4.7 	The Contractor shall at all times ensure that sleepers are adequately packed to avoid derailments or damage to perway material or the formation. Any such damage will be for the Contractor's account.

5.4.4.8 	If there is a mismatch at a fish-plated railjoint of more than 1 mm, this mismatch shall be reduced to less than 1 mm, as specified in Track Welding Specification SSS-8.

5.4.4.9 	When joints in rails, which are to be welded, are temporarily fishplated the following shall apply:

a) The joint shall be midway between sleepers, to be achieved by either moving of sleepers or cutting off short sections of rail.

b) The cutting of rails shall generally be in accordance with specification E10/1.

c) The joint may be fishplated by either:-

i) Using joggle type fishplates (painted yellow), together with four clamps; or

ii) Using conventional fishplates with drilling and bolting, except that this method may not be used on CrMn - rails.

d) On open lines, temporarily fishplated joints may not be left in the track for longer than three days.

e) The Contractor shall obtain the Technical Officer’s approval of the position of the joints. The Technical Officer will only certify payment for the joint if the joint was made at his request or instruction, and not when it was provided for the convenience of the Contractor.

5.4.4.10 The Contractor shall record daily at least the following information about work performed :-

a) The amount of work performed per scheduled item.

b) Whether the work was done under total occupation, occupation between trains or work permit.

c) The weather conditions.

d) The state of the work site and roads.

e) Details of any occurrence which may have a bearing on any claim which the Contractor may wish to make. No claims will be considered unless supported by an entry in the diary containing all the facts on which the claim is based.

5.4.5 	FINISHING

5.4.5.1 	After the track has been brought to the final level, the Contractor shall check and correct the running top, the expansion gaps, gauge and superelevation. He shall arrange with the Technical Officer to check, together with the Signalling Technician of the Railway Authority, turnouts, slips, scissors and diamond crossings and derailers to ensure that they have been installed correctly and operate correctly. He shall realign the track, tighten all fastenings, check and correct the quantity of ballast, and box in and trim.

5.4.5.2 	The Contractor shall be responsible for all maintenance of the Works until such time as the track is taken over by the Technical Officer, when the standard of the track shall be as specified.

5.4.6 	RELEASEMENTS AND SURPLUS MATERIAL

5.4.6.1 	The Contractor shall dispose of released and surplus material in accordance with the Project Specification.

5.4.6.2	Released material shall not be stacked or loaded into wagons together with new or second-hand material supplied surplus to requirements for the works. Each type of permanent way material shall be stacked separately. Material shall be loaded into wagons as directed by the Technical Officer.

5.4.6.3 	Material trains for the loading of released and surplus material will be arranged as provided for in the Project Specification.

5.4.6.4 	To achieve safe working conditions at the site, clearing and loading of released material shall be a continuous operation which shall be done as the work proceeds. Small items of released rail and sleeper fastenings, as well as wood sleepers, shall be cleared out of the section before the end of each day, as specified in the Project Specifications.

5.4.6.5 	The Contractor shall, on every day that material is loaded, give the Technical Officer a signed, dated list in duplicate for each wagon, detailing the type and quantity of material in each wagon and giving the wagon number and place where loaded. The Technical Officer will sign the lists and return the duplicate to the Contractor as a receipt.

5.4.6.6	If the Technical Officer instructs that material is to be left in stacks, the Contractor and Technical Officer shall together count it. The Contractor shall give the Technical Officer a signed list in duplicate of all such material. The list shall indicate where and on what date the stack was made. The Technical Officer will sign the list and return the duplicate to the Contractor as a receipt. Thereafter the Railway Authority will be responsible for that material.

5.5 	STANDARDS

5.5.1 	GENERAL

5.5.1.1 	Lines are classified into the following classes:-

Class S

Class N1

Class N2

Class N3

Yard lines

5.5.1.2 	An outline of the track design standard applicable to each class of line is shown in Annexure C Sheet 1 hereto.

5.5.1.3 	For each class of line, A, B or C categories of track condition standards are defined herein and in the supplementary specifications. The condition standards with which completed trackwork shall comply, are as specified in the Project Specification.

5.5.1.4 	During construction, the following interim condition standards shall apply :-

a) For opened up track, to allow trains to run at the temporary restricted speed. - C standard.

b) For destressing of rails - B standard, unless C standard has been specified for the completed trackwork.

5.5.2 	TRACK GAUGE

5.5.2.1 	The nominal gauge on the straight for broad-gauge track shall be 1 065 mm and for narrow-gauge track 610 mm.

5.5.2.2	The gauge for track on curves shall be as follows:

| RADIUS OF CURVE | NOT CHECK-RAILED | CHECK-RAILED |
| --- | --- | --- |
| BROAD-GAUGE TRACK |  |  |
| Under 135 m | 1 085 mm | 1 090 mm |
| 135 m - 150 m | 1 080 mm | 1 085 mm |
| 151 m - 175 m | 1 075 mm | - |
| 176 m - 200 m | 1 070 mm | - |
| Over 200 m | 1 065 mm | - |
| NARROW-GAUGE TRACK |  |  |
| Under 201 m | 620 mm |  |
| 201 m - 300 m | 615 mm |  |
| Over 300 m | 610 mm |  |

5.5.2.3 	Gauge widening on circular and transition curves, shall be provided in accordance with Annexure F hereof.

5.5.3 	SUPERELEVATION

5.5.3.1 	The Contractor shall provide superelevation as specified in the Project Specification or as directed by the Technical Officer. In the absence of such directives, it shall be provided in accordance with the clauses below.

5.5.3.2 	Superelevation shall be provided on curves on open lines in accordance with annexure G hereof. In yard tracks the superelevation shall be 10 mm on all curves.

5.5.3.3 	On curves without transitions, two thirds of the full superelevation shall be provided at the beginning and ends of the curves. The superelevation shall be increased to the full amount towards the middle of the curve and decreased to zero into the straight at a rate not exceeding 20 mm in 10 m.

5.5.3.4 	On curves with transitions, application of superelevation shall commence at the point where the transition curve meets the straight and be provided at a uniform rate over the transition curve, to reach the required value for the curve at the beginning of the circular curve, provided that the rate of application of superelevation does not exceed 20 mm in 10 m. If it is not possible to reach the required superelevation at the beginning of the circular curve at the abovementioned maximum rate, the increase of superelevation at this maximum rate shall be continued into the circular curve until the required superelevation is reached.

5.5.3.5 	On reverse curves where the intervening straight is less than 40 m, zero superelevation shall be provided for a distance of 6 m between the two curves.

5.5.4 	TORQUE

Unless otherwise specified in the Project Specification or supplementary specification E.10/12, all rail and sleeper fastenings, bolts and screws, shall be tightened to a torque of 340 N.m.

5.5.5 	CLEARANCES

At specific points, the Technical Officer may instruct that clearances less than the minimum specified in specification E7/1 shall apply.

5.6 	COMPLETION

5.6.1 	TAKING OVER

5.6.1.1 	The Contractor shall complete trackwork ready for taking over, at the rates and in quantities as specified in the Project Specification. The Technical Officer may at his sole discretion, take over portions of the work under lesser conditions than those specified in the Project Specifications, of which he will advise the Contractor.

5.6.1.2 	Work will only be taken over after it has been tested and found to be satisfactory.

5.6.2	MAINTENANCE PERIOD

Notwithstanding the requirements in the contract dealing with maintenance of the Works after completion thereof, the Contractor will be relieved of all responsibilities for the maintenance of any portion of the trackwork after the Technical Officer has taken it over, except that latent defect shall be rectified.

6. 	TOLERANCES

Unless otherwise specified in the Project Specification, the permissible deviations from the specified standards shall be within the limits specified hereinafter.

6.1 	HORIZONTAL ALIGNMENT

6.1.1 	TRACK CENTRELINE

The centreline of the track shall be aligned correctly to within 20 mm from the staked line, on all classes and standards of lines.

6.1.2 	STRAIGHT TRACK AND CURVES

On straight track and curves, the mid-ordinate measured on the gauge side of both rails from a chord of 10 m, shall not exceed the value calculated from the formulae specified in table A1 of Annexure A hereto. In addition, the number of measurements allowed to be one standard lower, is also specified in the above table.

6.2 	VERTICAL ALIGNMENT

6.2.1 	TRACK LEVEL.

Track levels shall be within 10 mm of the specified levels.

6.2.2 	RUNNING TOP AND VERTICAL CURVES

The maximum permissible deviation from the theoretical grade measured by means of a standard track gauge measuring instrument, shall not exceed the values calculated from the fomulae specified in table A1 Annexure A hereof. In addition the number of measurements allowed to be one standard lower, is also specified in the above table.

6.2.3 	SUPERELEVATION

The superelevation at any point, shall not differ from the required superelevation by more than the values in table A1 of Annexure A hereof.

In addition, the number of measurements allowed to be one standard lower, is also specified in the above table.

6.2.4 	TWIST

The algebraic difference between the measured superelevations at any two measuring points, shall not exceed the theoretical difference by more than the values calculated from the formulae in table A1 of Annexure A hereof. The values given in brackets in the table, is the calculated value for measuring points 5 m apart.

6.3 	TRACK GAUGE

The algebraic difference between the actual gauge and the required gauge shall not be more than the maximum nor less than the minimum shown in table A2 of Annexure A hereof. In addition, the algebraic difference between the deviations at any two measuring points 5 m apart, shall not be more than the maximum values in the above mentioned table.

6.4 	SLEEPER SPACING

The spacing between any two adjacent sleepers shall not exceed the specified spacing by more than the values shown in table A3 of Annexure A hereof.

In addition, the total number of sleepers on a 50 m portion of track, shall not differ from the specified number of sleepers by more than the numbers shown in table A4 of Annexure A hereof.

6.5 	SQUARENESS OF SLEEPERS

Sleepers shall not be out of square relative to the centreline of the track, by more than 25 mm for A Standard and 50 mm for B and C Standard lines, measured at the running edges of the rail crowns.

6.6 	BALLAST PROFILE

The dimensions Y, K and Z defined in the diagram in Annexure C sheet 2, shall not be less than the minimum nor more than the maximum values in the table in that Annexure, unless otherwise specified in the Project Specification.

6.7 	STRUCTURE GAUGE

The horizontal and vertical clearances shall be not less than those specified in specification E7/1. The horizontal distance from track centreline to a platform shall not exceed the specified distance by more than 20 mm.

7. 	TESTING

7.1 	QUALITY

7.1.1 	Testing of the trackwork will take the form of the checking of construction generally to comply with the specifications, and by measuring the items listed in 6 hereof.

7.1.2 	The Contractor shall measure and mark the track at 5 meter intervals and indicate the kilometre distance at each 20 m mark. The horizontal and vertical track alignment, and the gauge shall be measured at each 5 m station, clearance to obstructions where necessary, and the rest at 20 m stations. The results shall be recorded and evaluated by the Contractor before handing them to the Technical Officer. On open lines, this shall be done before the end of each day and prior to the opening of the track to traffic. Final measurements shall be made not longer than 24 hours before final handover, or as detailed in the Project Specification.

7.1.3 	The Contractor shall advise the Technical Officer in writing (stating kilometre distances), when he considers that he has completed all the work on a section which he wishes the Technical Officer to take over, and after he has done his own inspection and measuring of the work. The Technical Officer will, within 3 days of receipt of such notification, inspect the section in the company of the Contractor. The Technical Officer will point out any defects he sees to the Contractor who shall record such defects in duplicate. On completion of the inspection, both parties shall sign the record and the Technical Officer will endorse the record that either he is prepared to take over the track immediately subject to the defects being remedied within a specified time or that the Contractor shall remedy the defects and then ask for another inspection. The Technical Officer will retain the original of the record.

7.1.4	 At the start of any inspection by the Technical Officer in accordance with 7.1.3 hereof, the Technical Officer may define a sample test portion of that section that the Contractor wants him to take over. When inspection of that sample portion indicates defects at more than 5% of the number of measurements, the Technical Officer may abandon the inspection and will endorse the record accordingly. Before requesting another handover of that section, the Contractor shall re-inspect the section, and rectify all faults.

7.1.5 	The testing of the track will be deemed to be successful, if all measurements are within the specified tolerances.

7.2 	PRODUCTION

7.2.1 	The production rate tendered for work to be done under occupations, will be used as the basis to test the production actually achieved, for which penalties or bonuses will be calculated in terms of the Project Specification.

ANNEXURE A

TOLERANCES ON TRACK GEOMETRY STANDARDS

| TYPE | METHOD | PERMISSIBLE DEVIATION FROM STANDARD |  |  | NUMBER OF PERMISSIBLE MEASUREMENTS ONE STANDARD LOWER |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | A | B | C | per 500 m portion | per each set |
| VERTICAL ALIGNMENT Top - All track Superelevation - all track Twist - transition curves Twist - all other track | Gauge measuring instrument Gauge measuring instrument Calculated from superelevation Calculated from superelevation | 1:1000 3 mm 1:500 (10 mm) 1:1000 (5 mm) | 1:250 12 mm 1:400 (12,5 mm) 1:400 (12,5 mm) | 1:180 16 mm 1:288 (17,5 mm) 1:288 (17,5 mm) | 3 10 | 1 10% |
| HORIZONTAL ALIGNMENT Versine - curves Alignment - straight track | 10 m chord 10 m chord | 2,5 mm + 5% of correct versine 1:2000 | 2,5 mm + 20% of correct versine 1:500 | 2.5 mm + 30% of correct versine 1:360 | 8 8 | 10% 10% |

ANNEXURE E

SLEEPER SPACING

|  | Permissible deviation from specified spacing (mm) |  |  |
| --- | --- | --- | --- |
|  | A - Standard | B - Standard | C - Standard |
| At rail joints | 10 | 30 | 40 |
| Rest of Track | 25 | 100 | 150 |

SLEEPER PER 50 m TRACK

|  | Permissible deviation from specified number |  |  |
| --- | --- | --- | --- |
|  | A - Standard | B - Standard | C - Standard |
| Insufficient sleepers | 0 | 2 | 4 |
| Too many sleepers | 0 | 4 | 8 |

PASSENGER RAIL AGENCY OF SOUTH AFRICA LIMITED

E7/1 (July 110108)

SPECIFICATION FOR WORKS ON, OVER, UNDER OR ADJACENT TO RAILWAY LINES AND NEAR HIGH VOLTAGE EQUIPMENT

(This Specification shall be used in PRASA Contracts)

CONTENTS

1.	DEFINITIONS	PAGES NO'S.

PART A - GENERAL SPECIFICATION

2.	Authority of officers of PRASA	4

3.	Contractor's representatives	4

4.	Occupations and work permits	4

5.	Speed restrictions and protection	5

6.	Roads on PRASA property	5

7.	Clearances	5

8.	Stacking of material	5

10.	Excavation, shoring, dewatering and drainage	5

10.	Falsework for structures	6

11.	Piling	6

12.	Underground services	6

13.	Blasting	6

14.	Rail trolleys	7

15.	Signal track circuits	7

16.	Penalty for delays to trains	7

PART B - ADDITIONAL SPECIFICATION FOR WORK NEAR HIGH-VOLTAGE

ELECTRICAL EQUIPMENT

17.	General	8

18.	Work on buildings of fixed structures	8

110.	Work done on or outside of rolling stock, including

loading and unloading	8

20.	Use of equipment	10

21.	Carrying and handling material and equipment	10

22.	Precautions to be taken when erecting or removing

poles, antennae and trees	10

23.	Use of water	10

24.	Use of construction plant	10

25.	Work performed under dead conditions under cover

of a work permit	11

26.	Traction return circuits in rails	11

27.	Blasting	11

28.	High-voltage electrical equipment not maintained

and/or operated by PRASA	11

APPENDIXES

1.	Horizontal clearances 1 065 mm gauge

2.	Platform clearances

3.	Vertical clearances 1 065 mm gauge

1.	DEFINITIONS

The following definitions shall apply:

Authorised Person.  A person whether an employee of PRASA or not, who has been specially authorised to undertake specific duties in terms of Metrorail’s publication SAFETY INSTRUCTIONS: HIGH-VOLTAGE ELECTRICAL EQUIPMENT, and who holds a certificate or letter of authority to that effect.

Barrier.  Any device designed to restrict access to "live" high-voltage electrical equipment.

Bond.  A short conductor installed to provide electrical continuity.

Contractor.  Any person or organisation appointed by PRASA to carry out work on its behalf.

Dead.  Isolated and earthed.

Electrical Officer (Contracts).  The person appointed in writing by the responsible Electrical Engineer in PRASA as the person who shall be consulted by the Contractor in all electrical matters to ensure that the Contractor takes adequate safety precautions.

Executive Officer.  The person appointed by PRASA from time to time as the Executive Officer to act according to the rights and powers held by and obligations placed upon him in terms of the Contract.

High-Voltage.A voltage normally exceeding 1 000 volts.

Live.  A conductor is said to be "live" when it is at a potential different from that of the earth or any other conductor of the system of which it forms a part.

Near.  To be in such a position that a person's body or the tools he is using or any equipment he is handling may come within 3 metres of live exposed high-voltage electrical equipment.

Occupation.  An authorisation granted by PRASA for work to be carried out under specified conditions on, over under or adjacent to railway lines.

Occupation Between Trains.  An occupation during an interval between successive trains.

Project Manager.  The person or juristic person appointed by PRASA from time to time as the Project Manager, to administer the Contract according to the powers and rights held by and obligations placed upon him in terms of the Contract. Responsible Representative.The responsible person in charge, appointed by a contractor, who has undergone specific training (and holds a certificate) to supervise staff under his control to work on, over, under or adjacent to railway lines and in the vicinity of high-voltage electrical equipment.

Technical Officer.  The person or juristic person appointed by PRASA from time to time as the Technical Officer, to administer the Contractor's performance and execution of the Works according to the powers and rights held by and obligations placed upon the Technical Officer in terms of the Contract.

Total Occupation.An occupation for a period when trains are not to traverse the section of line covered by the occupation.

Work on.  Work undertaken on or so close to the equipment that the specified working clearances to the live equipment cannot be maintained.

Work Permit.  A combined written application and authority to proceed with work on or near dead electrical equipment.

2.	PART 1 - GENERAL SPECIFICATION

AUTHORITY OF OFFICERS OF PRASA

2.1	The Contractor shall co-operate with the officers of PRASA and shall comply with all instructions issued and restrictions imposed with respect to the Works which bear on the existence and operation of PRASA's railway lines and high-voltage equipment.

2.2	Without limiting the generality of the provisions of 2.1, any duly authorised representative of PRASA, having identified himself, may stop the work if, in his opinion, the safe passage of trains or the safety of PRASA assets or any person is affected.  CONSIDERATIONS OF SAFETY SHALL TAKE PRECEDENCE OVER ALL OTHER CONSIDERATIONS.

3.	CONTRACTOR'S REPRESENTATIVES

3.1	The Contractor shall nominate Responsible Representatives of whom at least one shall be available at any hour for call-out in cases of emergency.  The Contractor shall provide the Technical Officer with the names, addresses and telephone numbers of the representatives.

  - The Contractor guarantees that he has satisfied himself that the Responsible Representative is fully conversant with this specification and that he shall comply with all his obligations in respect thereof.

4              OCCUPATIONS AND WORK PERMITS

4.1	Work to be done during total occupation or during an occupation between trains or under a work permit shall be done in a manner decided by the Technical Officer and at times to suit PRASA requirements.

4.2	The Contractor shall organise the Works in a manner which will minimise the number and duration of occupations and work permits required.

4.3	PRASA will not be liable for any financial or other loss suffered by the Contractor arising from his failure to complete any work scheduled during the period of an occupation or work permit.

4.4	The Contractor shall submit to the Technical Officer, in writing, requests for occupations or work permits together with details of the work to be undertaken, at least 14 days before they are required.  PRASA does not undertake to grant an occupation or work permit for any particular date, time or duration.

4.5	PRASA reserves the right to cancel any occupation or work permit at any time before or during the period of occupation or work permit.  If, due to cancellation or change in date or time, the Contractor is not permitted to start work under conditions of total occupation

or work permit at the time arranged, all costs caused by the cancellation shall be born by the Contractor except as provided for in clauses 4.6 to 4.8.

4.6	When the Contractor is notified less than 2 hours before the scheduled starting time that the occupation or work permit is cancelled, he may claim reimbursement of his direct financial losses caused by the loss of working time up to the time his labour and plant

are employed on other work, but not exceeding the period of the cancelled occupation or work permit.

4.7	When the Contractor is notified less than 2 hours before the schedule starting time, or during an occupation or work permit, that the duration of the occupation or work permit is reduced, he may claim reimbursement of his direct financial losses caused by the loss of working time due to the reduced duration of the occupation or work permit.

4.8	Reimbursement the Contractor for any loss of working time in terms of 4.6 and 4.7, shall be subject to his claims being submitted within 14 days of the event with full details of labour and plant involved, and provided that the Technical Officer certifies that no other work on which the labour and plant could be employed was immediately available.

4.10	Before starting any work for which an occupation has been arranged, the Contractor shall obtain from the Technical Officer written confirmation of the date, time and duration of the occupation.

4.10	Before starting any work for which a work permit has been arranged, the Responsible Representative shall read and sign portion C of form No. T.1276 signifying that he is aware of the limits within which work may be undertaken. After the work for which the permit was granted has been completed, or when the work permit is due to be terminated, or if the permit is cancelled after the start, the same person who signed portion C shall sign portion D of the T.1276 form, thereby acknowledging that he is aware that the electrical equipment is to be made "live".  The Contractor shall advise all his workmen accordingly.

5.	SPEED RESTRICTIONS AND PROTECTION

  - When speed restrictions are imposed by PRASA because of the Contractor's activities, the Contractor shall organise and carry out his work so as to permit the removal of the restrictions as soon as possible.

5.2	When the Technical Officer considers protection to be necessary the Contractor shall, unless otherwise agreed, provide all protection including flagmen, other personnel and all equipment for the protection of PRASA's and the Contractor's personnel and assets, the public and including trains.

PRASA will provide training free of charge of the Contractor's flagmen and other personnel performing protection duties. The Contractor shall consult with the Technical Officer, whenever he considers that protection will be necessary, taking into account the minimum permissible clearances set out in appendixes 1 to 4.

5.3	The Contractor shall appoint a Responsible Representative to receive and transmit any instruction, which may be given by PRASA personnel providing protection.

6.	ROADS ON PRASA PROPERTY

The provision of clause 25 of the E.5, General Conditions of Contract, or clause 23 of the E.5 (MW), General Conditions of Contract for Maintenance Works, shall apply to the use of existing roads on PRASA's property.

7.	CLEARANCES

7.1	No temporary works shall encroach on the appropriate minimum clearances set out in Appendixes 1 to 4.

8.	STACKING OF MATERIAL

8.1	The Contractor shall not stack any material closer than 3 m from the centre line of any railway line without prior approval of the Technical Officer.

10.	EXCAVATION, SHORING, DEWATERING AND DRAINAGE

10.1	Unless otherwise approved by the Technical Officer any excavation adjacent to a railway line shall not encroach on the hatched area shown in Figure 1.

10.2	The Contractor shall provide at his own cost any shoring, dewatering or drainage of any excavation unless otherwise stipulated elsewhere in the Contract.

10.3	Where required by the Technical Officer, drawings of shoring for any excavation under or adjacent to a railway line shall be submitted and permission to proceed, obtained before the excavation is commenced.

10.4	The Contractor shall prevent ingress of water to the excavation but where water does enter, he shall dispose of it as directed by the Technical Officer.

10.5	The Contractor shall not block, obstruct or damage any existing drains either above or below ground level unless he has made adequate prior arrangements to deal with drainage.

10.	FALSEWORK FOR STRUCTURES

10.1	Drawings of falsework for the construction of any structure over, under or adjacent to any railway line shall be submitted to the Technical Officer and his permission to proceed obtained before the falsework is erected.  Each drawing shall be given a title and a distinguishing number and shall be signed by a registered professional engineer certifying that he has checked the design of the falsework and that the drawings are correct and in accordance with the design.

10.2	After the falsework has been erected and before any load is applied, the Contractor shall submit to the Technical Officer a certificate signed by a registered professional engineer certifying that he has checked the falsework and that it has been erected in accordance with the drawings.  Titles and numbers of the drawings shall be stated in the certificate. Notwithstanding permission given by the Technical Officer to proceed, the Contractor shall be entirely responsible for the safety and adequacy of the falsework.

11.	PILING

11.1	The Technical Officer will specify the conditions under which piles may be installed on PRASA property.

12.	UNDERGROUND SERVICES

12.1	No pegs or stakes shall be driven or any excavation made before the Contractor has established that there are no underground services, which may be damaged thereby.

12.2	Any damage shall be reported immediately to the Technical Officer, or to the official in charge at the nearest station, or to the traffic controller in the case of centralised traffic control.

13.	BLASTING

13.1	The provisions of clause 23 of the E.5, General Conditions of Contract or clause 21 of the E.5 (MW), General Conditions of Contract for Maintenance Work, shall apply to all blasting operations undertaken in terms of the Contract.

13.2	The Contractor shall provide proof that he has complied with the provisions of clauses 10.17.1 to 10.17.4 of the Explosives Regulations (Act 26 of 11056 as amended).

13.3	Blasting within 500m of a railway line will only be permitted during intervals between trains.  A person appointed by the Technical Officer, assisted by flagmen with the necessary protective equipment, will be in communication with the controlling railway station.

Only this person will be authorised to give the Contractor permission to blast, and the Contractor shall obey his instructions implicitly regarding the time during which blasting may take place.

13.4	The flagmen described in 13.3, where provided by PRASA, are for the protection of trains and PRASA property only, and their presence does not relieve the Contractor in any manner of his responsibilities in terms of Explosives Act or Regulations, or any obligation in terms of this Contract.

  - The person described in 13.3 will record in a book provided and retained by PRASA the dates and times –

(i)	when each request is made by him to the controlling station for permission to blast;

(ii)	when blasting may take place;

(iii)	when blasting actually takes place; and

(iv)	when he advises the controlling station that the line is safe for the passage of trains.

13.6	Before each blast, the Contractor shall record in the same book, the details of the blast to be carried out.  The person appointed by the Technical Officer and the person who will do the blasting shall both sign the book whenever an entry described in 13.5 is made.

13.7	The terms of clause 27 hereof shall be strictly adhered to.

14.	RAIL TROLLEYS

14.1	The use of rail trolleys or trestle trolleys on a railway line for working on high voltage equipment will be permitted only if approved by the Technical Officer and under the conditions stipulated by him.

14.2	All costs in connection with such trolley working requested by the Contractor shall, unless otherwise agreed, be borne by the Contractor, excluding the costs of any train protection services normally provided free of charge by PRASA.

15.	SIGNAL TRACK CIRCUITS

15.1	Where signal track circuits are installed, the Contractor shall ensure that no material capable of conducting an electrical current makes contact between rails of a railway line/lines.

15.2	No signal connections on track-circuited tracks shall be severed without the Technical Officer's knowledge and consent.

16.	PENALTY FOR DELAYS TO TRAINS

16.1	If any trains are delayed by the Contractor and the Technical Officer is satisfied that the delay was avoidable, a penalty will be imposed on the Contractor of R5 000 per hour or part thereof for the period of delay, irrespective of the number of trains delayed.

PART B - ADDITIONAL SPECIFICATION FOR WORK NEAR HIGH-VOLTAGE ELECTRICAL EQUIPMENT

17.	GENERAL

17.1	This specification is based on the contents of Metrorail’s publication SAFETY INSTRUCTIONS, HIGH-VOLTAGE ELECTRICAL EQUIP-MENT, as amended, a copy of which will be made available on loan to the Contractor for the duration of the contract.

These instructions apply to all work near live high-voltage equipment maintained and/or operated by PRASA, and the onus rests on the Contractor to ensure that he obtains a copy.

17.2	The Contractor's attention is drawn in particular to the contents of Part I, Sections 1 and 2 of the Safety Instructions: High-Voltage Electrical Equipment.

17.3	The Safety Instructions: High-Voltage Electrical Equipment cover the minimum safety precautions which must be taken to ensure safe working on or near high-voltage electrical equipment, and must be observed at all times.  Should additional safety measures be considered necessary because of peculiar local conditions, these may be ordered by and at the discretion of the Electrical Officer (Contracts).

17.4	This specification must be read in conjunction with and not in lieu of the Safety Instructions: High-Voltage Electrical Equipment.

17.5	The Contractor shall obtain the approval of the Electrical Officer (Contracts) before any work is done which causes or could cause any portion of a person's body or the tools he is using or any equipment he is handling, to come within 3 metres of any live high-voltage equipment.

17.6	The Contractor shall regard all high-voltage equipment as live unless a work permit is in force.

17.7	Safety precautions taken or barriers erected shall comply with the requirements of the Electrical Officer (Contracts), and shall be approved by him before the work to be protected is undertaken by the Contractor. The Contractor shall unless otherwise agreed bear the cost of the provision of the barriers and other safety precautions required, including the attendance of PRASA staff where this is necessary.

17.8	No barrier shall be removed unless authorised by the Electrical Officer (Contracts).

18.	WORK ON BUILDINGS OR FIXED STRUCTURES

18.1	Before any work is carried out or measurements are taken on any part of a building, fixed structure or earthworks of any kind above ground level situated within 3 metres of live high-voltage equipment, the Electrical Officer (Contracts) shall be consulted to ascertain the conditions under which the work may be carried out.

18.2	No barrier erected to comply with the requirements of the Electrical Officer (Contracts) shall be used as temporary staging or shuttering for any part of the Works.

18.3	The shuttering for bridge piers, abutments, retaining walls or parapets adjacent to or over any track may be permitted to serve as a barrier, provided that it extends at least 2,5 metres above any working level in the case of piers, abutments and retaining walls and 1,5 metres above any working level in the case of parapets.

110.	WORK DONE ON OR OUTSIDE OF ROLLING STOCK, INCLUDING LOADING OR UNLOADING

110.1	No person shall stand, climb or work whilst on any platform, surface or foothold higher than the normal unrestricted places of access, namely:-

- the floor level of trucks;

(ii)	external walkways on diesel, steam and electric locomotives, steam heat vans, etc. and

(iii)	walkways between coaches and locomotives.

When in these positions, no person may raise his hands or any equipment or material he is handling above his head.

110.2	In cases where the Contractor operates his own rail mounted equipment, he shall arrange for the walkways on this plant to be inspected by the Electrical Officer (Contracts) and approved, before commencement of work.

110.3	The handling of long lengths of material such as metal pipes, reinforcing bars, etc should be avoided, but if essential they shall be handled as nearly as possible in a horizontal position below head height.

110.4	The Responsible Representative shall warn all persons under his control of the danger of being near live high-voltage equipment, and shall ensure that the warning is fully understood.

  - Where the conditions in 110.1 to 110.3 cannot be observed the Electrical Officer (Contracts), shall be notified.  He will arrange for suitable Safety measures to be taken.  The Electrical Officer (Contracts), may in his discretion and in appropriate circumstances, arrange for a suitable employee of the Contractor to be specially trained by METRORAIL and at its costs, as an Authorised Person to work closer than 3 metres from live overhead conductors and under such conditions as may be imposed by the Senior responsible Electrical Engineer in PRASA.

20.	USE OF EQUIPMENT

20.1	Measuring Tapes and Devices

20.1.1	Measuring tapes may be used near live high-voltage equipment provided that no part of any tape or a person's body comes within 3 metres of the live equipment.

20.1.2	In windy conditions the distance shall be increased to ensure that if the tape should fall it will not be blown nearer than 3 metres from the live high-voltage equipment.

20.1.3	Special measuring devices longer than 2 metres such as survey staves and rods may be used if these are of non-conducting material and approved by the responsible Electrical Engineer in PRASA, but these devices must not be used within 3 metres of live high-voltage equipment in rainy or wet conditions.

20.1.4	The assistance of the Electrical Officer (Contracts) shall be requested when measurements within the limits defined in 20.1.1 to 20.1.3 are required.

20.1.5	The restrictions described in 20.1.1 to 20.1.3 do not apply on a bridge deck between permanent parapets nor in other situations where a barrier effectively prevents contact with the live high-voltage equipment.

20.2	Portable Ladders

20.2.1	Any type of portable ladder longer then 2 metres may only be used near live high-voltage equipment under the direct supervision of the Responsible Representative.  He shall ensure that the ladder is always used in such a manner that the distance from the base of the ladder to any live high-voltage equipment is greater than the fully extended length of the ladder plus 3 metres.  Where these conditions cannot be observed, the Electrical Officer (Contracts) shall be advised, and he will arrange for suitable safety measures to be taken.

21.	CARRYING AND HANDLING MATERIAL AND EQUIPMENT

21.1	Pipes, scaffolding, iron sheets, reinforcing bars and other material that exceeds 2 metres in length shall be carried completely below head height near live high-voltage equipment. For maximum safety two or more persons to maintain it as nearly as possible in a horizontal position should carry such material.  The utmost care must be take to ensure that no part of the material comes within 3 metres of any live high-voltage equipment.

21.2	Long lengths of wire or cable shall never be run out in conditions where a part of a wire or cable can come within 3 metres of any live high-voltage equipment unless the Electrical Officer (Contracts) has been advised and has approved appropriate safety precautions.

21.3	The presence of overhead power lines shall always be taken account of especially when communications lines or cables or aerial cables, stay wires, etc. are being erected above ground level.

22.	PRECAUTIONS TO BE TAKEN WHEN ERECTING OR REMOVING POLES, ANTENNAE, TREES ETC.

22.1	A pole may be handled for the purpose of erection or removal near high-voltage equipment under the following conditions:

- If the distance between the point at which the pole is to be erected or removed and the nearest live high-voltage equipment is more than the length of the pole plus 3 metres, the work shall be supervised by the Responsible Representative.

- If the distance described in (i) is less than the length of the pole plus 3 metres, the Electrical Officer (Contracts) shall be consulted to arrange for an Authorised Person to supervise the work and to ensure that the pole is earthed where possible.  The pole shall be kept in contact with the point of erection, and adequate precautions shall be taken to prevent contact with live high-voltage equipment.

22.2	The cost of supervision by an Authorised Person and the provision of earthing shall, unless otherwise agreed, be borne by the Contractor.

22.3	The provisions of clauses 22.1 and 22.2 shall also apply to the erection or removal of columns, antennae, trees, posts, etc.

23.	USE OF WATER

23.1	No water shall be used in the form of a jet if it can make contact with any live high-voltage equipment or with any person working on such equipment.

24.	USE OF CONSTRUCTION PLANT

24.1	"Construction plant" entails all types of plant including cranes, piling frames, boring machines, excavators, draglines, dewatering equipment and road vehicles with or without lifting equipment.

24.2	When work is being undertaken in such a position that it is possible for construction plant or its load to come within 3 metres of live high-voltage equipment, the Electrical Officer (Contracts) shall be consulted. He will arrange for an Authorised Person to supervise the work and to ensure that the plant is adequately earthed. The Electrical Officer (Contracts) will decide whether further safety measures are necessary.24.3	The cost of any supervision by an Authorised Person and the provision of earthing shall, unless otherwise agreed, be borne by the Contractor.

24.4	When loads are handled by cranes, non-metallic rope hand lines shall be used, affixed to such loads so as to prevent their swinging and coming within 3 metres of live high-voltage equipment.

24.5	Clauses 24.1 to 24.4 shall apply mutatis mutandis to the use of maintenance machines of any nature.

25.	WORK PERFORMED UNDER DEAD CONDITIONS UNDER COVER OF A WORK PERMIT

25.1	If the Responsible Representative finds that the work cannot be done in safety with the high-voltage electrical equipment live, he shall consult the Electrical Officer (Contracts) who will decide on the action to be taken.

25.2	If a work permit is issued the Responsible Representative shall:-

(i)	before commencement of work ensure that the limits within which work may be carried out have been explained to him by the Authorised Person who issued the permit to him, and that he fully understands these limits.

(ii)	sign portion C of the permit before commencement of work;

(iii)	explain to all persons under his control the limits within which work may be carried out, and ensure that they fully understand these limits;

(iv)	care for the safety of all persons under his control whilst work is in progress; and

(v)	withdraw all personnel under his control from the equipment on completion of the work before he signs portion D of the work permit.

26.	TRACTION RETURN CIRCUITS IN RAILS

26.1	DANGEROUS CONDITIONS CAN BE CREATED BY REMOVING OR SEVERING ANY BOND.

26.2	Broken rails with an air gap between the ends, and joints, at which fishplates are removed under "broken bond" conditions, are potentially lethal. The rails on either side of an air gap between rail ends on electrified lines shall not be touched simultaneously until rendered safe by PRASA personnel.

26.3	The Contractor shall not break any permanent bonds between rails or between rails and any structure. He shall give the Technical Officer at least 7 days written notice when removal of such bonds is necessary.

26.4	No work on the track which involves interference with the traction return rail circuit either by cutting or removing the rails, or by removal of bonds shall be done unless the Electrical Officer (Contracts) is consulted. He will take such precautions as may be necessary to ensure continuity of the return circuit before permitting the work to be commenced.

27.	BLASTING

27.1	The Contractor shall obtain the permission of the Electrical Officer (Contracts) before blasting, and shall give at least 14 days notice of his intention to blast.

27.2	No blasting shall be done in the vicinity of electrified lines unless a member of PRASA's electrical personnel is present.

  - The terms of clause 13 hereof shall be strictly adhered to.

28.	HIGH-VOLTAGE ELECTRICAL EQUIPMENT NOT MAINTAINED AND/OR OPERATED BY PRASA

Where the work is undertaken on or near high-voltage electrical equipment which is not maintained and/or operated by PRASA, the Occupational Health and Safety Act No. 85 of 110103, and Regulations and Instructions, or the Mines Health and Safety Act (Act 210 of 110106), shall apply.

Such equipment includes:-

(i)	Eskom and municipal equipment;

(ii)	the Contractor's own power supplies; and

(iii)	electrical equipment being installed but not yet taken over from the Contractor.

# Specification E4E

# SAFETY ARRANGEMENTS AND PROCEDURAL COMPLIANCE WITH THE OCCUPATIONAL HEALTH AND SAFETY ACT (ACT 85 OF 110103) AND APPLICABLE REGULATIONS

# 1.	General

1.1	The Contractor and Passenger Rail Agency of South Africa Ltd (hereinafter referred to as “ PRASA are individual employers, each in its own right, with their respective duties and obligations set out in the Occupational Health and Safety Act, Act 85 of 110103 (the Act) and applicable Regulations.

  - The Contractor accepts, in terms of the General Conditions of Contract and in terms of the Act, his obligations as an employer in respect of all persons in his employ, other persons on the premises or the Site or place of work or on the work to be executed by him, and under his control.  He shall, before commencement with the execution of the contract work, comply with the provisions set out in the Act, and shall implement and maintain a Health and Safety Plan as described in the Construction Regulations, 2003 and as approved by PRASA, on the Site and place of work for the duration of the Contract.

  - The Contractor accepts his obligation to complying fully with the Act and applicable Regulations notwithstanding the omission of some of the provisions of the Act and the Regulations from this document.

  - PRASA. accepts, in terms of the Act, its obligations as an employer of its own employees working on or associated with the site or place of work, and the Contractor and Technical Officer or his deputy shall at all times, co-operate in respect of the health and safety management of the site, and shall agree on the practical arrangements and procedures to be implemented and maintained during execution of the Works.

  - In the event of any discrepancies between any legislation and this specification, the applicable legislation will take precedence.

# 2.	Definitions

  - In this Specification any word or expression to which a meaning has been assigned in the Construction Regulations, shall have the meaning so assigned to it, unless the context otherwise indicates: -

  - The work included in this Contract shall for the purposes of compliance with the Act be deemed to be "Construction Work", which, in terms of the Construction Regulations, 2003 means any work in connection with: -

(a)	the erection, maintenance, alteration, renovation, repair, demolition or dismantling of or addition to a building or any similar structure;

- the installation, erection, dismantling or maintenance of fixed plant where such work includes the risk of a person falling;

- the construction, maintenance, demolition or dismantling of any bridge, dam, canal, road, railway, runway, sewer or water reticulation system or any similar civil engineering structure; or

- the moving of earth, clearing of land, the making of an excavation, piling, or any similar type of work;

  - “competent person” in relation to construction work, means any person having the knowledge, training and experience specific to the work or task being performed: Provided that where appropriate qualifications and training are registered as per the South African Qualifications Authority Act, 110105 these qualifications and training shall be deemed to be the required qualifications and training;

  - “contractor” means principal contractor and “subcontractor” means contractor as defined by the Construction Regulations, 2003.

  - “fall protection plan” means a documented plan, of all risks relating to working from an elevated position, considering the nature of work undertaken, and setting out the procedures and methods applied to eliminate the risk;

  - “health and safety file” means a file, or other record in permanent form, containing the information required to be kept on site in accordance with the Act and applicable Regulations;

  - “Health and Safety Plan ” means a documented plan which addresses the hazards identified and include safe work procedures to mitigate, reduce or control the hazards identified;

  - “Risk Assessment” means a programme to determine any risk associated with any hazard at a construction site, in order to identify the steps needed to be taken to remove, reduce or control such hazard;

2.10	“the Act” means the Occupational Health and Safety Act No. 85 of 110103.

# 3.	Procedural Compliance

3.1	The Contractor who intends to carry out any construction work shall, before carrying out such work, notify the Provincial Director in writing if the construction work:-

- includes the demolition of a structure exceeding a height of 3 metres; or

- includes the use of explosives to perform construction work; or

(c)	includes the dismantling of fixed plant at a height greater than 3m,

and shall also notify the Provincial Director in writing when the construction work exceeds 30 days or will involve more than 300 person days of construction work and if the construction work:-

- includes excavation work deeper than 1m; or

- includes working at a height greater than 3 metres above ground or a landing.

  - The notification to the Provincial Director shall be on a form similar to Annexure A of the Construction Regulations, 2003, also shown in Annexure 1 of this Specification.  The Contractor shall ensure that a copy of the completed notification form is kept on site for inspection by an inspector, Technical Officer or employee.

  - The Contractor shall, in accordance with the Act and applicable Regulations, make all the necessary appointments of competent persons in writing on a form similar to Annexure 2 of this Specification and deliver copies thereof to the Technical Officer.  Copies should also be retained on the health and safety file.

  - Subcontractors shall also make the above written appointments and the Contractor shall deliver copies thereof to the Technical Officer.

  - In the case of a self-employed Contractor or any subcontractor who has the appropriate competencies and supervises the work himself, the appointment of a construction supervisor in terms of regulation 6.1 of the Construction Regulations, 2003 will not be necessary.  The Contractor shall in such a case execute and sign a declaration, as in Annexure 3, by which he personally undertakes the duties and obligations of the "Chief Executive Officer" in terms of section 16(1) of the Act.

  - The Contractor shall, before commencing any work, obtain from the Technical Officer an access certificate as in Annexure 4 executed and signed by him, permitting and limiting access to the designated site or place of work by the Contractor and any subcontractors under his control.

  - Procedural compliance with Act and Regulations, as above, shall also apply to any subcontractors as employers in their own right.   The Contractor shall furnish the Technical Officer with full particulars of such subcontractors and shall ensure that they comply with the Act and Regulations and PRASAsafety requirements and procedures.

# 4.	Special Permits

Where special permits are required before work may be carried out such as for hotwork, isolation permits, work permits and occupations, the Contractor shall apply to the Technical Officer or the relevant authority for such permits to be issued.  The Contractor shall strictly comply with the conditions and requirements pertaining to the issue of such permits.

# 5.	Health and Safety Programme

5.1	The Tenderer shall, with his tender, submit a Health and Safety Programme setting out the practical arrangements and procedures to be implemented by him to ensure compliance by him with the Act and Regulations and particularly in respect of: -

- The provision, as far as is reasonably practical, of a working environment that is safe and without risk to the health of his employees and subcontractors in terms of section 8 of the Act;

(ii)	the execution of the contract work in such a manner as to ensure in terms of section 10 of the Act that persons other than those in the Contractor's employment, who may be directly affected by the contract work are not thereby exposed to hazards to their health and safety;

(iii)	ensuring, as far as is reasonably practical, in terms of section 37 of the Act that no employee or subcontractor of the Contractor does or omits to do any act which would be an offence for the Contractor to do or omit to do.

  - The Contractor's Health and Safety Programme shall be based on a risk assessment in respect of the hazards to health and safety of his employees and other persons under his control that are associated with or directly affected by the Contractor's activities in performing the contract work and shall establish precautionary measures as are reasonable and practical in protecting the safety and health of such employees and persons.

  - The Contractor shall cause a risk assessment contemplated in clause 5.2 above to be performed by a competent person, appointed in writing, before commencement of any Construction Work and reviewed during construction.  The Risk Assessments shall form part of the Health and Safety programme to be applied on the site and shall include at least the following:

- The identification of the risks and hazards that persons may be exposed to;

(b)	the analysis and evaluation of the hazards identified;

(c)	a documented Health and Safety Plan, including safe work procedures to mitigate, reduce or control the risks identified;

(d)	a monitoring and review plan.

5.4	The Health and Safety Plan shall include full particulars in respect of: -

(a)		The safety management structure to be instituted on site or place of work and the names of the Contractor's health and safety representatives and members of safety committees where applicable;

- the safe working methods and procedures to be implemented to ensure the work is performed in compliance with the Act and Regulations;

(c)	the safety equipment, devices and clothing to be made available by the Contractor to his employees;

(d)	the site access control measures pertaining to health and safety to be implemented;

(e)	the arrangements in respect of communication of health and safety related matters and incidents between the Contractor, his employees, subcontractors and the Technical Officer with particular reference to the reporting of incidents in compliance with Section 24 and General Administrative Regulation 8 of the Act and with the pertinent clause of the General Conditions of Contract forming part of the Contract and

(f)	the introduction of control measures for ensuring that the Safety Plan is maintained and monitored for the duration of the Contract.

  - The Health and Safety programme shall be subject to the Technical Officer's approval and he may, in consultation with the Contractor, order that additional and/or supplementary practical arrangements and procedures be implemented and maintained by the Contractor or that different working methods or safety equipment be used or safety clothes be issued which, in the Technical Officer's opinion, are necessary to ensure full compliance by the Contractor with his obligations as an employer in terms of the Act and Regulations.  The Technical Officer or his deputy shall be allowed to attend meetings of the Contractor's safety committee as an observer.

  - The Contractor shall take reasonable steps to ensure that each subcontractor’s Health and Safety Plan is implemented and maintained on the construction site:  Provided that the steps taken, shall include periodic audits at intervals mutually agreed to between them, but at least once every month.

  - The Contractor shall stop any subcontractor from executing any construction work, which is not in accordance with the Contractor’s, and/or subcontractor’s Health and Safety Plan for the site or which poses a threat to the health and safety of persons.

  - The Contractor shall ensure that a copy of the Health and Safety Plan is available on site for inspection by an inspector, Technical Officer, agent, subcontractor, employee, registered employee organisation, health and safety representative or any member of the health and safety committee.

  - The Contractor shall consult with the health and safety committee or, if no health and safety committee exists, with a representative group of employees, on the development, monitoring and review of the Risk Assessment.

  - The Contractor shall ensure that all employees under his control are informed, instructed and trained by a competent person regarding any hazard and the related work procedures before any work commences, and thereafter at such times as may be determined in the Risk Assessment.

  - The Contractor shall ensure that all subcontractors are informed regarding any hazard as stipulated in the Risk Assessment before any work commences, and thereafter at such times as may be determined in the Risk Assessment.

  - The Contractor shall ensure that all visitors to a construction site undergoes health and safety induction pertaining to the hazards prevalent on the site and shall be provided with the necessary personal protective equipment.

6.	Fall Protection Plan

    - In the event of the risk and hazard identification, as required in terms of clause 5.3 of this Specification, revealing risks relating to working from an elevated position the contractor shall cause the designation of a competent person, responsible for the preparation of a fall protection plan.

    - The Contractor shall implement, maintain and monitor the fall protection plan for the duration of Contract.  The Contractor shall also take such steps to ensure the continued adherence to the fall protection plan.

    - The fall protection plan shall include: -

- A Risk Assessment of all work carried out from an elevated position;

- the procedures and methods to address all the identified risks per location;

- the evaluation of the employees physical and psychological fitness necessary to work at elevated positions;

- the training of employees working from elevated positions; and

- the procedure addressing the inspection, testing and maintenance of all fall protection equipment.

# 7.	Hazards and Potential Hazardous Situations

The Contractor and the Technical Officer shall immediately notify one another of any hazardous or potentially hazardous situations which may arise during performance of the Contract by the Contractor or any subcontractor and, in particular, of such hazards as may be caused by the design, execution and/or location and any other aspect pertaining to the contract work.

# 8.	Health and Safety File

  - The Contractor shall ensure that a health and safety file is opened and kept on site and shall include all documentation required as per the Act and applicable regulations, and made available to an inspector, the Technical Officer, or subcontractor upon request.

  - The Contractor shall ensure that a copy of the both his Health and Safety Plan as well as any subcontractor’s Health and Safety Plan is available on request to an employee, inspector, contractor or the Technical Officer.

  - The Contractor shall hand over a consolidated health and safety file to the Technical Officer upon completion of the Construction Work and shall in addition to documentation mentioned in the Act and applicable Regulations include a record of all drawings, designs, materials used and other similar information concerning the completed structure.

# ANNEXURE 1

# OCCUPATIONAL HEALTH AND SAFETY ACT, 110103

Regulation 3(1) of the Construction Regulations

NOTIFICATION OF CONSTRUCTION WORK

1.	(a)	Name and postal address of principal contractor: _____________________________________________________________________

(b)	Name and tel. no of principal contractor’s contact person:

_____________________________________________________________________

- Principal contractor’s compensation registration number: _____________________________

3.	(a)	Name and postal address of client:  _____________________________________________________________________

(b)	Name and tel no of client’s contact person or agent:

_____________________________________________________________________

4.	(a)	Name and postal address of designer(s) for the project: _____________________________________________________________________

(b)	Name and tel. no of designer(s) contact person:

____________________________________________________________________

- Name and telephone number of principal contractor’s construction supervisor on site appointed in terms of regulation 6(1).  _____________________________________________________________________

- Name/s of principal contractor’s construction sub-ordinate supervisors on site appointed in terms of regulation 6(2).  ____________________________________________________________

- Exact physical address of the construction site or site office:  _____________________________________________________________________

- Nature of the construction work: _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- Expected commencement date: _______________________

- Expected completion date: ___________________________

- Estimated maximum number of persons on the construction site: _______________________

- Planned number of contractors on the construction site accountable to the principle contractor:

___________________

- Name(s) of contractors already chosen.

___________________

___________________

___________________

___________________

___________________

___________________

___________________

_______________________						_________________

## Principal Contractor 								Date

_______________________						_________________

  - Client										Date

*	THIS DOCUMENT IS TO BE FORWARDED TO THE OFFICE OF THE DEPARTMENT OF LABOUR PRIOR TO COMMENCEMENT OF WORK ON SITE.

*	ALL PRINCIPAL CONTRACTORS THAT QUALIFY TO NOTIFY MUST DO SO EVEN IF ANOTHER PRINCIPAL CONTRACTOR ON THE SAME SITE HAD DONE SO PRIOR TO THE COMMENCEMENT OF WORK.

ANNEXURE 2

# OCCUPATIONAL HEALTH AND SAFETY ACT, 110103 (ACT 85 OF 110103):

# SECTION/REGULATION: __________________________________________

# REQUIRED COMPETENCY: ________________________________________

| In terms of ________________________________________ I, |  |  |  |  |
| --- | --- | --- | --- | --- |
| representing the Employer) do hereby appoint |  |  |  |  |
| As the Competent Person on the premises at |  |  |  |  |
| (physical address) to assist in compliance with the Act and the applicable Regulations. |  |  |  |  |

Your designated area/s is/are as follows: -

Date:		____________________________________

Signature: -	____________________________________

Designation: -	____________________________________

# ACCEPTANCE OF DESIGNATION

| I, |  | do hereby accept this Designation and acknowledge that I |
| --- | --- | --- |
| understand the requirements of this appointment. |  |  |

Date:		____________________________________

Signature: -	____________________________________

Designation: -	____________________________________

ANNEXURE 3

# OCCUPATIONAL HEALTH AND SAFETY ACT, 110103 (ACT 85 OF 110103) :

### DECLARATION

| In terms of the above Act I, |  | am personally assuming the duties |
| --- | --- | --- |
| and obligations as Chief Executive Officer, defined in Section 1 of the Act and in terms of Section 16(1), I will, as far as is reasonably practicable, ensure that the duties and obligations of the Employer as contemplated in the above Act are properly discharged. |  |  |

Signature: -	____________________________________

Date:		____________________________________

# ANNEXURE 4

# SITE ACCESS CERTIFICATE

| Access to: |  |  |  | (Area) |
| --- | --- | --- | --- | --- |
| Name of Contractor/Builder: - |  |  |  |  |
| Contract/Order No.: |  |  |  |  |
| The contract works site/area described above are made available to you for the carrying out of associated works |  |  |  |  |
| In terms of your contract/order with |  |  |  |  |
| (company) |  |  |  |  |

Kindly note that you are at all times responsible for the control and safety of the Works Site, and for persons under your control having access to the site.

As from the date hereof you will be responsible for compliance with the requirements of the Occupational Health and Safety Act, 110103 (Act 85 of 110103) as amended, and all conditions of the Contract pertaining to the site of the works as defined and demarcated in the contract documents including the plans of the site or work areas forming part thereof.

Signed: ____________________________________	 Date: _______________________

# TECHNICAL OFFICER

# ACKNOWLEDGEMENT OF RECEIPT

| Name of Contractor/Builder: - |  |  | I, |
| --- | --- | --- | --- |
|  |  | do hereby acknowledge and accept the duties |  |
| and obligations in respect of the Safety of the site/area of Work in terms of the Occupational Health and Safety Act; Act 85 of 110103. |  |  |  |

Name :____________________________		Designation :	_______________________

Signature :_________________________		Date :		_______________________

Part C4

SITE INFORMATION

C4.1	LOCATION AND ACCESS TO THE SITE OF THE WORKS

The location of the sites is indicated in the scope of work and will also be pointed out at the time of the site inspection.

Access to the site of the Works is by public roads joining up with the service/mechanisation roads of PRASA along the railway line. The Contractor shall not make use of private roads to gain access to the service/mechanisation roads unless he can produce documentary proof of consent from the owner of such road and indemnifies PRASA against any claims that may arise from the use of such private roads. The Contractor shall acquaint himself with the available access to the site and the condition of the roads during the site inspection.

Vehicle access to certain sections is restricted. The Contractor shall make his own arrangements with regard to access to the sites and shall allow for this in his rates tendered for the Works.

the power, by one person or a group of persons holding the majority of the equity of an enterprise, alternatively, the person/s having the deciding vote or power to influence or to direct the course and decisions of the enterprise.

Joint venture or Consortium means an association of persons for the purpose of combining their expertise, property, capital, efforts, skill and knowledge in an activity for the execution of a contract.