| Approval Authority: | Triple Adjudication Sheileen Parsotam |
| --- | --- |
| Date of Submission/Meeting |  |
| Name of End-User | Thembuz Mbali |
| End-User BU & Division / Group | Asset Creation |
| Name of Executing Procurement Practitioner | Lonwabo Mavukwana |
| Sourcing Department | Procurement and Supply Chain Management – Cape Coastal Cluster (Eastern Cape) |
| PR No |  |
| Description of Procurement | Design, supply, installation, testing, commissioning and maintenance of the complete control centre solutions for the intelligent substation & security system for a pilot project |

- RESOLUTION REQUIRED

| Approval is sought to execute a commercial strategy for the procurement of: | - Design, supply, installation, testing, commissioning and maintenance of the complete control centre solutions for the intelligent substation & security system for a pilot project. - For: Asset Creation (Cape Coastal Cluster) - At a value of: R57 885 843.00 - For a duration of : 12 months. - Using: Using formal open tendering procurement mechanism - Applying: NEC 3 Term Service Contract (TSC). |
| --- | --- |

- MOTIVATION FOR THE TRANSACTION

| Background to the need for the Procurement | The need for this procurement is driven by the increasing vulnerability of Eskom’s critical infrastructure within the Cape Coastal Cluster. As outlined in SOW 559-155379501, traditional security measures are no longer sufficient to combat sophisticated threats, necessitating a transition to "Intelligent" systems. The Cape Coastal Cluster faces a critical security and operational crisis characterized by: - Failure of Passive Defence: Existing security relies on human "eyes-on" patrols and reactive recording. This has failed to prevent high-frequency vandalism and theft, leading to millions in asset replacement costs and lost revenue. - Operational Blind Spots: Current systems do not provide real-time data on plant health. Critical failures, such as transformer overheating or fires, are often only detected after a power trip, resulting in extended outages. - Energy Resilience Gaps: Existing security infrastructure lacks adequate backup power. During load shedding or localized faults, security systems go dark, creating "windows of opportunity" for criminal activity. - Fragmented Infrastructure: A "patchwork" of legacy, non-functional equipment hinders centralized monitoring and creates a maintenance burden for technical teams. The Solution: Transitioning to an Intelligent Security System (SOW 559-155379501) that integrates AI-driven detection with resilient, Eskom-standard network and power architecture. |
| --- | --- |
| Full Description of the Scope / Specifications | The scope for a typical Security Control Centre includes the comprehensive design, supply, installation, testing, commissioning and maintenance of the complete control centre solutions for the intelligent substation & security system, inclusive of: a) all required server infrastructure, b) dedicated overview monitors to provide for adequate situational awareness at all sites, c) dedicated or shared monitors to provide for site-category interrogation of video feeds and alarms, d) all other hardware required to a fully operational solution. e) A service provider is to provide maintenance service for 12 months from the date of commissioning. A typical design for the CNC’s, Substations, and Warehouses has been completed and will be shared during tendering stages. Intelligent Security System Pilot Project: a critical initiative aimed at enhancing intelligence and security capabilities across designated sites within Eskom Distribution Cape Coastal Cluster Eastern Cape and Western Cape. This project implements an advanced, AI-driven security and plant monitoring solution across the Cape Coastal Cluster. Moving beyond traditional passive surveillance, the strategy employs a Design, Supply, Install, and Commission model. This shifts technical accountability to the contractor while ensuring integration between fibre perimeter detection, AI anomaly sensing, and existing Eskom network infrastructure. The system is engineered for resilience, featuring dedicated LFP-based backup power to maintain security during 2-hour outages and strict adherence to Eskom’s Cybersecurity and Network standards (VLAN 1002) By referencing SOW 559-155379501, this contracting strategy ensures that the risk of technical non-performance remains with the provider, while Eskom maintains governance through the monthly DRT process and strict normative standards. |
| If a project, describe the various phases and activities of the project, and confirm which phases this strategy covers | The project follows a standard Engineering, Procurement, and Construction (EPC) lifecycle, specifically tailored for the high-security requirements of Eskom's infrastructure. Phase; Key Activities. 1. Initiation & Design; Site surveys, lighting assessments, and wayleave applications. Development of the "Intelligent Design" for CCC DRT approval.. 2. Procurement; Sourcing of long-lead items (AI Servers, LFP UPS, Fibre Sensors). Contractor mobilization and safety file approval.. 3. Execution (Install); Decommissioning legacy gear. Trenching, mounting poles, and installing AI cameras, fibre perimeter sensing, and Paradox panels.. 4. Integration & Test; Networking via VLAN 1002. Configuration of AI analytics and system stress testing (30-second network recovery check).. 5. Close-out & Handover; Training (Online/In-person). Issuance of CoCs and "As-Built" drawings. Transition to the 2-year maintenance cycle.. This Contracting Strategy is designed as a "cradle-to-grave" framework for the pilot phase. It explicitly covers: - Phase 1 (Design): Mandatory through the Design Review Team (DRT) gatekeeping process. - Phase 2 (Procurement): Covered via the 80/20 financial evaluation and Tier 1 equipment specs. - Phase 3 (Execution): Covered by the detailed technical BOQ and ORHVS safety requirements. - Phase 4 (Integration): Covered by the technical KPIs for network and AI performance. - Phase 5 (Handover): Covered by the decommissioning mandates and training requirements. The strategy also covers the first 2 years of the Operations Phase through the inclusion of a mandatory maintenance and support contract within the initial tender award. This ensures the contractor remains "on the hook" for the system's performance long after the physical installation is complete.. |
| Describe the Groups, Divisions and / or Business Units within Eskom which will be affected by the execution of this strategy | Asset Creation |
| Has investment approval / budgetary confirmation been obtained to proceed with execution of the strategy? Please indicate the confirmed budget value, who approved/confirmed and date of such approval /confirmation. | Yes, the budget has been approved as follows: For Eastern Cape, a budget amount of R32 551 643.00 was approved by Mr. M. Mndende (Project Accounting Manager) Cape Coastal Cluster -EC, dated 21 April 2026. For Western Cape, a budget amount of R25 334 200.00 was approved by Ms. A. Brey (Senior manager Finance) – Cape Coastal Cluster. Dated 22 April 2026. |
| Will Eskom require external financing for the procurement? Elaborate on the financing strategy, and if any special terms and conditions need to be approved in order to secure the funding? | No, the financing is internal. |
| Is this a significant / material transaction for which ministerial approval will be required in terms of S54 of the PFMA? Explain. | No, Ministerial approval is not required. |

- BUSINESS INTELLIGENCE

| Is this strategy informed by an RFI / EOI process? If so, confirm details of the RFI / EOI issued, responses received, and outcome of analysis of responses. | The strategy is not informed either request for information or expression of interest. |
| --- | --- |
| Provide detail on how Eskom currently procures / disposes of the required assets / goods / services or indicate whether this procurement is being executed for the first time in Eskom | This is first time Eskom procures these services; the transaction is based on pilot project. |
| Provide the annual forecasting plan for the procurement of the required assets / goods / services where applicable. | The duration of the pilot project is 12 months, thereafter a maintenance will start after each site commissioning, and the duration will be 24 months. |
| Provide the reason and outcome of any market analyses (products / services) that was carried out including where applicable, any specific scarce resources / materials involved, and/or any specialised skills required for delivering. on the required scope / specifications. Detail any market risk factors that impact on the product / service value chain (e.g political, social, environmental, legal, technological and economic). Indicate the number of local and international suppliers. | Eskom is procuring these services for the first time; the market analysis was not conducted. The project is based on a pilot, and the nature of the services does need a highly skills service providers in terms of technological. Secondly with the geopolitical issues that are currently happening global, delivery lead time and cost of imported equipment will impact Eskom negatively. The market research was not conducted therefore the market is unknown, therefore the pilot will also determine whether there is enough market in South Africa or International. |
| Elaborate or explain the TCO model to verify the cost estimation of the assets / goods / services to be procured / disposed. Describe the key cost components impacting the price, and associated variables to be considered. Attach TCO calculations. | The components cost of a security system is approximately 70% of the Total Cost of Ownership (TCO) and the remaining 30% is split between the Installation costs, Maintenance costs and overheads. The 70% ownership cost is made up of the following components: - Hardware Cost - Software Cost and licensing cost - Communication and data cost - Power and connectivity - Overheads - Testing |
| Stipulate the key risks associated with the execution of the strategy, and how such risks will be mitigated (e.g need for financial viability to be done) | Kindly refer to the below table: |
| R RISK; LEVEL (HIGH/MEDIUM/LOW); TREATMENT PLAN. Cost: Impact of design changes on costing and implementation time; Medium; The typical designs are known, and the budget has been set aside. Time: Late deliveries; Medium; Based on the geopolitical issues taking place across the work has potential of delaying any import material, therefore a service provider will encourage to consider local suppliers or import from the countries that are not affected by war.. Safety: Safety files not compliant to Eskom’s standards; Low; Safety staff on a regular basis will carry out safety file audits. The safety files will be approved before commencement of work on site.. Quality: Non-adherence to Eskom Supplier Quality Management requirements as per QM 58 specification, and poor workmanship for manufacturing of class 1-power transformers.; High; Include Quality management requirements for compliance prior to contract award, and subsequently during contract period. |
| Address the potential impact of CPA, forex, tax implications, shipping and insurances on the costing of the assets, goods or services to be procured /disposed | The CPA and Forex is not applicable; the contract is for the period of 12 months. |
| Clarify whether cataloguing / codification requirements are applicable for this procurement. If applicable confirm cost implications and how this requirement will be addressed in the tender | The nature of project is a pilot therefore activities have not been catalogued yet, this process will start after contract award, where a service will provide catalogue for the quoted activities then material numbers or and service numbers will be generated. |
| In the case of sole/single source procurement, attach the signed SSJF and set out any further details if required to support the motivation for using the sole / single source supplier] | Not applicable, the tender will be following open market procurement mechanism. |
| In the case of a closed enquiry (Multiple Source where market research and analysis is required to support the issuing of the enquiry to a few prospective suppliers) indicate the list of the proposed suppliers and details of the process that was undertaken to compile the list. | Not applicable, the tender will be following open market procurement mechanism. |

- COMMERCIAL EXECUTION STRATEGY

| Confirm that all members of the cross-functional team have completed the conflicts of interest declaration. Confirm if any conflicts of interests have been declared. | Some |
| --- | --- |
| Confirm that all members of the cross-functional team have completed an NDA | Some |
| Is this procurement PPPFA-exempt? Please indicate if PPPFA exemption is required, and the reasons therefor. | The PPPFA is not exempted, the strategy will in in line with PPPFA Act guidelines. |
| Will the outcome result in the award of a single contract to a single supplier, or the award of multiple contracts to multiple suppliers and the rationale therefor? Confirm if this strategy is linked to the placement of suppliers on a panel. | The strategy will result to multiple contract award from minimum of two (2) service providers within the cluster, however the award will be inline with PPR 2022, where highest scoring tenderer in terms of the PPPFA scoring including specific goals will be recommended. |
| Will alternative tenders be accepted? If yes, explain on what basis. | Alternative tenders are not acceptable. |
| Will execution be based on a competitive tender or a negotiation (no prior tendering) | The execution will be based on a competitive tender. |
| If a competitive tender, will the tender be an open or a closed tender? Indicate reasons for the selection. | Yes, competitive tender will be advertised in an open market, using Eskom tender bulletin and e-tendering system. |
| If an open competitive tender, indicate where the tender will be advertised, and the period of advertisement? [note this period must be aligned to requirements of the current approved PSCM Procedure 32-1034] | The period of tender advert will align with Eskom Procurement Supply chain management, that is an advert will be within minimum of 14 days |
| If a closed tender, state the names of the suppliers to whom the tender will be issued, confirm how the list of suppliers was derived. | Not applicable |
| If a closed tender, confirm how the tender will be issued, and how long the suppliers will have to respond to the tender. | Not Applicable |
| Confirm if a compulsory tender clarification meeting/site visit is required, and the reasons therefor. | A compulsory clarification meeting will be arranged and take place on MS Team. |
| Confirm any mandatory thresholds / requirements to be applied, the reasons therefor, the criteria and weightings to be allocated to each threshold / requirement. | A tenderer that does not submit mandatory documents by or the complete information required in mandatory documents by the deadlines as stipulated in the Tender Returnable section of the respective Invitation to Tender will be deemed non-responsive. Mandatory commercial requirements are: - Electronic copy of the tender in a PDF format. The price list needs to be submitted in PDF and a copy in excel format (The limit is 50MB per file and total submission of 900MB per submission) - Priced schedule - Signed Contract Data by contractor. - Completed NEC 3 Offer and acceptance. - Submit technical requirements. |
| Confirm the criteria to be applied for evaluation. | Kindly refer to the following table Functional Evaluation Criteria; Percentage of Total. 1. Requirements of 240-171000524; 80%. 2. Experience [section minimum pass-rate: 70%]; 20%. Minimum Total Percentage to be Achieved: 80%. |
| The following section details the Technical Evaluation process to be followed. It is imperative that Tenderers familiarise themselves with this and direct any questions as early as possible to the commercial representative for this tender. Scoring for all evaluations will be conducted as per sheet: Scoring Lookup Important: It is required to complete the orange-shaded "Tenderer's response" / "B-schedule" columns in all of these sheets. This, along with supporting information/proof provided as required, will be used to ascertain the proposal's level of compliance.. General notes:; Tenderers to complete all questions & B-schedule columns and provide all references to supporting documentation.. Tenderers to complete all orange-shaded fields. Eskom evaluators will use blue-shaded fields. Technical Returnables; 1. Technical Evaluation (this Excel). All sheets to be fully completed, and all justification & references provided, as required.. Sheet: 1. Requirements of Spec; Compliance to Eskom Specification 240-171000524: "Intelligent Substation & Security System Specification" will be determined in this section.. Compliance will be determined by means of a clause-by-clause evaluation, as well as a deviation schedule for all clauses not explicitly listed.. The specific requirement of this tender is stipulated in the column labelled: Schedule A.. Schedule A may require specific information to be provided by the tenderer. Where allowed or appropriate, this may be provided as text directly in the column labelled: Schedule B. Should further supporting information be required, this shall be provided separately (i.e. attached) and preferably referred to from Schedule B.. Items for which Schedule A requires only "State Compliance", the tenderer may only state their compliance, i.e. "Comply", "Do Not Comply", or "Partially Comply" (and provide reasons for not/partially complying). Evaluators will use the B-schedule responses (if completed) along with the tenderer's full submission to ascertain compliance.. Tenderers to state their compliance to each requirement in Schedule B (orange-shaded fields).. Eskom evaluators will use blue-shaded fields. Sheet: 2. Experience; These sections are heavily weighted.. By not providing satisfactory detail, the tenderer risks being penalised during Eskom's evaluation.. Where appropriate, detail can be provided directly within the Schedule B column.. Where required, additional documentation must be provided. Tenderers are encouraged to add suitable references (e.g. "See File XYZ attached") to the Schedule B.. Tenderer to state their compliance to each requirement in Schedule B (orange-shaded fields).. Eskom evaluators will use blue-shaded fields. Sheet: 3. Deviations; Tenderer to list all deviations for the standards referenced. This is an assessment of non-compliance and potential risks with the submission. Tenderers should be aware that the evaluation process will assess the acceptability of project deviations and risks, with recommendations presented to governance committees for review, and acceptance or not.. Tenderer to complete all orange-shaded fields. Eskom evaluators will use blue-shaded fields. |
| Confirm if this is a construction-related transaction and if CIDB is applicable. If CIDB is applicable, confirm with SDL&I whether any additional requirements with respect to CIDB that will impact the process/contract are applicable and the impact of these requirements. E.g. - Contract Participation Goal (CPG) relating to the engagement of targeted enterprises as established in the CIDB standard for indirect targeting for enterprise development through Construction works contracts - Contract Skills Development Goal (CSDG) as established in the CIDB Standard for Developing Skills through Infrastructure Contracts | Not applicable, the service provider will use the existing infrastructure within Eskom when doing installation furthermore the material that will be supplied is CIDB not related. |
| Confirm if NIPP Requirements will be applicable or not and where applicable the impact on the process/contract etc. | Note that NIPP will only be applicable for contracts with an FGN component or content / imports of USD 5 million or more. |
| Stipulate the Specific Goals, scoring and evidence that will be applied to the tender in terms of the PPPFA and as provided by SDL&I. | Price points will be calculated out of 80 or 90 for price. Price = Evaluated price, including VAT, and the remaining 10 or 20 is for specific goals. The prices and preference points will be added together to determine the highest scoring tenderer. The reason for choosing both PPPFA price evaluation criteria is: The total contract estimated value is above R50 million and the award can be split depending on the number of bids received. |
| Confirm if any Objective Criteria will be applied to the tender in terms of the PPPFA. If so, stipulate the Objective Criteria and evaluation methodology provided by SDL&I. | Not applicable. |
| Confirm if any Additional Contractual requirements (eg. Due diligence/Financial analysis due to risk assessment) will be applicable to the tender in addition to the mandatory Contractual Requirement of CSD registration (prior to award). | Mandatory Contractual Requirements that must be included in all tenders is the following: Proof of CSD registration. Further contractual requirements are as follows: |
| Contractual Requirements. Quality. Quality Requirements - Category 3: - List of Tender Returnable Category 3 - Form A Category 3 - Contract Quality Plan (CQP) - Quality Control Plan (QCP/ITP) - Supplier Quality Management Specification. SHE Requirements. - The Suppliers/ Tenderers will be required to compile an auditable Health and Safety Plan/Manual as per the provided Client OHS requirements and Contractor Health and Safety requirements Standard (32-726) to comply with the minimum legislative and organisational Health and Safety requirements for this tender. In addition to the legislative requirements governing health and safety, the Suppliers/ Tenderers shall comply with all the Eskom Holdings SOC Limited policies, procedures and standards. - Eskom's Annexure B: Acknowledgement of OHS legal and other requirements form, signed and submitted by the Tenderer with the Supplier OHS tender returnable. - OHS Plan. Must address the project /scope of work OHS risk(s) and aligned with the Client Health and Safety (OHS) requirements. - Baseline OHS Risk Assessment (BRA) Identification, assessment and management of OHS risks related to the scope of work. The methodology used for the risk assessment must be provided together with the Baseline Risk Assessment (BRA) - SHE Competencies: - Safety officer CR (8.5) (SACPCMP) - Construction Manager CR (8.1) (SACPCMP) - Supervisor CR(8.7) - Assistant Supervisor CR (8.8) - SHE Representative OHACT Section 17 - Hazardous Biological Agents Controller (HBAR) - Incident investigator GAR 9 (2) - Crane operator DMR 18 (11) - Lifting Machine Inspector DMR 18 (1) - Lifting Tackle inspector DMR 18(10) (e) - Inspector of Fall Arrest Systems – CR 10 (2)(d) - Mobile plant operator CR (23) - Excavation Supervisor CR (13) - Valid Letter of Good Standing (COIDA or equivalent.) - SHE policy signed by CEO/ MD – The submitted policy document must comply to OHS Act Section 7 or ISO 45001 requirements. - Medical Surveillance Program - Substance Abuse Program including proof of ownership if screening devices. Environmental Requirements. ENVIRONMENTAL The following Environmental documentation is required to be submitted as part of the tender returnable. - Environmental Policy- Company must demonstrate commitment to pollution prevention, compliance to Environmental legislation and continuous improvement. The policy must be signed and dated - Company Organogram- Showing Environmental Resource - Waste management strategy/ Plan- Plan must detail expected waste streams, how the waste would be stored whilst on site and how the waste would be, re-used, re-cycled or disposed of. - Environmental Emergency Preparedness & Response Plan- The plan must list possible environmental emergencies that could occur, and how to respond to such emergencies - Environmental incident Register- A template to record Environmental incidents. - Environmental Competency Training certificate- Proof of staff having received Environmental training. Financial Evaluation. Latest, approved (No draft annual financial statements or managements accounts are allowed for this process) annual financial statements of the tendering company (Not Parent or ultimate holding company), including: - Background to the company - A signed director’s report. - A signed auditor’s/reviewer’s/compiler’s/accounting officer’s report - Statement of financial position - Statement of comprehensive income - Statement of changes in equity - Statement of cash flows - Notes to the financial statements. - A signed copy of the public interest score (only applicable to South African entities that are not audited) - Giving the actual score - Indicating whether the company is owner managed or not - Confirming whether the annual financial statements were externally prepared or not. - Copies of the ITA34C for the current & previous years of assessment (only applicable to South African entities that are not audited) - For unincorporated JV or a SPV, each partner in the JV or a SPV must submit its annual financial statements including all items listed above.. |
| State if there will be a need for post-tender negotiations, on what basis and how suppliers will be selected for post-tender negotiations after evaluations. | Yes, the post tender negotiations will be conducted with the highest scoring tenderer in accordance with PPPFA act |
| If execution will be conducted via negotiations (no prior tendering) with one supplier (sole/single source) or two suppliers, confirm the reasons justifying why there is only one/two capable and independent suppliers available in the market. | Not Applicable. |

- SDL&I STRATEGY

| Is this procurement considered to be a designated sector as confirmed by the dtic. | Yes, some components in this procurement are designated for local content and production. |
| --- | --- |
| If not a designated sector, is Eskom intending to self-designate the commodity, if so, has approval been granted by the relevant authority? | No. |
| If a designated sector, confirm the threshold to be applied to local content. | Cables 90% |
| St State if any additional SDL&I requirements will be applied, if so, state the targets, under which requirement will it included in the tender data/requirements and the methodology for evaluation thereof. | None. |
| Confirm if local manufacturing opportunities are available with respect to this procurement and how such opportunities will be considered for purposes of evaluation. | Only as far as cables are concerned. |

- CONTRACTING STRATEGY

| If procurement is for a project or for phased delivery, confirm the selected contracting strategy (e.g. design and build, EPC, turnkey, etc.), and motivate the reasons therefor, and how the selected contracting strategy mitigates risks for Eskom. | The selection of the NEC3 TSC (Design and Build) ensures that Eskom is not just buying hardware but is securing a guaranteed security service. This strategy shifts the risk of system failure and technical misalignment to the contractor while providing Eskom with the flexibility to scale the pilot based on real-world performance. |
| --- | --- |
| State the selected NEC contract, with main and secondary options, to be used to give effect to the supply of the assets / goods / services, and why this selection best mitigates risks for Eskom. | NEC3 Term Service Contract (TSC) - Main Option: Option A (Priced contract with price list). - Dispute Resolution Option: - W1: Dispute resolution. - Secondary Options: - X2: Changes in the law (Protects against security regulation shifts). - X17: Low service damages (Links payment to KPI performance). - X18: Limitation of liability. - X19: Task Orders (Critical for phased delivery/installation). |
| Confirm if any specially drafted Z clauses are required, and the reasons for the inclusion thereof. |  |
| If the NEC is not an appropriate form of contract, state the reasons therefor, the most appropriate form of contract to be used, and confirm approval for the use of a non-standard agreement by the Eskom Legal Department. | NEC3 TSC is considered the "Standard" and most appropriate form of contract. |

- PROCUREMENT PLAN

The following dates set out the projected completion dates for the procurement activities.

| No. | Description of procurement activity | Projected completion date |
| --- | --- | --- |
| 1. | Contract strategy sign off: |  |
| 2. | Tender Advert date |  |
| 3. | Tender Clarification meeting |  |
| 4. | Tender Closing date |  |
| 5. | Evaluation of all streams |  |
| 6. | Mandate to negotiate |  |
| 7. | Negotiations |  |
| 8. | Feedback report |  |
| 9. | Contract award |  |

The following sets out the details of the various evaluations (Commercial /technical etc)

| Name of Evaluator | Designation of Evaluator | Evaluation Lead Times/completion dates |
| --- | --- | --- |

- DOCUMENT MANAGEMENT

The relevant Middle Manager Procurement, Sheileen Parsotam confirms that the documents listed in the P&SCM Documentation Completeness Checklist for Buyer’s Procurement File and Uploading on the EDMS have been checked, verified, and marked as complete and are stored in the Electronic Documentation Management System (EDMS) under this folder [Insert EDMS link where documents are stored].

- DECLARATION & SIGNATORIES

I hereby declare that I do have a conflict of interest in this matter.

I have completed a Conflict-of-Interest form and it is attached to this Strategy. I confirm that all information contained herein is, to the best of my knowledge, true and correct.

Note: This declaration above applies to the CFT, as well as those recommending/ supporting/approving the Strategy. Evidence of the completed Conflict of Interest declarations of the members of the CFT/relevant DAA are attached to this submission.

DEVELOPED BY: [Drafting note: Include all members of CFT in table below]

| Name | Designation | Signature |
| --- | --- | --- |
| Lonwabo Mavukwana | Senior Advisor Procurement |  |
| Elliot Ntaka | Programme Manager (Acting) |  |
| Henry Jordaan |  |  |
| Elre Du Plessis | Security Manager |  |
| Lusanda Ntombana |  |  |
| Ayanda Twetwa | Senior Advisor SDL and I |  |
| Chuma Xoseni | Quantity Surveyor Officer |  |
| Nathen Felkers | SHE officer |  |
| Shu-Aib Martin | Manager Contract Management |  |
| Thandokazi Ma |  |  |
| Archie Mabula |  |  |
| Bulelani Flekisi | Senior Advisor Quality Assurance |  |
| Zininzi Mfenqa | Manager Engineering Design |  |
| Mzamo Mndende | Manager Management Accounting |  |

| NAME: |  |
| --- | --- |
| DESIGNATION AND DIVISION |  |
| SIGNATURE: |  |
| DATE: |  |
| REMARKS ON SUBMISSION: |  |

DOA APPROVAL PROCESS:

| Recommended (as per approved DOA) |  | Conditionally Recommended |  | Rejected |  |
| --- | --- | --- | --- | --- | --- |
| NAME: |  |  |  |  |  |
| DESIGNATION: |  |  |  |  |  |
| SIGNATURE: |  |  |  |  |  |
| DATE: |  |  |  |  |  |
| REMARKS ON SUBMISSION: |  |  |  |  |  |

| Supported (as per approved DOA) |  | Conditionally Supported |  | Rejected |  |
| --- | --- | --- | --- | --- | --- |
| NAME: |  |  |  |  |  |
| DESIGNATION: |  |  |  |  |  |
| SIGNATURE : |  |  |  |  |  |
| DATE: |  |  |  |  |  |
| REMARKS ON SUBMISSION: |  |  |  |  |  |

| Approved by DAA. |  | Conditionally Approved by DAA |  | Rejected by DAA |  |
| --- | --- | --- | --- | --- | --- |
| NAME: |  |  |  |  |  |
| DESIGNATION: |  |  |  |  |  |
| SIGNATURE OF DAA: |  |  |  |  |  |
| DATE: |  |  |  |  |  |

REMARKS ON SUBMISSION: