{"text_format":"3","workbook":"xlsx","n_sheets":7,"sheets":["SECTION A","SECTION C","SECTION DB","SECTION LB","SECTION L","SECTION LF","SUMMARY"],"not_rendered":{"defined_names":7},"read":"whole","date_system":"1900"}

{"sheet":"SECTION A","index":0,"n_rows":194,"n_cols":9,"rows_kept":194,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[4,0,4,8],[5,0,5,8],[6,3,6,4],[7,0,7,8],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,3,22,4],[23,3,23,4],[24,3,24,4],[25,3,25,4],[26,3,26,4],[27,3,27,4],[28,3,28,4],[29,3,29,4],[30,3,30,4],[31,3,31,4],[32,3,32,4],[33,3,33,4],[34,3,34,4],[35,3,35,4],[36,3,36,4],[37,3,37,4],[38,3,38,4],[39,3,39,4],[40,3,40,4],[41,0,41,7],[42,0,42,8],[43,0,43,8],[44,0,44,8],[45,0,45,8],[46,0,46,8],[47,0,47,8],[48,0,48,8],[49,3,49,4],[50,0,50,7],[52,3,52,4],[53,3,53,4],[54,3,54,4],[55,3,55,4],[56,3,56,4],[57,3,57,4],[58,3,58,4],[59,3,59,4],[60,3,60,4],[61,3,61,4],[62,3,62,4],[63,3,63,4],[64,3,64,4],[65,3,65,4],[66,3,66,4],[67,3,67,4],[68,3,68,4],[69,3,69,4],[70,3,70,4],[71,3,71,4],[72,3,72,4],[73,3,73,4],[74,3,74,4],[75,3,75,4],[76,3,76,4],[77,3,77,4],[78,3,78,4],[79,0,79,7],[80,0,80,8],[81,0,81,8],[82,0,82,8],[83,0,83,8],[84,0,84,8],[85,0,85,8],[86,3,86,4],[87,0,87,7],[88,3,88,4],[89,3,89,4],[90,3,90,4],[91,3,91,4],[92,3,92,4],[93,3,93,4],[94,3,94,4],[95,3,95,4],[96,3,96,4],[97,3,97,4],[98,3,98,4],[99,3,99,4],[100,3,100,4],[101,3,101,4],[102,3,102,4],[103,3,103,4],[104,3,104,4],[105,3,105,4],[106,3,106,4],[107,3,107,4],[108,3,108,4],[109,3,109,4],[110,3,110,4],[111,3,111,4],[112,0,112,7],[113,0,113,8],[114,0,114,8],[115,0,115,8],[116,0,116,8],[117,0,117,8],[118,0,118,8],[119,3,119,4],[120,0,120,7],[121,3,121,4],[122,3,122,4],[123,3,123,4],[124,3,124,4],[125,3,125,4],[126,3,126,4],[127,3,127,4],[128,3,128,4],[129,3,129,4],[130,3,130,4],[131,3,131,4],[132,3,132,4],[133,3,133,4],[134,3,134,4],[135,3,135,4],[136,3,136,4],[137,3,137,4],[138,3,138,4],[139,3,139,4],[140,3,140,4],[141,3,141,4],[142,3,142,4],[143,3,143,4],[144,3,144,4],[145,3,145,4],[146,3,146,4],[147,3,147,4],[148,3,148,4],[149,3,149,4],[150,3,150,4],[151,3,151,4],[152,3,152,4],[153,3,153,4],[154,3,154,4],[155,3,155,4],[156,3,156,4],[157,3,157,4],[158,3,158,4],[159,0,159,7],[160,0,160,8],[161,0,161,8],[162,0,162,8],[163,0,163,8],[164,0,164,8],[165,0,165,8],[166,3,166,4],[167,0,167,7],[168,3,168,4],[169,3,169,4],[170,3,170,4],[171,3,171,4],[172,3,172,4],[173,3,173,4],[174,3,174,4],[175,3,175,4],[176,3,176,4],[177,3,177,4],[178,3,178,4],[179,3,179,4],[180,3,180,4],[181,3,181,4],[182,3,182,4],[183,3,183,4],[184,3,184,4],[185,3,185,4],[186,3,186,4],[187,3,187,4],[193,0,193,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["PRELIMINARY AND GENERAL"]
["SECTION 1200 A"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
[1,null,"SABS 1200A","PRELIMINARY AND GENERAL"]
[{"$nulls":3},"Note: Sum of 8.3 and 8.4 on P&G's excluding provisional sums should not exceed 15% of the project value"]
[]
[null,null,8.3,"FIXED-CHARGES AND VALUE RELATED ITEMS"]
[]
[1.1,null,"8.3.1","Contractural Requirements",null,"Sum",1]
[]
[null,null,"8.3.2","Establishment of Facilities on site"]
[]
[1.2,"LI","8.3.2.1","Facilities for the Engineer"]
[]
[{"$nulls":3},"a) Furnished Offices",null,"Sum",1]
[{"$nulls":3},"c) Contract Nameboards",null,"No.",1]
[1.3,null,"PSAB.3.2.2.d"," Survey Assistants and Equipments",null,"Sum",1]
[1.4,null,"PSAB.3.2.3.e","Accomodation for Engineer 's Representatives( including new sleeping bed with mattress, cooking stove and fridge)",null,"Sum",1]
[1.5,null,"PSAB.3.2.4.f","Carports",null,"No.",2]
[]
[1.6,"LI","8.3.2.2","Facilities for the Contractor"]
[]
[{"$nulls":3},"a) Office and storage sheds",null,"Sum",1]
[{"$nulls":3},"b) Workshops",null,"Sum",1]
[{"$nulls":3},"d) Living Accommodation",null,"Sum",1]
[{"$nulls":3},"e) Ablution and latrine facilities",null,"Sum",1]
[{"$nulls":3},"f) Tools and Equipment",null,"Sum",1]
[{"$nulls":3},"g) Water Supplies, Electric Power and Telephone",null,"Sum",1]
[{"$nulls":3},"i) Access ",null,"Sum",1]
[1.7,null,"PSAB.3.2.3.h"," Testing Equipment",null,"Sum",1]
[]
[1.8,null,"8.3.3","Other fixed-charge obligations "]
[{"$nulls":3},1,null,"Sum",1]
[{"$nulls":3},2,null,"Sum",1]
[{"$nulls":3},3,null,"Sum",1]
[]
["TOTAL CARRIED FORWARD"]
[]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY"]
["CONTRACT NO.:INF-W06/2026/2027"]
["PRELIMINARY AND GENERAL"]
["SECTION 1200 A"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[]
[1.9,null,"8.3.4","Removal of Site Establishment",null,"Sum",1]
[]
[{"v":1.1,"d":"1.10"},null,"PSAB.3.4.a","Additional Sampling of Materials and Analysis",null,"Psum",1,{"v":30000,"d":"30,000.00"},{"$f":"G55*H55","v":{"v":30000,"d":"R 30,000.00"}}]
[1.11,null,"PSAB.5.4.b","Handling cost and profit in respect of 1.1.10 above",null,"%",{"$f":"I55","v":{"v":30000,"d":"30,000.00"}}]
[1.12,null,"PSAB.5.5.c","Submission of Health and Safety File",null,"Psum",1,{"v":30000,"d":"30,000.00"},{"$f":"G57*H57","v":{"v":30000,"d":"R 30,000.00"}}]
[1.13,null,"PSAB.5.5.d","Handling cost and profit in respect of 1.3.12 above",null,"%",{"$f":"I57","v":{"v":30000,"d":"30,000.00"}}]
[]
[null,null,8.4,"TIME-RELATED ITEMS"]
[]
[null,null,"PSA8.4.2","Operation and maintenance of facilities on site for the duration of construction period"]
[]
[1.15,null,"8.4.2.1","Facilities for the Engineer"]
[]
[null,"LI","PSAB4.2.a","a) Furnished offices",null,"Month",7]
[null,null,"PSAB4.2.b","b) Telephone(R1000 per month airtime)",null,"Month",7]
[null,"LI","PSAB4.2.c","c) Contract Nameboards",null,"Month",7]
[null,"LI","PSAB.4.2.d","d) Survey assistants and maintenance of survey equipments",null,"Month",7]
[null,"LI","PSAB4.2.e","e) Carports",null,"Month",7]
[1.16,null,"8.4.2.2","Facilities for the Contractor"]
[]
[null,"LI",null,"a) Office and storage sheds",null,"Month",7]
[null,"LI",null,"b) Workshops",null,"Month",7]
[null,"LI",null,"d) Living Accommodation",null,"Month",7]
[null,"LI",null,"e) Ablution and latrine facilities",null,"Month",7]
[null,"LI",null,"f) Tools and Equipment",null,"Month",7]
[null,"LI",null,"g) Water Supplies, Electric Power and Communications",null,"Month",7]
[{"$nulls":3},"i) Access ",null,"Month",7]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY"]
["CONTRACT NO.:INF-W06/2026/2027"]
["PRELIMINARY AND GENERAL"]
["SECTION 1200 A"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[1.17,null,"PSA8.4.2.h","Testing Equipment",null,"Month",7]
[]
[1.18,null,"8.4.3","Supervision for duration of construction",null,"Month",7]
[]
[1.19,null,"8.4.4","Company and head office overhead costs for the duration of the construction",null,"Month",7]
[]
[{"v":1.2,"d":"1.20"},null,"PSAB4.2.b","Quality Control, Testing and Certification",null,"Month",7]
[]
[null,null,8.5,"SUMS STATED PROVISIONALLY BY THE ENGINEER:"]
[]
[1.21,null,"PSA8.5.1.a","Remunaration of a Community Liaison Officer at R4500.00 per month for the duration of construction",null,"Psum",{"v":1,"d":"1.00"},{"v":63000,"d":"R 63,000.00"},{"$f":"H99*G99","v":{"v":63000,"d":"R 63,000.00"}}]
[]
[1.22,null,"PSA8.5.2.b","Training of local labour by accrediated training provider",null,"Psum",{"v":1,"d":"1.00"},{"v":200000,"d":"R 200,000.00"},{"$f":"H101*G101","v":{"v":200000,"d":"R 200,000.00"}}]
[]
[1.23,null,"PSA8.5.3.c","Remuneration of local labour undergoing training",null,"Psum",{"v":1,"d":"1.00"},{"v":20000,"d":"R 20,000.00"},{"$f":"H103*G103","v":{"v":20000,"d":"R 20,000.00"}}]
[]
[1.24,null,"PSA8.5.4.d","Allowance for PSC members  on official meetings @ R150.00 per member present with no apology  ",null,"Psum",{"v":1,"d":"1.00"},{"v":30000,"d":"R 30,000.00"},{"$f":"H105*G105","v":{"v":30000,"d":"R 30,000.00"}}]
[]
[1.25,null,"PSA8.5.4.d","Occupational Health and Monitoring for the duration of the project",null,"Psum",{"v":1,"d":"1.00"},{"v":313044,"d":"R 313,044.00"},{"$f":"H107*G107","v":{"v":313044,"d":"R 313,044.00"}}]
[]
[1.26,null,"PSA8.5.4.d","Environmental Monitoring for the duration of the project",null,"Psum",{"v":1,"d":"1.00"},{"v":313044,"d":"R 313,044.00"},{"$f":"H109*G109","v":{"v":313044,"d":"R 313,044.00"}}]
[]
[1.27,null,"PSA8.3.7.g","Provision of Cellular telephones ",null,"Psum",{"v":1,"d":"1.00"},{"v":40000,"d":"R 40,000.00"},{"$f":"H111*G111","v":{"v":40000,"d":"R 40,000.00"}}]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY"]
["CONTRACT NO.:INF-W06/2026/2027"]
["PRELIMINARY AND GENERAL"]
["SECTION 1200 A"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[1.28,null,"PSA8.3.9.h","Protection of pedestrians during construction",null,"Psum",{"v":1,"d":"1.00"},{"v":40000,"d":"R 40,000.00"},{"$f":"H122*G122","v":{"v":40000,"d":"R 40,000.00"}}]
[]
[1.29,null,"PSA8.3.10.i","Provision for materials, special services,quality assurance and third party",null,"Psum",{"v":1,"d":"1.00"},{"v":50000,"d":"R 50,000.00"},{"$f":"H124*G124","v":{"v":50000,"d":"R 50,000.00"}}]
[]
[{"v":1.3,"d":"1.30"},null,"PSA8.3.10.j","Handling cost and profit in respect of all Provisional Sums above",null,"%",{"$f":"SUM(I99+I101+I103+I105+I107+I109+I111+I122+I124)","v":{"v":1069088,"d":"1,069,088.00"}}]
[]
[null,null,8.6,"PRIME COST ITEMS"]
[]
[1.31,null,"PSA8.6.1.a","Inspection, handling,transportation and installation of materials such as pipes and fittings etc.",null,"PCSum",{"v":1,"d":"1.00"},{"v":50000,"d":"R50,000.00"},{"v":50000,"d":"R 50,000.00"}]
[1.32,null,"PSA8.6.1.b","Handling cost and profit in respect of 1.4.1 above",null,"%",{"$f":"I130","v":{"v":50000,"d":"50,000.00"}}]
[null,null,8.7,"DAY WORKS"]
[]
[1.33,null,"PSA8.7.1","a)Labour"]
[]
[{"$nulls":3},"i)Site Agent",null,"hours",8]
[{"$nulls":3},"ii)Qualified Artisan/s",null,"hours",8]
[{"$nulls":3},"iii)Qualified Mechanic/s",null,"hours",8]
[{"$nulls":3},"iv)Foreman",null,"hours",8]
[{"$nulls":3},"v)Semi-skilled ",null,"hours",8]
[{"$nulls":3},"vi)Unskilled ",null,"hours",8]
[]
[1.34,null,"PSA8.7.2","b)Planthire: work rates on site"]
[]
[{"$nulls":3},"i)Tipper truck(5.5m3)",null,"hours",8]
[{"$nulls":3},"ii)Tipper truck(10m3)",null,"hours",8]
[{"$nulls":3},"iii)Flatbed truck (7ton)",null,"hours",8]
[{"$nulls":3},"iv)LDV",null,"hours",8]
[{"$nulls":3},"v)Tractor loader backhoe(TLB)",null,"hours",8]
[{"$nulls":3},"vi) Pedestrian roller( Bomag 90)",null,"hours",8]
[{"$nulls":3},"vii) Concrete mixer( 0.9m3)(wet)",null,"hours",8]
[{"$nulls":3},"viii) Water Tanker(10000L)",null,"hours",8]
[{"$nulls":3},"ix) Water Tanker(16000L)",null,"hours",8]
[{"$nulls":3},"x) Compressor",null,"hours",8]
[{"$nulls":3},"xi) Excavator",null,"hours",8]
[{"$nulls":3},"xii) Compactor…….(specify size)",null,"hours",8]
[{"$nulls":3},"xiii) Water pumps",null,"hours",8]
[{"$nulls":3},"xiv) Dumper…………….(specify size)",null,"hours",8]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY"]
["CONTRACT NO.:INF-W06/2026/2027"]
["PRELIMINARY AND GENERAL"]
["SECTION 1200 A"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[1.35,null,"PSA8.7.3","c) Planthire: Transport cost to and from site for low -bed truck",null,"km",300]
[]
[null,null,8.8,"TEMPORARY WORKS"]
[]
[1.36,null,"8.8.1","Main Access Road to works",null,"Sum",1]
[1.37,null,"8.8.2","Accomodation of Traffic for the duration of construction ",null,"Sum",1]
[]
[null,null,"8.8.4","Existing Services"]
[]
[1.38,"LI",null,"Temporary protection of existing services",null,"Psum",1,{"v":60000,"d":"R 60,000.00"},{"$f":"H178*G178","v":{"v":60000,"d":"R 60,000.00"}}]
[]
[1.39,"LI",null,"Relocation of existing services",null,"Psum",1,{"v":80000,"d":"R 80,000.00"},{"$f":"H180*G180","v":{"v":80000,"d":"R 80,000.00"}}]
[]
[{"v":1.4,"d":"1.40"},"LI",null,"Provision of an instrument to detection the location of existing services",null,"Psum",1,{"v":60000,"d":"R 60,000.00"},{"$f":"H182*G182","v":{"v":60000,"d":"R 60,000.00"}}]
[]
[1.41,null,null,"Provision of for rented hotel and other accomodation",null,"Psum",1,{"v":60000,"d":"R 60,000.00"},{"$f":"H184*G184","v":{"v":60000,"d":"R 60,000.00"}}]
[]
[1.42,null,null,"Handling cost and profit in respect of existing services  above",null,"%",{"$f":"SUM(I178+I180+I182+I184)","v":{"v":260000,"d":"260,000.00"}}]
{"$rows_empty":7}
["TOTAL CARRIED FORWARD TO SUMMARY"]

{"sheet":"SECTION C","index":1,"n_rows":39,"n_cols":9,"rows_kept":39,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[4,0,4,8],[5,0,5,8],[6,3,6,4],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,3,22,4],[23,3,23,4],[24,3,24,4],[25,3,25,4],[26,3,26,4],[27,3,27,4],[28,3,28,4],[29,3,29,4],[30,3,30,4],[31,3,31,4],[32,3,32,4],[33,3,33,4],[34,3,34,4],[35,3,35,4],[36,3,36,4],[37,3,37,4],[38,0,38,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["SITE CLEARANCE"]
["SECTION 1200 C"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
[2,null,"SABS        1200C","SITE CLEARANCE"]
[]
[2.1,null,"8.2.1","Clear and grub: 3meter wide strip",null,"m",{"v":22950,"d":"22950.00"}]
[]
[null,null,"8.2.2","Remove and grub large trees and tree stumps of girth:"]
[]
[2.2,null,null,"a)Over 1,0 m and up to and including 2,0 m",null,"No",{"v":5,"d":"5.00"}]
[2.3,null,null,"b)Over 2,0 m and up to and including 3,0 m",null,"No",{"v":2,"d":"2.00"}]
[2.4,null,null,"c)Over 3,0 m and up to and including 4,0 m",null,"No",{"v":2,"d":"2.00"}]
[]
[2.5,null,"8.2.5","Take down and reinstate existing fences",null,"km",{"v":0.8,"d":"0.80"}]
[]
[2.6,null,"8.2.6","Clear hedge or fence or both where not schedule separately",null,"m",{"v":100,"d":"100.00"}]
[]
[2.7,null,"8.2.9","Transport materials and debris to unspecified sites and dump",null,"m3.km",{"v":3500,"d":"3500.00"}]
[]
[2.8,null,"8.2.10","Remove topsoil to nominal depth of 150mm and stockpile",null,"m³",{"v":220,"d":"220.00"}]
[]
[null,null,"PSC2.11","Remove topsoil to spoil on a designated site identified by the community representatives",null,"m³",{"v":220,"d":"220.00"}]
[]
[2.9,null,"PSC2.12","Demolish existing concrete",null,"m³",{"v":2,"d":"2.00"}]
{"$rows_empty":9}
["TOTAL CARRIED TO SUMMARY"]

{"sheet":"SECTION DB","index":2,"n_rows":95,"n_cols":9,"rows_kept":95,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[5,0,5,8],[6,3,6,4],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,3,22,4],[23,3,23,4],[24,3,24,4],[25,3,25,4],[26,3,26,4],[27,3,27,4],[28,3,28,4],[29,3,29,4],[30,0,30,7],[31,0,31,8],[32,0,32,8],[33,0,33,8],[34,0,34,8],[35,0,35,8],[36,0,36,8],[37,3,37,4],[38,0,38,7],[39,3,39,4],[40,3,40,4],[41,3,41,4],[42,3,42,4],[43,3,43,4],[44,3,44,4],[45,3,45,4],[46,3,46,4],[47,3,47,4],[48,3,48,4],[49,3,49,4],[50,3,50,4],[51,3,51,4],[52,3,52,4],[53,3,53,4],[54,3,54,4],[55,0,55,7],[56,0,56,8],[57,0,57,8],[58,0,58,8],[59,0,59,8],[60,0,60,8],[61,0,61,8],[62,3,62,4],[63,0,63,8],[64,0,64,7],[65,3,65,4],[66,3,66,4],[67,3,67,4],[68,3,68,4],[69,3,69,4],[70,3,70,4],[71,3,71,4],[72,3,72,4],[73,3,73,4],[74,3,74,4],[75,3,75,4],[76,3,76,4],[77,3,77,4],[78,3,78,4],[79,3,79,4],[80,3,80,4],[81,3,81,4],[82,3,82,4],[83,3,83,4],[84,3,84,4],[85,3,85,4],[86,3,86,4],[87,3,87,4],[88,3,88,4],[89,3,89,4],[90,3,90,4],[91,3,91,4],[92,3,92,4],[93,3,93,4],[94,0,94,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["EARTHWORKS( PIPE TRENCHES)"]
["SECTION 1200 DB"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
[3,null,"SABS1200DB","EARTHWORKS (PIPE TRENCHES)"]
[]
[null,null,"8.3.2","Bulk Excavation"]
[]
[3.1,null,"8.3.2.a","Excavate in all materials and use for embankment or backfill,compose and  dispose of surplus/unsuitable material within a freehaul distance of 2,0km as ordered for the following :"]
[]
[{"$nulls":3},"i) Water pipes",null,"m³",{"v":13870,"d":"13870.00"}]
[3.2,null,"8.3.2.b","Extra over item 8.3.2a above and inclusive of freehaul distance of 2,0km for:         Note:Agreement should be made between the Engineer and the Contractor prior to the execution of this activities to avoid unnecessary disputes"]
[]
[{"$nulls":3},"a)Intermediate excavation  ",null,"m³",{"v":7980,"d":"7980.00"}]
[]
[{"$nulls":3},"b)Hard rock excavation     ",null,"m³",{"v":5750,"d":"5750.00"}]
[]
[{"$nulls":3},"c)Boulder Excavation , Class A     ",null,"m³",{"v":2850,"d":"2850.00"}]
[]
[{"$nulls":3},"d)Boulder Excavation (By Blasting)     ",null,"m³",{"v":3434,"d":"3434.00"}]
[]
[3.3,"LI","PSDB3.2.c","Labour Intensive Method on Exacavation :"]
[]
[{"$nulls":3},"i) Soft material",null,"m³",{"v":550,"d":"550.00"}]
[{"$nulls":3},"ii) Intermediate material",null,"m³",{"v":650,"d":"650.00"}]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["EARTHWORKS( PIPE TRENCHES)"]
["SECTION 1200 DB"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[3.4,"LI","PSDB3.2.d","Labour Intensive Method on Backfilling:"]
[]
[{"$nulls":3},"i) Backfill and Compaction of material of all type",null,"m³",{"v":12500,"d":"12500.00"}]
[{"$nulls":3},"ii) Soilcrete backfill where directed by the Engineer",null,"m³",{"v":450,"d":"450.00"}]
[{"$nulls":3},"iii) Dispose of surplus excavted material(limited overhaul of 0,5 to 1km).",null,"m³",{"v":160,"d":"160.00"}]
[{"$nulls":3},"iv) Backfill road crossings using a commercial or designated borrowpit type G4 class of material compacted to 98% Mod AASHTO density",null,"m³",{"v":300,"d":"300.00"}]
[{"$nulls":3},"v) Backfill to structures using approved cohessionless material from stockpile",null,"m³",{"v":300,"d":"300.00"}]
[]
[null,null,"8.3.3","Excavation Ancillaries"]
[3.5,null,"8.3.3.1","Make up deficiency in backfill ,material"]
[]
[{"$nulls":3},"b) Extra over for importation of materials from commercial sources or from a designated borrow pits, placed , mixed,watered, lay, compacted to 95% mod.AASHTO in layers not exceeding 150mm and tested by an accrediated independent  laboratory.",null,"m³",{"v":3200,"d":"3200.00"}]
[{"$nulls":3},"c)Dealing with overburden on designated borrow pits",null,"m³",{"v":350,"d":"350.00"}]
[3.6,null,"8.3.3.2","Opening up and closing down of designated borrow pits",null,"Psum",{"v":1,"d":"1.00"},{"v":20000,"d":"20,000.00"},{"$f":"H53*G53","v":{"v":20000,"d":"R 20,000.00"}}]
[3.7,null,"PSDB3.2","Handling cost and profit in respect of 4.16 above",null,"%",{"$f":"I53","v":{"v":20000,"d":"20000.00"}}]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["EARTHWORKS( PIPE TRENCHES)"]
["SECTION 1200 DB"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
["BROUGHT FORWARD"]
[]
[3.8,null,"8.3.3.4","Overhaul"]
[]
[{"$nulls":3},"a) Limited overhaul( 0,5km to 1,0km)",null,"m³",{"v":362,"d":"362.00"}]
[{"$nulls":3},"b) Overhaul in excess of free-haul of 1,0km",null,"m³.km",{"v":5500,"d":"5500.00"}]
[]
[3.9,null,"8.3.4","Particular Items"]
[]
[{"$nulls":3},"a) Shore trench opposite structure or service",null,"m",{"v":100,"d":"100.00"}]
[{"$nulls":3},"b) Tempoary works( including provision of necessay equipments, operate,maintanance and removing them):i.e control of water inflow",null,"sum",{"v":1,"d":"1.00"}]
[]
[{"v":3.1,"d":"3.10"},"LI","PSDB3.5","Existing Services"]
[]
[{"$nulls":3},"a. Excavate and expose of existing  services",null,"m³",{"v":120,"d":"120.00"}]
[]
[3.11,"LI","8.3.6.1","Re-instating of road surfaces complete with all courses"]
[{"$nulls":3},"i) Compaction in road reserves",null,"m2",{"v":1200,"d":"1200.00"}]
[]
[3.12,"LI","PSDB3.6.2","Extra-over item3,3,1 by means of 4% stabilized backfill material and the density compaction test(90%) layer(150mm) as ordered by the Engineer:"]
[]
[{"$nulls":3},"a) Lime stabilisation layer",null,"t","Rate Only",null,"Rate Only"]
[{"$nulls":3},"b) Cement stabilisation layer",null,"t",{"v":0.4,"d":"0.40"}]
{"$rows_empty":7}
["TOTAL CARRIED TO SUMMARY"]

{"sheet":"SECTION LB","index":3,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[4,0,4,8],[5,0,5,8],[6,3,6,4],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,3,22,4],[23,3,23,4],[24,3,24,4],[25,3,25,4],[26,3,26,4],[27,3,27,4],[28,3,28,4],[29,3,29,4],[30,3,30,4],[31,3,31,4],[32,3,32,4],[33,3,33,4],[34,3,34,4],[35,3,35,4],[36,3,36,4],[37,3,37,4],[38,3,38,4],[39,3,39,4],[40,3,40,4],[41,3,41,4],[42,3,42,4],[43,0,43,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["BEDDING FOR WATER PIPES"]
["SECTION 1200 LB"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
[4,null,"SABS 1200LB","BEDDING "]
[]
[4.1,null,"8.2.1","Provision of bedding from trench excavation:"]
[]
[{"$nulls":3},"a)Selected granular material ",null,"m³",{"v":3654,"d":"3654.00"}]
[{"$nulls":3},"b)Selected fill material",null,"m³",{"v":2436,"d":"2436.00"}]
[]
[null,null,"8.2.2","Provision of bedding by importation:"]
[]
[4.2,null,"8.2.2.1","From other necessary excavations:"]
[]
[{"$nulls":3},"a)Selected granular material",null,"m³",{"v":800,"d":"800.00"}]
[{"$nulls":3},"b)Selected fill material",null,"m³",{"v":1100,"d":"1100.00"}]
[]
[4.3,null,"8.2.2.2","From borrow pits:"]
[]
[{"$nulls":3},"a)Selected granular material ",null,"m³",{"v":220,"d":"220.00"}]
[{"$nulls":3},"b)Selected fill material   ",null,"m³",{"v":420,"d":"420.00"}]
[]
[4.4,null,"8.2.2.3","From commercial source( Provincially) "]
[]
[{"$nulls":3},"a)Selected granular material",null,"m³",{"v":100,"d":"100.00"}]
[{"$nulls":3},"b)Selected fill material",null,"m³",{"v":100,"d":"100.00"}]
[]
[4.5,"LI","8.2.3","Concrete bedding craddle(20Mpa/19mm)",null,"m³",{"v":20,"d":"20.00"}]
[]
[4.6,"LI","8.2.4","Encasing of pipes in concrete"]
[]
[{"$nulls":3},"a) Class 25Mpa/19mm",null,"m³",{"v":40,"d":"40.00"}]
[{"$nulls":3},"b) Extra -over items 8.2.2 for bedding stabilized with 4% cement as ordered by the engineer",null,"m³",{"v":75,"d":"75.00"}]
[]
[4.7,null,"8.2.5","Overhaul of material for bedding cradle and selected fill blanket",null,"m³.km",{"v":3312,"d":"3312.00"}]
[]
[4.8,"LI","PSLB8.2.6a","Compaction of trench bottom",null,"m2",{"$f":"30450","v":{"v":30450,"d":"30450.00"}}]
[]
["TOTAL CARRIED TO SUMMARY"]

{"sheet":"SECTION L","index":4,"n_rows":166,"n_cols":9,"rows_kept":166,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[4,0,4,8],[5,0,5,8],[6,3,6,4],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,3,22,4],[23,3,23,4],[24,3,24,4],[25,3,25,4],[26,3,26,4],[27,3,27,4],[28,3,28,4],[29,3,29,4],[30,3,30,4],[31,3,31,4],[32,3,32,4],[33,3,33,4],[34,3,34,4],[35,3,35,4],[36,3,36,4],[37,0,37,7],[38,0,38,8],[39,0,39,8],[40,0,40,8],[41,0,41,8],[42,0,42,8],[43,3,43,4],[45,0,45,7],[47,3,47,4],[48,3,48,4],[49,3,49,4],[50,3,50,4],[51,3,51,4],[52,3,52,4],[53,3,53,4],[54,3,54,4],[55,3,55,4],[56,3,56,4],[57,3,57,4],[58,3,58,4],[59,3,59,4],[60,3,60,4],[61,3,61,4],[62,3,62,4],[63,3,63,4],[64,3,64,4],[65,3,65,4],[66,3,66,4],[67,3,67,4],[68,3,68,4],[69,3,69,4],[70,3,70,4],[71,3,71,4],[72,3,72,4],[73,3,73,4],[74,3,74,4],[75,3,75,4],[76,3,76,4],[77,3,77,4],[78,3,78,4],[79,3,79,4],[80,3,80,4],[81,3,81,4],[82,3,82,4],[84,0,84,7],[85,0,85,8],[86,0,86,8],[87,0,87,8],[88,0,88,8],[89,0,89,8],[90,0,90,8],[91,3,91,4],[92,0,92,7],[93,3,93,4],[94,3,94,4],[95,3,95,4],[96,3,96,4],[97,3,97,4],[98,3,98,4],[99,3,99,4],[100,3,100,4],[101,3,101,4],[102,3,102,4],[103,3,103,4],[104,3,104,4],[105,3,105,4],[106,3,106,4],[107,3,107,4],[108,3,108,4],[109,3,109,4],[110,3,110,4],[111,3,111,4],[112,3,112,4],[113,3,113,4],[114,3,114,4],[115,3,115,4],[116,0,116,7],[117,0,117,8],[118,0,118,8],[119,0,119,8],[120,0,120,8],[121,0,121,8],[122,0,122,8],[123,3,123,4],[124,0,124,7],[125,3,125,4],[126,3,126,4],[127,3,127,4],[128,3,128,4],[129,3,129,4],[130,3,130,4],[131,3,131,4],[132,3,132,4],[133,3,133,4],[134,3,134,4],[135,3,135,4],[136,3,136,4],[137,3,137,4],[138,3,138,4],[139,3,139,4],[140,3,140,4],[141,3,141,4],[142,3,142,4],[143,3,143,4],[144,3,144,4],[145,3,145,4],[146,3,146,4],[147,3,147,4],[148,3,148,4],[149,3,149,4],[150,3,150,4],[151,3,151,4],[152,3,152,4],[153,3,153,4],[154,3,154,4],[155,3,155,4],[156,3,156,4],[157,3,157,4],[158,3,158,4],[159,3,159,4],[160,3,160,4],[161,3,161,4],[162,3,162,4],[163,3,163,4],[164,3,164,4],[165,0,165,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["MEDIUM PRESSURE PIPELINES AND ANCILLARIES "]
["SECTION 1200 L"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[5,null,"SABS     1200L","MEDIUM PRESSURE PIPELINES( as specified in SABS 1200L, SABS 1200GA and the Project Specifications)"]
[]
[null,null,"8.2.1","Supply, handle, lay, joint, bed(class B) the following uPVC pressure pipes ( conforming to SABS 966-1976 specifications) in 6m length each pipe fitted at one end with socket for mechanical jointing, in the following diameters."]
[]
[5.1,"LI",null,"i) Reticulation Network"]
[]
[{"$nulls":3},"a) 90 mm diameter, uPVC, Class 12",null,"m",{"v":5500,"d":"5,500"}]
[{"$nulls":3},"b) 75 mm diameter, uPVC, Class 12",null,"m",{"v":23750,"d":"23,750"}]
[{"$nulls":3},"c) 32mm Class PN10",null,"m",{"v":5300,"d":"5,300"}]
[{"$nulls":3},"d) 25mm Class PN10",null,"m",{"v":2000,"d":"2,000"}]
[{"$nulls":3},"e) 80mm diameter galvanised steel pipe",null,"m",{"v":1200,"d":"1,200"}]
[]
[null,null,"8.2.2","FIITINGS AND SPECIALS FOR FIXING ONTO uPVC PIPES"]
[]
[{"$nulls":3},"Fittings to be suitable for coupling directly(mechanically) onto pipes. Each fitting socketted for mechanical jointing. Fittingsto be Class 16(unless otherwise specified) . Fittings to be PVC, Cast Iron or epoxy coated steel."]
[]
[5.2,"LI",null,"a) Bends"]
[{"$nulls":3},"i) 90 degree: uPVC Class 16 to fit uPVC pipes"]
[{"$nulls":3},"a)75mm diameter ",null,"No",32]
[{"$nulls":3},"b)90mm diameter ",null,"No",1]
[]
[{"$nulls":3},"ii) 45 degree: uPVC Class 16 to fit uPVC pipes"]
[]
[{"$nulls":3},"a)75mm diameter ",null,"No",14]
[{"$nulls":3},"b)90mm diameter ",null,"No",1]
[]
[{"$nulls":3},"iii) 22.5 degree: uPVC Class 16 to fit uPVC pipes"]
[]
[{"$nulls":3},"a)75mm diameter ",null,"No",17]
[{"$nulls":3},"b)90mm diameter ",null,"No",1]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["MEDIUM PRESSURE PIPES"]
["SECTION 1200 L"]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[]
["BROUGHT FORWARD"]
[]
[{"$nulls":3},"iv)11.25 degree: uPVC Class 16 to fit uPVC pipes"]
[]
[{"$nulls":3},"a)75mm diameter ",null,"No",37]
[{"$nulls":3},"b)90mm diameter ",null,"No",1]
[]
[5.3,null,null,"b)Elbow:  Male/Female"]
[{"$nulls":3},"i)90 degree angle : Steel"]
[]
[{"$nulls":3},"1)80mm Norminal Diameter",null,"No",2]
[]
[{"$nulls":3},"ii)45 degree angle : Steel"]
[]
[{"$nulls":3},"1)80mm Norminal Diameter",null,"No",2]
[]
[5.4,null,null,"c)Plugs:Steel"]
[]
[{"$nulls":3},"i)80mm Norminal Diameter",null,"No",1]
[]
[5.5,null,null,"d)Repair Coupling: Steel"]
[]
[{"$nulls":3},"i)80mm Norminal Diameter",null,"No",2]
[]
[5.6,"LI",null,"e) Cast Iron Equal Tees: for uPVC"]
[]
[{"$nulls":3},"i)75mm dia",null,"No",60]
[{"$nulls":3},"ii)90mm dia",null,"No",1]
[]
[5.7,"LI",null,"f) Cast Iron Reducing Tee: Socket-ended to fit uPVC"]
[]
[{"$nulls":3},"i)75mm x90mm x 90mm dia",null,"No",6]
[{"$nulls":3},"i)90mm x 75mm dia",null,"No",2]
[]
[5.8,"LI",null,"g) End Caps"]
[]
[{"$nulls":3},"i)75mm dia",null,"No",7]
[{"$nulls":3},"ii)90mm dia",null,"No",1]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["MEDIUM PRESSURE PIPES"]
["SECTION 1200 L"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[5.9,"LI",null,"h) Repair Couplings for uPVC Pipes"]
[]
[{"$nulls":3},"i)75mm dia",null,"No",6]
[{"$nulls":3},"ii)90mm diameter ",null,"No",1]
[]
[{"v":5.1,"d":"5.10"},"LI",null,"i) Flange Adaptor"]
[]
[{"$nulls":3},"Cast iron bitumen dipped and lyng sockets to SABS 546 and SABS 966 with flange drilled to SABS 1123, table 16 complete including Supply, handle and joint to the system pipe uPVC Class 16 flange including all couplings where necessary."]
[]
[{"$nulls":3},"i)75mm dia",null,"No",6]
[{"$nulls":3},"ii)90mm dia",null,"No",1]
[]
[5.11,"LI","8.2.3","Isolation Valves"]
[]
[null,null,"8.2.3.1","Socketed Valves( Socketed RSV isolating valves, valves to be non- rising spindles with housing box together with cap top and rates shall include supply, lay and bed class 10 socket ended, clockwise gate valve to SABS 664 with housing box)"]
[{"$nulls":3},"i)75mm, diameter,class 16",null,"No",30]
[{"$nulls":3},"ii)90mm diameter,class 16",null,"No",2]
[5.12,"LI","8.2.3.2","Socketed Valves( Flanged RSV isolating valves, valves to be non- rising spindles with housing box together with cap top and rates shall include supply, lay and bed class 10 socket ended, clockwise gate valve to SABS 664 with housing box)"]
[{"$nulls":3},"i)80mm, class 16",null,"No",2]
[5.13,"LI","8.2.3.3","Non Return Valve"]
[]
[{"$nulls":3},"i) 80mm Nominal Diameter",null,"No",2]
[]
["TOTAL CARRIED FORWARD"]
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["MEDIUM PRESSURE PIPES"]
["SECTION 1200 L"]
[]
["ITEM NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
["BROUGHT FORWARD"]
[5.14,"LI","8.2.3.3","Air Valves( Vent O Mat Series RBX with screwed BSP male inlet or similar, complete with flange, barrel nipple and 80mm gate valve)"]
[]
[{"$nulls":3},"i)80mm dia Air Valve",null,"No",1]
[]
[5.15,"LI","8.2.3.4","Bulk water meter"]
[]
[{"$nulls":3},"( Kent or similar approved, flanged and drilled to SABS 1123,table 16)"]
[]
[{"$nulls":3},"i)80mm dia in Bulk Line",null,"No",1]
[{"$nulls":3},"ii)100mm dia in Bulk Line",null,"No",1]
[]
[5.16,"LI","8.2.9","Hydraulic Pipe Testing :"]
[]
[{"$nulls":3},"i)75mm uPVC medium pressure pipes-Class12",null,"m",{"v":23750,"d":"23,750"}]
[{"$nulls":3},"ii)90mm uPVC medium pressure pipes-Class12",null,"m",{"v":5500,"d":"5,500"}]
[{"$nulls":3},"iii) 32mm Class PN10",null,"m",{"v":5300,"d":"5,300"}]
[{"$nulls":3},"iv) 25mm Class PN10",null,"m",{"v":2000,"d":"2,000"}]
[{"$nulls":3},"v) 80mm Galvanised Steel Pipe",null,"m",{"v":1200,"d":"1,200"}]
[{"$nulls":3},"vi)Pipe Special and fittings for testing",null,"Sum",1]
[]
[5.17,"LI","PSLB2.10","Disinfecting Pipe Works:"]
[]
[{"$nulls":3},"i)75mm uPVC medium pressure pipes-Class12",null,"m",{"$f":"G139","v":{"v":23750,"d":"23,750"}}]
[{"$nulls":3},"ii)90mm uPVC medium pressure pipes-Class12",null,"m",{"$f":"G140","v":{"v":5500,"d":"5,500"}}]
[{"$nulls":3},"iii) 32mm Class PN10",null,"m",{"$f":"G141","v":{"v":5300,"d":"5,300"}}]
[{"$nulls":3},"iv) 25mm Class PN10",null,"m",{"$f":"G142","v":{"v":2000,"d":"2,000"}}]
[{"$nulls":3},"v) 80mm Galvanised Steel Pipe",null,"m",{"$f":"G143","v":{"v":1200,"d":"1,200"}}]
[]
[5.18,"LI","8.2.11","Thrust Blocks:"]
[]
[{"$nulls":3},"Formworks",null,"m2",180]
[{"$nulls":3},"Concreteworks(Class 20/19Mpa)",null,"m3",35]
[]
[5.19,"LI","PSLB2.13","Pipeline markers"]
[{"$nulls":3},"Supply and install pipeline markers",null,"No",60]
[]
[{"v":5.2,"d":"5.20"},"LI","8.2.15","Special Wrapping in Corrosive Soil"]
[]
[{"$nulls":3},"a)Supply and wrap steel pipes by Denso Tape with thickness of 1.15mm , widths  of a minimum of 100mm ",null,"m",450]
[]
["TOTAL CARRIED TO SUMMARY"]

{"sheet":"SECTION LF","index":5,"n_rows":23,"n_cols":9,"rows_kept":23,"merged":[[0,0,0,8],[1,0,1,8],[2,0,2,8],[3,0,3,8],[4,0,4,8],[5,3,5,4],[6,3,6,4],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,3,10,4],[11,3,11,4],[12,3,12,4],[13,3,13,4],[14,3,14,4],[15,3,15,4],[16,3,16,4],[17,3,17,4],[18,3,18,4],[19,3,19,4],[20,3,20,4],[21,3,21,4],[22,0,22,7]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
["ERF CONNECTIONS(Water)"]
["SECTION 1200 LF"]
["ITEM  NO","LI","PMT","DESCRIPTION",null,"UNIT","QTY","RATE","AMOUNT"]
[6,null,"SABS 1200LF","ERF WATER CONNECTIONS"]
[null,null,"8.2.1","Provide Erf Connections complete with excavations, saddles, pipelaying (HDPE, type iv(7210), class12 pipe), bedding, testing, connections, stop taps,  backfilling, concrete works, etc"]
[6.1,null,"8.2.1.a","On the same side of the the street as the water pipe"]
[]
[null,"LI",null,"i) Double short drawoff connections, saddle,standpipe bedding and concrete block(20/Mpa)(0.5m x 0.4m x 0.1m)less than 5,0m long from saddle, for 32mm diameter  ",null,"No.",50]
[null,"LI",null,"ii) Single short drawoff connections,saddle,standpipe,bedding and concrete block(20/19Mpa)(0.5m x 0.4m x 0.1m), less than 5,0m long from saddle, for 25mm diameter  ",null,"No.",130]
[6.2,null,"8.2.1.b"," Across the street from the water pipe"]
[null,"LI",null,"i) Double long drawoff connections,saddle,standpipe, bedding and concrete block(20/19Mpa)(0.5m x 0.4m x 0.1m))more than 15,0m long from saddle, for 32mm diameter  ",null,"No.",490]
[null,"LI",null,"iii) Single long drawoff connections,saddle,standpipe, bedding and concrete block(20/19Mpa)(0.5m x 0.4 x 0.1m),more than 15,0m long from saddle,for 25mm diameter  ",null,"No.",15]
[]
[6.3,null,"8.2.4","Supply and Install water meter complete including Plasson box (KENT KSM) or similar approved "]
[null,"LI",null,"i) 32mm diameter",null,"No.",540]
[null,"LI",null,"ii)25mm diameter",null,"No.",145]
[]
[6.4,null,"8.2.5","Extra over item 8.2.1 for hauling bedding and selected fill in excess of the freehaul of 2,0km ",null,"m3-km",85]
[null,"LI",null,"Note: This item 8,2,5 must be done only on instruction of the Engineer/Representative"]
["TOTAL CARRIED FORWARD TO SUMMARY"]

{"sheet":"SUMMARY","index":6,"n_rows":36,"n_cols":7,"rows_kept":36,"merged":[[3,1,3,5],[5,1,5,5],[6,1,6,5],[7,1,7,5],[8,1,8,5],[9,1,9,5],[10,1,10,5],[11,1,11,5],[12,1,12,5],[13,1,13,5],[14,1,14,5],[15,1,15,5],[16,1,16,5],[17,1,17,5],[18,1,18,5],[19,1,19,5],[20,1,20,5],[21,1,21,5],[22,1,22,5],[23,0,23,5],[24,1,24,5],[25,1,25,5],[26,1,26,5],[27,1,27,5],[28,1,28,5],[29,1,29,5],[30,1,30,5],[31,1,31,5],[32,1,32,5],[33,0,33,5],[34,0,34,6],[35,0,35,6]]}
["CAPRICORN DISTRICT MUNICIPALITY"]
["PHASHA WATER SUPPLY-CONTRACT B"]
["CONTRACT NO.:INF-W06/2026/2027"]
[]
["SUMMARY SCHEDULE OF QUANTITIES"]
["ITEM","DESCRIPTION",{"$nulls":4},"AMOUNT"]
[]
["SECTION A","PRELIMINARY AND GENERAL"]
[]
["SECTION C","SITE CLEARANCE"]
[]
["SECTION DB","EARTHWORKS( Pipe Trenches)"]
[]
["SECTION LB","BEDDING"]
[]
["SECTION L","MEDIUM PRESSURE PIPES "]
[]
["SECTION LF","ERF CONNECTIONS"]
[]
[]
[null,"SUB - TOTAL 1"]
[]
[null,"CONTINGENCIES( 10%)"]
["( Note: The sum provided above is under the sole control of the Engineer and may be deducted in whole or in part. The tenderer shall add 10% of the total of schedule of quantities  ( sub-total 1) for contingencies)"]
[]
[null,"SUB - TOTAL 2"]
[]
[null,"ESCALATION(2.5%)"]
[]
[null,"SUB - TOTAL 3"]
[]
[null,"VAT ( 15% )"]
[]
["TOTAL TENDER AMOUNT TO BE CARRIED TO FORM OF OFFER"]
["Bidder 's Signature:………………………………………………………."]
["Note: Verification with suppliers  on Rate Only Items will be done by the Consultant during construction"]