# Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

# C3.1: Employer’s works Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s works Information	2

1	Description of the works	5

1.1	Executive overview	5

1.2	Employer’s objectives and purpose of the works	5

1.3	Interpretation and terminology	5

2	Management and start up.	6

2.1	Management meetings	6

2.2	Documentation control	7

2.3	Health and safety risk management	7

2.4	Environmental constraints and management	8

2.5	Quality assurance requirements	9

2.6	Programming constraints	9

2.7	Contractor’s management, supervision and key people	9

2.8	Invoicing and payment	9

2.9	Insurance provided by the Employer	10

2.10	Contract change management	10

2.11	Provision of bonds and guarantees	10

2.12	Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor	10

2.13	Training workshops and technology transfer	10

3	Engineering and the Contractor’s design	10

3.1	Employer’s design	10

3.2	Parts of the works which the Contractor is to design	11

3.3	Procedure for submission and acceptance of Contractor’s design	11

3.4	Other requirements of the Contractor’s design	11

3.5	Use of Contractor’s design	11

3.6	Design of Equipment	11

3.7	Equipment required to be included in the works	11

3.8	As-built drawings, operating manuals and maintenance schedules	11

4	Procurement	11

4.1	People	11

4.1.1	Minimum requirements of people employed on the Site	11

4.1.2	BBBEE and preferencing scheme	11

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	12

4.1.4	Preferred subcontractors	12

4.1.5	Subcontract documentation, and assessment of subcontract tenders	12

4.1.6	Limitations on subcontracting	12

4.1.7	Attendance on subcontractors	12

4.2	Plant and Materials	13

4.2.1	Quality	13

4.2.2	Plant & Materials provided “free issue” by the Employer	13

4.2.3	Contractor’s procurement of Plant and Materials	13

4.2.4	Spares and consumables	13

4.3	Tests and inspections before delivery	13

4.4	Marking Plant and Materials outside the Working Areas	13

4.5	Contractor’s Equipment (including temporary works).	13

4.6	Cataloguing requirements by the Contractor	13

N/A	13

5	Construction	13

5.1	Temporary works, Site services & construction constraints	13

5.1.1	Employer’s Site entry and security control, permits, and Site regulations	13

5.1.2	Restrictions to access on Site, roads, walkways and barricades	13

5.1.3	People restrictions on Site; hours of work, conduct and records	14

5.1.4	Health and safety facilities on Site	14

5.1.5	Environmental controls, fauna & flora, dealing with objects of historical interest	14

5.1.6	Title to materials from demolition and excavation	14

5.1.7	Publicity and progress photographs	14

5.1.8	Contractor’s Equipment	15

5.1.9	Equipment provided by the Employer	15

5.1.10	Site services and facilities	15

5.1.11	Facilities provided by the Contractor	15

5.1.12	Existing premises, inspection of adjoining properties and checking work of Others	15

5.1.13	Survey control and setting out of the works	15

5.1.14	Excavations and associated water control	15

5.1.15	Underground services, other existing services, cable and pipe trenches and covers	15

5.1.16	Control of noise, dust, water and waste	15

5.1.17	Sequences of construction or installation	16

5.1.18	Giving notice of work to be covered up	16

5.1.19	Hook ups to existing works	16

5.2	Completion, testing, commissioning and correction of Defects	16

5.2.1	Work to be done by the Completion Date	16

5.2.2	Use of the works before Completion has been certified	16

5.2.3	Materials facilities and samples for tests and inspections	16

5.2.4	Commissioning	16

5.2.5	Start-up procedures required to put the works into operation	16

5.2.6	Take over procedures	16

5.2.7	Access given by the Employer for correction of Defects	16

5.2.8	Performance tests after Completion	16

5.2.9	Training and technology transfer	17

5.2.10	Operational maintenance after Completion	17

6	Plant and Materials standards and workmanship	17

6.1	Investigation, survey and Site clearance	17

6.2	Building works	17

6.3	Civil engineering and structural works	17

6.4	Electrical & mechanical engineering works	18

6.5	Process control and IT works	18

6.6	Other [as required]	18

7	List of drawings	18

7.1	Drawings issued by the Employer	18

C3.2	Contractor’s Works Information	19

# Description of the works

## Executive overview

The Central Grid submitted a work request to develop designs/drawings to refurbish the access roads and Rigi Substation/s forms part of the requested road refurbishments. The scope part of this road refurbishment at Rigi substation starts outside the station 309m long. The refurbishment is required as the surface has worn out and some sections have deteriorated so bad that there are pots holes and water ends up ponding when it rains. This poses difficulty for the staff and trucks driven there as well as a safety hazard.

## Employer’s objectives and purpose of the works

Repair and resurface the access road from outside the station main gate until the feeder bays.

Clean and repair any drainage along the road.

## Interpretation and terminology

The following abbreviations are used in this Works Information:

| Abbreviation | Meaning given to the abbreviation |  |  |
| --- | --- | --- | --- |
| CLN | Customer Load network |  |  |
| CoE | Centre of Excellence |  |  |
| DRT | Design Review Team |  |  |
| EA | Environmental Authorization |  |  |
| EIA | Environmental Impact Assessment |  |  |
| ENC | NTCSA National Contract |  |  |
| EMP | Environmental Management Plan |  |  |
| ERA | Execution Release Approval |  |  |
| HV | High voltage |  |  |
| OHS | Occupational Health and Safety |  |  |
| KP | Key Plan |  |  |
| MTS | Main Transmission Substation |  |  |
| MVA | Mega volt ampere |  |  |
| PDE | Power Delivery Engineering |  |  |
| SED | Standards Station Electric Diagram |  |  |
| SAICE | South African Institution of Civil Engineering |  |  |
| SAIEG | South African Institute for Engineering and Environmental Geologists |  |  |
| SANS | South African National Standards |  |  |
| SHE | Safety, Health & Environment |  |  |
| OEM | Original Equipment Manufacturer |  |  |
| SLDG | Substation Layout Design Guideline |  |  |
| TLB | Tractor-Loader-Backhoe |  |  |
| SURS | Substation User Requirement Specification |  |  |
| TMH | Technical Methods for Highways |  |  |
| TRFR | Transformer |  |  |
| SURS | Substation User Requirement Specification |  |  |
| FSS | Finance Shared Services |  |  |
| ASGI-SA | Accelerated Shared Growth Initiative – South Africa |  |  |
| TBC | To Be Confirmed |  |  |
| Definition |  | Description |  |
| Competent person |  |  | Person who is qualified by virtue of his experience, qualifications, training and in-depth contextual knowledge of road construction |
| Contractor |  |  | A person or party who is appointed to execute the works specified herein. |

# Management and start up.

## Management meetings

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Technical meeting (Risk register; compensation events; Issues) | PM request. | Rigi Substation or MST | Employer, Contractor, Technical staff and end users, safety and environmental staff. |
| Overall project progress and feedback | Monthly on the 1st Tuesday of each month or the next working day if the mention day is a Public holiday | Rigi Substation or MST | Employer, Contractor, Supervisor, and other Interested parties |
| Risk register and compensation events | As and when required | Site | PM, QS, Site Supervisor, Contractor |
| Overall contract progress and feedback | Monthly on Site | Site | Employer, Contractor, Supervisor, and Grid Representatives |
| Inaugural meeting | Before or after safety and environmental files have been assessed and approved. | Site | PM, QS, Site Supervisor, EA, Grid safety and environmental representatives and the Contractor. |
| Toolbox talk and risk assessment | Daily on Site before work begins. | Site | Contractor and Site Supervisor. |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings are submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings are recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

Meetings are arranged as per the specific contract requirements. During the design phase the progress feedback meetings are held at NTCSA Substation/s or via MST on a bi-weekly basis. This meeting is attended by Employer’s representatives and Contractor representatives.

## Documentation control

- All verbal communication are followed up with written confirmation

- All written communication should be on formal letters with Corporate letter heads

- An email system is used for general communication

- Minutes of Meetings are held for all meetings relating to the project

- Communication is extremely important and is managed to ensure maximum benefits to the project.

- A document management system will be implemented.

- All communication to be directed to the Project Manager

## Health and safety risk management

The Contractor shall at all times comply with the health and safety requirements prescribed by law as they may apply to the works.  The Contractor shall comply with the health and safety requirements contained in in the following documents:

•           SHEQ policy – 32 727

•           NTCSA Procurement and supply chain management procedure – 32-1034

•           SHE Requirements for the NTCSA Commercial process – 32- 726

•           Contractor health and safety requirements – 32-136

•           Integrated SHE organisation: roles and responsibilities and statutory appointments – 32-296

•           Life saving rules – 240-62196227

•           Working at heights – 32-418

•           NTCSA Vehicle safety specification – 32-345

•           Employer’s Health and Safety requirements - TST32-136

The authorization procedure for a permit to work shall be followed by the Contractor before commencing work on site. It is the Contractor’s responsibility to ensure that a permit to work is obtained before access to the work can be given. It is the Contractor’s responsibility to also ensure that the safety file has been audited by the Health and Safety Representatives before establishing site.

The Contractor must be in possession of current first aid certificate. The Contractor’s trucks must have a valid and current crane test certificate with the truck driver and crane operator’s certificate. All tools must have valid and current test certificates, which must be produced two weeks before site establishment.

The Contractor will only leave site once a written site instruction has been issued by an NTCSA site representative. Working hours will be from 08h00 to 16h00 during week days (as per outages) ,weekend work to be carried out only on request by  NTCSA.

The Contractor is to have an NTCSA certified and authorized person available in each area where work is being performed at all times in accordance with NTCSA transmission standard TST32-136 contractor safety in a high voltage environment.

A complete safety and risk assessment must be done BEFORE the contractor starts works on site. The Site Supervisor will be monitoring the works continuously to ensure strict adherence to Safety rules. If needed, the contractor is to visit the site at the Contractor’s own cost before work commences to familiarize with the scope of works and to assess any safety issues.

Before any excavation is commenced, it will be the responsibility of the Contractor to ascertain from the Site Supervisor the position of any existing services on site.  Once these are indicated to the contractor they shall be deemed “known”.  Any costs incurred for repairs to any “known” services shall be for the contractor’s account.

The Contractor shall allow safe access for other contractors and NTCSA personnel when required.

The Contractor shall establish a refuse control system.  All waste is to be collected and disposed of as required by NTCSA and the local authority.

The Contractor shall make his own arrangements for the provision of accommodation for his employees.

## Environmental constraints and management

The Contractor is required to ensure that all goods, services or works supplied in terms of the tender/contract/order conform to all applicable environment legislation, Authorisations, EPC32-727: NTCSA SHEQ Policy, ST32-726: SHE Requirements for the NTCSA Commercial Process and Project Specific Environmental Management Plan (EMP).

The NTCSA EMP provides the Aspects and Impacts that will require management and must be followed strictly. The Contractor shall prepare a separate mitigation plan for all environmental concerns raised through the EMP and in any other relevant forum. The contractor must develop method statements based on the EMP. All developed method statements must be approved by the Employer.

Any changes to the approved EMP shall be reported and approved by (BUER) and Project Manager prior to the commencement of work and during construction.. The supplier must ensure that all sub-contractors’ environmental management programmes comply with the contract shall define the specific system elements applicable to the subcontractor’s scope of work or supply.

Environmental meetings between NTCSA and the Contractor may be held regularly and copies of the minutes may be submitted to NTCSA on request. The contractor is to send a flash report for any environmental incidences that has occurred on site as soon as possible or within 24 hours to the SS /Grid Environmental and PM clearly stating any impact to the environment.

Contractor must now sign-off TRM-FM-0038 – NTCSA Holdings Transmission division contractor environmental compliance Proformas.

If waste is generated during project, it must be disposed at a registered site and contractor shall retain records of disposal.

Deviations from these requirements will be regarded as a non-conformance. Should there be a concerns regarding environmental performance and non-conformance to environmental requirements, management engagements and interventions will be introduced to determine a means to addressing the shortfalls.

Once these interventions have been explored and exhausted, then the NTCSA supplier disciplinary process must be followed.

The Contractor is to send a flash report for any environmental incidents that have occurred on site as soon as possible or within 24 hours to the Grid Environmental Advisor clearly stating any impact to the environment.

NB: The Contractor is to compile a complete environmental file. The file needs to be audited and approved by the Grid Environmental Department prior to commencement of work.

## Quality assurance requirements

Quality requirements will be negotiated and linked to contract award. Quality objectives are as follows:

- Contract Quality Plan Requirement as per Scope of works.

- Quality Control Plan (Inspection and Test Plan) Requirements as per scope of works.

- The supplier shall complete and sign Form A (Enquiry/Contract/Quality Requirements for QM       58 and ISO 9001).

The supplier shall submit objective evidence of a developed and implemented QMS that

complies with ISO 9001:2015 or any applicable standard of quality management system (the

latest applicable revision). The following documents (approved copies) shall be submitted:

Detailed objective criteria are attached in the Quality evaluation criteria form.

## Programming constraints

A comprehensive and fully detailed programme is to be submitted within the seven (7) days after the inaugural meeting and should be in MS Project format, indicating all milestones and critical dates. This programme must first be approved by the Project Manager and must be updated monthly or as requested by the Project Manager.

The following dates shall be clearly reflected on the programme:

Starting and completion dates for all activities as well as relevant key dates for hold or witness points. All relevant significant activities shall be shown in order to monitor the progress on site or in the workshop. The programme shall also reflect a 2-week period for inspection and correcting of Defects before the completion date.

Updated programmes must be available at all site meetings reflecting progress to date.

## Contractor’s management, supervision and key people

The Contractor submits an organogram with updated CVs of each employee on the project. Reporting structures and responsibilities are to be included on the organogram or in an addendum to the organogram. The organogram showing all key people involved in the contract 7 days after contract award. All key personnel must be appointed in writing, must be current for the specific site and area of work and must be kept on file.

## Invoicing and payment

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor shall address the tax invoice to NTCSA and include on each invoice the following information:

- Name and address of the Contractor and the Project Manager;

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- Description of service provided for each item invoiced based on the Price List;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT; The Purchase Order number

- Send all invoices in PDF to Accounts Payable Department: Invoicesntcsalocal@ntcsa.co.za

- The Contractor can request a park invoice report from Finance Shared Services (FSS) contact centre which can then be followed up and corrected. You are welcome to forward the details of invoices corrected to the FSS contact Centre.

- Every 25th of each month, the Employer and Contractor will perform an assessment on the work completed for the month. The assessment will be signed off by both parties.

## Insurance provided by the Employer

N/A

## Contract change management

Project Change Request Register unique identifier 240-87274313 (latest revision) will be used. All scope changes must be approved by the Project Manager.

## Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

## Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor

All project related documents to be kept in either electronic format or hard copies in files at the Contractor’s premises

## Training workshops and technology transfer

N/A

# Engineering and the Contractor’s design

## Employer’s design

Scope of work:

Rigi:

The following civil works needs to be done for Rigi Substations access road.

• Refurbish and construct 6m-9m wide tar road and 309m long

• Clean open-cut drains and gutters that run next to the road

• Conduct DCP and CBR test

• Place vegetation outside the gate of the substation

• Construct cut-off drain outside the gate of the substation

The Employer has designed for the works; the Contractor is mainly doing construction only. NTCSA has designed the new access road as detailed on the relevant drawings listed on this document and the quantities are given in the bill of quantities.

Repair and resurface the access road from outside the station main gate until the feeder bays

## Parts of the works which the Contractor is to design

The Contractor is to design any temporary works required to construct the works

## Procedure for submission and acceptance of Contractor’s design

N/A

## Other requirements of the Contractor’s design

N/A

## Use of Contractor’s design

N/A

## Design of Equipment

N/A

## Equipment required to be included in the works

N/A

## As-built drawings, operating manuals and maintenance schedules

The contractor shall

Prepare a report containing all the relevant information pertinent to the project; this should include the following but not limited to:

. As-built drawings presented in (dgn format).

. Operational Manual.

. Maintenance Manual.

The Contractor is to provide NTCSA with detailed “as built” records where deviations have been made from construction drawings within 14 days after Completion.

# Procurement

## People

### Minimum requirements of people employed on the Site

The Contractor shall comply with the Employer’s site requirements in the use of labour for the works

### BBBEE and preferencing scheme

The Contractor shall comply with the Employer’s Broad Based Black Economic Empowerment (B-BBEE) or preferencing scheme measures

### Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s ASGI-SA Compliance Schedule stated below

.

The Contractor shall keep accurate records and provide the Project Manager with reports on the Contractor’s actual delivery against the above stated ASGI-SA criteria.   [Elaborate on access to and format of records and frequency of submission etc.]

The Contractor’s failure to comply with his ASGI-SA obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract.

SD&L Compliance Matrix

### Preferred subcontractors

The Contractor submits the names of each proposed subcontractor to the Employer for acceptance. The Contractor does not appoint a subcontractor until the Employer has accepted him. The Contractor shall keep accurate records and provide the Project Manager with reports on the Contractor’s actual delivery against the stated SD&L criteria.

The Contractor’s failure to comply with his SDL&I obligations shall constitutes a breach on his/her part and therefore, as security for the fulfilment of all SDL&I obligations, NTCSA shall apply a penalty of 2.5% of every invoice amount (excluding VAT) for failure to submit SDL&I performance reports every quarter; or failure to meet the SDL&I contractual obligations.

### Subcontract documentation, and assessment of subcontract tenders

The NEC system is compulsory for all subcontract documentation

### Limitations on subcontracting

N/A

### Attendance on subcontractors

The Contractor is responsible for providing the Works as if he had not subcontracted

## Plant and Materials

### Quality

The Contractor adheres to all NTCSA standards and best practices for the design, installation and workmanship to ensure quality workmanship and sound installation practice.

The Contractor contacts the Project Manager to clarify any uncertainty regarding specifications or adheres to NTCSA standards provided.

### Plant & Materials provided “free issue” by the Employer

N/A

### Contractor’s procurement of Plant and Materials

N/A

### Spares and consumables

N/A

## Tests and inspections before delivery

N/A

## Marking Plant and Materials outside the Working Areas

N/A

## Contractor’s Equipment (including temporary works).

N/A

## Cataloguing requirements by the Contractor

## N/A

# Construction

## Temporary works, Site services & construction constraints

### Employer’s Site entry and security control, permits, and Site regulations

The contractor to abide by security protocols and access control procedures.

Alcohol testing will be conducted at any time on all employees entering the NTCSA premises. All staff that tested positive for alcohol abuse will not be allowed on site. Entry to the site is governed by the Grid’s Engineering Assistant and the Contractor shall adhere to all regulations given.

All employees are to sign the Workers declaration on entering and leaving the working area.

The Contractor is to have an NTCSA certified and authorized ORHVS person available on site at all times in accordance with NTCSA’s Construction Safety, Health and Environmental Management 32-136.

The authorized ORHVS person is to have a valid first aid level 2 certificate.

The authorization procedure for a permit to work shall be done before the Contractor commences work on site.

It is the Contractor’s responsibility to ensure that the authorization procedure for a permit to work is obtained before access to the work can be given.

### Restrictions to access on Site, roads, walkways and barricades

All vehicles must comply with the National Road Traffic Act, 1996 (Act No. 93 Of 1996)

Vehicle inspections will be conducted on a daily basis and check sheets must be kept at the Contractor’s offices.

### People restrictions on Site; hours of work, conduct and records

Restrictions and hours of work may apply on Sites.

It is very important that the Contractor keeps records of his people on Site, including those of his Subcontractors which the Project Manager or Supervisor have access to at any time.  These records may be needed when assessing compensation events

### Health and safety facilities on Site

The Contractor to supply the following for his employees:

- Job Specific Safety training

- Personal Protective Equipment

- Toolbox talks

- Safety Representatives to be trained for all areas of the works.

- Qualified First aiders to be appointed for all areas of the works

- There are no Toilet facilities available on site.

- The Contractor is to provide his own toilet facilities on site and ensure that these facilities are kept in a clean condition to NTCSA’s satisfaction.

- No work on site will be allowed to commence before the toilet facilities are available on site.

### Environmental controls, fauna & flora, dealing with objects of historical interest

SHE requirements must be clearly identified on notice boards.

A complaints register must be maintained. The Contractor shall seek Employer’s approval prior to engaging with the authorities.

There are no pictures allowed to be taken at the Substation/s without the written authorisation of the Project Manager.

The Contractor shall control his activities and processes in accordance with NTCSA Environmental Requirements TST41-120.

The Contractor shall establish a refuse control system.

All waste is to be collected and disposed of as required by NTCSA and the Local Authority.

### Title to materials from demolition and excavation

All the materials from excavation and demolition must be disposed of by the Contractor except where expressly stated by the PM or the relevant staff from the Grid. All rubble and other materials must be classified, weighed and transported to a registered dumping site.

### Publicity and progress photographs

A complaints register must be maintained. The Contractor shall seek Employer’s approval prior to engaging with the authorities.

There are no pictures allowed to be taken at Kwagga Substation without the written authorisation of the Project Manager.

### Contractor’s Equipment

The Contractor submits a list of all tools and equipment entering site. Equipment and tools not declared will become the Employer’s property.

On completion of the project, all tools and equipment will be removed only with permission from the Project Manager on the applicable approved Employer documents.

### Equipment provided by the Employer

N/A

### Site services and facilities

N/A

### Facilities provided by the Contractor

All drivers’ fitness to operate specified vehicles and licenses to be available at all times for inspections by the Employer.

The Contractor supplies all plant and materials required for providing the Works.

There are no Office or Telephone facilities available on site.  The Contractor is to provide his own facilities on site and ensure that these facilities are kept in a clean condition to NTCSA’s satisfaction.

There are no Toilet facilities available on site.  The Contractor is to provide his own toilet facilities on site and ensure that these facilities are kept in a clean condition to NTCSA’s satisfaction. No work on site will be allowed to commence before the toilet facilities are available on site.

### Existing premises, inspection of adjoining properties and checking work of Others

The contractor to take note of the surrounding equipment and buildings during construction. The work will be carried out on the access road to the substation.

### Survey control and setting out of the works

The Contractor is responsible for setting out the works as shown on the drawings

### Excavations and associated water control

All excavations to be verified with the Site Supervisor prior to excavation.

All necessary precautions shall be taken to ensure that deep excavations are safe and that the sides are stable, if not they shall be battered. All excavations are to be properly barricaded at all times.

### Underground services, other existing services, cable and pipe trenches and covers

Before any excavation is commenced, it will be the responsibility of the Contractor to ascertain from the “Engineering Assistant” the position of any existing services on site.  Once these are indicated to the Contractor they shall be deemed “known”.  Any costs incurred for repairs to any “known” services shall be for the Contractor’s account.

### Control of noise, dust, water and waste

To be included in the Risk Assessment.

As per authorisations and the Employers policies, procedures and work instructions.

The Contractor shall control his processes and procedures so as to minimise noise and dust.  All waste is to be collected and disposed of as required by NTCSA and the Local Authority.

### Sequences of construction or installation

To be determined by Employer and Contractor.

Accommodation of traffic during construction

### Giving notice of work to be covered up

All intended activities must be captured in the scope of work and also on the project schedule. The project schedule will be reviewed and updated weekly by the Project manager.

The Contractor is to give the Site Supervisor at least 3 days’ notice before covering up the work

### Hook ups to existing works

N/A

## Completion, testing, commissioning and correction of Defects

### Work to be done by the Completion Date

On or before the Completion Date the Contractor shall have done everything required to Provide the Works except for the work listed below which may be done after the Completion Date but in any case before the dates stated.  The Project Manager cannot certify Completion until all the work except that listed below has been done and is also free of Defects which would have, in his/her opinion, prevented the Employer from using the works and Others from doing their work.

|  | Item of work | To be completed by |
| --- | --- | --- |
|  | As built drawings of Central Grid Access road Refurbishment Project | Within five (5) days after Completion |

### Use of the works before Completion has been certified

N/A

### Materials facilities and samples for tests and inspections

N/A

### Commissioning

After Completion and provide the as built drawing

### Start-up procedures required to put the works into operation

N/A

### Take over procedures

The Contractor is to arrange an inspection at least 1 week before completion to inspect and identify any outstanding or incorrect items.

### Access given by the Employer for correction of Defects

The Contractor to arrange access with the Site supervisor 2 days to and use of a part of the works which has been taken over if needed to correct a Defect. The Contractor to undertake all necessary procedures before such access can be granted for example barricading.

### Performance tests after Completion

The access road should be 100% functional with no defects

The procedure for performance test is specified under the project quality plan document.

### Training and technology transfer

N/A

### Operational maintenance after Completion

The contractor shall provide standard road maintenance guideline as a minimum requirement

# Plant and Materials standards and workmanship

## Investigation, survey and Site clearance

N/A

## Building works

N/A

## Civil engineering and structural works

| Title | Date or revision | Tick if publicly available |
| --- | --- | --- |
| NTCSA Standard Specifications |  |  |
| Construction Safety, Health and Environmental Management 32-136 | Latest Rev. |  |
| NTCSA Life saving rules 32-421 | Latest Rev. |  |
| Safety, Health and Environmental (SHE) Policy 32-94 | Latest Rev. |  |
| 32-726 SHE Requirements for NTCSA Commercial Process | Latest Rev. |  |
| (SHE) Policy 32-727 | Latest Rev. |  |
| Smoking Procedure 32-36 | Latest Rev. |  |
| Vehicle and Driver Safety Management 32-93 | Latest Rev. |  |
| NTCSA Vehicle Safety 32-345 | Latest Rev. |  |
| TST41-120 Environmental Requirements for the Procurement of Assets, Goods and Services. | Latest Rev. |  |
| TPC41-283 Non Conformance Procedure | Latest Rev. |  |
| Occupational Health and Safety Act No. 85 of 1993 | Latest Rev. |  |
| QM58 Quality Requirements for Procurement of Assets, Goods & Services. | Latest Rev. |  |
| NTCSA Particular Specifications |  |  |
| EPS 3 Variations and Additions to Standardised Specifications | Attached |  |
| Standardised Specifications |  |  |
| SABS 1200 Standardised Specification for Civil Engineering Construction |  |  |
| SANS 2001 CC1:2007 Construction Works Part CC1: Concrete Works (structural) |  |  |
| SANS 2001 CS1:2007 Construction Works Part CS1: Structural steelwork |  |  |
| NWS 1058 Safety at Construction Sites |  |  |

## Electrical & mechanical engineering works

N/A

## Process control and IT works

N/A

## Other [as required]

N/A

# List of drawings

## Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

Note:  Some drawings may contain both Works Information and Site Information.

Refer to Waybill for Civil Works for drawing list

| Drawing number | Revision | Title |
| --- | --- | --- |
| RIG20P08-SE-D42 sht 0 | 0 | RIGI SUBSTATION ROAD LAYOUT & CROSS SECTION |

# C3.2	Contractor’s Works Information

This section of the Works Information will always be contract specific depending on the nature of the works. It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1. Typical sub headings could be a) Contractor’s design b) Plant and Materials specifications and schedules c) Other

This section could also be compiled as a separate file.