|  |  | PASSENGER RAIL AGENCY OF SOUTH AFRICA |
| --- | --- | --- |
|  |  | Appointment of professional consultants (for the design and monitoring of construction) to conduct studies, prepare designs, construction monitoring and close-out of various station projects within the Corridor 3 (Johannesburg to Naledi -Rail Priority Corridor Phase 3), South Gauteng Region |
| ## C.1.2 Contract Data |  |  |
| ## The Conditions of Contract are the Standard Professional Services Contract (July 2009) published by the Construction Industry Development Board (see www.cidb.org.za). Each item of data given below is cross-referenced to the clause in the Conditions of Contract to which it mainly applies. |  |  |
| # Part 1: Data provided by the Employer |  |  |
| Clause | ## Data |  |
|  | The Employer is PASSENGER RAIL AGENCY OF SOUTH AFRICA |  |
| 3.4 and 4.3.2 | The authorised and designated representative of the Employer is: Name: George Chauke The address for receipt of communications is: Telephone: 0674104186 Faxsimile: N/A E-mail: gchauke@prasa,com Address: Tippet Building 96 Rissik Street, Johannesburg. |  |
| 1 | The Project is To seek approval for specification / terms of reference / scope of work for the appointment of a consortium of consultants (for the design and monitoring of construction) to conduct studies, prepare designs, construction monitoring and close-out of various station projects within the Gauteng Region, South Gauteng Region Corridors. |  |
| 1 | The Period of Performance is 36 months or until final completion is reached |  |
| 1 | The Start Date is 14 days after commencement of contract |  |
| 3.4.1 | Communications by e-mail is the preferred method and not fax. |  |
| 3.5 | The location for the performance of the Project is in the Johannesburg to Naledi -Rail Priority Corridor Phase 3), South Gauteng Region |  |
| 3.6 | The Service Provider may not release public or media statements or publish material related to the Services or Project under any circumstances. |  |
| 3.9.2 | The time-based fees used to determine changes to the Contract Price are as stated in the Pricing schedule data |  |
| 3.12 | The penalty payable is R per Day subject to a maximum amount of 5% of the contract value |  |
| 3.15 | The programme shall be submitted within 10 Days of the award of the Contract. |  |
| 3.15.2 | The Service Provider shall update the programme at intervals not exceeding 1.5 weeks |  |
| 3.16 | The time-based fees shall not be adjusted for inflation. |  |
| 13.16.1 | The indices are those contained in Table A of P0141 Consumer Price Index for the CPI for all services published by Statistics South |  |
| 5.4.1 | The Service Provider is required to provide professional indemnity cover in an amount to a maximum of twice the professional fees, or R…, in respect of a claim without limit to the number of claims. |  |
| 5.5 | The Service Provider is required to obtain the Employer’s prior approval in writing before taking any of the following actions: 1 Issuing an instruction that will result in a cost and time adjustment of the Contract. 2 Issuing an instruction that will result in a time adjustment without cost of the Contract. 3 Appointing sub-contractors for the performance of any part of the Service 4 Appointment of key persons not listed by name in the Contract Data |  |
| 7.2 | The Service Provider is required to provide personnel in accordance with the provisions of clause 7.2 and to complete the Personnel Schedule. |  |
| 8.1 | The Service Provider is to commence the performance of the Services within 10 Working Days of date that the Contract becomes effective. |  |
| 8.2.1 | The Contract is concluded when Final Completion of the Project is Reached and the project has been capitalised |  |
| 8.4.3 (c) | The period of suspension under clause 8.5 is not to exceed 8 weeks |  |
| 9.1 | Copyright of documents prepared for the Project shall be vested with the Employer. |  |
| 11.1 | A Service Provider may subcontract any work which he has the skill and competency to perform. |  |
| 12.1 | Interim settlement of disputes is to be by Adjudication |  |
| 12.2 | Final settlement is by Arbitration |  |
| 12.3.3 | The adjudicator is the person appointed by the Association of Arbitrators Tel (011) 884 9164 |  |
| 12.4.1 | In the event that the parties fail to agree on an arbitrator, the arbitrator is nominated by Association of Arbitrators Tel (011) 884 9164 |  |
| 13.1.3 | All persons in a joint venture or consortium shall carry a minimum professional indemnity insurance of a maximum of twice the professional fees, or the amounts stipulated below. Discipline; Registration with professional council; Minimum Professional Indemnity Cover. Professional Architect; SACAP; R. Professional Quantity Surveyor; SACQSP; R. Professional Civil Engineer; ECSA; R. Professional Town Planner; ECSA; R. Professional Electrical Engineer; ECSA; R. Professional Mechanical Engineer; ECSA; R. Professional Fire Consultant (Mechanical or Civil Engineer); ECSA; R. Construction Health and Safety Agent; SACPCMP; R. Total; R. |
| 13.4 | Neither the Employer nor the Service Provider is liable for any loss or damage resulting from any occurrence unless a claim is formally made within 36 months from the date of termination or completion of the Contract. |  |
| 13.5.1 | The maximum amount of compensation payable by either Party to the other in respect of liability under the Contract is limited to a maximum of twice the professional fees, or R…. |  |
| 15 | The interest rate will be the ruling prime rate at the time the amount is due |  |