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Construction, Refurbishment and Commissioning of Coal and Ash Conveyor Belts.                                                       Contract No: 
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Part C1: Agreements & Contract Data


	Contents:
	

	C1.1
	Form of Offer and Acceptance

[to be inserted from Returnable Documents at award stage]

	C1.2a
	Contract Data provided by the Employer

	C1.2b
	Contract Data provided by the Contractor.

[to be inserted from Returnable Documents at award stage]








	
	
C1.1 Form of Offer & Acceptance


Offer
The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

· Design, Construction, Refurbishment and Commissioning of Coal and Ash Conveyor Belt. 
The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorized, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

	Option B
	The first forecast of the total Defined Cost plus the Fee exclusive of VAT is
	R [●]

	
	Sub total
	R [●]

	
	Value Added Tax @ 15% is
	R [●]

	
	The offered total of the amount due inclusive of VAT is1
	R [●]

	
	(in words) [●]



This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

	Signature(s)
	



	Name(s)
	



	Capacity
	



	For the
tenderer:
	

	
	

	Name & signature of
witness
	
Date

	Tenderer’s CIDB registration number (if applicable)
	









By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer. In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data. Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance) Part C2	Pricing Data
Part C3	Scope of Work: Works Information Part C4	Site Information
and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance. No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect. Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.


	Signature(s)
	
	

	Name(s)
	
	

	Capacity
	
	

	
for the Employer
	
	

	
	
	

	Name & signature of
witness		
	
	
Date
 	



Acceptance


Note:
1. 	This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.
2. The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.
3. A tenderer’s covering letter must not be included in the final contract document. Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

	No.
	Subject
	Details

	1
	[●]
	[●]

	2
	[●]
	[●]

	3
	[●]
	[●]

	4
	[●]
	[●]

	5
	[●]
	[●]

	6
	[●]
	[●]

	7
	[●]
	[●]




By the duly authorized representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.


	
	For the tenderer:
	
	For the Employer

	Signature
	
	
	

	Name
	
	
	

	Capacity
	
	
	

	On behalf of
	(Insert name and address of organisation)
	
	(Insert name and address of organisation)

	Name & signature of witness
	
	
	

	
Date
	
	
	


Schedule of Deviations to be completed by the Employer prior to contract award


C1.2 ECC3 Contract Data


Part one - Data provided by the Employer.

	Clause
	Statement
	Data

	1
	General
	

	The conditions of contract are the core clauses and the clauses for main Option

	
	
	B:        Priced contract with Bill of Quantities

	
	dispute resolution Option
	W1:	Dispute resolution procedure

	
	and secondary Options
	

	
	
	

	
	
	X2	Changes in the law

	
	
	X5:	Sectional Completion
X13:	Performance Bond

	
	
	X15:	Limitation of Contractor’s liability for design to reasonable skill and care

	
	
	X16:	Retention

	
	
	X18:	Limitation of liability

	
	
	

	
	
	Z:	Additional conditions of contract

	of the NEC3 Engineering and Construction Contract, April 2013 (ECC3)

	10.1
	The Employer is (Name):
	Eskom Rotek Industries SOC Ltd 
(Reg no: 1990/006897/30), a state-owned company incorporated in terms of the company laws of the Republic of South Africa 


	
	Address
	Roshland Office Park
Lower Germiston Road
Rosherville 

	10.1
	The Project Manager is: (Name)
	

	
	Address
	Roshland Office Park
Lower Germiston Road
Rosherville 


	
	Tel
	

	
	Fax
	

	
	e-mail
	

	10.1
	The Supervisor is: (Name)
	TBC







































responsibilities
Address


Tel No.


Fax No.


e-mail

11.2(13)
The works are
Design, Construction, Refurbishment and Commissioning of Coal and Ash Conveyor Belts to be Executed by Eskom Rotek Industries at Various Eskom Power Stations for a period of 4 years.
11.2(14)
The following matters will be included in the Risk Register
Refer Risk Register, Ash, and Coal Dust, inter alia. 



11.2(15)
The boundaries of the site are
Various Eskom Power Stations  
11.2(16)
The Site Information is in
Part 4: Site Information
11.2(19)
The Works Information is in
Part 3: Scope of Work and all documents and drawings to which it makes reference.
12.2
The law of the contract is the law of
the Republic of South Africa
13.1
The language of this contract is
English
13.3
The period for reply is
Two (2) weeks
2
The Contractor's main
Data required by this section of the core




3	Time

clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data.


	11.2(3)
	The completion date for the whole of the
works is
	

	

	11.2(9)
	The key dates and the conditions to be
	Condition to be met
	key date

	
	met are:
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	



	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	30.1
	The access dates are:
	Part of the Site
	Date

	
	
	1
	Access to various Eskom Power Stations
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	




	
	
	

	31.1
	The Contractor is to submit a first programme for acceptance within
	
Four (4) weeks of the Contract Date.
	



	31.2
	The starting date is
	01 April 2024

	32.2
	The Contractor submits revised programmes at intervals no longer than
	
Two (2) weeks.



	35.1
	The Employer is not willing to take over         the works before the Completion Date.          



	4
	Testing and Defects
	

	42.2
	The defects date is
	52 weeks after Completion of the whole of the
works.

	
	
	
	
	

	43.2
	The defect correction period is
	Time
	Defect
Category
	
Description

	
	
	24 Hours
	Priority 1
	System or equipment cannot be operated safely
and/or production loss

	
	
	3 days
	Priority 2
	Must be completed before operational acceptance.

	
	
	5 days
	Priority 3
	Must be completed prior to Client Acceptance.

	
	
	10 days
	Priority 4
	Any other defect



5 Payment

50.1	The assessment interval is	By no later than the 25th day of each successive
month.

	51.1
	The currency of this contract is the
	South African Rand.

	51.2
	The period within which payments are made is
	
Eight (8) weeks of the invoice date


51.4	The interest rate is	the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove)



for amounts due in Rands and

















6 Compensation events
60.1(13)	The place where weather is to be

(ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove.

recorded is:	Various Eskom Power Stations  
The weather measurements to be
recorded for each calendar month are,	the cumulative rainfall (mm)
the number of days with rainfall more than 10 mm
the number of days with minimum air temperature less than 0 degrees Celsius
the number of days with snow lying at 09:00 hours South African Time
and these measurements:

The weather measurements are supplied by
The weather data are the records of past
weather measurements for each calendar

[the South African Weather Bureau]

month which were recorded at:	Various Eskom Power Stations 
and which are available from:	the South African Weather Bureau and
included in Annexure A to this Contract Data provided by the Employer.

Assumed values for the ten-year return weather data for each weather measurement for each calendar month are:60.1(13)


As stated in Annexure A to this Contract Data provided by the Employer.



7 Title	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in
this Contract Data.

8 Risks and insurance


	80.1
	These are additional Employer's risks
	Refer to Option Z
	

	9
	Termination
	There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data.

	10
	Data for main Option clause
	
	
	

	E
	Cost reimbursable contract
	
	
	

	20.4
	The Contractor prepares forecasts of Defined Cost for the works at intervals no longer than
	
	

	
	
	Three (3) weeks.
	

	11
	Data for Option W1
	
	
	

	W1.1
	The Adjudicator is
	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA).

	W1.2(3)
	The Adjudicator nominating body is:
	the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body.

	W1.4(2)
	The tribunal is:
	arbitration.
	

	W1.4(5)
	The arbitration procedure is
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	
	The place where arbitration is to be held is
	South Africa
	

	
	The person or organisation who will choose an arbitrator
· if the Parties cannot agree a choice or
· if the arbitration procedure does not state who selects an arbitrator, is
	

the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.

	12
	Data for secondary Option clauses
	
	
	

	X2
	Changes in the law
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.

	X5
	Sectional Completion
	
	
	

	X5.1
	The completion date for each section of the works is:
	
	
	

	
	
	Section
	Description
	Completion date




	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	X13
	Performance Bond
	10% of the Contract Price.

	X15
	Limitation of the Contractor’s liability for his design to reasonable skill & care
	There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data.

	X16
	Retention
	
	
	

	X16.1
	The retention free amount is
	R0.00.
	
	

	
	The retention percentage is
	5% of the Contract price 
	
	

	X18
	Limitation of liability
	
	
	




	X18.1
	The Contractor’s liability to the Employer for indirect or consequential loss is limited to:
	R0.0 (zero Rand)

	X18.2
	For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to:
	the amount of the deductibles relevant to the event

	X18.3
	The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to
	The greater of
· the total of the Prices at the Contract Date and
· the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date.

	X18.4
	The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to:
	the total of the Prices other than for the additional excluded matters.

The Contractor’s total liability for the additional excluded matters is not limited.

The additional excluded matters are amounts for which the Contractor is liable under this contract for

· Defects due to his design which arise before the Defects Certificate is issued,
· Defects due to manufacture and fabrication outside the Site,
· loss of or damage to property (other than the works, Plant and Materials),
· death of or injury to a person and
· infringement of an intellectual property right.

	X18.5
	The end of liability date is
	(i) [10] years after the defects date for latent Defects and

(ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter.

A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility	on	the	Employer	or	the Supervisor to have discovered the Defect.




	Z
	The Additional conditions of contract
are
	

	
	
	Z1 to Z15 always apply.

	

Z1
	

Cession delegation and assignment
	

	Z1.1
	The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer.

	Z1.2
	Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry.

	
Z2
	
Joint ventures
	

	Z2.1
	If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract.

	Z2.2
	Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf.

	Z2.3
	The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing.

	
Z3
	
Change of Broad Based Black Economic Empowerment (B-BBEE) status

	Z3.1
	Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change.

	Z3.2
	The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager.

	Z3.3
	Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works.

	Z3.4
	Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93.

	
Z4
	
Confidentiality
	

	Z4.1
	The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient.

	Z4.2
	If the Contractor is uncertain about whether any such information is confidential, it is to be




	
	regarded as such until notified otherwise by the Project Manager.

	Z4.3
	In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed.

	Z4.4
	The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer.

	Z4.5
	The Contractor ensures that all his subcontractors abide by the undertakings in this clause.

	
Z5
	
Waiver and estoppel: Add to core clause 12.3:

	Z5.1
	Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing.

	
Z6
	
Health, safety and the environment: Add to core clause 27.4

	Z6.1
	The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor:
· accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site;
· warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and
· undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	Z6.2
	The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing.

	[bookmark: _Hlk137630148][bookmark: _Hlk137630219]
Z7
	
Provision of a Tax Invoice and interest. Add to core clause 51

	Z7.1
	Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate.

	Z7.2
	If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in
time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms




	
	of core clause 51.2 is then calculated from the delayed date by when payment is to be made.

	Z7.3
	The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment.

	
Z8
	
Notifying compensation events

	Z8.1
	Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”.

	
Z9
	
Employer’s limitation of liability

	Z9.1
	The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand)

	Z9.2
	The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the
Employer’s liability under the indemnity is limited.

	
Z10
	
Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it":

	Z10.1
	or had a business rescue order granted against it.

	
Z11
	
Addition to secondary Option X7 Delay damages (if applicable in this contract)

	Z11.1
	If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the
Termination Table.




	Z12
	Ethics
	

	For the purposes of this Z-clause, the following definitions apply:

	Affected Party
	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

	Coercive Action
	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

	Collusive Action
	
	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

	Committing Party
	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees,

	Corrupt Action
	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

	Fraudulent
	means any unlawfully or illegally intentional act or omission that misleads, or attempts to




	Action
	
	mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

	Obstructive Action
	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and

	Prohibited Action
	
	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

	Z12.1
	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

	Z12.2
	The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason.

	Z12.3
	If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

	Z12.4
	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

	
Z13
	
Insurance

	Z 13.1
	Replace core clause 84 with the following:




Insurance cover	84

84.1 When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force.

84.2 The Contractor provides the insurances stated in the Insurance Table A.

84.3 The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate.

INSURANCE TABLE A

	Insurance against
	Minimum amount of cover or minim limit of indemnity

	Loss of or damage to the works, Plant and Materials
	The replacement cost where not covered by the Employer’s insuranc

The Employer’s policy deductible, as Contract Date, where covered by the Employer’s insurance

	Loss of or damage to Equipment
	The replacement cost

	Liability for loss of or damage to property (except the works, Plant and
	Loss of or damage to property
Employer’s property




	Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract
	The replacement cost where not covered by the Employer’s insurance

The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance

Other property
The replacement cost

Bodily injury to or death of a person The amount required by applicable law

	Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract
	The amount required by the applicable law



Z 13.2	Replace core clause 87 with the following:
The Employer provides the insurances stated in the Insurance Table B.


INSURANCE TABLE B

	Insurance against or name of policy
	Minimum amount of cover or minimum of indemnity

	Assets All Risk
	Per the insurance policy document

	Contract Works insurance
	Per the insurance policy document

	Environmental Liability
	Per the insurance policy document

	General and Public Liability
	Per the insurance policy document

	Transportation (Marine)
	Per the insurance policy document

	Motor Fleet and Mobile Plant
	Per the insurance policy document

	Terrorism
	Per the insurance policy document

	Cyber Liability
	Per the insurance policy document

	Nuclear Material Damage and Business Interruption
	Per the insurance policy document

	Nuclear Material Damage Terrorism
	Per the insurance policy document




	Z14
	Nuclear Liability

	Z14.1
	The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS.

	Z14.2
	The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the
presence of the Contractor or that person or any property of the Contractor or such person at




	or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z14.3
	Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer.

	Z14.4
	The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter.

	Z14.5
	The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned.

	
Z15
	
Asbestos
	

	For the purposes of this Z-clause, the following definitions apply:

	AAIA
	
	means approved asbestos inspection authority.

	ACM
	
	means asbestos containing materials.

	AL
	
	means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL.

	Ambient Air
	means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet.

	Compliance Monitoring
	means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	OEL
	
	means occupational exposure limit.

	Parallel Measurements
	means measurements performed in parallel, yet separately, to existing measurements to verify validity of results.

	Safe Levels
	means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles.

	Standard
	
	means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles.

	SANAS
	
	means the South African National Accreditation System.

	TWA
	
	means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA.

	Z15.1
	The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health




	
	and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM.

	Z15.2
	Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan.

	Z15.3
	The Employer manages asbestos and ACM according to the Standard.

	Z15.4
	In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe.

	Z15.5
	The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable.

	Z15.6
	The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001.

	Z15.7
	Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation.




C1.2 Contract Data

Part two - Data provided by the Contractor.


Notes to a tendering contractor:

1. Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN)[footnoteRef:1] in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes. [1:  Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za ] 

2. The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data
3. [bookmark: Text530]Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

	Clause
	Statement
	Data

	10.1
	The Contractor is (Name):
	[bookmark: Text531]     

	
	Address
	[bookmark: Text532]     

	
	Tel No.
	[bookmark: Text533]     

	
	Fax No.
	[bookmark: Text534]     

	[bookmark: _Hlk137628982]11.2(8)
	The direct fee percentage is
	     %

	
	The subcontracted fee percentage is
	[bookmark: Text434]     %

	11.2(18)
	The working areas are the Site and
	[bookmark: Text526]     

	24.1
	The Contractor's key persons are:
	

	
	1	Name:
	[bookmark: Text527]     

	
		Job:
	     

	
		Responsibilities:
	     

	
		Qualifications:
	[bookmark: Text366]     

	
		Experience:
	[bookmark: Text367]     

	
	2	Name:
	     

	
		Job
	     

	
		Responsibilities:
	     

	
		Qualifications:
	     

	
		Experience:
	     

	
	
	[bookmark: Text529]CV's (and further key persons data including CVs) are appended to Tender Schedule entitled     .

	11.2(3)
	The completion date for the whole of the works is
	
[bookmark: Text370]     

	11.2(14)
	The following matters will be included in the Risk Register
	
Refer to risk register 

	11.2(19)
	The Works Information for the Contractor’s design is in:
	
Refer to Contract Data

	31.1
	The programme identified in the Contract Data is
	
Refer to Contract data



























PART 2: PRICING DATA
ECC3 Option B



	Document reference
	Title
	

	C2.1
	Pricing assumptions: Option B
	

	C2.2
	First forecast of total Defined Priced Contract with Bill of Quantities 
	





· C2.1 Pricing assumptions: Option B


How work is priced and assessed for payment

All Prices are to be shown excluding VAT unless instructed otherwise by the Employer in Tender Data or in an instruction the Employer has given before the tenderer enters his Prices.



[bookmark: _bookmark19]
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	Item
	 Description 
	 Unit 
	 QTY 
	 Rate 
	 Amount 
	 Specifications comments 

	 
	 
	 
	 
	 
	 
	 

	 
	 Engineering Design 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	1
	 BMH Corporate Specialist_  Pr.Eng/Pr.Tech  (Category A) 
	 Hrs 
	         2 500.00 
	 
	 
	 

	2
	 BMH Chief Mechanical Engineer Pr.Eng/Tech (Category B) 
	 Hrs 
	         1 500.00 
	 
	 
	 

	3
	 BMH Senior Mechanical Engineer (Category C) 
	 Hrs 
	         3 000.00 
	 
	 
	 

	4
	 BMH Mechanical Engineer (Category D) 
	 Hrs 
	         1 500.00 
	 
	 
	 

	5
	 BMH Senior Technologist 
	 Hrs 
	            500.00 
	 
	 
	 

	6
	 BMH Technologist 
	 Hrs 
	            200.00 
	 
	 
	 

	7
	 BMH Technician 
	 Hrs 
	            320.00 
	 
	 
	 

	8
	 BMH Land Surveyor 
	 Hrs 
	            600.00 
	 
	 
	 

	9
	 Corporate Specialist_ EC&I Pr.Eng/Tech (Category A) 
	 Hrs 
	            800.00 
	 
	 
	 

	10
	 Chief Engineer EC&I Pr.Eng/Tech (Category B) 
	 Hrs 
	            800.00 
	 
	 
	 

	11
	 Senior  Engineer EC&I (Category C) 
	 Hrs 
	            800.00 
	 
	 
	 

	12
	 EC&I Engineer (Category D) 
	 Hrs 
	            800.00 
	 
	 
	 

	13
	 EC&I Technician 
	 Hrs 
	            800.00 
	 
	 
	 

	14
	 Corporate Specialist_ Civil & Structures (Category A) 
	 Hrs 
	            500.00 
	 
	 
	 

	15
	 Chief Engineer Civil (Pr.Eng/Pr.Tech) (Category B) 
	 Hrs 
	            500.00 
	 
	 
	 

	16
	 Senior  Engineer Civil & Structures (Category C) 
	 Hrs 
	            500.00 
	 
	 
	 

	17
	 Civil & Structural Engineer (Category D) 
	 Hrs 
	            500.00 
	 
	 
	 

	18
	 Civil & Structural Senior Technologist 
	 Hrs 
	            200.00 
	 
	 
	 

	20
	 Civil Technician 
	 Hrs 
	            500.00 
	 
	 
	 

	21
	 HVAC/LPS Corporate Specialist (Pr.Eng/Pr.Tech) Category A 
	 Hrs 
	            200.00 
	 
	 
	 

	22
	 HVAC/LPS Chief Engineer (Category B) 
	 Hrs 
	            200.00 
	 
	 
	 

	23
	 HVAC/LPS Senior Engineer (Category C) 
	 Hrs 
	            200.00 
	 
	 
	 

	24
	 HVAC/LPS Engineer (Category D) 
	 Hrs 
	            200.00 
	 
	 
	 

	25
	 HVAC/LPS Technician 
	 Hrs 
	            200.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 BMH Design Software Package 
	 
	 
	 
	 
	 

	26
	 Sidewinder 9.22 (Dongle's to be provided) 
	 No 
	                2.00 
	 
	 
	 

	27
	 Sidewinder Training 
	 No 
	              16.00 
	 
	 
	 

	28
	 Sidewinder Licence Maintenance 
	 Year 
	                4.00 
	 
	 
	 

	25
	 Newton Professional 
	 No 
	                1.00 
	 
	 
	 

	26
	 Newton Training 
	 No 
	                3.00 
	 
	 
	 

	27
	 Newton Licence Maintenance 
	 Year 
	                4.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 Drawings & 3D Models 
	 
	 
	 
	 
	 

	28
	 Drawing Office Manager 
	 Hrs 
	         4 000.00 
	 
	 
	 

	29
	 Chief Draughtman 
	 Hrs 
	         5 000.00 
	 
	 
	 

	30
	 Senior Draughman 
	 Hrs 
	         5 000.00 
	 
	 
	 

	31
	 Junior Daughtman 
	 Hrs 
	         4 000.00 
	 
	 
	 

	32
	 Alignment Specialist 
	 Hrs 
	         2 000.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 Construction & Commissioning Support 
	 
	 
	 
	 
	 

	33
	 Senior BMH Project Manager 
	 Hrs 
	         5 000.00 
	 
	 
	 

	34
	 Construction Manager BMH 
	 Hrs 
	         5 000.00 
	 
	 
	 

	35
	 Commissioning Manager BMH 
	 Hrs 
	         3 000.00 
	 
	 
	 

	36
	 Project Engineering Manager BMH 
	 Hrs 
	         3 000.00 
	 
	 
	 

	37
	 Piping Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	38
	 Rigging Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	39
	 Mechanical Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	40
	 Boilermaker Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	41
	 Workshop Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	42
	 Welding Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	43
	 Civil Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	44
	 Quality Manager 
	 Hrs 
	         7 680.00 
	 
	 
	 

	45
	 Quality Technician 
	 Hrs 
	         7 680.00 
	 
	 
	 

	46
	 Quality Supervisor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	47
	 Materials Controller 
	 Hrs 
	         7 680.00 
	 
	 
	 

	49
	 Project Expeditor 
	 Hrs 
	         7 680.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	 Idlers 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	50
	Carry Idler Type 1
	Set
	            200.00 
	 
	 
	127 diameter 10° vee series 25

	51
	Return Idler Type 2
	Set
	            200.00 
	 
	 
	127 diameter 35° troughing 3 roll off-set series 25

	52
	Impact Idler Type 3
	Set
	            100.00 
	 
	 
	45° RETRACTABLE IMPACT IDLER SERIES 40 - 3 ROLL Ø159 

	53
	Transition Idler Type 4
	Set
	            100.00 
	 
	 
	25° TRANSITION IDLER SERIES 40 - 3 ROLL Ø152 

	 
	 
	 
	 
	 
	 
	 

	 
	Pulleys
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	54
	Type 1
	 Set 
	                5.00 
	 
	 
	 Drive Pulley Ø830 x 2000 F/W 

	55
	Type 2
	 Set 
	                5.00 
	 
	 
	 Head/drive Pulley Ø660 O/lagging x 2000 F/W 

	56
	Type 3
	 Set 
	                5.00 
	 
	 
	 Snub Pulley Ø424 O/LAGGING x 2000 F/W  

	57
	Type 4 
	 Set 
	                5.00 
	 
	 
	 Bend Pulley Ø654 x 2000 F/W  

	58
	Type 5
	 Set 
	                5.00 
	 
	 
	 Head/Drive Pulley Ø830 x 2300 F/W 

	59
	Type 6
	 Set 
	                2.00 
	 
	 
	 1000mm diameter/12mm ceramic/1500 F.W/2050mm B.C/SNL 3168 /SKF 23168 or similar  TAC/280mm H.D /280mm B.D / Shaft EN8-N 

	60
	Type 7
	 Set 
	                2.00 
	 
	 
	 1000mm diameter/10mm rubber/1500 F.W/2050mm B.C/SNL 3168 /SKF 231608or similar TAC/340mm H.D /320mm B.D / Shaft EN8-N 

	 
	 
	 
	 
	 
	 
	 

	 
	Scrapers
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	61
	Primary
	Set
	                8.00 
	 
	 
	E911 Primary belt scraper or similar

	62
	Secondary
	Set
	                8.00 
	 
	 
	 E255 Secondary belt scraper or similar

	63
	V-plough
	Set
	                8.00 
	 
	 
	E405 V-Plough or sumilar

	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	Drive System
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	64
	VSD Induction Motor
	 Set 
	                3.00 
	 
	 
	 Name Plate : 355kw/1485rpm (4 pole) Motor Voltage 3.3kv 

	65
	HS Coupling
	 Set 
	                3.00 
	 
	 
	 Buffer Roller Coupling : BR 276 Black Inserts (80a) 

	66
	New Gearbox
	 Set 
	                3.00 
	 
	 
	 Bevel Helical horizontal mounted, QHRG 2, Ratio 15:1 

	67
	LS Coupling
	 Set 
	                3.00 
	 
	 
	 Rigid: Flanged Coupling 

	68
	Base Plate
	 Set 
	                3.00 
	 
	 
	 Torque arm mounted base plate 

	 
	 
	 
	 
	 
	 
	 

	69
	VSD Induction Motor
	 Set 
	                2.00 
	 
	 
	 Name Plate : 630kw/1485rpm (4 pole) Motor Voltage 3.3kv 

	70
	HS Coupling
	 Set 
	                2.00 
	 
	 
	 Buffer Roller Coupling : BR 306 Yellow inserts (93a) 

	71
	New Gearbox
	 Set 
	                2.00 
	 
	 
	 Bevel Helical horizontal mounted, QHRG 2, Ratio 19:1 

	72
	LS Coupling
	 Set 
	                2.00 
	 
	 
	 Rigid: Flanged Coupling 

	73
	Base Plate
	 Set 
	                2.00 
	 
	 
	 Torque arm mounted base plate 

	 
	 
	 
	 
	 
	 
	 Holdback - BS250HS-250 mm c/w strd torque arm 

	 
	 
	 Set 
	                2.00 
	 
	 
	 

	74
	VSD Induction Motor
	 Set 
	                2.00 
	 
	 
	 Name Plate : 110kw/1485rpm (4 pole) Motor Voltage 400kv 

	75
	HS Coupling
	 Set 
	                2.00 
	 
	 
	 Buffer Roller Coupling : BR 179 Yellow inserts (93a) 

	76
	New Gearbox
	 Set 
	                2.00 
	 
	 
	 Bevel Helical horizontal mounted,Ratio 19:1 

	77
	LS Coupling
	 Set 
	                2.00 
	 
	 
	 Rigid: Flanged Coupling 

	78
	Base Plate
	 Set 
	                2.00 
	 
	 
	 Torque arm mounted base plate 

	79
	Holdback
	 Set 
	                4.00 
	 
	 
	 Holdback - BS85-85 mm c/w strd torque arm 

	 
	 
	 
	 
	 
	 
	 

	80
	Disc Brake
	 Set 
	                2.00 
	 
	 
	 Complete drive 

	 
	 
	 
	 
	 
	 
	 

	 
	Belting
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	81
	Steelcord Reinforcement Type 1
	m
	400.00
	 
	 
	2400 wide steel cord belt class 

	82
	Steelcord Reinforcement Type 2
	m
	400.00
	 
	 
	 800ST 

	83
	Splices steelcord
	No
	            250.00 
	 
	 
	1800 wide steel cord belt class 

	84
	Splices fabric plant
	No
	            250.00 
	 
	 
	 1200 ST 

	 
	 
	 
	 
	 
	 
	 

	 
	Steelwork & Concrete Works
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	85
	Conveyor Steel Support Structure - Galvanized & Fabricated as per drawings
	 tonnes 
	            100.00 
	 
	 
	 I-beams, H-Beams, handrails, idler frames 

	86
	Supply Fabricated Chute as per issued drawings (Excluding lining)
	 tonnes 
	              20.00 
	 
	 
	 Chute steel material 

	87
	VRN 400 Plates for Hoppers
	 m2 
	            250.00 
	 
	 
	 300.000X600.000MMX16.00MM VRN CUT TO SIZE (including bolts) 

	88
	Supply Ceramic Lining for Chutes as per Eskom Spec and Issued Drawings
	 m2 
	         1 500.00 
	 
	 
	 

	89
	Roof sheeting and install supply as per fabrication drawings
	 m2 
	         2 500.00 
	 
	 
	 HH Robertson Klip-Lok 700 profile 0,58 mm thick high yield stress ASTM 446 grade E (3T), heavy industrial Z 275 galvanised- Chromadek Gemsbok Sand, complete with roof ventilators and other accessories 

	90
	Site Cladding supply and install fabrication drawings
	 m2 
	         2 500.00 
	 
	 
	 HH Robertson Klip-Lok 700 profile 0,58 mm thick high yield stress ASTM 446 grade E (3T), heavy industrial Z 275 galvanised- Chromadek Gemsbok Sand.

	91
	Transluscent sheeting as per fabrication drawings
	 m2 
	            750.00 
	 
	 
	transluscent sheeting

	92
	Concrete
	m3
	         2 000.00 
	 
	 
	35Mpa /19mm

	92
	Reinforcement
	tonnes
	              60.00 
	 
	 
	Cut to size ready for installation

	 
	 
	 
	 
	 
	 
	 

	 
	Take-Up
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	93
	Electric Winch with Control Panel
	 Set 
	                5.00 
	 
	 
	 Motorised Hand Winch with Control Panel 2.2kW, 400V 

	94
	Steel Rope
	 m 
	            350.00 
	 
	 
	 26mm steel rope 

	95
	Sheaves
	 Set 
	                5.00 
	 
	 
	 438mm Root Diameter Sheaves 

	96
	Accessories
	 Set 
	                5.00 
	 
	 
	 26mm D Shackel, Clamps etc 

	97
	Take-Up Mass
	 tonnes 
	              10.00 
	 
	 
	 Counterweight mass 

	98
	Take-Up Tower Strcuture
	 tonnes 
	              10.00 
	 
	 
	 New platform structure for take-up structure 

	99
	13000 S Motorized hand winch 
	 Set 
	                5.00 
	 
	 
	 

	100
	Punchings
	 tonnes 
	                5.00 
	 
	 
	 

	101
	Guards
	 m2 
	            500.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	102
	Electric Winch with Control Panel
	 Set 
	                5.00 
	 
	 
	 Motorised Hand Winch with Control Panel 7.5kW, 400V 

	103
	Steel Rope
	 m 
	            350.00 
	 
	 
	 36mm steel rope 

	104
	Sheaves
	 Set 
	                5.00 
	 
	 
	 580mm Root Diameter Sheaves 

	105
	Accessories
	 Set 
	                5.00 
	 
	 
	 36mm D Shackel, Clamps etc 

	106
	Take-Up Mass
	 tonnes 
	              10.00 
	 
	 
	 Counterweight mass 

	107
	Take-Up Tower Strcuture
	 tonnes 
	              10.00 
	 
	 
	 New platform structure for take-up structure 

	108
	Belt Reels
	 Set 
	                4.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	 
	Electrical Control and Instrumentation
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	109
	 PVC SWA 4C 2.5 Cu BLUE STRIPE BVX04DCM 
	 m 
	            400.00 
	 
	 
	 

	110
	  PVC SWA 4C 4 Cu BLUE STRIPE BVX04ECM 
	 m 
	            800.00 
	 
	 
	 

	111
	  PVC SWA 4C 6 Cu BLUE STRIPE BVX04FCM 
	 m 
	         1 200.00 
	 
	 
	 

	112
	  PVC SWA 4C 10 Cu BLUE STRIPE BVX04GCM 
	 m 
	         2 000.00 
	 
	 
	 

	113
	  PVC SWA 4C 16 Cu BLUE STRIPE BVX04HCM 
	 m 
	         1 200.00 
	 
	 
	 

	114
	  PVC SWA 4C 25 Cu BLUE STRIPE BVX04KCM
	 m 
	         1 600.00 
	 
	 
	 

	115
	  PVC SWA 4C 35 Cu BLUE STRIPE BVX04LCM 
	 m 
	            400.00 
	 
	 
	 

	116
	  PVC SWA 4C 50 Cu BLUE STRIPE BVX04MCM 
	 m 
	            800.00 
	 
	 
	 

	117
	  PVC SWA 3C 70 Cu BLUE STRIPE BVX03NCM 
	 m 
	            400.00 
	 
	 
	 

	118
	  PVC SWA 4C 70 Cu BLUE STRIPE BVX04NCM 
	 m 
	            400.00 
	 
	 
	 

	119
	  PVC SWA 4C 95 Cu BLUE STRIPE BVX04PCM 
	 m 
	            400.00 
	 
	 
	 

	120
	  PVC SWA 3C 150 Cu BLUE STRIPE BVX03RCM
	 m 
	         3 600.00 
	 
	 
	 

	121
	Supply bulkhead light fittings on galvanized steel bracket - 100W/HPS, bracket mtd bulkhead and lamp, including accessories etc. (subject to completed electrical drawings)
	No
	500
	 
	 
	 

	122
	Supply aluminium/Copper 70mm2 x1 core BCEW earth Conductor fixed (on to cable racking) in all positions, etc., to all heights above floor level, etc. and to all areas. Including Earth bar,bonding, weld,extensible copper earth electrode etc. (will be subject to completed electrical drawings)
	m
	500
	 
	 
	 

	123
	 Supply and Installation of 5x Automated Multi-Deck Weigbridges (24m  x 3m) 
	 No 
	                5.00 
	 
	 
	 Including civil works, commissioning APNR cameras, sensors and 5x Prefabricated Control Room 

	 
	 
	 
	 
	 
	 
	 

	124
	 Supply and delivery of Civil, BMH, Electrical, C&I, LPS, Plant  as per SoW (32% x Sum of item 1 to 122 of the BoQ) 
	 Sum  
	                1.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	125
	 Installation (10% x Sum of item I to 122 of the BoQ) 
	 Sum 
	                1.00 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 

	126
	 Site establishment, accomodation, transport, food, flights (5% x Sum of item 1 to 122 of the oQ) 
	 Sum 
	                1.00 
	 
	 
	 

	 
	
	
	
	
	
	

	 
	 Total Price Excl VAT 
	 R                               -   
	




[image: ]
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